## Form
| Project Number: |  |  | GR180 | [5 empty] | Use this form if the new project has not been created in PowerPlant after requesting a new project through Cherwell
| Project Description: |  |  | Rio Grande Unit 7 Generator Rewind
| Total Project Capital Cost: |  |  | 2231459
| Reporting Date: |  |  | 2020-01-20
This form and supplemental documentation should be submitted to Financial Forecasting when requesting funds for a capital project greater than $500,000 and for an individual work order, included in a blanket project, over $500,000.
PROJECT OVERVIEW
Project Manager: |  | Chris Carroll |  |  |  | Project Manager Phone Number: |  | x2924
Owning Cost Center: |  | 5131 POWER PLANT RIO GRANDE |  |  |  | Major Project Location: |  | 19 - NM RIO GRANDE - UNIT 7
Project Functional Class: |  | Steam Production |  |  |  | Business Segment: |  | 127 RIO GRANDE - UNIT 7
Associated Projects: |  | N/A
In-Lieu of Component |  | Purchase power agreement RFP had no responses.
Project Priority |  | HIGH - Important and Urgent
Project overview/scope: |  | The Rio Grande Unit 7 will have the generator disassembled, inspected and reassembled after it is rewound with new hardware.
Business Justification: |  | This unit is needed to support local generation during summer months.
Project Risks and Constraints: |  | The greates risk to the project is threefold, Scope, schedule and budget. This is an unplanned forced outage. The full extent of all repairs will not be known until the unit is fully disassembled. There is a risk of cost increases.
Primary Reason for Expenditure |  |  | System Reliabilty & Improvement
Secondary Reason for Expenditure |  |  | Safety & Security
Has the RFP process been completed | [5 empty] | Excludes AFUDC; mandatory if RFP process complete
If yes, Bid Estimate Date: | [5 empty] | Bid Estimate: |  |  | 0
If dollars are included in a blanket project, what is the amount? | [5 empty] | Total dollars included in FERC account 183000. That amount must be included in project cost |  |  | 0
0
Estimated Start Date: |  |  | 2020-01-25 |  |  | Estimated Completion Date: |  |  | 2020-05-31
If applicable, describe and identify asset being replaced/retired
The assets being retired and replaced include the stator bars, 104 in total, a full set of stator wedges, ripple springs, ring blocking, radial rings, all tapes ties, blocks, resin, paint and miscellaneious bolting and parts needed to perform a rewind.
Please describe the potential Cost Savings and/or Cost Avoidance for this project:
The best cost avoidance at this juncture is a well managed project that maintains strict schedule and scope control to prevent avoidable delays. Cost for repair is less expensive than purchase of possibly unavailable power during peak summer months.
Describe alternatives considered:
A Purchase power agreement to replace the lost generation
What was the reason for selecting the proposed project over the alternatives considered?
There were no responses to the PPA RFP
COST/BENEFIT ANALYSIS
Select Best Alternative: |  | Alternative A
|  | 10 Year Total |  |  | 30 Year Total |  | 10 Year PV |  | 30 Year PV
COST
Capital Expenditures: |  | 2231459 |  |  | 2231459 |  | 2084988.5541 |  | 2084988.5541
O&M Expenses: |  | 0 |  |  | 0 |  | 0 |  | 0
Financing Costs (Benefit): |  | 365101.7114 |  |  | -1484873.3621 |  | 290682.6453 |  | -144726.801
Income Tax Exp (Benefit): |  | 583748 |  |  | 1548763 |  | 399823.4351 |  | 691927.8116
TOTAL COSTS |  | 3180308.7114 |  |  | 2295348.6379 |  | 2775494.6345 |  | 2632189.5647
BENEFITS
Revenue Requirement: |  | 3007366.6602 |  |  | 5174704.5883 |  | 2123485.0105 |  | 2900882.956
Cost Savings: |  | 0 |  |  | 0 |  | 0 |  | 0
Cost Avoidance: |  | 0 |  |  | 0 |  | 0 |  | 0
AFUDC: |  | 74161.6975 |  |  | 74161.6975 |  | 69293.8075 |  | 69293.8075
Other Benefits: |  | 0 |  |  | 0 |  | 0 |  | 0
TOTAL BENEFITS |  | 3081528.3577 |  |  | 5248866.2858 |  | 2192778.818 |  | 2970176.7635
BENEFIT-COST RATIO | [6 empty] | 0.79005 |  | 1.1284
Please list major milestones:
Milestone: | [7 empty] | Completed by:
Place order with GE | [7 empty] | 2020-01-25
Generator disassembly; Ship rotor off site for rings off inspection | [7 empty] | 2020-02-15
Engineering complete | [7 empty] | 2020-02-15
Material ships | [7 empty] | 2020-03-17
Stator rewind begins on site | [7 empty] | 2020-04-01
Rewind and generator reassembly complete | [7 empty] | 2020-04-30
Click here to enter a date.
Click here to enter a date.
Please list internal and external resources assigned to this project:
Resource Name: |  | Department/Company: |  |  | Have you contacted this resource about the project & related timing:
General Electric | [6 empty] | If no, explain why not:
PG Outage Group | [6 empty] | If no, explain why not:
PG Engineering | [6 empty] | If no, explain why not:
RG Management | [6 empty] | If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
If no, explain why not:
checklist for items to be submitted
Has Environmental been contacted?
If applicable, has land been secured for this project?
Have all the applicable line items on the Business Case Overview been completed?
Do the milestones you identified take into consideration availability of resources?
Cash flow projection with detail must be submitted for the project, is it enclosed?
Did you provide supporting documents for cash flows (i.e. L&R, Promod)?
Does the Total Project Cost on page 1 equal the Total Project Cost on your cash flow analysis?
If applicable, did you attach the financial analysis for each alternative?
Please provide additional information not disclosed for the committee’s consideration:
Project Manager / Preparer Signature:
Name: |  | Chris Carroll
| Date: | 2020-01-20
Approver Signature:
Name:
Date:
Please fill in the white areas with no shading.
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
No
No
No
No
No
No
No
No
No
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
Yes
No
Yes
No
No
Yes
Run Spell Check Function