## Developer Budget
ARBORETUM ESTATES / FM 148
[6 empty] | BUDGET |  |  |  | APPROVED TO DATE |  |  |  | ED ESTIMATE
|  |  | 197145 | 311145 | 78000 | 389145 |  |  | 58500 | 181058.79 | STAFF / DEVELOPER NOTES |  | 126000 | 444688.5
Parcel | Parcel Address | Property Owner | Original Appraisal Water Easement ONLY | Developer - Negotiation Maximum (App + $10,500) | Estimated Land Acquisition Fees | Developer Reimbursement Estimate Negotiation Max + Land Acq Fees | Property Owner Settlement Request | Status | Estimated Land Acquisition Fees | Developer Reimbursement Estimate Settlement + Land Acq Fees |  |  | Estimated ED Fees | Developer Reimbursement Estimate (inc. ED) Appraisal (+30%) + Acq Fees & ED Fees
58244 P-1 15182 P-2 | FM 148 | SQUEAKY LOMAS LP 6609 Sapphire Circle S Colleyville, Tx 76034 | [8 empty] | Easement document to developer 11.08.2023
24335 P-3 | 10991 NORTH FM 148 | JOHN PHILLIP BROWN & NORA FAYE 10991 N FM RD 148 Terrell, Texas 75160 | 10959 | 21459 | 6500 | 27959 | 21257.76 | Approved 11.07.2023 | 6500 | 27757.76 | 11.16.2023 - CLOSING SCHEDULED | EXECUTED EASEMENT TO DEVELOPER 11.30.2023 | 10500 | 31246.7
24336 P-4 | FM 148 | DANIEL ROBLEDO & OLGA ANDRADE 11049 N FM Rd 148 Terrell, Texas 75160 | 9950 | 20450 | 6500 | 26950 | 20027.31 | Approved by PO 11.22.2023 | 6500 | 26527.31 | 11.22.2023 - CLOSING SCHEDULED | EXECUTED EASEMENT TO DEVELOPER 11.30.2023 | 10500 | 29935
24337 P-5 | 11049 NORTH FM 148 | DANIEL ROBLEDO & OLGA ANDRADE 11049 N FM Rd 148 Terrell, Texas 75160 | 5010 | 15510 | 6500 | 22010 | 16667.75 | Approved by PO 11.22.2023 | 6500 | 23167.75 | 11.22.2023 - CLOSING SCHEDULED | EXECUTED EASEMENT TO DEVELOPER 11.30.2023 | 10500 | 23513
24338 P-6 | 11095 NORTH FM 148 | A1 B&J HOME AWAY FROM HOME, LLC 3113 Sunset Ct Mesquite, Texas 75150 | 5010 | 15510 | 6500 | 22010 | 5010 | CLOSED | 6500 | 11510 | CLOSED - Received executed easement Friday 11.17.2023 | EXECUTED EASEMENT TO DEVELOPER 11.30.2023 | 10500 | 23513
24339 P-7 | 11113 NORTH FM 148 | RICHARD ROCKWELL PO Box 34 Terrell, Texas 75160 | 5010 | 15510 | 6500 | 22010 | 5933.04 | CLOSED 11.14.2023 | 6500 | 12433.04 | 11.16.2023 - CLOSING SCHEDULED | EXECUTED EASEMENT TO DEVELOPER 11.30.2023 | 10500 | 23513
24340 P-8 | 11139 NORTH FM 148 | R.B. GREEN & MILDRED 11139 N FM RD 148 Terrell, Texas 75160 | 6210 | 16710 | 6500 | 23210 |  |  |  | 0 | Clearing title issues; property owner willing to sign easement, waiting on title confirmation |  | 10500 | 25073
15186 P-9 | 11157 FM 148 | JEFFERY L. WOOLVERTON 520 Timberside Terrell, Texas 75161 | 11393 | 21893 | 6500 | 28393 | 11393 | Meeting PO 11.28.2023 for signature | 6500 | 17893 | Property owner willing to sign, has been sick, consultant following up this week | EXECUTED EASEMENT TO DEVELOPER 11.30.2023 | 10500 | 31810.9
15189 P-10 | 11181 FM 148 | EVENCIO VALDELAMAR 11181 N FM 148 Terrell, Texas 75160 | 7650 | 18150 | 6500 | 24650 | 5933.04 | CLOSED 11.10.2023 | 6500 | 12433.04 | 11.16.2023 - CLOSING SCHEDULED CONTRACTOR - BORE PROPERTY; LOCATE SEPTIC TANK | EXECUTED EASEMENT TO DEVELOPER 11.30.2023 | 10500 | 26945
15185 P-11 | FM 148 | FM 148 TERRELL LP 3316 Grand Mesa Drice Plano, Texas 75025 | 14783 | 25283 | 6500 | 31783 | 15706.39 | CLOSED 11.09.2023 | 6500 | 22206.39 | 11.09.2023 - CLOSING SCHEDULED | EXECUTED EASEMENT TO DEVELOPER 11.30.2023 | 10500 | 36217.9
15190 P-12 | 11287 FM 148 | WILL A SR ALLEN & ROSA L PO Box 214 Terrell, Texas 75160 | 14461 | 24961 | 6500 | 31461 | 20630.5 | CLOSED 11.10.2023 | 6500 | 27130.5 | 11.16.2023 - CLOSING SCHEDULED | EXECUTED EASEMENT TO DEVELOPER 11.30.2023 | 10500 | 35799.3
15187 P-13 | 11317 NORTH FM 148 | BADYAL & SANDHU LLC 306 Ashley Sunnyvale, Texas 75182 | 11892 | 22392 | 6500 | 28892 |  |  |  |  | 01.15.2024 - Hearing schedule We had originally agreed to bore property, however we can remove that option if we move to ED - we are still hopeful we will settle this one without an official hearing. |  | 10500 | 32459.6
15184 P-14 | FM 148 | GREGORY LAMB PO Box 25106 Dallas, Texas 75225 TXDOT | 82817 | 93317 | 6500 | 99817 |  |  |  | 0 | Snapp - contact M Clark regarding TxDot access to existing encasement |  | 10500 | 124662.1