## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
GV01-16 | Meadow Lake Substation | Guadalupe | New Substation, w 30MVA PWT, distribution bays 4 circuits | 2020-03-15 | 2021-01-29 |  | 4.9 M |  | - |  | 100% | 0 | 138 | 0 | 0 | Steel/Pipe Bus | 0 | 0 | 0 | 0 |  | Complete
GV01-21 | Geronimo Substation | Guadalupe | Replace 20 MVA T1 unit with 40 MVA unit | 2021-02-01 | 2021-07-14 |  | 2.3 M |  |  |  | 100% | 138 |  | 0 | 0 | Steel | 0 | 0 | 0 | 0 |  | Complete
GV02-21 | Schumansville Substation | Guadalupe | Replace 20 MVA T2 unit with 40 MVA unit | 2021-09-01 | 2021-11-30 |  | 1.9 M |  |  |  | 100% | 138 |  | 0 | 0 | Steel | 0 | 0 | 0 | 0 |  | Complete
GV03-21 | Gonzales Interchange (LCRA) - Gonzales (GVEC) T-line and Terminals | Gonzales | Upgrade relaying at both terminals and rebuild existing 69 kV line to 138 kV line w concrete poles | 2021-04-01 | 11/31/2021 |  | 3.3 M |  |  |  | 100% | 69 | 138 | 1 | 795 drake | Concrete/Steel | 60 | 1 | 60 | 1 |  | Complete
GV04-21 | Cibolo Subtation 138 Terminal Addition and Upgrades | Guadalupe | Expand station to accommodate new T306 terminal and future T3, plus add breakers and switches to the existing station | 2021-06-02 | 2021-12-31 |  | 4.7 M |  |  |  | 85% | 138 |  | 0 | 0 | Steel/Pipe Bus | 0 | 0 | 0 | 0 |  | Substation construction in progress, Powerbank delivers Dec 2022
GV05-21 | McQueeney Substaton 138 Terminal Addition | Guadalupe | Modifications and improvements to add new T306 terminal | 2021-06-02 | 2021-11-30 |  | 2.25 M |  |  |  | 95% | 138 |  | 0 | 0 | Steel/Pipe Bus | 0 | 0 | 0 | 0 |  | Construction in progress
GV01-22 | Santa Clara Substation | Guadalupe | New Substation, w (2) 40MVA PWTs, distribution bays to feed manufacturing plant | 2022-05-01 | 2023-03-31 |  | 4.75 M |  | - |  | 13% | 138 |  | 0 | 0 | Steel/Pipe Bus | 0 | 0 | 0 | 0 |  | Construction in progress
GV02-22 | Delhi Substation | Caldwell | New Substation, w 20MVA PWT, distribution bays 4 circuits | 2022-03-15 | 2022-08-31 |  | 3.85 M |  | - |  | 59% | 69 |  | 0 | 0 | Steel/Pipe Bus | 0 | 0 | 0 | 0 |  | Construction in progress
GV03-22 | Santa Clara Tap to Santa Clara Substation | Guadalupe | New double circuit 138kV transmission line | 2022-05-09 | 11/31/2022 |  | 4.2 M |  |  |  | 20% | 0 | 138 | 3.7 | 1192 Bunting | Concrete/Steel | 0 | 0 | 80 | 3.6 |  | Construction in progress
GV04-22 | Cibolo to McQueeney 138 Ckt Addition, T306 | Guadalupe | Add New 138kV transmission line circuit to existing structures, 1192 Bunting conductor | 2022-05-09 | 11/31/2022 |  | 6.9 M |  |  |  | 5% | 0 | 138 | 10.6 | 1192 Bunting |  | 60 | 10.3 | 0 | 0 |  | Construction in progress