## LCRA TSC MCPR July 2022
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | MCPR Row Number | Project Manager
1014910 | TXDOT US 83 Relief Route Rio Grande City-La Grulla (T485) | Starr | Modify existing transmission line (T485), Rio Grande City-La Grulla, to accommodate road expansion by TXDOT. | 2018-11-09 | 2018-11-30 | 2018-11-30 |  | 266000 | 255812.56 | -3.83% | 100 | 138 | 138 | 31.66 | 3x1-795 ACSR/AW "Drake/AW" | Steel Poles | Varies | 31.6 | n/a | n/a | 25.101 (C)(5)(B) |  | 5 | Ellie Ross
1017348 | Cooks Point TL Addition (CCN) | Burleson | Construct a new 138-kV transmission line to provide a transmission point of interconnection to a new load-serving substation | 2020-07-01 | 2021-06-30 | 2021-06-30 | T-Line $ 26.5 - 34.1M; Substation $ 6.1 - 6.7M |  |  |  | 100 | 0 | 138 | 17-23 | 2x1- 795 ACSR "Drake" | TBD; Poles and/or H-Frames | 0 | 0 | Varies; 80 | 17-23 | 45838 | 6/17/19 - PUC Approved Route 12; approved route cost estimate in CCN application for transmission line $29M; substation $6.2M | 48 | Manny Garcia
1016356 | Bellville S - Glidden TL Addition (T113) (Bellville S-Glidden TL Storm Hardening - 1016355) | Austin County/Colorado | Replace 11 lattice tangent tower structures with steel pole structures to meet storm hardening requirements; the existing rating of the transmission circuit will be maintained at 110 MVA. | 2018-08-23 | 2019-09-20 | 2019-09-20 |  | 10029000 | 10232378.24 | 2.028% | 100 | 69 | 69 | 31.24 | Existing: (1)795 ACSR “Drake” New: Bellville-Str 26 (1)959 ACSS “Suwannee” and Str.27-Glidden (1)795 ACSR “Drake” | Bellville-Str.26 Concrete H-Frame and Steel DE Str. 27-Glidden Steel DE, Lattice Towers, and concrete tangents | 120 | 31.24 | 120 | 31.24 | 25.101 (C)(5)(B) |  | 49 | Thuanny Anderson
1017514 | Airline - Naval Base TL Addition (T475) (Airline TL Relocation - 1017336) | Nueces | Relocate transmission facilities on (T475) and (T476). The present 69-kV configuration at Airline Substation does not allow for one power bank to serve as a backup for the other during outage. | 2019-09-24 | 2019-09-30 | 2019-09-30 |  | 993000 |  |  | 100 | 69 | 138 | 6.39 | (1) 795kcl ACSR/AW "Drake" | Steel Monopole | Centerline; 16 | 6.39 | n/a | n/a | 25.101 (C)(5)(D) |  | 57 | Ellie Ross
1017515 | Airline - Naval Base TL Addition (T476) (Airline TL Relocation - 1017336) | Nueces | Relocate transmission facilities on (T475) and (T476). The present 69-kV configuration at Airline Substation does not allow for one power bank to serve as a backup for the other during outage. | 2019-03-28 | 2019-04-16 | 2019-04-16 |  | 331000 | 119480.24 | -63.9% | 100 | 69 | 138 | 7.98 | (1) 795 kcl ACSR/AW "Drake" | Steel Monopole | Centerline | 7.98 | n/a | n/a | 25.101 (C)(5)(D) |  | 58 | Ellie Ross
1018756 | Heines - Naval Base TL Addition (T685) (Heines Substation Addition - 1018743) | Nueces | Provide metering facilities. Provide transmission service to a load-serving substation. Provide real-time monitoring facilities at the Heines Substation. (Once Heines Substation Addition is complete, the transmission assets on (T476) will be renumbered to T685 Heines - Naval Base) | 2018-10-03 | 2020-05-07 | 2020-05-07 |  | 894000 | 717789.02 | -19.71% | 100 | 69 | 138 | 5.3 | (1) 795 kcl ACSR/AW "Drake" | Steel Monopole | Centerline | 5.3 | n/a | n/a | 25.101 (C)(5)(A) |  | 59 | Enayatullah Sharifi
1018755 | Airline - Heines TL Addition (T476) (Heines Substation Addition - 1018743) | Nueces | Provide metering facilities. Provide transmission service to a load-serving substation. Provide real-time monitoring facilities at the Heines Substation. | 2018-10-11 | 2020-05-07 | 2020-05-07 |  | 994000 | 717788.99 | -27.79% | 100 | 69 | 138 | 2.57 | (1) 795 kcl ACSR/AW "Drake" | Steel Monopole | Centerline | 2.57 | n/a | n/a | 25.101 (C)(5)(A) |  | 60 | Enayatullah Sharifi
1018663 | Rio Pecos - Horse Crossing TL Addition (T682) [Horse Cross - Rio Pecos TL Add - 1018600] | Crane | Provide transmission service to a generator. (This circuit will be added to the open position on the structures on the existing (T451) Rio Pecos - Crane, after the project is complete the transmission line will be numbered T682 Rio Pecos - Horse Crossing) | 2021-01-08 17:00 | 2021-05-28 | 2021-06-01 |  | 1871000 |  |  | 100 | 0 | 138 | 0.76 | (2) 795 ACSR Drake | Steel/Concrete Monopoles | 80; Centerline | 0.76 | n/a | n/a | 25.101 (C)(5)(C) |  | 61 | Manny Garcia
1019260 | Winchester - Salem T170 TL Addition (T170) (Winchester Autotransformer Addition - 1017413) | Fayette | Install new autotransformer capacity, add new structures Winchester Substation. | 2018-10-01 | 2020-03-25 | 2020-03-25 17:00 |  | 2287000 | 772567.15 | -66.22% | 100 | 138 | 138 | 37.28 | (1) 795 kcl ACSR/AW "Drake" | H-Frames, Steel Poles, & Lattice Towers | 100; Centerline | 37.16 | n/a | n/a | 25.101 (C)(5)(A) |  | 62 | Jack Sandel
1017777 | Winchester - Fayetteville TL Addition (T165) (Winchester Autotransformer Addition - 1017413) | Fayette | Install new autotransformer capacity, add new structures Winchester Substation. | 2018-10-01 | 2020-03-26 17:00 | 2020-03-26 17:00 |  | 2535000 | 998437.6 | -60.61% | 100 | 138 | 138 | 18.92 | (1) 795 kcl ACSR/AW "Drake" | H-Frames, Steel Poles, & Lattice Towers | 100; Centerline | 18.75 | n/a | n/a | 25.101 (C)(5)(A) |  | 63 | Jack Sandel
1019038 | Plum - La Grange TL Addition (T208) (Riverside Circuit Breaker Addition - 1018925) | Fayette | Increase the reliability of substation equipment at the Riverside Substation. | 2019-01-28 | 2020-12-30 | 2020-10-20 |  | 1873000 | 1874108.81 | 0.0592% | 100 | 138 | 138 | 8.39 | 795 ACSR. GA2 Drake. 3/8 EHS. OPGW | Wood H-frame | Undefined Centerline | 5.58 | Undefined Centerline | 5.58 | 25.101 (C)(5)(B) |  | 66 | Tyreeta Young
1016702 | Altair - Nada TL Addition (T545) (Glidden Area TL Upgrade - 1016219) | Colorado | OPGW (fiber) installation (T545) and Substation upgrade at Nada and Altair substations from 69kV to 138kV | 2018-12-03 | 2019-05-31 | 2019-05-31 |  | 7068000 |  |  | 100 | 69 | 138 | 14.12 | 795 Drake ASCR & 26/7 & Single | Steel, Wood, & Lattice | Blanket | 14.12 | Blanket | 14.1 | 25.101 (C)(5)(B) |  | 72 | Manny Garcia
1019321 | Lakeway - Marshall Ford T179 Addition (T179) (Lakeway AE Marshall Ford TL SH - 1019096) | Travis | Increase the reliability of circuit (T179) on the Lakeway (AE) – Marshall Ford 2.4 le138 kV transmission line. | 2019-01-25 | 2019-06-21 17:00 | 2019-06-21 |  | 3172000 | 2103161.03 | -33.7% | 100 | 138 | 138 | 2.4 | (6x1) 795 ACSR "Drake" | Steel Towers | 100 | 2.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 73 | Amir Toor
1019603 | Lakeway - Marshall Ford Fiber Addition (T179) (LCRA Fiber Backbone FY 19 Telecom Upgrade - 1019084) | Travis | Install 2.42 miles of 72-count OPGW from Lakeway (AE) to Marshall Ford (T179). | 2019-02-13 | 2019-06-21 08:00 | 2019-06-21 |  | 648000 | 511085.78 | -21.13% | 100 | 138 | 138 | 2.4 | (6x1) 795 ACSR "Drake" | Steel Towers | 100 | 2.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 74 | Amir Toor
1019317 | Rockport - Fulton T474 TL Addition (T474) Hurricane Response System Upgrade - 1019095 | Nueces, Aransas | Increase reliability, repair storm damage, & upgrade circuit (T477) on the N Padre Tap-Port Aransas 18.23-le 69-kV TL and circuit (T474) on the Fulton-Rockport 138-kV 7.36-le 69-kV TL. | 2019-02-07 | 2019-09-23 | 2019-09-23 |  | 3836000 | 3832641.61 | -0.08755% | 100 | 69 | 69 | 7.4 | (1x) 795 ACSR/AW Drake | Steel Monopole, Concrete Monopole | Unknown (AEP-owned) | - | - | - | 25.101 (C)(5)(B) |  | 76 | Robert Badger
1017557 | Deer Creek - Luling TL Addition (T538) (Darst Creek Circuit Breaker Addition - 1017352) | Guadalupe | Add four 138-kV, 3000A, 40kAIC circuit breakers in a ring bus configuration to Darst Creek substation | 2019-02-22 | 2019-05-23 | 2019-05-23 |  | 1104000 | 1128090.94 | 2.182% | 100 | 69 | 69 | 15.84 | Drake 795 ACSR, Single | Concrete & Steel | Blanket | 15.84 | Blanket | 15.84 | 25.101 (C)(5)(B) |  | 77 | Manny Garcia
1019133 | Rim Rock - Turtle Creek TL Addition (T270) (Rim Rock - Turtle Creek TL Storm Hardening - 1018968) | Kerr | Increase the reliability of circuit (T270) on the Rim Rock - Turtle Creek 7.6 le 138kV transmission line | 2020-09-16 | 2021-05-05 17:00 | 2021-05-05 |  | 11350000 | 11309631.69 | -0.3557% | 100 | 138 | 138 | 7.6 | (1x) 795 ACSR Drake | Steel Monopole | 60; 100 | 7.6 | 60; 100 | 7.6 | 25.101 (C)(5)(B) |  | 79 | Jacob Miller
1018599 | Bakersfield - Solstice TL Addition (CCN) | Pecos | Construct a new 345-kV transmission line to connect LCRA TSC's existing Bakersfield station and AEP Texas' Solstice Switch Station | 2020-01-07 | 2020-12-17 | 2020-12-17 | T-line $148 - $192M; Bakersfield Substation - $6M; Solstice Switch Station (AEP) - $38M |  |  |  | 100 | 0 | 345 | 130-190 | 1926.9 kcl ACSS/Cumberland (LCRA TSC) and 1590 ACSS (AEP Texas) | Double-circuit steel lattice towers | 0 | 0 | 150 | 68 - 92 | 48787 | 5/28/19 PUC Approved Route 24; approved route cost estimate in CCN application for transmission line $155.9M; LCRA TSC's Bakersfield substation $6.5M; AEP's Solstice Switch Station $38.4M | 82 | Glenn Brunson
1017897 | Culberson - Kunitz TL Addition (T271) (Culberson-Kunitz Overhaul - 1017896) | Culberson | Structure replacement upgrades to steel and concrete Poles | 2019-05-28 | 2020-06-01 | 2020-06-01 10:46 |  | 2015000 |  |  | 100 | 138 | 138 | 28.88 | Linnet; 336kcl; 0.721” | Wood | 100 | 28.88 | n/a | n/a | 25.101 (C)(5)(B) |  | 83 | Danny Hartsell
1019319 | N. Padre Tap - Port A. (T-477) (Hurricane Response System Upgrade - 1019095) | Nueces | Increase the reliability, repair storm damage, and upgrade circuit (T477) on the North Padre Tap – Port Aransas 18.23-le 69-kV transmission line and circuit (T474) on the Fulton – Rockport 138-kV 7.36-le 69-kV transmission line. | 2019-10-14 | 2019-12-20 | 2019-12-27 |  | 3748000 | 3623960.31 | -3.309% | 100 | 69 | 69 | 15 | 795 ACSS/AW Drake x1 | Steel monopole, Concrete Monopole, Hybrid Steel/Concrete | (AEP-owned) | n/a | n/a | n/a | 25.101 (C)(5)(B) |  | 89 | Robert Badger
1019337 | Elroy - Wolf Lane (T-582) (LCRA TSC FIBER BUILD OUT FY19 - 1019097) | Travis | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2019-03-18 | 2019-05-13 | 2019-05-13 |  | 2078000 | 2078325.26 | 0.01565% | 100 | 138 | 138 | 3.78 | 795 Drake ACSR GA2 | Wood H-frame, LD Steel H-frame, Steel Pole, Tower | 100 | 3.78 | n/a | n/a | 25.101 (C)(5)(B) |  | 90 | Robert Badger
1020260 | Red Creek - Amos Creek TL Addition (T424) (Amos Creek Substation Addition - 1020230) | Concho | Transmission line cut-in to provide transmission service to a generator. | 2019-09-03 | 2020-03-12 13:48 | 2020-03-12 13:48 |  | 2630000 | 2577184.06 | -2.008% | 100 | 345 | 345 | 49 | 1590 ACSR Falcon x2 | Steel Lattice tower | 100 | 49 | n/a | n/a | 25.101 (C)(5)(B) |  | 91 | Robin Mims
1019327 | Austrop - Garfield (T182) (LCRA TSC FIBER BUILD OUT FY19 - 1019097) | Travis | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2019-04-15 | 2019-11-22 | 2019-11-27 |  | 4182000 | 4182362.62 | 0.008671% | 100 | 345 | 345 | 8.33 | Bundled 795 ACSR "Drake" | Lattice Tower | 170; Centerline | 8.33 | n/a | n/a | 25.101 (C)(5)(B) |  | 92 | Robert Badger
1019374 | Marshal Ford - McNeil T161 TL Addition (T161) (Marshall Ford-McNeil TL Relocation - 1019212) | Travis | Increase transmission service reliability to the Austin Energy Hamilton Substation. | 2019-05-01 | 2019-06-12 | 2019-06-12 |  | 1893000 | 1782304.37 | -5.848% | 100 | 69 | 69 | 13.4 | 4/0 & 795 kcl ACSR | Lattice Towers & Steel Poles | 100 | 13.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 93 | Robert Badger
1021300 | Granite Mountain – Marble Fall TL Upgrade [Marble Falls Double Circuit TL Upgrade - 1020559] | Burnet | Increase the reliability of transmission facilities on the T195 Granite Mountain – Marble Falls 4.1-le 138-kV transmission line | 2019-11-01 | 2020-04-03 17:00 | 2020-04-03 17:00 |  | 4204000 | 4159209.68 | -1.065% | 100 | 138 | 138 | 4.08 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | Varies 80; 100 | 4.08 | n/a | n/a | 25.101 (C)(5)(B) |  | 95 | Tony Rhodes
1016579 | Fair Oaks Ranch - Esperanza TL Addition (T503) [Esperanza Substation Addition - 1016187] | Kendall | LCRA TSC will build a 138kV substation and cut-in T503 to provide transmission/ metering services and real-time monitoring facilities | 2019-09-06 | 2019-10-25 | 2019-10-25 |  | 1179000 | 1022923.08 | -13.24% | 100 | 138 | 138 | 8.25 | Single 795 kcl ACSR | Steel Poles | 100 | 8.11 | 80 | 8.25 | 25.101 (C)(5)(B) |  | 96 | Robin Mims
1019301 | Kendall - Comfort T243 TL Addition (T243) [BoerneCicoComfrtKendall TL Upgrade - 1019089] | Kendall | Increase capacity and reliability of the transmission facilities of the Boerne Cico – Comfort 17-le 138kV transmission circuit (T148) and the Comfort t- Kendall 1.1-le 138-kV transmission circuit (T243) | 2019-10-21 | 2020-02-03 | 2020-01-31 |  | 2658000 | 2475055.72 | -6.883% | 100 | 138 | 138 | 1.08 | Bundled 959.6 SUWANNEE ACSS/TW | Steel Single Poles/ Tower/ Steel H-frame | 100 | 1.08 | n/a | n/a | 25.101 (C)(5)(B) |  | 99 | Tyreeta Young
1019303 | BoerneCico - Comfort T148 TL Addition (T148) [BoerneCicoComfrtKendall TL Upgrade - 1019089] | Kendall | Increase capacity and reliability of the transmission facilities of the Boerne Cico – Comfort 17-le 138kV transmission circuit (T148) and the Comfort t- Kendall 1.1-le 138-kV transmission circuit (T243) | 2019-09-03 08:00 | 2020-05-11 | 2020-05-11 |  | 8237000 | 7757525.34 | -5.821% | 100 | 138 | 138 | 16.93 | Bundled 795 DRAKE ACSR | Steel Single Poles | 100 | 16.93 | n/a | n/a | 25.101 (C)(5)(B) |  | 100 | Tyreeta Young
1018934 | Fayetteville - Winchester TL Upgrade (T165) [Fayetteville-Winchester TL Upgrade - 1018933] | Fayette | Increase capacity and capability of circuit T165 on the Fayetteville – Winchester 138-kV upgrade | 2019-09-01 | 2020-03-23 17:00 | 2020-03-23 17:00 |  | 15240000 | 14476089.56 | -5.013% | 100 | 138 | 138 | 18.9 | 1433 kcl ACSS/TW Merrimack | steel monopoles | 100 | 18.9 | n/a | n/a | 25.101 (C)(5)(B) |  | 101 | Amir Toor
1019122 | Giddings - Lyle Wolz TL Addition (T155) [Lexington CB Addition - 1018914] | Lee | Add two new structures to accommodate substation expansion. Increase transmission service reliability to the Lexington Substation. | 2019-08-12 | 2019-10-01 | 2019-10-01 |  | 360000 | 398104.57 | 10.58% | 100 | 138 | 138 | 21 | 795 ASCR | steel monopoles | 100 | 21 | n/a | n/a | 25.101 (C)(5)(B) |  | 102 | Vaibhav Pitale
1017394 | Mountain Home TL Addition (CCN) | Kerr, Gillespie | Construct a new 138-kV transmission line to provide a transmission point of interconnection to a new load-serving substation | 2021-08-27 | 2022-12-27 17:00 |  | T-line $46.5 - $58.5M; Substation $7.1 - $7.5M |  |  |  | 55 | 0 | 138 | 21-29 | 795 Kcl 26/7 ACSR “Drake” | tbd; steel or concrete poles | 0 | 0 | varies; 100 | 21-29 | 49523 | 7/6/20 - PUC Approved Route Hunt 37A; approved route cost estimate in CCN application for transmission line $47M; substation $7.3M | 103 | Bradley Wallner
1019026 | Fayetteville - Glidden TL Addition (T176) [Fayette Area TL Upgrades - 1018913] | Fayette, Colorado | Increase the capacity of the Fayetteville to Glidden 138-kV transmission circuit (T176) | 2019-09-16 | 2020-05-14 | 2020-05-14 |  | 14488000 | 14495701.79 | 0.05316% | 100 | 138 | 138 | 20.02 | Single 959.6 ACSS/TW Suwannee & Single OPGW (AFL DNO-11243) Static | Steel Monopoles, Hybrid H-Frames | 100 | 20 | n/a | n/a | 25.101 (C)(5)(B) |  | 105 | Hooman Larimi
1020270 | Amos Creek - Bow Wood TL Addition (T709) [Amos Creek Substation Addition - 1020230 ] | Concho, Tom Green | Provide transmission service to a generator | 2019-09-03 | 2020-03-12 09:36 | 2020-03-12 |  | 335000 | 217547.14 | -35.06% | 100 | 138 | 138 | 49.33 | (2x) - 1590 kcl ACSR Falcon | Steel Lattice, Steel monopole | 160 | 49.33 | n/a | n/a | 25.101 (C)(5)(B) |  | 106 | Robin Mims
1019325 | McNeil - Gilleland Creek (T147) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Travis | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2020-01-20 | 2020-03-31 17:00 | 2020-03-31 17:00 |  | 1989000 | 1986726.85 | -0.1143% | 100 | 138 | 138 | 7.62 | 1433.6 ACSS/TW "MERRIMACK" / Single | Steel Monopoles & Tower | 100 | 7.62 | n/a | n/a | 25.101 (C)(5)(B) |  | 107 | Robert Badger
1019341 | Paige - Winchester TL Addition (T615) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Bastrop | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2019-09-23 | 2019-12-18 | 2020-05-14 |  | 3339000 | 3289674.58 | -1.477% | 100 | 138 | 138 | 14.85 | Bundled Linnit and Single Drake | Steel Mono Pole, Wood H-Frames, Concrete # Poles | 100 | 14.85 | n/a | n/a | 25.101 (C)(5)(B) |  | 108 | Robert Badger
1019335 | Wells Branch - Round Rock (T527) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Travis, Williamson | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment | 2019-09-16 | 2019-11-01 | 2019-11-01 |  | 1555000 | 1582277.51 | 1.754% | 100 | 138 | 138 | 5.28 | (2) 795 KCL ACSR/GA2 “DRAKE” | Steel/concrete Pole, Concrete H-Frame | 100 | 5.28 | n/a | n/a | 25.101 (C)(5)(B) |  | 109 | Robert Badger
1017767 | Sim Gideon - Winchester TL Addition (T152) [Winchester Autotransformer Additions - 1017413] | Bastrop | Install a new autotransformer capacity, add new structures Winchester Substation. | 2019-09-01 | 2020-04-27 | 2020-05-14 |  | 986000 | 1227048.24 | 24.45% | 100 | 138 | 138 | 20.74 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | Varies (75;100) | 20.74 | Varies (75;100) | 20.84 | 25.101 (C)(5)(B) |  | 110 | Jack Sandel
1017769 | Smithville - Winchester TL Addition (T175) [Winchester Autotransformer Additions - 1017413] | Bastrop | Install a new autotransformer capacity, add new structures Winchester Substation. | 2019-09-01 | 2020-04-27 | 2020-05-14 |  | 737000 | 728560.12 | -1.145% | 100 | 138 | 138 | 15.1 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | Varies (80; 100) | 15.1 | Varies (80; 100, Aerials to 180) | 14.7 | 25.101 (C)(5)(B) |  | 111 | Jack Sandel
1017771 | Winchester - Piney Creek TL Addition (T186) [Winchester Autotransformer Additions - 1017413] | Fayette | Install a new autotransformer capacity, add new structures Winchester Substation. | 2019-09-01 | 2020-03-18 17:00 | 2020-05-14 |  | 709000 | 114464.87 | -83.86% | 100 | 138 | 138 | 1.38 | Single 1433.6 54/19 ACSR/TW Merrimack/TW | Lattice Towers & Steel Poles | 100 | 1.38 | 100 | 1.59 | 25.101 (C)(5)(B) |  | 112 | Jack Sandel
1017773 | Winchester - Giddings TL Addition (T222) [Winchester Autotransformer Addition - 1017413] | Bastrop | Install new autotransformer capacity, add new structures Winchester Substation. | 2019-09-01 | 2020-03-17 | 2020-05-14 |  | 837000 | 622921.49 | -25.58% | 100 | 138 | 138 | 10.51 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | Varies 75; 100 | 10.51 | Varies 75; 100 | 10.68 | 25.101 (C)(5)(B) |  | 113 | Jack Sandel
1017775 | Paige - Winchester TL Addition (T615) [Winchester Autotransformer Additions - 1017413] | Lee | Install a new autotransformer capacity, add new structures Winchester Substation. | 2019-09-01 | 2020-04-27 | 2020-05-14 |  | 850000 | 769873.73 | -9.427% | 100 | 138 | 138 | 14.83 | Single 795 26/7 ACSR Drake | Lattice Towers & Steel Poles | 100; Centerline | 14.83 | 100; Centerline | 15.09 | 25.101 (C)(5)(B) |  | 114 | Jack Sandel
1018759 | Crane - Rio Pecos TL Addition (T451) [Castle Mountain Substation Addition - 1018744] | Upton, Crane | Cut-in T451 to a new substation, Provide transmission service (new Castle Mountain substation) for Solar Prime LLC. | 2019-09-05 | 2020-03-27 17:00 | 2020-05-14 |  | 463000 | 365015.85 | -21.16% | 100 | 138 | 138 | 0.4 | Bundled 795 ACSR Drake, Single 3/8 EHS Static & Single DNO-11243 OPGW | Steel Monopole Dead End | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B) |  | 115 | Dave Ilges
1017649 | LaGrange - FPP 138kV TL Addition (T263) [FPP 138kV - La Grange TL Overhaul - 1017648] | Fayette | Increase the reliability and capability of circuit T263 on the FPP 138kV – La Grange 7.9-le 138-kV transmission line | 2020-01-02 | 2020-05-15 | 2020-05-15 17:00 |  | 4096000 | 3786436.01 | -7.558% | 100 | 138 | 138 | 7.89 | Single 795 ACSR Drake & 2 OPGW (AFL DNO-11243) & (ALCOA 52 OPT-GW) | Steel Monopole Dead Ends, Wooden H-Frame Tangents | 100 | 7.8 | n/a | n/a | 25.101 (C)(5)(B) |  | 116 | Jacob Miller
1019333 | Round Rock - Chief Brady (T378) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Williamson | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment | 2019-11-01 | 2019-11-18 | 2019-11-18 |  | 1174000 | 1181058.42 | 0.6012% | 100 | 138 | 138 | 1.2 | (1) 795 ACSR/GA2 "Drake"; RR AF to #55B has (2) 959 ACSS/TW HS "Suwannee" | steel H-frame, steel lattice | 100; Centerline | 1.2 | n/a | n/a | 25.101 (C)(5)(B) |  | 117 | Robert Badger
1019329 | Chief Brady - Georgetown (T355) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Williamson | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment | 2019-12-16 | 2020-03-02 | 2020-03-02 |  | 2469000 | 2468756.51 | -0.009862% | 100 | 138 | 138 | 3.17 | (1) 795 ACSR/GA2 "Drake" | Steel Lattice and pole, Steel H-Frame | 100 | 3.0 | n/a | n/a | 25.101 (C)(5)(B) |  | 118 | Robert Badger
1019339 | Georgetown - Rivery (T597) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Williamson | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment | 2020-01-31 | 2020-11-30 | 2020-11-18 |  | 2591000 | 2497008.58 | -3.628% | 100 | 138 | 138 | 5.1 | (1) 795 ACSR/GA2 "Drake" | steel H-frame, concrete pole, steel pole | 50 Centerline; blanket | 5.10 | n/a | n/a | 25.101 (C)(5)(B) |  | 119 | Robert Badger
1021975 | Altair - Glidden TL Addition (T544) [Kleimann (Columbus) CB Addition - 1018910] | Upton, Crockett | Increase reliability of transmission facilities on the T544 Glidden-Altair 12.22-le 69-kV TL. | 2019-11-18 | 2020-02-10 | 2020-05-14 |  | 1365000 | 611939.49 | -55.17% | 100 | 69 | 138 | 3.33 | 795 ACSR Drake, single | Steel & Concrete monopoles | 80; Blanket | 12.41 | 80; Blanket | n/a | 25.101 (C)(5)(B) |  | 120 | David Marshall
1017538 | Goforth-Turnersville TL Addition (T272) [Crosswinds Substation Addition-1017349] | Hays | Acquire 7.5 acres and expand new LCRA TSC facilities with a three-ring bus configuration | 2020-03-10 | 2020-05-14 | 2020-05-14 |  | 1038000 | 290673.12 | -72% | 100 | 138 | 138 | 3.77 | 795 ACSR Drake, single | Lattice, Wood H-frame, Steel monopole | 100 | 6.69 | 100 | 3.77 | 25.101 (C)(5)(B) |  | 121 | Andres Villegas
1017540 | Crosswinds-Goforth TL Addition (T661) [Crosswinds Substation Addition-1017349] | Hays | Acquire 7.5 acres and expand new LCRA TSC facilities with a three-ring bus configuration | 2020-03-10 | 2020-05-14 | 2020-05-14 |  | 10000 | 85038.34 | 750.4% | 100 | 138 | 138 | 3.31 | 795 ACSR Drake, single | Wood H-frame, Steel monopole | 100 | n/a | 100 | n/a | 25.101 (C)(5)(B) |  | 123 | Andres Villegas
1014015 | Camp Wood - Leakey TL Addition (T269) [Camp Wood - Leakey TL Overhaul - 1016183] | Real | Increase the reliability of transmission facilities on the T269 Camp Wood-Leakey 17.3 le 69-kV transmission line and upgrade the line to 795 ACSR Drake conductor (111 MVA at 69-kV), 138-kV capable with an OPGW shield wire. | 2020-11-30 17:00 | 2021-06-30 | 2021-06-30 |  | 43428000 |  |  | 100 | 69 | 138 | 17.32 | Single 795 ACSR Drake | Steel & Lattice | Varies; 60 | 17.32 | n/a | n/a | 25.101 (C)(5)(B) |  | 125 | Sarah Wilson
1019114 | Zorn - Pooley Rd TL Addition (T158) [Luling-Zorn TL Overhaul - 1019113] | Guadalupe | Increase the reliability of transmission facilities on the T373 Schulenburg - Glidden 20.25- | 2020-02-03 | 2021-08-31 | 2021-05-06 |  | 7228000 |  |  | 100 | 138 | 138 | 28.02 | 795 ACSR Drake | Concrete and Steel poles | 100 | 28.02 | n/a | 28.02 | 25.101 (C)(5)(B) |  | 126 | Vaibhav Pitale
1020454 | Harris Branch - McNeil TL Relocation/Addition (T146) [Harris Branch - McNeil TL Relocation - 1020379] | Travis | Provide transmission service reliability improvements | 2020-02-20 | 2020-05-07 | 2020-05-07 |  | 1408000 | 1342128.41 | -4.678% | 100 | 138 | 138 | 6.87 | 795 ACSR Drake. | Steel Lattice Tower and Monopole | 100 | 6.87 | 100' | n/a | 25.101 (C)(5)(B) |  | 128 | Bradley Wallner
1022277 | Roma - Rio Grande City TL Addition (T465) [Escobares Substation Addition - 1022173] | Starr | Provide transmission service to a load-serving substation. Provide real-time monitoring facilities at the Escobares Substation. Provide a transmission point of interconnection. | 2020-10-19 | 2021-02-04 | 2021-02-04 |  | 2327000 | 1603861.69 | -31.08% | 100 | 138kV | 138kV | 13.7 | (1) Drake ACSR | Steel Monopoles | Varies 50; 80 | 12.7 | Varies;40-100 | 0.5 | 25.101 (C)(5)(B) |  | 129 | Glenn Brunson
1022830 | Giddings - Warda TL Addition (T137) [Gidding-Warda TL Upgrade - 1022731] | Fayette, Lee | Increase the reliability of transmission facilities on the T137 Giddings - Warda 9.66-le 69-kV transmission line by converting the line to 138-kV operation and increasing the transmission capacity. | 2020-04-01 | 2020-10-19 12:00 | 2020-10-16 |  | 12383000 |  |  | 100 | 0kv (De-energized) | 138kv | 9.66 | (1) 959.6 ACSS "Suwannee" | Steel and Concrete Monopoles | 100 | 9.66 | 100 | n/a | 25.101 (C)(5)(B) |  | 130 | Manny Garcia
1020552 | Burnet - Lampasas TL Addition (T219) [Burnet-Lampasas TL Overhaul - 1020371] | Burnet, Lampasas | Increase the reliability of transmission facilities on the T219 Burnet - Lampasas 23.4-le 138-kV transmission line. | 2020-03-15 | 2021-10-01 | 2021-05-11 |  | 19159000 |  |  | 100 | 138 | 138 | 23.3 | Single 795 ACSR Drake | Wood H-frames | Centerline | 23.3 | Centerline | n/a | 25.101 (C)(5)(B) |  | 132 | Haley Jewell
1019285 | T271 TL Addition (T271) [Pinnacle Substation Addition - 1019007] | Culberson | LCRA TSC will build a new substation (Pinnacle) adjacent to T271 to interconnect the new 186.3 MW solar generation facility. Replace transmission structures to allow for substation cut-in and upgraded conductor and OPGW. | 2020-01-29 | 2020-10-14 17:00 | 2020-10-14 17:00 |  | 10800000 |  |  | 100 | 69 | 138 | 18.1 | Single 1433 ACSS/TW Merrimack | Steel monopole | 100 | 18.1 | 100 | n/a | 25.101 (C)(5)(B) |  | 134 | Jeremy Svagdis
1017435 | Elgin SW - Gilleland Creek TL Addition (T421) [Kimbro Substation Addition - 1017433] | Travis, Williamson | Provide transmission service to generator. | 2020-04-06 17:00 | 2021-04-30 | 2021-02-26 |  | 853000 | 464064.74 | -45.6% | 100 | 138 | 138 | 12.9 | (1) per phase Merrimack ACSS | Steel Dead-end Monopole | 100 | 12.9 | NA | NA | 25.101 (C)(5)(B) |  | 135 | Vaibhav Pitale
1016698 | Glidden - Altair TL Addition (T544) [Glidden Area TL Upgrade - 1016219] | Colorado | Increase the capacity and reliability of transmission facilities on the Glidden-Altair 12.2 le 69-kV transmission line (T544) and the Altair-Nada 14.12 le 69-kV transmission line (T545). | 2021-08-19 | 2021-09-13 | 2021-09-13 |  | 858000 |  |  | 100 | 138 | 138 | 12.2 | 795 ACSR Drake | Steel & Concrete | 80 | 12.2 | 80 | 12.3 | 25.101 (C)(5)(B) |  | 136 | Manny Garcia
1016491 | Cushman - Hwy 123 TL Addition (T572) [Meadow Lake Substation Addition - 1016198] | Guadalupe | Provide transmission service along with metering and real-time monitoring facilities for GVEC's new Meadow Lake Substation. Replace structure #30 with two large angle dead end structures to route T572 into and out of the new LCRA/GVEC owned Meadow Lake. | 2020-08-17 17:00 | 2020-12-21 | 2020-12-18 |  | 658000 | 229903.56 | -65.06% | 100 | 138 | 138 | 6.48 | Single 795 ACSR Drake | Steel Monopole | 80 | 6.48 | n/a | n/a | 25.101 (C)(5)(B) |  | 137 | Robin Mims
1023677 | Asherton - Bevo TL Addition (T603) [Asherton - Bevo TL Relocation - 1022882] | Dimmit | Relocate dead-end structure #1 on the T603 Bevo to Asherton 138-kV transmission line to outside of the AEP-owned Asherton Substation. Re-route and re-ternate T603 to a new point-of-interconnection (POI) structure owned by AEP and installed by AEP outside of the Asherton Substation. | 2022-02-07 | 2022-04-01 | 2022-04-01 |  | 447000 |  |  | 100 | 138 | 138 | 8.05 | (1) 795 Drake ACSR | Steel monopoles | AEP owned | AEP owned | AEP owned | AEP owned | 25.101 (C)(5)(B) |  | 139 | Glenn Brunson
1016493 | Cushman - Meadow Lake TL Addition (T647) [Meadow Lake Substation Add - 1016198] | Guadalupe | Provide transmission service along with metering and real-time monitoring facilities for GVEC's new Meadow Lake Substation. | 2020-08-17 17:00 | 2020-12-21 | 2020-12-18 |  | 643000 | 907989.43 | 41.21% | 100 | 138 | 138 | 3.6 | Single 795 ACSR Drake | Steel monopole | 80 | 3.6 | n/a | n/a | 25.101 (C)(5)(B) |  | 140 | Robin Mims
1020445 | HiCross - Turner TL Addition (T143) [HiCross-Turner TL Storm Harden-1020386] | Travis, Hays | Increase the reliability of transmission facilities on the T143 Hi Cross - Turnersville 8.8-le 138-kV transmission line. | 2020-06-03 08:00 | 2021-04-06 | 2021-04-06 |  | 5618000 |  |  | 100 | 138 | 138 | 7.9 | bundled 795 ACSR Drake | Concrete and Steel monopoles | 100 | 7.9 | n/a | n/a | 25.101 (C)(5)(B) |  | 141 | Sarah Wilson
1022213 | Hi-Cross - Turnersville TL Addition (T143) [LCRA Fiber Backbone FY20 - 1021196] | Travis, Hays | Increase the reliability of the fiber network by replacing deteriorated OPGW and All-Dielectric Self -Supporting (ADSS) fiber to improve telecommunications system reliability. | 2020-11-09 08:00 | 2021-04-06 | 2021-04-06 |  | 1065000 | 329191.08 | -69.09% | 100 | 138 | 138 | 7.9 | bundled 795 ACSR Drake | Concrete and Steel monopoles | 100 | 7.9 | n/a | n/a | 25.101 (C)(5)(B) |  | 142 | Sarah Wilson
1019265 | Fayetteville - Bellville S TL Addition (T216) [New Bremen CB Add - 1018919] | Austin, Colorado, Fayette | Increase the reliability of transmission facilities on the T216 Fayetteville – Bellville South 28.19-les 138-kV transmission Line | 2021-05-03 17:00 | 2021-05-06 | 2021-05-06 |  | 416000 | 311675.48 | -25.08% | 100 | 138 | 138 | 0.5 | 1433.6 ACSS MERRIMACK | Steel Pole | 100 | 0.05 | n/a | n/a | 25.101 (C)(5)(B) |  | 143 | Tyreeta Young
1021775 | Twin Buttes - Brown (T551) TL Addition [Amos Creek Circuit Breaker Addition - 1021517] | Tom Green, Concho | Cut-in T551 to existing substation to provide transmission services to a generator | 2020-10-07 | 2020-11-24 | 2020-11-19 |  | 1147000 | 313189.5 | -72.69% | 100 | 345 | 345 | 88.3 | 1590 ACSR Falcon Bundled | Steel Pole | 160 | 88.3 | n/a | n/a | 25.101 (C)(5)(B) |  | 144 | Robin Mims
1023668 | Gabriel - Glasscock TL Addition (T359) [Gabriel Substation Upgrade - 1020410] | Williamson | LCRA TSC will upgrade the configuration of 138-kV from Single Bus/Single Breaker to the breaker and a half bus configuration and replace five existing CBs at Gabriel Substation. | 2021-05-19 | 2022-05-13 | 2022-05-13 |  | 361000 |  |  | 100 | 138 | 138 | 6.59 | Single 795 ACSR Drake | Steel Pole | 80 | 6.59 | n/a | n/a | 25.101 (C)(5)(B) |  | 146 | Aldo Romero
1021176 | Gabriel - Jarrell TL Addition (T224) [Gabriel Substation Upgrade - 1020410] | Williamson | Upgrade the configuration of 138-kV from Single Bus/Single Breaker to the breaker and a half bus configuration and replace five existing CBs at Gabriel Substation. | 2020-08-17 | 2022-05-13 | 2022-05-13 |  | 1083000 |  |  | 100 | 138 | 138 | 1.26 | Single 795 ACSR Drake | Steel Pole | 60 | 1.26 | n/a | n/a | 25.101 (C)(5)(B) |  | 147 | Aldo Romero
1021174 | Gabriel - Georgetown East TL Addition (T223) [Gabriel Substation Upgrade - 1020410] | Williamson | Upgrade the configuration of 138-kV from Single Bus/Single Breaker to the breaker and a half bus configuration and replace five existing CBs at Gabriel Substation. | 2020-08-17 | 2022-05-13 | 2022-05-13 |  | 1083000 |  |  | 100 | 138 | 138 | 1.26 | Single 795 ACSR Drake | Steel Pole | 60 | 1.26 | n/a | n/a | 25.101 (C)(5)(B) |  | 148 | Aldo Romero
1023667 | Gabriel - Rivery TL Addition (T457) [Gabriel Substation Upgrade - 1020410] | Williamson | Upgrade the configuration of 138-kV from Single Bus/Single Breaker to the breaker and a half bus configuration and replace five existing CBs at Gabriel Substation. | 2021-05-19 | 2022-05-13 | 2022-05-13 |  | 361000 |  |  | 100 | 138 | 138 | 2.43 | Bundled 795 ACSR Drake | Steel Pole | Varies | 2.43 | n/a | n/a | 25.101 (C)(5)(B) |  | 149 | Aldo Romero
1023966 | Fairland - Lago Vista TL Addition (T414) [Transmission Connector Shunt NORTH - FY 2020 System Upgrade - 1023813] | Burnet, Travis | Improve the reliability of transmission facilities by installing transmission connector shunts on the 12.6-le Coronado-Fairland, 5-le Lakeway-Marshall Ford and 21.4-le Fairland-Lago Vista 138-kV transmission lines. | 2020-06-23 | 2020-07-28 | 2020-07-21 17:00 |  | 668000 | 555708.51 | -16.81% | 100 | 138 | 138 | 21 | 795 Condor ACSR 795 Drake ACSR | Lattice Towers | 100 | 21 | n/a | n/a | 25.101 (C)(5)(B) |  | 150 | Jeremy Svagdis
1023967 | Coronado - Fairland TL Addition (T110) [Transmission Connector Shunt NORTH - FY 2020 System Upgrade - 1023813] | Burnet, Llano | Improve the reliability of transmission facilities by installing transmission connector shunts on the 12.6-le Coronado-Fairland, 5-le Lakeway-Marshall Ford and 21.4-le Fairland-Lago Vista 138-kV transmission lines. | 2020-06-01 | 2020-11-05 | 2020-06-12 17:00 |  | 415000 | 258375.18 | -37.74% | 100 | 138 | 138 | 12.4 | Single 795 ASCR/SD Condor and Single 795 ACSR Drake | Lattice Towers | 100 | 12.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 151 | Jeremy Svagdis
1023949 | Fayetteville - Salem TL Addition (T177) [Transmission Connector Shunt EAST - FY 2020 System Upgrade - 1023812] | Austin, Washington, Fayette | Improve the reliability of transmission facilities by installing transmission connector shunts on the 19.3-le double circuit consisting of FPP Yard #1-Salem 345-kV and Fayetteville-Salem 138-kV transmission lines. | 2020-09-14 17:00 | 2020-09-17 | 2020-09-17 |  | 246000 | 172468.22 | -29.89% | 100 | 138 | 138 | 19.32 | Single 795 ASCR/SD Condor and Single 795 ACSR Drake | Lattice Towers | Varies | 19.32 | n/a | n/a | 25.101 (C)(5)(B) |  | 152 | Jeremy Svagdis
1023948 | FPP Yard #1 - Salem TL Addition (T211) [Transmission Connector Shunt EAST - FY 2020 System Upgrade - 1023812] | Austin, Washington, Fayette | Improve the reliability of transmission facilities by installing transmission connector shunts on the 19.3-le double circuit consisting of FPP Yard #1-Salem 345-kV and Fayetteville-Salem 138-kV transmission lines. | 2020-09-14 17:00 | 2020-09-17 | 2020-09-17 |  | 459000 | 176810.12 | -61.48% | 100 | 345 | 345 | 27.43 | Single 795 ASCR/SD Condor and Single 795 ACSR Drake | Lattice Towers | Varies | 27.43 | n/a | n/a | 25.101 (C)(5)(B) |  | 153 | Jeremy Svagdis
1023901 | Lockhart - Luling TL Addition (T184) [transmission Connector Shunt SOUTH - FY 2020 System Upgrade - 1023814] | Caldwell | Improve the reliability of transmission facilities by installing transmission connector shunts on the 16.8-le Lockhart-Luling and 17.1-le Lockhart-Red Rock 138-kV transmission lines. | 2020-07-15 | 2020-08-05 | 2020-08-05 |  | 119000 | 80865.84 | -32.05% | 100 | 138 | 138 | 16.83 | Single 795 ASCR/SD Condor and Single 795 ACSR Drake | Lattice Towers, Wood H-Frames | Varies | 16.83 | n/a | n/a | 25.101 (C)(5)(B) |  | 154 | Jeremy Svagdis
1023918 | Lockhart - Red Rock TL Addition (T578) [transmission Connector Shunt SOUTH - FY 2020 System Upgrade - 1023814] | Bastrop, Caldwell | Improve the reliability of transmission facilities by installing transmission connector shunts on the 16.8-le Lockhart-Luling and 17.1-le Lockhart-Red Rock 138-kV transmission lines. | 2020-07-15 | 2020-08-06 | 2020-08-06 |  | 133000 | 78124.64 | -41.26% | 100 | 138 | 138 | 17.11 | Single 795 ASCR/SD Condor and Single 795 ACSR Drake | Lattice Towers, Wood H-Frames | Varies | 17.11 | n/a | n/a | 25.101 (C)(5)(B) |  | 155 | Jeremy Svagdis
1014165 | Goldthwaite - Lampasas TL Addition (T128) [Goldthwaite - Lampasas TL Overhaul - 1015217] | Mills, Hamilton, Lampasas | Increase the reliability of circuits T128 & T672 on the Goldthwaite - Lampasas 49.77-le 138-kV transmission line. | 2020-07-01 | 2021-05-16 | 2021-05-13 |  | 4617000 | 4570208.65 | -1.013% | 100 | 138 | 138 | 23.74 | Single 795 Drake ACSR | Steel poles, Steel & Wood Hframes | 100; Centerline | 23.74 | n/a | n/a | 25.101 (C)(5)(B) |  | 156 | Robert Badger
1021428 | Sherwood Shores - Coronado TL Addition (T635) [Coronado-Sherwood Shores TL SH - 1021211] | Burnet | Increase the reliability of circuit T635 on the Coronado – Sherwood Shores 12.2-le 138-kV transmission line | 2021-09-16 | 2022-05-11 | 2022-05-11 |  | 12145000 |  |  | 100 | 138 | 138 | 12.15 | Single 795 Drake ACSR | Steel Poles/Steel Lattice | Centerline | 12.15 | n/a | n/a | 25.101 (C)(5)(B) |  | 157 | Vicki O'Connor
1020467 | Gabriel - Rivery TL Addition (T457) [Gabriel-Rivery TL SH - 1019092] | Williamson | Increase the capacity and reliability of circuit T457 on the Gabriel – Rivery 2.4-le 138-kV transmission line | 2020-11-02 | 2021-07-30 | 2021-05-15 |  | 7622000 | 6807356.62 | -10.69% | 100 | 138 | 138 | 2.43 | Bundled 795 Drake ACSR | Steel Poles | 40;100 | 2.4 | 60; 80;120; 130;150 | 2.4 | 25.101 (C)(5)(B) |  | 158 | Tolu Odunlami
1019172 | Turtle Creek - Hunt TL Addition (T240) [Turtle Creek Substation Upgrade - 1018970] | Kerr | Increase Reliability to the Turtle Creek substation | 2020-09-09 08:00 | 2020-10-06 | 2020-10-06 17:00 |  | 519000 |  |  | 100 | 138 | 138 | 0.1 | Single 336 ACSR Linnet | Wood poles | n/a | n/a | 80 (Temporary) | 0.1 (Temporary) | 25.101 (C)(5)(B) |  | 160 | Jacob Miller
1019170 | Turtle Creek - Verde Creek TL Addition (T221) [Turtle Creek Substation Upgrade - 1018970] | Kerr | Increase Reliability to the Turtle Creek substation | 2020-09-09 08:00 | 2020-11-14 | 2020-11-16 |  | 1119000 |  |  | 100 | 138 | 138 | 0.1 | Single 336 ACSR Linnet | Wood poles | n/a | n/a | 80 (Temporary) | 0.1 (Temporary) | 25.101 (C)(5)(B) |  | 161 | Jacob Miller
1023941 | Evant - Lampasas TL Addition (T672) [Goldthwaite–Lampasas TL OH - 1015217] | Lampasas, Coryell | Increase the reliability of circuits T128 & T672 on the Goldthwaite - Lampasas 49.77-le 138-kV transmission line. | 2020-07-01 | 2021-03-15 | 2021-03-15 |  | 5412000 | 4840753.86 | -10.56% | 100 | 138 | 138 | 26.02 | Single 795 Drake ACSR | Steel poles, Steel & Wood Hframes | 100; Centerline | 26.02 | n/a | n/a | 25.101 (C)(5)(B) |  | 162 | Robert Badger
1024000 | Lakeway - Marshall Ford TL Addition (T180) [transmission Connector Shunt North-FY 2020 System Upgrade - 1023813] | Travis | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-07-27 | 2020-07-28 | 2020-07-28 |  | 57000 | 27158.84 | -52.35% | 100 | 138 | 138 | 0.27 | Single 795 Condor ACSR/SD | Lattice Towers | 100 | 0.27 | n/a | n/a | 25.101 (C)(5)(B) |  | 163 | Jeremy Svagdis
1024054 | FPP - Lytton T255 TL Repair Addition [FPP Yard 2 - Lytton Springs transmission Line Upgrade - 1024058] | Fayette | Replace damaged equipment on the T255 FPP Yard #2 – Lytton Springs transmission line and increase the reliability of the line by installing new transmission line structure components and replacing original REDWING conductor with bundled Drake conductor. | 2020-04-17 | 2020-10-23 | 2020-05-18 |  | 4024000 | 3961865.47 | -1.544% | 100 | 345 | 345 | 61.1 | Bundled 715.5 Redwing ACSR; top phase between structures #30 to #77 Bundled 795 Drake ACSR | Lattice | 100 | 61.1 | n/a | n/a | 25.101 (C)(4) |  | 164 | Jack Sandel
1020874 | Fayetteville - Frelsburg TL Addition (T176) [Frelsburg Circuit Breaker Addition 1020378] | Fayette, Colorado | Increase transmission service reliability to the Frelsburg Substation. | 2020-08-10 | 2021-03-03 | 2021-03-03 |  | 892000 | 390628.67 | -56.21% | 100 | 138 | 138 | 20.06 | (1)959.6 ACSS/TW "Suwannee" (1)AFL DNO-11243 (1)3/8" EHS Steel | Steel monopoles | 125; 75 Centerline | 20.06 | n/a | n/a | 25.101 (C)(5)(B) |  | 165 | Bradley Wallner
1019024 | Plum - Flatonia TL Addition (T133) [Fayette Area TL Upgrades - 1018913] | Fayette | Increase the capacity of the Fayetteville to Glidden 138-kV transmission circuit (T176) and the Flatonia to Plum 138-kV transmission circuit (T133). | 2020-09-08 | 2021-05-14 | 2021-05-14 |  | 10196000 |  |  | 100 | 138 | 138 | 19.63 | (1)959.6 ACSS/TW "Suwannee" (1)AFL DNO-11242 (1)3/8" EHS Steel | Single pole and H-Frame (Steel, Wood, Concrete) | 100 | 19.53 | n/a | n/a | 25.101 (C)(5)(B) |  | 166 | Hooman Larimi
1020876 | Fayetteville - Mockingbird TL Addition (T714) [Frelsburg Circuit Breaker Addition 1020378] | Fayette, Colorado | Increase transmission service reliability to the Frelsburg Substation. | 2020-08-10 | 2021-03-03 | 2021-03-03 |  | 44000 | 353764.96 | 704% | 100 | 138 | 138 | 10.2 | (1)959.6 ACSS/TW "Suwannee" (1)AFL DNO-11243 (1)3/8" EHS Steel | Steel monopoles | 75 | 10.2 | n/a | n/a | 25.101 (C)(5)(B) |  | 167 | Bradley Wallner
1020465 | Gabriel - Glasscock TL Addition (T359) [Gabriel - Glasscock TL Storm Hardening - 1019091] | Williamson | Increase the reliability and capability of circuit T359 on the Gabriel - Glasscock 6.6-le 138-kV transmission line. | 2020-10-27 | 2021-04-09 | 2021-04-07 |  | 4412000 | 3157020.4 | -28.44% | 100 | 138 | 138 | 6.59 | Single 795 ACSR Drake | Single Steel Monopoles | 80 | 6.59 | n/a | n/a | 25.101 (C)(5)(B) |  | 168 | Tolu Odunlami
1021444 | Paleface - Miller Creek TL Addition (T124) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Travis, Hays, Blanco, | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124 and replacing four structures | 2020-08-03 | 2021-08-28 | 2021-08-30 |  | 3764000 |  |  | 100 | 138 | 138 | 17 | Single 795 ACSR Drake | Single Steel Monopoles | 80 | 17 | n/a | n/a | 25.101 (C)(5)(B) |  | 169 | Robert Badger
1019263 | Bevo - Rosita Creek TL Addition (T463) [Dimmit CB Addition - 1018912] | Maverick, Dimmit | Increase the reliability of transmission facilities on the T463 Rosita Creek – Bevo 47.63-le 138-kV transmission line. | 2021-03-02 | 2021-11-30 | 2021-11-11 |  | 1539000 |  |  | 100 | 138 | 138 | 36.85 | Single 795 ACSR Drake | Steel monopoles | Centerline | 36.85 | n/a | n/a | 25.101 (C)(5)(B) |  | 170 | Tolu Odunlami
1022229 | T626 TL Addition [LCRA Fiber Backbone FY20 - 1021196] | Travis | Increase the reliability of the fiber network by replacing deteriorated OPGW and All-Dielectric Self -Supporting (ADSS) fiber to improve telecommunications system reliability. | 2021-05-25 | 2021-05-28 | 2021-05-28 |  | 580000 | 454558.76 | -21.63% | 100 | 138 | 138 | 0.92 | 795 ACSR "Drake" 3/8" EHS Steel AFL DNO-11243 AFL ADSS "AC0729C621BE1" | Steel Lattice, H-frame, poles | 100 | .92 | n/a | n/a | 25.101 (C)(5)(B) |  | 171 | Sarah Wilson
1023975 | Bergheim – Kendall TL Addition (T656) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal, Kendall | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-10-23 | 2020-12-10 | 2020-12-10 |  | 490000 | 573265.05 | 16.99% | 100 | 345 | 345 | 27.23 | Bundled 795 ACSR/SD Condor | Lattice Tower | 100 | 27.23 | n/a | n/a | 25.101 (C)(5)(B) |  | 172 | Jeremy Svagdis
1023976 | Bergheim – Hays Energy TL Addition (T389) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal, Hays | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-11-04 | 2020-12-15 | 2020-12-15 |  | 765000 | 929161.13 | 21.46% | 100 | 345 | 345 | 34.18 | Bundled 795 ACSR/SD Condor | Lattice Tower | 100 | 34.18 | n/a | n/a | 25.101 (C)(5)(B) |  | 173 | Jeremy Svagdis
1023982 | Bergheim – Fair Oaks TL Addition (T238) Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal, Kendall | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-10-07 | 2020-10-07 | 2020-10-07 |  | 59000 | 26845.69 | -54.5% | 100 | 138 | 138 | 4.08 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 4.08 | n/a | n/a | 25.101 (C)(5)(B) |  | 174 | Jeremy Svagdis
1023980 | Esperanza – Fair Oaks Ranch TL Addition (T503) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Kendall | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-10-05 | 2020-12-01 | 2020-12-01 |  | 73000 | 35407.71 | -51.5% | 100 | 138 | 138 | 4.36 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 4.36 | n/a | n/a | 25.101 (C)(5)(B) |  | 175 | Jeremy Svagdis
1023977 | Kendall – Welfare TL Addition (T584) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Kendall | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-09-23 | 2020-11-03 | 2020-11-03 |  | 100000 | 140008.18 | 40.01% | 100 | 138 | 138 | 10.16 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 10.16 | n/a | n/a | 25.101 (C)(5)(B) |  | 176 | Jeremy Svagdis
1023979 | Boerne – Esperanza TL Addition (T657) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Kendall | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-09-30 | 2020-10-02 | 2020-10-02 |  | 110000 | 86760.34 | -21.13% | 100 | 138 | 138 | 3.9 | Single 795 ACSR/SD Condor | Lattice Tower | 85 | 3.9 | n/a | n/a | 25.101 (C)(5)(B) |  | 177 | Jeremy Svagdis
1023978 | Boerne – Welfare TL Addition (T228) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Kendall | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-09-28 | 2020-09-30 | 2020-09-30 |  | 150000 | 114960.86 | -23.36% | 100 | 138 | 138 | 9.5 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 9.5 | n/a | n/a | 25.101 (C)(5)(B) |  | 178 | Jeremy Svagdis
1023986 | Highway 46 – River Oaks TL Addition (T518) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-11-04 | 2020-11-04 | 2020-11-04 |  | 100000 | 83378.58 | -16.62% | 100 | 138 | 138 | 8.64 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 8.64 | n/a | n/a | 25.101 (C)(5)(B) |  | 179 | Jeremy Svagdis
1023987 | River Oaks - Henne TL Addition (T237) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-10-21 | 2020-10-22 | 2020-10-22 |  | 78000 | 70806.65 | -9.222% | 100 | 138 | 138 | 3.79 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 3.79 | n/a | n/a | 25.101 (C)(5)(B) |  | 180 | Jeremy Svagdis
1023983 | Antler – Bergheim TL Addition (T493) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-10-09 | 2020-11-18 | 2020-11-18 |  | 123000 | 23888.32 | -80.58% | 100 | 138 | 138 | 7.18 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 7.18 | n/a | n/a | 25.101 (C)(5)(B) |  | 181 | Jeremy Svagdis
1023985 | Antler – Highway 46 TL Addition (T610) [Transmission Connector Shunt WEST- FY 2020 System Upgrade - 1023811] | Comal | Improve the reliability of transmission facilities by installing transmission connector shunts | 2020-10-19 | 2020-11-13 | 2020-11-13 |  | 132000 | 60535.57 | -54.14% | 100 | 138 | 138 | 10.4 | Single 795 ACSR/SD Condor | Lattice Tower | 100 | 10.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 182 | Jeremy Svagdis
1021481 | Brenham - Highway 36 Substation (T468) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Washington | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124, T141, T199, T232, T426, and T468. | 2020-08-06 | 2020-11-05 | 2020-11-05 |  | 895000 | 390366.03 | -56.38% | 100 | 138 | 138 | 2.3 | (1)959.6 ACSS Suwannee TW (1)3/8" EHS Steel NEW (1)AFL DNO-11243 | Steel/Concrete Single pole & H-Frame | Centerline; 75 | 2.3 | n/a | n/a | 25.101 (C)(5)(B) |  | 183 | Robert Badger
1021465 | Brenham - Salem TL Addition (T199) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Washington | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124, T141, T199, T232, T426, and T468. | 2020-09-14 | 2020-12-17 | 2020-12-17 |  | 725000 | 702153.13 | -3.151% | 100 | 138 | 138 | 3.18 | 959.6 kcmil ACSS/TW | Steel H-frame | 100 | 3.18 | n/a | n/a | 25.101 (C)(5)(B) |  | 184 | Robert Badger
1022278 | Pooley Rd - Luling TL Addition (T712) [Luling - Zorn TL Overhaul - 1019113] | Guadalupe, Caldwell | Increase the reliability of transmission facilities on T158 | 2020-08-17 08:00 | 2021-08-31 | 2021-05-06 |  | 3723000 | 3627355.88 | -2.569% | 100 | 138 | 138 | 28.02 | (1) 795 ACSR Drake | Steel & Concrete SC Monopoles | Centerline; 80-100 | 28.02 | n/a | n/a | 25.101 (C)(5)(B) |  | 187 | Vaibhav Pitale
1024067 | Sim Gideon - Bastrop TL Addition (T172) [Sim Gideon - Structure 13 TL Upgrade 1023964] | Bastrop, Travis | Increase the reliability of transmission facilities on the T171 Austrop – Sim Gideon and T172 Bastrop – Sim Gideon 2.6-mile 138-kV double-circuit transmission line by removal and replacement of Structure #4 and Structure #5. | 2020-09-21 | 2020-12-18 | 2020-12-18 |  | 568000 | 396306.12 | -30.23% | 100 | 138 | 138 | 4.15 | (1) 795 ACSR Drake | Lattice Tower | Centerline; 100-125 | 4.15 | n/a | n/a | 25.101 (C)(5)(B) |  | 188 | Aldo Romero
1024084 | Sim Gideon - Austrop TL Addition (T171) [Sim Gideon - Structure 13 TL Upgrade 1023964] | Bastrop, Travis | Increase the reliability of transmission facilities on the T171 Austrop – Sim Gideon and T172 Bastrop – Sim Gideon 2.6-mile 138-kV double-circuit transmission line by removal and replacement of Structure #4 and Structure #5. | 2020-09-21 | 2020-12-18 | 2020-12-18 |  | 572000 | 689885.57 | 20.61% | 100 | 138 | 138 | 15.61 | (1) 795 ACSR Drake | Lattice Tower | Centerline; 100-125 | 15.61 | n/a | n/a | 25.101 (C)(5)(B) |  | 189 | Aldo Romero
1023421 | Sim Gideon - Austrop T171 TL Addition (T171) [Austrop-Sim Gideon Str 7 TL SH-1024417] | Bastrop, Travis | Reduce the flood risk and potential for damage to substation equipment on T547 Altair - Eagle Lake and T171 Sim Gideon - Austrop transmission lines. | 2020-10-26 | 2020-12-18 | 2020-12-18 |  | 254000 | 203908.94 | -19.72% | 100 | 138 | 138 | 15.61 | (1) 795 ACSR Drake | Lattice Tower | Centerline; 100-125 | 15.61 | n/a | n/a | 25.101 (C)(5)(B) |  | 190 | Jack Sandel
1024055 | Lincoln T731 TL Addition (T731) [Lincoln Substation Upgrade - 1022729] | Lee | Provide transmission service/reactive power support to new load at the Lincoln Substation. LCRA TSA will construct a new 138-kV transmission line from the existing Lincoln Substation to the new point of interconnect at the Enterprise Substation. | 2020-09-23 | 2020-09-25 | 2020-09-25 |  | 1160000 | 105532.71 | -90.9% | 100 | 0 | 138 | 0.03 | 3x1 795 DRAKE ACSR | Concrete Dead-end | n/a | n/a | BBEC Owned within Sub. | BBEC Owned within Sub. | 25.101 (C)(5)(B) |  | 191 | Manny Garcia
1021973 | T723 Motorman-Upton TL Addition (T723) [Motorman Substation Addition - 1021552] | Upton, Crane | Construct a 3-breaker ring bus cut in to the existing T441 Crane East to Upton 138-kV transmission line. | 2022-02-07 | 2022-06-09 | 2022-06-29 |  | 679000 |  |  | 100 | 138 | 138 | 17.97 | 1233.6 Yukon ACSS/TW & Single | Concrete Pole | Centerline; 80 | 17.97 | Centerline; 80 | n/a | 25.101 (C)(5)(A) |  | 192 | Glenn Brunson
1023799 | T441 LCRA Crane-Motorman TL Addition (T441) [Motorman Substation Addition - 1021552] | Upton, Crane | Construct a 3-breaker ring bus cut in to the existing T441 Crane East to Upton 138-kV transmission line. | 2022-02-07 | 2022-06-09 | 2022-06-29 |  | 16000 |  |  | 100 | 138 | 138 | 12.16 | 1233.6 Yukon ACSS/TW & Single | Concrete Pole | Centerline; 80 | 30.14 | Centerline; 80 | n/a | 25.101 (C)(5)(A) |  | 193 | Glenn Brunson
1019051 | McCarty Ln-Hilltop T375-TL Addition (T375) [Ranch Road 12 CB Addition - 1018923] | Hays | Increase the reliability of transmission facilities on the T375 McCarty Lane – Hilltop 10.65-mile 138kV transmission line. | 2020-10-26 | 2021-04-02 | 2021-04-01 |  | 1117000 | 603946.44 | -45.93% | 100 | 138 | 138 | 3.96 | 927.2 Greeley | H-Frame, Steel Pole, Lattice Tower | Varies 85 - 125 | 85/125 | n/a | n/a | 25.101 (C)(5)(B) |  | 194 | Tolu Odunlami
1018763 | Crane-Rio Pecos TL Addition (T451) [Soda Lake Substation Addition - 1018745] | Crane | Provide transmission service to a generator | 2021-04-02 | 2021-05-14 | 2021-06-03 |  | 692000 | 361190 | -47.8% | 100 | 138 | 138 | 12.24 | (2) 795 kcmil ACSR "Drake" | Concrete pole, steel pole | Centerline; 80 | 12.24 | Centerline; 80 | n/a | 25.101 (C)(5)(A) |  | 195 | Scott Stacher
1020471 | Eckert - Nebo TL Addition (T126) [Eckert - Nebo TL Overhaul - 1020377] | Gillespie | Increase the reliability of circuit T126 on the Eckert- Nebo 0.7 mile 69 Kv transmission line | 2021-01-15 | 2021-04-14 | 2021-04-14 |  | 2198000 | 1783683.8 | -18.85% | 100 | 69 | 138 | 0.7 | Single 795 Drake | Steel Tangents H-Frames | 100 | 0.7 | n/a | n/a | 25.101 (C)(5)(B) |  | 198 | Robin Mims
1023831 | Wingarten TL Addition [Wingarten Substation Upgrade - 1022733] | Zavala | Increase transmission service reliability to the Wingarten Substation. Reroute the existing line tap of the La Pryor-Turtle Creek TL from its current configuration to a newly installed AEP owned box structure. | 2020-12-14 | 2020-12-18 | 2020-12-16 |  | 600000 |  |  | 100 | 69 | 138 | 0.05 | 795 kcmil ACSR (26/7), one conductor/phase | Concrete pole | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B) | work within substation | 199 | Jeremy Svagdis
1022221 | T635 TL Addition [LCRA Fiber Backbone FY20 - 1021196] | Burnet, Llano | Increase the reliability of the fiber network by replacing deteriorated OPGW and All-Dielectric Self -Supporting (ADSS) fiber to improve telecommunications system reliability. | 2021-09-16 | 2022-05-06 | 2022-05-06 |  | 821000 |  |  | 100 | 138 | 138 | 12.15 | Single 795 ACSR Drake | Steel Monopole | Centerline | 12.15 | n/a | n/a | 25.101 (C)(5)(B) |  | 200 | Vicki O'Connor
1021471 | Waller - Chappell Hill TL Addition (T232) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Washington, Waller | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124, T141, T199, T232, T426, and T468. | 2021-02-01 | 2021-05-16 | 2021-05-14 |  | 1088000 |  |  | 100 | 138 | 138 | 15.93 | Single 795 ACSR Drake | Wood H-Frame | Varies 75 -85 | 15.93 | n/a | n/a | 25.101 (C)(5)(B) |  | 201 | Robert Badger
1021477 | Miller Creek - Mountaintop TL Addition (T426) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Blanco | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124, T141, T199, T232, T426, and T468. | 2021-09-03 | 2021-10-14 | 2021-10-14 |  | 1743000 |  |  | 100 | 138 | 138 | 4.81 | (1x) 1433 ACSS/TW Merrimack | Steel Monopole | Centerline 60 - 100 | 4.81 | n/a | n/a | 25.101 (C)(5)(B) |  | 202 | Russ Chissom
1023406 | Warda-Winchester (T170) TL Addition [Warda - Winchester TL Upgrade 1023202] | Fayette | Increase the transmission capacity of T170: Warda – Winchester 138-kV transmission circuit. LCRA TSC will upgrade T170: Warda - Winchester transmission line to a minimum 105 degree F ambient temperature rating of 580 MVA at 138-kV using single 1433 Merr | 2020-11-29 12:00 | 2021-05-14 | 2021-05-14 |  | 5053000 |  |  | 100 | 138 | 138 | 4.11 | 1-1433.6 ACSS/TW/MA3 "Merrimack" | Steel Pole | 100 | 4.11 | n/a | n/a | 25.101 (C)(5)(B) |  | 203 | Tanya Noujaim
1023877 | Ft Mason-Mason TL Addition (T651) [Fort Mason Circuit Breaker - 1023806] | Mason | Provide transmission service to a generator; Upgrade 138-kV ring bus to accommodate new circuit termination | 2021-02-01 | 2021-04-30 | 2021-04-30 |  | 929000 | 587205.86 | -36.79% | 100 | 138 | 138 | .035 | 1-795 ACSR DRAKE | Steel Dead-End Pole | n/a | n/a | 100 | .018 | 25.101 (C)(5)(A) |  | 204 | Robin Mims
1023860 | Lakeway-Marshall TL Addition (T180) [Lakeway - Marshall Ford TL Upgrade - 1023808] | Travis | Increase the reliability of transmission facilities on the T180 Lakeway – Marshall Ford 0.27-mile 138-Kv transmission line by replacing the existing Condor conductor from Marshall Ford Substation structure #1A to structure #1B. | 2021-01-11 | 2021-02-04 | 2021-02-04 |  | 854000 | 589381.25 | -30.99% | 100 | 138 | 138 | 5 | Single 959 ACSS Suwannee conductor (0.27 mile from Marshall Ford Substation to Str. 1A to Str. 1B) | Steel Lattice Towers | 100 | 4.5 | n/a | n/a | 25.101 (C)(5)(B) |  | 205 | Tyreeta Young
1021459 | Wolf Lane - Wyldwood TL Addition (T141) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Bastrop | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124, T141, T199, T232, T426, and T468. | 2021-03-01 | 2021-05-16 | 2021-05-13 |  | 1980000 |  |  | 100 | 138 | 138 | 5.76 | 1 x 795 Drake ACSR | steel lattice towers, wood/steel H-frame, steel monopoles | 100 | 5.76 | n/a | n/a | 25.101 (C)(5)(B) |  | 206 | Robert Badger
1024390 | OPGW Addition (T187) 1023373 [Ferguson to Wirtz Fiber Upgrade-1023373] | Burnet, Llano | Increase the reliability of the fiber network by replacing deteriorated Optical Ground Wire (OPGW) from Ferguson to Wirtz to improve telecommunication system reliability. | 2021-02-01 | 2021-05-15 | 2021-05-07 |  | 600000 | 343842.43 | -42.69% | 100 | 138 | 138 | 9.4 | 795 Drake ACSR | Lattice Towers | 100 | 9.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 207 | Christopher Grimes
1023950 | T-187 TL Addition [Ferguson - Wirtz TL Storm Hardening - 1023805] | Burnet, Llano | Increase the reliability of transmission facilities on the T187 Ferguson – Sherwood Shores 9.3-mile 138-kV transmission line from Ferguson Substation to Wirtz Substation. | 2021-02-01 | 2021-05-15 | 2021-05-07 |  | 3575000 |  |  | 100 | 138 | 138 | 9.4 | 795 Drake ACSR | Lattice Towers | 100 | 9.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 208 | Christopher Grimes
1020882 | Ferguson - Sherwood Shores TL Addition Storm Hardening (T187) [Ferguson - Sherwood Shores TL Storm Hardening - 1020881] | Burnet, Llano | Increase the reliability of circuit T187 on the Ferguson – Sherwood Shores 3.5-mile 138-kV transmission line from Sherwood Shores Substation to the Wirtz Split. | 2021-01-06 | 2021-05-17 | 2021-05-17 |  | 6634000 |  |  | 100 | 138 | 138 | 3.4 | 795 Drake ACSR | Steel Monopoles | centerline | 3.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 209 | Christopher Grimes
1021982 | SherWShores-Wirtz Split TL Addition (T187) [LCRA Fiber Backbone FY20 - 1021196] | Burnet, Llano | Increase the reliability of the fiber network by replacing deteriorated OPGW and All-Dielectric Self -Supporting (ADSS) fiber to improve telecommunications system reliability. | 2021-04-26 | 2021-05-14 | 2021-05-14 |  | 280000 |  |  | 100 | 138 | 138 | 3.4 | 795 Drake ACSR | Steel Monopoles | centerline | 3.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 210 | Sarah Wilson
1024927 | G-T255 FPP to Lyton Springs Structure Stress Remediation Add [GA FY 21 TSC-G-T255 Str. Stress - 1024926] | Fayette | Install new dead-end assemblies that will be connected to the cage of structure 46 on the T255 FPP to Lytton Springs transmission line. New dead-end hardware will be required with new conductor for jumpers. | 2021-01-25 | 2021-04-23 | 2021-04-23 |  | 243000 |  |  | 100 | 345 | 345 | 61.08 | Top Phase: Bundled (2) 795 Drake ACSR Middle and Bottom Phases: Bundled (2) 715.5 Redwing ACSR | Tower | 100' | 61.08 | n/a | n/a | 25.101 (C)(5)(B) |  | 211 | Lindsay Mijares
1024192 | Gilleland-Silicon Hill TL Addition (T734) [Gilleland Creek Circuit Breaker Addition - 1024005] | Travis | Upgrade 138-kV bay to breaker-and-a-half to accommodate new circuit termination. | 2021-01-04 | 2022-06-30 |  |  | 389000 |  |  | 95 | 138 | 138 | .04 | 795 ACSR | Steel DE Monopole | 80' | n/a | 80' | n/a (POI) | 25.101 (C)(5)(A) |  | 212 | Aldo Romero
1023420 | Altair - Eagle Lake TL Addition (T547) Ph. II [Flood Mitigation Phase II – FY 2021 - 1023189] | Colorado | Reduce the flood risk and potential for damage to substation equipment on T547 Altair - Eagle Lake and T171 Sim Gideon - Austrop transmission lines. | 2021-02-16 | 2021-05-07 | 2021-05-07 |  | 2012000 | 1620649.61 | -19.45% | 100 | 138 | 138 | 8.4 | 795 ACSR | Steel DE 3 Pole / Steel HF | Blanket | 8.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 213 | Jack Sandel
1021422 | Redwood - McCarty TL Addition (T262) [Rattler Substation Addition - 1020484] | Hays | Provide transmission service to a load-serving substation. Provide metering facilities. Provide real-time monitoring facilities at the Substation. | 2021-03-01 | 2021-05-12 | 2021-05-12 |  | 719000 | 331639.72 | -53.87% | 100 | 138 | 138 | 2.3 | (2) Drake ACSR | steel monopoles, concrete H-frames | 50' | 2.3 | n/a | n/a | 25.101 (C)(5)(A) |  | 214 | Sarah Wilson
1020865 | Clearfork-Lockhart TL Addition (T601) [Clear Fork-Lockhart TL OH - 1020864] | Caldwell | Increase the reliability and capability of circuit T601 on the Clear Fork – Lockhart transmission line | 2021-05-17 | 2021-11-20 | 2021-09-17 |  | 4649000 |  |  | 100 | 69 | 138 | 3.04 | Existing (1)4/0 ACSR "Penguin" New (2)959.6 ACSS/TW/HS "Suwannee" | Wood/Steel H-frame, Steel Monopole | Centerline (Varies) | 3.04 | 100 | n/a | 25.101 (C)(5)(B) | ROW per Easement Enhancement FY19 System Upgrade - 1019090 | 215 | Jack Sandel
1020838 | Lampasas-Kempner TL Addition (T154) [Kempner Circuit Breaker Addition-1020381] | Lampasas | Increase transmission service reliability to the Kempner Substation and Lampasas Substation. Increase the reliability and capability of transmission facilities on the T154 Copperas Cove (PEC) - Lampasas 13.5-mile 138kV transmission line. | 2021-05-17 | 2021-09-05 | 2021-09-03 |  | 2529000 |  |  | 100 | 138 | 138 | 8.04 | (1)795kcmil ACSR/GA2 "Drake" | Wood & Steel H-frame, Tower and monopole | Centerline (varies) | 8.04 | n/a | n/a | 25.101 (C)(5)(A) | Additional landowners notified; Supplemental notice affidavit filed 4/15/21 | 216 | David Rich
1020969 | Kempner-Copperas Cove TL Addition (T721) [Kempner Circuit Breaker Addition-1020381] | Lampasas | Increase transmission service reliability to the Kempner Substation and Lampasas Substation. Increase the reliability and capability of transmission facilities on the T154 Copperas Cove (PEC) - Lampasas 13.5-mile 138kV transmission line. | 2021-05-17 | 2021-09-05 | 2021-09-03 |  | 1819000 |  |  | 100 | 138 | 138 | 5.62 | (1)795kcmil ACSR/GA2 "Drake" | Wood & Steel H-frame, Tower and monopole | Centerline (varies) | 5.62 | n/a | n/a | 25.101 (C)(5)(A) |  | 217 | David Rich
1020856 | Clearfork-Robert Brown TL Addition (T519) [Clear Fork-Robert Brown Jr TL Overhaul - 1020855] | Caldwell | Increase the reliability and capability of circuit T519 on the Clear Fork – Robert Brown Jr 8.8-mile 69-kV transmission line. | 2021-11-15 | 2022-04-19 | 2022-04-19 |  | 7550000 |  |  | 100 | 69 | 138 | 8.75 | (2)959.6kcmil ACSS/TW/HS "Suwannee" | Steel Monopole | Centerline | 8.75 | 80 | 8.75 | 25.101 (C)(5)(B) | ROW per Easement Enhancement FY19 System Upgrade - 1019090 | 218 | Manny Garcia
1025542 | F - T550 Divide-TB TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Coke, Tom Green | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 13:00 | 2021-02-21 | 2021-02-21 | 109000 | 214844 | 243663.95 | 13.41% | 100 | 345 | 345 | 30.8 | Bundled 1590 kcmil ACSR Falcon | Steel Lattice | 160 | 30.8 | n/a | n/a | 25.101 (C)(3) |  | 219 | Tony Rhodes
1025575 | F - T438 FtLncstr-FrdRnch TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Crockett, Pecos, Terrell | February 2021 winter storm emergency repair and restoration work. | 2021-02-16 12:11 | 2021-02-20 08:46 | 2021-02-20 08:46 | 5000 | 7539 |  |  | 100 | 138 | 138 | 43.45 | Bundled 795 kcmil ACSR Drake | Concrete Pole | 80 | 43.45 | n/a | n/a | 25.101 (C)(3) |  | 220 | Tony Rhodes
1025452 | F - T431 Divide-GasCrk TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Coke, Sterling | February 2021 winter storm emergency repair and restoration work. | 2021-02-12 | 2021-02-20 | 2021-02-20 | 141000 | 278626 | 178632.32 | -35.89% | 100 | 345 | 345 | 5.89 | Bundled 1590 kcmil ACSR Falcon | Steel Lattice | 160 | 5.89 | n/a | n/a | 25.101 (C)(3) |  | 221 | Tony Rhodes
1025537 | F - T440 Skywst-Sprbry TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Midland | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 01:53 | 2021-02-17 21:43 | 2021-02-17 21:43 | 24000 | 63547 | 81569.97 | 28.36% | 100 | 138 | 138 | 9.06 | Single 1233.6 kcmil ACSS/TW Yukon | Concrete Pole | Varies - 75& Blanket | 9.06 | n/a | n/a | 25.101 (C)(3) |  | 222 | Tony Rhodes
1025534 | F - T610 Antler-Hwy 46 TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Comal | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 | 2021-02-17 | 2021-03-12 | 151000 | 340625 | 218127.68 | -35.96% | 100 | 138 | 138 | 10.4 | Single 795 kcmil ACSR/TW/GA2 Condor | Steel Lattice | 100 | 10.4 | n/a | n/a | 25.101 (C)(3) |  | 223 | Tony Rhodes
1025551 | F - T391 Mac-Hockley TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Harris, Waller | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 18:09 | 2021-02-16 14:38 | 2021-02-16 14:38 | 5000 |  |  |  | 100 | 138 | 138 | 12.06 | Single 959.6 kcmil ACSS/TW Suwannee | Concrete Pole | 80 | 12.06 | n/a | n/a | 25.101 (C)(3) |  | 224 | Tony Rhodes
1025549 | F - T558 BH - Kendall TL Repair [Big Hill – Kendall Transmission Line Restoration - 1025819] | Gillespie, Kendall, Kerr, Kimble, Schleicher | February 2021 winter storm emergency repair and restoration work. | 2021-02-13 20:02 | 2021-02-26 10:26 | 2021-07-22 | 1023000 | 2004000 |  |  | 100 | 345 | 345 | 139.17 | Bundled 1926.7 kcmil ACSS/TW Cumberland | Steel Lattice | Varies | 139.17 | n/a | n/a | 25.101 (C)(3) |  | 225 | Tony Rhodes
1025544 | F - T493 Antler-Brghm TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Comal | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 11:33 | 2021-02-16 07:29 | 2021-03-09 | 118000 | 294019 | 192293.75 | -34.6% | 100 | 138 | 138 | 7.18 | Single 795 Condor ACSR/SD | Steel Lattice | 100 | 7.18 | n/a | n/a | 25.101 (C)(3) |  | 226 | Tony Rhodes
1025545 | F - T559 BH-Kendall TL Repair [Big Hill – Kendall Transmission Line Restoration - 1025819] | Gillespie, Kendall, Kerr, Kimble, Schleicher | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 10:36 | 2021-02-26 10:51 | 2021-07-22 | 1023000 | 2005000 | 2064915.99 | 2.988% | 100 | 345 | 345 | 139 | (2)1926.9 ACSS/TW "Cumberland" | Steel Lattice | 120 | 139 | n/a | n/a | 25.101 (C)(3) |  | 227 | Tony Rhodes
1025454 | F - T487 Hunt-Ingram TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Kerr | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 | 2021-02-17 | 2021-05-10 | 64000 | 295133 | 273946.25 | -7.179% | 100 | 138 | 138 | 6.39 | (1)336.4 ACSR "Linnet" | Steel Lattice | 60 Centerline | 6.39 | n/a | n/a | 25.101 (C)(3) |  | 228 | Tony Rhodes
1025450 | F - T448 Gillspie-HSBay TL Repair [Gillespie - Horseshoe Bay Transmission Line Restoration and Upgrade - 1025920] | Gillespie, Llano | February 2021 winter storm emergency repair and restoration work. | 2021-02-17 | 2021-08-18 | 2021-02-19 | 174000 | 1118000 |  |  | 100 | 138 | 138 | 36.42 | (1)795 ACSR "Drake" | Steel Lattice | 75 Centerline | 36.42 | n/a | n/a | 25.101 (C)(3) | Additional TL repair work ongoing | 229 | Jeremy Svagdis
1025558 | F - T110 Coronado-Flnd TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Burnet, Llano | February 2021 winter storm emergency repair and restoration work. | 2021-02-11 22:49 | 2021-02-12 15:20 | 2021-02-12 15:20 | 11000 |  |  |  | 100 | 138 | 138 | 12.5 | (1)795 ACSR "Drake" | Steel Lattice | 100 Centerline | 12.5 | n/a | n/a | 25.101 (C)(3) |  | 230 | Tony Rhodes
1025576 | F - T221 TrtlCrk-VrdeCrk TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Kerr | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 03:14 | 2021-02-17 14:33 | 2021-04-15 | 11000 | 22062 | 22860.65 | 3.62% | 100 | 138 | 138 | 10.34 | (1)336.4 ACSR "Linnet" | Wood Pole | 80 M&B, 100, Centerline | 10.34 | n/a | n/a | 25.101 (C)(3) |  | 231 | Tony Rhodes
1025449 | F - T192 Ferg-Gillspie TL Repair [Gillespie - Horseshoe Bay Transmission Line Restoration and Upgrade - 1025920] | Gillespie, Llano | February 2021 winter storm emergency repair and restoration work. | 2021-02-17 | 2021-08-18 | 2021-02-19 | 165000 | 1090000 | 2054950.12 | 2.542% | 100 | 138 | 138 | 39.18 | (1)795 ACSR "Drake" | Steel Lattice | 30,M&B, Centerline | 39.18 | n/a | n/a | 25.101 (C)(3) | Additional TL repair work ongoing | 232 | Jeremy Svagdis
1025547 | F - T389 Berghm-Hays E TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Comal, Hays | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 11:33 | 2021-02-17 15:16 | 2021-03-12 | 94000 | 355760 | 183336.31 | -48.47% | 100 | 345 | 345 | 33.92 | 795 CONDOR ACSR/SD (BUNDLED) 1433.6 MERRIMACK ACSS/TW (BUNDLED) | Steel Lattice | 170 Centerline 100' M & B | 33.92 | n/a | n/a | 25.101 (C)(3) |  | 233 | Tony Rhodes
1025557 | F - T422 Divide to TB TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Coke, Tom Green | February 2021 winter storm emergency repair and restoration work. | 2021-02-11 06:11 | 2021-02-22 10:07 | 2021-02-22 10:07 | 216000 | 392117 | 246119.83 | -37.23% | 100 | 345 | 345 | 30.86 | 1590 FALCON ACSR (BUNDLED) | Steel Lattice | 160 Centerline | 30.86 | n/a | n/a | 25.101 (C)(3) |  | 234 | Tony Rhodes
1025453 | F - T564 Big Hill-TB TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Schleicher, Tom Green | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 | 2021-02-20 | 2021-04-04 | 565000 | 2315966 | 2199752.76 | -5.018% | 100 | 345 | 345 | 37.89 | 1926.9 CUMBERLAND ACSS/TW (BUNDLED) | Steel Pole | 140-160 | 37.89 | n/a | n/a | 25.101 (C)(3) |  | 235 | Tony Rhodes
1025550 | F - T148 BC-Comfort TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Kendall | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 16:26 | 2021-02-20 12:55 | 2021-04-28 | 285000 | 642717 | 456688.23 | -28.94% | 100 | 138 | 138 | 16.93 | 795 DRAKE ACSR (BUNDLED) | Steel Pole | 75-140 Centerline Blanket | 16.93 | n/a | n/a | 25.101 (C)(3) |  | 236 | Tony Rhodes
1025568 | F - T266 Gillspie-Nimtz TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Gillespie | February 2021 winter storm emergency repair and restoration work. | 2021-02-17 00:52 | 2021-02-17 16:00 | 2021-05-14 | 42000 | 203128 | 303986.08 | 49.65% | 100 | 138 | 138 | 2.92 | 795 DRAKE ACSR (SINGLE) | Steel Lattice | Varies | 2.92 | n/a | n/a | 25.101 (C)(3) |  | 237 | Tony Rhodes
1025559 | F - T548 EagleLk-El Cmp TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Colorado | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 23:42 | 2021-02-15 15:04 | 2021-02-15 15:04 | 44000 | 47597 | 122742.82 | 157.9% | 100 | 69 | 69 | 38.176 | 795 ARBUTUS AAC (SINGLE) 795 DRAKE ACSR (SINGLE) 4/0 PENGUIN ACSR (SINGLE) 336.4 LINNET ACSR (SINGLE) 1/0 RAVEN ACSR (SINGLE) | Wood H-Frame | Blanket CL | 38.18 | n/a | n/a | 25.101 (C)(3) |  | 238 | Tony Rhodes
1025540 | F - T342 Kendall-MtnTop TL Repair [Kendall – Mountain Top Fiber Restoration and Upgrade - 1025820] | Blanco, Gillespie, Kendall | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 16:40 | 2021-02-26 | 2021-06-08 | 418000 |  |  |  | 100 | 138 | 138 | 35.27 | Single 1433.6 Merrimack ACSS/TW | Steel monopole | 60, 100 | 35.27 | n/a | n/a | 25.101 (C)(3) |  | 239 | Sarah Wilson
1025535 | F - T288 Hrpr-LvOak TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Gillespie | February 2021 winter storm emergency repair and restoration work. | 2021-02-13 | 2021-02-17 | 2021-02-17 | 117000 | 119378 | 122186.72 | 2.353% | 100 | 69 | 69 | 21.67 | (1)2/0 ACSR "Quail"/ (1)1/0 ACSR "Raven" | Wood pole | 40 | 21.66 | n/a | n/a | 25.101 (C)(3) |  | 240 | Tony Rhodes
1025447 | F - T130 Gillspie-SndStne TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Gillespie, Llano | February 2021 winter storm emergency repair and restoration work. | 2021-02-19 | 2021-02-19 | 2021-02-19 | 127000 | 140329.79 | 256563.76 | 82.83% | 100 | 69 | 69 | 36.22 | ACSR (12/7) Cochin/ACSR (26/7) Linnet/ACSR (26/7) Drake 4/0 ACSR (6/1) Penguin | Wood H-Frames | 100 | 36.22 | n/a | n/a | 25.101 (C)(3) |  | 241 | Tony Rhodes
1025536 | F - T508 Doss - Harper TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Gillespie | February 2021 winter storm emergency repair and restoration work. | 2021-02-12 | 2021-02-17 | 2021-02-17 | 196000 | 207161 | 203845.73 | -1.6% | 100 | 69 | 69 | 14.09 | (1)4/0 ACSR "Penguin" | Wood Pole | Centerline | 14.09 | n/a | n/a | 25.101 (C)(3) |  | 242 | Tony Rhodes
1025533 | F - T255 FPP-Lytt Sprgs TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Bastrop, Caldwell, Fayette | February 2021 winter storm emergency repair and restoration work. | 2021-02-14 | 2021-02-17 | 2021-02-17 | 203000 | 203000 | 251422.12 | 23.85% | 100 | 345 | 345 | 61.12 | Double Bundle 715.5 ACSR 30/19 Redwing | Steel Lattice | 100 | 61.12 | n/a | n/a | 25.101 (C)(3) |  | 243 | Tony Rhodes
1025448 | F - T214 FtMason-Gillspie TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Gillespie, Mason | February 2021 winter storm emergency repair and restoration work. | 2021-02-17 | 2021-02-25 | 2021-02-25 | 414000 | 876218 | 945885.26 | 7.951% | 100 | 138 | 138 | 12.86 | Single 795 MCM ACSR (26/7) Drake | Wood H-Frames | 75, 100 | 12.86 | n/a | n/a | 25.101 (C)(3) |  | 244 | Tony Rhodes
1025621 | F-T151 Sim Gideon-Paige TL Repair [Winter Storm - FY 2021 System Restoration - 1025756] | Bastrop | February 2021 winter storm emergency repair and restoration work. | 2021-04-24 | 2021-04-24 | 2021-04-24 | 15864.43 | 15864 |  |  | 100 | 138 | 138 | 9.77 | (1) 795 Drake ACSR | Wood H-Frame, Lattice Tower, Steel Pole | Varies | 9.77 | n/a | n/a | 25.101 (C)(3) |  | 244.25 | Tony Rhodes
1023652 | Hilltop-RR 12 TL Addition (T375) [Hilltop - Ranch Road 12 TL Upgrade - 1023190] | Hays | Increase the reliability of transmission facilities on the T375: Hilltop – Ranch Road 12 3.95-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. | 2021-09-20 | 2022-06-30 |  |  | 9300000 |  |  | 94 | 138 | 138 | 3.97 | 3x1 ~ 1433.6 ACSS/TW "Merrimack" | Steel Poles | Varies | 3.97 | n/a | n/a | 25.101 (C)(5)(B) |  | 245 | Jeff Baranzyk
1023723 | T699 McCarty Lane-RR 12 TL Addition [McCarty Lane - Ranch Road 12 TL Upgrade - 1023196] | Hays | Increase the reliability of transmission facilities on the T699 McCarty Lane – Ranch Road 12 6.7-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. | 2021-08-23 | 2022-06-28 | 2022-02-08 |  | 9710000 |  |  | 100 | 138 | 138 | 6.67 | 3x1 ~ 1433.6 ACSS/TW "Merrimack" | Steel Poles | Varies,100 | 6.67 | n/a | n/a | 25.101 (C)(5)(B) |  | 246 | Jeff Baranzyk
1024076 | T233 TL Addition [McCarty Lane-RR 12 TL Upgrade - 1023196] | Hays, Comal | Increase the reliability of transmission facilities on the T699 McCarty Lane – Ranch Road 12 6.7-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. | 2021-08-23 | 2022-06-28 | 2022-02-08 |  | 827000 |  |  | 100 | 138 | 138 | 6.56 | 3x1 ~ 959.6 ACSS/TW "Suwannee" | Steel Poles | Varies | 6.56 | n/a | n/a | 25.101 (C)(5)(B) |  | 247 | Jeff Baranzyk
1023795 | T262 TL Addition [McCarty Lane-RR 12 TL Upgrade - 1023196] | Hays | Increase the reliability of transmission facilities on the T699 McCarty Lane – Ranch Road 12 6.7-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. | 2021-08-23 | 2022-06-28 | 2022-01-07 |  | 976000 |  |  | 100 | 138 | 138 | 2.3 | 3x2 ~ 959.6 ACSS/TW "Suwannee" | Steel Poles | Varies | 2.3 | n/a | n/a | 25.101 (C)(5)(B) |  | 248 | Jeff Baranzyk
1024074 | T324 TL Addition [McCarty Lane-RR 12 TL Upgrade - 1023196] | Hays | Increase the reliability of transmission facilities on the T699 McCarty Lane – Ranch Road 12 6.7-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. | 2021-08-23 | 2022-06-28 | 2022-01-07 |  | 815000 |  |  | 100 | 138 | 138 | 0.1 | 2x3 ~ 795 ACSR "Drake" | Steel Pole | Varies | 0.1 | n/a | n/a | 25.101 (C)(5)(B) |  | 249 | Jeff Baranzyk
1024151 | Coronado-Fairland TL Addition (T110) [Coronado - Fairland TL Upgrade - 1023802] | Coronado | Increase the reliability of transmission facilities on the T110 Coronado – Fairland conductor by replacing 12.4 mile 138-kV transmission line of existing Condor conductor and 25 structures. | 2021-08-30 | 2022-03-11 | 2022-03-11 |  | 6492000 |  |  | 100 | 138 | 138 | 12.4 | Single 795 ACSR Drake | Lattice Towers and Steel Monopoles | 100 Centerline | 12.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 250 | Hooman Larimi
1020859 | Red Rock-Tahitian T153 TL Addition (T153) [Red Rock-Tahitian TL Upg - 1020858] | Bastrop | Increase the reliability of transmission facilities on the T153 Red Rock – Tahitian Village 12.6-mile 138-kV transmission line. | 2021-09-16 | 2022-03-31 | 2022-03-31 |  | 12818000 |  |  | 100 | 138 | 138 | 12.67 | (1)959.6 ACSS/TW/HS "Suwannee" (1) 995.0 kcmil Type 13 ACCS/TW/C7-TP (1)AFL DNO-11243 OPGW | Steel Monopole | 100 | 12.67 | n/a | n/a | 25.101 (C)(5)(B) |  | 251 | Kandus Macmillan
1020868 | TurtleCreek-VerdeCreek TL Addition (T221) [Turtle Crk-Verde Crk TL OH-1020867] | Kerr | Increase the reliability of transmission facilities on the T221 Turtle Creek – Verde Creek 10.3-mile 138-kV transmission line. | 2021-08-01 | 2022-03-18 | 2022-03-26 |  | 8851000 |  |  | 100 | 138 | 138 | 10.26 | Single 795 ACSR "Drake" & DNO-11243 OPGW & 3/8 EHS Static Wire | Steel Monopoles | 100, Meets & Bounds | 10.26 | n/a | n/a | 25.101 (C)(5)(B) |  | 252 | David Rich
1024946 | Plum-Muldoon TL Addition (T133) [Muldoon Substation Addition - 1024679] | Fayette | New three breaker ring bus substation to provide a 138-kV line termination for a 240 MW solar generation facility. | 2022-11-18 | 2023-03-10 |  |  | 6400000 |  |  | 0 | 138 | 138 | 11.07 | (1) 959.6 ACSS/TW "Suwannee" (1) DNO-11243 (1) 3/8" EHS & (1) 3/8" HS | Steel poles, H-frames, Lattice tower | 100 | 19.64 | n/a | n/a | 25.101 (C)(5)(A) |  | 253 | Bradley Wallner
1019041 | Schulenberg - Glidden TL Addition (T373) [Weimar Circuit Breaker Addition - 1018928] | Colorado | Increase transmission service reliability to the Weimar Substation. Increase the reliability of transmission facilities on the T373 Schulenburg - Glidden 20.25- mile 138-kV transmission line. | 2021-08-30 | 2022-03-25 | 2022-03-25 |  | 535000 |  |  | 100 | 138 | 138 | 12.88 | (1) 795 ACSR/GA2 “DRAKE” | Steel poles, H-frames, Lattice tower | Blanket | 12.88 | n/a | n/a | 25.101 (C)(5)(B) |  | 254 | Tyreeta Young
1021249 | Coronado - Graphite Mine TL Addition (T109) [Graphite Mine CB Addition - 1020373] | Burnet, Lampasas | Increase transmission service reliability to the Graphite Mine Substation. | 2021-07-05 | 2021-11-04 | 2021-11-03 |  | 3639000 |  |  | 100 | 138 | 138 | 5.61 | Single 795 ACSR Drake & DNO-11243 OPGW & 3/8 EHS Static Wire | Steel Monopole, Concrete Monopole | 100 | 5.61 | n/a | n/a | 25.101 (C)(5)(A) |  | 255 | David Rich
1021355 | Lampasas - Graphite Mine TL Addition (T715) [Graphite Mine CB Addition - 1020373] | Burnet, Lampasas | Increase transmission service reliability to the Graphite Mine Substation. | 2021-08-02 | 2021-11-04 | 2021-11-03 |  | 780000 |  |  | 100 | 138 | 138 | 21.93 | Single 795 ACSR Drake & DNO-11243 OPGW & 3/8 EHS Static Wire | Steel Monopole, Concrete Monopole, Lattice Tower | 100 & Centerline | 21.93 | n/a | n/a | 25.101 (C)(5)(A) |  | 256 | David Rich
1020123 | Magnolia Mercer-Luling TL Addition (T701) [Magnolia Mercer CB Addition - 1018915] | Caldwell | Increase the reliability of substation equipment at the Magnolia Mercer Substation | 2021-10-01 | 2022-04-21 | 2022-04-21 |  | 186000 |  |  | 100 | 69 | 138 | 15.83 | (1) 795 ACSR /GA2 "Drake" Conductor (1) DNO-11243 Shield Wire | Wood H-frames, Tower | Centerline | 15.83 | n/a | n/a | 25.101 (C)(5)(B) |  | 257 | Manny Garcia
1019178 | Luling-Mercer TL Addition (T157) [Magnolia Mercer CB Addition - 1018915] | Caldwell | Increase the reliability of substation equipment at the Magnolia Mercer Substation | 2021-10-01 | 2022-04-21 | 2022-04-21 |  | 557000 |  |  | 100 | 69 | 69 | 15.83 | (1) 336 ACSR "Linnet" Conductor (1) 4/0 ACSR "Penguin" Shield Wire | Tower | Centerline | 15.83 | n/a | n/a | 25.101 (C)(5)(B) |  | 258 | Manny Garcia
1019331 | Schulenburg-Glidden TL Addition (T373) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Fayette, Colorado | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2021-11-03 | 2022-03-25 | 2022-03-25 |  | 6500000 |  |  | 100 | 138 | 138 | 7.57 | (1) 795 ACSR "Drake" (1) DNO-11243 (1) 3/8" EHS STEEL | Steel, Concrete, and Hybrid Monopoles | Blanket; 20 | 7.57 | n/a | 7.57 | 25.101 (C)(5)(B) |  | 259 | Russ Chissom
1023940 | Weimar-Glidden TL Addition(T704) [LCRA TSC Fiber Build Out FY19 - 1019097] | Colorado | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2022-09-15 | 2023-03-02 |  |  | 8646000 |  |  | 0 | 138 | 138 | 12.86 | (1) 795 ACSR "Drake" (1) DNO-11243 (1) 3/8" EHS STEEL | Steel, Concrete, and Hybrid Monopoles | Blanket; 20 | 12.86 | n/a | 12.86 | 25.101 (C)(5)(B) |  | 260 | Kandus Macmillan
1024827 | Cedar Canyon-HiLonesm BESS TL Addition (T741) [Cedar Canyon Circuit Breaker Addition - 1024678] | Iraan, Crockett | This project provides a point of interconnection for a new 50.6 MW Battery Energy Storage at the 345-kV Cedar Canyon Substation by adding a new bay into a double bus/double breaker configuration to accommodate the new interconnection. | 2022-04-11 | 2022-05-02 | 2022-05-02 |  | 702000 |  |  | 100 | n/a | 345 | <1mi (374ft) | Bundled 959 Suwannee | Steel Monopole | n/a | n/a | 200 X 200 plot | 200' X 200 plot | 25.101 (C)(5)(A) |  | 261 | Sarah Wilson
1025114 | King Mountain-North McCamey TL Addition (T452) [King Mountain - North McCamey Transmission Line Relocation Project - 1024877] | Crane, Upton | Relocate and modify transmission facilities on the DC T455/T452 King Mountain – North McCamey 138kV transmission line. | 2022-01-18 | 2022-03-17 | 2022-03-17 |  | 1617000 |  |  | 100 | 138 | 138 | 10.44 | (2x) 795 ACSR Drake | Steel Poles, Concrete Poles | 80 | 10.44 | n/a | n/a | 25.101 (C)(5)(F) |  | 262 | Melissa Horn
1025115 | King Mountain-North McCamey TL Addition (T455) [King Mountain - North McCamey Transmission Line Relocation Project - 1024877] | Crane, Upton | Relocate and modify transmission facilities on the DC T455/T452 King Mountain – North McCamey 138kV transmission line. | 2022-01-18 | 2022-03-17 | 2022-03-17 |  | 983000 |  |  | 100 | 138 | 138 | 10.44 | (2x) 795 ACSR Drake | Steel Poles, Concrete Poles | 80 | 9 | n/a | n/a | 25.101 (C)(5)(F) |  | 263 | Melissa Horn
1023353 | King Mountain - Crane II TL Addition (T732) [King Mountain Substation Upgrade - 1023073] | Crane | Provide transmission service to a generator. Add a 138-kV bay and associated circuit breaker to the existing substation. | 2021-12-01 | 2023-03-01 |  |  | 2301000 |  |  | 95 | n/a | 138 | 0.13 | (1) 959.6 KCMIL ACSS "Suwannee" | Steel Monopole | n/a | n/a | 80 | 0.13 | 25.101 (C)(5)(A) |  | 264 | Kandus Macmillan
1020853 | San Marcos-Robert Brown TL Addition (T220) [Robert Brown Jr-San Marcos TL Overhaul -1020852] | Hays, Caldwell | Increase the reliability and capability of circuit T220 on the Robert Brown Jr – San Marcos 4.91-mile 69-kV transmission line. | 2022-04-19 | 2022-07-29 |  |  | 5187000 |  |  | 75 | 69 | 138 | 4.9 | (2)959.6 ACSS/TW/HS "Suwannee" (2)995.0 T13 ACSS/TW/C7-TP (1)AFL DNO-11243 | Steel Monopole | Varies | 4.9 | 100 | 4.9 | 25.101 (C)(5)(B) |  | 265 | Manny Garcia
1018662 | Rio Pecos - Crane TL Addition (T451) [Horse Cross - Rio Pecos TL Add - 1018600] | Crane | Provide transmission service to a generator. Add fiber on existing T451 between Rio Pecos and Horse Crossing Substation | 2020-12-11 | 2021-05-03 | 2021-06-01 |  | 108000 | 90814.19 | -15.91% | 100 | 138 | 138 | 8.29 | (2)795 ACSR/GA2 "Drake" (1)AFL DNO-11243 | Concrete & Steel poles | 80 | 8.29 | n/a | n/a | 25.101 (C)(5)(C) |  | 267 | Manny Garcia
1025786 | A-frame (T373) Replacement Weimar Substation [G-T373 Replace frame Weimar Sub – 1025785] | Weimar, Colorado | Replace existing T373 A-Frame at Weimar Substation | 2022-01-20 | 2022-03-25 | 2022-03-25 |  | 130000 |  |  | 100 | 138 | 138 | 7.57 | (1) 795 ACSR "Drake" (1) DNO-11243 (1) 3/8" EHS STEEL | Steel, Concrete, and hybrid monopoles, Super duty A-Frame | Varies | 7.57 | n/a | n/a | 25.101 (C)(5)(B) |  | 268 | David Marshall
1025518 | Bellville S-Glidden TL Addition (T113) [Columbus Area TL Relocation -1024945] | Colorado, Austin Counties | Relocate and modify transmission facilities on the T113 Bellville South - Gidden 69-KV transmission between structure #135 and structure #137 | 2022-02-07 | 2022-03-17 | 2022-03-17 |  | 1127000 |  |  | 100 | 69 | 69 | 31.2 | 795 ACSR Drake | Steel Poles, Lattice | 100 | 31.2 | n/a | n/a | 25.101 (C)(5)(F) |  | 269 | Melissa Horn
1026472 | F - T154 TL Addition [Gen Add FY22 TSC Failed Equip - 1026451] | Lampasas | Replace rusted out crossarms, insulators & add bird discouragers on STR's 4/1, 6/2, and 6/3 | 2021-07-27 | 2021-09-02 | 2021-09-02 |  | 6320.52 |  |  | 100 | 138 | 138 | 8.04 | 795 ACSR Drake | Wood H-Frame | Centerline (Varies) | 8.04 | n/a | n/a | 25.101 (C)(3) |  | 270 | Tanya Noujaim
1026283 | F- Swiftex-Cedar OPGW Rpl (T367) [Gen Add FY21 TSC Failed Equip - 1024336] | Bastrop | OPGW fiber repair on a 2.4 mile section of T367 Cedar Hill Swiftex 138 kV TL from LCRA TSC's Swiftex Substation. Immediate steps were taken to complete necessary restoration activities due to the nature of the damage and the critical facilities involved. | 2021-05-23 | 2021-05-27 | 2021-05-27 |  | 400000 | 281474.05 | -29.63% | 100 | 138 | 138 | 9.91 | 795 ACSR Drake | Steel Poles | Varies | 9.91 | n/a | n/a | 25.101 (C)(3) |  | 271 | Tanya Noujaim
1026476 | F-(T197)(T242) Marshall Ford-Neil Rplc [Gen Add FY22 TSC Failed Equipment - 1026451] | Travis | Emergency repair work to Str#55 on T197/T242 to "Make Safe" | 2021-08-30 | 2021-09-02 | 2021-09-02 | 364000 |  |  |  | 100 | 138 | 138 | 14.18 | (1) 795 Drake ACSR | Steel Monopoles/Lattice Towers | Varies 30-125 | 14.18 | n/a | n/a | 25.101 (C)(3) |  | 272 | Jeremy Svagdis
1026818 | (T197)(T242) Str. #55 Repair Damage [1008416 - TSC Customer Billing] | Travis | Emergency repair work to Str#55 to restore/install permanent structures | 2021-10-25 | 2021-10-31 | 2021-10-31 |  | 79443 |  |  | 100 | 138 | 138 | 14.18 | (1) 795 Drake ACSR | Steel Monopoles/Lattice Towers | Varies 30-125 | 14.18 | n/a | n/a | 25.101 (C)(3) |  | 273 | Jeremy Svagdis
1026811 | (T490)(T273) Str. #21/7B Repair Damage [1008416 - TSC Customer Billing ] | Hays | Emergency repair work to Str #21/7B | 2021-08-28 | 2021-08-31 | 2021-09-12 |  | 56774 |  |  | 100 | 138 | 138 | 2.78 | (1) 795 Drake ACSR | Steel Monopoles/Lattice Towers | 100 | 2.78 | n/a | n/a | 25.101 (C)(3) |  | 274 | Jeremy Svagdis
1026845 | F-(T490)(T273) Goforth-Canyon Rplc [Gen Add FY22 TSC Failed Equipment - 1026451 | Hays | Emergency repair work to Str #21/7B T490/T273 to restore/install permanent structures | 2021-09-10 | 2021-09-14 | 2021-09-12 | 254000 |  |  |  | 100 | 138 | 138 | 2.78 | (1) 795 Drake ACSR | Steel Monopoles/Lattice Towers | 100 | 2.78 | n/a | n/a | 25.101 (C)(3) |  | 275 | Jeremy Svagdis
1019323 | Flatonia-Schulenburg TL Addition (T112) [LCRA TSC Fiber Build Out FY19 - 1019097] | Fayette | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2021-12-01 | 2022-06-30 |  |  | 7300000 |  |  | 65 | 138 | 138 | 11.99 | (1) 795 ACSR "Drake" | Steel Poles | 100 CL/ Blanket | 11.92 | n/a | n/a | 25.101 (C)(5)(B) |  | 276 | Kandus Macmillan
1025191 | Kenedy Switch-Nordheim W TL Addition (T577) [Kennedy Switch-Nordheim West TL Overhaul - 1024845] | DeWitt, Karnes | Increase the reliability of transmission facilities on the T577 Kenedy Switch – Nordheim West 15.88-mile 138-kV transmission line. | 2022-01-14 | 2022-03-04 | 2022-02-24 |  | 277000 |  |  | 100 | 138 | 138 | 15.902 | Drake 795 ACSR, single | Concrete, Monopoles | Blanket | 15.902 | n/a | n/a | 25.101 (C)(5)(B) |  | 277 | David Marshall
1026973 | Coronado-Buchanan TL Addition (T107) [FY22 G-T107 Coronado-Buch Fbr Repl - 1026972] | Burnet | Replace existing OPGW on T107 between STR's #137 to #138A and the underground fiber from STR#138A to Buchanan Plant with updated 72-count standard all dielectric fiber cable. | 2021-12-01 | 2022-04-08 | 2022-04-08 |  | 246000 |  |  | 100 | 69 | 69 | 2.35 | (1) 795 ACSR Drake | Lattice, H-frame | M&B 190/CL100/Blanket | 2.35 | n/a | n/a | 25.101 (C)(5)(B) |  | 278 | Kandus Macmillan
1024711 | HiCross-Marshall Ford TL Addition (T142) [HiCross-Marshall Ford Transmission Line Relocation - 1024589] | Travis | Relocate LCRA TSC elements on the T142 Hi Cross – Marshall Ford 138-kV transmission line that cross Austin Energy (AEN) bus work at Barton and Salem Walk substations. | 2023-03-01 | 2023-05-15 |  |  | 1616000 |  |  | 0 | 138 | 138 | 16.5 | (1) 1433.6 ACSS/TW Merrimack | Steel Poles, Steel H-Frames, Lattice Towers | 100 | 16.5 | n/a | n/a | 25.101 (C)(5)(E) |  | 279 | Kandus Macmillan
1025540 | Kendall-Mountain Top TL Addition (T342) [Kendall - Mountain Top Fiber Restoration and Upgrade -1025820] | Blanco, Kendall | Upgrade the T342 Optical Ground Wire (OPGW) between Kendall Substation (S241) and Mountaintop (PEC) Substation (S265)to improve reliability and capacity of the subtending CREZ East Fiber Route. | 2022-02-07 | 2022-04-29 | 2022-04-27 |  | 4562000 |  |  | 100 | 138 | 138 | 43.62 | (1) 1433.6 ACSS/TW Merrimack | Steel Poles | 100 , Centerline | 43.62 | n/a | n/a | 25.101 (C)(5)(B) |  | 280 | Sarah Wilson
1027093 | F-T579 TL Add Rplc [Gen Add FY22 TSC Failed Equip - 1026451] | Dewitt | Replace insulators as necessary | 11/1/2021 | 2021-11-12 | 2021-11-12 | 121000 |  |  |  | 100 | 138 | 138 | 14.24 | (1) 795 ACSR Drake | Steel Lattice, Steel Pole | 85 | 14.24 | n/a | n/a | 25.101 (C)(3) |  | 281 | Tanya Noujaim
1026970 | F- T226 TL Add Rplc [Gen Add FY22 TSC Failed Equip - 1026451] | Gonzales | Replace insulators, shoes & dampers on structures | 2021-11-15 | 2021-11-24 | 2021-11-24 | 117000 |  |  |  | 100 | 138 | 138 | 15.11 | (1) 795 ACSR Drake | Steel Lattice | 85 | 15.11 | n/a | n/a | 25.101 (C)(3) |  | 282 | Tanya Noujaim
1026971 | F-T609 TL Add Rplc [Gen Add FY22 TSC Failed Equip - 1026451] | Dewitt | Replace dampers as necessary | 11/29/2021 | 2021-12-03 | 2021-12-03 | 34000 |  |  |  | 100 | 138 | 138 | 2.75 | (1) 795 ACSR Drake | Steel Lattice, Steel Pole | 85 | 2.75 | n/a | n/a | 25.101 (C)(3) |  | 283 | Tanya Noujaim
1025066 | Hunt-Ingram SH TL Addition (T487/T521) [Hunt - Ingram TL Storm Hardening - 1024843] | Kerr | LCRA TSC will perform a Storm Hardening on structures and conductors on the 6.4-mile Hunt – Ingram (T487) transmission line | 2022-08-01 | 2023-05-15 |  |  | 7000000 |  |  | 0 | 138 | 138 | 4.48 | (1) 959.6 ACSS SUWANNEE | Steel Monopole | Varies 60, 100 | 4.48 | n/a | n/a | 25.101 (C)(5)(B) |  | 284 | Robin Mims
1025028 | HarperRd-Jack Frmn TL Addition (T368) [Harper Road - Jack Furman TL Storm Hardening - 1024842] | Kerr | LCRA TSC will perform a Storm Hardening on structures and conductors on the 6.4-mile Hunt – Ingram (T487) transmission line | 2022-02-01 | 2023-01-05 |  |  | 4500000 |  |  | 5 | 138 | 138 | 4.64 | (1) 959.6 ACSS SUWANNEE | Steel Monopole | Varies (100, 80, 20) | 4.64 | n/a | n/a | 25.101 (C)(5)(B) |  | 285 | Robin Mims
1025059 | Ingram-Jack Furman Storm Hardening TL Addition (T521) [Ingram - Jack Furman TL Storm Hardening - 1024844] | Kerr | LCRA TSC will perform a Storm Hardening on structures and conductors on the 6.4-mile Hunt – Ingram (T487) transmission line | 2022-08-01 | 2023-03-15 |  |  | 3000000 |  |  | 0 | 138 | 138 | 3.25 | (1) 959.6 ACSS SUWANNEE | Steel Monopole | Varies | 3.25 | n/a | n/a | 25.101 (C)(5)(B) |  | 286 | Robin Mims
1025008 | Buchanan-Buchanan CTEC TL Addition (T106) [Buchanan (CTEC) - Buchanan TL Overhaul - 1024835] | Llano County | Increase reliability of the structures and conductor | 2022-02-14 | 2022-06-06 |  |  | 7500000 |  |  | 100 | 69 | 69 | 2.8 | (1) 336.4 ACSR LINNET (1) 959.6 ACSS SUWANNEE | Steel Lattice Tower/ Steel Monopole | M&B/100 | 2.8 | n/a | n/a | 25.101 (C)(5)(B) |  | 287 | Sarah Wilson
1025479 | Bakersfield Substation Addition [Bakersfield-Big Hill TL Addition - 1024834] | Pecos County | Upgrade substation equipment to interconnect another TSP’s 345-kV circuit from Big Hill to Bakersfield | 2022-08-01 | 2023-05-15 |  |  | 593800 |  |  | 0 | 345 | 345 | n/a | n/a | A-Frame | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B) |  | 288 | Aldo Romero
1025502 | Cedar Canyon Substation Addition [Bakersfield-Big Hill TL Addition - 1024834] | Crockett County | Upgrade substation equipment to interconnect another TSP’s 345-kV circuit from Big Hill to Bakersfield | 2022-03-07 | 2023-05-15 |  |  | 634000 |  |  | 5 | 345 | 345 | n/a | n/a | A-Frame | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B) |  | 289 | Aldo Romero
1025506 | Noelke Substation Addition [Bakersfield-Big Hill TL Addition - 1024834] | Crockett County | Upgrade substation equipment to interconnect another TSP’s 345-kV circuit from Big Hill to Bakersfield | 2022-08-01 | 2023-05-15 |  |  | 728000 |  |  | 0 | 345 | 345 | n/a | n/a | A-Frame | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B) |  | 290 | Aldo Romero
1025507 | Schneeman Draw Substation Addition [Bakersfield-Big Hill TL Addition - 1024834] | Schleicher County | Upgrade substation equipment to interconnect another TSP’s 345-kV circuit from Big Hill to Bakersfield | 2022-03-07 | 2023-05-15 |  |  | 960000 |  |  | 50 | 345 | 345 | n/a | n/a | A-Frame | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B) |  | 291 | Aldo Romero
1025509 | Big Hill Substation Addition [Bakersfield-Big Hill TL Addition - 1024834] | Schleicher County | Upgrade substation equipment to interconnect another TSP’s 345-kV circuit from Big Hill to Bakersfield | 2022-02-01 | 2023-05-15 |  |  | 1220000 |  |  | 35 | 345 | 345 | n/a | n/a | A-Frame | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B) |  | 292 | Aldo Romero
1026453 | Austrop-Garfield TL Addition (T182) [TL Clearance Mitigation FY22 - 1025813] | Bastrop | Strengthen structures to support clearance mitigation. | 2022-03-29 | 2022-05-10 | 2022-05-10 |  | 375000 |  |  | 100 | 345 | 345 | 8.34 | (2) 795 DRAKE ACSR | Lattice Tower | 170 | 8.34 | n/a | n/a | 25.101 (C)(5)(B) |  | 296 | Andres Villegas
1026454 | Garfield-Lytton Spg TL Addition (T352) [TL Clearance Mitigation FY22 - 1025813] | Bastrop | Strengthen structures to support clearance mitigation. | 2022-03-29 | 2022-05-10 | 2022-05-10 |  | 375000 |  |  | 100 | 345 | 345 | 12.31 | (2) 795 DRAKE ACSR | Lattice Tower | 170 | 12.31 | n/a | n/a | 25.101 (C)(5)(B) |  | 297 | Andres Villegas
1026455 | Lytton Spg-Zorn TL Addition (T246) [TL Clearance Mitigation FY22 - 1025813] | Bastrop | Strengthen structures to support clearance mitigation. | 2022-03-29 | 2022-05-10 | 2022-05-10 |  | 375000 |  |  | 100 | 345 | 345 | 23.05 | (2) 795 DRAKE ACSR | Lattice Tower | 170 | 23.05 | n/a | n/a | 25.101 (C)(5)(B) |  | 298 | Andres Villegas
1026445 | Austrop-Zorn TL Addition (T185) [TL Clearance Mitigation FY22 - 1025813] | Bastrop | Strengthen structures to support clearance mitigation. | 2022-03-29 | 2022-05-15 |  |  | 375000 |  |  | 75 | 345 | 345 | 43.75 | (2) 795 DRAKE ACSR | Lattice Tower | 170 | 43.75 | n/a | n/a | 25.101 (C)(5)(B) |  | 299 | Andres Villegas
1024943 | Harwood-Thompsonville TL Addition (T145) [Bluestem Substation Addition - 1023910] | Gonzales | Construct the new 69-kV (138-kV capable) Bluestem Substation with a 3-breaker ring bus configuration off the T145 Harwood – Thompsonville– Waelder transmission line | 2022-02-12 | 2022-06-16 | 2022-06-16 |  | 1459000 |  |  | 100 | 138 | 138 | 21.8 | (1) 795 DRAKE ACSR | Steel Monopole | 100 | 21.8 | n/a | n/a | 25.101 (C)(5)(A) |  | 300 | Andres Villegas
1026823 | Harwood-Bluestem TL Addition (T145) [Bluestem Substation Addition - 1023910] | Gonzales | Construct the new 69-kV (138-kV capable) Bluestem Substation with a 3-breaker ring bus configuration off the T145 Harwood – Thompsonville– Waelder transmission line | 2022-02-12 | 2022-06-16 | 2022-06-16 |  | 106000 |  |  | 100 | 138 | 138 | 13.53 | (1) 795 DRAKE ACSR | Steel Monopole | 100 | 13.53 | n/a | n/a | 25.101 (C)(5)(A) |  | 301 | Andres Villegas
1026825 | Bluestem-Delhi TL Addition (T748) [Bluestem Substation Addition - 1023910] | Gonzales | Construct the new 69-kV (138-kV capable) Bluestem Substation with a 3-breaker ring bus configuration off the T145 Harwood – Thompsonville– Waelder transmission line | 2022-02-12 | 2022-06-16 | 2022-06-16 |  | 139000 |  |  | 100 | 138 | 138 | 0.04 | (1) 795 DRAKE ACSR | Steel Monopole | 100 | 0.04 | n/a | n/a | 25.101 (C)(5)(A) |  | 302 | Andres Villegas
1026824 | Bluestem-Thompsonville (T749) TL Addition [Bluestem Substation Addition - 1023910] | Gonzales | Construct the new 69-kV (138-kV capable) Bluestem Substation with a 3-breaker ring bus configuration off the T145 Harwood – Thompsonville– Waelder transmission line | 2022-02-12 | 2022-06-16 | 2022-06-16 |  | 139000 |  |  | 100 | 138 | 138 | 8.27 | (1) 795 DRAKE ACSR | Steel Monopole | 100 | 8.27 | n/a | n/a | 25.101 (C)(5)(A) |  | 303 | Andres Villegas
1027198 | McNeil-Gilleland Addition (T147) [Gen Add FY22 TSC Failed Equipment - 1026451] | Travis | Repair failed conductor splice on the bottom phase | 2021-11-22 | 2021-11-24 | 2021-11-24 | 139000 |  |  |  | 100 | 138 | 138 | 7.52 | (1) 795 DRAKE ACSR | Steel Monopole, Wood Poles | 100 | 7.52 | n/a | n/a | 25.101 (C)(3) |  | 304 | Tanya Noujaim
1020862 | Lockhart - Red Rock TL Addition (T578) [Lockhart - Red Rock TL Overhaul - 1020861] | Bastrop, Caldwell | Increase the reliability of transmission facilities on the T578 Lockhart structure #301- Red Rock 11.3 mile 138-kV transmission line | 2022-09-15 | 2023-05-15 |  |  | 13500000 |  |  | 0 | 138 | 138 | 17.1 | (1) 959.6 ACSS/TW/MA3 "SUWANNEE" | Steel Monopole | 100 | 17.1 | n/a | n/a | 25.101 (C)(5)(B) |  | 305 | Glenn Brunson
1020469 | Gonzales - Hocheim TL Addition (T542) [Gonzales - Hocheim TL Overhaul - 1020411] | Gonzales, Dewitt | Tear down and rebuild of the 19.3 mile section. Replace wood structures with concrete and steel structures and 795 ASCR "Drake" and DNO-11243 fiber. | 2022-06-15 | 2023-02-15 |  |  | 24900000 |  |  | 0 | 69 | 69 | 53.4 | (1) 2/0 QUAIL ACSR (1) 795 DRAKE ACSR | Steel Monopole | Blanket, Varies | 53.4 | n/a | n/a | 25.101 (C)(5)(B) |  | 306 | Glenn Brunson
1027309 | Schkade Fiber TL Addition (T429) [GA FY22-Schkade Fbr Add-1027306] | Tom Green | Replace existing telecom systems used for transmission operations functionality at Schkade Substation | 2022-05-02 | 2023-05-15 |  |  | 180000 |  |  | 80 | 138 | 138 | 16.82 | (2) 795 ACSR "DRAKE" | Steel Poles | Centerline, 80 | 16.82 | n/a | n/a | 25.101 (C)(5)(B) |  | 307 | Kandus Macmillan
1024787 | Bastrop W-Split TL Addition (T410) [Bastrop West-Split T410 TL SH - 1024579] | Bastrop | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2023-04-28 |  |  | 3507000 |  |  | 0 | 138 | 138 | 2.37 | (1) 959.6 ACSS/TW/MA3 "SUWANNEE" | Steel Poles | Centerline, 100 | 2.37 | n/a | n/a | 25.101 (C)(5)(B) |  | 308 | Jeremy Svagdis
1024720 | Sim Gideon-Tahitian Village TL Addition (T648) [Sim Gideon - Tahitian Village TL Storm Hardening - 1024600] | Bastrop | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2023-04-28 |  |  | 4591000 |  |  | 0 | 138 | 138 | 5.05 | (1) 959.6 ACSS/TW/MA3 "SUWANNEE" | Steel Poles | Varies, 100, 150, 200 | 5.05 | n/a | n/a | 25.101 (C)(5)(B) |  | 309 | Jeremy Svagdis
1025803 | BWSplit-Sim GideonTL Addition (T410) [Sim Gideon - Tahitian Village TL Storm Hardening - 1024600] | Bastrop | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2023-04-28 |  |  | 3464000 |  |  | 0 | 138 | 138 | 4.37 | (1) 959.6 ACSS/TW/MA3 "SUWANNEE" | Steel Poles | Varies, 100, 150, 200 | 4.37 | n/a | n/a | 25.101 (C)(5)(B) |  | 310 | Jeremy Svagdis
1027518 | F-T511 Zorn Addition [Gen Add FY22 TSC Failed Equipment - 1026451] | Travis, Caldwell | Repair downed shield wire between structures 46 and 47 south of Zorn Substation. | 2022-02-04 | 2022-02-04 | 2022-02-04 | 7600 |  |  |  | 100 | 345 | 345 | 71.02 | (2) SUWANNEE/ACSS/TW | Steel Lattice | Varies, 120, 200 | 71.02 | n/a | n/a | 25.101 (C)(3) |  | 311 | Tanya Noujaim
1022978 | Lockhart-Luling TL Addition (T184) [Lockhart-Luling TL Overhaul - 1022800] | Bastrop, Caldwell | Increase the reliability of transmission facilities on the T184 Lockhart structure #301 - Luling 10.9 mile 138-kV transmission line. | 2022-09-15 | 2023-05-15 |  |  | 1438000 |  |  | 0 | 138 | 138 | 11.1 | 3X1 795 ACSR Drake | Wood H-Frame | 85 & 100 | 11.1 | n/a | n/a | 25.101 (C)(5)(B) |  | 312 | Glenn Brunson
1027414 | F-T545 TL Upgrade [Gen Add FY22 TSC Failed Equipment - 1026451] | Colorado | Replace a vertically split pole | 2022-01-24 | 2022-02-01 | 2022-02-01 | 314723 |  |  |  | 100 | 138 | 138 | 14.15 | (1) 795 ACSR Drake | Steel Pole & Steel H-Frame | Blanket | 14.15 | n/a | n/a | 25.101 (C)(3) |  | 313 | Tanya Noujaim
1027663 | Settlers Substation Addition Ph. 1 [Settlers Substation Addition -1027353] | Bastrop, Travis | Construct a temporary hard tap on the LCRA TSC's T171 Austrop to Sim Gideon and T231 Bastrop to Webberville transmission lines | 2022-05-17 | 2022-05-25 |  |  | 1393000 |  |  | 0 | (T171)(T231) 138 | (T171)(T231) 138 | (T171) 15.61 & (T231) 14.67 | (T171)(T231) 795 DRAKE ACSR (1) | (T171)(T231) Towers & Tower Poles | (T171)(T231) 125 | (T171) 15.61 & (T231) 14.67 | n/a | n/a | 25.101 (C)(5)(B) |  | 314 | Manny Garcia
1024727 | Antler-Bergheim TL Add (T493) [Antler-Bergheim Transmission Line Upgrade 1024576] | New Braunfels, Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2024-09-09 | 2024-12-12 |  |  | 9499000 |  |  | 0 | 138 | 138 | 7.17 | (2) 959.6 Suwannee/ACSS/TW/HS | Steel Monopole | 100 | 7.17 | n/a | n/a | 25.101 (C)(5)(B) |  | 315 | Aldo Romero
1024728 | Antler Flyover-Bergheim TL Add (T389) [Antler-Bergheim Transmission Line Upgrade 1024576] | New Braunfels, Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2024-09-09 | 2024-12-12 |  |  | 47554000 |  |  | 0 | 138 | 138 | 7.17 | (2) 1433.6 Merrimack/ACSS/TW/HS | Steel Monopole | 100 | 7.17 | n/a | n/a | 25.101 (C)(5)(B) |  | 316 | Aldo Romero
1024736 | Hays Energy-Henne Split Structure TL Addition (T389) [Hays Energy-Henne Split Transmission Line Upgrade - 1024587] | Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-09-01 | 2022-12-01 |  |  | 33708000 |  |  | 0 | 138 | 138 | 5.37 | (2) 1433.6 Merrimack/ACSS/TW/HS | Steel Monopole | 100 | 5.37 | n/a | n/a | 25.101 (C)(5)(B) |  | 317 | Robin Mims
1024740 | Henne Split Structure-River Oaks Flyover TL Add (T389) [Henne-River Oaks Transmission Line Upgrade - 1024588] | Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-09-01 | 2022-12-01 |  |  | 9716000 |  |  | 0 | 138 | 138 | 2.28 | (2) 1433.6 Merrimack/ACSS/TW/HS | Steel Monopole | 100 | 2.28 | n/a | n/a | 25.101 (C)(5)(B) |  | 318 | Robin Mims
1024738 | Henne-River Oaks (T237) TL Addition [Henne-River Oaks Transmission Line Upgrade - 1024588] | Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-09-01 | 2022-12-01 |  |  | 17754000 |  |  | 0 | 138 | 138 | 3.79 | (2) 959.6 Suwannee/ACSS/TW/HS | Steel Monopole | 100 | 3.79 | n/a | n/a | 25.101 (C)(5)(B) |  | 319 | Robin Mims
1024743 | River Oaks Flyover-Hwy 46 Flyover TL Add (389) [Highway 46-River Oaks Transmission Line Upgrade - 1024590] | Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-09-01 | 2022-12-01 |  |  | 45392000 |  |  | 0 | 345 | 345 | 8.64 | (2) 1433.6 Merrimack/ACSS/TW/HS | Steel Monopole | 100 | 8.64 | n/a | n/a | 25.101 (C)(5)(B) |  | 320 | Robin Mims
1024745 | River Oaks-Hwy 46 TL Addition (T518) [Highway 46-River Oaks Transmission Line Upgrade - 1024590] | Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-09-01 | 2022-12-01 |  |  | 8465000 |  |  | 0 | 138 | 138 | 8.64 | (2) 959.6 Suwannee/ACSS/TW/HS | Steel Monopole | 100 | 8.64 | n/a | n/a | 25.101 (C)(5)(B) |  | 321 | Robin Mims
1027017 | Clear Springs Cir Bkr Add (T752) TL OH- 1027017 [Clear Springs Generator Circuit Breaker Addition - 1026518] | Seguin, Guadalupe | Upgrade the (S454) Clear Springs Substation to facilitate an interconnection project | 2022-07-25 | 2023-04-30 |  |  | 3026000 |  |  | 0 | n/a | 138 | 0.1 | (1) 959.6 ACSS Suwannee | Steel Monopole | Substation property & POI 80' x 80' plot | Substation property | 80' x 80' plot | 80' x 80' plot | 25.101 (C)(5)(A) |  | 322 | David Marshall
1021446 | Crane Sub Add [Crane Circuit Breaker Addition - 1021215] | Crane, Crane | Provide transmission service to the Crane Substation. | 2022-07-11 | 2022-12-09 |  |  | 1185000 |  |  | 0 | n/a | 138 | 0.5 | (1) 1233.6 Yukon ACSS/TW | Steel Monopole | n/a | n/a | 100 | 0.5 | 25.101 (C)(5)(A) |  | 323 | David Marshall
1018947 | Odlaw - Uvalde TL Addition (T570) [Asphalt Mines Sub Upgrade - 1018944] | Uvalde, Kinney | Increase transmission service reliability to the Asphalt Mines Substation. | 2022-07-18 | 2023-05-15 |  |  | 447000 |  |  | 0 | 138 | 138 | 26.2 | (1) 795 DRAKE ACSS/MA2 | Steel Monopole | Undefined Centerline | 26.2 | n/a | n/a | 25.101 (C)(5)(B) |  | 324 | Melissa Carugati
1025078 | Starcke-Wirtz TL Addition (T654) [Starcke - Wirtz TL Storm Hardening - 1024854] | Burnet | LCRA TSC will perform a Storm Hardening on the 6.7-mile Starcke – Wirtz (T654) 138-kV transmission line. | 2022-07-11 | 2023-05-15 |  | 6245000 | 2357000 |  |  | 0 | 138 | 138 | 6.65 | (1) 795 ACSR "Drake" | Steel Monopole | Varies | 6.65 | n/a | n/a | 25.101 (C)(5)(B) |  | 325 | Jeremy Svagdis
1023686 | Hilltop-Strahan TL Add (T445) [Hilltop - Strahan TL Upgrade - 1023192] | Hays | Increase the reliability of transmission facilities on the T445: Hilltop – Strahan 1.25-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. | 2022-09-15 | 2023-02-15 |  |  | 4677000 |  |  | 0 | 138 | 138 | 0.82 | (1) 1433 ACSS/TW "Merrimack" | Steel Poles | Varies | 0.82 | n/a | n/a | 25.101 (C)(5)(B) |  | 326 | Jeff Baranzyk
1024012 | Fayetteville - Salem TL Addition (T177/T211) [Fayetteville - Salem Transmission Line Upgrade - 1023804] | Washington, Fayette | Rebuilding of the existing 19.3 Miles 345/138 KV Double Circuit TL T177 & T211 from Fayetteville Substation to the Salem Substation. | 2022-07-05 | 2023-05-15 |  |  | 77800000 |  |  | 0 | 138/345 (T177/T211) | 138/345 (T177/T211) | 19.34/27.45 (T177/T211) | (1) 959.6 ACSS/TW HS "SUWANNEE"/ (2) 959.6 ACSS/TW HS "SUWANNEE" (T177/T211) | Steel Poles | 85-100 | 19.34/27.45 (T177/T211) | n/a | n/a | 25.101 (C)(5)(B) |  | 327 | Hooman Larimi
1023873 | Fairland-Lago Vista TL Addition (T414) [Fairland -Lago Vista TL Upgrade 1023803] | Travis, Burnet | Increase the reliability of transmission facilities on the T414 Fairland – Lago Vista 21-mile 138-kV transmission line by replacing the existing Condor conductor. | 2022-08-01 | 2023-05-15 |  |  | 13689000 |  |  | 0 | 138 | 138 | 21.04 | (1) 795 ACSR "Drake" | Steel Towers & Galvanized Steel Pole | 100 | 21.04 | n/a | n/a | 25.101 (C)(5)(B) |  | 328 | Hooman Larimi
1026437 | Eckert-Nebo TL Addition (T126) [Eckert Power Transformer Upgrade - 1025306] | Gillespie | Increase the reliability of substation equipment at the Eckert Substation. | 2024-02-06 | 2023-04-25 |  |  | 89000 |  |  | 0 | 69 | 138 | 0.7 | (1) 795 ACSR "Drake" | Steel Poles | 100 | 0.7 | n/a | n/a | 25.101 (C)(5)(B) |  | 329 | Robin Mims
1026439 | Sandstone Mtn-Gillespie TL Addition (T130) [Eckert Power Transformer Upgrade - 1025306] | Gillespie, Llano | Increase the reliability of substation equipment at the Eckert Substation. | 2024-02-06 | 2023-05-11 |  |  | 428000 |  |  | 0 | 69 | 138 | 36.33 | (1) 959 SUWANNEE ACSS | Steel H-Frames | 100 | 36.33 | n/a | n/a | 25.101 (C)(5)(B) |  | 330 | Robin Mims
1025850 | Ferguson-Sherwood TL Addition (T187) [Starcke-Wirtz TL Storm Hardening - 1024854] | Burnet | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2024-05-15 |  |  | 57000 |  |  | 0 | 138 | 138 | 9.35 | (1) 795 ACSR "Drake" | Steel Poles and Lattice Towers | Varies | 9.35 | n/a | n/a | 25.101 (C)(5)(B) |  | 331 | Jeremy Svagdis
1025852 | Marble F-Granite Mtn TL Addition (T195) [Starcke-Wirtz TL Storm Hardening - 1024854 | Burnet | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2024-05-15 |  |  | 52000 |  |  | 0 | 138 | 138 | 4.08 | (1) 795 ACSR "Drake" | Steel Poles and Lattice Towers | Varies | 4.08 | n/a | n/a | 25.101 (C)(5)(B) |  | 332 | Jeremy Svagdis
1025851 | Ferguson-GraniteMtn TL Addition (T376) [Starcke-Wirtz TL Storm Hardening - 1024854 | Burnet | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2024-05-15 |  |  | 54000 |  |  | 0 | 138 | 138 | 5.75 | (1) 795 ACSR "Drake" | Steel Poles and Lattice Towers | Varies | 5.75 | n/a | n/a | 25.101 (C)(5)(B) |  | 333 | Jeremy Svagdis
1026089 | Wirtz-Burnet TL Addition (T218) [Starcke-Wirtz TL Storm Hardening - 1024854 | Burnet | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2024-05-15 |  |  | 52000 |  |  | 0 | 138 | 138 | 16.08 | (1) 795 ACSR "Drake" | Steel Poles and Lattice Towers | Varies | 16.08 | n/a | n/a | 25.101 (C)(5)(B) |  | 334 | Jeremy Svagdis
1025012 | Buchanan CTEC-Pitsburg TL Addition (T267) [Buchanan (CTEC) - Pitsburg TL Overhaul - 1024836] | Llano County | Overhaul T267 to increase reliability of the structures and conductor | 2022-08-04 | 2023-06-30 |  |  | 20518000 |  |  | 0 | 69 | 69 | 14.49 | (1) 336.4 ACSR "LINNET" (1) 4/0 ACSR "PENGUIN" (1) 959.6 ACSS/TW/MA3 "SUWANNEE" (1) 4/0 ACSR "PENGUIN" (1) 959.6 ACSS/TW/MA3 "SUWANNEE" | Steel Lattice & Steel Poles | 100 | 14.49 | n/a | n/a | 25.101 (C)(5)(B)
1026798 | Chief Brady TL Addition (T378) [Chief Brady Substation Upgrade – 1025303] | Williamson | Chief Brady Substation will be upgraded to increase the bus rating and replace equipment identified as obsolete. The substation upgrade will also install Tier 3 Physical Security Measures | 2022-10-10 | 2023-04-03 |  |  | 551800 |  |  | 0 | 138 | 138 | 5.12 | 795 ASCR Drake, single | Steel H-frames, Steel Poles, Steel Lattice | Varies, 80 - 100 | 5.12 | n/a | n/a | 25.101 (C)(5)(B)
1027302 | T336 Fiber Replacement Project [PI Switch-Loop 337 Fiber Restoration - 1027886] | Comal | Replace and restore OPGW fiber on T336 | 2022-01-10 | 2022-05-13 |  | 1800000 |  |  |  | 100 | 138 | 138 | 3.5 | (1) 959.6 ACSS/TW/M3A “SUWANNEE” | Concrete Poles | n/a | 3.5 | n/a | n/a | 25.101 (C)(3)
1024072 | Lockhart-Red Rock TL Addition (T578/T184) [Lockhart-Split TL Upgrade - 1023809] | Bastrop, Caldwell | Increase the reliability and capability of transmission facilities on the T184 Lockhart – Luling and T578 Lockhart – Red Rock 5.7-mile 138-kV double-circuit section of transmission line from Lockhart Substation to structure #75 (previously structure #301). | 2023-02-01 | 2023-05-15 |  |  | 8000000 |  |  | 0 | 138 | 138 | 5.7 | (1) 959.6 ACSS/TW/M3A “SUWANNEE” | Steel Poles | 85 | 5.7 | n/a | n/a | 25.101 (C)(5)(B)
1023899 | Lockhart - Luling TL Addition (T184) [Lockhart-Split TL Upgrade - 1023809] | Bastrop, Caldwell | Increase the reliability and capability of transmission facilities on the T184 Lockhart – Luling and T578 Lockhart – Red Rock 5.7-mile 138-kV double-circuit section of transmission line from Lockhart Substation to structure #75 (previously structure #301). | 2023-02-01 | 2023-05-15 |  |  | 8000000 |  |  | 0 | 138 | 138 | 5.7 | (1) 959.6 ACSS/TW/M3A “SUWANNEE” | Steel Poles | 85 | 5.7 | n/a | n/a | 25.101 (C)(5)(B)
1027616 | Muldoon-Flatonia TL Addition (T739)[Muldoon Substation Addition - 1024679] | Fayette | New three breaker ring bus substation to provide a 138-kV line termination for a 240 MW solar generation facility. | 2022-11-18 | 2023-03-10 |  |  | 207000 |  |  | 0 | 138 | 138 | 8.6 | (1) 959.6 SUWANNEE ACSS/TW | Steel Pole, Steel H-frame | 100; Centerline | 8.6 | n/a | n/a | 25.101 (C)(5)(A)
1027617 | Muldoon-7V Slr Ranch TL Addition (T740)[Muldoon Substation Addition - 1024679] | Fayette | New three breaker ring bus substation to provide a 138-kV line termination for a 240 MW solar generation facility. | 2022-11-18 | 2023-03-10 |  |  | 188000 |  |  | 0 | n/a | 138 | 0.02 | (1) 959.6 SUWANNEE ACSS/TW | Steel Pole | n/a | n/a | 100 | 0.02 | 25.101 (C)(5)(A)
1024297 | Hornsby TL Addition (T511) [Hornsby Substation Addition - 1023852] | Travis | Provide Transmission service to a load serving substation | 2022-09-15 | 2023-04-15 |  |  | 75785000 |  |  | 0 | 345 | 345 | 57.15 | (2) 959.6 SUWANNEE ACSS/TW | Lattice Towers | Varies | 57.15 | 120 | 0.15 | 25.101 (C)(5)(A)
1024549 | Hornsby TL Addition (T738) [Hornsby Substation Addition - 10235852] | Austin/Travis | Provide Transmission service to a load serving substation | 2022-09-15 | 2023-04-15 |  |  | 75785000 |  |  | 0 | 345 | 345 | 14.22 | (2) 959.6 SUWANNEE ACSS/TW | Lattice Towers | Varies | 14.22 | 120 | 0.15 | 25.101 (C)(5)(A)
1024783 | Brenham-Hwy 36 TL Addition (T468) [Flood Mitigation FY 2022 System Upgrade - 1024586] | Brenham/ Washington | Reduce the risk of erosion and flooding to transmission facilities | 2022-10-05 | 2022-12-22 |  |  | 130000 |  |  | 0 | 138 | 138 | 2.29 | (1) 959.6 SUWANNEE ACSS/TW | Concrete H-Frame and Concrete Monopole | 75 | 2.29 | n/a | n/a | 25.101 (C)(5)(B)
1024785 | Gilleland-Clear Spr TL Addition (T511)[Flood Mitigation FY 2022 System Upgrade - 1024586] | Manor/Travis | Reduce the risk of erosion and flooding to transmission facilities | 2022-10-05 | 2022-12-22 |  |  | 2914000 |  |  | 0 | 345 | 345 | 71 | (2) 959.6 SUWANNEE ACSS/TW | Towers, Poles & H-Frames | 120; 125 | 71 | n/a | n/a | 25.101 (C)(5)(B)
1027544 | Crane - Upton TL Addition (T441) [Crane East Substation Upgrade - 1026913] | Upton | Install circuit breakers and capacitor banks at Crane East Substation | 2022-10-17 | 2023-05-15 |  |  | 5993000 |  |  | 0 | 138 | 138 | 27 | (1) 1233.6 YUKON/TW/MA2 | Steel Pole Dead ends/Delta braced post steel pole tangents | Centerline | 27 | n/a | n/a | 25.101 (C)(5)(B)