## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
TLAD01 | New Heights 230kV Substation | Montgomery | Construct new 230kV double circuit cut-in to new Heights Substation from existing 230kV Line #822 | 2018-07-02 | 2019-06-07 | 2019-06-20 | 5,336,463 T-line 14,510,804 Substation | 27694983 |  |  | 100% | na | 230 | 2.8 | 666 ACSS Flamingo | Concrete or Steel | na | na | 175 | 1.4 | 46408 | Working on final cost
TLH100 | Garden to Legend New 230kV Line | Jefferson County, TX | Construct new 230kV line from proposed new Garden Substation to proposed new Legend Substation | 2018-07-02 | 2020-05-29 | 2020-08-12 | 34,772,442 to 46,355,987 T-line 32,915,077 Substation | 69584588 |  |  | 100% | na | 230 | 11.4 to 15.8 | 1272 ACSS Bittern | Concrete or Steel | 225 | 0.3 to 2.7 | 62.5 to 125 | 10.4 to 15.4 | 47003 | Final project cost dependent on potential pipeline AC mitigation spend in 2022. Mitigation study is currently underway.
TLY011 | Hull to sour Lake 69kV Rebuild | Liberty and Hardin Counties, TX | Rebuild existing 69kV line from existing Hull Substation to existing Sour Lake Substation | 2019-01-02 | 2020-12-01 |  | 47478583 | 48679887 |  |  | 98% | 69 | na | 27.57 | 666 ACSR Flamingo | Concrete or Steel | 25 to 50 | 27.57 | na | na | 25.101(c)(5)(B) (i)(ii)
LLV013 | New Timberland 230kV Substation | Liberty and Harris Counties, TX | Construct new 230kV double circuit cut-in to new Timberland Substation from existing 230kV Line #822 | 2021-04-01 | 2022-04-29 |  | 33,997,858 to 37,334,542 T-line 23,348,490 Substation |  |  |  |  | na | 230 | 15.4 to 23.4 | 666 ACSR Flamingo | Concrete or Steel | na | na | 125 | 7.7 to 11.7 | 49715
TLH090 | Lewis Creek to Porter New 230kV Line | Montgomery County, TX | Construct new 230kV Line from existing Lewis Creek Substation to existing Porter Substation | 2019-09-23 | 2021-07-10 | 2021-07-10 |  | 36440000 |  |  | 100% | na | 230 | 27.3 | 1272 ACSS Bittern | Concrete or Steel | 100 to 275 | 27.3 | na | na | 25.101(c)(5)(A) (i)(ii) and 25.101 ( c ) (5)(B)(i)(ii) | Working on final cost
TLH089 | Lewis Creek to Sheawill to Fort Worth Pipe Rebuild | Montgomery County, TX | Rebuild existing 138 kV Line 503 from existing Lewis Creek Substation to existing Sheawill Substation to existing Fort Worth Pipe Substation | 2020-07-18 | 2021-07-21 | 2021-07-21 |  | 9320000 |  |  | 100% | 138 | na | 14.8 | 666 ACSS Flamingo | Concrete or Steel | 150 | 14.8 | na | na | 25.101(c)(5)(B) (i)(ii) | Working on final cost
TLH095 | Lewis Creek to Goree to Rivtrin Rebuild | Montgomery and Walker Counties, TX | Rebuild existing 138 kV Line 487 from existing Lewis Creek Substation to existing Gorree Substation to existing Rivtrin Substation Substation | 2019-10-12 | 2020-12-22 | 2020-12-22 |  | 20160000 |  |  | 100% | 138 | na | 35.6 | 666 ACSS Flamingo | Concrete or Steel | 150 to 275 | 35.6 | na | na | 25.101(c)(5)(B) (i)(ii) | Working on final cost
TLZ500 | Panorama to Longmire Rebuild | Montgomery County, TX | Rebuild existing 138kV Line 596 from existing Panorama Substation to existing Longmire Substation | 2019-09-16 | 2020-04-21 | 2020-04-21 |  | 3948663 |  |  | 100% | 138 | na | 2.7 | 1272 ACSS Bittern | Concrete or Steel | 100 | 2.7 | na | na | 25.101(c)(5)(B) (i)(ii) | Working on final cost
TLH050 | Longmire to Ponderosa Rebuild | Montgomery County, TX | Rebuild existing 138kV Line 106 from existing Longmire Substation to existing Ponderosa Substation | 2019-09-09 | 2020-09-21 | 2020-09-21 |  | 4666842 |  |  | 100% | 138 | na | 3.1 | 1272 ACSS Bittern | Concrete or Steel |  | 3.1 | na | na | 25.101(c)(5)(B) (i)(ii) | Working on final cost
TLH091 | Alden to Lewis Creek Rebuild | Montgomery County, TX | Rebuild existing 138kV Line 569 from existing Alden Substation to existing Lewis Creek Substation | 2019-09-16 | 2020-09-21 | 2020-09-21 |  | 3080956 |  |  | 100% | 138 | na | 5.4 | 1272 ACSS Bittern | Concrete or Steel |  | 5.4 | na | na | 25.101(c)(5)(B) (i)(ii) | Working on final cost
PSJ7385 | Hurricane Laura Emergency Restoration |  | Emergency restoration of the ETI Transmission System caused by Hurricane Laura | 2020-08-27 |  |  |  |  | 9030122 | [11 empty] | 25.83(d)
PSJ7388 | Hurricane Delta Emergency Restoration |  | Emergency restoration of the ETI Transmission System caused by Hurricane Delta | 2020-10-09 |  |  |  |  | 3487885 | [11 empty] | 25.83(d)
STL006 | New High Island 138kV Substation | Galveston County, TX | Construct new 138kV High Island Substation | 2020-05-01 | 2021-06-08 | 2021-06-08 |  | 8846918 |  |  | 100% | [9 empty] | 25.83(a)(3) | Working on final cost
TLAF12 | Stowell to High Island L-89 voltage upgrade | Chambers and Galveston Counties, TX | Upgrade existing 69kV Stowell to High Island Line 89 voltage to 138kV | 2021-03-01 | 2021-06-08 | 2021-06-08 |  | 3044338 |  |  | 100% | 69 | 138 | 0.29 | ACSR 666 Flamingo | Steel |  |  | N/A | N/A | 25.101(c)(5)(B) (i)(ii) | Working on final cost
DSJ000 | New Veteran 230kV Substation | Walker County, TX | Construct new 230kV Veteran Substation | 2021-06-21 | 2022-03-30 | 2022-04-26 |  | 21330748 |  |  | 100% | [9 empty] | 25.83(a)(3) | Working of final cost
TLJ021 | Veteran to Rocky Creek L-139 | Walker County, TX | New 230kV transmission circuit cut-in to new Veteran Substation from existing 230 kV line from Lewis Creek to Rocky Creek | 2022-01-10 | 2022-03-30 | 2022-04-26 |  | 712599 |  |  | 100% |  | 230 | 0.3 | 1272 ACSS Bittern | Concrete or Steel |  |  | N/A | N/A | 25.101(c)(5)(A) (i)(ii) | Working of final cost
TLJ020 | Veteran to Lewis Creek L-123 | Walker County, TX | New 230kV transmission circuit cut-in to new Veteran Substation from existing 230 kV line from Lewis Creek to Rocky Creek | 2022-01-20 | 2022-03-30 | 2022-04-26 |  | 743619 |  |  | 100% |  | 230 | 0.3 | 1272 ACSS Bittern | Concrete or Steel |  |  | N/A | N/A | 25.101(c)(5)(A) (i)(ii) | Working of final cost
STJ007 | New Commerce 138kV Substation | Montgomery County, TX | Construct new 138kV Commerce Substation | 2020-08-19 | 2021-07-30 | 2021-08-26 |  | 14113910 |  |  | 100% | [9 empty] | 25.83(a)(3) | Working on final cost
LTJ999 | L-587 New Commerce 138kV Substation Cut-In | Montgomery County, TX | New 138kV doouble circuit transmission line from new Commerce 138kV Substation to existing 138kV transmission line 587 | 2021-07-08 | 2021-07-30 | 2021-08-26 |  | 1229544 |  |  | 100% |  | 138 | 0.1 | 649.5 ACAR Dove | Steel |  |  | N/A | N/A | 25.101(c)(5)(A) (i)(ii) | Working on final cost
U75983 | CPChem L-584 Relocation | Orange County, TX | At customer's request, relocate a 2.5 miles section of 138kV T-line that runs through customer's property to the outer extents of the property as directed by customer. Relocated line section will be approximately 3 miles. This project is fully funded by the customer. | 2021-08-12 | 2022-01-10 | 2022-01-10 |  | 12000000 |  |  | 100% | 138 | N/A | 3 | 1272 ACSR Bittern | Steel | 100 | 2.5 | 140 | 3 | 25.101(c)(5)(B) (i)(ii) | Working on final cost
DSJ138 | New Millbend 138kV Substation | Montgomery County, TX | Construct new 138kV transmission line from existing 138kV line 92 or 586 to new Millbend Substation | 2023-04-01 | 2024-03-31 |  | 41,514,951 to 62,378,730 T-Line 22,353,621 to 23,879,295 Substation |  |  |  |  | na | 138 | 10.8 to 17.88 | 666 ACSS Flamingo | Concrete or Steel | na | na | 60 to 100 | 5.4 to 8.94 | 52241
DSJ230 | New Castle 230kV Substation | Montgomery and Grimes Counties, TX | Construct new230kV transmission line from existing 230kV line 136 to new Castle Substation | 2023-04-01 | 2024-03-31 |  | 31,429,246 to 39,233,765 T-Line 16,861,754 to 18,146,771 Substation |  |  |  |  | na | 230 | 12.46 to 16.46 | 1272 ACSS Bittern | Concrete or Steel | na | na | 72.5 to 125 | 6.23 to 8.23 | 52304
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.