## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
29-2656 | PS38 | Cherokee County | New 138 kV Transmission Line from Arp Tap Switching Station to new PS38 (Lake Tyler) Substation | July 2020 | December 1, 2021 |  | $1.1M for transmission line | $1.2M |  |  | 0 | N/A | 138 | 0.65 | 336 ACSR Linnet | Single pole, 75-95 ft, steel | N/A | N/A | 100 | 0.6 | §25.83 §25.101.c | radial line to new pump station