## LCRA TSC MCPR Oct. 2022
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
1017348 | Cooks Point TL Addition (CCN) | Burleson | Construct a new 138-kV transmission line to provide a transmission point of interconnection to a new load-serving substation | 2020-07-01 | 2021-06-30 | 2021-06-30 | T-Line $ 26.5 - 34.1M; Substation $ 6.1 - 6.7M |  |  |  | 100 | 0 | 138 | 17-23 | 2x1- 795 ACSR "Drake" | TBD; Poles and/or H-Frames | 0 | 0 | Varies; 80 | 17-23 | 48358 | 6/17/19 - PUC Approved Route 12; approved route cost estimate in CCN application for transmission line $29M; substation $6.2M
1017514 | Airline-Naval Base T475 RMV (Airline TL Relocation - 1017336) | Nueces | Relocate transmission facilities on (T475) and (T476). The present 69-kV configuration at Airline Substation does not allow for one power bank to serve as a backup for the other during outage. | 2019-09-24 | 2019-09-30 | 2019-09-30 |  | 993000 |  |  | 100 | 69 | 138 | 6.39 | (1) 795kcl ACSR/AW "Drake" | Steel Monopole | Centerline; 16 | 6.39 | n/a | n/a | 25.101 (C)(5)(D) | The scope of this project, 1017513 Airline - Naval Base TL Addition, was reduced to only include the removal of one structure which was captured on the 1017514 Airline-Naval Base T475 RMV project.
1018663 | Rio Pecos - Horse Crossing TL Addition (T682) [Horse Cross - Rio Pecos TL Add - 1018600] | Crane | Provide transmission service to a generator. (This circuit will be added to the open position on the structures on the existing (T451) Rio Pecos - Crane, after the project is complete the transmission line will be numbered T682 Rio Pecos - Horse Crossing) | 2021-01-08 17:00 | 2021-05-28 | 2021-06-01 |  | 1871000 |  |  | 100 | 0 | 138 | 0.76 | (2) 795 ACSR Drake | Steel/Concrete Monopoles | 80; Centerline | 0.76 | n/a | n/a | 25.101 (C)(5)(C)
1016702 | Altair - Nada TL Addition (T545) (Glidden Area TL Upgrade - 1016219) | Colorado | OPGW (fiber) installation (T545) and Substation upgrade at Nada and Altair substations from 69kV to 138kV | 2018-12-03 | 2019-05-31 | 2019-05-31 |  | 7068000 |  |  | 100 | 69 | 138 | 14.12 | 795 Drake ASCR & 26/7 & Single | Steel, Wood, & Lattice | Blanket | 14.12 | Blanket | 14.1 | 25.101 (C)(5)(B)
1018599 | Bakersfield - Solstice TL Addition (CCN) | Pecos | Construct a new 345-kV transmission line to connect LCRA TSC's existing Bakersfield station and AEP Texas' Solstice Switch Station | 2020-01-07 | 2020-12-17 | 2020-12-17 | T-line $148 - $192M; Bakersfield Substation - $6M; Solstice Switch Station (AEP) - $38M |  |  |  | 100 | 0 | 345 | 130-190 | 1926.9 kcl ACSS/Cumberland (LCRA TSC) and 1590 ACSS (AEP Texas) | Double-circuit steel lattice towers | 0 | 0 | 150 | 68 - 92 | 48787 | 5/28/19 PUC Approved Route 24; approved route cost estimate in CCN application for transmission line $155.9M; LCRA TSC's Bakersfield substation $6.5M; AEP's Solstice Switch Station $38.4M
1017897 | Culberson - Kunitz TL Addition (T271) (Culberson-Kunitz Overhaul - 1017896) | Culberson | Structure replacement upgrades to steel and concrete Poles | 2019-05-28 | 2020-06-01 | 2020-06-01 10:46 |  | 2015000 |  |  | 100 | 138 | 138 | 28.88 | Linnet; 336kcl; 0.721” | Wood | 100 | 28.88 | n/a | n/a | 25.101 (C)(5)(B)
1017394 | Mountain Home TL Addition (CCN) | Kerr, Gillespie | Construct a new 138-kV transmission line to provide a transmission point of interconnection to a new load-serving substation | 2021-08-27 | 2022-12-27 17:00 |  | T-line $46.5 - $58.5M; Substation $7.1 - $7.5M |  |  |  | 90 | 0 | 138 | 21-29 | 795 Kcl 26/7 ACSR “Drake” | tbd; steel or concrete poles | 0 | 0 | varies; 100 | 21-29 | 49523 | 7/6/20 - PUC Approved Route Hunt 37A; approved route cost estimate in CCN application for transmission line $47M; substation $7.3M
1014015 | Camp Wood - Leakey TL Addition (T269) [Camp Wood - Leakey TL Overhaul - 1016183] | Real | Increase the reliability of transmission facilities on the T269 Camp Wood-Leakey 17.3 le 69-kV transmission line and upgrade the line to 795 ACSR Drake conductor (111 MVA at 69-kV), 138-kV capable with an OPGW shield wire. | 2020-11-30 17:00 | 2021-06-30 | 2021-06-30 |  | 43428000 |  |  | 100 | 69 | 138 | 17.32 | Single 795 ACSR Drake | Steel & Lattice | Varies; 60 | 17.32 | n/a | n/a | 25.101 (C)(5)(B)
1019114 | Zorn - Pooley Rd TL Addition (T158) [Luling-Zorn TL Overhaul - 1019113] | Guadalupe | Increase the reliability of transmission facilities on the T373 Schulenburg - Glidden 20.25- | 2020-02-03 | 2021-08-31 | 2021-05-06 |  | 7228000 |  |  | 100 | 138 | 138 | 28.02 | 795 ACSR Drake | Concrete and Steel poles | 100 | 28.02 | n/a | 28.02 | 25.101 (C)(5)(B)
1022830 | Giddings - Warda TL Addition (T137) [Gidding-Warda TL Upgrade - 1022731] | Fayette, Lee | Increase the reliability of transmission facilities on the T137 Giddings - Warda 9.66-le 69-kV transmission line by converting the line to 138-kV operation and increasing the transmission capacity. | 2020-04-01 | 2020-10-19 12:00 | 2020-10-16 |  | 12383000 |  |  | 100 | 0kv (De-energized) | 138kv | 9.66 | (1) 959.6 ACSS "Suwannee" | Steel and Concrete Monopoles | 100 | 9.66 | 100 | n/a | 25.101 (C)(5)(B)
1020552 | Burnet - Lampasas TL Addition (T219) [Burnet-Lampasas TL Overhaul - 1020371] | Burnet, Lampasas | Increase the reliability of transmission facilities on the T219 Burnet - Lampasas 23.4-le 138-kV transmission line. | 2020-03-15 | 2021-10-01 | 2021-05-11 |  | 19159000 |  |  | 100 | 138 | 138 | 23.3 | Single 795 ACSR Drake | Wood H-frames | Centerline | 23.3 | Centerline | n/a | 25.101 (C)(5)(B)
1019285 | T271 TL Addition (T271) [Pinnacle Substation Addition - 1019007] | Culberson | LCRA TSC will build a new substation (Pinnacle) adjacent to T271 to interconnect the new 186.3 MW solar generation facility. Replace transmission structures to allow for substation cut-in and upgraded conductor and OPGW. | 2020-01-29 | 2020-10-14 17:00 | 2020-10-14 17:00 |  | 10800000 |  |  | 100 | 69 | 138 | 18.1 | Single 1433 ACSS/TW Merrimack | Steel monopole | 100 | 18.1 | 100 | n/a | 25.101 (C)(5)(B)
1016698 | Glidden - Altair TL Addition (T544) [Glidden Area TL Upgrade - 1016219] | Colorado | Increase the capacity and reliability of transmission facilities on the Glidden-Altair 12.2 le 69-kV transmission line (T544) and the Altair-Nada 14.12 le 69-kV transmission line (T545). | 2021-08-19 | 2021-09-13 | 2021-09-13 |  | 858000 |  |  | 100 | 138 | 138 | 12.2 | 795 ACSR Drake | Steel & Concrete | 80 | 12.2 | 80 | 12.3 | 25.101 (C)(5)(B)
1023677 | Asherton - Bevo TL Addition (T603) [Asherton - Bevo TL Relocation - 1022882] | Dimmit | Relocate dead-end structure #1 on the T603 Bevo to Asherton 138-kV transmission line to outside of the AEP-owned Asherton Substation. Re-route and re-ternate T603 to a new point-of-interconnection (POI) structure owned by AEP and installed by AEP outside of the Asherton Substation. | 2022-02-07 | 2022-04-01 | 2022-04-01 |  | 447000 |  |  | 100 | 138 | 138 | 8.05 | (1) 795 Drake ACSR | Steel monopoles | AEP owned | AEP owned | AEP owned | AEP owned | 25.101 (C)(5)(B)
1020445 | HiCross - Turner TL Addition (T143) [HiCross-Turner TL Storm Harden-1020386] | Travis, Hays | Increase the reliability of transmission facilities on the T143 Hi Cross - Turnersville 8.8-le 138-kV transmission line. | 2020-06-03 08:00 | 2021-04-06 | 2021-04-06 |  | 5618000 |  |  | 100 | 138 | 138 | 7.9 | bundled 795 ACSR Drake | Concrete and Steel monopoles | 100 | 7.9 | n/a | n/a | 25.101 (C)(5)(B)
1023668 | Gabriel - Glasscock TL Addition (T359) [Gabriel Substation Upgrade - 1020410] | Williamson | LCRA TSC will upgrade the configuration of 138-kV from Single Bus/Single Breaker to the breaker and a half bus configuration and replace five existing CBs at Gabriel Substation. | 2021-05-19 | 2022-05-13 | 2022-05-13 |  | 361000 |  |  | 100 | 138 | 138 | 6.59 | Single 795 ACSR Drake | Steel Pole | 80 | 6.59 | n/a | n/a | 25.101 (C)(5)(B)
1021176 | Gabriel - Jarrell TL Addition (T224) [Gabriel Substation Upgrade - 1020410] | Williamson | Upgrade the configuration of 138-kV from Single Bus/Single Breaker to the breaker and a half bus configuration and replace five existing CBs at Gabriel Substation. | 2020-08-17 | 2022-05-13 | 2022-05-13 |  | 1083000 |  |  | 100 | 138 | 138 | 1.26 | Single 795 ACSR Drake | Steel Pole | 60 | 1.26 | n/a | n/a | 25.101 (C)(5)(B)
1021174 | Gabriel - Georgetown East TL Addition (T223) [Gabriel Substation Upgrade - 1020410] | Williamson | Upgrade the configuration of 138-kV from Single Bus/Single Breaker to the breaker and a half bus configuration and replace five existing CBs at Gabriel Substation. | 2020-08-17 | 2022-05-13 | 2022-05-13 |  | 1083000 |  |  | 100 | 138 | 138 | 1.26 | Single 795 ACSR Drake | Steel Pole | 60 | 1.26 | n/a | n/a | 25.101 (C)(5)(B)
1023667 | Gabriel - Rivery TL Addition (T457) [Gabriel Substation Upgrade - 1020410] | Williamson | Upgrade the configuration of 138-kV from Single Bus/Single Breaker to the breaker and a half bus configuration and replace five existing CBs at Gabriel Substation. | 2021-05-19 | 2022-05-13 | 2022-05-13 |  | 361000 |  |  | 100 | 138 | 138 | 2.43 | Bundled 795 ACSR Drake | Steel Pole | Varies | 2.43 | n/a | n/a | 25.101 (C)(5)(B)
1021428 | Sherwood Shores - Coronado TL Addition (T635) [Coronado-Sherwood Shores TL SH - 1021211] | Burnet | Increase the reliability of circuit T635 on the Coronado – Sherwood Shores 12.2-le 138-kV transmission line | 2021-09-16 | 2022-05-11 | 2022-05-11 |  | 12145000 |  |  | 100 | 138 | 138 | 12.15 | Single 795 Drake ACSR | Steel Poles/Steel Lattice | Centerline | 12.15 | n/a | n/a | 25.101 (C)(5)(B)
1019024 | Plum - Flatonia TL Addition (T133) [Fayette Area TL Upgrades - 1018913] | Fayette | Increase the capacity of the Fayetteville to Glidden 138-kV transmission circuit (T176) and the Flatonia to Plum 138-kV transmission circuit (T133). | 2020-09-08 | 2021-05-14 | 2021-05-14 |  | 10196000 |  |  | 100 | 138 | 138 | 19.63 | (1)959.6 ACSS/TW "Suwannee" (1)AFL DNO-11242 (1)3/8" EHS Steel | Single pole and H-Frame (Steel, Wood, Concrete) | 100 | 19.53 | n/a | n/a | 25.101 (C)(5)(B)
1021444 | Paleface - Miller Creek TL Addition (T124) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Travis, Hays, Blanco, | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124 and replacing four structures | 2020-08-03 | 2021-08-28 | 2021-08-30 |  | 3764000 |  |  | 100 | 138 | 138 | 17 | Single 795 ACSR Drake | Single Steel Monopoles | 80 | 17 | n/a | n/a | 25.101 (C)(5)(B)
1019263 | Bevo - Rosita Creek TL Addition (T463) [Dimmit CB Addition - 1018912] | Maverick, Dimmit | Increase the reliability of transmission facilities on the T463 Rosita Creek – Bevo 47.63-le 138-kV transmission line. | 2021-03-02 | 2021-11-30 | 2021-11-11 |  | 1539000 |  |  | 100 | 138 | 138 | 36.85 | Single 795 ACSR Drake | Steel monopoles | Centerline | 36.85 | n/a | n/a | 25.101 (C)(5)(B)
1021973 | T723 Motorman-Upton TL Addition (T723) [Motorman Substation Addition - 1021552] | Upton, Crane | Construct a 3-breaker ring bus cut in to the existing T441 Crane East to Upton 138-kV transmission line. | 2022-02-07 | 2022-06-09 | 2022-06-29 |  | 679000 |  |  | 100 | 138 | 138 | 17.97 | 1233.6 Yukon ACSS/TW & Single | Concrete Pole | Centerline; 80 | 17.97 | Centerline; 80 | n/a | 25.101 (C)(5)(A)
1023799 | T441 LCRA Crane-Motorman TL Addition (T441) [Motorman Substation Addition - 1021552] | Upton, Crane | Construct a 3-breaker ring bus cut in to the existing T441 Crane East to Upton 138-kV transmission line. | 2022-02-07 | 2022-06-09 | 2022-06-29 |  | 16000 |  |  | 100 | 138 | 138 | 12.16 | 1233.6 Yukon ACSS/TW & Single | Concrete Pole | Centerline; 80 | 30.14 | Centerline; 80 | n/a | 25.101 (C)(5)(A)
1023831 | Wingarten TL Addition [Wingarten Substation Upgrade - 1022733] | Zavala | Increase transmission service reliability to the Wingarten Substation. Reroute the existing line tap of the La Pryor-Turtle Creek TL from its current configuration to a newly installed AEP owned box structure. | 2020-12-14 | 2020-12-18 | 2020-12-16 |  | 600000 |  |  | 100 | 69 | 138 | 0.05 | 795 kcmil ACSR (26/7), one conductor/phase | Concrete pole | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B) | work within substation
1022221 | T635 TL Addition [LCRA Fiber Backbone FY20 - 1021196] | Burnet, Llano | Increase the reliability of the fiber network by replacing deteriorated OPGW and All-Dielectric Self -Supporting (ADSS) fiber to improve telecommunications system reliability. | 2021-09-16 | 2022-05-06 | 2022-05-06 |  | 821000 |  |  | 100 | 138 | 138 | 12.15 | Single 795 ACSR Drake | Steel Monopole | Centerline | 12.15 | n/a | n/a | 25.101 (C)(5)(B)
1021471 | Waller - Chappell Hill TL Addition (T232) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Washington, Waller | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124, T141, T199, T232, T426, and T468. | 2021-02-01 | 2021-05-16 | 2021-05-14 |  | 1088000 |  |  | 100 | 138 | 138 | 15.93 | Single 795 ACSR Drake | Wood H-Frame | Varies 75 -85 | 15.93 | n/a | n/a | 25.101 (C)(5)(B)
1021477 | Miller Creek - Mountaintop TL Addition (T426) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Blanco | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124, T141, T199, T232, T426, and T468. | 2021-09-03 | 2021-10-14 | 2021-10-14 |  | 1743000 |  |  | 100 | 138 | 138 | 4.81 | (1x) 1433 ACSS/TW Merrimack | Steel Monopole | Centerline 60 - 100 | 4.81 | n/a | n/a | 25.101 (C)(5)(B)
1023406 | Warda-Winchester (T170) TL Addition [Warda - Winchester TL Upgrade 1023202] | Fayette | Increase the transmission capacity of T170: Warda – Winchester 138-kV transmission circuit. LCRA TSC will upgrade T170: Warda - Winchester transmission line to a minimum 105 degree F ambient temperature rating of 580 MVA at 138-kV using single 1433 Merr | 2020-11-29 12:00 | 2021-05-14 | 2021-05-14 |  | 5053000 |  |  | 100 | 138 | 138 | 4.11 | 1-1433.6 ACSS/TW/MA3 "Merrimack" | Steel Pole | 100 | 4.11 | n/a | n/a | 25.101 (C)(5)(B)
1021459 | Wolf Lane - Wyldwood TL Addition (T141) [LCRA TSC Fiber Build-Out FY 2020 Telecommunications Upgrade - 1021212] | Bastrop | Increase the reliability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment for circuits T124, T141, T199, T232, T426, and T468. | 2021-03-01 | 2021-05-16 | 2021-05-13 |  | 1980000 |  |  | 100 | 138 | 138 | 5.76 | 1 x 795 Drake ACSR | steel lattice towers, wood/steel H-frame, steel monopoles | 100 | 5.76 | n/a | n/a | 25.101 (C)(5)(B)
1023950 | T-187 TL Addition [Ferguson - Wirtz TL Storm Hardening - 1023805] | Burnet, Llano | Increase the reliability of transmission facilities on the T187 Ferguson – Sherwood Shores 9.3-mile 138-kV transmission line from Ferguson Substation to Wirtz Substation. | 2021-02-01 | 2021-05-15 | 2021-05-07 |  | 3575000 |  |  | 100 | 138 | 138 | 9.4 | 795 Drake ACSR | Lattice Towers | 100 | 9.4 | n/a | n/a | 25.101 (C)(5)(B)
1020882 | Ferguson - Sherwood Shores TL Addition Storm Hardening (T187) [Ferguson - Sherwood Shores TL Storm Hardening - 1020881] | Burnet, Llano | Increase the reliability of circuit T187 on the Ferguson – Sherwood Shores 3.5-mile 138-kV transmission line from Sherwood Shores Substation to the Wirtz Split. | 2021-01-06 | 2021-05-17 | 2021-05-17 |  | 6634000 |  |  | 100 | 138 | 138 | 3.4 | 795 Drake ACSR | Steel Monopoles | centerline | 3.4 | n/a | n/a | 25.101 (C)(5)(B)
1021982 | SherWShores-Wirtz Split TL Addition (T187) [LCRA Fiber Backbone FY20 - 1021196] | Burnet, Llano | Increase the reliability of the fiber network by replacing deteriorated OPGW and All-Dielectric Self -Supporting (ADSS) fiber to improve telecommunications system reliability. | 2021-04-26 | 2021-05-14 | 2021-05-14 |  | 280000 |  |  | 100 | 138 | 138 | 3.4 | 795 Drake ACSR | Steel Monopoles | centerline | 3.4 | n/a | n/a | 25.101 (C)(5)(B)
1024927 | G-T255 FPP to Lyton Springs Structure Stress Remediation Add [GA FY 21 TSC-G-T255 Str. Stress - 1024926] | Fayette | Install new dead-end assemblies that will be connected to the cage of structure 46 on the T255 FPP to Lytton Springs transmission line. New dead-end hardware will be required with new conductor for jumpers. | 2021-01-25 | 2021-04-23 | 2021-04-23 |  | 243000 |  |  | 100 | 345 | 345 | 61.08 | Top Phase: Bundled (2) 795 Drake ACSR Middle and Bottom Phases: Bundled (2) 715.5 Redwing ACSR | Tower | 100' | 61.08 | n/a | n/a | 25.101 (C)(5)(B)
1024192 | Gilleland-Silicon Hill TL Addition (T734) [Gilleland Creek Circuit Breaker Addition - 1024005] | Travis | Upgrade 138-kV bay to breaker-and-a-half to accommodate new circuit termination. | 2021-01-04 | 2022-06-30 |  |  | 389000 |  |  | 100 | 138 | 138 | .04 | 795 ACSR | Steel DE Monopole | 80' | n/a | 80' | n/a (POI) | 25.101 (C)(5)(A)
1020865 | Clearfork-Lockhart TL Addition (T601) [Clear Fork-Lockhart TL OH - 1020864] | Caldwell | Increase the reliability and capability of circuit T601 on the Clear Fork – Lockhart transmission line | 2021-05-17 | 2021-11-20 | 2021-09-17 |  | 4649000 |  |  | 100 | 69 | 138 | 3.04 | Existing (1)4/0 ACSR "Penguin" New (2)959.6 ACSS/TW/HS "Suwannee" | Wood/Steel H-frame, Steel Monopole | Centerline (Varies) | 3.04 | 100 | n/a | 25.101 (C)(5)(B) | ROW per Easement Enhancement FY19 System Upgrade - 1019090
1020838 | Lampasas-Kempner TL Addition (T154) [Kempner Circuit Breaker Addition-1020381] | Lampasas | Increase transmission service reliability to the Kempner Substation and Lampasas Substation. Increase the reliability and capability of transmission facilities on the T154 Copperas Cove (PEC) - Lampasas 13.5-mile 138kV transmission line. | 2021-05-17 | 2021-09-05 | 2021-09-03 |  | 2529000 |  |  | 100 | 138 | 138 | 8.04 | (1)795kcmil ACSR/GA2 "Drake" | Wood & Steel H-frame, Tower and monopole | Centerline (varies) | 8.04 | n/a | n/a | 25.101 (C)(5)(A) | Additional landowners notified; Supplemental notice affidavit filed 4/15/21
1020969 | Kempner-Copperas Cove TL Addition (T721) [Kempner Circuit Breaker Addition-1020381] | Lampasas | Increase transmission service reliability to the Kempner Substation and Lampasas Substation. Increase the reliability and capability of transmission facilities on the T154 Copperas Cove (PEC) - Lampasas 13.5-mile 138kV transmission line. | 2021-05-17 | 2021-09-05 | 2021-09-03 |  | 1819000 |  |  | 100 | 138 | 138 | 5.62 | (1)795kcmil ACSR/GA2 "Drake" | Wood & Steel H-frame, Tower and monopole | Centerline (varies) | 5.62 | n/a | n/a | 25.101 (C)(5)(A)
1020856 | Clearfork-Robert Brown TL Addition (T519) [Clear Fork-Robert Brown Jr TL Overhaul - 1020855] | Caldwell | Increase the reliability and capability of circuit T519 on the Clear Fork – Robert Brown Jr 8.8-mile 69-kV transmission line. | 2021-11-15 | 2022-04-19 | 2022-04-19 |  | 7550000 |  |  | 100 | 69 | 138 | 8.75 | (2)959.6kcmil ACSS/TW/HS "Suwannee" | Steel Monopole | Centerline | 8.75 | 80 | 8.75 | 25.101 (C)(5)(B) | ROW per Easement Enhancement FY19 System Upgrade - 1019090
1025549 | F - T558 BH - Kendall TL Repair [Big Hill – Kendall Transmission Line Restoration - 1025819] | Gillespie, Kendall, Kerr, Kimble, Schleicher | February 2021 winter storm emergency repair and restoration work. | 2021-02-13 20:02 | 2021-02-26 10:26 | 2021-07-22 | 1023000 | 2004000 |  |  | 100 | 345 | 345 | 139.17 | Bundled 1926.7 kcmil ACSS/TW Cumberland | Steel Lattice | Varies | 139.17 | n/a | n/a | 25.101 (C)(3)
1025450 | F - T448 Gillspie-HSBay TL Repair [Gillespie - Horseshoe Bay Transmission Line Restoration and Upgrade - 1025920] | Gillespie, Llano | February 2021 winter storm emergency repair and restoration work. | 2021-02-17 | 2021-08-18 | 2021-02-19 | 174000 | 1118000 |  |  | 100 | 138 | 138 | 36.42 | (1)795 ACSR "Drake" | Steel Lattice | 75 Centerline | 36.42 | n/a | n/a | 25.101 (C)(3) | Additional TL repair work ongoing
1023652 | Hilltop-RR 12 TL Addition (T375) [Hilltop - Ranch Road 12 TL Upgrade - 1023190] | Hays | Increase the reliability of transmission facilities on the T375: Hilltop – Ranch Road 12 3.95-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. | 2021-09-20 | 2022-06-30 | 2022-05-18 |  | 9300000 |  |  | 99 | 138 | 138 | 3.97 | 3x1 ~ 1433.6 ACSS/TW "Merrimack" | Steel Poles | Varies | 3.97 | n/a | n/a | 25.101 (C)(5)(B)
1023723 | T699 McCarty Lane-RR 12 TL Addition [McCarty Lane - Ranch Road 12 TL Upgrade - 1023196] | Hays | Increase the reliability of transmission facilities on the T699 McCarty Lane – Ranch Road 12 6.7-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. | 2021-08-23 | 2022-06-28 | 2022-02-08 |  | 9710000 |  |  | 100 | 138 | 138 | 6.67 | 3x1 ~ 1433.6 ACSS/TW "Merrimack" | Steel Poles | Varies,100 | 6.67 | n/a | n/a | 25.101 (C)(5)(B)
1024076 | T233 TL Addition [McCarty Lane-RR 12 TL Upgrade - 1023196] | Hays, Comal | Increase the reliability of transmission facilities on the T699 McCarty Lane – Ranch Road 12 6.7-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. | 2021-08-23 | 2022-06-28 | 2022-02-08 |  | 827000 |  |  | 100 | 138 | 138 | 6.56 | 3x1 ~ 959.6 ACSS/TW "Suwannee" | Steel Poles | Varies | 6.56 | n/a | n/a | 25.101 (C)(5)(B)
1023795 | T262 TL Addition [McCarty Lane-RR 12 TL Upgrade - 1023196] | Hays | Increase the reliability of transmission facilities on the T699 McCarty Lane – Ranch Road 12 6.7-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. | 2021-08-23 | 2022-06-28 | 2022-01-07 |  | 976000 |  |  | 100 | 138 | 138 | 2.3 | 3x2 ~ 959.6 ACSS/TW "Suwannee" | Steel Poles | Varies | 2.3 | n/a | n/a | 25.101 (C)(5)(B)
1024074 | T324 TL Addition [McCarty Lane-RR 12 TL Upgrade - 1023196] | Hays | Increase the reliability of transmission facilities on the T699 McCarty Lane – Ranch Road 12 6.7-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. | 2021-08-23 | 2022-06-28 | 2022-01-07 |  | 815000 |  |  | 100 | 138 | 138 | 0.1 | 2x3 ~ 795 ACSR "Drake" | Steel Pole | Varies | 0.1 | n/a | n/a | 25.101 (C)(5)(B)
1024151 | Coronado-Fairland TL Addition (T110) [Coronado - Fairland TL Upgrade - 1023802] | Coronado | Increase the reliability of transmission facilities on the T110 Coronado – Fairland conductor by replacing 12.4 mile 138-kV transmission line of existing Condor conductor and 25 structures. | 2021-08-30 | 2022-03-11 | 2022-03-11 |  | 6492000 |  |  | 100 | 138 | 138 | 12.4 | Single 795 ACSR Drake | Lattice Towers and Steel Monopoles | 100 Centerline | 12.4 | n/a | n/a | 25.101 (C)(5)(B)
1020859 | Red Rock-Tahitian T153 TL Addition (T153) [Red Rock-Tahitian TL Upg - 1020858] | Bastrop | Increase the reliability of transmission facilities on the T153 Red Rock – Tahitian Village 12.6-mile 138-kV transmission line. | 2021-09-16 | 2022-03-31 | 2022-03-31 |  | 12818000 |  |  | 100 | 138 | 138 | 12.67 | (1)959.6 ACSS/TW/HS "Suwannee" (1) 995.0 kcmil Type 13 ACCS/TW/C7-TP (1)AFL DNO-11243 OPGW | Steel Monopole | 100 | 12.67 | n/a | n/a | 25.101 (C)(5)(B)
1020868 | TurtleCreek-VerdeCreek TL Addition (T221) [Turtle Crk-Verde Crk TL OH-1020867] | Kerr | Increase the reliability of transmission facilities on the T221 Turtle Creek – Verde Creek 10.3-mile 138-kV transmission line. | 2021-08-01 | 2022-09-26 | 2022-03-26 |  | 8851000 |  |  | 100 | 138 | 138 | 10.26 | Single 795 ACSR "Drake" & DNO-11243 OPGW & 3/8 EHS Static Wire | Steel Monopoles | 100, Meets & Bounds | 10.26 | n/a | n/a | 25.101 (C)(5)(B)
1024946 | Plum-Muldoon TL Addition (T133) [Muldoon Substation Addition - 1024679] | Fayette | New three breaker ring bus substation to provide a 138-kV line termination for a 240 MW solar generation facility. | 2022-11-18 | 2023-03-10 |  |  | 6400000 |  |  | 0 | 138 | 138 | 11.07 | (1) 959.6 ACSS/TW "Suwannee" (1) DNO-11243 (1) 3/8" EHS & (1) 3/8" HS | Steel poles, H-frames, Lattice tower | 100 | 19.64 | n/a | n/a | 25.101 (C)(5)(A)
1021249 | Coronado - Graphite Mine TL Addition (T109) [Graphite Mine CB Addition - 1020373] | Burnet, Lampasas | Increase transmission service reliability to the Graphite Mine Substation. | 2021-07-05 | 2021-11-04 | 2021-11-03 |  | 3639000 |  |  | 100 | 138 | 138 | 5.61 | Single 795 ACSR Drake & DNO-11243 OPGW & 3/8 EHS Static Wire | Steel Monopole, Concrete Monopole | 100 | 5.61 | n/a | n/a | 25.101 (C)(5)(A)
1021355 | Lampasas - Graphite Mine TL Addition (T715) [Graphite Mine CB Addition - 1020373] | Burnet, Lampasas | Increase transmission service reliability to the Graphite Mine Substation. | 2021-08-02 | 2021-11-04 | 2021-11-03 |  | 780000 |  |  | 100 | 138 | 138 | 21.93 | Single 795 ACSR Drake & DNO-11243 OPGW & 3/8 EHS Static Wire | Steel Monopole, Concrete Monopole, Lattice Tower | 100 & Centerline | 21.93 | n/a | n/a | 25.101 (C)(5)(A)
1020123 | Magnolia Mercer-Luling TL Addition (T701) [Magnolia Mercer CB Addition - 1018915] | Caldwell | Increase the reliability of substation equipment at the Magnolia Mercer Substation | 2021-10-01 | 2022-04-21 | 2022-04-21 |  | 186000 |  |  | 100 | 69 | 138 | 15.83 | (1) 795 ACSR /GA2 "Drake" Conductor (1) DNO-11243 Shield Wire | Wood H-frames, Tower | Centerline | 15.83 | n/a | n/a | 25.101 (C)(5)(B)
1019178 | Luling-Mercer TL Addition (T157) [Magnolia Mercer CB Addition - 1018915] | Caldwell | Increase the reliability of substation equipment at the Magnolia Mercer Substation | 2021-10-01 | 2022-04-21 | 2022-04-21 |  | 557000 |  |  | 100 | 69 | 69 | 15.83 | (1) 336 ACSR "Linnet" Conductor (1) 4/0 ACSR "Penguin" Shield Wire | Tower | Centerline | 15.83 | n/a | n/a | 25.101 (C)(5)(B)
1019331 | Schulenburg-Glidden TL Addition (T373) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Fayette, Colorado | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2021-11-03 | 2022-03-25 | 2022-03-25 |  | 6500000 |  |  | 100 | 138 | 138 | 7.57 | (1) 795 ACSR "Drake" (1) DNO-11243 (1) 3/8" EHS STEEL | Steel, Concrete, and Hybrid Monopoles | Blanket; 20 | 7.57 | n/a | 7.57 | 25.101 (C)(5)(B)
1023940 | Weimar-Glidden TL Addition(T704) [LCRA TSC Fiber Build Out FY19 - 1019097] | Colorado | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2022-09-15 | 2023-03-02 |  |  | 8646000 |  |  | 0 | 138 | 138 | 12.86 | (1) 795 ACSR "Drake" (1) DNO-11243 (1) 3/8" EHS STEEL | Steel, Concrete, and Hybrid Monopoles | Blanket; 20 | 12.86 | n/a | 12.86 | 25.101 (C)(5)(B)
1024827 | Cedar Canyon-HiLonesm BESS TL Addition (T741) [Cedar Canyon Circuit Breaker Addition - 1024678] | Iraan, Crockett | This project provides a point of interconnection for a new 50.6 MW Battery Energy Storage at the 345-kV Cedar Canyon Substation by adding a new bay into a double bus/double breaker configuration to accommodate the new interconnection. | 2022-04-11 | 2022-05-02 | 2022-05-02 |  | 702000 |  |  | 100 | n/a | 345 | <1mi (374ft) | Bundled 959 Suwannee | Steel Monopole | n/a | n/a | 200 X 200 plot | 200' X 200 plot | 25.101 (C)(5)(A)
1025114 | King Mountain-North McCamey TL Addition (T452) [King Mountain - North McCamey Transmission Line Relocation Project - 1024877] | Crane, Upton | Relocate and modify transmission facilities on the DC T455/T452 King Mountain – North McCamey 138kV transmission line. | 2022-01-18 | 2022-03-17 | 2022-03-17 |  | 1617000 |  |  | 100 | 138 | 138 | 10.44 | (2x) 795 ACSR Drake | Steel Poles, Concrete Poles | 80 | 10.44 | n/a | n/a | 25.101 (C)(5)(F)
1025115 | King Mountain-North McCamey TL Addition (T455) [King Mountain - North McCamey Transmission Line Relocation Project - 1024877] | Crane, Upton | Relocate and modify transmission facilities on the DC T455/T452 King Mountain – North McCamey 138kV transmission line. | 2022-01-18 | 2022-03-17 | 2022-03-17 |  | 983000 |  |  | 100 | 138 | 138 | 10.44 | (2x) 795 ACSR Drake | Steel Poles, Concrete Poles | 80 | 9 | n/a | n/a | 25.101 (C)(5)(F)
1023353 | King Mountain - Crane II TL Addition (T732) [King Mountain Substation Upgrade - 1023073] | Crane | Provide transmission service to a generator. Add a 138-kV bay and associated circuit breaker to the existing substation. | 2021-12-01 | 2023-03-01 |  |  | 2301000 |  |  | 95 | n/a | 138 | 0.13 | (1) 959.6 KCMIL ACSS "Suwannee" | Steel Monopole | n/a | n/a | 80 | 0.13 | 25.101 (C)(5)(A)
1020853 | San Marcos-Robert Brown TL Addition (T220) [Robert Brown Jr-San Marcos TL Overhaul -1020852] | Hays, Caldwell | Increase the reliability and capability of circuit T220 on the Robert Brown Jr – San Marcos 4.91-mile 69-kV transmission line. | 2022-04-19 | 2022-07-29 |  |  | 5187000 |  |  | 100 | 69 | 138 | 4.9 | (2)959.6 ACSS/TW/HS "Suwannee" (2)995.0 T13 ACSS/TW/C7-TP (1)AFL DNO-11243 | Steel Monopole | Varies | 4.9 | 100 | 4.9 | 25.101 (C)(5)(B)
1025786 | A-frame (T373) Replacement Weimar Substation [G-T373 Replace frame Weimar Sub – 1025785] | Weimar, Colorado | Replace existing T373 A-Frame at Weimar Substation | 2022-01-20 | 2022-03-25 | 2022-03-25 |  | 130000 |  |  | 100 | 138 | 138 | 7.57 | (1) 795 ACSR "Drake" (1) DNO-11243 (1) 3/8" EHS STEEL | Steel, Concrete, and hybrid monopoles, Super duty A-Frame | Varies | 7.57 | n/a | n/a | 25.101 (C)(5)(B)
1025518 | Bellville S-Glidden TL Addition (T113) [Columbus Area TL Relocation -1024945] | Colorado, Austin Counties | Relocate and modify transmission facilities on the T113 Bellville South - Gidden 69-KV transmission between structure #135 and structure #137 | 2022-02-07 | 2022-03-17 | 2022-03-17 |  | 1127000 |  |  | 100 | 69 | 69 | 31.2 | 795 ACSR Drake | Steel Poles, Lattice | 100 | 31.2 | n/a | n/a | 25.101 (C)(5)(F)
1026472 | F - T154 TL Addition [Gen Add FY22 TSC Failed Equip - 1026451] | Lampasas | Replace rusted out crossarms, insulators & add bird discouragers on STR's 4/1, 6/2, and 6/3 | 2021-07-27 | 2021-09-02 | 2021-09-02 |  | 6320.52 |  |  | 100 | 138 | 138 | 8.04 | 795 ACSR Drake | Wood H-Frame | Centerline (Varies) | 8.04 | n/a | n/a | 25.101 (C)(3)
1026476 | F-(T197)(T242) Marshall Ford-Neil Rplc [Gen Add FY22 TSC Failed Equipment - 1026451] | Travis | Emergency repair work to Str#55 on T197/T242 to "Make Safe" | 2021-08-30 | 2021-09-02 | 2021-09-02 | 364000 |  |  |  | 100 | 138 | 138 | 14.18 | (1) 795 Drake ACSR | Steel Monopoles/Lattice Towers | Varies 30-125 | 14.18 | n/a | n/a | 25.101 (C)(3)
1026818 | (T197)(T242) Str. #55 Repair Damage [1008416 - TSC Customer Billing] | Travis | Emergency repair work to Str#55 to restore/install permanent structures | 2021-10-25 | 2021-10-31 | 2021-10-31 |  | 79443 |  |  | 100 | 138 | 138 | 14.18 | (1) 795 Drake ACSR | Steel Monopoles/Lattice Towers | Varies 30-125 | 14.18 | n/a | n/a | 25.101 (C)(3)
1026811 | (T490)(T273) Str. #21/7B Repair Damage [1008416 - TSC Customer Billing ] | Hays | Emergency repair work to Str #21/7B | 2021-08-28 | 2021-08-31 | 2021-09-12 |  | 56774 |  |  | 100 | 138 | 138 | 2.78 | (1) 795 Drake ACSR | Steel Monopoles/Lattice Towers | 100 | 2.78 | n/a | n/a | 25.101 (C)(3)
1026845 | F-(T490)(T273) Goforth-Canyon Rplc [Gen Add FY22 TSC Failed Equipment - 1026451 | Hays | Emergency repair work to Str #21/7B T490/T273 to restore/install permanent structures | 2021-09-10 | 2021-09-14 | 2021-09-12 | 254000 |  |  |  | 100 | 138 | 138 | 2.78 | (1) 795 Drake ACSR | Steel Monopoles/Lattice Towers | 100 | 2.78 | n/a | n/a | 25.101 (C)(3)
1019323 | Flatonia-Schulenburg TL Addition (T112) [LCRA TSC Fiber Build Out FY19 - 1019097] | Fayette | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2021-12-01 | 2023-06-29 |  |  | 7300000 |  |  | 65 | 138 | 138 | 11.99 | (1) 795 ACSR "Drake" | Steel Poles | 100 CL/ Blanket | 11.92 | n/a | n/a | 25.101 (C)(5)(B)
1025191 | Kenedy Switch-Nordheim W TL Addition (T577) [Kennedy Switch-Nordheim West TL Overhaul - 1024845] | DeWitt, Karnes | Increase the reliability of transmission facilities on the T577 Kenedy Switch – Nordheim West 15.88-mile 138-kV transmission line. | 2022-01-14 | 2022-03-04 | 2022-02-24 |  | 277000 |  |  | 100 | 138 | 138 | 15.902 | Drake 795 ACSR, single | Concrete, Monopoles | Blanket | 15.902 | n/a | n/a | 25.101 (C)(5)(B)
1026973 | Coronado-Buchanan TL Addition (T107) [FY22 G-T107 Coronado-Buch Fbr Repl - 1026972] | Burnet | Replace existing OPGW on T107 between STR's #137 to #138A and the underground fiber from STR#138A to Buchanan Plant with updated 72-count standard all dielectric fiber cable. | 2021-12-01 | 2022-04-08 | 2022-04-08 |  | 246000 |  |  | 100 | 69 | 69 | 2.35 | (1) 795 ACSR Drake | Lattice, H-frame | M&B 190/CL100/Blanket | 2.35 | n/a | n/a | 25.101 (C)(5)(B)
1024711 | HiCross-Marshall Ford TL Addition (T142) [HiCross-Marshall Ford Transmission Line Relocation - 1024589] | Travis | Relocate LCRA TSC elements on the T142 Hi Cross – Marshall Ford 138-kV transmission line that cross Austin Energy (AEN) bus work at Barton and Salem Walk substations. | 2023-03-01 | 2023-05-15 |  |  | 1616000 |  |  | 0 | 138 | 138 | 16.5 | (1) 1433.6 ACSS/TW Merrimack | Steel Poles, Steel H-Frames, Lattice Towers | 100 | 16.5 | n/a | n/a | 25.101 (C)(5)(E)
1025540 | Kendall-Mountain Top TL Addition (T342) [Kendall - Mountain Top Fiber Restoration and Upgrade -1025820] | Blanco, Kendall | Upgrade the T342 Optical Ground Wire (OPGW) between Kendall Substation (S241) and Mountaintop (PEC) Substation (S265)to improve reliability and capacity of the subtending CREZ East Fiber Route. | 2022-02-07 | 2022-04-29 | 2022-04-27 |  | 4562000 |  |  | 100 | 138 | 138 | 43.62 | (1) 1433.6 ACSS/TW Merrimack | Steel Poles | 100 , Centerline | 43.62 | n/a | n/a | 25.101 (C)(5)(B) | The Costs associated with this project have moved from the Failed Equipment project to a Capital Improvement Project.
1027093 | F-T579 TL Add Rplc [Gen Add FY22 TSC Failed Equip - 1026451] | Dewitt | Replace insulators as necessary | 11/1/2021 | 2021-11-12 | 2021-11-12 | 121000 |  |  |  | 100 | 138 | 138 | 14.24 | (1) 795 ACSR Drake | Steel Lattice, Steel Pole | 85 | 14.24 | n/a | n/a | 25.101 (C)(3)
1026970 | F- T226 TL Add Rplc [Gen Add FY22 TSC Failed Equip - 1026451] | Gonzales | Replace insulators, shoes & dampers on structures | 2021-11-15 | 2021-11-24 | 2021-11-24 | 117000 |  |  |  | 100 | 138 | 138 | 15.11 | (1) 795 ACSR Drake | Steel Lattice | 85 | 15.11 | n/a | n/a | 25.101 (C)(3)
1026971 | F-T609 TL Add Rplc [Gen Add FY22 TSC Failed Equip - 1026451] | Dewitt | Replace dampers as necessary | 11/29/2021 | 2021-12-03 | 2021-12-03 | 34000 |  |  |  | 100 | 138 | 138 | 2.75 | (1) 795 ACSR Drake | Steel Lattice, Steel Pole | 85 | 2.75 | n/a | n/a | 25.101 (C)(3)
1025066 | Hunt-Ingram SH TL Addition (T487/T521) [Hunt - Ingram TL Storm Hardening - 1024843] | Kerr | LCRA TSC will perform a Storm Hardening on structures and conductors on the 6.4-mile Hunt – Ingram (T487) transmission line | 2022-08-22 | 2023-05-15 |  |  | 7000000 |  |  | 5 | 138 | 138 | 4.48 | (1) 959.6 ACSS SUWANNEE | Steel Monopole | Varies 60, 100 | 4.48 | n/a | n/a | 25.101 (C)(5)(B)
1025028 | HarperRd-Jack Frmn TL Addition (T368) [Harper Road - Jack Furman TL Storm Hardening - 1024842] | Kerr | LCRA TSC will perform a Storm Hardening on structures and conductors on the 6.4-mile Hunt – Ingram (T487) transmission line | 2022-08-22 | 2023-01-05 |  |  | 4500000 |  |  | 5 | 138 | 138 | 4.64 | (1) 959.6 ACSS SUWANNEE | Steel Monopole | Varies (100, 80, 20) | 4.64 | n/a | n/a | 25.101 (C)(5)(B)
1025059 | Ingram-Jack Furman Storm Hardening TL Addition (T521) [Ingram - Jack Furman TL Storm Hardening - 1024844] | Kerr | LCRA TSC will perform a Storm Hardening on structures and conductors on the 6.4-mile Hunt – Ingram (T487) transmission line | 2022-08-22 | 2023-03-15 |  |  | 3000000 |  |  | 5 | 138 | 138 | 3.25 | (1) 959.6 ACSS SUWANNEE | Steel Monopole | Varies | 3.25 | n/a | n/a | 25.101 (C)(5)(B)
1025008 | Buchanan-Buchanan CTEC TL Addition (T106) [Buchanan (CTEC) - Buchanan TL Overhaul - 1024835] | Llano County | Increase reliability of the structures and conductor | 2022-02-14 | 2022-06-06 |  |  | 7500000 |  |  | 100 | 69 | 69 | 2.8 | (1) 336.4 ACSR LINNET (1) 959.6 ACSS SUWANNEE | Steel Lattice Tower/ Steel Monopole | M&B/100 | 2.8 | n/a | n/a | 25.101 (C)(5)(B)
1025479 | Bakersfield Substation Addition [Bakersfield-Big Hill TL Addition - 1024834] | Pecos County | Upgrade substation equipment to interconnect another TSP’s 345-kV circuit from Big Hill to Bakersfield | 2022-11-01 | 2023-05-15 |  |  | 593800 |  |  | 0 | 345 | 345 | n/a | n/a | A-Frame | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B)
1025502 | Cedar Canyon Substation Addition [Bakersfield-Big Hill TL Addition - 1024834] | Crockett County | Upgrade substation equipment to interconnect another TSP’s 345-kV circuit from Big Hill to Bakersfield | 2022-03-07 | 2023-05-15 |  |  | 634000 |  |  | 8 | 345 | 345 | n/a | n/a | A-Frame | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B)
1025506 | Noelke Substation Addition [Bakersfield-Big Hill TL Addition - 1024834] | Crockett County | Upgrade substation equipment to interconnect another TSP’s 345-kV circuit from Big Hill to Bakersfield | 2022-08-01 | 2023-05-15 |  |  | 728000 |  |  | 25 | 345 | 345 | n/a | n/a | A-Frame | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B)
1025507 | Schneeman Draw Substation Addition [Bakersfield-Big Hill TL Addition - 1024834] | Schleicher County | Upgrade substation equipment to interconnect another TSP’s 345-kV circuit from Big Hill to Bakersfield | 2022-03-07 | 2023-05-15 |  |  | 960000 |  |  | 55 | 345 | 345 | n/a | n/a | A-Frame | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B)
1025509 | Big Hill Substation Addition [Bakersfield-Big Hill TL Addition - 1024834] | Schleicher County | Upgrade substation equipment to interconnect another TSP’s 345-kV circuit from Big Hill to Bakersfield | 2022-02-01 | 2023-05-15 |  |  | 1220000 |  |  | 60 | 345 | 345 | n/a | n/a | A-Frame | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B)
1026453 | Austrop-Garfield TL Addition (T182) [TL Clearance Mitigation FY22 - 1025813] | Bastrop | Strengthen structures to support clearance mitigation. | 2022-03-29 | 2022-05-10 | 2022-05-10 |  | 375000 |  |  | 100 | 345 | 345 | 8.34 | (2) 795 DRAKE ACSR | Lattice Tower | 170 | 8.34 | n/a | n/a | 25.101 (C)(5)(B)
1026454 | Garfield-Lytton Spg TL Addition (T352) [TL Clearance Mitigation FY22 - 1025813] | Bastrop | Strengthen structures to support clearance mitigation. | 2022-03-29 | 2022-05-10 | 2022-05-10 |  | 375000 |  |  | 100 | 345 | 345 | 12.31 | (2) 795 DRAKE ACSR | Lattice Tower | 170 | 12.31 | n/a | n/a | 25.101 (C)(5)(B)
1026455 | Lytton Spg-Zorn TL Addition (T246) [TL Clearance Mitigation FY22 - 1025813] | Bastrop | Strengthen structures to support clearance mitigation. | 2022-03-29 | 2022-05-10 | 2022-05-10 |  | 375000 |  |  | 100 | 345 | 345 | 23.05 | (2) 795 DRAKE ACSR | Lattice Tower | 170 | 23.05 | n/a | n/a | 25.101 (C)(5)(B)
1026445 | Austrop-Zorn TL Addition (T185) [TL Clearance Mitigation FY22 - 1025813] | Bastrop | Strengthen structures to support clearance mitigation. | 2022-03-29 | 2022-05-15 |  |  | 375000 |  |  | 100 | 345 | 345 | 43.75 | (2) 795 DRAKE ACSR | Lattice Tower | 170 | 43.75 | n/a | n/a | 25.101 (C)(5)(B)
1024943 | Harwood-Thompsonville TL Addition (T145) [Bluestem Substation Addition - 1023910] | Gonzales | Construct the new 69-kV (138-kV capable) Bluestem Substation with a 3-breaker ring bus configuration off the T145 Harwood – Thompsonville– Waelder transmission line | 2022-02-12 | 2022-06-16 | 2022-06-16 |  | 1459000 |  |  | 100 | 138 | 138 | 21.8 | (1) 795 DRAKE ACSR | Steel Monopole | 100 | 21.8 | n/a | n/a | 25.101 (C)(5)(A)
1026823 | Harwood-Bluestem TL Addition (T145) [Bluestem Substation Addition - 1023910] | Gonzales | Construct the new 69-kV (138-kV capable) Bluestem Substation with a 3-breaker ring bus configuration off the T145 Harwood – Thompsonville– Waelder transmission line | 2022-02-12 | 2022-06-16 | 2022-06-16 |  | 106000 |  |  | 100 | 138 | 138 | 13.53 | (1) 795 DRAKE ACSR | Steel Monopole | 100 | 13.53 | n/a | n/a | 25.101 (C)(5)(A)
1026825 | Bluestem-Delhi TL Addition (T748) [Bluestem Substation Addition - 1023910] | Gonzales | Construct the new 69-kV (138-kV capable) Bluestem Substation with a 3-breaker ring bus configuration off the T145 Harwood – Thompsonville– Waelder transmission line | 2022-02-12 | 2022-06-16 | 2022-06-16 |  | 139000 |  |  | 100 | 138 | 138 | 0.04 | (1) 795 DRAKE ACSR | Steel Monopole | 100 | 0.04 | n/a | n/a | 25.101 (C)(5)(A)
1026824 | Bluestem-Thompsonville (T749) TL Addition [Bluestem Substation Addition - 1023910] | Gonzales | Construct the new 69-kV (138-kV capable) Bluestem Substation with a 3-breaker ring bus configuration off the T145 Harwood – Thompsonville– Waelder transmission line | 2022-02-12 | 2022-06-16 | 2022-06-16 |  | 139000 |  |  | 100 | 138 | 138 | 8.27 | (1) 795 DRAKE ACSR | Steel Monopole | 100 | 8.27 | n/a | n/a | 25.101 (C)(5)(A)
1027198 | McNeil-Gilleland Addition (T147) [Gen Add FY22 TSC Failed Equipment - 1026451] | Travis | Repair failed conductor splice on the bottom phase | 2021-11-22 | 2021-11-24 | 2021-11-24 | 139000 |  |  |  | 100 | 138 | 138 | 7.52 | (1) 795 DRAKE ACSR | Steel Monopole, Wood Poles | 100 | 7.52 | n/a | n/a | 25.101 (C)(3)
1020862 | Lockhart - Red Rock TL Addition (T578) [Lockhart - Red Rock TL Overhaul - 1020861] | Bastrop, Caldwell | Increase the reliability of transmission facilities on the T578 Lockhart structure #301- Red Rock 11.3 mile 138-kV transmission line | 2022-09-15 | 2023-05-15 |  |  | 13500000 |  |  | 0 | 138 | 138 | 17.1 | (1) 959.6 ACSS/TW/MA3 "SUWANNEE" | Steel Monopole | 100 | 17.1 | n/a | n/a | 25.101 (C)(5)(B)
1020469 | Gonzales - Hocheim TL Addition (T542) [Gonzales - Hocheim TL Overhaul - 1020411] | Gonzales, Dewitt | Tear down and rebuild of the 19.3 mile section. Replace wood structures with concrete and steel structures and 795 ASCR "Drake" and DNO-11243 fiber. | 2022-06-15 | 2023-02-15 |  |  | 24900000 |  |  | 50 | 69 | 69 | 53.4 | (1) 2/0 QUAIL ACSR (1) 795 DRAKE ACSR | Steel Monopole | Blanket, Varies | 53.4 | n/a | n/a | 25.101 (C)(5)(B)
1027309 | Schkade Fiber TL Addition (T429) [GA FY22-Schkade Fbr Add-1027306] | Tom Green | Replace existing telecom systems used for transmission operations functionality at Schkade Substation | 2022-05-02 | 2023-05-15 |  |  | 180000 |  |  | 80 | 138 | 138 | 16.82 | (2) 795 ACSR "DRAKE" | Steel Poles | Centerline, 80 | 16.82 | n/a | n/a | 25.101 (C)(5)(B)
1024787 | Bastrop W-Split TL Addition (T410) [Bastrop West-Split T410 TL SH - 1024579] | Bastrop | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2023-04-28 |  |  | 3507000 |  |  | 0 | 138 | 138 | 2.37 | (1) 959.6 ACSS/TW/MA3 "SUWANNEE" | Steel Poles | Centerline, 100 | 2.37 | n/a | n/a | 25.101 (C)(5)(B)
1024720 | Sim Gideon-Tahitian Village TL Addition (T648) [Sim Gideon - Tahitian Village TL Storm Hardening - 1024600] | Bastrop | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2023-04-28 |  |  | 4591000 |  |  | 0 | 138 | 138 | 5.05 | (1) 959.6 ACSS/TW/MA3 "SUWANNEE" | Steel Poles | Varies, 100, 150, 200 | 5.05 | n/a | n/a | 25.101 (C)(5)(B)
1025803 | BWSplit-Sim GideonTL Addition (T410) [Sim Gideon - Tahitian Village TL Storm Hardening - 1024600] | Bastrop | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2023-04-28 |  |  | 3464000 |  |  | 0 | 138 | 138 | 4.37 | (1) 959.6 ACSS/TW/MA3 "SUWANNEE" | Steel Poles | Varies, 100, 150, 200 | 4.37 | n/a | n/a | 25.101 (C)(5)(B)
1027518 | F-T511 Zorn Addition [Gen Add FY22 TSC Failed Equipment - 1026451] | Travis, Caldwell | Repair downed shield wire between structures 46 and 47 south of Zorn Substation. | 2022-02-04 | 2022-02-04 | 2022-02-04 | 7600 |  |  |  | 100 | 345 | 345 | 71.02 | (2) SUWANNEE/ACSS/TW | Steel Lattice | Varies, 120, 200 | 71.02 | n/a | n/a | 25.101 (C)(3)
1022978 | Lockhart-Luling TL Addition (T184) [Lockhart-Luling TL Overhaul - 1022800] | Bastrop, Caldwell | Increase the reliability of transmission facilities on the T184 Lockhart structure #301 - Luling 10.9 mile 138-kV transmission line. | 2022-09-15 | 2023-05-15 |  |  | 1438000 |  |  | 0 | 138 | 138 | 11.1 | 3X1 795 ACSR Drake | Wood H-Frame | 85 & 100 | 11.1 | n/a | n/a | 25.101 (C)(5)(B)
1027414 | F-T545 TL Upgrade [Gen Add FY22 TSC Failed Equipment - 1026451] | Colorado | Replace a vertically split pole | 2022-01-24 | 2022-02-01 | 2022-02-01 | 314723 |  |  |  | 100 | 138 | 138 | 14.15 | (1) 795 ACSR Drake | Steel Pole & Steel H-Frame | Blanket | 14.15 | n/a | n/a | 25.101 (C)(3)
1027663 | Settlers Substation Addition Ph. 1 [Settlers Substation Addition -1027353] | Bastrop, Travis | Construct a temporary hard tap on the LCRA TSC's T171 Austrop to Sim Gideon and T231 Bastrop to Webberville transmission lines | 2022-12-01 | 2022-05-25 |  |  | 1393000 |  |  | 0 | (T171)(T231) 138 | (T171)(T231) 138 | (T171) 15.61 & (T231) 14.67 | (T171)(T231) 795 DRAKE ACSR (1) | (T171)(T231) Towers & Tower Poles | (T171)(T231) 125 | (T171) 15.61 & (T231) 14.67 | n/a | n/a | 25.101 (C)(5)(B)
1024727 | Antler-Bergheim TL Add (T493) [Antler-Bergheim Transmission Line Upgrade 1024576] | New Braunfels, Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2024-09-09 | 2024-12-12 |  |  | 9499000 |  |  | 0 | 138 | 138 | 7.17 | (2) 959.6 Suwannee/ACSS/TW/HS | Steel Monopole | 100 | 7.17 | n/a | n/a | 25.101 (C)(5)(B)
1024728 | Antler Flyover-Bergheim TL Add (T389) [Antler-Bergheim Transmission Line Upgrade 1024576] | New Braunfels, Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2024-09-09 | 2024-12-12 |  |  | 47554000 |  |  | 0 | 138 | 138 | 7.17 | (2) 1433.6 Merrimack/ACSS/TW/HS | Steel Monopole | 100 | 7.17 | n/a | n/a | 25.101 (C)(5)(B)
1024736 | Hays Energy-Henne Split Structure TL Addition (T389) [Hays Energy-Henne Split Transmission Line Upgrade - 1024587] | Hays, Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-09-01 | 2022-12-01 |  |  | 33708000 |  |  | 0 | 138 | 138 | 5.37 | (2) 1433.6 Merrimack/ACSS/TW/HS | Steel Monopole | 100 | 5.37 | n/a | n/a | 25.101 (C)(5)(B)
1024740 | Henne Split Structure-River Oaks Flyover TL Add (T389) [Henne-River Oaks Transmission Line Upgrade - 1024588] | Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-09-01 | 2022-12-01 |  |  | 9716000 |  |  | 0 | 138 | 138 | 2.28 | (2) 1433.6 Merrimack/ACSS/TW/HS | Steel Monopole | 100 | 2.28 | n/a | n/a | 25.101 (C)(5)(B)
1024738 | Henne-River Oaks (T237) TL Addition [Henne-River Oaks Transmission Line Upgrade - 1024588] | Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-09-01 | 2022-12-01 |  |  | 17754000 |  |  | 0 | 138 | 138 | 3.79 | (2) 959.6 Suwannee/ACSS/TW/HS | Steel Monopole | 100 | 3.79 | n/a | n/a | 25.101 (C)(5)(B)
1024743 | River Oaks Flyover-Hwy 46 Flyover TL Add (389) [Highway 46-River Oaks Transmission Line Upgrade - 1024590] | Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-09-01 | 2022-12-01 |  |  | 45392000 |  |  | 0 | 345 | 345 | 8.64 | (2) 1433.6 Merrimack/ACSS/TW/HS | Steel Monopole | 100 | 8.64 | n/a | n/a | 25.101 (C)(5)(B)
1024745 | River Oaks-Hwy 46 TL Addition (T518) [Highway 46-River Oaks Transmission Line Upgrade - 1024590] | Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-09-01 | 2022-12-01 |  |  | 8465000 |  |  | 0 | 138 | 138 | 8.64 | (2) 959.6 Suwannee/ACSS/TW/HS | Steel Monopole | 100 | 8.64 | n/a | n/a | 25.101 (C)(5)(B)
1027017 | Clear Springs Cir Bkr Add (T752) TL OH- 1027017 [Clear Springs Generator Circuit Breaker Addition - 1026518] | Seguin, Guadalupe | Upgrade the (S454) Clear Springs Substation to facilitate an interconnection project | 2022-07-19 | 2023-10-01 |  |  | 3026000 |  |  | 34 | n/a | 138 | 0.1 | (1) 959.6 ACSS Suwannee | Steel Monopole | Substation property & POI 80' x 80' plot | Substation property | 80' x 80' plot | 80' x 80' plot | 25.101 (C)(5)(A)
1021446 | Crane Sub Add [Crane Circuit Breaker Addition - 1021215] | Crane, Crane | Provide transmission service to the Crane Substation. | 2024-08-05 | 2024-12-13 |  |  | 1185000 |  |  | 0 | n/a | 138 | 0.5 | (1) 1233.6 Yukon ACSS/TW | Steel Monopole | n/a | n/a | 100 | 0.5 | 25.101 (C)(5)(A)
1018947 | Odlaw - Uvalde TL Addition (T570) [Asphalt Mines Sub Upgrade - 1018944] | Uvalde, Kinney | Increase transmission service reliability to the Asphalt Mines Substation. | 2022-08-15 | 2023-05-15 |  |  | 447000 |  |  | 0 | 138 | 138 | 26.2 | (1) 795 DRAKE ACSS/MA2 | Steel Monopole | Undefined Centerline | 26.2 | n/a | n/a | 25.101 (C)(5)(B)
1025078 | Starcke-Wirtz TL Addition (T654) [Starcke - Wirtz TL Storm Hardening - 1024854] | Burnet | LCRA TSC will perform a Storm Hardening on the 6.7-mile Starcke – Wirtz (T654) 138-kV transmission line. | 2022-07-11 | 2023-05-15 |  | 6245000 | 2357000 |  |  | 5 | 138 | 138 | 6.65 | (1) 795 ACSR "Drake" | Steel Monopole | Varies | 6.65 | n/a | n/a | 25.101 (C)(5)(B)
1023686 | Hilltop-Strahan TL Add (T445) [Hilltop - Strahan TL Upgrade - 1023192] | Hays | Increase the reliability of transmission facilities on the T445: Hilltop – Strahan 1.25-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. | 2022-09-15 | 2023-05-15 |  |  | 4677000 |  |  | 5 | 138 | 138 | 0.82 | (1) 1433 ACSS/TW "Merrimack" | Steel Poles | Varies | 0.82 | n/a | n/a | 25.101 (C)(5)(B)
1024012 | Fayetteville - Salem TL Addition (T177) [Fayetteville - Salem Transmission Line Upgrade - 1023804] | Washington, Fayette | Rebuilding of the existing 19.3 Miles 345/138 KV Double Circuit TL T177 & T211 from Fayetteville Substation to the Salem Substation. | 2022-07-05 | 2023-05-15 |  |  | 77800000 |  |  | 28 | 138 | 138 | 19.34 | (1) 959.6 ACSS/TW HS "SUWANNEE" | Steel Poles | 85-100 | 19.34 | n/a | n/a | 25.101 (C)(5)(B)
1024013 | FPP Yrd 1 - Salem TL Addition (T211) [Fayetteville - Salem Transmission Line Upgrade - 1023804] | Washington, Fayette | Rebuilding of the existing 19.3 Miles 345/138 KV Double Circuit TL T177 & T211 from Fayetteville Substation to the Salem Substation. | 2022-07-05 | 2023-05-15 |  |  | 62519000 |  |  | 28 | 345 | 345 | 27.45 | 959.6 ACSS/TW HS "SUWANNEE" | Steel Poles | 85-100 | 27.45 | n/a | n/a | 25.101 (C)(5)(B)
1023873 | Fairland-Lago Vista TL Addition (T414) [Fairland -Lago Vista TL Upgrade 1023803] | Travis, Burnet | Increase the reliability of transmission facilities on the T414 Fairland – Lago Vista 21-mile 138-kV transmission line by replacing the existing Condor conductor. | 2022-08-01 | 2023-05-15 |  |  | 26962000 |  |  | 0 | 138 | 138 | 21.04 | (1) 795 ACSR "Drake" | Steel Towers & Galvanized Steel Pole | 100 | 21.04 | n/a | n/a | 25.101 (C)(5)(B)
1026437 | Eckert-Nebo TL Addition (T126) [Eckert Power Transformer Upgrade - 1025306] | Gillespie | Increase the reliability of substation equipment at the Eckert Substation. | 2024-02-06 | 2023-04-25 |  |  | 89000 |  |  | 0 | 69 | 138 | 0.7 | (1) 795 ACSR "Drake" | Steel Poles | 100 | 0.7 | n/a | n/a | 25.101 (C)(5)(B)
1026439 | Sandstone Mtn-Gillespie TL Addition (T130) [Eckert Power Transformer Upgrade - 1025306] | Gillespie, Llano | Increase the reliability of substation equipment at the Eckert Substation. | 2024-02-06 | 2023-05-11 |  |  | 428000 |  |  | 0 | 69 | 138 | 36.33 | (1) 959 SUWANNEE ACSS | Steel H-Frames | 100 | 36.33 | n/a | n/a | 25.101 (C)(5)(B)
1025850 | Ferguson-Sherwood TL Addition (T187) [Starcke-Wirtz TL Storm Hardening - 1024854] | Burnet | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2024-05-15 |  |  | 57000 |  |  | 5 | 138 | 138 | 9.35 | (1) 795 ACSR "Drake" | Steel Poles and Lattice Towers | Varies | 9.35 | n/a | n/a | 25.101 (C)(5)(B)
1025852 | Marble F-Granite Mtn TL Addition (T195) [Starcke-Wirtz TL Storm Hardening - 1024854 | Burnet | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2024-05-15 |  |  | 52000 |  |  | 5 | 138 | 138 | 4.08 | (1) 795 ACSR "Drake" | Steel Poles and Lattice Towers | Varies | 4.08 | n/a | n/a | 25.101 (C)(5)(B)
1025851 | Ferguson-GraniteMtn TL Addition (T376) [Starcke-Wirtz TL Storm Hardening - 1024854 | Burnet | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2024-05-15 |  |  | 54000 |  |  | 5 | 138 | 138 | 5.75 | (1) 795 ACSR "Drake" | Steel Poles and Lattice Towers | Varies | 5.75 | n/a | n/a | 25.101 (C)(5)(B)
1026089 | Wirtz-Burnet TL Addition (T218) [Starcke-Wirtz TL Storm Hardening - 1024854 | Burnet | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2024-05-15 |  |  | 52000 |  |  | 5 | 138 | 138 | 16.08 | (1) 795 ACSR "Drake" | Steel Poles and Lattice Towers | Varies | 16.08 | n/a | n/a | 25.101 (C)(5)(B)
1025012 | Buchanan CTEC-Pitsburg TL Addition (T267) [Buchanan (CTEC) - Pitsburg TL Overhaul - 1024836] | Llano County | Overhaul T267 to increase reliability of the structures and conductor | 2022-08-04 | 2023-06-30 |  |  | 20518000 |  |  | 11 | 69 | 69 | 14.49 | (1) 336.4 ACSR "LINNET" (1) 4/0 ACSR "PENGUIN" (1) 959.6 ACSS/TW/MA3 "SUWANNEE" (1) 4/0 ACSR "PENGUIN" (1) 959.6 ACSS/TW/MA3 "SUWANNEE" | Steel Lattice & Steel Poles | 100 | 14.49 | n/a | n/a | 25.101 (C)(5)(B)
1026798 | Chief Brady TL Addition (T378) [Chief Brady Substation Upgrade – 1025303] | Williamson | Chief Brady Substation will be upgraded to increase the bus rating and replace equipment identified as obsolete. The substation upgrade will also install Tier 3 Physical Security Measures | 2022-08-08 | 2023-04-03 |  |  | 551800 |  |  | 27 | 138 | 138 | 5.12 | 795 ASCR Drake, single | Steel H-frames, Steel Poles, Steel Lattice | Varies, 80 - 100 | 5.12 | n/a | n/a | 25.101 (C)(5)(B)
1027302 | T336 Fiber Replacement Project [PI Switch-Loop 337 Fiber Restoration - 1027886] | Comal | Replace and restore OPGW fiber on T336 | 2022-01-10 | 2022-05-13 | 2022-05-13 | 1800000 |  |  |  | 100 | 138 | 138 | 3.5 | (1) 959.6 ACSS/TW/M3A “SUWANNEE” | Concrete Poles | n/a | 3.5 | n/a | n/a | 25.101 (C)(3)
1024072 | Lockhart-Red Rock TL Addition (T578/T184) [Lockhart-Split TL Upgrade - 1023809] | Bastrop, Caldwell | Increase the reliability and capability of transmission facilities on the T184 Lockhart – Luling and T578 Lockhart – Red Rock 5.7-mile 138-kV double-circuit section of transmission line from Lockhart Substation to structure #75 (previously structure #301). | 2023-02-01 | 2023-05-15 |  |  | 5469000 |  |  | 0 | 138 | 138 | 5.7 | (1) 959.6 ACSS/TW/M3A “SUWANNEE” | Steel Poles | 85 | 5.7 | n/a | n/a | 25.101 (C)(5)(B) | Parent Project Budget had been utilized in previous report. Updated to Sub-Project Final Estimated Cost
1023899 | Lockhart - Luling TL Addition (T184) [Lockhart-Split TL Upgrade - 1023809] | Bastrop, Caldwell | Increase the reliability and capability of transmission facilities on the T184 Lockhart – Luling and T578 Lockhart – Red Rock 5.7-mile 138-kV double-circuit section of transmission line from Lockhart Substation to structure #75 (previously structure #301). | 2023-02-01 | 2023-05-15 |  |  | 2385000 |  |  | 0 | 138 | 138 | 5.7 | (1) 959.6 ACSS/TW/M3A “SUWANNEE” | Steel Poles | 85 | 5.7 | n/a | n/a | 25.101 (C)(5)(B) | Parent Project Budget had been utilized in previous report. Updated to Sub-Project Final Estimated Cost
1027616 | Muldoon-Flatonia TL Addition (T739)[Muldoon Substation Addition - 1024679] | Fayette | New three breaker ring bus substation to provide a 138-kV line termination for a 240 MW solar generation facility. | 2022-11-18 | 2023-03-10 |  |  | 207000 |  |  | 0 | 138 | 138 | 8.6 | (1) 959.6 SUWANNEE ACSS/TW | Steel Pole, Steel H-frame | 100; Centerline | 8.6 | n/a | n/a | 25.101 (C)(5)(A)
1027617 | Muldoon-7V Slr Ranch TL Addition (T740)[Muldoon Substation Addition - 1024679] | Fayette | New three breaker ring bus substation to provide a 138-kV line termination for a 240 MW solar generation facility. | 2022-11-18 | 2023-03-10 |  |  | 188000 |  |  | 0 | n/a | 138 | 0.02 | (1) 959.6 SUWANNEE ACSS/TW | Steel Pole | n/a | n/a | 100 | 0.02 | 25.101 (C)(5)(A)
1024297 | Hornsby TL Addition (T511) [Hornsby Substation Addition - 1023852] | Travis | Provide Transmission service to a load serving substation | 2022-09-26 | 2023-04-15 |  |  | 10700000 |  |  | 3 | 345 | 345 | 57.15 | (2) 959.6 SUWANNEE ACSS/TW | Lattice Towers | Varies | 57.15 | 120 | 0.15 | 25.101 (C)(5)(A) | Parent Project Budget had been utilized in previous report. Updated to Sub-Project Final Estimated Cost
1024549 | Hornsby TL Addition (T738) [Hornsby Substation Addition - 10235852] | Austin/Travis | Provide Transmission service to a load serving substation | 2022-09-26 | 2023-04-15 |  |  | 2500000 |  |  | 3 | 345 | 345 | 14.22 | (2) 959.6 SUWANNEE ACSS/TW | Lattice Towers | Varies | 14.22 | 120 | 0.15 | 25.101 (C)(5)(A) | Parent Project Budget had been utilized in previous report. Updated to Sub-Project Final Estimated Cost
1024783 | Brenham-Hwy 36 TL Addition (T468) [Flood Mitigation FY 2022 System Upgrade - 1024586] | Brenham/ Washington | Reduce the risk of erosion and flooding to transmission facilities | 2023-01-22 | 2023-03-22 |  |  | 130000 |  |  | 0 | 138 | 138 | 2.29 | (1) 959.6 SUWANNEE ACSS/TW | Concrete H-Frame and Concrete Monopole | 75 | 2.29 | n/a | n/a | 25.101 (C)(5)(B)
1024785 | Gilleland-Clear Spr TL Addition (T511)[Flood Mitigation FY 2022 System Upgrade - 1024586] | Manor/Travis | Reduce the risk of erosion and flooding to transmission facilities | 2022-12-22 | 2023-02-22 |  |  | 2914000 |  |  | 0 | 345 | 345 | 71 | (2) 959.6 SUWANNEE ACSS/TW | Towers, Poles & H-Frames | 120; 125 | 71 | n/a | n/a | 25.101 (C)(5)(B)
1027544 | Crane - Upton TL Addition (T441) [Crane East Substation Upgrade - 1026913] | Upton | Install circuit breakers and capacitor banks at Crane East Substation | 2022-10-17 | 2023-05-15 |  |  | 1800000 |  |  | 0 | 138 | 138 | 27 | (1) 1233.6 YUKON/TW/MA2 | Steel Pole Dead ends/Delta braced post steel pole tangents | Centerline | 27 | n/a | n/a | 25.101 (C)(5)(B) | Parent Project Budget had been utilized in previous report. Updated to Sub-Project Final Estimated Cost
1024797 | Esperanza - Boerne TL Add (T657) [Boerne-Esperanza TL Upgrade -1024583 ] | Kendall | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-12-01 | 2024-05-25 |  |  | 13679000 |  |  | 0 | 138 | 138 | 3.9 | (2) 959 ACSS/TS Suwannee | Steel Monopole | 35 / 70 / 85 / 100 / Undefined | 3.9 | n/a | n/a | 25.101 (C)(5)(B)
1024795 | Esperanza Bypass-Boerne Split Structure TL Add (T656) [Boerne-Esperanza TL Upgrade -1024583 ] | Kendall | This project will Increase the reliability of the transmission facilities by replacing aging conductor | 2022-12-01 | 2024-05-25 |  |  | 12428000 |  |  | 0 | 345 | 345 | 1.5 | (2) 1433 ACSS/TW Merrimack | Steel Monopole | 85' / 100' | 1.5 | n/a | n/a | 25.101 (C)(5)(B)
1024805 | Fair Oaks Flyover-Esperanza Bypass TL Add (T656) [Esperanza-Fair Oaks TL Upgrade - 1024585] | Comal, Kendall | This project will increase the reliability of the transmission facilities by replacing aging conductor. | 12/1/2022 |  |  |  | 22634000 |  |  | 0 | 345 | 345 | 4.36 | (2) 1433 ACSS/TW Merrimack | Steel Monopole | 75' / 100' | 4.36 | n/a | n/a | 25.101 (C)(5)(B)
1024732 | Bergheim-Fair Oaks TL Addition (T238) [Bergheim-Fair Oaks Ranch Transmission Line Upgrade -1024581] | Comal, Kendall | This project will increase the reliability of the transmission facilities by replacing the aging conductor. | 12/1/2022 |  |  |  | 7653000 |  |  | 0 | 138 | 138 | 4.08 | (2) 959 ACSS/TS Suwannee | Steel Monopole | 100' | 4.08 | n/a | n/a | 25.101 (C)(5)(B)
1024733 | Bergheim-Fair Oaks Flyover TL Addition (T656) [Bergheim-Fair Oaks Ranch Transmission Line Upgrade -1024581] | Kendall | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-12-01 | 2025-05-15 |  |  | 20000000 |  |  | 0 | 345 | 345 | 4.08 | (2) 1433 ACSS/TW Merrimack | Steel Monopole | 100' | 4.08 | n/a | n/a | 25.101 (C)(5)(B)
1024799 | Boerne-Welfare TL Addition (T228) [Boerne Split-Welfare TL Upgrade - 1024582] | Kendall | This project will Increase the reliability of the transmission facilities by replacing aging conductor | 2022-12-01 | 2025-05-15 |  |  | 15800000 |  |  | 0 | 138 | 138 | 9.51 | (2) 959 ACSS/TS Suwannee | Steel Monopole | 35 / 70 / 85 / 100 / Undefined | 9.51 | n/a | n/a | 25.101 (C)(5)(B)
1024801 | Boerne Split Structure-Welfare Flyover (T656) [Boerne Split-Welfare TL Upgrade - 1024582] | Kendall | This project will Increase the reliability of the transmission facilities by replacing aging conductor | 2022-12-01 | 2025-05-15 |  |  | 39061000 |  |  | 0 | 345 | 345 | 7.25 | (2) 1433 ACSS/TW Merrimack | Steel Monopole | 85/100 | 7.25 | n/a | n/a | 25.101 (C)(5)(B)
1026324 | Bellville - Hwy. 36 TL Addition (T467) [Containment Structures Transmission Line Upgrade 1025812] | Washington, Austin | Containment structures installed along transmission line(s) will improve system reliability | 2022-10-15 |  |  |  | 2419000 |  |  | 0 | 138 | 138 | 13.11 | (1) 959.6 ACSS/TW "SUWANNEE" | Steel Poles and Steel H-Frames | CL width undefined | 13.11 | n/a | n/a | 25.101 (C)(5)(B)
1024984 | Headwaters-Doss TL Addition (T508) [Mountain Home Substation Addition 1024902] | Gillespie | Relocate T508 to cut in to the new Headwaters Substation. LCRA TSC acquired T508 from CTEC. | 2022-11-01 | 2023-01-31 |  |  | 584000 |  |  | 0 | 69 | 69 | 14.1 | (1) 4/0 ACSR "PENGUIN" | Wood Poles | Blanket | 14.1 | n/a | n/a | 25.101 (C)(5)(B)
1028700 | F-T130 TL Addition | Gillespie | Replacing T130 structures burned by the Big Sky wildfire crossing ROW on 8/2/2022 | 8/3/2022 |  |  | 31000 |  |  |  | Ongoing | 69 | 69 | 36.26 | (1) 4/0 ACSR "PENGUIN" (1) 211.3 ACSR "COCHIN" (1) 959 ACSS "SUWANNEE" (1) 336.4 ACSR/GA2 "LINNET" (1) 795 ACSR/GA2 "DRAKE" | Wood H-Frames, Wood Poles, Steel Poles & Steel Lattice | 100 | 36.26 | n/a | n/a | 25.101 (C)(3)
1024803 | Fair Oaks - Esperanza TL Add (T503) [Esperanza-Fair Oaks TL Upgrade - 1024585] | Kendall | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-12-01 | 2024-05-15 |  |  | 9625000 |  |  | 0 | 138 | 138 | 4.36 | (2) 959 ACSS/TS Suwannee | Steel Monopole | 75' / 100 | 4.36 | n/a | n/a | 25.101 (C)(5)(B)
1024742 | Bastrop W-Bluebonnet (T516) TL Addition [Bastrop West-Bluebonnet (T516) TL Relocation - 1024616] | Bastrop | Relocate T516 within existing ROW to accommodate TxDOT widening of State Hwy. 71 | 2023-01-09 | 2023-03-30 |  |  | 1891000 |  |  | 0 | 138 | 138 | 6.1 | (1) Drake 795 ACSR | STEEL MONOPOLES & WOOD H-FRAME | 100 | 6.1 | n/a | n/a | 25.101 (C)(5)(F)
1027512 | Hornsby-Giga Tx En TL Addition (T755) [Hornsby Circuit Breaker Addition - 1027350] | Travis | Provide a point of interconnection for a new battery energy storage system at the 345-kV Hornsby Substation by adding an additional breaker-and-a-half bay to accommodate the new interconnection | 2022-12-01 | 2023-04-15 |  |  | 1124000 |  |  | 0 | n/a | 345 | 0.06 | (2) 959 ACSS/TW SUWANNEE | Steel Poles | n/a | n/a | 120 | 0.06 | 25.101 (C)(5)(A)
1027241 | Dimmit-Rosita Creek TL Addition (T697) [Containment Structures Transmission Line Upgrade 1025812] | Dimmit and Maverick | Containment Structures installed to improve system reliability | 2022-12-12 | 2023-02-24 |  |  | 5999000 |  |  | 0 | 138 | 138 | 40.18 | (1) 795 ACSR DRAKE | Steel Poles | 75-95 ft and Blanket | 40.18 | n/a | n/a | 25.101 (C)(5)(B)
1017679 | Peach-Headwaters TL Addition (T288) [T288 CTEC Transfer] [Mountain Home Substation Addition 1017394] | Gillespie County | Replace existing 69kV structures and conductor with 138 kV structures and OPGW | 2023-01-16 | 2023-12-31 |  |  | 42300000 |  |  | 0 | 69 | 138 | 21.72 | (1) 795 ACSR DRAKE | Steel Poles | Varies | 21.72 | n/a | n/a | 25.101 (C)(5)(B)