## MonthlyReportForm
Utility Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
15T62065 | Graham - Archer City 69 kV | City of Graham, Young County | Replace existing wood pole H-frames with Two (2) new single-circuit, concrete H-frame tangent structures (Str. 36/7 & 36/8). | 2021-12-04 | 2021-12-20 | 2021-12-20 | 266076 | 253850 |  |  | 100 | 69 | na | 0.39 | 4/0 ACSS | Concrete H-frames | 100 | 0.38826 | na | na | 25.101(c)(5)(B)
0PT04098 (M3211) | Roanoke to Coppell (BEC) 138 kV Line: Cut-In at Vineyard Switch (West) | City of Grapevine, Tarrant County | Separate and terminate the Roanoke Switch - Euless 138 kV Line to establish the new Vineyard Switch. | 2021-12-12 | 2021-12-18 | 2021-12-18 | 400262 | 907000 |  |  | 100 | 138 | 138 | 0.13 | 1926.9 ACSS/TW | Steel Poles | na | na | Varies | 0.13 | 25.101(c)(5)(B)
0PT04329 (R8444) | Installation for Canyon Wind POI, Scurry County South Switch-Canyon Wind 138 kV Line | City of Dunn, Scurry County | Installation with new single-circuit, steel monopole dead end structures. The installation is at the request of the Canyon Wind. | 2021-07-22 | 2023-02-01 |  | 1412752 | 1483494 |  |  | 99 | na | 138 | 0.28 | 959 ACSS/TW Suwannee | Steel Monopole Structures | na | na | Varies | 0.28 | 25.101(c)(5)(A)
0PT04105 0PT41190 (M3211) | Vineyard Switch - Coppell 138kV Line: Disconnect and Rebuild Vineyard Switch to McKamy Tap | City of Grapevine, Tarrant County | Disconnect the Grapevine Junction - Coppell line section and extend to the new Vineyard Switch | 2021-07-14 | 2021-12-18 | 2021-12-18 |  | 6648486 |  |  | 100 | 138 | 138 | 1.5 | 1926.9 ACSS/TW | Steel Poles | Varies | 0.5 | Varies | 0.97 | 25.101(c)(5)(A)
0PT40715 (M3092) | Austin Ranch Sub - Josey Sub (BEPC): Construct Line | City of The Colony, Denton County | Construct a 138 kV line from Austin Ranch Substation to establish Josey Substation | 2021-08-07 | 2021-10-01 | 2021-10-01 |  | 615867 |  |  | 100 | 138 | na | 0.1 | 959.6 kcmil ACSS/TW/HS Suwannee | Steel Dead ends | na | na | 100 | 0.1 | 25.101(c)(5)(A)
0PT41144 0PT41151 0PT41155 (M5066) | Carmichael - DeCordova 138 kV Line | City of Granbury, Hood County | Connect the new Carmichael Bend Sw. Sta. to the DeCordova Sw. Station and reterminate the Mitchell Bend - DeCordova line from the existing DeCordova Sw. Sta. to the new Carmichael Bend Sw. Sta. | 2020-09-03 | 2021-06-22 | 2021-06-22 |  | 3515606 |  |  | 100 | 345 | 138 | 2.5 | 1590 kcmil ACSR 54/19 Falcon 959.6 kcmil ACSS/TW Suwannee | Steel Towers and Poles | 600 | 2.5 | na | na | 25.101(c)(5)(A)
0PT41092 | Corn Trail Switch - Brown Switch 345 kV Line: CMPC Insulator Replacement | City of Comanche, Comanche County | Replace insulators on the Corn Trail - Brown 345 kV Line. | 2020-03-25 | 2021-12-13 | 2021-12-13 |  | 2635498 |  |  | 100 | 345 | 345 | 90.2 | 2 - 1590 kcmil ACSR Falcon | Steel Lattice Towers | 160 | 45.1 | na | na | 25.101(c)(5)(B)
0PT40515 | Gainesville North Switch - Spring 138 kV Line : I-35 Relocation for TxDOT | City of Gainesville, Cooke County | Relocate structures 41/8, 41/9, 42/1, 42/2 and 42/3 adjacent to I-35 in Gainesville, TX. The relocated structures will utilize single circuit concrete or steel H-frames. | 2023-02-10 | 2023-06-30 | [5 empty] | 0 | 138 | na | 0.1 | 795 ACSR Drake | Concrete H-Frame | 100 | 0.1 | na | na | 25.101(c)(5)(F)
0PT40577 | Stone Creek Switch - Gainesville Sub 69 kV Line : I-35 Relocation for TxDOT | City of Gainesville, Cooke County | Relocate structures 4/5, 4/6, 4/7 and 4/8 adjacent to I-35 in Gainesville, TX. | 2023-03-16 | 2023-06-30 | [5 empty] | 0 | 69 | na | 0.3 | 1/0 ACSR | Concrete H-Frame | 147 | 0.3 | na | na | 25.101(c)(5)(F)
0PT41233 (M3211) | Roanoke Switch - Euless 138 kV Line: OPGW Replacement | City of Grapevine, Tarrant County | Replace the existing shield wire on the 7/8 - Grapevine Ball Street section (1.8 miles) of the Roanoke Switch - Euless 138 kV Line with 0.546” OD 48 count OPGW. Additionally, Grapevine Junction will be reconfigured by re-terminating the conductor from structure 15/10W to 15/10E. | 2022-01-14 | 2022-01-27 | 2022-01-27 |  | 495463 |  |  | 100 | 138 | 138 | 1.8 | 1926.9 ACSS/TW | Steel Poles | Varies | 1.8 | na | na | 25.101(c)(5)(A)
0PT03990 (M4131) | Cedar Hill Sw - Sorcey Road Sub - Cedar Hill Sub 138kV Line Rebuild (Phase 2) | City of Cedar Hill, Dallas County | Upgrade the 1.7-mile Cedar Hill Sub to Sorcey Road Sub 138 kV line. | 2021-10-16 | 2021-12-27 | 2021-12-27 |  | 2900084 |  |  | 100 | 138 | na | 1.7 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles | 250 | 1.7 | na | na | 25.101(c)(5)(B)
0PT03996 (M4131) | Cedar Hill Sw - Sorcey Road Sub - Cedar Hill Sub 138kV Line Rebuild (Phase 3) | City of Cedar Hill, Dallas County | Upgrade the 0.8-mile Duncanville South Loop 138 kV line. | 2021-10-05 | 2021-12-27 | 2021-12-27 |  | 2449729 |  |  | 100 | 138 | na | 0.8 | 1926.9 kcmil ACSS/TW Cumberland | Steel Poles | 75 | 0.8 | na | na | 25.101(c)(5)(B)
0PT39833 (R8540) | LCRA Crane – Crane East 138 kV Line : Manning (Hazel) POD for Concho Chickadee Neal via LCRA Motorman Switch | Upton County | Establish the point of delivery from LCRA’s Motorman Switch to Concho’s Chickadee Neal on the Crane – Crane East 138 kV (LCRA) transmission line. | 2022-06-07 | 2022-08-24 | 2022-08-24 |  | 792075.51 |  |  | 100 | 138 | na | 0.11 | 1926.9 ACSS/TW Cumberland | Steel Poles & H-Frame Switch | na | na | 100 | 0.11 | 25.101(c)(5)(A)
0PT41539 (R8526) | Owl Hills Sub - Tunstill POD 138 kV Line : Install Second Circuit | Culberson and Reeves Counties | Install second circuit to the Owl Hills - Tunstill POD 138 kV Line. | 2020-02-24 | 2021-11-23 | 2021-11-23 |  | 10258859 |  |  | 100 | 138 | na | 18.5 | 1926.9 kcmil ACSS/TW | Steel Poles | 70 | 18.5 | na | na | 25.101(c)(5)(C) | Second circuit to the 48582 Owl Hills - Tunstill POD 138 kV Line CCN.
0PT38110 (M5278) | Everman Switch - Venus Switch 345 kV Line : Reterminate at Timberview Switch | City of Everman, Tarrant County | Reterminate the Everman Switch - Venus Switch 345 kV Line from Everman Switch to new Timberview Switch. | 2021-08-26 | 2022-05-31 | 2022-05-31 |  | 6350000 |  |  | 100 | 345 | na | 0.3 | 2-959.6 kcmil ACSS/TW Suwannee | Steel Tower | 150 | 0.1 | 150 | 0.2 | 25.101(c)(5)(A)
0PT38112 (M5278) | Benbrook Switch - Everman Switch 345 kV Line : Retermination at Timberview Switch | City of Everman, Tarrant County | Reterminate the Benbrook Switch - Everman Switch 345 kV Line from the Everman Switch to new Timberview Switch. | 2021-08-26 | 2021-12-22 | 2021-12-22 |  | 3150000 |  |  | 100 | 345 | na | 0.3 | 2-959.6 kcmil ACSS/TW Suwannee | Steel Tower | 150 | 0.1 | 150 | 0.2 | 25.101(c)(5)(A)
0PT38113 0PT46408 (M5278) | Everman Switch - Cedar Hill Switch 345 kV Line : Retermination at Timberview Switch | City of Everman, Tarrant County | Reterminate the Everman Switch - Cedar Hill Switch 345 kV Line from the Everman Switch to new Timberview Switch | 2021-08-25 | 2022-05-31 | 2022-05-31 |  | 3550000 |  |  | 100 | 345 | na | 0.3 | 2-959.6 kcmil ACSS/TW Suwannee | Steel Tower | 150 | 0.1 | 150 | 0.2 | 25.101(c)(5)(A)
0PT38114 (M5278) | Everman Switch - DeCordova Switch 345 kV Line : Retermination at Timberview Switch | City of Everman, Tarrant County | Retermination the Everman Switch - DeCordova Switch 345 kV Line from Everman Switch to new Timberview Switch | 2021-08-20 | 2022-05-31 | 2022-05-31 |  | 3150000 |  |  | 100 | 345 | na | 0.3 | 2-959.6 kcmil ACSS/TW Suwannee | Steel Tower | 150 | 0.1 | 150 | 0.2 | 25.101(c)(5)(A)
0PT41810 (R984) | Allen Sw - Monticello Sw 345kV Line: Stouts Creek Cut In | City of Sulphur Springs, Hopkins County | Line work associated with connecting the 345 kV Stouts Creek Switch | 2023-09-19 | 2023-11-16 | [5 empty] | 0 | 345 | na | 35 | 2-795 kcmil ACSR Drake | Steel Tower | 170 | 35 | na | na | 25.101(c)(5)(A)
0PT41981 | Yucca Drive Switch - Northern Natural Gas 69 kV Line: Coyanosa Substation Retermination | City of Coyanosa, Pecos County | Reterminate the Coyanosa Station in the Yucca Drive Switch - Northern Natural Gas 69 kV Line. | 2021-09-15 | 2021-12-13 | 2021-12-13 |  | 1425000 |  |  | 100 | 69 | na | 0.8 | 4/0 ACSR Penguin | Steel Poles | Varies | 0.5 | Varies | 0.3 | 25.101(c)(5)(A)
18T65206 (M3047) | Renner Switch- Allen Switch/Plano Tennyson Switch 138 kV Line: Rebuild STR 11/4D - Plano Tennyson | City of Plano, Collin County | Rebuild the existing Renner - Allen/Plano Tennyson 138 kV line with double circuit, bundled conductor | 2021-08-02 | 2021-12-16 | 2021-12-16 |  | 6028557 |  |  | 100 | 138 | na | 3.4 | 2-959.6 ACSS/TW/HS Suwannee | Steel Poles | 100 | 1.7 | na | na | 25.101(c)(5)(B)
0PT42574 | China Grove Switch - Radium - Paint Creek 138 kV Line: HB 4150 Lake Stamford Crossings | City of Haskell, Haskell County | Rebuild a section of the China Grove - Radium - Paint Creek 138 kV Line. | 2021-10-18 | 2021-12-10 | 2021-12-10 |  | 7143317 |  |  | 100 | 138 | na | 1 | 636 ACSR Grosbeak | Steel Poles | 50 | 1 | na | na | 25.101(c)(5)(B)
0PT40858 | Jacksboro Switch - Krum West Switch 345 kV Line: Failed Dead End Replacements | City of Decatur, Wise County | Replace line dead-end terminals and insulator assemblies on the Jacksboro - Krum West 345 kV line. | 2020-12-04 | 2021-12-22 | 2021-12-22 |  | 590000 |  |  | 100 | 345 | na | 0.1 | 1590 kcmil ACSR | Steel Towers | 100 | 0.1 | na | na | 25.101(c)(5)(B)
17T62191 0PT39212 0PT45873 0PT45874 0PT45875 (M5155) | Handley SES - Lakewood Sub - Pantego Sub 138 kV Line: Rebuild North and South Circuits | City of Arlington, Tarrant County | Rebuild the Handley SES - Lakewood Sub - Pantego Sub North and South Circuits (Phase 1) of the Handley SES - Sherry 138 kV Line. | 2021-07-01 | 2021-12-29 | 2021-12-29 |  | 9533605 |  |  | 100 | 138 | na | 3.8 | 1926.9 kcmil ACSS/TW | Steel Poles | Varies | 3.8 | na | na | 25.101(c)(5)(B)
0PT42346 (R753) | Hutto - Round Rock - Gabriel 138 kV Line: Midnight Sub Cut- In | City of Round Rock, Williamson County | Line work associated with establishing Midnight Substation. This work is occurring on the Hutto Switch - Round Rock - Gabriel 138kV line. | 2021-06-01 | 2021-10-12 | 2021-10-12 |  | 1106338 |  |  | 100 | 138 | na | 0.4 | 795 ACSR | Wood H-Frames | 100 | 0.4 | na | na | 25.101(c)(5)(A) | Temporary work done for Midnight Sub
18T65207 (M4088) | Northaven Switch - Morrison Lane Switch 138 kV Double Circuit Line Section: Rebuild Northaven - Welch Road - Marsh Lane | City of Dallas, Dallas County | Rebuild 2.9 mile section of Northaven Switch - Morrison Lane Switch 138 kV Double Circuit Line from Northaven to Marsh Lane Sub. | 2021-08-16 | 2021-12-22 | 2021-12-22 |  | 8175427 |  |  | 100 | 138 | na | 5.8 | 1926.9 ACSS/TW | Steel Poles | 100 | 2.9 | na | na | 25.101(c)(5)(B)
0PT38695 (R463) | Waco West Switch – Waco East Switch 138kV Line: Rebuild Waco West Switch - Structure 1/8 Line Section | City of Waco, McLennan County | Rebuild the 10.6-mile Waco West Switch - Structure 1/8 138 kV line section of the Waco West Switch – Waco East Switch 138 kV Line. | 2021-02-10 | 2021-12-16 | 2021-12-16 |  | 20528867 |  |  | 100 | 138 | na | 10.6 | 1926.9 kcmil ACSS/TW | Steel Poles | 100 | 10.6 | na | na | 25.101(c)(5)(B)
0PT42378 | Handley-Liggett 138 kV: SE Connector Relocation For TxDOT | City of Fort Worth, Tarrant County | Relocation with new double circuit, steel monopole, tangent & dead end structures. | 2021-04-21 | 2022-03-02 | 2022-03-02 |  | 2474886 |  |  | 100 | 138 | na | 2 | 959 ACSS "Suwannee" (Non-Bundled) | Steel Pole | varies | 1.0021 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT42380 | Handley-Saginaw 138 kV: SE Connector Relocation For TxDOT | City of Fort Worth, Tarrant County | Relocation with new double circuit, steel monopole, tangent & dead end structures. | 2021-04-26 | 2021-11-19 | 2021-11-19 |  | 2560873 |  |  | 100 | 138 | na | 2 | 1926 ACSS "Cumberland" (Non-Bundled) & 1233 ACSS "Yukon" (Non-Bundled) | Steel Pole | varies | 0.99527 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT42381 | Handley-Richland Hills 69 kV: SE Connector Relocation For TxDOT | City of Fort Worth, Tarrant County | Relocation with new single circuit, steel monopole, tangent & dead end structures. | 2021-05-14 | 2021-11-03 | 2021-11-03 |  | 2236717 |  |  | 100 | 69 | na | 0.99 | 300 ACSR "Ostrich" (Non-Bundled) & 959 ACSS "Suwannee" (Non-Bundled) | Steel Pole | varies | 0.98902 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT40925 0PT42534 (R6097) | Eustace SE Tap - Eustace Sub 138 Kev Line : Rebuild | City of Mabank, Henderson County | Rebuild the 2.1-mile Eustace Southeast Tap - Eustace 138 kV Line Section of the Eustace Southeast Switch (RCEC) - Mabank 138 kV Line using a conductor rated for 2071A or greater. New 138 kV double-circuit structures with one circuit in place will be installed. | 2021-03-04 | 2021-11-21 | 2021-11-21 |  | 3827444 |  |  | 100 | 138 | na | 2.1 | 2- 1926.9 MCM ACSS/TW/HS "Cumberland" | Steel Pole | 100 | 2.1 | na | na | 25.101(c)(5)(B)
0PT42091 0PT42650 (R6097) | Pauline Sub - Mabank Sub 138 kV Line : Rebuild | City of Mabank, Henderson County | Rebuild the 3.4-mile Pauline Sub - Mabank Sub 138 kV Line Section of the 9.3-mile Eustace Southeast Switch (RCEC) - Mabank 138 kV Line Section using a conductor rated for 2071A or greater. New 138 kV double-circuit structures with one circuit in place will be installed. | 2021-12-01 | 2021-12-18 | 2021-12-18 |  | 6507114 |  |  | 100 | 138 | na | 3.4 | 1926 ACSS/TW Cumberland | Steel Pole & H- Frame | 50 | 3.4 | na | na | 25.101(c)(5)(B)
0PT42090 (R6097) | Eustace Sub - Pauline Sub 138 kV Line : Rebuild | City of Mabank, Henderson County | Rebuild the 3.8-mile Eustace Sub - Pauline Sub 138 kV Line Section of the 9.3-mile Eustace Southeast Switch (RCEC) - Mabank 138 kV Line Section using a conductor rated for 2071A or greater. New 138 kV double-circuit structures with one circuit in place will be installed. | 2021-09-29 | 2021-11-21 | 2021-11-21 |  | 4835000 |  |  | 100 | 138 | na | 3.8 | 1926 ACSS/TW Cumberland | Steel Pole | 100 | 3.8 | na | na | 25.101(c)(5)(B)
0PT41843 0PT41275 0PT46188 (R8308) | Big Spring Switch - Stanton East Switch 138 kV Line: Line work associated with Natural Dam Station Retermination NTUSU Big Spring Switch - Stanton East Switch 138 kV Line: Natural Dam Retirements and Modifications Only | Howard County | Reterminate the Big Spring Switch - Stanton East Switch 138 kV Line at Natural Dam Station | 2021-10-06 | 2021-12-01 | 2021-12-01 |  | 2086725 |  |  | 100 | 138 | na | 0.23 | 959 ACSS/TW | Steel Pole | 70 | 0.23 | na | na | 25.101(c)(5)(A)
0PT41736 0PT42802 (M4315) | Ennis Switch - Desoto Switch 138 kV Line: Cut In Pebble Creek Switch | City of Red Oak, Ellis County | Separate and terminate the Ennis Switch - Desoto Switch 138 kV Line to establish the new Pebble Creek Switch. | 2021-03-05 | 2021-11-04 | 2021-11-04 |  | 3163564 |  |  | 100 | 138 | 138 | 1.2 | 2 - 959.6 MCM ACSS/TW/HS “Suwannee” | Steel Pole | 100 | 0.1 | 75 | 0.5 | 25.101(c)(5)(A)
0PT39818 (M5279) | Bryan Ave Sub - Forest Hill Switch 69 kV Line : Forest Hill Switch Station Retermination | City of Fort Worth, Tarrant County | Re-terminate the Bryan Ave - Forest Hill Switch 69-kV Line into Marrs Switch. | 2021-04-21 | 2021-12-15 | 2021-12-15 |  | 413500 |  |  | 100 | 69 | na | 0.05 | 795 MCM ACSR Drake | Steel Pole | 50 | 0.05 | na | na | 25.101(c)(5)(A)
0PT41822 0PT42106 (R1721) | Elm Mott - Bosque (BEC) 138 kV Line: Rebuild Rogers Hill Sub (BEC) - Bosque Switch (BEC) | City of Elm Mott, McLennan County | Rebuild the Rogers Hill Sub (BEC) - Bosque Switch (BEC) section of the Elm Mott Switch to Bosque Switch (BEC) 138 kV Line. | 2021-04-20 | 2021-12-09 | 2021-12-09 |  | 15593878 |  |  | 100 | 138 | na | 13.7 | 959.6 MCM ACSS/TW/HS “Suwannee” | Steel Pole | 100 | 13.7 | na | na | 25.101(c)(5)(B)
0PT41119 | TxDOT SH 5 Relocation Anna Sw.-Valley Jct. 345 kV Line | City of Anna, Collin County | Relocation with new double circuit, steel monopole, tangent structures. | 2021-03-01 | 2021-06-01 | 2021-06-01 |  | 370435 |  |  | 100 | 345 | na | 0.38 | 2 -1590 ACSR Falcon | Steel Pole | 230 | 0.19 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT41124 | TxDOT SH 5 Relocation Anna Sw.-Anna 138 kV Tap Line | City of Anna, Collin County | Relocation with new double circuit, steel monopole, tangent structures. | 2021-03-10 | 2021-06-01 | 2021-06-01 |  | 267067 |  |  | 100 | 138 | na | 0.38 | 959 ACSS "Suwannee" (Non-Bundled) | Steel Pole | 230, shared | 0.19 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT42990 (M4095) | Mountain Creek Switch - Norwood Switch 138 kV Line : Install Sectionalizing Switch At TRA Tap | City of Dallas, Dallas County | Install Manually Operated, Sectionalizing Switch at TRA Tap | 2021-11-15 | 2021-12-14 | 2021-12-14 |  | 745000 |  |  | 100 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT42820 | Audelia Termination-lake Highlands 138 kV Line: Pumping Plant Replacement | City of Dallas, Dallas County | Replacing the two existing UG Transmission HPFF Pressurization Plants at lake Highland Sub with a new HPFF Pressurization Plant. | 2021-08-31 | 2021-11-15 | 2021-11-15 |  | 1021498 |  |  | 100 | 138 | na | 0 | 600 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT42409 | Lake Creek Switch - Elm Mott 138 kV Line: HB4150 Tradinghouse Creek Reservoir Lake Crossing | McLennan County | Provide a clearance upgrade from structure 1/1 thru structure 1/5 section of the Lake Creek Switch - Elm Mott 138 kV Line. | 2021-03-24 | 2021-12-14 | 2021-12-14 |  | 2718935 |  |  | 100 | 69 | 138 | 6.8 | 795 kcmil ACSR Drake | Steel Pole | 100 | 5.2 | 50 | 0.06 | 25.101(c)(5)(A) | Lake Remediation project for HB-4150
0PT40674 0PT43239 (M5222) | Forest Hill Switch - Handley Switch 69 kV Line: Convert Duval To Bryan Ave To 138 kV | City of Fort Worth, Tarrant County | Rebuild a portion of the Forest Hill Switch - Handley Switch 69 kV Line at its new terminal locations at the Duval Switch Station and at the Bryan Ave Switch Station for the 138 kV line conversion. | 2021-03-08 | 2021-12-14 | 2021-12-14 |  | 11867564 |  |  | 100 | 69 | 138 | 6.7 | 959.6 ACSS/TW "Suwannee" | Steel Poles | 50 | 4.97 | na | na | 25.101(c)(5)(B)
0PT40622 (M5222) | Forest Hill Switch - Handley Switch 69 kV Line : Line Conversion To 138 kV (Handley Switch-Duval Section) | City of Fort Worth, Tarrant County | Reterminate the Forest Hill Switch - Handley Switch 69 kV Line at its new terminal location at the Handley Switch Station and at the Duval Switch Station for the 138 kV line conversion. | 2022-10-13 | 2023-05-15 |  |  | 2993815 |  |  | 1 | 69 | 138 | 0.3 | 959.6 ACSS/TW Suwannee | Steel Poles | 50 | 0.3 | na | na | 25.101(c)(5)(B) | Upgrade to 138 kV and extend alignment to Handley 138 kV Station.
0PT43606 (R8503) | Wink Switch – Wink Sub 138 kV line: Reconductor from POI to Wink Switch for TNMP Wink Sub | Winkler County | Re-establish the point of delivery for Texas-New Mexico Power’s Wink substation on the Wink Sw. – Wink Sub 138 kV transmission line. | 2021-03-26 | 2021-06-01 | 2021-06-01 |  | 255000 |  |  | 100 | 138 | na | 0.15 | 1926 ACSS/TW | Steel Pole | Varies | 0.15 | na | na | 25.101(c)(5)(B)
0PT42008 (M4317) | Ferris Switch - Corsicana Switch 69 kV Line: Rebuild 6/96A to Gamma Substation to 138 kV | Palmer, Ellis County | Loop the Ennis Switch - Desoto Switch 138 kV Line into Palmer substation and convert the Palmer 69 kV substation to 138 kV operation. | 2021-05-26 | 2021-11-22 | 2021-11-22 |  | 3991010 |  |  | 100 | 69 | 138 | 2 | 1926.9 ACSS/TW | Steel Pole | 80 | 1 | na | na | 25.101(c)(5)(B)
19T62004 (R1735) | Everman Switch-Venus Switch 345 kV Line: High Temperature Upgrade (WEST Line) | City of Everman, Tarrant County | Replace 33 Towers to maintain NESC Clearances, while operating under high temperature | 2021-03-08 | 2021-12-09 | 2021-12-09 |  | 9750000 |  |  | 100 | 345 | na | 17.3 | 795 ACSR | Steel Tower | 150 | 17.3 | na | na | 25.101(c)(5)(A)
0PT04039 (R1735) | Everman Switch -Venus Switch 345 kV Line: High Temperature Upgrade (East Line) | City of Everman, Tarrant County | Rebuild East Circuit of the Everman Switch - Venus Switch 345kV Line for high temperature upgrade. | 2021-10-16 | 2021-12-09 | 2021-12-09 |  | 1255490 |  |  | 100 | 345 | na | 17.3 | 795 ACSR | Steel Tower | 150 | 17.3 | na | na | 25.101(c)(5)(B)
0PT43330 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 10/3 | City of Graham, Young County | Replace structure 10/3 on the Graham Switch - Tonkawa Switch 345 kV Line. | 2021-04-20 | 2021-12-03 | 2021-12-03 |  | 626485 |  |  | 100 | 345 | na | 0.2 | 795 ACSR Drake | Steel Tower | 140 | 0.2 | na | na | 25.101(c)(5)(B)
0PT42410 | Lake Creek Switch - Tradinghouse Switch 345 kV Line: HB4150 Tradinghouse Creek Reservoir Lake Crossing | McLennan County | Reconductor a section of the Lake Creek Switch - Tradinghouse Switch 345 kV Line. | 2021-03-18 | 2021-12-10 | 2021-12-10 |  | 4249522 |  |  | 100 | 345 | na | 3.6 | 2-795 ACSS/E3X/MA5 Drake | Steel Tower | 160 | 3.6 | na | na | 25.101(c)(5)(B) | Lake Remediation project for HB-4150
0PT40627 (R8523) | Andrews County South Switch - Fullerton Switch 138 kV Line : POI for Rodeo Solar Generator | Andrews County | Install one span of wire to connect the customer owned transmission line to Rodeo Solar to existing Nelson Switch. | 2023-01-01 | 2023-12-31 | [5 empty] | 0 | 138 | na | 0.03 | 1590 ACSR Falcon | Steel Pole | na | na | 60 | 0.03 | 25.101(c)(5)(A)
0PT38904 0PT39410 (M4275) | Payne Switch - Royce City 138 kV Line: Rebuild Anna Tap - Greenbrier Switch | City of Melissa, Collin County | Rebuild Anna Tap - Greenbrier Switch section of the Payne Switch - Royce City 138 kV Line. | 2021-07-28 | 2021-11-24 | 2021-11-24 |  | 17281028 |  |  | 100 | 138 | na | 9.6 | 1926.9 ACSS/TW Cumberland | Steel and Concrete Poles | Varies | 9.6 | na | na | 25.101(c)(5)(B)
0PT40829 (M5274) | Eagle Mountain Switch - Deen Switch 138 kV Line: Rebuild Rosen Heights Tap - Deen Switch | City of Saginaw, Tarrant County | Rebuild the Rosen Heights Tap - Deen Switch section of the Eagle Mountain Switch - Deen Switch 138 kV line. | 2021-08-09 | 2021-12-21 | 2021-12-21 |  | 11578310 |  |  | 100 | 138 | na | 8 | 2-959.6 ACSS/TW Suwannee | Steel Poles | Varies | 8 | na | na | 25.101(c)(5)(B)
0PT43686 (M4323) | Ferris Switch - Waxahachie OCF 69kV Line: Rebuild Ferris - Str 28/253 | City of Waxahachie, Ellis County | Rebuild the structure 17/458 to structure 28/353 section of the Ferris Switch to Waxahachie OCF 69kV Line. | 2022-06-15 | 2022-12-15 |  |  | 15856613 |  |  | 96 | 69 | na | 11.5 | 959.6 ACSS/TW Suwannee | Steel Pole, Steel Tower | Varies | 11.5 | na | na | 25.101(c)(5)(B)
0PT43332 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 27/5 | City of Throckmorton, Throckmorton County | Replace structure 27/5 with a 47506 window tower deadend. | 2021-04-20 | 2021-12-03 | 2021-12-03 |  | 606013 |  |  | 100 | 345 | na | 0.1 | 2-795 ACSR Drake | Lattice Tower | 140 | 0.1 | na | na | 25.101(c)(5)(B)
0PT43333 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 44/4 | City of Throckmorton, Throckmorton County | Replace structure 44/4 with a 47506 window tower deadend. | 2021-04-20 | 2021-12-03 | 2021-12-03 |  | 606013 |  |  | 100 | 345 | na | 0.1 | 2-795 ACSR Drake | Lattice Tower | 140 | 0.1 | na | na | 25.101(c)(5)(B)
0PT42854 | Monticello Switch - Paris Switch 345 kV Line : HB 4150 Monticello Lake Crossing | Mt Pleasant County and Titus County | This project includes reconductoring and an installation of a structure on Monticello SW - Woodard Sw 345 kV. | 2021-03-19 | 2021-11-05 | 2021-11-05 |  | 3011751 |  |  | 100 | 345 | na | 2.5 | 2-795 ACSS Drake | Lattice Tower | Varies | 2.5 | na | na | 25.101(c)(5)(B)
0PT43952 (M4271) | Parkdale Switch - Sargent Road Switch 138 kV Line : High temp upgrade | City of Dallas, Dallas County | Upgrade the Parkdale Switch – Sargent Road Switch 138 kV Line for high temperature operation. | 2021-04-21 | 2021-11-15 | 2021-11-15 |  | 600000 |  |  | 100 | 138 | na | 5 | 1233.6 ACSS/TW Yukon | Steel Tower | 200 | 5 | na | na | 25.101(c)(5)(A)
0PT43334 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 54/2 | Haskell County | Replace structure 54/2 with a 47506 window tower deadend. | 2021-04-20 | 2021-12-03 | 2021-12-03 |  | 609950 |  |  | 100 | 345 | na | 0.2 | 2- 795 ACSR | Steel Tower | 150 | 0.2 | na | na | 25.101(c)(5)(B)
0PT43338 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 35/2 | Throckmorton County | Replace structure 35/2 with a 47506 window tower deadend. | 2021-04-20 | 2021-12-03 | 2021-12-03 |  | 615170 |  |  | 100 | 345 | na | 0.2 | 2- 795 ACSR | Steel Tower | 140 | 0.2 | na | na | 25.101(c)(5)(B)
0PT42413 | Sam Switch - Tradinghouse Switch 345 kV Line: HB4150 Tradinghouse Creek Reservoir Lake Crossing | McLennan County | Modify a section of the Sam Switch - Tradinghouse Switch 345 kV Line. | 2021-09-03 | 2021-12-15 | 2021-12-15 |  | 3011242 |  |  | 100 | 345 | na | 0.8 | 2-795 ACSS/E3X/MA5 Drake | Steel Tower | 160 | 0.8 | na | na | 25.101(c)(5)(B) | Lake Remediation project for HB-4150
0PT42411 | Temple Pecan Creek/Lake Creek - Tradinghouse Switch 345 kV Line: HB4150 Tradinghouse Creek Reservoir Lake Crossing | McLennan County | Modify a section of the Temple Pecan Creek/Lake Creek - Tradinghouse Switch 345 kV Line. | 2021-09-13 | 2021-12-17 | 2021-12-17 |  | 2538911 |  |  | 100 | 345 | na | 0.6 | 2-795 ACSS/E3X/MA5 Drake | Steel Tower | 160 | 0.6 | na | na | 25.101(c)(5)(B) | Lake Remediation project for HB-4150
0PT43339 0PT43941 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 63/2 | Haskell County | Replace structure 63/2 with a 47506 window deadend. | 2021-04-26 | 2021-12-03 | 2021-12-03 |  | 564700 |  |  | 100 | 345 | na | 0.2 | 2- 795 ACSR Drake | Steel Tower | 140 | 0.2 | na | na | 25.101(c)(5)(B)
0PT42340 (R762) | Killeen Switch - Belton Station/Killeen Switch - Killeen Fort Hood Station 138 kV line: Cut In Killeen Stagecoach Sub | Bell County | Line Work Associated with establishing Stagecoach Sub approximately located near structure 1/7. | 2021-06-23 | 2021-09-20 | 2021-09-20 |  | 887921 |  |  | 100 | 138 | na | 0.8 | 1926.9 ACSS Cumberland | Steel Poles | 100 | 0.4 | na | na | 25.101(c)(5)(A)
0PT43331 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 19/2 | City of Graham, Young County | Replace structure 19/2 with a 47506 window tower deadend. | 2021-04-20 | 2021-12-03 | 2021-12-03 |  | 608000 |  |  | 100 | 345 | na | 0.2 | 795 ACSR Drake | Steel Tower | 140 | 0.2 | na | na | 25.101(c)(5)(B)
0PT43342 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 105/2 | City of Sweetwater, Fisher County | Replace structure 105/2 on the Graham Switch – Tonkawa Switch 345 kV line that crosses FM1085 in Fisher county with window tower deadend. | 2021-04-20 | 2021-12-03 | 2021-12-03 |  | 522975 |  |  | 100 | 345 | na | 0.2 | 2- 795 ACSR Drake | Steel Tower | 140 | 0.2 | na | na | 25.101(c)(5)(B)
0PT43343 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 114/3 | City of Sweetwater, Fisher County | Replace structure 114/3 on the Graham Sw. _Tonkawa Sw. 345 kV line with a window tower deadend. | 2021-04-20 | 2021-12-03 | 2021-12-03 |  | 522615 |  |  | 100 | 345 | na | 0.2 | 2- 795 ACSR Drake | Steel Tower | 140 | 0.2 | na | na | 25.101(c)(5)(B)
0PT39811 | Morgan Creek Switch - Big Spring Switch 69 kV Line : CMPC Line Hardening (Str. 46/9 - 46/11) | City of Westbrook City, Mitchell County | Rebuild the section of structures 46/ 6- 46/14 of the Morgan Switch - Big Spring Switch 69 kV line. | 2021-11-16 | 2021-12-14 | 2021-12-14 |  | 1330457 |  |  | 100 | 69 | na | 0.5 | 336 ACSR Linnet | Wood Pole | 50 | 0.5 | na | na | 25.101(c)(5)(B)
0PT43221 | Northhaven Switch-Renner Switch 138 kV: DART Relocation for Cotton Belt Knoll Trail | City of Addison, Dallas County | Relocation of structures on the Northhaven Switch-Renner Switch 138 kV line to accommodate the Cotton Belt Rail Crossing at Knoll Trail in Addison, TX. | 2021-10-11 | 2021-11-03 | 2021-11-03 |  | 385000 |  |  | 100 | 138 | na | 0.07 | 1926 ACSS/TW Cumberland | Steel Pole | varies | 0.07 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Dallas Area Rapid Transit (DART) and is 100% reimbursable by the Dallas Area Rapid Transit (DART).
0PT42680 | NW Carrollton-Hackberry Junction 345 kV: DART Relocation for Cotton Belt Cypress Waters Station | City of Coppell, Dallas County | Addition of structure T-704A on NW Carrollton-Hackberry Junction 345 kV line. | 2021-11-01 | 2021-11-12 | 2021-11-12 |  | 550007 |  |  | 100 | 345 | na | 0.23 | 2-1590 ACSR Falcon | Steel Tower | varies | 0.23 | na | na | 25.101(c)(5)(F) | Relocation is at the request of the Dallas Area Rapid Transit (DART) and is 100% reimbursable by the Dallas Area Rapid Transit (DART).
0PT43341 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 98/2 | Jones County | Replace structure 98/2 on the Graham Switch - Tonkawa Switch 345 kV Line that crosses US highway 180 W. | 2021-04-20 | 2021-12-03 | 2021-12-03 |  | 623423 |  |  | 100 | 345 | na | 0.2 | 2-795 ACSR Drake | Steel Tower | 140 | 0.2 | na | na | 25.101(C)(5)(B)
0PT42004 (M4317) | Ferris Switch - Corsicana Switch 69 kV Line: Rebuild Str. 3/2 to Rice Sub to 138 kV | City of Ennis, Ellis County; City of Rice, Navarro County | Rebuild the Ferris Switch - Corsicana Switch 69 kV Line from structure 3/2 to Rice Substation and convert to 138 kV operation. Disconnect the Ferris Switch - Corsicana Switch 69 kV Line at Ferris 69 kV Switch and Structure 3/2 near Ennis Southeast. Establish the Ennis Southeast - Rice 138 kV Line Section by converting and upgrading the 6.7-mile of Ferris Switch - Corsicana Switch 69 kV Line from Structure 3/2 to Rice Substation. | 2021-07-14 | 2021-10-20 | 2021-10-20 |  | 12023678 |  |  | 100 | 69 | 138 | 6.7 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 6.7 | na | na | 25.101(c)(5)(B)
0PT43666 (M4323) | Holliday Sub - Baylor Switch 69 kV Line : Rebuild 23 Miles | Cities of Holliday, Dundee, Baylor, Counties of Baylor, Archer | Rebuild the existing 23 mile single circuit wood pole Holliday - Baylor 69 kV line utilizing 138 kV double circuit steel poles with one circuit in place. | 2021-06-17 | 2021-11-03 | 2021-11-03 |  | 23155765 |  |  | 100 | 69 | na | 23 | 959.6 ACSS Suwannee | Steel Pole | 50 | 23 | na | na | 25.101(c)(5)(B) | Date was corrected to match actual Construction Complete and Energization date.
0PT40396 (R6132) | Sam Switch – Tradinghouse Switch 345 kV Line: Four Brothers Switch Cut In for Sun Valley Solar | Hill County | Establish the Four Brothers Switching Station on the Sam Switch - Tradinghouse Switch 345 kV line. | 2022-03-04 | 2022-04-01 | 2022-04-01 |  | 1788914 |  |  | 100 | 345 | na | 0.12 | 2 -959.6 ACSS/TW Swannee | Steel pole & Steel Towers | 170 | 0.06 | na | na | 25.101(c)(5)(A) | Date was corrected to match actual Construction Start, Construction Complete and Energization date.
0PT43644 | Collin Switch - Stone Creek Switch 138 kV Line: Prosper Substation Cut In | City of Prosper, Collin County | Cut in Prosper Substation on the Collin Switch - Stone Creek Switch 138 kV Line. | 2021-05-05 | 2021-06-18 | 2021-06-18 |  | 1149437 |  |  | 100 | 138 | na | 0.2 | 1926.9 ACSS/TW/HS Cumberland | Steel Pole | 100 | 0.2 | na | na | 25.101(c)(5)(A)
16T64146 (R6151) | Temple Substation - Little River Substation 69 kV Line: CMPC Rebuild | Bell County | Rebuild the Temple Substation - Little River Substation 69 kV Line section | 2021-08-07 | 2021-12-21 | 2021-12-21 |  | 12301430 |  |  | 100 | 69 | na | 7.5 | 959.6 ACSS/TW/HS Suwannee | Steel Pole | 50 | 7.4 | na | na | 25.101(c)(5)(B)
0PT43492 0PT44173 0PT44830 (R8563) | North Andrews Switch - Means 138 kV Line: Install Landfill POD to Re-terminate Exxon Means POD | City of Andrews, Andrews County | Establish the Landfill Point of Delivery (POD) by disconnecting the existing Exxon Means Tap from the Andrews North Sw. - Mckenzie Draw Sw. 138 kV line and connecting to the Andrews North Sw. - Fullerton Sw. 138 kV line. | 2021-09-15 | 2021-12-20 | 2021-12-20 |  | 1907266 |  |  | 100 | 138 | na | 0.4 | 959.6 ACSS/TW Swannee | Steel Poles | 50 | 0.15 | 75 | 0.37 | 25.101(c)(5)(A)
0PT43305 0PT41769 (R6119) | Waco West Switch - Temple Elm Creek Switch 138 kV Line : Moores Mill Station Cut In | City of Temple, Bell County | Cut in the Moores Mill Substation on the Waco West - Temple Elm Creek 138 kV Line. | 2021-07-06 | 2021-11-12 | 2021-11-12 |  | 1200000 |  |  | 100 | 138 | na | 0.45 | 959.6 ACSS/TW Swannee | Steel Pole | 50 | 0.16 | 100 | 0.3 | 25.101(c)(5)(A)
0PT38116 0PT39387 (M5279) | Everman Switch - Marrs Switch 138 kV Lines #3 & #4 Rebuild | City of Fort Worth, Tarrant County | Rebuild the 4.2-mile Everman Switch - Forest Hill Switch - Marrs Switch 138 kV Lines #3 & 4. | 2021-06-28 | 2021-12-15 | 2021-12-15 |  | 12305000 |  |  | 100 | 138 | na | 4.2 | 1926.9 MCM ACSS/TW/HS Cumberland | Steel Pole | 50 | 4.2 | na | na | 25.101(c)(5)(B)
0PT42829 | Trinidad Switch - Corsicana Sub 138 kV Line : HB 4150 Richland Chambers Crossing | City of Corsicana, Navarro County | Reconductoring the north circuit of the Trinidad Switch - Corsicana Sub 138 kV Line as well as installing new davit arms and raising structures in order to meet clearance. | 2021-10-07 | 2021-11-01 | 2021-11-01 |  | 503034 |  |  | 100 | 138 | na | 1.2 | 795 ACSS/TW E3X Drake | Steel Pole | 100 | 1.2 | na | na | 25.101(c)(5)(B)
0PT43597 (R8573) | Dermott Switch - Endurance Park Storage POI 138 kV Line : Install line for Endurance Park Storage POI | City of Dermott, Scurry County | Install a 138 kV Point of Interconnection (POI) for Endurance Park Storage. | 2022-01-21 | 2022-09-01 | 2022-09-01 |  | 1027784 |  |  | 100 | na | 138 | 0.2 | 1926 ACSS Cumberland | Steel Pole | 800 | 0.2 | na | na | 25.101(c)(5)(A)
0PT43340 | Graham Switch - Tonkawa Switch 345 kV Line : Replace Structure 88/3 | Jones County | Replace structure 88/3 on the Graham Switch - Tonkawa Switch 345 kV Line that crosses US highway 180 W. | 2021-04-10 | 2021-12-03 | 2021-12-03 |  | 625476 |  |  | 100 | 345 | 0 | 0.2 | 2 - 795 ACSR Drake | Steel Tower | 150 | 0.2 | na | na | 25.101(C)(5)(B)
0PT42097 0PT44856 (R8526) | Riverton Switch - Tunstill POD 138 kV Line : Install Second Circuit | Reeves County | Install second circuit to the Riverton - Tunstill POD 138 kV Line. | 2021-07-08 | 2021-11-23 | 2021-11-23 |  | 4941678 |  |  | 100 | 138 | na | 5.4 | 1926.9 kcmil ACSS/TW | Steel Poles | 70 | 5.4 | na | na | 25.101(c)(5)(C) | Second circuit to the Riverton - Tunstill POD 138 kV Line CCN.
0PT38463 (R9015) | Big Spring - Buzzard Draw 69 kV: Rebuild the line to operate at 138kV | Howard County | This project is to rebuild the 21 mile section of Big Spring to Buzzard Draw 69 kV Line. | 2021-06-01 | 2021-12-17 | 2021-12-17 |  | 25000000 |  |  | 100 | 69 | 138 | 21.3 | 959.6 ACSS/TW/HS Suwannee | Steel and Concrete Poles | 50 | 21.3 | na | na | 25.101(c)(5)(B) | Temporary work
0PT41307 0PT44855 (R8526) | Horseshoe Springs Switch - Owl Hills 138 kV Line : Install Second Circuit | Reeves County | Install a new 30-mile, 138 kV second conductor on existing double-circuit structures from Horseshoe Springs Switch to Owl Hills. | 2021-04-30 | 2021-12-17 | 2021-12-17 |  | 25700801 |  |  | 100 | 138 | na | 30 | 1926.9 ACSS/TW/HS Cumberland | Steel Pole | 70 | 30 | na | na | 25.101(c)(5)(C)
0PT44350 (M5274) | Hicks Switch - Deen Switch 138 kV Line: Replace Structure 12/1 | City of Saginaw, Tarrant County | Replace structure 12/1 on the Hicks Switch - Deen Switch 138 kV Line. | 2021-10-02 | 2021-12-20 | 2021-12-20 |  | 390000 |  |  | 100 | 138 | na | na | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | na | na | 25.101(c)(5)(B)
0PT44478 | Waxahachie Sub - S. Ennis Switch 138 kV Line : HB 4150 Bardwell Lake Crossing | City of Bardwell, Ellis County | This rebuild will involve raising the cross arms on two (2) single-circuit wood H-frame structures on Waxahachie Sub - S. Ennis Switch 138 kV Line. | 2021-12-09 | 2021-12-10 | 2021-12-10 |  | 138348 |  |  | 100 | 138 | na | 0.1 | 795 ACSR Drake | Wood H-Frames | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT43543 | Watermill Switch - Seagoville Switch 138 kV Line : Relocate Str. 3/3 and 3/1 | City of Lancaster, Dallas County | The scope of this project entails relocating structures 3/3 and 3/1 on Watermill Switch - Seagoville Switch 138 kV Line. | 2022-12-16 | 2022-12-31 | [5 empty] | 0 | 138 | na | 0.5 | 795 ACSR Drake | Steel Pole | 90 | 0.1 | na | na | 25.101(c)(5)(B)
0PT43542 | Waco West Switch - Lake Creek Switch 138 kV Line : Structure Replacement | City of Waco, McLennan County | Structure 10/10 on Waco West - Lake Creek 138 kV line will be relocated away from eroding creek by the district and erosion control guards will be installed. | 2022-03-31 | 2022-04-11 | 2022-04-11 |  | 412325 |  |  | 100 | 138 | na | 0.1 | 636 ACSR Grosbeak | Wood H-Frame | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT44753 (R8538) | Midland East Switch - Buffalo Sub 138 kV Line : Reterminate | City of Midland, Midland County | Reterminate the Midland East Switch - Buffalo Sub 138 kV Line to the Midland East Switch Station. | 2021-10-29 | 2021-11-16 | 2021-11-16 |  | 567709 |  |  | 100 | 138 | na | 0.25 | 1926.9 MCM ACSS/TW/HS Cumberland | Steel Pole | Varies | 0.25 | na | na | 25.101(c)(5)(A)
0PT44752 (R8538) | Midland East Switch - Midland County Northwest Switch 138 kV Line : Reterminate | City of Midland, Midland County | Reterminate the Midland East Switch - Midland County Northwest Switch 138 kV Line to the Midland East Switch Station. | 2021-11-11 | 2021-12-12 | 2021-12-12 |  | 1951902 |  |  | 100 | 138 | na | 0.5 | 1926.9 MCM ACSS/TW/HS Cumberland | Steel Pole | Varies | 0.5 | na | na | 25.101(c)(5)(A)
0PT44751 (R8538) | Midland East Switch - McKenzie Draw Switch 138 kV Line : Reterminate | City of Midland, Midland County | Reterminate the Midland East Switch - McKenzie Draw Switch 138 kV Line to the Midland East Switch Station. | 2021-11-17 | 2021-12-12 | 2021-12-12 |  | 1484875 |  |  | 100 | 138 | na | 0.5 | 1926.9 MCM ACSS/TW/HS Cumberland | Steel Pole | Varies | 0.5 | na | na | 25.101(c)(5)(A)
0PT44750 (R8538) | Midland East Switch - Midessa South Switch 138 kV Line : Reterminate | City of Midland, Midland County | Reterminate the Midland East Switch - Midessa South Switch 138 kV Line to the Midland East Switch Station. | 2021-11-17 | 2022-12-15 |  |  | 462521 |  |  | 99 | 138 | na | 0.25 | 1926.9 MCM ACSS/TW/HS Cumberland | Steel Pole | Varies | 0.25 | na | na | 25.101(c)(5)(A)
0PT44640 0PT44924 (R6161) | Lake Brownwood Tap - Lake Brownwood Sub 69 kV Line : Rebuild | City of Brownwood, Brown County | Rebuild the 2.3 mile Lake Brownwood Tap - Lake Brownwood Sub 69 kV Line. | 2021-08-16 | 2021-12-15 | 2021-12-15 |  | 3279939 |  |  | 100 | 69 | na | 2.3 | 959.6 ACSS/TW Suwannee | Steel Poles, Concrete Poles | Varies 35-128 | 2.3 | na | na | 25.101(c)(5)(B)
0PT44497 | Edgemere Sub - Bandera Sub 138 kV Line : Rebuild Cathodic Protection System | City of Dallas, Dallas County | Rebuild the Cathodic Protection System on the Edgemere Sub - Bandera Sub 138 kV Line. | 2021-09-13 | 2021-11-15 | 2021-11-15 |  | 274922 |  |  | 100 | 138 | na | na | 900 AL HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT44493 (R6151) | Temple Switch - Killeen Switch 345 kV Line : Relocate and Raise Str 5/2 | City of Temple, Bell County | This project is to relocate and raise Structure 5/2 on the Temple to Killeen 345 kV Line due to the Temple to Little River 69 kV Line rebuild project. | 2021-09-22 | 2021-12-03 | 2021-12-03 |  | 308432 |  |  | 100 | 345 | na | 0.1 | 795 ACSR Drake 2-959.6 ACSS/TW/HS Suwannee | Steel Tower | 250 | 0.1 | na | na | 25.101(c)(5)(B)
0PT44492 (R6151) | Bob Poague Sub - Seaton Sub 69 kV Line : Relocate and Raise Str 7/4 | City of Temple, Bell County | This project is to relocate and raise Structure 7/4 on the Bob Poague to Seaton 69 kV Line due to the Little River Road expansion project as well as the Temple to Little River 69 kV Line rebuild project. | 2021-08-04 | 2021-11-15 | 2021-11-15 |  | 125000 |  |  | 100 | 69 | na | 0.1 | 795 ACSS Drake | Steel Pole | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT44491 | North Network Sub - Bryan Sub 138 kV Line : Rebuild Cathodic Protection System | City of Dallas, Dallas County | Rebuild the Cathodic Protection System on the North Network Sub - Bryan Sub 138 kV Line . | 2021-11-29 | 2021-12-16 | 2021-12-16 |  | 446000 |  |  | 100 | 138 | na | na | 1500 AL HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT44488 | Greenville Ave Switch - Matilda Sub 138 kV Line: Rebuild Cathodic Protection System | City of Dallas, Dallas County | Rebuild the Cathodic Protection System on the Greenville Ave Switch - Matilda Sub 138 kV Line. | 2021-09-07 | 2021-11-15 | 2021-11-15 |  | 278019 |  |  | 100 | 138 | na | na | 600 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT44370 | Randol Mill - Heritage Sub 138 kV Line : OPGW Only | City of Fort Worth, Tarrant County | Install a splice box at structure 7/12. | 2021-09-20 | 2021-09-23 | 2021-09-23 |  | 203689 |  |  | 100 | 138 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT44352 | Decatur - Chico West - Oran 69 kV Line: HB4150 Lake Bridgeport Crossing | City of Chico, Wise County | Line work associated with providing additional clearance over the Lake Bridgeport crossing | 2021-10-04 | 2021-11-19 | 2021-11-19 |  | 1729170 |  |  | 100 | 69 | na | 0.5 | 959.6 ACSS/TW Suwannee | Steel Poles | 40 | 0.5 | na | na | 25.101(c)(5)(C)
0PT43222 (R4023) | Willow Creek Switch - Clear Crossing Switch 345 kV Line : Modify one circuit of a double circuit 345 kV transmission line | City of Throckmorton, Throckmorton County | Line work associated with connecting the 345 kV Tecumseh Creek Switch | 2021-10-15 | 2021-11-18 | 2021-11-18 |  | 4090000 |  |  | 100 | 345 | na | 0.3 | 2-1926.9 ACSS/TW Cumberland | Steel Pole | 0.2 | 140 | 200 | 0.3 | 25.101(c)(5)(A)
0PT42965 | Venus Sw - Gerdau Sw 138 kV Line: Install Change of Ownership Point for Gerdau’s Furnace A Circuit. | City of Midlothian, Ellis County | Install one steel deadend to serve as point of interconnection with Gerdau. | 2021-08-18 | 2022-06-23 | 2022-06-23 |  | 479147 |  |  | 100 | 138 | na | 0.1 | 795 ACSR Drake | Steel Pole | Variable | 0.1 | na | na | 25.101(c)(5)(A)
0PT42348 | Watermill to Cedar Hill 138 kV Line: Reindeer Substation Cut In | City of Lancaster, Dallas County | Line work associated with establishing Reindeer Substation | 2021-12-03 | 2021-12-10 | 2021-12-10 |  | 224289 |  |  | 100 | 138 | na | 0.1 | 1590 ACSR Falcon | Steel Poles | 250 | 0.1 | na | na | 25.101(c)(5)(A)
0PT43688 0PT43094 (R8552) | SL Telephone Road Sub - Tall City Sub 138kV Line: Rebuild | Midland County | Rebuild the Telephone Road-Tall City 138 kV Line | 2021-07-01 | 2021-12-03 | 2021-12-03 |  | 18652557 |  |  | 100 | 138 | na | 12 | 1926.9 ACSS/TW Cumberland | Steel Poles | 70 | 12 | na | na | 25.101(c)(5)(C)
0PT40576 0PT41142 | Navarro Sub - Wortham Junction 69 kV Line : CMPC Line Hardening (Str. 6/17-6/19) | Richland City, Navarro County | Rebuild a section of the Navarro – Wortham Junction 69 kV Line in Navarro County. | 2021-10-12 | 2021-11-01 | 2021-11-01 |  | 902847 |  |  | 100 | 69 | na | 0.2 | 3/0 ACSR Pigeon | Wood Pole | 50 | 0.2 | na | na | 25.101(c)(5)(B)
0PT44851 0PT46615 0PT44615 | Graham - Breckenridge 138 kV Line: Gunsolus Sub Line Connection | City of Breckenridge, Stephens County | Build new loop line section from existing Breckenridge to the new Gunsolus Switch and then back to Breckenridge. | 2021-10-12 | 2022-05-01 | 2022-05-01 |  | 1861863 |  |  | 100 | na | 138 | 0.3 | 959.6 ACSS Suwannee | Steel Pole | na | na | 100 | 0.3 | 25.101(c)(5)(A) | Project was inadvertently reported complete. Updates made to estimated finish date and percent complete.
0PT44472 (R6151) | Temple Sub - Little River Sub 69 kV Line: Reroute for Little River Road Expansion | City of Temple, Bell County | This project is to re-route and rebuild the section of line affected by the Little River Road Expansion and Blackland Road Extension projects. | 2021-08-22 | 2021-12-21 | 2021-12-21 |  | 785651 |  |  | 100 | 69 | na | 0.35 | 959.6 ACSS/TW/HS Suwannee | Steel Pole | 50 | 0.35 | na | na | 25.101(c)(5)(B)
0PT43980 (R8504) | Sand Lake Switch - TNMP's Cochise Switch 138 kV Line: Install Single Span to TNMP | Ward County | Terminate Texas-New Mexico Power’s two 138 kV lines out of Cochise Switch at Sand Lake Switch. | 2021-11-04 | 2021-12-01 | 2021-12-01 |  | 379801 |  |  | 100 | na | 138 | 0.08 | 1926 ACSS/TW Cumberland | Steel poles | 100 | 0.09 | na | na | 25.101(c)(5)(A)
0PT45010 (R8581) | Wink Basin Tap No 1 East 69 kV Line: Wink Basin Sub - Wink Gulf Tap 69 kV Section Rebuild | City of Kermit, Winkler County | Rebuild the 1.9 mile Wink Basin Sub - Wink Gulf Tap 69 kV section on the Wink Basin Tap No 1 East 69 kV line | 2021-08-03 | 2022-12-15 |  |  | 3000000 |  |  | 67 | 69 | 138 | 1.9 | 1926 ACSS/TW Cumberland | Steel Poles | 50 | 1.9 | na | na | 25.101(c)(5)(B)
0PT44327 0PT46292 (R8581) | Wink Switch - Keystone No 1 East 69 kV Line: Shifting Sands Sub - Wink Gulf Tap 69 kV Section Rebuild | City of Kermit, Winkler County | Rebuild the 12.6 mile Shifting Sands Sub - Wink Gulf Tap 69 kV section on the Wink Switch - Keystone No 1 East 69 kV line. | 2021-07-20 | 2022-12-15 |  |  | 10000000 |  |  | 93 | 69 | 138 | 12.6 | 1926 ACSS/TW Cumberland | Steel Poles | 50 | 12.6 | na | na | 25.101(c)(5)(B)
0PT44275 0PT44345 (R8452) | Horseshoe Springs Switch - Owl Hills Substation 138 kV Line : Cut-in at Drill Hole Switch | Culberson County | Tap both circuits on the Horseshoe Springs - Owl Hills double circuit 138 kV line to establish the new Drill Hole Switch. | 2021-09-12 | 2021-12-17 | 2021-12-17 |  | 2651342 |  |  | 100 | 138 | na | 0.42 | 795 ACSR Drake | Steel Poles | 70 | 0.21 | na | na | 25.101(c)(5)(A) | Oncor Station property.
0PT42385 (M4302) | Ennis Switch - Ennis Sub 138 kV Line: Retermination at Shankle Switch | City of Ennis, Ellis County | Reterminate the Ennis Switch - Ennis Sub 138kV line to its new bay position at the new Shankle Switch. | 2021-09-20 | 2021-12-01 | 2021-12-01 |  | 1499380 |  |  | 100 | 138 | na | 0.1 | 1926 ACSS/TW Cumberland | Steel Pole | 85 | 0.1 | na | na | 25.101(c)(5)(A)
0PT45129 | Eagle Mountain Switch - Bennett Road Switch 138 kV Line: CMPC Clearance Violation Remediation | City of Saginaw, Tarrant County | Replace structure 1/5 with a new tangent to remediate an existing clearance violation. | 2021-12-03 | 2021-12-10 | 2021-12-10 |  | 291870 |  |  | 100 | 138 | na | 0.3 | 795 ACSR Drake | Steel Pole | 150 | 0.3 | na | na | 25.101(c)(5)(B)
0PT44791 | Graham Plant Switch - Burwick Switch 345kV Line: HB4150 Lake Graham Crossing | Young County | Line work associated with providing additional clearance over the Lake Graham Crossing | 2021-10-06 | 2021-11-19 | 2021-11-19 |  | 1473520 |  |  | 100 | 345 | na |  |  |  | 160 | 0.4 | na | na | 25.101(c)(5)(C)
0PT44585 (R3023) | Blackwater Draw – Paleo Bess Solar 345 kV Line: Line Interconnection | Hale County | Install a new, single-circuit 345 kV transmission line from Blackwater Draw Switch station dead-end to a Point of Interconnection (“POI”) on a dead-end structure located near the Blackwater Draw Switch east property boundary. | 2022-02-10 | 2023-07-21 |  |  | 976885 |  |  | 99 | na | 345 | 0.2 | 2-959.6 ACSS/TW Suwannee | Steel Pole | na | na | 150 | 0.2 | 25.101(c)(5)(A)
0PT44302 | Randol Mill Sub - Randol Mill Tap East 138 kV Line : OPGW Only | City of Fort Worth, Tarrant County | Install OPGW and 4 splice boxes from Randol Mill Tap East to Randol Mill Sub. Splice boxes to be installed at Randol Mill Tap East, structure 1/3, structure 2/4 and Randol Mill Sub. | 2021-10-29 | 2021-11-09 | 2021-11-09 |  | 1091329 |  |  | 100 | 138 | na | 2 | 795 ACSR Drake | Steel Tower | 160 | 2 | na | na | 25.101(c)(5)(A)
0PT43960 0PT46326 (R985) | Commerce Switch - Scatter Branch Sub 138 kV Line: Rebuild and convert 69 kV Line to 138 kV operation | City of Commerce, Hunt County | Rebuild a section from Commerce Switch to Scatter branch (Str 56/3) of the Commerce Switch - Royse Switch 69 kV Line and convert to 138 kV operation. | 2021-12-17 | 2022-05-09 | 2022-05-09 |  | 12433688 |  |  | 100 | 69 | 138 | 7.4 | 959.6 ACSS/TW Suwannee | Steel Poles | 70 | 7.4 | na | na | 25.101(c)(5)(B)
0PT43730 (R4027) | Krum West Switch – Belltown Power 345 kV Line: BT Noble Solar Generator Interconnect | City of Krum, Denton County | Establish a Point of Interconnect (POI) to Belltown Power’s Noble Solar on the Krum West Switch - Belltown Power POI 345 kV Line. | 2021-09-08 | 2021-12-21 | 2021-12-21 |  | 700000 |  |  | 100 | na | 345 | 0.2 | 2-1926.9 ACCS/TW Cumberland | Steel Tower | 0 | 0 | 120 | 0.2 | 25.101(c)(5)(A)
0PT43151 | Graham Switch - Barton Switch 138 kV Line : CMPC Crossarm Replacement | City of Graham, Young County | Replace cross arms on Graham Switch - Barton Switch 138 kV line | 2021-09-17 | 2021-11-01 | 2021-11-01 |  | 1262315 |  |  | 100 | 138 | na | 14.4 | 636 ACSR Grosbeak | Wood H-Frame | 50 | 14.4 | na | na | 25.101(c)(5)(B)
0PT43007 (R9015) | Big Spring Switch - Big Spring West Sub 138 kV Line : Big Spring CRMWD Cut In | City of Big Spring, Howard County | Cut in the new 138 kV Big Spring CRMWD station into the Big Spring-Big Spring West 138 kV Line. | 2021-10-09 | 2021-11-19 | 2021-11-19 |  | 304025 |  |  | 100 | 138 | na | 0.1 | 959.6 ACSS/TW/HS Suwannee | Steel Poles | 65 | 0.1 | na | na | 25.101(c)(5)(A)
0PT42119 (M4302) | Trinidad Switch - Liggett Switch 138 kV Line: Reterminate section from Montfort Switch - Ennis Switch 138 kV into Shankle Switch | City of Ennis, Ellis County | Reterminate the Montfort Switch - Ennis Switch 138 kV Line and Desoto Switch - Ennis Switch 138kV Line at Shankle Switch | 2021-09-14 | 2021-12-01 | 2021-12-01 |  | 2713267 |  |  | 100 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole, Wood H-Frame | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT41823 (M4302) | Ennis West Switch - Ennis Switch 138 kV Line: Retermination at Shankle Switch | City of Ennis, Ellis County | Reterminate the Ennis Switch - Ennis West Switch at 138 kV Line at Shankle Switch | 2021-08-31 | 2021-12-01 | 2021-12-01 |  | 1101508 |  |  | 100 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 0.1 | na | na | 25.101(c)(5)(A)
0PT40680 (M5222) | Forest Hill Switch - Handley Switch 69 kV Line: Convert Bryan Ave Tap to Forest Hill to 138 kV | City of Fort Worth, Tarrant County | Reterminate the Forest Hill Switch - Handley Switch 69 kV Line at its new terminal location at the Marrs Switch Station | 2023-04-26 | 2023-05-15 | [5 empty] | 0 | 69 | 138 | 0.5 | 2- 795 ACSR Drake | Steel Pole | 100 | 0.5 | na | na | 25.101(c)(5)(C)
0PT38085 (M364) | Plano West Switch - Richardson 138 kV Line : Rebuild | City of Richardson, Dallas County | Upgrade the 3-miles Plano West Switch - Richardson 138 kV Line | 2022-03-01 | 2022-06-20 | 2022-06-20 |  | 12107865 |  |  | 100 | 138 | na | 3 | 2 - 1926.9 ACSS/TW/HS Cumberland | Steel Pole | 100 | 3 | na | na | 25.101(c)(5)(C)
0PT04017 (M4250) | Cedar Hill Switch 138 kV Line - Camp Wisdom 138 kV Line (Camp Wisdom - Love Bird Tap) | City of Cedar Hill, Dallas County | Upgrade the 4-mile Love Bird Tap - Camp Wisdom 138 kV Line | 2021-09-23 | 2021-12-16 | 2021-12-16 |  | 6448027 |  |  | 100 | 138 | na | 4 | 2-959.6 ACSS/TW/HS Suwanee | Steel Pole | 80 | 4 | na | na | 25.101(c)(5)(C)
15T64033 0PT47317 | Mary Avenue 138 kV Line Cut-in | City of Waco, McLennan County | Line Work Associated with Mary Avenue Substation | 2023-01-09 | 2023-10-15 | [5 empty] | 0 | 138 | na | 0.6 | 2-959.6 ACSS/TW/HS Suwanee | Steel Pole | na | na | varies | 0.6 | 25.101(c)(5)(A)
0PT45459 | Kirkland Park Switch - Blackwell St Sub 138 kV Line : Replace damaged insulators | City of Dallas, Dallas County | Replace approximately fifty-four (54) damaged suspension insulators with new suspension insulators with shackles. | 2021-09-27 | 2021-11-01 | 2021-11-01 |  | 252799 |  |  | 100 | 138 | na | 2 | 1033.5 ACSR Curlew | Steel Poles | 50 | 2 | na | na | 25.101(c)(5)(B)
0PT45435 | Palestine Sub - Crockett Sub 69 kV Line: Retermination into Elkhart Sub | City of Elkhart, Anderson County | Reterminate Palestine Sub - Crockett Sub 69 kV Line into Elkhart Sub | 2021-11-18 | 2021-12-17 | 2021-12-17 |  | 192725 |  |  | 100 | 69 | na | 0.1 | 2/0 ACST Quail | Wood Pole | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT45370 | Huntington - Etoile - Zavalla Pump 138 kV Line : HB 4150 Sam Rayburn Reservoir Crossing | Angelina County | Replace and Install two new structures on the Huntington - Etolie-Zavalla Pump 138 kV Line to meet required HB4150 clearance requirements over the Sam Rayburn Reservoir. | 2021-09-16 | 2021-10-13 | 2021-10-13 |  | 1280135 |  |  | 100 | 138 | na | 0.1 | 795 ACSR Drake | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT45248 (R8147) | Midland East Switch - Midland Downtown Sub 138 kV Line : Install Second Circuit From Midland East - Str. 13/8 | City of Midland, Midland County | Install a second circuit onto new double-circuit structures from Midland East Switch to Str. 13/8 for the Midland East Switch - Midland Downtown Sub 138 kV Line. | 2021-10-28 | 2022-06-01 | 2022-06-01 |  | 1076287 |  |  | 100 | 138 | na | 1.05 | 1926.9 ACSS/TW/HS Cumberland | Steel Pole | 50 | 1.05 | na | na | 25.101(c)(5)(C)
0PT45245 | Northhaven Switch - Blackwell ST Sub 138 kV Line : Replace damaged insulators | City of Dallas, Dallas County | Replace approximately one hundred and thirty two (132) damaged suspension insulators with new suspension insulators with shackles. | 2021-10-08 | 2021-11-01 | 2021-11-01 |  | 363377 |  |  | 100 | 138 | na | 3 | 1033.5 ACSR Curlew | Steel Poles | 50 | 3 | na | na | 25.101(c)(5)(B)
0PT43986 (M4324) | Kemp Ranch Switch - Cedar Hill Switch 138 kV Line : Cut-In to Establishing Soap Creek Sw | City of Midlothian, Ellis County | Line work associated with connecting the 138 kV Soap Creek Switch | 2021-12-03 | 2022-06-01 | 2022-06-01 |  | 2150000 |  |  | 100 | 138 | na | 0.58 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 80 | 0.29 | 25.101(c)(5)(A)
0PT38107 0PT45301 (R8147) | Midland East Switch - Spraberry Switch 138 kV Line : Rebuild | City of Midland, Midland County | Rebuild the Midland East Switch - Spraberry Switch 138 kV Line on double-circuit structures with one circuit in place from Midland East Switch to Spraberry Switch. | 2021-10-29 | 2022-06-01 | 2022-06-01 |  | 21717063 |  |  | 100 | 138 | na | 13.7 | 1926.9 ACSS/TW/HS Cumberland | Steel Pole | 50 | 13.7 | na | na | 25.101(c)(5)(B)
0PT45571 | Waxahachie OCF - Ferris 69 kV Line: Damaged Tower Project | City of Red Oak, Ellis County | Replace 1 damaged tower with a wood pole structure. | 2021-06-20 | 2021-06-22 | 2021-06-22 |  | 56050 |  |  | 100 | 69 | na | 0.01 | 336 ACSR Linnet | Wood Pole | 50 | 0.01 | na | na | 25.101(c)(3) | Emergency Project
0PT45280 | Bardwell Lake Switch - Waxahachie Sub 69 kV Line | Ellis County | Replace 4 towers along the Bardwell Lake - Waxahachie 69 kV line as a result of a storm. | 2021-05-03 | 2021-06-21 | 2021-06-21 |  | 661793 |  |  | 100 | 69 | na | 0.5 | 1/0 Copper | Wood Poles | Varies | 0.5 | na | na | 25.101(c)(3) | Emergency Project
0PT45299 (R985) | Commerce Switch - Sulphur Springs Switch 138 kV Line: Re-term at Commerce Switch | City of Commerce City, Hunt County | Rebuild a section from Commerce Switch - Str 1/4 of the Commerce Switch - Sulphur Springs 138 kV Line | 2021-12-16 | 2022-05-02 | 2022-05-02 |  | 639877 |  |  | 100 | 138 | na | 0.3 | 959.6 ACSS/TW/HS Suwannee | Steel Pole | 70 | 0.3 | na | na | 25.101(c)(5)(B)
0PT45276 | Handley-Lancaster 138 kV: SE Connector Relocation for TxDOT | City of Fort Worth, Tarrant County | Relocation with new double circuit, steel monopole, tangent and angle structures on Handley-Lancaster 138 kV Line. | 2021-10-29 | 2021-11-19 | 2021-11-19 |  | 550521 |  |  | 100 | 138 | na | 0.18 | 1534 ACAR & 795 ACSR Drake | Steel Pole | varies | 0.18 | na | na | 25.101(C)(5)(F) | Relocation is a request and 100% reimbursable by the Texas Department of Transportation.
0PT45221 | Liggett Switch - Norwood Switch 138 kV Line: OPGW | City of Irving, Dallas County | Install OPGW on the Liggett to Norwood 138kV Line. | 2022-02-10 | 2022-04-01 | 2022-04-01 |  | 826932 |  |  | 100 | 138 | na | 12.8 | 959.6 ACSS/TW/HS Suwannee | Steel Lattice Tower | 50 | 6.4 | na | na | 25.101(c)(5)(A)
0PT44627 (R6130) | Jewett Switch - Fairfield West Sub 138 kV Line: Cut In Blain Sub | Freestone County | Cut in the Jewett Switch - Fairfield West Sub 138 kV Line to establish the new Blain substation. | 2021-12-14 | 2022-02-01 | 2022-02-01 |  | 791401 |  |  | 100 | 138 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT42892 | Norwood-NW Carrollton 138 kV: I-35 E Phase 2 Relocation for TxDOT | City of Carrollton, Dallas County | Relocation with new double circuit, steel monopole, tangent and dead end structures on Norwood-NW Carrollton 138 kV Line. | 2021-12-27 | 2022-02-02 | 2022-02-02 |  | 793317 |  |  | 100 | 138 | na | 0.22 | 959 ACSS/TW Cumberland | Steel Pole | 100 | 0.22 | na | na | 25.101(C)(5)(F) | Relocation is a request and 100% reimbursable by the Texas Department of Transportation.
0PT42888 | Liggett-Collin 138 kV: I-35 E Phase 2 Relocation for TxDOT | City of Carrollton, Dallas County | Relocation with new double circuit, steel monopole, tangent structure on Liggett-Collin 138 kV Line. | 2021-10-20 | 2021-11-12 | 2021-11-12 |  | 434549 |  |  | 100 | 138 | na | 0.21 | 2-1590 ACSR Falcon | Steel Pole | 100 | 0.21 | na | na | 25.101(C)(5)(F) | Relocation is a request and 100% reimbursable by the Texas Department of Transportation.
18T65208 (M4088) | Northaven Switch - Morrison Lane Switch 138 kV Line: Rebuild Marsh Lane-Morrison Lane | City of Dallas, Dallas County | Rebuild 3.2 mile section of Northaven Switch - Morrison Lane Switch 138 kV Double Circuit Line from Morrison Lane Switch to Marsh Lane Sub. | 2022-01-10 | 2022-05-16 | 2022-05-16 |  | 10745318 |  |  | 100 | 138 | na | 6.4 | 1926.9 ACSS/TW | Steel H-Frame, Steel Pole | 100 | 3.2 | na | na | 25.101(c)(5)(B)
0PT42661 | Royse City - Trinidad 138 kV Line HB 4150 Cedar Creek Reservoir | City of Royse City, Waco County | Replace 22 structures located in 3 sections along the Royse City - Trinidad 138 kV Line. | 2021-10-23 | 2021-12-15 | 2021-12-15 |  | 6652712 |  |  | 100 | 138 | na | 2.1 | 795 ASCR Drake | Steel Pole | 100 | 2.1 | na | na | 25.101(c)(5)(A)
0PT42662 | Stryker Creek - Lufkin 138 kV Line: HB4150 Lake Nacogdoches Lake Crossings | City of Lufkin, Tyler County | Replace 5 structures located along the Stryker Creek - Lufkin 138 kV Line. | 2021-10-08 | 2021-12-06 | 2021-12-06 |  | 1875417 |  |  | 100 | 138 | na | 0.7 | 795 ASCR Drake | Steel Pole | 100 | 0.7 | na | na | 25.101(c)(5)(A)
0PT45078 | Sulphur Springs SW - Rivercrest SW - Monticello SW 138 kV: Structure Replacement | Franklin County Hopkins County | Replacement of wood cross arms, insulators and poles on Sulphur Springs SW - Rivercrest SW - Monticello SW 138 kV Line. | 2021-07-07 | 2021-10-31 | 2021-10-31 |  | 330554 |  |  | 100 | 138 | na | 59.41 | 636 ACSR aluminum | Wood pole | 100 | 59.41 | na | na | 25.101(c)(5)(B)
0PT44307 | Bennett Sub - Chico West Sub 69 kV Line: Structure Replacement | City of Chico, Wise County | Replacement of poles and insulators on Bennett Sub - Chico West Sub 69 kV Line. | 2021-07-12 | 2021-12-28 | 2021-12-28 |  | 200333 |  |  | 100 | 69 | na | 14.4 | 1/0 ACSR Raven | Wood pole | Varies | 14.4 | na | na | 25.101(c)(5)(B)
0PT41086 | Yucca Drive Switch - Holt Switch 138 kV Line : Structure Replacement | City of Odessa, Ector County | Replacement of crossarms and poles on Yucca Drive Switch - Holt Switch 138 kV Line. | 2021-09-20 | 2021-11-09 | 2021-11-09 |  | 212716 |  |  | 100 | 138 | na | 10 | 795 ACSR Drake | Wood pole | 75 | 10 | na | na | 25.101(c)(5)(B)
0PT44737 | Weatherford Sub - Springtown Sub 138 kV Line : Crossarms and Insulators Replacement | City of Fort Worth, Tarrant County | Replacement of crossarms and insulators on Weatherford Sub - Springtown Sub 138 kV Line. | 2021-03-03 | 2021-12-28 | 2021-12-28 |  | 207994 |  |  | 100 | 138 | na | 5.61 | 336 ACSR Linnet | Wood pole | 100 | 5.61 | na | na | 25.83(a)(3)
0PT45389 | Sandhills Tap-Sandhills Sub 138 kV Line:Structure Replacement | City of Crane, Crane County | Replacement of wood poles, insulators and crossarms on the Sandhills Tap - Sandhills Sub 138 kV Line. | 2021-09-01 | 2021-10-01 | 2021-10-01 |  | 295466 |  |  | 100 | 138 | na | 11.44 | 4/0 ACSR Penguin | Wood pole | 50 | 11.44 | na | na | 25.101(c)(5)(B)
0PT44559 | Watermill Switch - Seagoville Switch 138 kV Line : Structure Replacement | City of Dallas, Dallas County | Replacement of structures, crossarms and insulators on Watermill Switch - Seagoville Switch 138 kV Line. | 2021-05-03 | 2022-06-01 | 2022-06-01 |  | 543752 |  |  | 100 | 138 | na | 12 | 795 ACSR | Wood pole | 100 | 12 | na | na | 25.101(c)(5)(B)
0PT45509 | Valley SW-Stone Creek SW 138kv: Replace poles, standRemove project under 250ks, timbers and crossarms | City of Denison, Grayson County | Replace poles, standRemove project under 250ks, timbers and crossarms on Valley SW - Stone Creek SW 138kV line. | 2021-09-07 | 2021-12-02 | 2021-12-02 |  | 276979 |  |  | 100 | 138 | na | 1.82 | 211 ACSR | Wood Pole | 100 | 1.82 | na | na | 25.101(c)(5)(B)
0PT45603 | Holliday to Electra 69 kV line, KMA Tap : Replace cross arms and multiple structures | City of Kamay, Wichita County | Replace cross arms and multiple structures on 69kV line, KMA TAP | 2021-11-10 | 2021-12-17 | 2021-12-17 |  | 212395 |  |  | 100 | 69 | na | 6.07 | 4/0 ACSR Penguin | Wood H Frame | 50 | 6.07 | na | na | 25.101(c)(5)(B)
0PT45623 | Bowie Sub - Henrietta Sub 69 kV Line : Line Maintenance | City of Henrietta, Clay County | Replace cross arms and poles on the Bowie Sub - Henrietta Sub 69 kV Line | 2021-11-01 | 2021-12-17 | 2021-12-17 |  | 332441 |  |  | 100 | 69 | na | 11.4 | 1/0 ACSR Raven | Wood pole | 50 | 11.4 | na | na | 25.101(c)(5)(B)
0PT45667 | Yucca Switch - Northern Natural Gas 69 kV Line: Replace Wood Poles and Insulators (TSP21011) | Ward County | Replace wood poles and insulators on multiple structures on the Yucca Switch - Northern Natural Gas 69 kV line | 2021-06-26 | 2021-09-09 | 2021-09-09 |  | 453161 |  |  | 100 | 69 | na | 15.14 | 336 ACSR Linnet | Wood pole | 50 | 15.14 | na | na | 25.101(c)(5)(B)
0PT45507 | Radial Line Project: Gordonville Tap-Gordonville: Replace poles, crossarms, xbrace & vee braces | City of Gordonville, Cooke County | Replace poles, crossarms, xbrace & vee braces on Gordonville Tap - Gordonville. | 2021-07-26 | 2021-12-02 | 2021-12-02 |  | 309668 |  |  | 100 | 138 | na | 26.16 | 3/0 ACSR Pigeon | Wood pole | 100 | 26.16 | na | na | 25.101(c)(5)(B)
0PT45665 | Radial Line Project Grapeland Mag Tap 138 kV : Replace Poles and Arms Energized on Grapeland Mag Tap | Houston County | Replace Poles and Arms Energized on Grapeland Mag Tap. | 2021-08-30 | 2021-11-19 | 2021-11-19 |  | 205979 |  |  | 100 | 138 | na | 10.3 | 4/0 ACSR Penguin | Wood H Frame | 100 | 10.3 | na | na | 25.101(c)(5)(B)
0PT45672 | Yucca Drive Switch - Crane 69 kV Line: Replace Wood Poles and Insulators Due to Storm (TSP21010) | Ward County | Replace Wood Poles and Insulators Due to Storm (TSP21010) on Yucca Drive Switch - Crane 69 kV Line. | 2021-06-26 | 2021-11-18 | 2021-11-18 |  | 438637 |  |  | 100 | 69 | na | 5.11 | 1/0 ACSR Raven | Wood pole | 50 | 5.11 | na | na | 25.101(c)(5)(B)
0PT45755 | Moss Switch - Holt Switch 138 kV: Replace Wood Pole, Crossarms and Insulators | Ector County | Replace Wood Pole, Crossarms and Insulators on Moss Switch - Holt Switch 138kV. | 2021-09-13 | 2021-11-01 | 2021-11-01 |  | 361350 |  |  | 100 | 138 | na | 2.32 | 336 ACSR Linnet | Wood H Frame | 75 | 2.32 | na | na | 25.101(c)(5)(B)
0PT45399 0PT45955 (R8594) | Horseshoe Springs Switch - Riverton Switch 138 kV Line : Install Old Michigan POD for Cimarex Energy's Station | City of Pecos, Culberson County | Establish Old Michigan POD to Cimarex’s Triple Crown Substation. | 2022-02-16 | 2022-04-01 | 2022-04-01 |  | 1444467 |  |  | 100 | 138 | na | 0.09 | 959 ACSS/TW Suwannee | Steel Poles/ H-frame Switch | 50 | 0.03 | 70 | 0.06 | 25.101(c)(5)(A)
0PT45371 | Handley-Duval 138 kV: SE Connector Relocation for TxDOT | City of Fort Worth, Tarrant County | Relocation with new double circuit, steel monopole, tangent structure on Handley-Duval 138 kV Line. | 2021-11-15 | 2021-11-19 | 2021-11-19 |  | 357832 |  |  | 100 | 138 | na | 0.18 | 959 ACSS/TW Suwannee | Steel Pole | varies | 0.18 | na | na | 25.101(C)(5)(F) | Relocation is a request and 100% reimbursable by the Texas Department of Transportation.
0PT45226 (M4292) | Nevada Substation to Royse Switch 138 kV Line Rebuild | City of Royse, Rockwall County | Rebuild the Nevada - Royse 138 kV line section. | 2022-01-11 | 2022-04-25 | 2022-04-25 |  | 3029964 |  |  | 100 | 138 | na | 4.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 4.2 | na | na | 25.101(c)(5)(B)
0PT45108 (M4236) | Royse Switch - Rowlett Sub 138 kV Line : Reconductor Royse Switch to Fate Sub | Royse City, Rockwall County | Reconductor the Royse Switch - 10/10C (Fate Sub) section of the Royse Switch - Rowlett Sub 138 kV Line. | 2022-04-14 | 2022-05-12 | 2022-05-12 |  | 4355202 |  |  | 100 | 138 | na | 3.29 | 2-959.6 ACSS/TW/HS Suwannee | Steel Pole | Varies | 3.29 | na | na | 25.101(c)(5)(B)
0PT45090 0PT45952 (M4342) | Kaufman NW Switch - Mankin Switch 138 kV Line : Install Kings Creek Switch and Re-terminate Rayburn's Oak Grove Tap | City of Kaufman, Kaufman County | Re-terminate the Kaufman NW Switch - Mankin Switch 138 kV line into Kings Creek Switch as part of rebuilding the existing Oak Grove 138 kV Tap. | 2022-04-01 | 2022-05-02 | 2022-05-02 |  | 2345172 |  |  | 100 | 138 | na | 0.5 | 1926.9 ACSS/TW Cumberland | Steel Poles | na | na | 100 | 0.5 | 25.101(c)(5)(A)
0PT45033 0PT46670 (M5172) | Flat Rock BEPC Switch - Azle Switch 138 kV Line : Rebuild 138 kV Line Section | City of Fort Worth, Tarrant County | Rebuild Oncor’s 5.1 mile portion of the 11.5 mile Weatherford Switch – Flat Rock BEPC POI – Azle Switch 138 kV Line. | 2021-11-23 | 2022-05-15 | 2022-05-15 |  | 5370613 |  |  | 100 | 138 | na | 5.1 | 2-1926.9 ACSS/TW/HS Cumberland | Steel Pole | 100 | 5.1 | na | na | 25.101(c)(5)(B)
0PT44895 (R8601) | Buzzard Draw Switch - Getty Vealmoor Tap 138 kV Line : Install Oncor's POD for HighPeak Energy's Sub | City of Big Spring, Howard County | Buzzard Draw Switch - Getty Vealmoor Tap 138 kV Line : Install Wildhorse POD for HighPeak Energy's Sub | 2022-04-06 | 2022-06-01 | 2022-06-01 |  | 1631712 |  |  | 100 | 138 | na | 0.25 | 959 ACSS/TW Suwannee | Steel 3 Pole, Steel H-Frame | 75 | 0.25 | na | na | 25.101(c)(5)(A)
0PT44514 (R8583) | Flintkote South Tap - Flintkote Switch 69 kV Line : Cut-in for Beacon Hill Sub | City of Sweetwater, Nolan County | Line work associated with connecting the 69 kV Beacon Hill Substation | 2021-12-10 | 2022-02-01 | 2022-02-01 |  | 655834 |  |  | 100 | 69 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | 50 | 0.1 | 25.101(c)(5)(A)
0PT44127 (M4320) | Waxahachie Switch - Bardwell Switch 69 kV Line : Rebuild | City of Waxahachie, Ellis County | Rebuild the Waxahachie Switch – Bardwell Lake Switch section of the Hillsboro - Waxahachie 69 kV Line. | 2022-02-01 | 2022-11-25 |  |  | 12949145 |  |  | 99 | 138 | 69 | 7.9 | 959.6 ACSS/TW/HS Suwannee | Steel Poles | 80 | 7.9 | na | na | 25.101(c)(5)(B)
0PT44068 (R989) | Stone Creek Switch - Valley Switch 138 kV Line : Cut-in to establish Loy Lake 138 kV capacitor bank | City of Denison, Grayson County | Cut in the Loy Lake Capacitor Bank on the Stone Creek - Valley 138 kV Line. | 2022-04-14 | 2022-06-23 | 2022-06-23 |  | 900000 |  |  | 100 | 138 | na | 0.3 | 959.6 ACSS/TW Swannee | Steel Poles | 200 | 0.3 | na | na | 25.101(c)(5)(A)
0PT43899 (R8570) | Eskota Switch - Sweetwater No. 2 Sub 69 kV Line: Rebuild the Flintkote Tap 69 kV section | City of Sweetwater, Nolan County | Upgrade the Flintkote Tap 69 kV Line from the Eskota Switch - Sweetwater No. 2 Sub 69kV Line. | 2021-12-14 | 2022-02-01 | 2022-02-01 |  | 1300842 |  |  | 100 | 69 | na | 1 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 0.5 | na | na | 25.101(c)(5)(B)
0PT43692 (R6147) | Bellmead Sub - Elm Mott Switch 69 kV Line : Conversion to 138 kV | City of Waco, McLennan County | Conversion to 138 kV as a part of rebuilding the Waco East Switch - Elm Mott Switch 69 kV line conversion to 138 kV operation | 2022-01-05 | 2022-05-18 | 2022-05-18 |  | 6597154 |  |  | 100 | 69 | 138 | 12.4 | 2 - 1233.6 ACSS/TW/HS Yukon | Steel Poles | 100 | 6.2 | na | na | 25.101(C)(5)(B) | Date was corrected to match actual Construction start date.
0PT43251 (R8258) | Midland East Switch - Falcon Seaboard Switch 345 kV Line : Reterminate at Midland East Switch | City of Midland, Midland County | Reterminate the Midland East Switch - Falcon Seaboard Switch 345 kV Line to the Midland East Switch Station. | 2022-04-12 | 2022-08-01 | 2022-08-01 |  | 1558975 |  |  | 100 | 345 | na | 0.3 | 2 - 1926.9 ACSS/TW/HS Cumberland | Steel Tower | 150 | 0.3 | na | na | 25.101(c)(5)(A)
0PT43250 (R8258) | NTUSU Midland East Switch - Midland County Northwest Switch 345 kV Line : Reterminate | City of Midland, Midland County | Reterminate the Midland East Switch - Midland County Northwest Switch 345 kV Line to the Midland East Switch Station. | 2022-04-06 | 2022-08-01 | 2022-08-01 |  | 2147515 |  |  | 100 | 345 | na | 0.3 | 2 - 1926.9 ACSS/TW/HS Cumberland | Steel Tower | 150 | 0.3 | na | na | 25.101(c)(5)(A)
0PT42416 (M4292) | Payne Switch - Royse City 138 kV Line : Rebuild Audie Murphy POI to Royse Switch | City of Royse, Rockwall County | Rebuild the Audie Murphy POI to Royse Switch section of the Payne Switch - Royse City 138 kV line. | 2022-01-11 | 2022-12-15 |  |  | 28941915 |  |  | 67 | 138 | na | 13.9 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 13.9 | na | na | 25.101(c)(5)(B)
0PT02808 (M4250) | Cedar Hill Switch 138 kV Line - Camp Wisdom 138 kV Line: Rebuild Cedar Hill Switch - Love Bird Tap Section | City of Cedar Hill, Dallas County | Rebuild a section of the Cedar Hill Switch – Love Bird Tap 138 kV Line. | 2022-01-18 | 2022-11-30 |  |  | 8189827 |  |  | 89 | 138 | 138 | 5.4 | 2-959.6 ACSS/TW/HS Suwannee | Steel Pole | 80 | 5.4 | na | na | 25.101(c)(5)(B)
0PT44156 (R8562) | Sand Lake Switch - Culberson Switch 138 kV Line: Cut-in at McIlvain Sub | City of Pecos, Reeves County | Cut in at Mcllvain Sub | 2022-03-23 | 2022-05-06 | 2022-05-06 |  | 1200183 |  |  | 100 | 138 | na | 0.17 | 1926.9 ACSS/TW | Steel Pole | na | na | 100 | 0.17 | 25.101(c)(5)(A)
0PT44435 (R6159) | Establish Outlaw Switch in the Navarro SW (LST) -Limestone (CNP) 345 kV Line | Cities of Richland, Pursley, and Currie, Navarro County | Cut in the (LST) Navarro SW - (CNP) Limestone 345 kV Line to establish the new Outlaw Switch | 2022-03-05 | 2022-06-01 | 2022-06-01 |  | 1761913 |  |  | 100 | 345 | na | 0.42 | 959.6 ACSS/TW Suwannee | Steel Tower | na | na | 335 | 0.42 | 25.101(c)(5)(A)
0PT45887 (R8602) | Buzzard Draw Switch – Getty Vealmoor Tap 138 kV Line: Install High Plains POD for Surge Energy's Vincent Sub | City of Big Spring, Howard County | Establish High Plains POD for Surge Energy's Vincent Sub | 2022-09-22 | 2022-12-31 |  |  | 1335866 |  |  | 99 | 138 | na | 0.3 | 959.6 ACSS/TW Suwannee | Steel Poles/ H-frame Switch | na | na | 70 | 0.3 | 25.101(c)(5)(A)
0PT43552 (R6148) | Sandow Switch - Elgin Switch 138 kV line: Brushy Creek Switch Re-termination | City of Elgin, Williamson County | Re-terminate the Sandow – Elgin 138 kV line at its new terminal location in the Brushy Creek 138 kV Switching station | 2022-02-22 | 2022-05-02 | 2022-05-02 |  | 1109985 |  |  | 100 | 138 | na | 0.14 | 1926.9 ACSS/TW Cumberland & 2- 959 ACSS/TW Suwannee | Steel poles | 100 | 0.14 | na | na | 25.101(c)(5)(A)
0PT43553 0PT45713 (R6148) | Elgin Switch – Taylor 138 kV line: Brushy Creek Switch Re-termination | City of Elgin, Williamson County | Re-terminate the Elgin - Taylor 138 kV line at its new terminal location in the Brushy Creek 138 kV Switching station. | 2022-02-28 | 2022-05-02 | 2022-05-02 |  | 1344449 |  |  | 100 | 138 | na | 0.37 | 1926.9 ACSS/TW Cumberland & 2- 959.6 ACSS/TW Suwannee | Steel poles | 100 | 0.28 | 70 | 0.09 | 25.101(c)(5)(A)
0PT43554 (R6148) | Brushy Creek Switch – Elgin Switch 138 kV line: Construct new line | City of Elgin, Williamson County | Build the Brushy Creek - Elgin 138 kV line. | 2022-03-03 | 2022-05-02 | 2022-05-02 |  | 950469 |  |  | 100 | 138 | na | 0.17 | 1926.9 ACSS/TW Cumberland & 2- 959.6 ACSS/TW Suwannee | Steel Pole | 100 | 0.03 | Varies | 0.14 | 25.101(c)(5)(A)
0PT43501 (R6148) | Brushy Creek Switch - River Valley Storage 138 kV Line: Line work to connect the Brushy Creek Switch to the River Valley Battery Storage Facilities | City of Elgin, Williamson County | Build the Brushy Creek - River Valley Storage 138 kV line. | 2022-02-15 | 2022-05-15 | 2022-05-15 |  | 366675 |  |  | 100 | na | 138 | 0.05 | 959.6 ACSS/TW Suwannee | Steel poles | varies | 0.05 | na | na | 25.101(c)(5)(A)
0PT44765 (R6152) | Mankin Switch – Kaufman Northwest Switch 138 kV Line: Will White POI for Rayburn’s Tool Sub | City of Tool, Henderson County | Establish the Will White POI for Rayburn Country Electric Cooperative’s Tool substation. | 2022-02-21 | 2022-04-01 | 2022-04-01 |  | 1730834 |  |  | 100 | 138 | na | 0.03 | 959.6 ACSS/TW Suwannee | Steel Poles | 70 | 0.03 | na | na | 25.101(c)(5)(A)
0PT44767 0PT45247 (R6170) | Iron Bridge Tap - Ables Springs Tap West 138 kV Line: Kitsee POI for Rayburn's Duck Cove Sub | City of Terrell, Kaufman County | Establish Kitsee POI for Rayburn Country Electric Cooperative’s Duck Cove substation. | 2022-03-23 | 2022-10-20 | 2022-10-20 |  | 1483316 |  |  | 100 | 138 | na | 0.29 | 959.6 ACSS/TW Suwannee | Steel Poles | 70 | 0.04 | varies | 0.25 | 25.101(c)(5)(A)
0PT44681 (R6158) | Brown Switch - IP Radian POI 345 kV Line | City of Brookesmith, Brown County | Establish a Point of Interconnect for IP Radian | 2021-12-02 | 2022-06-21 | 2022-06-21 |  | 3834123 |  |  | 100 | na | 345 | 0.95 | 2-1926.9 ACSS/TW/HS Cumberland | Lattice Towers | na | na | 160 | 0.95 | 25.101(c)(5)(A)
0PT44126 (R6155) | Rattlesnake Switch - Jewett Switch 345 kV Line : Line modification to connect St. Johns Switch | City of Marlin, Falls County | Cut in the Rattlesnake Sw. - Jewett Sw. 345 kV Line to establish the new St. Johns Switch. | 2022-03-02 | 2022-04-21 | 2022-04-21 |  | 1419274 |  |  | 100 | 345 | na | 0.25 | 2-959.6 ACSS/TW Suwannee | Steel Towers | 225 | 0.25 | na | na | 25.101(c)(5)(A)
0PT43905 0PT46229 (R6137) | Duck Cove Tap #1 - Wills Point Sub 69 kV Line: Rebuild | City of Wills Point, Van Zandt County | Rebuild the Duck Cove Tap #1 - Wills Point Sub 69 kV | 2022-03-17 | 2022-09-28 | 2022-09-28 |  | 7808064 |  |  | 100 | 69 | 138 | 3.1 | 959.6 ACSS/TW Suwannee | Steel Monopole | 50 | 3.1 | na | na | 25.101(c)(5)(B)
0PT45992 | Jacksonville Switch-Jacksonville Plant North 69 kV Line : Radial line work replace broken poles, distribution arms and insulators | City of Jacksonville, Cherokee County | Replace broken poles, distribution arms and insulators on Jacksonville Switch to Jacksonville Plant North 69 kV Line. | 2021-11-01 | 2021-12-28 | 2021-12-28 |  | 364434 |  |  | 100 | 69 | na | 1.6 | 1/0 ACSR Raven | Wood Pole | 50 | 1.6 | na | na | 25.101(c)(5)(B)
0PT46102 | South Marlin Tap - Lott Falls Road Sub 69 kV Line : Replace poles crossarms and insulators | City of Marlin, Falls County | Replace Poles Crossarms and Insulators on South Marlin Tap to Lott Falls Road Sub 69 kV Line. | 2021-11-15 | 2021-12-21 | 2021-12-21 |  | 262738 |  |  | 100 | 69 | na | 11.1 | 4/0 ACSR Penguin | Wood Pole | 50 | 11.1 | na | na | 25.101(c)(5)(B)
0PT43969 | Sandow Switch - Austrop Sub 345 kV Line | City of Rockdale, Lee County, Williamson County and Miliam County | Replacement of insulators and installation of varmint guards on Sandow Switch to Austrop Sub 345 kV Line. | 2022-02-28 | 2022-05-10 | 2022-05-10 |  | 396086 |  |  | 100 | 345 | na | 18.84 | 795 ACSR Drake | Steel Lattice Tower | 125 | 18.84 | na | na | 25.101(c)(5)(E)
0PT46168 | Jacksboro Sinclair Tap - Jacksboro REA Switch 69 kV Line: Replace multiple cross arms and poles | City of Jacksboro, Jack County | Replace multiple cross arms and poles on Jacksboro Sinclair Tap to Jacksboro REA Switch 69 kV Line. | 2021-11-01 | 2021-12-13 | 2021-12-13 |  | 264059 |  |  | 100 | 69 | na | 2.67 | 4/0 ACSR Penguin | Wood Pole | 100 | 2.67 | na | na | 25.101(c)(5)(B)
0PT44253 0PT46213 (R3021) | Windmill Switch - AJ Swope Switch 345 kV Line : Wallaby Switch Cut In for Dawn Solar POI | Deaf Smith County | Cut in the Windmill Switch - AJ Swope Switch 345 kV Line to establish Wallaby Switch. | 2023-02-20 | 2024-11-14 | [5 empty] | 0 | 345 | na | 0.45 | 2-1926.9 ACSS/TW Cumberland | Steel Lattice Towers | 175 | 0.4 | 410 | 0.05 | 25.101(c)(5)(A)
0PT46164 (M5278) | Timberview Switch - Everman Switch 345 kV Line : Station Interconnect | City of Everman, Tarrant County | Line work to connect new Timberview Switch to existing Everman Switch. | 2022-02-24 | 2022-05-31 | 2022-05-31 |  | 1722481 |  |  | 100 | na | 345 | 0.5 | 2-1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 100 | 0.5 | 25.101(c)(5)(A)
0PT45834 0PT46000 (R8569) | SL Salt Flat Road - SkyWest 138 kV Line: Rebuild | Midland County | Rebuild the Salt Flat Road - SkyWest 138 kV line to 1926 ACSS/TW capable structures. | 2022-04-01 | 2022-07-20 | 2022-07-20 |  | 2630091 |  |  | 100 | 138 | na | 1 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 1 | na | na | 25.101(c)(5)(B)
0PT44967 (M4122) | Sterrett Switch - Sardis Switch 138kV Line: Reconfigure Str 31/6 to 31/11 to accommodate Desoto to Sterrett Rebuild | Waxahachie/Ellis County | Upgrade the 6.2 mile Glenn Heights to Sterrett section of the Desoto Sw- Sterrett Sw 138kV Line | 2022-01-19 | 2022-03-02 | 2022-03-02 |  | 919869 |  |  | 100 | 138 | na | 6.2 | 1926.9 ACSS/TW/HS Cumberland | Steel Poles | 100 | 6.2 | na | na | 25.101(c)(5)(B)
0PT44457 (R6157) | Temple Pecan Creek Switch to Tradinghouse Switch and Temple Switch to Lake Creek Switch 345 kV Double-Circuit Transmission Line Changes | City of Golinda, Falls County | Line work associated to create clearance under 345 kV Line for the new 138kV Cow Bayou Switch. | 2022-03-23 | 2022-06-22 | 2022-06-22 |  | 749115 |  |  | 100 | 345 | na | 0.5 | 2-795 ACSR Drake | Steel Tower | 125 | 0.25 | na | na | 25.101(c)(5)(A)
0PT44456 (R6157) | Temple Pecan Creek Switch - Lake Creek Switch 138 kV Line : Modify line for connecting Cow Bayou Switch | City of Golinda, Falls County | Line work associated with connecting the new 138kV Cow Bayou Switch. | 2022-03-18 | 2022-05-03 | 2022-05-03 |  | 958849 |  |  | 100 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT44873 0PT47804 (R8600) | McDonald Rd Switch - Spraberry Switch 138 kV Line : Cut-in to Desert Wind Sub | City of Garden City, Glasscock County | Cut-in the McDonald Rd- Switch-Spraberry Switch 138 kV line and the Spraberry Switch-Garden City 69 kV into the new Desert Wind Sub and decommission Garden City | 2022-04-14 | 2022-07-20 | 2022-07-20 |  | 545011 |  |  | 100 | 138/69 | 138 | 0.8 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 0.8 | na | na | 25.101(c)(5)(A)
0PT45324 | China Grove Switch - Paint Creek Sub 138 kV Line : Install new H-Frame Switch at Radium Substation | Jones County | Replace the existing wood 3-pole switch POI structure with a steel H-frame switch re-used from the Ennis Creek project. Install new 3-pole deadend "outrigger" structure. Replace adjacent wood H-frame suspension structures with new wood H-frame suspension structures. | 2022-04-05 | 2022-04-29 | 2022-04-29 |  | 996929 |  |  | 100 | 138 | na | 0.3 | 636 ACSR Grosbeak | Steel H-Frame and Wood H-Frame | 100 | 0.25 | na | na | 25.101(c)(5)(B)
0PT44067 (R8567) | McDonald Road Switch – Spraberry Switch 138 kV Line : Cut-In to establish capacitor bank | Midland County | Establish the Tex Harvey capacitor bank on the McDonald Road Switch – Spraberry Switch 138 kV line. | 2022-02-04 | 2022-05-25 | 2022-05-25 |  | 354054 |  |  | 100 | 138 | na | 0.05 | 959 ACSS/TW Suwannee | Steel Poles | Varies | 0.05 | na | na | 25.101(c)(5)(A)
0PT42891 | Norwood-Denton-Bowie 138 kV: I-35 E Phase 2 Relocation for TxDOT | City of Carrollton, Dallas County | Relocation with new double circuit, steel monopole, deadend structures on Norwood-Denton-Bowie 138 kV Line. | 2022-01-08 | 2022-03-02 | 2022-03-02 |  | 3188087 |  |  | 100 | 138 | na | 0.22 | 1926.9 ACSS/TW Cumberland | Steel Pole | varies | 0.11 | na | na | 25.101(C)(5)(F) | Relocation is a request and 100% reimbursable by the Texas Department of Transportation.
0PT44966 (M4122) | Desoto Switch - Sterrett Switch 138kV Line: Rebuild Glenn Heights (BEC) to Sterrett SW | Waxahachie/Ellis County | To accommodate the Desoto to Sterrett Rebuild, structures 31/6 - 31/11 will need to be upgraded and wire transferred to the new structures. | 2022-01-24 | 2022-05-02 | 2022-05-02 |  | 9629545 |  |  | 100 | 138 | na | 0.2 | 795 ACSR Drake | Steel Poles | 100 | 0.2 | na | na | 25.101(c)(5)(B)
0PT43524 0PT44590 (R8555) | NTUSU Brown Sub - Koch Tap 138 kV Line : Buzzard Draw Switch Cut In | City of Big Spring, Howard County | Connect the existing Brown - Vealmoor 138kV Line into Buzzard Draw Switch. This creates the new Brown - Buzzard Draw and Vealmoor - Buzzard Draw 138kV lines. | 2022-02-09 | 2022-06-01 | 2022-06-01 |  | 1480819 |  |  | 100 | 138 | na | 0.2 | 959.6 ACSS/TW/HS Suwannee | Steel Pole | 50 | 0.2 | na | na | 25.101(c)(5)(A)
0PT43514 (R8505) | Wickett (TNMP) Switch - Wolf Switch 138 kV Line : Terminate line for TNMP | City of Monahans, Ward County | Installing one POI structure and one span of wire to connect TNMP’s line to Wolf Switch | 2022-04-08 | 2022-05-15 | 2022-05-15 |  | 270862 |  |  | 100 | na | 138 | 0.1 | 1926 ACSS/TW Cumberland | Steel Monopole | Varies | 0.1 | na | na | 25.101(c)(5)(A)
0PT44154 (R790) | McGregor Phillips-Harris Creek 69 kV Rebuild | City of McGregor, McLennan County | Rebuild section of Waco West to McGregor Phillips 69kV to establish new Harris Creek Station. | 2022-11-05 | 2022-12-31 |  |  | 711416 |  |  | 1 | 69 | na | 1.5 | 336.4 ASCR Linnett | Wood 3 - Pole, Wood Pole | Varies | 1.5 | na | na | 25.101(c)(5)(A)
0PT45584 | Audelia Termination- Lake Highlands 138 kV Line: Rebuild Cathodic Protection | City of Dallas, Dallas County | Rebuild the Cathodic Protection System on the Audelia Sub - Lake Highlands 138 kV Line 138 kV Line. | 2021-12-13 | 2021-12-17 | 2021-12-17 |  | 155644 |  |  | 100 | 138 | na | na | 600 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B) | This project was broken into two separate work scopes. Cost estimate has been revised to omit work scope estimates found on 0PT46831.
0PT44279 (R6145) | Brownwood Sub - Comanche Switch 138 kV Line : Pinkney Sub Cut In | City of Blanket, Brown County | Line work associated with establishing Pinkney Substation. The work is occurring on the Comanche Switch - Brownwood Sub 138 kV line. | 2022-03-16 | 2022-05-15 | 2022-05-15 |  | 1674435 |  |  | 100 | 138 | na | 1 | 959 ACSS/TW Suwannee | Steel Pole, Wood H-Frame | 100 | 0.6 | 100 | 0.4 | 25.101(c)(5)(A)
0PT46361 | Mountain Creek Switch - Westmoreland Sub 138 kV Line : Relocate Structure S4WT355 | City of Dallas, Dallas County | Relocate structure S4WT355 at the request of a developer for a driveway.. | 2022-05-11 | 2022-05-11 | 2022-05-11 |  | 174385 |  |  | 100 | 138 | na | 0.05 | 336.4 ACSR Linnet | Steel Pole | 24 | 0.05 | na | na | 25.101(c)(5)(D)
0PT46336 (R990) | Farmersville Switch - Monticello Switch 345 kV North Circuit Line : Install a 345 kV point-of-interconnection (POI) for Hopkins Solar Generator at Birthright 345 kV Switch | Sulphur Springs County | Installing two single circuit 3-pole structures to cut in the Farmersville Switch - Monticello Switch 345kV Line to the new Birthright Switch creating a 345 kV point-of-interconnection (POI) for Hopkins Solar Generator. | 2023-03-15 | 2023-05-18 | [5 empty] | 0 | 345 | na | 0.9 | (2) - 1590 ACSR Falcon | Steel 3 Poles | 170 | 0.9 | na | na | 25.101(c)(5)(A)
0PT46334 (M5155) | Handley - Sherry 138 kV Line: Rebuild Pantego Sub - Sherry Line Section (North Circuit) | City of Arlington, Tarrant County | Rebuild the Handley-Sherry 138kV Line: Pantego Sub to Sherry Sub | 2022-03-16 | 2022-12-15 |  |  | 2966653 |  |  | 72 | 138 | na | 5.1 | 1926.9 ACSS/TW Cumberland | Steel Poles | 50 | 5.1 | na | na | 25.101(c)(5)(C)
0PT46193 | Krum West Switch - Anna Switch 345 kV Line : OPGW | City of Valley View, Cooke County | Replace OPGW and a splice box on the Krum West Switch - Anna Switch 345 kV Line. | 2022-03-04 | 2022-03-04 | 2022-03-04 |  | 146260 |  |  | 100 | 345 | na | 0.2 | 2-1926.9 ACSS/TW/HS (Cumberland) | Steel Lattice Tower | 160 | 0.2 | na | na | 25.101(c)(5)(A)
0PT37599 0PT39320 (M5155) | Handley - Sherry 138 kV Line: Rebuild Pantego Sub - Sherry Line Section (South Circuit) | City of Arlington, Tarrant County | Rebuild the Handley-Sherry 138kV Line: Pantego Sub to Sherry Sub | 2022-03-18 | 2022-12-15 |  |  | 10533506 |  |  | 83 | 138 | na | 5.1 | 1926.9 ACSS/TW Cumberland | Steel Poles | 50 | 5.1 | na | na | 25.101(c)(5)(C)
0PT45598 (M4230) | Venus Switch - Cedar Hill Switch 345 kV Line: Reconductor Britton Road - STR 14/4 | City of Mansfield, Tarrant County | Reconductor the portion of the 345kV Venus Switch - Cedar Hill Switch circuit that goes from Britton Road station to structure 14/4 using a conductor rated for 3200 A or greater. | 2022-03-29 | 2022-11-01 |  |  | 4461425 |  |  | 99 | 345 | na | 6.2 | 2-959.6 ACSS/TW (Suwannee) | Lattice Towers | 150 | 6.2 | na | na | 25.101(c)(5)(B)
0PT43019 (M4230) | Venus Switch - Cedar Hill Switch 345 kV Line: Reconductor Venus Switch - Britton Road | City of Venus, Ellis County | Reconductor the portion of the 345kV Venus Switch - Cedar Hill Switch circuit that goes from Britton Road station to structure 14/4 using a conductor rated for 3200 A or greater. | 2022-11-14 | 2022-12-15 |  |  | 5674693 |  |  | 0 | 345 | na | 7.4 | 2-959.6 ACSS/TW (Suwannee) | Lattice Towers | 150 | 7.4 | na | na | 25.101(c)(5)(B)
0PT46123 | Temple Sub - Taylor Sub 69 kV Line : Replace Poles on Various Structures | City of Temple, Bell County | Replacement of poles and insulators on Temple Sub - Taylor Sub 69 kV Line. | 2021-08-23 | 2021-10-13 | 2021-10-13 |  | 40613 |  |  | 100 | 69 |  | 40.48 | 3/0 ACSR Pigeon | Wood Pole |  | 40.48 | na | na | 25.83(a)(3) | Project did not initially meet reporting criteria. However, project cost increased after the submittal of initial estimates and has been added to the MCPR in compliance with 25.83(a)(3).
0PT46591 0PT47256 | Weatherford East Switch - Weatherford Switch 69 kV Line: Relocate 23/8 | City of Weatherford, Parker County | Relocate structure 23/8 to make way for a new road crossing the 69 kV Line. | 2022-03-23 | 2022-03-25 | 2022-03-25 |  | 138000 |  |  | 100 | 69 | na | 0.2 | 4/0 ACSR Penguin | Wood H-frame | 50 | 0.2 | na | na | 25.101(c)(5)(D)
0PT44572 (R6160) | Hillsboro Substation to Navarro Substation 138 kV Retermination/Shoo-Fly | City of Navarro, Navarro County | Line work associated with new 138kV Revolution Switch Station | 2024-03-11 | 2024-04-15 | [5 empty] | 0 | 138 | na | 0.15 | 959.6 ACSS/TW/HS Suwannee | Steel 3 - Pole, Steel Pole | na | na | 100 | 0.15 | 25.101(c)(5)(A)
0PT44730 (M4071) | Cedar Crest Switch - Wall Street Sub 138 kV Line: 69 kV to 138 kV Line Conversion | City of Dallas, Dallas County | Line work associated with the conversion of the Cedar Crest - Wall Street Line from 69 kV to 138 kV operation. | 2022-04-06 | 2022-06-17 | 2022-06-17 |  | 514751 |  |  | 100 | 69 | 138 | 0.2 | 959 ACSS/TW Suwannee | Steel Pole | 100 | 0.2 | na | na | 25.101(c)(5)(B)
0PT43618 (R990) | Farmersville Switch - Monticello Switch 345 kV South Circuit Line : Install a 345 kV point-of-interconnection (POI) for Hopkins Solar Generator at Birthright 345 kV Switch | Sulphur Springs County | Replacing structures 29/4 - 30/2 on the Farmersville Switch - Monticello Switch 345kV Line to allow the north circuit to cut in to the new Birthright Switch station | 2023-03-15 | 2023-05-18 | [5 empty] | 0 | 345 | na | 0.9 | 2 -795 ACSR Drake | Steel Towers | 170 | 0.9 | na | na | 25.101(c)(5)(B)
0PT46322 | Wolf Switch - General Tire Switch 138 kV Line: Judkins Sub Cut-In | Ector County | Reterminate for the rebuild of Judkins substation. | 2022-01-05 | 2022-10-05 | 2022-10-05 |  | 1921953 |  |  | 100 | 138 | na | 0.3 | 1926.9 ACSS Cumberland | Steel Pole | 50 | 0.3 | na | na | 25.101(c)(5)(A)
0PT43467 (M4701) | Monticello Switch - Farmersville Switch 345 kV Line : Line Cut-In to Cyclone Switch | Hopkins County | Cut in the Monticello - Farmersville 345 kV Line to establish the new Cyclone Switching Station | 2022-04-06 | 2022-11-17 |  |  | 4594824 |  |  | 99 | 345 | na | 0.9 | 2-1926.9 ACSS/TW Cumberland | Steel Poles/ Steel Towers | 170 | 0.9 | na | na | 25.101(c)(5)(A)
0PT44782 0PT46251 (R6153) | Brushy Creek Switch - Taylor Switch 138kV Line: Rebuild | City of Taylor, Williamson County | Rebuild the Brushy Creek - Taylor 138 kV line. | 2022-02-21 | 2022-12-15 |  |  | 18400000 |  |  | 97 | 138 | na | 11.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 11.4 | na | na | 25.101(c)(5)(B)
0PT44118 0PT44363 0PT44874 (R8580) | Johnson Draw POD - Flat Iron 138 kV Line | Midland County | Construct the new single-circuit 138 kV line connecting the Johnson Draw POD to the proposed Flat Iron Substation. | 2022-04-27 | 2022-08-10 | 2022-08-10 |  | 5257000 |  |  | 100 | na | 138 | 2.8 | 1926.9 ACSS/TW Cumberland | Steel or Concrete Poles | na | na | 70 | 2.8 | 25.101(c)(5)(A) | CCN Application Withdrawn on 10/21/21. Project is proceeding under 25.101(c)(5)(A) as an exempt project under SB 1281. Initial costs have been removed in accordance with the MCPR entry instructions.
0PT46586 | Preston North Sub - Meadow Creek Sub 138 kV Line : Rebuild/Replace Cathodic Protection System | City of Dallas, Dallas County | Replace the cathodic protection system on the Preston North - Meadow Creek 138 kV Line. | 2022-09-30 | 2022-10-01 | 2022-10-01 |  | 284469 |  |  | 100 | 138 | na | na | 1500 AL | na | na | na | na | na | 25.101(c)(5)(B)
0PT45398 | Farmersville Switch - Anna Switch 345 kV Line : Insulator Replacement | Collin County | Replace 411 existing polymer insulator assemblies with toughened glass insulator assemblies on the Farmersville - Anna Switch 345 kV Line. | 2022-11-12 | 2023-02-15 |  |  | 2244627 |  |  | 0 | 345 | na | 25 | (2) - 1590 ACSR Falcon | Steel Poles and Lattice | 160 | 25 | na | na | 25.101(c)(5)(B)
0PT42080 | DFW C East - DFW B East 138 kV Line: Pumping Plant Replacement | City of Dallas, Dallas County | Replace the pumping plant at DFW B East sub on the DFW C East - DFW B East 138 kV Line. | 2022-04-04 | 2022-06-17 | 2022-06-17 |  | 981132 |  |  | 100 | 138 | na | na | 1750 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT39816 | Stanton East Switch - Spraberry Switch 69 kV Line : CMPC Line Hardening (Str. 40/7 - 40/9) | City of Stanton, Martin County | Rebuild the section of the Stanton East Switch - Spraberry Switch 69 kV Line that crosses Interstate 20 in Martin County. | 2022-03-17 | 2022-04-07 | 2022-04-07 |  | 1191328 |  |  | 100 | 69 | na | 0.22 | 4/0 ACSR, 959 ACSS | Wood and Steel Pole | 50 | 0.22 | na | na | 25.101(c)(5)(B)
0PT46197 (R6187) | Sandow Switch - Temple Switch 138 kV Line: Install Tin Roof POD | City of Temple, Bell County | Provide a 138 kV point of delivery to the Rowan Green Data LLC. | 2022-03-18 | 2022-06-15 | 2022-06-15 |  | 1037180 |  |  | 100 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel H-Frame | 100 | 0.3 | 70 | 0.1 | 25.101(c)(5)(A)
0PT45401 (M4275) | Payne Switch - Royse City 138 kV Line: Greenbrier Switch Retermination | City of Princeton, Collin County | Reterminate the Payne Switch - Royse City 138 kV Line into newly established Greenbrier Switch station. | 2022-04-27 | 2022-06-20 | 2022-06-20 |  | 2278377 |  |  | 100 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.4 | na | na | 25.101(c)(5)(B)
0PT46715 | Paris Switch : Replace Auto Tertiary Bushing | City of Paris, Lamar County | Replace auto tertiary bushing. | 2021-11-10 | 2021-12-07 | 2021-12-07 |  | 204695 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Emergency / Failed Project
0PT46831 | Audelia Termination-Lake Highlands 138 kV: Install ISPs for Cathodic Protection | City of Dallas, Dallas County | Install ISPs for the Cathodic Protection System on the Audelia Sub - Lake Highlands 138 kV Line. | 2022-02-21 | 2022-03-01 | 2022-03-01 |  | 110936 |  |  | 100 | 138 | na | na | 600 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B) | Project 0PT45584 was broken into two separate work scopes. Cost estimate reflects work scope omitted from 0PT45584.
0PT46236 (R8581) | Wink Basin Tap No 1 East 69 kV Line: Structure 3/2 - Structure 4/1 69 kV Section Rebuild to 138 kV | City of Kermit, Winkler County | Rebuild the 1.0 mile Structure 3/2 - Structure 4/1 section of the Wink Switch - Keystone No 1 East 69 kV line. | 2022-03-15 | 2022-12-15 |  |  | 1555655 |  |  | 67 | 69 | 138 | 0.96 | 1926 ACSS/TW Cumberland | Steel Pole | 50 | 0.96 | na | na | 25.101(c)(5)(B) | Project previously placed on hold due to permitting; estimated start date updated to reflect initial date of project construction.
0PT46062 (R8581) | Wink Switch - Keystone No 1 East 69 kV Line: Shifting Sands Sub - Wink Gulf Tap 69 kV section rebuild structure 8/7 to Shifting Sands Sub | City of Kermit, Winkler County | Rebuild the 4.0 mile structure 8/7 to Shifting Sands section of the Wink Switch-Keystone No 1 East 69 kV line. | 2022-07-20 | 2022-12-15 |  |  | 6227141 |  |  | 55 | 69 | 138 | 4 | 1926 ACSS/TW Cumberland | Steel Pole | 50 | 4 | na | na | 25.101(c)(5)(B)
0PT45023 (M4071) | Cedar Crest Switch - Industrial Blvd Switch 138 kV Line : Reterminate at Compton Sub | City of Dallas, Dallas County | Reterminate the existing Cedar Crest Switch – Industrial Blvd Switch 138 kV Line into Compton Street Substation. The adjacent Cedar Crest Switch - Dealey Substation 138 kV Line will also have a structure replaced. | 2022-04-05 | 2022-05-16 | 2022-05-16 |  | 679452 |  |  | 100 | 138 | na | 0.2 | 959 ACSS/TW Suwannee | Steel Pole | 100 | 0.2 | na | na | 25.101(c)(5)(B)
0PT43740 | Nacogdoches-Chireno 138 kV: SH 21 @ Carizzo Creek Relocation for TxDOT | City of Lufkin, Angelina County | Replace existing wood pole H-frames with two (2) new single-circuit, concrete H-frame tangent structures (Str. 4/2 and 4/3). | 2022-05-10 | 2022-06-08 | 2022-06-08 |  | 591144 |  |  | 100 | 138 | na | 0.36 | 336 ACSR "Linnet" | Concrete H-Frame | 100 | 0.36 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT43246 | East Waco-West Waco, M&M Tap 138 kV: TxDOT Relocation for SH 6 @ Loop 340 | City of Waco, McLennan County | Relocation with new single circuit, steel monopole, tangent & swing angle structures. | 2022-04-04 | 2022-04-26 | 2022-04-26 |  | 1285252 |  |  | 100 | 138 | na | 0.33 | 1926 ACSS/TW Cumberland | Steel Pole | 100 | 0.33 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT46044 | Hillsboro Switch - Cleburne Switch 138 kV Line: Replace 5 poles and 14 arms | City of Cleburne, Hill County | Replacement of crossarms and poles on Hillsboro Switch - Cleburne Switch 138 kV Line. | 2021-09-07 | 2021-12-20 | 2021-12-20 |  | 190091 |  |  | 100 | 138 | na | 3.54 | 795 ACSR Drake | Wood H-Frame | 100 | 3.54 | na | na | 25.83(a)(3) | Project did not initially meet reporting criteria. However, project cost increased after the submittal of initial estimates and has been added to the MCPR in compliance with 25.83(a)(3).
0PT45707 0PT47747 (R8581) | Wink Switch - Wink Basin Sub 138 kV Line : 69 kV Conversion to 138 kV | City of Wink, Winkler County | Rebuild the 2.9 mile Wink Switch - Wink Basin 69 kV section on the Wink Switch - Keystone No 1 East 69 kV Line. | 2022-12-05 | 2022-12-15 | [5 empty] | 0 | 69 | 138 | 2.9 | 1926 ACSS/TW Cumberland | Steel Poles | 50 | 2.9 | na | na | 25.101(c)(5)(B)
0PT42081 | DFW C East - DFW B East 138 kV Line: Rebuild Cathodic Protection System | City of Dallas, Dallas County | Rebuild the Cathodic Protection System on the DFW C East - DFW B East 138 kV Line. | 2022-10-03 | 2022-10-08 | 2022-10-08 |  | 358970 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.101(c)(5)(B)
0PT43897 0PT43896 0PT48828 (R8570) | Eskota Switch - Sweetwater No. 2 Sub 69 kV Line: Rebuild | City of Sweetwater, Nolan County | Rebuilding 12.2 miles of double circuit wood poles with new steel poles. Installing one circuit. | 2022-06-16 | 2022-12-15 |  |  | 18576188 |  |  | 38 | 69 | na | 24.2 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 12.2 | na | na | 25.101(c)(5)(B)
0PT43959 0PT46325 (R985) | Caddo Mills Explorer Tap - Caddo Mills Explorer Sub 69 kV Line Rebuild | City of Caddo Mills, Hunt County | Rebuild the Caddo Mills Explorer Tap 69 kV Line. | 2022-06-09 | 2022-12-15 |  |  | 6069434 |  |  | 95 | 69 | 138 | 3 | 959.6 ACSS/TW Suwannee | Steel 2 - Pole, Steel Pole | Varies | 3 | na | na | 25.101(c)(5)(B)
0PT43958 (R985) | Burrow POI - Caddo Mills Explorer Tap 69 kV Line Rebuild | City of Caddo Mills, Hunt County | Rebuild a section from Caddo Mills Explorer Tap to Burrow POI of the Commerce Switch - Royse Switch 69 kV Line. | 2022-05-26 | 2022-12-15 |  |  | 10835669 |  |  | 88 | 69 | 138 | 4.5 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel H-Frame, Steel Pole | Varies | 4.5 | na | na | 25.101(c)(5)(B)
0PT43548 0PT49066 (R4028) | Baylor - Seymour 69 kV Line : Rebuild | Cities of Mabelle and Seymour, Baylor County | Rebuild the existing 15 mile single circuit wood pole Baylor - Seymour 69 kV line utilizing 138 kV double circuit steel poles with one circuit in place. | 2022-05-10 | 2022-10-30 |  |  | 25016336 |  |  | 76 | 69 | 138 | 15.1 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | 50 | 15.1 | na | na | 25.101(c)(5)(B)
0PT45995 (R2014) | Big Brown Switch - Richland Chambers Switch 345 kV Line : Raise Line for Pin Oak Switch 138 kV | City of Fairfield, Freestone County | Install one lattice tower to raise line for new Pin Oak Station. | 2022-04-18 | 2022-06-03 | 2022-06-03 |  | 871651 |  |  | 100 | 345 | na | 0.2 | 2-795 ACSR | Steel Lattice Tower | 375 | 0.1 | na | na | 25.101(c)(5)(A)
0PT46736 (M3010) | Rose Hill Switch - Rose Hill Tap 138 kV Line: Reterminate Rose Hill Station | City of Terrell, Kaufman County | Reterminate Rose Hill Switch - Rose Hill Tap 138 kV Line into new Rose Hill Switch Station. | 2022-03-18 | 2022-11-23 |  |  | 1007982 |  |  | 52 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.3 | 50 | 0.1 | 25.101(c)(5)(A)
0PT46332 0PT47028 (M3010) | Terrell South Switch-Rose Hill Switch 138 kV Line: Reterminate Rose Hill Station | City of Terrell, Kaufman County | Reterminate Terrell South Switch - Rose Hill Switch 138 kV Line into new Rose Hill Switch Station. | 2022-04-01 | 2022-11-23 |  |  | 879157 |  |  | 99 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT43898 (R8570) | Eskota Switch - Sweetwater No. 2 Sub 69 kV Line: Rebuild the U.S. Gypsum Sub Tap section | City of Sweetwater, Nolan County | Rebuild the 1.37 mile U.S. Gypsum Sub Tap section of the Eskota Switch - Sweetwater No. 2 Sub 69 kV line to DCSP with both circuits installed. | 2022-08-04 | 2022-12-15 |  |  | 2668839 |  |  | 99 | 69 | na | 2.8 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 1.4 | na | na | 25.101(c)(5)(B)
0PT47623 | Stephenville Switch - Comanche Switch 138 kV Line | City of Proctor, Comanche County | Replace crossarms and structures at various locations on the Stephenville Switch - Comanche Switch 138 kV Line. | 2022-05-01 | 2022-10-31 | 2022-10-31 |  | 220733 |  |  | 100 | 138 | na | 37.18 | 636 ACSR GROSBEAK | Wood H-Frame | 100 | 37.18 | na | na | 25.101(c)(5)(B)
0PT44353 | Royse Switch - Shamburger Switch 345 kV Line : install buzzard deterrents & replace insulators | City of Royse City, Rockwall County | Insulators/buzzard deterrents replaced on various structures on the Royse Switch - Shamburger Switch 345 kV Line. | 2022-05-02 | 2022-06-01 | 2022-06-01 |  | 340252 |  |  | 100 | 345 | na | 81.42 | 795 ACSR | Steel Lattice Tower | 150 | 81.42 | na | na | 25.101(c)(5)(B) | Project did not initially meet reporting criteria under 25.83(a)(3), however recent estimates indicate project cost will exceed $250,000.
0PT47151 | Ennis West Switch - Sterrett Sub 138 kV Line : HB4150 Clearance Remediation | City of Ennis, Ellis County | Replacing wood H-frame structures with taller H-frame structures, raising cross arms, replacing wood cross arms with steel cross arms, and removing bells from insulator assemblies on the Waxahachie Sub - S. Ennis Switch 138 kV Line. | 2022-05-10 | 2022-06-29 | 2022-06-29 |  | 310599 |  |  | 100 | 138 | na | 1 | 795 ACSR Drake | Wood H-Frame | 100 | 1 | na | na | 25.101(c)(5)(B)
0PT45724 0PT47700 (R8596) | Andrews North Sub - Mustang Sub 138 kV Line : Rebuild | Andrews County | Rebuild Andrews North Sub - Mustang Sub 138 kV Line. | 2022-06-17 | 2022-12-31 |  |  | 22845646 |  |  | 84 | 138 | na | 12.9 | 2 - 1926.9 ACSS/TW Cumberland | Steel Pole, Wood 3 - Pole | varies | 12.9 | na | na | 25.101(c)(5)(B)
16T64147 (R6151) | Little River-Holland 69 kV Line: Rebuild | City of Little River-Academy, Bell County | Rebuild the 9.1 mile Little River - Holland 69 kV Line | 2022-06-29 | 2022-12-15 |  |  | 11553237.91 |  |  | 99 | 69 | na | 9.1 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 9.1 | na | na | 25.101(c)(5)(B)
0PT46594 | Rivercrest Switch - Clarksville Switch 69 kV Line : Refurbish | Sulphur Springs County | Replacing cross-arms and insulators on the Rivercrest Switch - Clarksville Switch 69 kV Line. | 2022-09-19 | 2022-12-01 |  |  | 4979412.79 |  |  | 32 | 69 | na | 18.5 | 336 ACSR Linnet | Steel H-Frame, Steel Pole, Wood H-Frame | 100 | 18.5 | na | na | 25.101(c)(5)(B)
0PT45117 (R5156) | SL Clear Crossing (ETT) - Willow Creek Switch 345 kV Line: Cut-In to establish Thomas Price Switch | Young County | Cut-In to establish Thomas Price Switch. | 2022-10-27 | 2022-11-10 |  |  | 2626362 |  |  | 11 | 345 | na | 0.2 | 2- 1926 ACSS Cumberland | Steel Lattice Tower, Steel Pole | Varies | 0.1 | na | na | 25.101(c)(5)(A)
0PT46658 (R6143) | Sandow Switch - Taylor Sub 138 kV Line: Taylor Sub Retermination | City of Taylor, Williamson County | Reterminate the Sandow - Taylor 138 kV line at the Taylor Station | 2022-11-03 | 2022-12-15 |  |  | 795232 |  |  | 17 | 138 | na | 0.13 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.13 | na | na | 25.101(c)(5)(A)
0PT46739 0PT47643 (R8605) | Buzzard Draw – Lamesa Switch 138 kV line: Install Hardy Morgan POI for GSEC's New Ackerly Sub | City of Lamesa, Dawson County | Establish Hardy Morgan POI for GSEC's New Ackerly Sub. | 2023-02-13 | 2023-03-31 | [5 empty] | 0 | 138 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel 3- Pole, Steel H-Frame, Steel Pole | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT43900 (R6142) | Trinidad Sub - Navarro Switch 69 kV Line: Retermination into Creslenn Ranch Switch | City of Trinidad, Henderson County | Reterminate the Trinidad Switch - Navarro Switch from Trinidad Switch to the new Creslenn Ranch Switch | 2022-09-16 | 2022-12-15 |  |  | 1340348 |  |  | 99 | 69 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H-Frame | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT44949 (R6142) | Trinidad Switch - Palestine Switch 69 kV Line : Retermination into Creslenn Ranch | City of Trinidad, Henderson County | Reterminate the Trinidad Switch - Palestine Switch from Trinidad Sw to the new Creslenn Ranch Switch | 2022-09-15 | 2022-12-15 |  |  | 1121398 |  |  | 99 | 69 | na | 0.2 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole | 70 | 0.2 | na | na | 25.101(c)(5)(A)
0PT46339 0PT47740 (R8611) | Quarry Field Switch - Wink Switch 138 kV Line : Install Yantis Ranch POD for WPX Energy Permian's Monument Draw North Substation | City of Wink, Winkler County | Establish Yantis Ranch POD for WPX Energy Permian's Monument Draw North Substation. | 2022-10-14 | 2022-11-15 |  |  | 2175797.5 |  |  | 96 | 138 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel H-Frame, Steel Pole | 50 | 0.1 | 100 | 0.2 | 25.101(c)(5)(A)
0PT43312 0PT46324 (R8558) | Midland County Northwest Switch - Texaco Mabee Tap 138 kV Line : Rebuild | City of Midland, Midland County | Rebuild the Midland County NW Switch - Texaco Mabee Tap 138 kV Line. | 2022-08-24 | 2022-12-15 |  |  | 13082826 |  |  | 53 | 138 | na | 13 | 1926.9 ACSS/TW/HS Cumberland | Steel 2 - Pole, Steel 3 - Pole, Steel H-Frame, Steel Pole | 75 | 6.55 | na | na | 25.101(c)(5)(B)
0PT42879 0PT47805 (R4015) | Bellevue Sub - Bowie Sub 69 kV Line: Rebuild Smith Creek Sub - Tower One Sub 138 kV Line | City of Bowie, Montague County | Rebuild the 10-mile Smith Creek - Tower One 138 kV Line Section of the Burnett - Bowie 69 kV Line using a conductor rated 1649 A or greater. New 138 kV double-circuit structures with one circuit in place will be installed. | 2022-06-08 | 2022-12-15 |  |  | 11036755 |  |  | 80 | 69 | 138 | 10 | 959.6 ACSS/TW/HS Suwannee | Steel Pole | 50 | 10 | na | na | 25.101(c)(5)(B)
0PT45364 0PT44946 | Wedgwood Switch - Pafford St Switch 138 kV Line : Line Retermination Into New Rosemont Switch | City of Fort Worth, Tarrant County | Reterminate the Wedgwood Switch – Pafford Street Switch 138 kV Line at its new terminal location at the Rosemont Switch. | 2022-11-06 | 2022-12-15 |  |  | 2591809 |  |  | 0 | 138 | na | 0.5 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 55 | 0.25 | 25.101(c)(5)(D)
OPT47396 (R4028) | Seymour Tap - Olney BEPC Switch 69 kV Line : Relocation of 3 Structures | City of Seymour, Baylor County | Relocation and replacement of structure on Seymour Tap - Olney BEPC Switch 69 kV Line. | 2022-10-21 | 2022-10-30 |  |  | 597852 |  |  | 11 | 69 | na | 0.11 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | 50 | 0.11 | 25.101(c)(5)(B)
0PT44759 (M4320) | Bardwell Switch - Italy Sub 69 kV Line : Rebuild | City of Forreston, Ellis County | Rebuild the Bardwell Lake Switch - Italy section of the Hillsboro - Waxahachie 69 kV Line. Bundle existing circuits of the Italy - Hillsboro section of the Hillsboro - Waxahachie 69 kV Line. | 2022-07-25 | 2022-12-15 |  |  | 11790246 |  |  | 38 | 69 | 138 | 6.1 | 959.6 ACSS/TW/HS Suwannee | Steel Pole | 80 | 6.1 | na | na | 25.101(c)(5)(B)
0PT45495 0PT43815 (M5172) | Handley Switch - Executive Parkway Switch 138 kV Line : Reconductor the Hurst Sub - International Airport Sub 138 kV Line | City of Fort Worth, Tarrant County | Reconductor the Handley Switch - Executive Parkway Switch 138 kV Line between the Hurst Substation - International Airport Substation. | 2022-09-12 | 2022-12-15 |  |  | 6709213 |  |  | 5 | 138 | na | 11.2 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | 100 | 11.2 | na | na | 25.101(c)(5)(B)
0PT46733 (M5172) | BEPC Flat Rock Tap Switch – BEPC Flat Rock Substation: Rebuild 138 kV Line Section using a conductor rated 2569 A or greater. | City of Weatherford, Parker County | Rebuild the 4.1 mile Oncor owned section of the 6.4-mile Weatherford – BEPC Flat Rock Substation+H308 138 kV Line. | 2022-08-02 | 2022-12-15 |  |  | 7584140 |  |  | 82 | 138 | na | 8.2 | 1926 ACSS/TW Cumberland | Steel Pole | 50 | 4.1 | na | na | 25.101(c)(5)(B)
0PT43481 0PT45336 (M5172) | Weatherford Switch – BEPC Flat Rock Tap Switch 138 kV Line: Rebuild 138 kV Line Section using a conductor rated 2569 A or greater. | City of Weatherford, Parker County | Rebuild the 2.3-mile Oncor owned section of the 6.4-mile Weatherford – BEPC Flat Rock Substation 138 kV Line. | 2022-07-07 | 2022-12-15 |  |  | 4046457.61 |  |  | 23 | 138 | na | 2.3 | 1926 ACSS/TW Cumberland | Steel H-Frame, Steel Pole | 50 | 2.3 | na | na | 25.101(c)(5)(B)
0PT43447 0PT46560 (R2014) | Trinidad Switch - Fairfield West - Long Lake Sub 138 kV Line : Rebuild from Big Brown Tap to Pin Oak Switch 138 kV | City of Trinidad, Henderson County | Rebuild Trinidad Switch-Fairfield West-Long Lake from Big Brown Tap over to structure 4/9 and new cut-in for Pin Oak Switch. | 2022-09-15 | 2022-12-15 |  |  | 9101916 |  |  | 33 | 138 | na | 8 | 1926 ACSS/TW Cumberland | Steel H-Frame, Steel Pole | 225 | 3.5 | 225 | 0.5 | 25.101(c)(5)(B)
0PT46569 | Big Spring Switch - Gunsight Switch 138 kV Line : Crossarm Replacement | City of Big Spring, Howard County | Replace 80 structures on and all crossarms on Big Spring - China Grove - Gunsight 138 kV line. | 2022-09-22 | 2022-12-31 |  |  | 8846141 |  |  | 50 | 138 | na | 57 | 636 ACSR Grosbeak | Wood H-Frame | Varies | 57 | na | na | 25.101(c)(5)(B)
0PT45684 | D East 1- D East 2 138 kV Line: Rebuild Cathodic Protection | City of Dallas, Dallas County | Rebuild the Cathodic Protection System on the D East 1- D East 2 138 kV Line. | 2022-10-27 | 2022-12-30 |  |  | 347454 |  |  | 99 | na | na | na | na | na | na | na | na | na | 25.101(c)(5)(B)
0PT46166 (R6142) | Trinidad Switch 69 kV Line to Power Plant | City of Trinidad, Henderson County | Reterminate the Luminant Power Plant 69kV from Trinidad Switch to a new POI from the Navarro Switch - Creslenn Ranch Switch 69kV Line | 2022-09-23 | 2022-12-15 |  |  | 508558 |  |  | 97 | 69 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT46165 (R6142) | Trinidad Switch 138 kV Interconnection Line to Trinidad Autotransformer | City of Trinidad, Henderson County | Line work associated to demolish the Trinidad Switch 69 kV yard, connections remain the same, new structures needed | 2022-09-09 | 2022-12-15 |  |  | 787396 |  |  | 51 | 138 | na | 0.1 | 795 ACSR Drake | Steel 3 - Pole | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT46163 (6142) | Creslenn Ranch Switch - Trinidad Switch 69 kV Line :New Interconnection | City of Trinidad, Henderson County | Reterminate the Trinidad Switch 69kV Auto Line, create new Creslenn Ranch Switch to Trinidad Switch 69kV Line | 2022-09-07 | 2022-12-15 |  |  | 536847 |  |  | 67 | 69 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT45941 | Wichita Falls South Switch - Burnett Switch 138 kV Line : CMPC Line Hardening (Str. 7/3 - 7/8) | City of Wichita Falls, Wichita County | Rebuild a section of the Wichita Falls South—Burnett 138 kV line that crosses US-287 in Wichita County. | 2022-11-08 | 2022-12-15 |  |  | 1874557 |  |  | 22 | 138 | na | 0.5 | 959.6 ACSS/TW Suwannee | Steel Pole, Wood H-Frame | 50 | 0.5 | na | na | 25.101(c)(5)(B)
0PT44950 (R6142) | Trinidad Switch - Athens Switch 69 kV Line : Retermination into Creslenn Ranch | City of Trinidad, Henderson County | Reterminate the Trinidad Switch - Athens Switch from Trinidad Switch to the new Creslenn Ranch Switch | 2022-11-02 | 2022-12-15 |  |  | 478539 |  |  | 99 | 69 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel H-Frame | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT46950 0PT48085 (R8612) | Odessa EHV Switch - Monahans - Wolf Switch: Line work for Dry Wind Tap to Sandhills Sub | City of Monahans, Crane County | Establish the Dry Wind Tap and install the new circuit from Dry Wind Tap to Sandhills Sub | 2022-11-12 | 2022-12-16 |  |  | 3706579 |  |  | 0 | 138 | na | 8.5 | 1926.9 ACSS/TW Cumberland | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 8.1 | varies | 0.4 | 25.101(c)(5)(A)
0PT46954 (R8612) | Wolf Switch - General Tire Switch: Rebuild Sandhills Tap – Sandhills Substation 138 kV line section using double-circuit structures | City of Monahans, Crane County | Rebuild the Sandhills Tap – Sandhills Sub 138 kV line | 2022-09-12 | 2022-12-15 |  |  | 11133776 |  |  | 18 | 138 | na | 8 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | 50 | 7.8 | varies | 0.2 | 25.101(c)(5)(B)
0PT47613 (R8612) | Wolf Switch - General Tire Switch: Rebuild Sandhills Tap – Dry Wind Tap 138 kV line section using double-circuit structures | City of Monahans, Ector and Crane County | Rebuild the Sandhills Tap - Dry Wind Tap line section on the Wolf Switch - General Tire Switch 138 kV line | 2023-01-02 | 2023-05-15 | [5 empty] | 0 | 138 | na | 3.5 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | 50 | 3.3 | varies | 0.2 | 25.101(c)(5)(B)
0PT47493 | Sulphur Springs Switch - Canton Switch 138 kV Line : Replace Cross Arms, Insulators & Poles. | City of Emory, Hopkins County, Rains County | Replacement of cross arms, insulators and poles on various structures on the Sulphur Springs Switch - Canton Switch 138kV Line. | 2022-10-17 | 2022-11-30 |  |  | 379903 |  |  | 99 | 138 | na | 5.38 | 636 ACSR Grosbeak | Wood H-Frame | 100 | 5.38 | na | na | 25.101(c)(5)(B)
0PT46660 (R6143) | Temple Sub - Taylor Sub 69 kV Line: Taylor Sub Retermination | City of Taylor, Williamson County | Reterminate the Temple - Taylor 69 kV line at the Taylor Station | 2022-11-03 | 2022-12-15 |  |  | 1002659 |  |  | 51 | 69 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel Pole, Wood Pole | Varies | 0.1 | na | na | 25.101(c)(5)(A)
0PT46830 (R8610) | Sandhills Tap - Sandhills Sub 138 kV Line: Schumm POD for Blackbeard Operating, LLC | City of Monahans, Crane County | Provide a 138 kV point-of-delivery (POD) for Blackbeard Operating, LLC on the Sandhills Tap - Sandhills 138 kV Line Section. | 2022-10-12 | 2022-12-01 |  |  | 2089938 |  |  | 41 | na | 138 | 0.2 | 1926.9 ACSS/TW Cumberland | Steel 3-Pole, Steel H-Frame, Steel Pole | na | na | 70 | 0.2 | 25.101(c)(5)(A)
0PT46632 (R8604) | Horseshoe Springs Switch - Three Mile Draw Switch 138 kV Line : Install Crater Rock Switch for Hayhurst Texas Solar's Allen Sub | City of Orla, Culberson County | Cut-in for Crater Rock 138 kV Switch on the Horseshoe Springs Switch - Three Mile Draw Switch 138 kV Line. | 2022-11-07 | 2022-12-15 |  |  | 1437763 |  |  | 0 | na | 138 | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | varies | 0.2 | 25.101(c)(5)(A)
0PT46847 (R8609) | Spraberry Switch - Polecat Switch 138 kV line: Meyers Draw POD for Endeavor's Battle Tex Sub | City of Midland, Midland County | Establish Meyers Draw Point of Delivery (POD) to Endeavor Energy's Battle Tex Substation on the Sprayberry - Polecat 138 kV Line | 2022-11-07 | 2022-12-02 |  |  | 3375632 |  |  | 0 | 138 | na | 0.5 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel H-Frame, Steel Pole | 50 | 0.3 | varies | 0.2 | 25.101(c)(5)(A)
0PT46323 | Valley South Sub - Farmersville Switch 345 kV Line: Erosion Control at Structure 24/2 | City of Blue Ridge, Collin County | Relocate structure 24/2 on the Valley South Sub - Farmersville Switch 345 kV Line | 2022-10-18 | 2022-12-09 |  |  | 819869 |  |  | 34 | 345 | na | 0.2 | 795 ACSR Drake | Steel Lattice Tower | 170 | 0.1 | na | na | 25.101(c)(5)(B)
0PT47860 | Leon Switch - Deleon Sub 69 kV Line : Storm Restoration | City of Gorman, Eastland County | Rebuild the Leon Switch - Deleon Sub 69 kV line due to west Texas fires. | 2022-03-18 | 2022-05-01 | 2022-05-01 |  | 1285620 |  |  | 100 | 69 | na | 4.29 | #2 CU | Wood Pole | 50 | 4.29 | na | na | 25.101(c)(3) | Storm project
0PT47169 (R8622) | Quarry Field Switch - Wink Switch 138 kV Line : Install Ashby POD for Energy Transfer's WT2 Sub | Wink County | Establish the point of delivery (POD) to Energy Transfer's WT2 Substation on the Quarry Field Switch – Wink Switch 138 kV Line | 2022-10-28 | 2023-02-01 |  |  | 2392691 |  |  | 20 | 138 | na | 0.5 | 1926.9 ACSS/TW Cumberland | Steel H-Frame, Steel Pole | 50 | 0.3 | 70 | 0.2 | 25.101(c)(5)(A)
0PT39815 0PT43848 | Stanton East Switch - Spraberry Switch 69 kV Line : CMPC Line Hardening (Str. 26/11 & 26/12) | City of Stanton, Martin County | Rebuild the section of the Stanton East Switch - Spraberry Switch 69 kV Line that crosses IH-20 in Midland, TX. | 2022-11-04 | 2022-12-31 |  |  | 386820 |  |  | 0 | 69 | na | 0.23 | 4/0 ACSR Penguin | Concrete Pole, Wood Pole | 50 | 0.23 | na | na | 25.101(C)(5)(B)
0PT43962 (R985) | Scatter Branch Sub - Caddo Mills Explorer Tap 69 kV Line: Rebuild Scatter Branch - Caddo Mills Explorer Tap | City of Greenville, Hunt County | Rebuild from Scatter Branch Sub to Caddo Mills Explorer Tap of the Commerce Switch - Royse Switch 69 kV Line. | 2022-10-17 | 2023-05-15 |  |  | 30785002 |  |  | 6 | 69 | na | 19.1 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 19.1 | na | na | 25.101(c)(5)(B)
0PT48235 | Jewett Switch - Brown Mag Sub 69 kV Line : Replace 9 Poles and 10 Cross Arms Energized | Leon County | Replace Poles and Cross Arms Jewett Switch - Brown Mag Sub 69 kV Line. | 2022-08-22 | 2022-11-18 |  |  | 372814 |  |  | 10 | 69 | na | 9.95 | 4/0 ACSR Penguin | Wood H-Frame | 50 | 9.95 | na | na | 25.101(c)(5)(B)
0PT48231 | Windthorst Switch - Rice Switch 138 kV Line : 2022 Summer Work- Replacing poles, cross arms, and x- braces on multiple structures | Archer County | Replace poles, cross arms, and x- braces on various structures on Windthorst Switch - Rice Switch 138 kV Line. | 2022-07-01 | 2022-12-31 |  |  | 319573 |  |  | 99 | 138 | na | 11.46 | 336 ACSR Linnet | Wood H-Frame | 50 | 11.46 | na | na | 25.101(c)(5)(B)
0PT46946 (M5222) | Marrs Switching Station – Rolling Hills Substation 138 kV Line: Re-terminate the Marrs Switching Station – Rolling Hills Substation 138 kV Line at Marrs Switching Station | City of Fort Worth, Tarrant County | Re-terminate the Marrs Switching Station – Rolling Hills Substation 138 kV Line at a new terminal location in the Marrs Switching Station to accommodate the for the new Marrs Switching Station | 2023-03-20 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 0.2 | na | na | 25.101(c)(5)(B)
0PT46934 (R8498) | Midland East Sub - Spraberry Switch 138 kV Line : Cut in to Consavvy Switch | City of Midland, Midland County | Loop in the existing Midland East Sub - Spraberry Switch 138 kV Line into Consavvy 138 kV Switch. | 2022-11-14 | 2022-12-31 |  |  | 1278057 |  |  | 0 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 75 | 0.1 | na | na | 25.101(c)(5)(A)
0PT46033 | Kemp Ranch Switch - Sardis Switch 138 kV Line : Reterminate at Midlothian South Sub | City of Midlothian, Ellis County | Reterminate the Kemp Ranch Switch - Sardis Switch 138 kV Line at Midlothian South Sub | 2022-11-07 | 2022-12-15 |  |  | 1502626 |  |  | 0 | 138 | na | 0.7 | 959.6 ACSR/TW Suwannee | Steel Pole, Wood H-Frame | 100 | 0.7 | na | na | 25.101(c)(5)(A)
0PT45940 | Wichita Falls North Switch - Pleasant Valley Switch 69 kV Line : CMPC Line Hardening (Str. 2/12 - 2/15) | City of Wichita Falls, Wichita County | Rebuild a section of the Wichita Falls North Switch to Pleasant Valley Switch 69 kV across Interstate 44 in Wichita County. | 2022-10-13 | 2022-12-15 |  |  | 704094 |  |  | 99 | 69 | na | 0.2 | 336.4 ACSR Linnet | Steel Pole, Wood Pole | 40 | 0.2 | na | na | 25.101(c)(5)(B)
0PT45939 | Burnett Switch - Pleasant Valley Switch 69 kV Line : CMPC Line Hardening (Str. 4/11 - 4/14) | City of Wichita Falls, Wichita County | Rebuild the section of the Burnett Switch - Pleasant Valley Switch 69 kV Line that crosses Interstate 44. | 2022-10-26 | 2022-12-15 |  |  | 1139681 |  |  | 36 | 69 | na | 0.32 | 636 ACSR Grosbeak | Steel Pole, Wood Pole | varies | 0.32 | na | na | 25.101(c)(5)(B)
0PT45538 | Audelia Termination- Lake Highlands 138 kV Line: U.G. Termination Replacement | City of Dallas, Dallas County | Replace the 138 kV Underground Transmission Terminations at Audelia and Lake Highlands Sub. | 2022-11-07 | 2022-12-30 |  |  | 785485 |  |  | 0 | 138 | na | na | 600 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT45138 (R6164) | Brownwood - Coleman Co. 69 kV and 138 kV Line : Reterminate 138 kV line into Bangs Sub due to Station Rebuild | City of Bangs, Brown County | Line work associated with converting Bangs substation to 138 kV. The work is occurring on the Brownwood - Coleman County 69 kV and 138 kV line. | 2022-11-14 | 2022-12-17 |  |  | 1199052 |  |  | 0 | 138 | na | 0.6 | 959.6 ACSS/TW Suwanne 336.4 ACSR Linnet | Steel Pole | varies | 0.3 | na | na | 25.101(c)(5)(A)
0PT44570 (R6160) | Corsicana Sub to Navarro Sub 138 kV Line: Re-terminate at Revolution Switch | City of Corsicana, Navarro County | Modify the Corsicana Substation CB 15015/15020 – Navarro Substation 138 kV transmission line. | 2024-01-10 | 2024-04-15 | [5 empty] | 0 | 138 | na | 0.15 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 100 | 0.15 | 25.101(c)(5)(B)
0PT44528 0PT44520 (R3022) | SL Ogallala - Tule Canyon 345 kV Line: Kress Switch Interconnection | City of Kress, Kress County | Cut-In the Ogallala - Tule Canyon 345 kV Line to establish the new Kress Switch. | 2022-10-03 | 2022-12-01 |  |  | 1891641 |  |  | 9 | 345 | na | 0.1 | 2 -1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 160 | 0.1 | na | na | 25.101(c)(5)(A)
0PT43720 (R6141) | Lake Creek Switch - Waco West Switch 138 kV Line : Reterminate at Peppervine Switch | City of Waco, McLennon County | Retermination into new Peppervine Switch | 2023-03-03 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 80 | 0.1 | na | na | 25.101(c)(5)(B)
0PT43678 (R6144) | Brownwood Sub - Dublin Sub 69 kV Line : Proctor Sub Removal | City of Proctor, Comanche County | Remove connector to Proctor Substation to accommodate the removal and decommissioning of Proctor Station | 2022-11-28 | 2022-12-17 |  |  | 250000 |  |  | 0 | 69 | na | 0.1 | #1 Cu | Wood Pole | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT43477 (M4122) | Desoto Switch - Sterrett Switch 138 kV Line: Rebuild Desoto to Glenn Heights (BEC) | City of Glenn Heights, Dallas and Ellis County | Rebuild the Desoto to Glenn Heights section of the Desoto to Sterrett 138 kV line | 2022-09-27 | 2022-12-05 |  |  | 4013639 |  |  | 35 | 138 | na | 2.1 | 1926.9 ACSS/ TW Cumberland | Steel 3 - Pole, Steel Pole | 100 | 2.1 | na | na | 25.101(c)(5)(B)
0PT43948 0PT46138 (M4236) | Royse Switch - Rowlett Sub 138 kV Line : Reconductor Fate Sub to Creekside Sub | Royse City, Rockwall County | Reconductor the Fate Sub - Rowlett Sub section of the Royse Switch - Rowlett 138 kV Line. | 2022-09-30 | 2022-12-15 |  |  | 13223812 |  |  | 76 | 138 | na | 8.52 | 2-959.6 ACSS/TW Suwannee | Steel H-Frame, Steel Pole | Varies | 8.52 | na | na | 25.101(c)(5)(B)
0PT46763 (M4175) | Lancaster Sub - Desoto Pleasant Run 138 kV Line Reconductor | City of Desoto, Dallas County | Reconductor the 3.6-mile Lancaster Sub - Desoto Pleasant Run section of the Watermill - Cedar Hill 138 kV Line | 2022-11-07 | 2022-12-23 |  |  | 4973307 |  |  | 0 | 138 | na | 3.6 | 959.6 ACSS/TW/E3X Suwannee | Steel Pole | Varies | 3.6 | na | na | 25.101(c)(5)(B)
0PT45103 (M4175) | Reindeer Sub - Lancaster Sub 138 kV Line: Reconductor | City of Lancaster, Dallas County | Reconductor the Reindeer Sub - Lancaster Sub 138 kV line section | 2022-09-06 | 2022-12-15 |  |  | 3604361 |  |  | 97 | 138 | na | 2.6 | 959.6 ACSS/TW/E3X Suwannee | Steel Pole | Varies | 2.6 | na | na | 25.101(c)(5)(B)
0PT46762 (M4175) | Watermill Switch - Reindeer Sub 138 kV Line: OPGW Replacement | City of Lancaster, Dallas County | Replace the existing shield wire on the Watermill Switch - Reindeer Sub section of the Watermill Switch - Cedar Hill Switch Sub 138 kV Line. | 2022-09-19 | 2022-12-15 |  |  | 757645 |  |  | 99 | 138 | na | 2.6 | na | na | Varies | 2.6 | na | na | 25.101(c)(5)(B)
0PT46646 (R6183) | Hillsboro Switch - Navarro Switch 138 kV Line: Install Ash Creek Switch for Pitts Dudik Solar | City of Hubbard, Hill County | Cut in the Navarro - Hillsboro 138 kV Line to establish the new Ash Creek Switch Station. | 2023-02-25 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.31 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.25 | 195 | 0.06 | 25.101(c)(5)(A)
0PT46529 (R6185) | Trinidad Switch - Navarro Switch 138 kV Line : Cut-In for Long Prairie Switch | City of Navarro, Navarro County | Cut in the Trinidad Switch - Navarro Switch 138 kV Line to establish the new Long Prairie Switch Station. | 2022-10-20 | 2022-11-18 |  |  | 1426002 |  |  | 34 | 138 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 190 | 0.2 | 180 | 0.06 | 25.101(c)(5)(A)
0PT42423 (M4346) | Rivercrest Switch - Paris Switch 138 kV Line : Eiffel Solar Interconnect at Hawk Hollow Switch | City of Paris, Lamar County | Cut in the Rivercrest Switch - Paris Switch and Paris Switch - Tenaska - Lamar Blossom 138kV Lines to establish the new Hawk Hollow Switch Station. | 2022-09-29 | 2022-12-15 |  |  | 2121374 |  |  | 34 | 138 | na | 0.16 | 959.6 ACSS/TW/HS Suwannee | Steel Pole | 100 | 0.06 | 340 | 0.02 | 25.101(c)(5)(A)
0PT46497 (M3009) | Paris Switch - Commerce Switch 138 kV Line: Cut-in to establish Crossroads Switch | City of Enloe, Delta County | Cut in the Paris Switch - Commerce Switch 138 kV Line to establish Crossroads Switch Station. | 2022-10-25 | 2022-11-17 |  |  | 1656164 |  |  | 34 | 138 | na | 0.14 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.01 | 180 | 0.04 | 25.101(c)(5)(A)
0PT39029 | Hurst - Bell 138 kV Line: Bell Helicopter POD | City of Hurst, Tarrant County | This project will reterminate the Hurst to Bell 138 kV Line into the new Bell Helicopter Owned Sub. | 2022-08-05 | 2022-12-31 |  |  | 729841 |  |  | 71 | 138 | na | 0.15 | 795 ACSR Drake | Steel Pole | 40 | 0.1 | 70 | 0.05 | 25.101(c)(5)(A)
0PT46901 (R8574) | Pegasus South Tap - Quickriver Tap 138 kV Line | City of Odessa, Midland County | Rebuild the Pegasus South Tap - Quickriver Tap 138 kV Line on double-circuit structures with one circuit in place from Pegasus South Tap to Quickriver tap. Cut in the Pegasus South Tap to Pegasus South 138 kV Line to establish the new Quickriver Tap. | 2022-10-05 | 2023-03-31 |  |  | 8987319 |  |  | 19 | 138 | na | 5.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 5.1 | na | na | 25.101(c)(5)(B)
0PT46966 (R8574) | Pleasant Farms - Pegasus South Tap 138 kV Line | City of Odessa, Midland County | Rebuild the Pleasant Farms - Pegasus South Tap 138 kV Line on double-circuit structures with one circuit in place from Pleasant Farms - Pegaus South Tap. | 2022-11-14 | 2023-03-31 |  |  | 8454264 |  |  | 0 | 138 | na | 4 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | Varies | 4 | na | na | 25.101(c)(5)(B)
0PT41809 0PT47334 (R8607) | SL NTUSU SU Glass Ranch Switch - Sale Ranch Switch 138 kV Line : Red Sand POD for Endeavor's Tiger Sub | City of Midland, Martin County | Establish Red Sand Point of Delivery (POD) to Endeavor Energy's Tiger Substation on Glass Ranch Switch - Sale Ranch Switch 138 kV Line | 2022-09-26 | 2022-11-15 |  |  | 2116406 |  |  | 51 | 138 | na | 0.81 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel H-Frame, Steel Pole | 100 | 0.5 | Varies | 0.34 | 25.101(c)(5)(A)
0PT47762 0PT48228 (R6174) | McGregor Phillips-Harris Creek 138 kV : Rebuild | City of McGregor, McLennan County | Rebuild section of Waco West to McGregor Phillips 69 kV to establish new Harris Creek Station. | 2022-10-17 | 2022-12-31 |  |  | 3647064 |  |  | 34 | 69 | 138 | 1.35 | 1926 ACSS/TW Cumberland | Steel Pole | Varies | 1.35 | na | na | 25.101(c)(5)(A)
0PT43677 0PT48461 (R6144) | Stephenville Switch - Comanche Switch 138 kV Line : Sabana Substation Cut-In | City of Proctor, Comanche County | Line work associated with connecting the new 138kV Sabana Substation. | 2022-10-05 | 2022-11-01 | 2022-11-01 |  | 1194221 |  |  | 100 | 138 | na | 0.25 | 959.6 ACSS/TW Suwannee | Steel Pole | 100 | 0.25 | na | na | 25.101(c)(5)(A)
0PT43718 (R6141) | Waco West Switch - Waco East Switch - Elm Mott Switch 138 kV Line : Reterminate at Peppervine Switch | City of Waco, McLennan County | Retermination into new Peppervine Switch | 2023-03-03 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.2 | 1926.9 ACSS/TW/HS Cumberland | Steel Pole | 80 | 0.2 | na | na | 25.101(c)(5)(B)
0PT43719 (R6141) | Waco West Switch - McGregor Phillips - Temple Elm Creek Switch 138 kV Line : Reterminate at Peppervine Switch | City of Waco, McLennon County | Retermination into new Peppervine Switch | 2023-03-03 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 80 | 0.2 | na | na | 25.101(c)(5)(B)
0PT43721 (R6141) | Waco East Sub - Waco West Switch 138 kV Line : Reterminate at Peppervine Switch | City of Waco, McLennon County | Retermination into new Peppervine Switch | 2023-03-03 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | 80 | 0.2 | na | na | 25.101(c)(5)(B)
0PT43727 (R6141) | Waco West Switch - Waco West Sub 138 kV Line : Reterminate at Peppervine Switch | City of Waco, McLennan County | Retermination into new Peppervine Switch | 2023-03-01 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 80 | 0.2 | na | na | 25.101(c)(5)(C)
0PT43691 0PT48058 (R6147) | Waco East Switch - Bellmead Sub 69kV Line: Conversion to 138 kV | City of Waco, McLennan County | Conversion to 138 kV as a part of rebuilding the Waco East Switch - Elm Mott Switch 69 kV line conversion to 138 kV operation | 2022-09-11 | 2022-12-01 |  |  | 9173498 |  |  | 29 | 69 | 138 | 3.8 | 1926.9 kcmil ACSS/TW Cumberland | Steel Pole | 70 | 3.8 | na | na | 25.101(c)(5)(B)
0PT47250 | Oakland Sub - Medill Terminal Sub 138 kV Line : Add OPGW | City of Dallas, Dallas County | Install OPGW and 4 splice boxes from Oakland Sub to Medill Terminal Sub. | 2022-11-28 | 2022-12-16 |  |  | 613962 |  |  | 0 | 138 | na | 2.53 | 336 ACSR Linnet | Steel Pole | Varies | 2.53 | na | na | 25.101(c)(5)(A)
0PT47314 (R8498) | Longshore Switch - Odessa EHV Sub 345 kV Line: Cut-In to establish Consavvy Switch | City of Midland, Midland County | Cut-in the Longshore Switch - Odessa EHV Sub double circuit 345 kV line to establish the new Consavvy Switch. | 2022-08-20 | 2022-12-31 |  |  | 1748991 |  |  | 67 | 345 | na | 0.1 | 2-1926.9 ACSS/TW/HS Cumberland | Steel Lattice Tower | 120 | 0.1 | na | na | 25.101(c)(5)(A)
0PT46941 (R8498) | Morgan Creek Switch - Quail Switch 345 kV Line : Cut-In to establish Consavvy Switch | City of Midland, Midland County | Cut-In the Morgan Creek Switch - Quail Switch double circuit 345 kV line into the new Consavvy Switch. | 2022-10-07 | 2022-12-31 |  |  | 2351854 |  |  | 67 | 345 | na | 0.1 | 2-1926.9 ACSS/TW/HS Cumberland | Steel Lattice Tower | 120 | 0.1 | na | na | 25.101(c)(5)(A)
0PT46936 (R8498) | Spraberry Switch - Stanton East Switch 69 kV Line : Reroute around Consavvy Switch | City of Midland, Midland County | Rebuild 0.6 miles of the Spraberry Switch - Stanton East Switch 69kV line around Consavvy 138 kV Switch Station. | 2022-10-25 | 2022-12-31 |  |  | 2104393 |  |  | 22 | 69 | na | 0.6 | 1926.9 ACSS/TW/HS Cumberland | Steel Pole | 50 | 0.6 | na | na | 25.101(c)(5)(B)
0PT47089 (R6206) | Leon Switch - Cisco 138 kV Line: Retermination into Mountain Branch Sub | City of Eastland, Eastland County | Re-terminate into the New Mountain Branch Sub | 2022-11-07 | 2023-05-15 |  |  | 499908 |  |  | 0 | 138 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel Poles | Varies | 0.1 | na | na | 25.101(c)(5)(B)
0PT48284 | Tyler Grande Switch - Overton Sub : 138 kV pole/arm replacement | City of Tyler, Smith County | Replacement of various poles and crossarm on Tyler Grande Switch - Overton Sub line. | 2022-08-01 | 2022-12-30 |  |  | 237625 |  |  | 99 | 138 | na | 16.24 | 4/0 CU Penguin | Wood H-Frame | 100 | 16.24 | na | na | 25.101(c)(5)(B)
0PT44965 (R8479) | Sargent Road Switch - Industrial Blvd Switch 138 kV Line : Rebuild | City of Dallas, Dallas County | Yucca Drive Switching Station – Northern Natural Sub 69 kV Line to establish the new Courtney Creek 138 kV Switching Station | 2024-01-01 | 2024-05-15 | [5 empty] | 0 | 69 | 138 | 1.6 | 1926 ACSS/TW Cumberland | Steel Pole | 70 | 0.3 | 70 | 0.5 | 25.101(c)(5)(C)
0PT48355 0PT49178 (R8530) | Moss Switch - Red Lakes Switch 138 kV Line : Rebuild | Odessa County | Rebuild the 14.0 mile Moss Switch - Red Lakes Switch 138 kV line. | 2023-01-02 | 2023-06-30 | [5 empty] | 0 | 138 | na | 14 | 1926.9 ACSS/TW/HS Cumberland | Steel H - Pole, Steel Pole | 70 | 14 | na | na | 25.101(c)(5)(A)
0PT46925 (R8624) | Barber Lake Switch - Morgan Creek Switch 138 kV Line : Install Moser Canyon POD for PPM Data's Project Frontier | City of Colorado City, Mitchell County | Rebuild 0.4-miles of the Barber Lake Switch - Morgan Creek Switch 138kV Line East Circuit to establish the Moser Canyon point of delivery (POD) from PPM Data’s Project Frontier Substation. | 2023-02-20 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.4 | 1926.9 ACSS/TW/HS Cumberland | Steel 3 - Pole, Steel H-Frame, Steel Pole | na | na | 50 | 0.4 | 25.101(c)(5)(A) | The existing ROW width is centerline only easement. This will remain in place to allow for a future circuit. An additional centerline only easement will be acquired, on which the new POD line section will be placed.
0PT48360 0PT49382 (R8606) | SL Consavvy Switch - Pronghorn Switch 138 kV Line: Rebuild | City of Odessa, Odessa County | Rebuild of the Consavvy - Pronghorn section of the S Midland - Pronghorn 138 kV Line | 2022-11-14 | 2023-05-15 |  |  | 10445048 |  |  | 0 | 138 | na | 7 | 1926 ACSS/TW Cumberland | Steel 2 - Pole, Steel Pole | 70 | 7 | na | na | 25.101(c)(5)(B)
0PT46565 (M4071) | Watermill Switch - Cedar Crest Switch 138 kV Line : Reterminate at Cedar Crest Sub (West) | City of Dallas, Dallas County | Reterminate the Watermill Switch - Cedar Crest Switch 138 kV Line on the east side of Cedar Crest Sub. | 2022-11-07 | 2023-05-15 |  |  | 631905 |  |  | 0 | 138 | na | 0.1 | 959 ACSS/TW Suwannee | Steel Pole | 90 | 0.1 | na | na | 25.101(c)(5)(B)
0PT46759 0PT46760 (R8606) | SL South Midland Switch - Consavvy Switch 138 kV Line: Rebuild | City of Odessa, Odessa County | Rebuild from South Midland Switch - Consavvy Switch | 2023-01-04 | 2023-05-15 | [5 empty] | 0 | 138 | na | 3 | 959 ACSS/TW Suwannee | Steel Pole | 70 | 3 | na | na | 25.101(c)(5)(B)
0PT48075 (R6136) | Fairfield West - Mexia Main 138 kV Line: Retermination into Fairfield West Switch | City of Fairfield, Freestone County | Reterminate the Fairfield West - Mexia Main 138 kV Line at its new terminal location at Fairfield West Switch. | 2022-11-01 | 2023-05-15 |  |  | 858013 |  |  | 1 | 138 | na | 0.1 | 959 ACSS/TW Suwannee | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT46882 0PT49379 (R8479) | Yucca Drive Switch - Northern Natural Gas Sub 69 kV Line: Cut-in Courtney Creek Switch - Fort Stockton Switch (AEP) 138 kV Line | City of Grand Falls, Ward County | Cut in the Yucca Drive Switching Station – Northern Natural Sub 69 kV Line to establish the new Courtney Creek 138 kV Switching Station | 2022-12-01 | 2023-02-15 | [5 empty] | 0 | 69 | 138 | 0.8 | 1926 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole, Wood 3 - Pole | 70 | 0.3 | 70 | 0.5 | 25.101(c)(5)(C)
0PT00208 (M3038) | Blackland Switch - Terrell Switch 138 kV Line: Establish Lawrence Substation | City of Terrell, Kaufman County | Establish the Lawrence Substation on the Blackland Switch - Terrell Switch 138 kV Line | 2022-10-19 | 2022-12-15 |  |  | 1077026 |  |  | 34 | 138 | na | 0.25 | 959.6 ACSS/TW/HS Suwannee | Steel Pole | 70 | 0.25 | na | na | 25.101(c)(5)(A)
0PT45022 (M4071) | Watermill Switch - Cedar Crest Switch 138 kV Line : Reterminate at Cedar Crest Sub (East) | City of Dallas, Dallas County | Reterminate the Watermill Switch - Cedar Crest Switch 138 kV Line on the west side of Cedar Crest Sub. | 2022-11-14 | 2022-12-19 |  |  | 776715 |  |  | 0 | 138 | na | 0.1 | 959 ACSS/TW Suwannee | Steel Pole | 90 | 0.1 | na | na | 25.101(c)(5)(B)
0PT47097 (M5136) | Sherry Switch - Fish Creek Switch 138 kV Line : Grand Prairie Associated Line Work (North Circuit) | City of Grand Prairie, Dallas County | Line Work Associated with connecting Grand Prairie Substation for the Sherry Switch - Fish Creek 138 kV Line. | 2022-09-20 | 2023-03-15 |  |  | 669782 |  |  | 34 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 0.4 | na | na | 25.101(C)(5)(B)
0PT46691 (M5136) | Sherry Switch - Cedar Hill Switch 138 kV Line : Grand Prairie Associated Line Work (South Circuit) | City of Grand Prairie, Dallas County | Line Work Associated with connecting Grand Prairie Substation with Sherry Switch - Cedar Hill Switch 138 kV Line. | 2022-09-16 | 2023-05-30 |  |  | 1583604 |  |  | 42 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 0.4 | na | na | 25.101(c)(5)(A)
0PT46747 (R6195) | Venus Switch - Sam Switch 345 kV Line : Cut-in to establish Fort Smith Switch | City of Hillsboro, Hill County | Cut in to the Venus Switch - Sam Switch 345 kV Line to establish Fort Smith Switch | 2022-09-26 | 2022-11-10 |  |  | 1317149 |  |  | 99 | 345 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 170 | 0.1 | na | na | 25.101(c)(5)(A)
0PT46319 (R788) | Whitney Switch - Stephenville Switch 138 kV Line: Antler Hollow Associated Line Work (North Circuit) | City of Stephenville, Erath County | Line work associated with establishing Antler Hollow Substation. | 2022-10-22 | 2022-12-16 |  |  | 1003868 |  |  | 99 | 138 | na | 0.2 | 959.6 ACSS/TW Suwannee | Steel Pole | 70 | 0.2 | na | na | 25.101(c)(5)(A)
0PT47477 (R4022) | Holliday Sub - Bowman Switch 138 kV Line : Cut-In to Establish Pecan Tree Sub | City of Holliday, Archer County | This project is to cut-in the Holliday Sub - Bowman Switch 138 kV Line to the planned Pecan Tree Sub. | 2022-11-15 | 2022-12-31 |  |  | 1579933 |  |  | 0 | 138 | na | 0.2 | 959.6 ACSS/TW Suwannee | Steel Pole | varies | 0.2 | na | na | 25.101(c)(5)(B)
0PT47460 (R4015) | Hopewell - Johnson SS (BEPC) 138 kV Line: Reterminate to establish Hopewell Switch | City of Bowie, Montague County | Reterminate the existing Montague - Johnson SS (BEPC) 69 kV Line at its new terminal location at the new Hopewell Switch. | 2022-10-11 | 2022-12-31 |  |  | 297610 |  |  | 34 | 69 | 138 | 0.2 | 959.6 ACSS/TW/HS Suwannee | Steel Pole | varies | 0.2 | na | na | 25.101(c)(5)(B)
0PT47321 | Mountain Creek Switch - West Levee Switch 138 kV Line : Line Hardening | City of Dallas, Dallas County | Replace 5 poles along the Mountain Creek Switch - West Levee Switch 138 kV Line | 2022-10-20 | 2022-11-15 |  |  | 1504761 |  |  | 50 | 138 | na | 0.23 | 1926.9 ACSS/TW Cumberland | Steel Pole | 10 | 0.23 | na | na | 25.101(c)(5)(B)
0PT45396 | Graham Switch - Burwick Switch 345 kV Line : Insulator Replacement | City of Graham, Young County | Replacing polymer insulators with toughened glass insulators. | 2022-10-17 | 2022-12-31 |  |  | 1320366 |  |  | 13 | 345 | na | 18 | 1590 ACSR Falcon | Steel Towers | Varies | 18 | na | na | 25.101(c)(5)(B)
0PT40247 | EPDC Sub - SOUTH MAIN TERMINAL Sub 138 kV Line : Replace Terminations & Rebuild Cathodic Protection System | City of Fort Worth, Tarrant County | Replace 138 kV Underground Transmission Terminations and rebuild Cathodic Protection System at EPDC SUB. | 2022-09-26 | 2022-10-10 | 2022-10-10 |  | 738236 |  |  | 100 | 138 | na | na | 600 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT46781 (M4702) | Farmersville Switch - Monticello Switch 345 kV Line : Cut-in Saltillo Switch for Stampede Solar | Hopkins County | Cut in to the Farmersville Switch - Monticello Switch 345 kV Line to establish Saltillo Switch | 2022-09-29 | 2022-11-17 |  |  | 1656513 |  |  | 99 | 345 | na | 0.35 | 2 -1926.9 ACSS/TW Cumberland | Steel Pole | 170 | 0.31 | 170 | 0.04 | 25.101(c)(5)(A)
0PT46610 0PT48345 (R6184) | Brown Switch - Killeen Switch 345 kV Line : Cut-in to establish Russell Gap Switch | Mills County | Cut - In to Brown - Killeen Switch 345 kV Line to Establish Russell Gap Switch | 2022-11-09 | 2022-11-17 |  |  | 1999500 |  |  | 0 | 345 | na | 0.21 | 2 -1926.9 ACSS Cumberland | Steel Lattice Tower | 80 | 0.21 | na | na | 25.101(c)(5)(A)
0PT44731 (R788) | Comanche Peak Switch - Stephenville Switch 138 kV Line: Antler Hollow Associated Line Work (South Circuit) | City of Stephenville, Erath County | Line work associated with establishing Antler Hollow Substation | 2022-10-22 | 2022-12-16 |  |  | 746949 |  |  | 99 | 138 | na | 0.2 | 959.6 ACSS/TW Suwannee | Steel Pole | 70 | 0.2 | na | na | 25.101(c)(5)(A)
0PT43881 (R4022) | Bowman- Graham Switch 138 kV Line: Cut-in to Short Grass Sub | City of Archer, Archer County | Cut in to the Bowman - Graham Switch 138 kV line to establish the new Short Grass Substation | 2022-11-14 | 2022-11-30 |  |  | 359938 |  |  | 0 | 138 | na | 0.1 | 2-795 ASCR Drake | Steel Tower | 120 | 0.1 | na | na | 25.101(c)(5)(A)
0PT47719 | Allen Switch - Plano West Sub 138 kV Line : Structure Replacement | City of Richardson, Collin County | Project will be to replace Structure 1/1C which is located outside of Plano West Substation on the Allen Switch – Plano West 138 kV Line | 2023-03-14 | 2023-04-17 | [5 empty] | 0 | 138 | na | 0.1 | 795 ACSR Drake | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT48230 0PT49393 (R8326) | Crane Switch - Odessa North Sub 69 kV Line : Cut In to Establish Apple Sub | City of Odessa, Ector County | Cut in to the Crane Switch - Odessa North Sub 69 kV Line to establish Apple Sub | 2022-10-18 | 2022-12-30 |  |  | 1491907 |  |  | 34 | 69 | na | 0.15 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 0.15 | na | na | 25.101(c)(5)(A)
0PT47462 (R4015) | Hopewell - Joy (BEPC) 138 kV Line: Reterminate to establish Hopewell Switch | City of Bowie, Montague County | Reterminate the existing Montague - Joy SS (BEPC) 69 kV Line at its new terminal location at the new Hopewell Switch. | 2022-10-11 | 2022-12-31 |  |  | 407914 |  |  | 33 | 69 | 138 | 0.2 | 959.6 ACSS/TW/HS Suwannee | Steel Pole | Varies | 0.2 | na | na | 25.101(c)(5)(B)
0PT44238 0PT46722 (R6215) | Taylor Switch - Hutto Switch 138 kV Line: Mallard Switch Cut-in | City of Taylor, Williamson County | Construct the cut-in line for the new Mallard Sw station. | 2023-01-30 | 2023-05-15 | [5 empty] | 0 | na | 138 | 1.63 | 1926.9 kcmil ACSS/TW | Steel Pole | na | na | 140 | 1.63 | 25.101(c)(5)(A)
0PT46992 (R6215) | Brushy Creek Switch - Mallard Switch 138 kV Line: Add Second Circuit from Str. 1/5 to Mallard Switch | City of Taylor, Williamson County | Install a second circuit on the Brushy Creek - Mallard 138 kV line from 1/5A to Mallard | 2023-01-23 | 2023-05-15 | [5 empty] | 0 | na | 138 | 6.51 | 1926.9 kcmil ACSS/TW | Steel Pole | Varies | 6.51 | na | na | 25.101(c)(5)(C)
0PT47713 (R6216) | Pintail Switch - Hutto Switch 138 kV Line: Pintail Switch Cut-in | City of Taylor, Williamson County | Construct the cut-in line for the new Pintail Sw station. | 2023-01-16 | 2023-05-15 | [5 empty] | 0 | na | 138 | 1.54 | 1926.9 ACSS/TW | Steel Pole | na | na | 140 | 1.54 | 25.101(c)(5)(A)
0PT47710 (R6211) | Pintail Switch - Hutto Switch 138 kV Line: Add Second Circuit from Pintail to Taylor West | City of Taylor, Williamson County | Install a second circuit on the Pintail - Hutto 138 kV line from Pintail to Taylor West | 2023-05-22 | 2023-10-15 | [5 empty] | 0 | na | 138 | 2.26 | 1926.9 ACSS/TW | Steel Pole | Varies | 2.26 | na | na | 25.101(c)(5)(C)
0PT47934 (R6215) | Mallard Switch - Pintail Switch 138 kV Line : Tie Lines | City of Taylor, Williamson County | Construct the tie line between the Mallard and Pintail switching stations. | 2023-01-02 | 2023-05-15 | [5 empty] | 0 | na | 138 | 0.16 | 1926.9 ACSS/TW | Steel Pole | na | na | Varies | 0.16 | 25.101(c)(5)(A)
0PT47711 (R6216) | Pintail Switch - SAS FAB1 138 kV Line: Construct New Double Circuit POD Line | City of Taylor, Williamson County | Construct the POD line from Pintail to SAS FAB1 | 2023-01-16 | 2023-05-15 | [5 empty] | 0 | na | 138 | 2 | 1926.9 ACSS/TW | Steel 2 - Pole, Steel Pole | na | na | Varies | 1 | 25.101(c)(5)(A)
0PT46975 (R6215) | Mallard Switch - SAS FAB1 138kV Line: Construct New Double Circuit POD Line | City of Taylor, Williamson County | Construct the POD line from Mallard to SAS FAB1 | 2023-01-16 | 2023-05-15 | [5 empty] | 0 | na | 138 | 1.62 | 1926.9 ACSS/TW | Steel 2 - Pole, Steel Pole | na | na | Varies | 0.81 | 25.101(c)(5)(A)
0PT45225 (M4292) | Payne Switch - Royse City 138 kV Line: Rebuild Greenbrier Switch to Audie Murphy POI | City of Farmersville, Collin County | Rebuild the Greenbrier Switch to Audie Murphy POI section of the Payne Switch - Royse City 138 kV Line. | 2023-01-09 | 2023-05-15 | [5 empty] | 0 | 138 | na | 3.5 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 3.5 | na | na | 25.101(c)(5)(B)
0PT46074 0PT46072 (R8565) | SL East Stiles Sub - St. Lawrence Sub 138 kV Line: Rebuild | Glasscock and Reagan Counties | Rebuild 13.1 miles of East Stiles – St. Lawrence 138kV Line | 2023-02-01 | 2023-05-15 | [5 empty] | 0 | 138 | na | 13.1 | 1926.9 ACSS/TW/HS Cumberland | Steel Pole | 90 | 13.1 | na | na | 25.101(c)(5)(B)
0PT46744 (M4126) | Centerville Switch - Centerville Road - Lake Hubbard Switch 138 kV Double-Circuit Line: Reconductor | City of Dallas, Dallas County | Reconductor the Centerville Switch to Lake Hubbard 138 kV Double Circuit line | 2023-01-23 | 2023-05-15 | [5 empty] | 0 | 138 | na | 13.6 | 959.6 ACSS/TW Suwannee E3X | Steel Tower | Varies | 6.8 | na | na | 25.101(c)(5)(B)
0PT43949 0PT46562 (M4236) | Rowlett Sub - Oates Sub 138 kV Line : Rebuild | City of Rowlett & Garland Dallas County | Rebuild the Rowlett Sub -Oates 138 kV Line. | 2023-01-16 | 2023-05-15 | [5 empty] | 0 | 138 | na | 5.7 | 959.6 ACSS/TW SUWANNEE | Steel Pole | Varies | 5.7 | na | na | 25.101(c)(5)(b)
0PT46764 (M4175) | Desoto Pleasant Run - Cedar Hill Switch Sub 138-kV Line Reconductor | City of Desoto, Dallas County | Reconductor the 6.1-mile Desoto Pleasant Run - Cedar Hill section of the Watermill - Cedar Hill 138 kV Line | 2023-01-04 | 2023-05-15 | [5 empty] | 0 | 138 | na | 6.1 | 959.6 ACSS/TW/E3X Suwannee | Steel Pole, Lattice Tower | Varies | 6.1 | na | na | 25.101(c)(5)(B)
0PT45726 0PT48485 (R8596) | Mustang Sub - Paul Davis Tap 138 kV Line : Rebuild | City of Andrews, Andrews County | Rebuild the Mustang Sub - Paul Davis Tap 138 kV Line. | 2023-01-02 | 2023-05-15 | [5 empty] | 0 | 138 | na | 12.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 12.1 | 80 | na | na | 25.101(c)(5)(B)
0PT48275 | Hurst - Bell Helicopter 138 kV Line: Structure Modification | City of Hurst, Tarrant County | Replace a structure on the Hurst - Bell Helicopter 138-kV Line | 2022-12-27 | 2022-12-31 | [5 empty] | 0 | 138 | na | 0.1 | 336.4 ACSR LINNET | Wood Pole | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT48509 (R4015) | Burnett Switch - Old Lake Switch 69 kV Line: Rebuild Fisher Road - Lanham Tap section to 138 kV | City of Wichita Falls, Wichita County | Rebuild Fisher Road - Lanham Tap section of the Burnett Switch - Old Lake Switch 69 kV Line to 138 kV. | 2023-01-30 | 2023-05-15 | [5 empty] | 0 | 69 | 138 | 10.4 | 959.6 ACSS/TW SUWANNEE | Steel 3 -Pole, Steel H-Frame, Steel Pole | 50 | 10.4 | na | na | 25.101(c)(5)(B)
0PT46826 | Trinidad Switch - Eustace Southeast Sub 138 kV Line : Replace Structure 61/8A | City of Trinidad, Henderson County | Replace structure 61/8A due to corrosion of structure leg. | 2022-11-15 | 2022-12-30 | [5 empty] | 0 | 138 | na | 0.01 | 1033.5 ACSR Curlew | Steel H-Frame | 160 | 0.01 | na | na | 25.101(c)(5)(B)
0PT46145 | SL AJ Swope Sub - Alibates Sub 345 kV Line : Galloping Device Installation | Carson County and Potter County | Install spacer dampers and replace hardware on AJ Swope Sub - Alibates Sub 345 kV Line | 2022-11-29 | 2023-05-15 |  |  | 1592160 |  |  | 0 | 345 | na | 33.8 | 2-1926.9 ACSR/TW Cumberland | Lattice Tower | 175 | 16.9 | na | na | 25.101(c)(5)(B)
0PT46842 (R8304) | Texaco Mabee Tap - Midland East Switch 138 kV Line : Double Circuit Line Rebuild | City of Midland, Midland County | Rebuild the Texaco Mabee Tap to Midland East 138 kV Line. | 2022-12-05 | 2023-05-15 | [5 empty] | 0 | 138 | na | 15.4 | 1926.9 ACSS/TW Cumberland | Steel 3- Pole, Steel H-Frame, Steel Pole | 75 | 7.7 | na | na | 25.101(c)(5)(B)
0PT46945 (M5222) | Handley Switch – Handley Sub 69 kV Strain Bus: Rebuild and Reconfigure as the Handley Switch - Rosedale Sub 138 kV Line | City of Fort Worth, Tarrant County | Re-terminate the Handley Switching Station – Handley Substation 69 kV Strain Bus at its new terminal location at the Handley Switching Station | 2022-10-13 | 2023-05-15 |  |  | 1602887 |  |  | 1 | 69 | 138 | 0.2 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel h-Frame, Steel Pole | 50 | 0.2 | na | na | 25.101(c)(5)(B)
0PT47517 | NW Carrollton Sub - Gainesville Sub 138 kV Line : Relocation for City of Denton Hickory Creek Road | City of Denton, Denton County | Relocate the NW Carrollton - Gainesville 138 kV Line at the request of the City of Denton | 2022-11-15 | 2022-12-31 |  |  | 1077549 |  |  | 0 | 138 | na | 0.5 | 795 ACSR Drake | Concrete H-Frame | 100 | 0.5 | n/a | n/a | 25.101(c)(5)(F) | Relocation is at the request of the City of Denton and is 100% reimbursable by the City of Denton.
0PT47380 (R8625) | Spraberry Switch - Polecat Switch 138 kV Line: Install Stephenson Lake POD for Pinnacle Energy Transition Operating Co. | City of Midland, Midland County | Establish Stephenson Lake Point of Delivery (POD) to Pinnacle Energy's Floyd Ranch Substation on the Spraberry - Polecat 138 kV Line | 2023-02-20 | 2023-05-12 | [5 empty] | 0 | 138 | na | 0.7 | 1926.9 ACSS/TW Cumberland | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 0.4 | varies | 0.3 | 25.101(c)(5)(A)
0PT47315 (R6207) | Lake Creek Switch - Jewett Switch 138 kV Line: Install Riesel Switch for Coral Solar | City of Riesel, Falls County | Cut into the Lake Creek - Jewett 138 kV Line to establish the new Riesel Switch | 2023-02-02 | 2023-04-13 | [5 empty] | 0 | 138 | na | 0.3 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.2 | varies | 0.1 | 25.101(c)(5)(A)
0PT47771 (R6213) | Temple Switch - Lake Creek Switch 345 kV Line: Cut-in to Establish Belfalls Switch for Big Elm Solar | City of Temple, Bell County | Cut into the Temple - Lake Creek 345 kV Line to establish the new Belfalls Switch | 2023-03-13 | 2023-05-11 | [5 empty] | 0 | 345 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Lattice Tower, Steel Pole | 125 | 0.2 | na | na | 25.101(c)(5)(A)
0PT47738 (R6210) | Bell County East Switch - TNP One (TNMP) Switch 345 kV Line: Cut-in to Establish Hog Creek Switch | Milam County | Cut into the Bell County East - TNP One (TNMP) 345 kV Line to establish the new Hog Creek Switch | 2023-02-20 | 2023-05-11 | [5 empty] | 0 | 345 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Lattice Tower, Steel Pole | 160 | 0.1 | varies | 0.1 | 25.101(c)(5)(A)
0PT46644 0PT47903 (R8614) | Sale Ranch Switch - Natural Dam Switch 138 kV Line : Install Rock Lake POD for Diamondback's Robinson Ranch | City of Stanton, Martin County | Provide a 138 kV point-of-delivery for Diamondback E&P, LLC on the Sale Ranch - Natural Dam 138 kV Line | 2023-01-09 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel 3-Pole, Steel H-Frame, Steel Pole | na | na | 70 | 0.4 | 25.101(c)(5)(A)
0PT47431 | Medill Sub - East Network Sub 138 kV Line: Rebuild/Replace Cathodic Protection | City of Dallas, Dallas County | Replace the cathodic protection system on the Medill Sub - East Network Sub 138 kV Line. | 2023-02-06 | 2023-05-19 | [5 empty] | 0 | 138 | na | na | 1250 CU | na | na | na | na | na | 25.101(c)(5)(B)
0PT48581 | Wink - Wink Basin - Keystone 69 kV Line: Replace Wood Poles and Insulators | City of Kermit, Winkler County | Various wood poles and insulator replacements on Wink - Wink Basin - Keystone 69 kV Line. | 2022-06-01 | 2022-08-30 | 2022-08-30 |  | 139650 |  |  | 100 | 69 | na | 10.21 | 336.4 ACSR Linnet | Wood H-Frame | 50 | 10.21 | na | na | 25.101(c)(3)
0PT49021 | NTUSU Luther - Vealmoor 138 kV: High Temp Upgrade | Howard County | Install shunts required to increase the 9.84 mile Luther - Vealmoor 138 kV line maximum operating temperature. | 2022-11-21 | 2022-12-31 |  |  | 294567 |  |  | 0 | 138 | na | 9.84 | 795 ACSR Drake | Steel Pole | varies | 9.84 | na | na | 25.101(c)(5)(A)
0PT47706 (M4330) | Haggerty Switch Station - MEMC Southwest Substation (North) 138 kV Line | City of Sherman, Grayson County | Reroute the North MEMC Southwest Tap 138kV single circuit line 0.6 miles into the new Haggerty 138 kV Switch Station. | 2022-12-23 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.6 | 2-959.6 ACSS/TW Suwannee | Steel Pole | na | na | 100 | 0.6 | 25.101(c)(5)(B)
0PT47674 (M4330) | Haggerty Switch Station: Sherman TI 138 kV Tie Line to XFMR #2 | City of Sherman, Grayson County | Build the new tie line between the new Haggerty 138 kV Switch Station and existing Sherman TI Substation (XFMR #2) | 2023-01-03 | 2023-04-25 | [5 empty] | 0 | na | 138 | 0.1 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | varies | 0.1 | 25.101(c)(5)(B)
0PT47676 (M4330) | Haggerty Switch Station: Sherman TI 138 kV Tie Line to XFMR #1 | City of Sherman, Grayson County | Build the new tie line between the new Haggerty 138 kV Switch Station and existing Sherman TI Substation (XFMR #1) | 2023-01-03 | 2023-05-05 | [5 empty] | 0 | na | 138 | 0.1 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | varies | 0.1 | 25.101(c)(5)(B)
0PT47705 (M4330) | Valley-Anna 138 kV Line: Establish Haggerty 138 kV Switch | City of Sherman, Grayson County | Reroute the Valley/Anna 138 kV double circuit line 0.3 miles into the new Haggerty 138 kV Switch Station | 2023-01-16 | 2023-05-05 | [5 empty] | 0 | 138 | na | 1.2 | 2-959.6 ACSS/TW Suwannee | Steel Pole | 80 | 0.3 | varies | 0.3 | 25.101(c)(5)(B)
0PT48310 (M4330) | Haggerty Switch Station: 138kV Line to TI SM1-1 | City of Sherman, Grayson County | Build the new line between the new Haggerty 138 kV Switch Station and new TI SM1-1 | 2023-03-20 | 2023-05-15 | [5 empty] | 0 | na | 138 | 1 | 2-959.6 ACSS/TW Suwannee | Steel Pole | na | na | varies | 1 | 25.101(c)(5)(B)
0PT48311 (M4330) | Haggerty Switch Station: 138 kV Line to TI SM1-2 | City of Sherman, Grayson County | Build the new line between the new Haggerty 138 kV Switch Station and new TI SM1-2 | 2023-03-20 | 2023-05-15 | [5 empty] | 0 | na | 138 | 1 | 2-959.6 ACSS/TW Suwannee | Steel Pole | na | na | varies | 1 | 25.101(c)(5)(B)
0PT47391 (R8619) | Wolf Switch - Moss Switch 345 kV Line : Cut-in Meteor Switch 345 kV for Greyhound Solar | Ector County | Cut in the Wolf Switch - Moss Switch 345 kV Line to establish the new Meteor Switch 345 kV for Greyhound Solar | 2023-03-27 | 2023-05-18 | [5 empty] | 0 | 345 | na | 0.1 | 2-1926.9 ACSS/TW Cumberland | Steel Lattice Tower | na | na | 180 | 0.1 | 25.101(c)(5)(A)
0PT47792 (M5324) | Jacksboro Switch - Krum West Switch 345 kV Line : Cut-in Bird Dog Switch | Denton County | Cut in the Jacksboro Switch - Krum West Switch 345 kV Line to establish the new Bird Dog Switch | 2023-01-09 | 2023-05-18 | [5 empty] | 0 | 345 | na | 0.1 | 2-959.6 ACSS/TW Suwannee | Steel Lattice Tower | na | na | 366 | 0.1 | 25.101(c)(5)(A)
0PT47803 (M5326) | Watermill Switch - Parkdale Switch 138 kV Line: Cut-in Lavender Switch for SDC's Wilmer Data Center | Dallas County | Cut in the Watermill Switch - Parkdale Switch 138 kV Line to establish the new Lavender Switch for SDC's Wilmer Data Center | 2023-02-20 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.8 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | 100 | 0.4 | 25.101(c)(5)(A)
0PT48967 (M5326) | Lavender Switch – SDC Wilmer (Focus) 138kV Line: Station Tie Lines Build | Dallas County | Built the two (2) new tie lines between Oncor's Lavender station and Stream's Focus station | 2023-03-01 | 2023-05-15 | [5 empty] | 0 | na | 138 | 0.2 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | varies | 0.1 | 25.101(c)(5)(A)
0PT48536 (R8642) | SL Pronghorn - Salt Flat Road 138 kV Line: Rebuild | Midland County | Rebuild the Pronghorn - Salt Flat Road 138 kV line to 1926 ACSS/TW capable structures. | 2023-09-15 | 2023-12-15 | [5 empty] | 0 | 138 | na | 7.2 | 795 ACSR Drake | Steel Pole | varies | 7.2 | na | na | 25.101(c)(5)(B)
0PT47467 | DFW B East - DFW C East 138 kV Line: Replace U.G Terminations | City of Dallas, Dallas County | Replace six 138 kV Underground Transmission Terminations at DFW B East - DFW C East. | 2023-01-23 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | 1750 kcmil CU | na | na | na | na | na | 25.101(c)(5)(B)
0PT49323 0PT49343 (R8606) | Grey Well Draw - Consavvy 138 kV Line: Install 2nd Circuit | City of Midland, Midland County | Establish a line section between Grey Well Draw and Consavvy by adding a second circuit to the existing Midland E – Spraberry 138 kV Line. | 2022-11-11 | 2022-12-31 |  |  | 3018279 |  |  | 0 | 138 | na | 2.9 | 1926 ACSS/TW | Steel Poles | 50 | 2.8 | 0.1 | 70 | 25.101(c)(5)(C)
0PT47279 (M4331) | Kemp Ranch Switch - Sardis Switch 138 kV Line : Cut-in Newton Branch Sub for Martin Marietta | City of Midlothian, Ellis County | Cut in the Kemp Ranch Switch - Sardis Switch 138 kV Line to establish the new Newton Branch Substation. | 2023-01-02 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.06 | 2-959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0.06 | na | na | 25.101(c)(5)(A)
0PT49020 (M4236) | Royse Switch - Rowlett Sub 138 kV Line : Reconductor Creekside Sub to Rowlett Sub | City of Royse, Rockwall County | Reconductor the Creekside Sub - Rowlett Sub section of the Royse Switch - Rowlett 138 kV Line. | 2023-01-02 | 2023-03-31 | [5 empty] | 0 | 138 | na | 1.36 | 2-959.6 ACSS/TW Suwannee | Steel Pole | Varies | 1.36 | na | na | 25.101(c)(5)(B)
0PT47545 | North Network Sub - Bryan Sub 138 kV Line | City of Dallas, Dallas County | Replace six 138 kV Underground Transmission Terminations at North Network - Bryan Sub 138kV. | 2023-01-09 | 2023-06-30 | [5 empty] | 0 | 138 | na | na | 1500 AL HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT48531 (M3015) | Krum West Switch - Hummingbird Storage POI 345 kV Line: Install Line for Hummingbird Storage | Denton County | Build a 345 kV Point of Interconnection (POI) to KCE TX 10, LLC Hummingbird Storage from Krum West Switch | 2023-01-16 | 2023-05-11 | [5 empty] | 0 | na | 345 | 0.18 | 2-1926.9 ACSS/TW Cumberland | Steel Tower | 160 | 0.18 | na | na | 25.101(c)(5)(A)
0PT48339 (R6094) | Athens - Tyler Switch 69 kV: Rebuild Murchison to Str 33/1 to 138 kV | City of Murchison, Henderson County | Rebuild a 6.7 miles section of the Athens to Tyler Switch 69 kV line as a 138 kV double circuit line with only one circuit installed. | 2023-03-06 | 2023-06-30 | [5 empty] | 0 | 69 | 138 | 6.7 | 959.6 ACSS/TW Suwannee | Steel Pole, Steel 3- Pole, Steel H-Frame | Centerline | 6.7 | na | na | 25.101(c)(5)(B)
0PT48089 (M5359) | Hicks Switch - Roanoke Switch 138 kV Line : Install Elizabethtown POI for BEC's Brandon Sandman Sub | City of Fort Worth, Denton County | Cut in the Hicks Switch - Roanoke Switch 138 kV Line to establish the new Elizabethtown POI | 2023-02-07 | 2023-03-15 | [5 empty] | 0 | 138 | na | 0.11 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 60 | 0.11 | 25.101(c)(5)(A)
0PT48102 (M4352) | Greenville Avenue Switch - Lomo Alto Sub 138 kV Line : Relocate Line Section for Station Rebuild | City of Dallas, Dallas County | Relocate 4 structures of the Greenville Avenue Switch - Lomo Alto 138 kV Line. | 2023-01-17 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.28 | 1926.9 ACSS/TW Cumberland | Steel Pole | 60 | 0.28 | na | na | 25.101(c)(5)(D)
0PT47753 (R6208) | Bell County East Switch - Chillingham POI 345 kV Line: Install Line for Chillingham Solar | Bell County | Establish a 345 kV point of interconnection (POI). | 2023-02-01 | 2023-05-11 | [5 empty] | 0 | na | 345 | 0.21 | 2-959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel Pole | na | na | 120 | 0.21 | 25.101(c)(5)(A)
0PT47754 (R6209) | Bell County East Switch - Five Wells POI 345 kV Line: Install Line for Five Wells Solar | Bell County | Establish a 345 kV point of interconnection (POI). | 2023-02-16 | 2023-05-18 | [5 empty] | 0 | 345 | na | 0.3 | 2-959.6 ACSS/TW Suwannee | Steel 3-Pole | na | na | 160 | 0.21 | 25.101(c)(5)(A)
0PT47990 (R6209) | Bell County East Switch - TNP ONE Switch 345 kV Line : Raise Structure 1/2 | Bell County | Modify a section of BCE - TNP ONE 345 kV line. | 2023-02-02 | 2023-05-04 | [5 empty] | 0 | 345 | na | 0.82 | 2-1590 ACSR Falcon | Steel Lattice Tower | 160 | 0.41 | na | na | 25.101(c)(5)(B)
0PT49337 (M3019) | Decordova Switch – Carmichael Bend Switch 138 kV Line: Reconductor | City of Granbury, Hood County | Reconductor the Decordova Switch - Carmichael Bend Switch 138 kV line where it crosses Lake Granbury. | 2023-03-15 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.5 | 954 ZTACCR/TW C7 - TS Arches | Steel Lattice Tower | varies | 0.5 | na | na | 25.101(c)(5)(B)
0PT49060 | Sargent Road Switch - West Levee Sub 345 kV Line : Replace OPGW | City of Dallas, Dallas County | The existing OPGW between West Levee and Sargent Road is damaged and no spare fibers exist. This project is to replace the existing OPGW. | 2023-02-01 | 2023-05-31 | [5 empty] | 0 | 345 | na | 5.1 | 1590 ASCR Falcon | Steel Pole | Varies | 5.1 | na | na | 25.101(c)(5)(B)
0PT49001 | Graham Plant Switch - Cook Field Road Switch 345 kV Line : Relocate structure 27/6 | Stephens County | Rebuild a section of the Graham Plant Switch - Cook Field Road Switch 345 kV Line | 2023-03-02 | 2023-06-30 | [5 empty] | 0 | 345 | na | 1.4 | 2 - 795 ACSR Drake | Steel Lattice Tower | 120 | 0.7 | na | na | 25.101(c)(5)(B)
0PT48650 | Odessa EHV – Spraberry 138 kV Line: Salt Lake Substation Cut-In | City of Midland, Midland County | Line work associated with establishing a new transformer on Salt Lake Substation | 2023-03-15 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.1 | 1926.9 ACSS/TW/HS Cumberland | Steel Pole | 75 | 0.1 | na | na | 25.101(c)(5)(A)
0PT48629 | Watermill Switch - Sargent Road Switch 345 kV Line : Replace OPGW | City of Dallas, Dallas County | Replace the OPGW on the Watermill Switch - Sargent Road Switch 345 kV Line. | 2023-03-01 | 2023-05-15 | [5 empty] | 0 | 345 | na | 12.6 | 1590 ASCR Falcon | Steel Pole | varies | 12.6 | na | na | 25.101(c)(5)(B)
0PT47591 | Watermill Switch - Seagoville Switch 138 kV Line : Replace Structures 9/1 and 9/4 | City of Wilmer, Dallas County | Replace structures on Watermill Switch - Seagoville Switch 138 kV Line | 2023-02-28 | 2023-05-31 | [5 empty] | 0 | 138 | na | 0.3 | 1926.9 ACSS/TW Cumberland | Steel Poles | 100 | 0.3 | na | na | 25.101(c)(5)(B)
0PT48745 | Jewett Switch - Lake Creek Switch 138 kV Line : Replace structure 31/2 with steel H-frame | Limestone County | Replace structure on Jewett Switch - Lake Creek Switch 138 kV Line. | 2023-02-15 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.5 | 795 ACSR Drake | Steel H-Frame | 100 | 0.5 | na | na | 25.101(c)(5)(B)
0PT48983 | Krum Switch - Jacksboro Switch 345 kV Line : Increase Foundation Reveal Cap | City of Chico, Wise County | Increase foundation caps on structures for Krum Switch - Jacksboro Switch 345 kV Line. | 2023-01-02 | 2023-05-15 | [5 empty] | 0 | 345 | na | 0.9 | 2-1590 ACSR Falcon | Steel Lattice Tower | 160 | 0.9 | na | na | 25.101(c)(5)(B)
0PT48506 (R4015) | Bellevue Sub - Bowie Sub 69 kV Line: Reconfiguration Remove Bowie Sub Connection | City of Bowie, Montague County | Reconfiguration remove Bowie Sub connection on the Bellevue Sub - Bowie Sub 69 kV Line. | 2023-01-02 | 2023-03-31 | [5 empty] | 0 | 69 | na | 0.1 | 336.4 ACSR Linnett | Steel Pole | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT47718 | Jewett - Long Lake - Palestine South 138 kV Line: Relocate Structure 2/9 | City of Jewett, Leon County | Relocate structure on Jewett - Long Lake - Palestine South 138 kV Line | 2023-01-02 | 2023-05-31 | [5 empty] | 0 | 138 | na | 0.1 | 795 ACSR Drake | Steel Poles | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT46085 (R6138) | Pin Oak Switch - Fairfield West Switch 138kV Line: Rebuild from Fairfield West to Fairfield Switch (BEPC) 138 kV | Freestone County | Rebuild the 7.7 mile Trinidad - Jewett 138 kV Line section from Fairfield West to Big Brown Tap using double circuit structures with one circuit in place. Use a conductor rated 1649 amps or greater. | 2023-01-02 | 2023-05-15 | [5 empty] | 0 | 138 | na | 4.8 | 1926.9 kcmil ACSS/TW Cumberland | Steel Pole | 100 | 4.8 | na | na | 25.101(c)(5)(B)
0PT48054 (R944) | Commerce Switch - Sulphur Springs Switch 138 kV Line: Reterminate at Cumby Tap | City of Cumby, Hopkins County | Reterminate the Commerce Switch - Sulphur Springs Switch 138 kV line at Cumby Tap. | 2023-01-03 | 2023-12-15 | [5 empty] | 0 | 138 | na | 0.2 | 795 ACSR Drake | Steel Pole | varies | 0.2 | na | na | 25.101(c)(5)(A)
0PT48971 | Stryker Creek Switch - Lufkin Switch 345 kV Line : Replace and relocate tower 23/2 | Nacogdoches County | Replacing Structure on Stryker Creek Switch - Lufkin Switch 345 kV Line. | 2023-01-04 | 2023-06-30 | [5 empty] | 0 | 345 | na | 0.5 | 2 - 795 ACSR Drake | Steel Lattice Tower | 150 | 0.5 | na | na | 25.101(c)(5)(B)
0PT48508 (R4015) | Fisher Road Switch - Riley 345 kV Line: Replace Structure 1/1 | City of Wichita Falls, Wichita County | Replace one structure of the Fisher Road - Oklaunion 345 kV line | 2023-01-04 | 2023-05-15 | [5 empty] | 0 | 345 | na | 0.1 | 2-795 ACSR Drake | Steel Lattice Tower | 150 | 0.1 | na | na | 25.101(c)(5)(B)
0PT48780 0PT47487 (R8027) | SL Ogallala Switch - Tule Canyon Switch 345 kV Line : Cut-in for Ozark Trail Switch | Swisher County | The work required to loop the Ogallala Switch - Tule Canyon Switch 345 kV line into Ozark Trail Switch. | 2023-01-09 | 2024-04-18 | [5 empty] | 0 | 345 | na | 0.1 | 1926 ACSS/TW Cumberland | Steel Lattice Tower | na | na | 175 | 0.1 | 25.101(c)(5)(B)
0PT43468 (M4205) | Carrollton Northwest Switch - Carrollton East Switch 138 kV Line : Line Termination at Carrollton Northwest | City of Carrollton, Dallas County | Establish the Carrollton East Switch - Carrollton Northwest Switch 138 kV Double-Circuit Line and Carrollton Northwest Switch - Northlake Switch 138 kV Line by terminating the existing Carrollton East Switch - Northlake Switch 138 kV Line at Carrollton Northwest Switch. | 2023-01-09 | 2023-05-15 | [5 empty] | 0 | 138 | na | 1.8 | 959.6 ACSS/TW Suwannee | Steel Pole | varies | 0.9 | na | na | 25.101(c)(5)(A)
0PT46982 (R8615) | Morgan Creek Switch - McDonald Road 138 kV Line : Install Navigation Sub for Targa's PS4 | Mitchell County | Line work associated with the retermination of both the Deen Sw - Roanoke Sw and Roanoke Sw - Euless Sub 138 kV Lines. | 2023-01-17 | 2023-03-31 | [5 empty] | 0 | 138 | na | 0.3 | 1926.9 ACSS/TW/HS Cumberland | Steel Poles | 50 | 0.3 | na | na | 25.101(c)(5)(A)
0PT42619 0PT42843 (R8591) | Wolfcamp Tap - Courtney Creek Switch 69 kV Line: Add 2nd Circuit | Pecos County | Rebuild the 9.3-mile Wolfcamp Tap - Courtney Creek Switch 69 kV Line section of the 51.7-mile Yucca Drive Switch - Northern Natural 69 kV Line. | 2023-01-16 | 2023-06-30 | [5 empty] | 0 | 69 | 138 | 9.3 | 1926 ACSS/TW Cumberland | Steel 3 - Pole | 50 | 9.3 | na | na | 25.101(c)(5)(B)
0PT47513 | Killeen Taft Sub - Killeen Switch 138 kV Line : Install OPGW | City of Killeen, Bell County | Installing OPGW from Killeen Taft Sub to Killeen Switch. Leave splice drop at Killeen Elms Road. | 2023-01-26 | 2023-05-15 | [5 empty] | 0 | 138 | na | 12 | 1590 ACSR Falcon | Steel Poles | 100 | 6 | na | na | 25.101(c)(5)(B)
0PT02607 (R9022) | Graham - Morgan Creek 345kV line (South): Reterminate at Mulberry Creek due to Station Rebuild | City of Abilene, Jones County | Line work associated with rebuilding Mulberry Creek 345 kV Switch Station | 2023-01-30 | 2023-12-01 | [5 empty] | 0 | 345 | na | 1.2 | 2 -1926 ACSS/TW Cumberland | Steel Pole, Steel Lattice Tower | 120 | 0.4 | varies | 0.2 | 25.101(c)(5)(A)
0PT47795 (M5323) | Valley Switch - Paris Switch 345 kV Line : Cut-in for Pacific Switch | Lamar County | To provide service to the Customer’s generating facility, modifications to one circuit of the double circuit 345kV transmission line will be necessary. The work required to loop the Valley Switch - Paris Switch 345 kV line into Pacific Switch. | 2023-02-01 | 2023-05-18 | [5 empty] | 0 | 345 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel Lattice Tower | 250 | 0.1 | na | na | 25.101(c)(5)(A)
0PT42093 0PT42844 (R8591) | Blair Lake Substation - Courtney Creek Switch 69 kV Line: Conversion to 138 kV | Pecos County | Rebuild 13.8 miles of the Yucca Drive Switch – Northern Natural Substation 69 kV Line between Blair Lake Substation – the new Courtney Creek Switch and convert the circuit to 138 kV. | 2023-02-06 | 2023-06-30 | [5 empty] | 0 | 69 | 138 | 13.8 | 1926 ACSS/TW Cumberland | Steel Pole | 50 | 13.6 | 50 | 0.23 | 25.101(c)(5)(B)
0PT44564 (M5310) | Venus Switch Sta. - Cedar Hill 138 kV Line: Padera Sub Cut In | City of Midlothian, Ellis County | Cut-In to Venus Switch - Cedar Hill 138 kV Line to Establish Padera Substation | 2023-02-15 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.18 | 1926.9 ACSS/TW/E3X Cumberland | Steel Pole | 100 | 0.12 | 100 | 0.06 | 25.101(c)(5)(A)
0PT44557 (M5314) | Hicks Switch - Deen Switch 138 kV Line : Cut in to Horseman Sub (formerly Saginaw SE Sub) | City of Fort Worth, Tarrant County | Cut in the Hicks Switch - Deen Switch 138 kV line to the Horseman Sub | 2023-02-23 | 2023-05-01 | [5 empty] | 0 | 138 | na | 0.2 | 959.6 ACSS/TW/E3X Suwannee | Steel Pole | 75 | 0.1 | na | na | 25.101(c)(5)(A)
0PT48603 (M5330) | Roanoke Switch - Euless Switch 138 kV Line : Retermination at Roanoke Switch | City of Roanoke, Denton County | Line work associated with the retermination of both the Deen Sw - Roanoke Sw and Roanoke Sw - Euless Sub 138 kV Lines. | 2023-02-24 | 2023-04-01 | [5 empty] | 0 | 138 | na | 0.4 | 2 - 959.6 ACSS/TW/E3X | Steel Pole | Varies | 0.2 | na | na | 25.101(c)(5)(A)
0PT46932 0PT48703 (R8593) | NTUSU Brown Sub - Grady Sub 138 kV Line: Expanse Switch Cut In | Martin County | Loop in the Brown Sub - Grady Sub 138 kV line into the new Expanse 345/138 kV Switch | 2023-02-27 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.51 | 1926.9 ACSS/TW/E3X Cumberland | Steel Pole | 70 | 0.5 | 100 | 0.01 | 25.101(c)(5)(A)
0PT48643 (R8595) | McKenzie Draw - Lamesa Sub 138 kV Line: Lamesa Sub Cut - In | Dawson County | Line Work Associated with Retermination of Lamesa Sub | 2023-03-06 | 2023-06-15 | [5 empty] | 0 | 138 | na | 0.01 | 959.6 ACSS/TW Suwannee | Steel A-Frame | 100 | 0.01 | na | na | 25.101(c)(5)(B)
0PT47106 0PT47929 (R8617) | SL Blue Acres Sub - South Midland Sub 138 kV Line : Rebuild | City of Midland, Midland County | Rebuild the 5.5 mile Blue Acres Sub – South Midland Sub 138 kV Line with double circuit capable structures. | 2023-03-01 | 2023-11-01 | [5 empty] | 0 | 138 | na | 5.5 | 1926 ACSS/TW Cumberland | Steel 3 - Pole, Steel Poles | 70 | 5.5 | na | na | 25.101(c)(5)(B)
0PT48642 (R8649) | Getty Vealmoor 138 kV Tap Line: Cut-In to Esttablish Vincent Sub (fka Getty Vealmoor Sub) | City of Big Spring, Howard County | Cut in the Big Spring Switch - China Grove Switch - Gunsight Switch 138 kV Line to establish the new Vincent substation. | 2023-03-06 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.6 | 1926.9 ACSS/TW Cumberland | Steel Poles, Wood H-Frame, Wood Pole | 75 | 0.6 | na | na | 25.101(c)(5)(A)
0PT46985 | Temple Switch - Temple Sub 138 kV Line : Install OPGW | City of Temple, Bell County | Install OPGW from Temple Switch to Temple Substation | 2023-03-06 | 2023-05-15 | [5 empty] | 0 | 138 | na | 1.7 | 795 ACSR Drake | Steel Lattice Tower, Steel and Concrete Pole | 100 | 1.7 | na | na | 25.101(c)(5)(A)
0PT43540 (M5317) | Tyson Nick Solar: Establish a 138 kV POI for customer's generator (Tyson Nick Solar Project, LLC) at Toco Switch | City of Paris, Lamar County | Establish 138 kV point of interconnection of the Tyson Nick Solar generating facility | 2023-03-07 | 2023-04-13 | [5 empty] | 0 | na | 138 | 0.1 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | varies | 0.1 | 25.101(c)(5)(A)
0PT47231 | Handley - Lancaster 138 kV: Replace STR 2/6 due to Erosion | City of Fort Worth, Tarrant County | Replacing structure on Handley - Lancaster 138 kV Line. | 2023-03-08 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.4 | 795 ACSR DRAKE and 1534.0 ACAR | Steel Pole | 50 | 6.8 |  |  | 25.101(c)(5)(B)
0PT48309 (M4330) | Haggerty Switch Station - MEMC Southwest Substation (South) 138 kV Line | City of Sherman, Grayson County | Reroute the South MEMC Southwest Tap 138 kV single circuit line 0.6 miles into the new Haggerty 138 kV Switch. | 2023-03-15 | 2024-05-15 | [5 empty] | 0 | na | 138 | 0.6 | 2 - 959 ACSS/TW SUWANNEE | Steel Pole | na | na | 50 | 0.6 | 25.101(c)(5)(A)
0PT48118 (M4322) | Mountain Creek Switch - West Levee 138 kV Line: Line Reroute for Campion 138 kV Sub | City of Dallas, Dallas County | Line Reroute for Campion 138 kV Sub. | 2023-03-15 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.3 | 1926 ACSS/TW Cumberland | Steel Poles | 70 | 0.3 | na | na | 25.101(c)(5)(A)
0PT48116 (M4322) | Mountain Creek Switch - Norwood Switch 138 kV Line: Establish Transmission Loop Feed for Campion 138 kV Sub | City of Dallas, Dallas County | Establish Transmission Loop Feed for Campion 138 kV Sub. | 2023-03-15 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.25 | 1926 ACSS/TW Cumberland | Steel Pole | na | na | 70 | 0.25 | 25.101(c)(5)(A)
0PT43639 (M4322) | Mountain Creek Switch - West Dallas 138 kV Line: Establish Transmission Loop Feed for Campion 138 kV Sub | City of Dallas, Dallas County | Establish the transmission loop feed into the new Campion 138 kV Sub. | 2023-03-15 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.25 | 1926 ACSS/TW Cumberland | Steel Pole | na | na | 70 | 0.25 | 25.101(c)(5)(A)
0PT48845 (R8621) | Delaware River Switch - Delaware Ranch Sub 138 kV Line: Build Tie Line | Culberson County | Build the tie line between the new Delaware River Switch and existing Delaware Ranch Sub. | 2023-03-20 | 2023-05-18 | [5 empty] | 0 | na | 138 | 0.1 | 1926 ACSS/TW Cumberland | Steel Pole | na | na | 0.1 | varies | 25.101(c)(5)(B)
0PT48229 (R6182) | Palestine - Palestine South 138 kV line: Reterminate at Palestine South | City of Palestine, Anderson County | Reterminate the Palestine - Palestine South 138 kV line at Palestine South. | 2023-03-20 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.4 | 959 ACSS/TW Suwannee | Steel Pole | varies | 0.4 | na | na | 25.101(c)(5)(A)
0PT48223 (R6182) | Palestine South - Long Lake 138 kV line: Reterminate at Palestine South | City of Palestine, Anderson County | Reterminate the Palestine South - Long Lake 138 kV line at Palestine South. | 2023-03-20 | 2023-05-15 | [5 empty] | 0 | 138 | na | 0.2 | 959 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | varies | 0.2 | na | na | 25.101(c)(5)(A)
0PT47787 (R8621) | Horseshoe Springs Switch - Riverton Switch 138 kV Line : Cut-in for Delaware River Switch | Culberson County | Cut in the Watermill Switch - Parkdale Switch 138 kV Line to establish the new Lavender Switch for SDC's Wilmer Data Center | 2023-03-20 | 2023-05-18 | [5 empty] | 0 | na | 138 | 0.4 | 1926 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | na | na | 75 | 0.4 | 25.101(c)(5)(A)
0PT46888 (M4137) | Mesquite East Switch - Sunnyvale 138 kV Line: Rebuild | City of Mesquite, Dallas County | Rebuild the Mesquite East Switch - Sunnyvale 138 kV Line. | 2023-03-20 | 2023-05-15 | [5 empty] | 0 | 138 | na | 4.08 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | 2.04 | na | na | 25.101(c)(5)(b)
0PT47790 0PT48725 (R6182) | Palestine - Crockett 69 kV Line: Rebuild Palestine Switch - Elkhart Switch | City of Palestine, Anderson County | Rebuild the Palestine - Crockett 69 kV line from Palestine Switch - Elkhart Switch. | 2023-04-10 | 2023-09-15 | [5 empty] | 0 | 69 | na | 10 | 959 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | varies | 10 | na | na | 25.101(c)(5)(B)
0PT41200 (R944) | Cumby Tap Switch - Cumby Sub 69 kV Line : Conversion to 138 kV | City of Cumby, Hopkins County | Reterminate the Cumby Tap Switch - Cumby Sub 69 kV line at Cumby Sub. | 2023-04-10 | 2023-12-15 | [5 empty] | 0 | 69 | 138 | 0.2 | 336.4 ACSR Linnet | Steel Pole | varies | 0.2 | na | na | 25.101(c)(5)(A)
0PT48098 0PT49115 (R6172) | McGregor Phillips Tap Switch - Waco West Switch 69 kV Line : Rebuild Structure 24/4B to McGregor Phillips Switch | City of McGregor, McLennan County | Rebuild the McGregor Phillips Tap Switch - Waco West Switch 69 kV Line from Structure 24/4B to McGregor Phillips Switch. | 2023-04-15 | 2023-08-31 | [5 empty] | 0 | 69 | 138 | 2 | 1926.9 ACSS/TW/HS Cumberland | Steel Pole, Wood Pole | 100 | 1 | na | na | 25.101(c)(5)(B)
0PT47983 (R8669) | Wink Switch - Aroya Switch 138 kV Line : Establish White Dune 138 kV POD for Trinity Mining's Black Pearl Substation | City of Wink, Winkler County | Provide a 138 kV point-of-delivery (POD) for Trinity Mining Technologies, LLC on the Wink Switch - Aroya Switch 138 kV Line Section. | 2023-03-01 | 2023-05-30 | [5 empty] | 0 | 138 | na | 0.23 | 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 0.2 | Varies | 0.03 | 25.101(c)(5)(A)
0PT47982 (R8660) | Wolf Switch - Wink Switch 138 kV Line : Establish Arenosa 138 kV POD for Trinity Mining's Captain Jack Substation | City of Wink, Winkler County | Provide a 138 kV point-of-delivery (POD) for Trinity Mining Technologies, LLC on the Wolf Switch - Wink Switch 138 kV Line Section. | 2023-03-01 | 2023-05-30 | [5 empty] | 0 | 138 | na | 0.23 | 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 0.2 | Varies | 0.03 | 25.101(c)(5)(A)
0PT48973 | Martin Lake Switch - Stryker Creek Switch 345 kV Line : Replace and relocate Str. 41/1 | City of Tatum, Rusk County | Replacing Structure on Martin Lake Switch - Stryker Creek Switch 345 kV Line. | 2023-04-17 | 2023-06-30 | [6 empty] | 345 | na | 0.5 | 2-1590 ACSR Falcon | Steel Lattice Tower | 150 | 0.5 | na | na | 25.101(c)(5)(B)
0PT48376 (R6224) | Hutto Switch - Gilleland Creek Switch 138 kV Line : Cut-in to establish Double Creek Sub | City of Round Rock, Williamson County | Build new line section to cut in Double Creek 138 kV Sub. | 2023-01-16 | 2023-05-15 | [6 empty] | 138 | na | 0.6 | 1926 ACSS/TW Cumberland | Steel Pole | na | na | 95 | 0.3 | 25.101(c)(5)(A)
0PT48556 (R8597) | SL East Stiles – Rocky Road 138 kV Line: Rebuild | Reagan County | Rebuild the SL East Stiles – Rocky Road 138 kV Line. | 2023-01-01 | 2023-09-15 | [6 empty] | 138 | na | 7.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 58 | 7.1 | na | na | 25.101(c)(5)(B)
0PT47802 (R6217) | Bell County East Switch - TNP One (TNMP) Switch 345 kV Line : Cut-in to establish Brangus Switch for Halo Solar. | Milam County | Cut into the Bell County East - TNP One (TNMP) 345 kV Line to establish the new Brangus Switch. | 2023-02-08 | 2023-05-18 | [6 empty] | 345 | na | 1.34 | 2-1926.9 ACSS/TW Cumberland | Lattice Tower | 160 | 0.1 | varies | 0.57 | 25.101(c)(5)(A)
0PT48608 | Bell County East Switch - Sandow Switch 345 kV Line : Replacement of Insulators and Installation of Varmit Guards | City of Rockdale, Milam County | Replace Insulators and Varmit Guards on various structures of Bell County East Switch - Sandow Switch 345 kV Line. | 2023-01-01 | 2023-05-15 | [6 empty] | 345 | na | 5.87 | 959.6 ACSS/TW Suwannee | Steel lattice | 125 | 5.87 | na | na | 25.101(c)(5)(a)
Line Clearance Review Program (LCRP)
Projects Relating to HB 4150 (HB 4150) | TBD | TBD | TBD | 2022-07-01 | TBD |  |  | TBD |  |  |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | Projects related to efforts required under HB 4150.
0PT48834 (HB4150) | Big Spring Switch - Gunsight Switch 138 kV Line : Clearance Improvement | Howard County | Replace 6 structures along Big Spring - Gunsight 138 kV Line, approximately .5 miles, and raise 16 crossarms. | 2022-11-28 | 2022-12-31 |  |  | 462444.56 |  |  | 0 | 138 | na | 57 | 636 ACSR Grosbeak, 336 ACSR Linnet | Wood H-Frame | Varies | 57 | na | na | 25.101(c)(5)(b)
STATIONS
0PT03981 (M5155) | Sherry Switch: Two Line Terminal Upgrade | City of Arlington, Tarrant County | Upgrade line terminal and associated equipment to meet as a part of upgrading the Handley Sherry 138 kV Double-circuit Line | 2022-04-19 | 2022-12-15 |  |  | 406246 |  |  | 78 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40632 (R3050) | Ogallala Switch : Install Terminal for Nazareth Solar | City of Nazareth, Castro County | Install one 345 kV, 3200 A circuit breaker at Install a 345 kV (POI) for customer's generator (TX Nazareth Solar, LLC). | 2023-07-31 | 2023-07-31 | [6 empty] | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3) | On hold
0PT04155 0PT38702 | Blagg Sub: Establish Substation with one Transf. and Two Feeder Breakers: | City of Denton, Denton County | Establish Substation with one Transf. and Two Feeder Breakers | 2020-07-28 | 2020-12-31 | 2020-12-31 |  | 4832694 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39275 0PT38451 | Dooley Sub : Replace one transformer | City of Monahans, Ward County | Rebuild existing Northward Sub with one transformer and establish new Dooley Sub with one transformer | 2020-04-05 | 2020-06-30 | 2020-06-30 |  | 3514683.05 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39486 | Lakecrest Sub (Fish Creek) : Establish Substation with one Transformer and Three Feeder Breaker | City of Grand Prairie, Dallas County | Establish Substation with one transformer and three feeder breakers | 2020-05-08 | 2020-12-30 | 2020-12-30 |  | 4390668 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38868 16T80023 | Monument Draw Sub: Establish substation with one transformer and two feeder breakers | City of Andrews, Andrews County | Establish substation with one transformer, two feeder breakers | 2020-03-27 | 2020-12-08 | 2020-12-08 |  | 4241336 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT40876 0PT39914 | Triangle Sub : Install one Transformer on #2 | City of Stanton, Martin County | Install a second transformer and remove transformers #1 and #2 at Stanton Substation. Complete installation of fiber for line protection, modify 138 kV bus protection to provide redundancy. | 2022-01-31 | 2022-10-01 |  |  | 3625120 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39289 | Waxahachie Sub : Replace two Transformers with one upgraded Transformer and add 2 Feeder Breakers | City of Azle, Tarrant County | Replace two Transformers with one upgraded Transformer and add 2 Feeder Breakers | 2021-07-17 | 2021-12-29 | 2021-12-29 |  | 5920088 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40615 (R8523) | Nelson Switch : Establish a 138 kV POI for Rodeo Solar Generator | City of Odessa, Ector County | Establish a 138 kV (POI) for Rodeo Solar Generator by installing one 138 kV, 3200 A circuit breaker in existing ring-bus. | 2020-09-18 | 2022-12-15 |  |  | 1240255 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | Cost and project was updated to include ROW estimates in November 2020. This was not accurate and the project is being revised back to its original values.
0PT40650 (R8540) | Manning POD: Establish a 138 kV POD | City of Odessa, Ector County | Establish a 138 kV POD on the LCRA Crane East - Crane 138 kV line. | 2020-12-11 | 2022-08-16 | 2022-08-16 |  | 922339 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
19T63016 (R8444) | Scurry County South Switch: Add 138 kV line terminal for Canyon Wind | City of Snyder, Scurry County | Install a new 138 kV bay with two 138 kV, 3200 A circuit breakers and associated equipment to install a 138 kV POI for customer's generator. | 2021-07-16 | 2023-02-01 |  |  | 1995325 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41551 | Stanton Sub : Install a fourth transformer at Stanton Substation with a one transformer, remove transformers #1 and #2 at Stanton Substation and demo 69 kV wood structure | City of Stanton, Martin County | Install a fourth transformer at Stanton Substation with a one transformer, remove transformers #1 and #2 at Stanton Substation and demo 69 kV wood structure. | 2020-08-28 | 2020-12-10 | 2020-12-10 |  | 2143550 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39282 0PT39322 | Poolville Sub : Establish Substation with one transformer and two feeder breakers | City of Weatherford, Parker County | Establish Substation with one transformer and two feeder breakers. | 2021-01-26 | 2021-06-28 | 2021-06-28 |  | 4307847 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | Costs updated to include associated ROW estimates.
0PT40937 0PT42656 | Blair Lake Sub : Establish station with 47 MVA, 138/69-21.6 kV Transformer and Install Distribution Automation on Feeder 6321 | City of Pecos, Reeves County | Replace Bank #1 with 47 MVA, 138/69-21.6 kV transformer. Also includes all work associated with PETE 40783 (Install Distribution Automation on Feeders 6321). | 2021-07-11 | 2021-12-30 | 2021-12-30 |  | 3439065 |  |  | 100 | na | 69/138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40648 (R8544) | Dillon POD : Establish 138 kV POD | Martin County | Provide a 138 kV (POD) on the Andrews North McKenzie Draw 138 kV line by installing three138 kV 3200 A motor operated sectionalizing switches and low-voltage metering. | 2021-01-12 | 2022-11-18 |  |  | 764363 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40611 | Graham 345 kV Switch: Auto protection upgrade | Young County | Upgrade 138 kV/345 kV auto protection panels (2 panels total) and (1) Tertiary reactor panel. Modify 345 kV DC system to allow fully redundant DC sources. Add 345 kV bus CCVT's C & D buses. Replace 345 kV C&D house battery chargers with 35A. | 2020-10-19 | 2022-05-23 | 2022-05-23 |  | 1180134 |  |  | 100 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40543 | Graham Plant Switch : Bus protection upgrade scope | Young County | Modify relaying to include installing two gen interconnection/separation schemes, and upgrade 138 kV Bus A&B protection. Add 138 kV bus CCVT's on A & B buses to provide backup for single-breaker line protection. | 2020-10-22 | 2022-05-23 | 2022-05-23 |  | 1438785 |  |  | 100 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41627 (R984) | Stouts Creek Switch : Establish Station for (POI) | Hopkins County | Establish station by installing three 345 kV, 3200 A circuit breakers in a 3-breaker ring bus arrangement for a (POI). Station will connect to the Allen Switch- Monticello Switch 345 kV line. | 2023-05-08 | 2023-11-16 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41218 (M4311) | Ennis West Switch: Install 138 kV circuit breakers | City of Ennis, Ellis County | Install 138 kV circuit breakers and re-terminate Oncor line terminals | 2021-01-12 | 2021-05-09 | 2021-05-09 |  | 2281324 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38759 (R6069) | Redland Switch: Rebuild Herty North Switch with a 6-breaker 138 kV breaker-and-a-half bus arrangement | City of Lufkin, Angelina County | Rebuild Herty North Switch with a 6-breaker 138 kV breaker-and-a-half bus arrangement. | 2020-08-25 | 2021-06-01 | 2021-06-01 |  | 8859445 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42130 | Irving Valley View Sub : Install transformer #4 with one transformer and two feeder breakers | City of Irving, Dallas County | Install transformer #4 with one 138/25 kV transformer and two feeder breakers. | 2020-12-03 | 2021-06-01 | 2021-06-01 |  | 3726946 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42207 0PT42302 | Alcatraz Sub : Establish substation with two transformers and four feeder breakers | Loving County | Establish substation with two transformers and four OH feeder breakers. | 2021-01-25 | 2021-12-06 | 2021-12-06 |  | 5923526 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42121 | Midland West Sub : Install transformer #4 by adding one transformer and one feeder breaker with UG exit | City of Odessa, Midland County | Install transformer #4 by adding one transformer and one feeder breaker with UG exit. | 2021-02-26 | 2021-08-17 | 2021-08-17 |  | 1813969 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42665 (M3092) | Austin Ranch Sub : Establish a POI 138 kV for Brazos | City of The Colony, Denton County | Establish a 138 kV POI at Austin Ranch. Install two LS switches | 2021-04-09 | 2022-06-06 | 2022-06-06 |  | 256060 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42794 | Plano Shiloh Road Sub : Install a third transformer at Plano Shiloh Rd and three breakers | City of Plano, Collin County | Install a third transformer at Plano Shiloh Rd and three breakers | 2021-03-30 | 2021-06-30 | 2021-06-30 |  | 6182250 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42143 | Driver Sub : Install transformer #4 with one transformer and two feeders | City of Odessa, Midland County | Install transformer #2 with one transformer and two UG feeder breakers | 2021-01-05 | 2021-12-19 | 2021-12-19 |  | 2640072 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41447 (M5317) | Toco Switch: Add a single line terminal to establish POI | City of Toco, Lamar County | Add a single line terminal to the existing ring-bus for the POI. | 2023-02-27 | 2023-04-13 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42139 | Celina Southeast Sub : Install transformer #2 with one transformer and two UG feeder breakers | City of Celina, Collin County | Install transformer #2 with one transformer and two 25 kV feeder breakers. | 2023-01-16 | 2025-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | On hold
0PT42176 | Brookhollow Sub : Install transformer #3 with one transformer and two feeder breakers | City of Arlington, Tarrant County | Install transformer #3 with one transformer and two feeder breakers. | 2021-02-28 | 2021-12-13 | 2021-12-13 |  | 2900455 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41016 (M5222) | Duval Sub: Remove 69 kV station and establish 138-12.5 kV station | City of Fort Worth, Tarrant County | 69 kV station and establish 138-12.5 kV station | 2022-07-15 | 2022-12-16 |  |  | 8309347 |  |  | 61 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40560 (R6132) | Four Brothers Switch : Establish 345 kV switch bus with a 3-breaker arrangement | City of Waco, Hill County | Establish 345 kV switch bus with a 3-breaker arrangement | 2021-10-13 | 2022-05-09 | 2022-05-09 |  | 6227825 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03978 (M5155) | Handley Switch: Upgrade line terminal and associated equipment | City of Fort Worth, Tarrant County | Upgrade line terminal and associated equipment as a part of upgrading the Handley – Sherry 138 kV double-circuit line. | 2021-12-01 | 2022-12-15 |  |  | 580434 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03979 (M5155) | Lakewood Sub: 138 kV terminal upgrade | City of Fort Worth, Tarrant County | Upgrade line terminal and associated equipment as a part of upgrading the Handley – Sherry 138 kV double-circuit line. | 2021-03-10 | 2021-12-14 | 2021-12-14 |  | 1204494 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41222 (R8308) | Natural Dam Sub: Station Expansion | City of Big Spring, Howard County | Upgrade the 138 kV switch by installing one 3200 A, 138 kV circuit breaker in a 5-breaker ring bus arrangement. | 2021-02-01 | 2021-12-22 | 2021-12-22 |  | 1095864 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41451 0PT42232 (M4302) | Shankle Switch: Establish 138 kV breaker and a half station (formerly Ennis Switch) | City of Ennis, Ellis County | Establish station by installing eight 138 kV, 3200 A circuit breakers in a breaker-and-a-half bus arrangement. | 2021-05-07 | 2021-12-16 | 2021-12-16 |  | 6304766 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42652 | Shipwreck Sub : Install the 3rd transformer with two feeder breakers | City of Odessa, Reagan County | Install the 3rd transformer with two feeder breakers. | 2021-04-12 | 2021-10-01 | 2021-10-01 |  | 2759170 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41031 18T80022 (M5278) | Timberview Switch: Establish 345 kV Switch | City of Everman, Tarrant County | Establish 345 kV switch bus with a 15-breaker and-a-half bus arrangement. | 2021-06-07 | 2021-12-22 | 2021-12-22 |  | 20561331 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42128 0PT42305 | Flat Land (Red Lake) Sub : Establish Flat Land Sub with two transformers and two feeder breakers. | City of Stanton, Martin County | Establish Flat Land Sub with two transformers and two feeder breakers. | 2021-02-25 | 2021-06-17 | 2021-06-17 |  | 5071351 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42713 (R8526) | Horseshoe Springs Switch : Establish line terminal by installing one 3200A, 138 kV circuit breaker(s) | City of Orla, Culberson County | Establish line terminal by installing one 3200A, 138 kV circuit breaker(s). | 2021-04-10 | 2021-11-16 | 2021-11-16 |  | 462379 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42712 (R8526) | Riverton Switch : Establish line terminal by installing one 3200A, 138 kV circuit breaker(s) | City of Orla, Culberson County | Establish line terminal by installing one 3200A, 138 kV circuit breaker(s). | 2021-03-02 | 2021-12-07 | 2021-12-07 |  | 1165607 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42797 (R4023) | Tecumseh Creek Switch: Establish 345 kV station for POI | City of Graham, Young County | Establish 345 kV, three breaker ring bus with circuit breakers to provide a POI. | 2021-05-05 | 2021-11-15 | 2021-11-15 |  | 7174910 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03987 (M4088) | Morrison Lane Switch: Upgrade all line terminal and associated equipment | City of Dallas, Dallas County | Upgrade all line terminal and associated equipment as a part of the rebuilding the Northaven Switch Station - Morrison Lane Switch Station 138 kV double-circuit line. | 2022-03-01 | 2022-05-23 | 2022-05-23 |  | 486520 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43602 0PT43314 | Prosper Sub : Establish substation with one transformer and two feeder breakers | City of Prosper, Collin County | Establish substation with one transformer and two feeder breakers. | 2021-04-27 | 2021-06-29 | 2021-06-29 |  | 8512765 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42179 | Campion (formerly Bluebonnet Lakes) Sub : Establish station with one transformer and two feeder breakers | City of Grand Prairie, Dallas County | Establish station with one transformer and two feeder breakers. | 2022-11-20 | 2023-05-15 |  |  | 8473410 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42377 (M4247) | Carrollton Northwest Switch : Replace the existing autotransformer | City of Carrollton, Denton County | Replace the existing autotransformer and install one 345 kV, 3200A circuit breaker on the 345 kV bus. | 2021-07-21 | 2021-12-21 | 2021-12-21 |  | 8135469 |  |  | 100 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41323 (M5134) | Calmont Switch: Install one capacitor bank consisting of three 18.4 MVAR stages | City of Fort Worth, Tarrant County | Install one capacitor bank consisting of three 18.4 MVAR stages of voltage and supervisory controlled 138 kV transmission capacitors at Calmont 138 kV Switch. | 2021-10-04 | 2021-12-30 | 2021-12-30 |  | 1704594 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41599 (M4093) | Mountain Creek Switch : Install two 138 kV, 3200 A circuit breakers | City of Dallas, Dallas County | Install two 138 kV, 3200 A circuit breakers for Mountain Creek Switch- Cedar Crest Switch 138 kV double-circuit line. | 2021-08-14 | 2021-12-15 | 2021-12-15 |  | 1361266 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41754 0PT40063 | Oil Mill Lake Sub : Rebuild Marlin sub on new site | City of Marlin, Falls County | Establish station to replace Marlin with two transformers. Connect the station to the Marlin Switch – Groesbeck Switch 69 kV line and install three 138 kV line sectionalizing switches. | 2021-04-19 | 2021-12-10 | 2021-12-10 |  | 5356546 |  |  | 100 | 69 | 69/138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43555 (R8492) | Rexall Switch : Replace two 138 kV circuit breakers with auto sectionalizing switches | City of Odessa, Midland County | Replace two 138 kV circuit breakers with auto sectionalizing switches | 2021-10-13 | 2021-12-22 | 2021-12-22 |  | 1055811 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42512 | Venus Switch : Establish a new transformer with two feeder breakers | City of Venus, Ellis County | Establish a new transformer with two feeder breakers | 2020-07-21 | 2021-12-08 | 2021-12-08 |  | 3636039 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42153 14T80018 17T80007 | Stagecoach Sub : Establish station with one transformer and two feeder breakers | City of Killeen, Bell County | Establish station with one transformer and two feeder breakers. | 2021-05-14 | 2021-12-16 | 2021-12-16 |  | 5884419 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43812 | SL Windmill Switch : Replace RTU | Carson County | Replace RTU | 2021-07-05 | 2021-10-22 | 2021-10-22 |  | 392113 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43811 | SL Alibates Switch : Replace RTU | City of Hereford, Deaf Smith County | Replace RTU | 2021-07-16 | 2021-10-22 | 2021-10-22 |  | 360801 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(a)(3) | Date was corrected to match actual Construction Complete and Energization date
0PT43523 0PT41759 | Moores Mill Sub : Establish substation with one transformer and four feeder breakers | City of Temple, Bell County | Establish substation with one transformer and four feeder breakers | 2021-05-07 | 2021-11-15 | 2021-11-15 |  | 5551467 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42651 | Kennedale Sub : Remove the existing 345 kV transformers from substation and install a 3rd transformer | City of Kennedale, Tarrant County | Remove the existing 345 kV transformers from substation and install a 3rd transformer and complete distribution feeder exit work | 2021-06-10 | 2021-12-17 | 2021-12-17 |  | 3600695 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42148 | Mansfield Sub : Install transformer #3 with one transformer and two feeder breakers | City of Mansfield, Tarrant County | Install transformer #3 with one transformer and two feeder breakers | 2021-07-22 | 2021-12-30 | 2021-12-30 |  | 2859366 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39293 17T80045 0PT40089 | Elkhart Sub : Install transformer #2 with one transformer and one feeder breaker | Elkhart County | Install transformer #2 with one transformer and one feeder breaker | 2021-08-18 | 2021-12-16 | 2021-12-16 |  | 3379346 |  |  | 100 | na | 69 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39290 | Lake Brownwood Sub : Establish a new substation with one transformer and two feeder breakers | City of Brownwood, Brown County | Establish a new substation with one transformer and two feeder breakers and demolish the existing station. | 2021-06-07 | 2021-12-15 | 2021-12-15 |  | 2485000 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43503 | Graham 345 kV Switch : Replace two circuit switchers with 345 kV circuit breakers | City of Graham, Young County | Replace two circuit interrupters #6333 and #6353 with 345 kV breakers and add leaker management | 2021-10-16 | 2022-03-14 | 2022-03-14 |  | 1485043 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43638 | Midland Downtown Sub : Replace two existing transformers and add one feeder breakers to bank #1. | City of Midland, Midland County | Replace two existing transformers and add one feeder breakers to bank #1 | 2021-08-09 | 2021-12-01 | 2021-12-01 |  | 3594743 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39494 0PT38777 (M4275) | Greenbrier Switch (formerly Princeton) : Establish Switching Station | City of Princeton, Collin County | Establish switching station adjacent to the existing Princeton POD by installing six 138 kV circuit breakers in a breaker-and-a-half arrangement as part of the line upgrade from Anna Tap - Princeton Switch. | 2021-11-09 | 2022-06-23 | 2022-06-23 |  | 7283918 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43517 | Hemphill Switch : Replace two 138 kV circuit breakers | City of Fort Worth, Tarrant County | Replace two 138 kV circuit breakers | 2021-09-14 | 2021-12-17 | 2021-12-17 |  | 473962 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43511 | Sherman South Switch : Replace one 138 kV circuit breaker | City of Sherman, Grayson County | Replace one 138 kV circuit breaker | 2021-10-09 | 2021-12-06 | 2021-12-06 |  | 274819 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43502 | Monticello Switch : Replace one 345 kV circuit breaker and replace EPS metering 345 kV CCVTS | City of Mount Pleasant, Titus County | Replace one 345 kV circuit breaker | 2022-04-04 | 2022-05-26 | 2022-05-26 |  | 586617 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42711 0PT43445 (R8452) | Drill Hole (formerly known as Owl Hills West) Switch: Install two capacitor banks consisting of three 18.4 MVAR stages | Culberson County | Install two capacitor banks consisting of three 18.4 MVAR stages of voltage and supervisory controlled 138 kV transmission capacitors on each circuit of the Horseshoe Springs Switch – Riverton Switch 138 kV double-circuit line. | 2021-09-07 | 2021-12-30 | 2021-12-30 |  | 5804579 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42174 | Temple Southeast Sub : Install transformer #2 and add two feeder breakers | City of Temple, Bell County | Install transformer #2 and add two feeder breakers | 2021-06-18 | 2021-11-02 | 2021-11-02 |  | 2584402 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40959 0PT41841 | Reindeer Sub : Establish substation with one transformers and two feeder breakers | City of Lancaster, Dallas County | Establish substation with one transformers and two feeder breakers | 2021-07-30 | 2021-12-29 | 2021-12-29 |  | 4893263 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44371 | Goddard Sub : Replace switchgear with outdoor feeder breakers and install distribution automation on two feeders | City of Midland, Midland County | Replace switchgear with outdoor feeder breakers and install distribution automation on two feeders | 2021-07-20 | 2021-12-15 | 2021-12-15 |  | 3088405 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43862 | Landfill POD : Establish 138kV Point of Delivery | Andrews County | Landfill POD : Establish 138kV Point of Delivery | 2021-10-29 | 2021-11-19 | 2021-11-19 |  | 793020 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41041 0PT42306 (R8479) | Courtney Creek (Pecos) Switch: Establish 138/69 kV Switching Station | Pecos County | Establish the Courtney Creek 138/69 kV Switch in order to tie into AEP's Rio Pecos Switch - Fort Stockton Switch 138 kV line. The switching station will be installed initially as a 5-breaker 138 kV breaker-and-a-half arrangement with one 138/69 kV autotransformer and one 69 kV line terminal. | 2022-09-15 | 2023-02-15 |  |  | 10020859.34 |  |  | 9 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39677 (M5279) | Forest Hill Sub : Create a Loop In - Loop Out Connection | City of Fort Worth, Tarrant County | Create a loop in - loop out connection and install associated equipment as a part of reconductoring the 4.0-mile Everman Switch - Rolling Hills - Marrs Switch 138 kV double-circuit line | 2021-06-11 | 2021-12-15 | 2021-12-15 |  | 1427268 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39492 (M364) | Richardson Sub : Upgrade line terminal as a part of upgrading the Plano West Switch - Richardson Collins 138 kV line | City of Richardson, Dallas County | Upgrade line terminal as a part of upgrading the Plano West Switch - Richardson Collins 138 kV line | 2022-01-03 | 2022-03-21 | 2022-03-21 |  | 956152 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41032 (M5278) | Everman Switch: Reconfigure 345 kV station by constructing a 4-breaker 345 kV in a ring bus arrangement | City of Fort Worth, Tarrant County | Reconfigure 345 kV station by constructing a 4-breaker 345 kV in a ring bus arrangement. | 2021-06-28 | 2022-06-01 | 2022-06-01 |  | 4728468 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41214 (M4134) | Lake Hubbard Switch: Install two 138 kV circuit breakers | City of Garland, Dallas County | Install two 138 kV circuit breakers and upgrade the Prairie Creek line terminal equipment. | 2021-08-19 | 2021-12-01 | 2021-12-01 |  | 941092 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43953 (R8538) | Midland East Switch: 138 kV station rebuild | City of Midland, Midland County | Rebuild the 138 kV switch as an 13-breaker initial, 18-breaker ultimate breaker-and-a-half arrangement. | 2021-06-10 | 2021-12-15 | 2021-12-15 |  | 10097944 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44443 0PT44618 | Blain (formerly known as Dew) Sub : Establish substation with one transformer and two feeder breakers | City of Dew, Freestone County | Establish substation with one transformer and two feeder breakers | 2021-08-11 | 2022-10-15 |  |  | 4802523 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41017 0PT41805 | Stuart (formerly Bryan Avenue) Substation: Convert Station from 69 kV to 138 kV operation by rebuilding a new substation to replace the existing station | City of Fort Worth, Tarrant County | Rebuild a new substation to replace the four existing transformers and switchgear feeder breakers with two transformers and eight new switchgear type feeder breakers. | 2021-04-12 | 2023-05-15 |  |  | 8238720 |  |  | 72 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | Station grading began prior to reporting on the MCPR. All construction work has ceased and will resume 45 days from the reporting date on June 28.
0PT43010 0PT40574 | Gunsolus Creek Substation : Establish a new station with two transformers and seven feeder breakers on a new site to replace Breckenridge Sub. | City of Breckenridge, Stephens County | Establish a new station with two transformers and seven feeder breakers on a new site to replace Breckenridge Substation. | 2021-08-17 | 2021-12-28 | 2021-12-28 |  | 5432920 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41229 0PT39325 | Bell Mountain (formerly Hudson Oaks) Substation : Establish substation with one transformer and two feeder breakers | City of Hudson Oaks, Parker County | Establish substation with one transformer and two feeder breakers | 2022-10-17 | 2023-05-01 |  |  | 6859188 |  |  | 3 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41015 (M5222) | Handley Switch: Remove 69 kV station, and add 138 kV terminal by using the existing autotransformer position | City of Fort Worth, Tarrant County | Remove all existing 69 kV equipment from the station and add 138 kV terminal by using the existing autotransformer position. | 2023-01-24 | 2023-05-15 |  |  | 2131413 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT02811 (M4250) | Duncanville Substation: Upgrade all line terminal and associated equipment | City of Duncanville, Dallas County | Upgrade all line terminal and associated equipment as a part of upgrading the Cedar Hill Switch - Camp Wisdom Road Switch 138 kV line | 2022-01-07 | 2022-05-19 | 2022-05-19 |  | 954401 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40561 (R990) | Birthright Switch: Establish 3 breaker ring bus switch and modify relaying at Monticello Switch and Farmersville Switch | Birthright County | Establish 345 kV ring-bus switch in the Farmersville Switch-Monticello Switch 345 kV line and give generator one point-of-interconnection | 2022-11-28 | 2023-05-18 |  |  | 6648534 |  |  | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41219 (R8504) | Sand Lake Switch: 138 kV line terminal additions | Ward County | Install four 138 kV, 3200 A circuit breakers (two new half positions) and associated equipment to terminate the new 138 kV Cochise lines. | 2021-08-30 | 2021-12-14 | 2021-12-14 |  | 2959349 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41705 (R6097) | Mabank Substation: Upgrade terminal equipment | City of Mabank, Henderson County | Upgrade terminal equipment to meet or exceeds 3200 A part of rebuilding the Eustace Southeast Switch (RCEC) - Mabank 138 kV line section. | 2021-09-15 | 2021-12-22 | 2021-12-22 |  | 374809 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42336 (R6155) | St. Johns Switch: Establish 345 kV switch in a 3-breaker ring bus arrangement to provide a new generator 345 kV point of interconnection (POI) | Falls County | Establish a 345 kV generator point of interconnection (POI) in the Rattlesnake Road Switch-Jewett Switch 345 kV line by establishing St. Johns 345 kV Switch by installing three 345 kV 3200 A circuit breakers in a ring bus arrangement | 2021-10-08 | 2022-04-14 | 2022-04-14 |  | 7163244 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43512 | Oran Switch : Replace one 138 kV circuit breaker | City of Graford, Palo Pinto County | Replace one 138 kV circuit breaker | 2021-10-20 | 2021-12-13 | 2021-12-13 |  | 322222 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44089 | Beacon Hill Substation : Establish station with one transformer and two feeder breakers | City of Sweetwater, Nolan County | Establish substation with one transformer and two feeder breakers | 2021-07-08 | 2022-06-21 | 2022-06-21 |  | 4266750 |  |  | 100 | na | 138/69 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44195 | Tyler West Sub : Install FID's on both transformers and install two new retrofit transformer protection panels | City of Tyler, Smith County | Remove and replace the two transformer flash buses with FID’s. Also install two new retrofit transformer protection panels. | 2021-10-01 | 2021-12-15 | 2021-12-15 |  | 585465 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43961 0PT44072 0PT48344 (R2014) | Pin Oak (formerly known as Big Brown Tap) Switch: Establish 138 kV substation using a 5-breaker 138 kV breaker-and-a-half arrangement | City of Fairfield, Freestone County | Establish 138 kV substation using a 5-breaker 138 kV breaker-and-a-half arrangement as part of rebuilding the Big Brown Tap 138 kV Switch. | 2022-06-09 | 2022-12-15 |  |  | 9206432.91 |  |  | 65 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43957 0PT44928 0PT44608 (R8258) | Midland East Switch: 345 kV substation rebuild | City of Midland, Midland County | Rebuild the Midland East 345 kV Switch as a 7-breaker 345 kV breaker-and-a-half bus arrangement. Install two 3200 A, 138 kV circuit breakers and two new autotransformers as apart of rebuilding the Midland East Switch 345/138 kV Switch. | 2021-09-17 | 2022-12-15 |  |  | 20264435 |  |  | 91 | na | 345/138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43082 (R8573) | Dermott Switch : Establish a line terminal | City of Snyder, Scurry County | Add one 3200 A, 138 kV circuit breaker to establish a point-of-interconnection. | 2022-01-24 | 2022-10-31 |  |  | 1325428 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41741 (R3021) | Wallaby Switch : Install three 3200 A ,345 kV circuit breakers in a ring bus configuration | City of Dawn, Deaf Smith County | Establish switching station by installing three 3200 A, 345 kV circuit breakers in a ring bus configuration. | 2022-11-14 | 2024-11-14 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41020 (M5222) | Forest Hill Switch: Remove 69 kV equipment | City of Fort Worth, Tarrant County | Disconnect and remove the existing 138/69 kV autotransformer, 69 kV circuit breaker and associated equipment. Includes removal of all existing remaining 69 kV equipment and lattice structures. | 2023-04-10 | 2023-05-15 | [5 empty] | 0 | 138/69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40273 (R6158) | Brown Switch: Add one breaker to the 345 kV breaker-and-a-half arrangement | City of Brookesmith, Brown County | Add one breaker to the 345 kV breaker-and-a-half arrangement for point-of-interconnection. | 2021-10-04 | 2022-06-22 | 2022-06-22 |  | 3668033 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38432 0PT45236 R9015 | Big Spring CRMWD Sub: Convert station to 138 kV | City of Big Spring, Howard County | Convert to 138 kV and connect to the nearby Big Spring Switch - Big Spring West 138 kV line. | 2021-09-17 | 2022-03-29 | 2022-03-29 |  | 2178049 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43707 (M4324) | Soap Creek Switch: Establish a new 138 kV, 3 breaker ring bus station for point-of-interconnection | City of Midlothian, Ellis County | Establish substation by installing three 3200 A, 138 kV circuit breakers in a 3-breaker ring bus arrangement for a point-of-interconnection. | 2021-11-15 | 2022-06-01 | 2022-06-01 |  | 4317006 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44263 (M4236) | Royse Switch: 138 kV terminal upgrade | City of Royse City, Rockwall County | Upgrade line equipment as a part of rebuilding the 138 kV line | 2021-11-05 | 2022-05-13 | 2022-05-13 |  | 1148524 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42930 | Rocky Creek Switch: Install transformer #2 with one transformer and a feeder breaker | City of Fort Worth, Tarrant County | Install transformer #2 with one transformer and a feeder breaker | 2021-12-09 | 2022-05-05 | 2022-05-05 |  | 2137797 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44234 | Taylor West Sub : Install transformer #3 with one transformer and two feeder breakers | City of Hutto, Williamson County | Install transformer #3 with one transformer and two feeder breakers | 2021-09-27 | 2022-06-20 | 2022-06-20 |  | 2381361 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44244 | Inwood Road Sub : Install transformer #3 with one transformer and three switchgear style breakers | City of Dallas, Dallas County | Install transformer #3 with one transformer and three switchgear style breakers | 2022-01-11 | 2022-11-18 |  |  | 4794016 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45363 | Mt Enterprise 345 kV Switch : Replace 345 kV circuit breaker | City of Henderson, Rusk County | Replace 345 kV circuit breaker | 2022-03-22 | 2022-04-19 | 2022-04-19 |  | 561637 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45362 | Webb 345 kV: Replace 345 kV circuit breaker | City of Arlington, Tarrant County | Replace 345 kV circuit breaker | 2022-02-25 | 2022-04-19 | 2022-04-19 |  | 520462 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Date was corrected to match actual Construction start date.
0PT44633 0PT44809 0PT47809 (R6170) | Kitsee POI : Establish 138 kV point-of-interconnection | City of Terrell, Kaufman County | Establish a 138 kV point-of-interconnection including the installation of three 138 kV, 2000 A motor operated sectionalizing switches. | 2022-03-17 | 2022-11-01 | 2022-11-01 |  | 658784 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44632 0PT45249 (R6152) | Will White POI : Establish 138 kV point-of-interconnection | City of Tool, Henderson County | Establish a 138 kV point -of-interconnection including the installation of three 138 kV 2000 A motor operated sectionalizing switches. | 2022-02-09 | 2022-12-01 |  |  | 811168 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44266 (R797) | Killeen Switch : Replace 345/138 kV autotransformer #1 | City of Killeen, Bell County | Replace the existing autotransformer #1 and install two 37.5 MVAR reactor banks on the tertiary of the new autotransformer. Install one 345 kV, 3200 A circuit breaker. | 2022-01-09 | 2022-05-17 | 2022-05-17 |  | 3243212 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43849 | Buzzard Draw Switch: Install two 138 kV line terminals, remove auto, and remove 69 kV yard | City of Big Spring, Howard County | Install one 3200 A, 138 kV circuit breaker to complete ring bus arrangement and Buzzard Draw 69 kV Switch will be removed and de-energized. | 2022-01-10 | 2022-05-02 | 2022-05-02 |  | 1985171 |  |  | 100 | 138/69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43651 (R8558) | Mockingbird Sub: Reconfigure for double tap connection to 138 kV lines. | City of Midland, Midland County | Reconfigure for double tap connection to 138 kV lines | 2022-11-07 | 2022-12-15 |  |  | 248277 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42285 (R6148) | Brushy Creek Switch : Establish 138 kV breaker-and-a-half station | City of Coupland, Williamson County | Establish station with seven 138 kV circuits breakers in a breaker-and-a-half arrangement. | 2021-10-07 | 2022-05-18 | 2022-05-18 |  | 7576227 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41220 (R8505) | Wolf Switch: 138 kV line terminal addition | City of Monahans, Ward County | Install one 3200 A, 138 kV circuit breaker. | 2022-03-24 | 2022-05-18 | 2022-05-18 |  | 981337 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42635 | Sherry Switch : Replace MDAR relaying panels for two circuit breakers | City of Arlington, Tarrant County | Replace MDAR relaying panels for two circuit breakers | 2021-04-27 | 2022-03-01 | 2022-03-01 |  | 335867 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43642 (R3023) | Blackwater Draw Switch : Add rung with two 345 kV breakers | City of Abernathy, Hale County | Install two 3200 A, 345 kV circuit breakers as part of installing a 345 kV point-of-interconnection. | 2022-01-03 | 2023-07-21 |  |  | 3838169 |  |  | 99 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39309 | Sycamore Creek Sub : Install transformer #4 with two feeder breakers | City of Benbrook, Tarrant County | Install transformer #4 with two feeder breakers and also add two feeder breakers on transformer #3 | 2021-09-13 | 2023-05-25 |  |  | 2988557 |  |  | 2 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44887 0PT39254 | Waco M&M Mars Sub : Install transformer #3 with 2 feeder breakers | City of Waco, McLennan County | Install transformer #3 with two feeder breakers | 2022-04-29 | 2022-12-01 |  |  | 6227656 |  |  | 59 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44317 (R4022) | Pecan Tree Sub: Establish 138 kV substation and install one transformer with three feeder breakers | City of Holliday, Archer County | Establish 138 kV substation and install one transformer with three feeder breakers | 2022-07-15 | 2022-12-20 |  |  | 5882174 |  |  | 42 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44296 (M5172) | Azle Sub : Upgrade 138 kV line terminals | City of Fort Worth, Tarrant County | Upgrade 138 kV line terminal and associated equipment | 2023-03-15 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44280 (R8575) | Salt Flat Road Sub : Install 55.2 MVAR 138 kV capacitor with three18.4 MVAR stages | Midland County | Install one capacitor bank consisting of three 18.4 MVAR stages of voltage and supervisory controlled 138 kV transmission capacitors | 2021-12-10 | 2022-05-09 | 2022-05-09 |  | 2469535 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43991 | Grady: Install 55.2 MVAR 138 kV capacitors | Martin County | Install one capacitor bank consisting of three 18.4 MVAR stages of 138 kV voltage and supervisory controlled emergency transmission capacitors | 2022-03-10 | 2022-06-14 | 2022-06-14 |  | 2440391 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43989 (R8568) | Centralia: Install 55.2 MVAR 138 kV capacitor bank | Upton County | Install one capacitor bank consisting of three 18.4 MVAR stages of 138 kV voltage and supervisory controlled emergency transmission capacitors. | 2021-12-20 | 2022-05-24 | 2022-05-24 |  | 2141814 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43970 | Loy Lake Sub : Establish station with one transformer, two feeder breakers and three18.4 MVAR 138 kV capacitors | City of Denison, Grayson County | Establish station with one transformer, two feeder breakers and three18.4 MVAR 138 kV capacitors | 2022-02-03 | 2022-08-31 |  |  | 6731530 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43655 (R8561) | Lamesa Switch: Replace existing 138/69 kV autotransformer #1 | City of Lamesa, Dawson County | Replace existing 138/69 kV autotransformer #1 | 2022-03-31 | 2022-06-20 | 2022-06-20 |  | 867512 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04143 | Millers Ferry Substation: Install transformer #3 with two feeder breakers | City of Wilmer, Dallas County | Install transformer #3 with two feeder breakers | 2021-11-01 | 2022-07-13 | 2022-07-13 |  | 2127772 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41261 (R6157) | Cow Bayou Switch : Establish a 138 kV POI 4-breaker ring bus switchyard | City of North Prairie, Falls County | Establish a 138 kV POI 4-breaker ring bus switchyard | 2022-03-03 | 2022-12-15 |  |  | 5992225 |  |  | 95 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43978 0PT44757 (R8551) | Brown: Install 55.2 MVAR 138 kV capacitors and relay modifications for Buzzard Draw Switch 138 kV line terminal | City of Ackerly, Martin County | Install one capacitor bank consisting of three 18.4 MVAR stages of 138 kV voltage and supervisory controlled emergency transmission capacitors. | 2022-01-01 | 2022-05-12 | 2022-05-12 |  | 2105080 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43591 (M4230) | Venus Switch: Upgrade line terminal and associated equipment on two circuit breakers | City of Venus, Ellis County | Upgrade line terminal and associated equipment on two circuit breakers | 2022-11-28 | 2022-12-15 |  |  | 458141 |  |  | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45122 | Calmont Sub : Add transformer #8 with 3 feeders and rework 138 bus, and remove transformer #2 and #3 along with switchgear | City of Fort Worth, Tarrant County | Add transformer #8 with 3 feeders and rework 138 bus, and remove transformer #2 and #3 along with LV switchgear | 2022-06-24 | 2022-12-31 |  |  | 5218758 |  |  | 23 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45089 0PT46036 0PT45953 (M4342) | Kings Creek Switch : Establish new station | City of Kaufman, Kaufman County | Establish 138 kV switch by installing three 3200 A, 138 kV circuit breakers in a 3-breaker ring bus arrangement, ultimate 4-breaker 138 kV ring bus arrangement | 2021-12-15 | 2022-05-24 | 2022-05-24 |  | 4525866 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44276 0PT44552 (R8452) | Pinkney Sub: Establish new substation with one transformer and one feeder | City of Blanket, Brown County | Establish a new substation with one transformer and one feeder breaker | 2022-01-21 | 2022-06-30 | 2022-06-30 |  | 4599118 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44264 0PT44838 (R6139) | Battleground (formerly known as Coupland) Sub : Establish substation with one transformer and one feeder breaker | Williamson County | Establish a new substation with one transformer and one feeder breaker | 2022-02-10 | 2022-06-29 | 2022-06-29 |  | 4929534 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44243 | Kleberg Sub : Replace transformer #2 and rebuild LV bus with two feeder breakers per transformer | City of Dallas, Dallas County | Replace transformer #2 and rebuild LV bus with two feeder breakers per transformer | 2022-01-10 | 2022-06-01 | 2022-06-01 |  | 2862907 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44230 0PT46714 | Kimball Road Sub : Install bank #3 with one transformer and one feeder breaker | City of Grapevine, Tarrant County | Install bank #3 with one transformer and one feeder breaker | 2022-01-04 | 2022-05-31 | 2022-05-31 |  | 4018618 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44228 | Bird Nest Sub : Install bank #2 with one transformer and two feeder breakers | City of Pflugerville, Travis County | Install bank #2 with one transformer and two feeder breakers | 2022-01-14 | 2022-06-01 | 2022-06-01 |  | 2170661 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42132 (R3022) | Kress Switch : Establish station and install three 345 kV, 3200 A circuit breakers in a ring bus configuration | Swisher County | Establish station and install three 345 kV, 3200 A circuit breakers in a ring bus configuration | 2022-08-14 | 2022-12-01 |  |  | 7986575 |  |  | 43 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45124 | Lakecrest Sub : Add station #2 with one transformer and four feeder breakers | City of Grand Prairie, Dallas County | Add station #2 with one transformer and four feeder breakers | 2022-02-12 | 2022-06-30 | 2022-06-30 |  | 2582476 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45742 | Prairie Creek Sub : Replace transformers #1 and #2 | City of Dallas, Dallas County | Replace transformers #1 and #2 and add six circuit breakers | 2022-04-05 | 2022-12-01 |  |  | 6444164 |  |  | 89 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43983 0PT44754 0PT47107 (R8562) | Aquifer Tap : Install 110.4 MVAR 138 kV capacitors | Reeves County | Install two capacitor banks each consisting of three 18.4 MVAR stages of 138 kV voltage and supervisory controlled transmission capacitors. | 2022-02-28 | 2022-07-05 | 2022-07-05 |  | 5072146 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43964 (R8567) | Tex Harvey Sub: Install 55.2 MVAR 138 kV capacitor bank | City of Midland, Midland County | Install a bank consisting of three 18.4 MVAR stages of 138 kV voltage and supervisory controlled transmission capacitors. | 2022-02-18 | 2022-06-16 | 2022-06-16 |  | 1617138 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43598 (R468) | Marlin South Sub: Install 27.6 MVAR 69 kV capacitor bank | City of Marlin, Falls County | Install a bank consisting of three 9.2 MVAR stages of 69 kV voltage and supervisory controlled transmission capacitors. | 2022-02-07 | 2022-11-30 |  |  | 1983299 |  |  | 82 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43028 (M4701) | Cyclone Switch : Establish 3 breaker ring bus station | Hopkins County | Install three 345 kV, 3200 A circuit breakers in a ring bus arrangement to establish station. | 2021-12-17 | 2022-10-18 | 2022-10-18 |  | 9495167 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43026 0PT45543 (R6159) | Outlaw Switch: Establish four breaker ring bus station | City of Richland, Navarro County | Establish four breaker ring bus station. | 2021-12-28 | 2022-06-08 | 2022-06-08 |  | 9503939 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43592 (M4122) | Desoto Switch: Line terminal upgrade for one circuit breaker | City of Dallas, Dallas County | Upgrade terminal equipment on one circuit breaker to 2000A, and upgrade the line relaying communications to fiber. | 2022-10-15 | 2022-12-15 |  |  | 326944 |  |  | 94 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42269 (R6160) | Revolution Switch: Rebuild 138 kV station in a 10-breaker 138 kV breaker-and-a-half arrangement | City of Navarro, Navarro County | Rebuild existing Navarro 138 kV station in a 10-breaker 138 kV breaker-and-a-half arrangement. | 2023-10-01 | 2024-04-18 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45741 | Wichita Falls Riverbend Sub : Upgrade both transformers | City of Wichita Falls, Wichita County | Upgrade both transformers | 2022-01-19 | 2022-07-11 | 2022-07-11 |  | 4940165 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44242 0PT44554 (R6144) | Sabana Sub : Establish station with one transformer and two feeder breakers | City of Proctor, Comanche County | Establish station with one transformer and two feeder breakers. | 2022-01-27 | 2022-10-30 |  |  | 4557630 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45378 0PT45956 (R8594) | Old Michigan POD : Establish 138 kV POD | Culberson County | Provide a 138 kV point-of-delivery (POD). | 2022-04-04 | 2022-06-23 | 2022-06-23 |  | 1602497 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45121 | Wall Street Sub : Replace station #2 transformer and replace existing oil low voltage circuit breakers | City of Dallas, Dallas County | Replace station #2 transformer and replace existing oil low voltage circuit breakers. | 2022-01-05 | 2022-06-30 | 2022-06-30 |  | 4968473 |  |  | 100 | 69/138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43030 | Breckenridge Sub : Decommission distribution equipment and install an SSVT | City of Breckenridge, Stephens County | Decommission distribution equipment, and install an SSVT in order to power the control house. | 2022-03-15 | 2022-08-01 | 2022-08-01 |  | 538487 |  |  | 100 | 69/138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42151 0PT42559 (R8600) | Desert Wind Sub : Establish station with one transformer and two 25 kV feeder breakers | City of Dallas, Dallas County | Establish station with one transformer and two 25 kV feeder breakers. | 2022-02-11 | 2022-08-02 | 2022-08-02 |  | 5753245 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42594 | Caddo Mills Hwy 66 Sub - Establish a new 138-25 kV substation with two transformers | City of Caddo Mills, Hunt County | Establish substation with two transformers to replace Caddo Mills Sub. | 2022-04-08 | 2022-12-15 |  |  | 6922256 |  |  | 81 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44260 | Rowlett Sub: Upgrade line equipment | City of Rowlett, Rockwall County | Upgrade line equipment. | 2023-01-04 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44999 (R4021) | Bowman Switch : Relay upgrades for 138 kV bus A, auto #1 and replace tertiary reactors for auto #1 | City of Wichita Falls, Wichita County | Bus and auto relay upgrades for 138 kV bus A and auto #1. | 2022-02-28 | 2022-06-20 | 2022-06-20 |  | 1228217 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45227 (R6160) | Navarro Sub : Reconfigure 138 kV bus & relocate line terminals to Revolution Switch | City of Navarro, Navarro County | Reconfigure 138 kV bus & relocate line terminals to Revolution Switch. | 2023-01-04 | 2023-04-13 | [5 empty] | 0 | 69/138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44254 | Dalrock Sub: Upgrade line equipment | City of Rowlett, Rockwall County | Upgrade line equipment. | 2022-07-29 | 2022-12-15 |  |  | 889654 |  |  | 21 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44337 0PT46862 | Waco Katy Sub: Rebuild station to 138 kV operation | City of Waco, McLennan County | Establish station with one transformer and two feeders | 2023-06-02 | 2023-12-15 |  |  | 2992104 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45025 | Odessa EHV Switch : Relay upgrades for 138 kV and auto# 2 | City of Odessa, Ector County | Upgrade relaying for 138 kV, 345/138 kV and auto # 2 | 2022-03-07 | 2022-07-26 | 2022-07-26 |  | 732642 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46115 | Century Sub : Replace three circuit breakers | City of Arlington, Tarrant County | Replace three circuit breakers | 2022-04-11 | 2022-06-15 | 2022-06-15 |  | 393749 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39491 (M364) | West Plano Sub : Upgrade line terminal to 3200 A | City of Plano, Denton County | Upgrade line terminal to 3200 A | 2022-03-01 | 2022-06-15 | 2022-06-15 |  | 275909 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43824 (R6142) | Creslenn Ranch: Rebuild 69 kV station to a four position ring bus | City of Trinidad, Henderson County | Establish a new 69 kV four position ring bus to replace the existing 69 kV at Trinidad Switch. | 2022-05-20 | 2022-12-15 |  |  | 4354061 |  |  | 89 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44226 | White Settlement West Sub : Install a 138-25 kV transformer #2 with one feeder breaker | City of Fort Worth, Tarrant County | Install 138-25 kV transformer #2 with one feeder breaker | 2022-08-05 | 2022-12-10 |  |  | 2316447 |  |  | 77 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44246 | Temple Northwest Sub : Replace two 138-12.5 kV transformers | City of Temple, Bell County | Replace two 138-12.5 kV transformers | 2022-08-08 | 2022-12-16 |  |  | 5313490 |  |  | 70 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44258 | Temple Southeast Sub : Replace 138-12.5 kV transformer #1 and replace station #1 circuit breakers | City of Temple, Bell County | Replace 138-12.5kV transformer #1 and replace station #1 circuit breakers | 2022-09-02 | 2022-12-01 |  |  | 1663935 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44850 (R51561) | Thomas Price Switch: Establish new station by installing three 345 kV, 5000 A circuit breakers in a 3-breaker ring bus arrangement. | City of Graham, Young County | Establish new station by installing three 345 kV, 5000 A circuit breakers in a 3-breaker ring bus arrangement. | 2022-05-09 | 2022-11-10 |  |  | 7861206 |  |  | 94 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45886 | Judkins Sub : Replace transformers #1 and #2 with two transformers | Ector County | Replace transformers #1 and #2 with two transformers | 2022-01-11 | 2022-10-31 |  |  | 5543166 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46052 0PT46421 (R8602) | High Plains POD: Establish a 138 kV point of delivery (POD) | City of Big Spring, Howard County | Establish a 138 kV point of delivery (POD) | 2022-09-26 | 2022-12-31 |  |  | 897944 |  |  | 58 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44103 (R8580) | Flat Iron Substation | Midland County | Construct the new Flat Iron Substation | 2021-11-15 | 2022-08-10 | 2022-08-10 |  | 10651000 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | CCN Application Withdrawn on 10/21/21. Project is proceeding under 25.101(c)(5)(A) as an exempt project under SB 1281. Initial costs have been removed in accordance with the MCPR entry instructions.
0PT46409 | Parker Switch : Replace two overdutied breakers | City of Weatherford, Parker County | Replace two breakers | 2022-10-21 | 2022-11-30 |  |  | 1171492 |  |  | 10 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46384 | Carrollton Northwest Switch : Replace three overdutied breakers | City of Carrollton, Denton County | Replace three breakers | 2022-09-19 | 2022-12-15 |  |  | 1568439 |  |  | 55 | 138 |  | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46386 | Kirkland Park Switch : Replace two overdutied breakers | City of Dallas, Dallas County | Kirkland Park Switch : Replace two breakers | 2022-10-03 | 2022-11-30 |  |  | 696589 |  |  | 99 | 138 |  | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46004 (R8601) | Wildhorse POD: Establish 138 kV point of delivery | Howard County | Establish a 138 kV point of delivery with three 138 kV motor operated sectionalizing switches. | 2022-03-26 | 2022-05-20 | 2022-05-20 |  | 783746 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46134 (R6187) | Tin Roof POD: Establish 138 kV point of delivery with capacitor bank | Bell County | Establish point of delivery with installation of three stages of 36.8 MVAR 138 kV capacitor banks. | 2022-02-18 | 2022-08-15 | 2022-08-15 |  | 3570723 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46155 (R6189) | Sandow Switch : Install capacitor bank #2 | City of Thorndale, Milam County | Install 110.4 MVAR capacitor bank on the 138 kV East Bus. Capacitor installation to consist of three 36.8 MVAR stages | 2022-01-07 | 2022-05-01 | 2022-05-01 |  | 2222624 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43551 (R6148) | Elgin Switch : Modify relay as a part of connecting Brushy Creek Switch | Williamson County | Modify relay as a part of connecting Brushy Creek Switch | 2022-04-18 | 2022-06-01 | 2022-06-01 |  | 313885 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44295 (M5172) | Weatherford Switch : Upgrade 138 kV line terminal | City of Weatherford, Parker County | Upgrade all line terminal and associated equipment for the 138 kV circuit breaker. | 2022-12-03 | 2022-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45737 0PT46724 (R8604) | Crater Rock Switch : Establish three breaker ring POI station | Culberson County | Establish three breaker ring POI station. | 2022-08-07 | 2022-12-15 |  |  | 6077188 |  |  | 54 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
13T65029 | Lawrence Sub : Establish with one transformer and two 25 kV feeder breakers | Kaufman County | Establish with one transformer and two feeder breakers . | 2022-07-15 | 2022-12-15 |  |  | 4603754 |  |  | 81 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43825 (R6143) | Taylor Sub: Establish 138 kV ring bus and upgrade distribution station | City of Taylor, Williamson County | Establish a new four position 138 kV ring bus to replace the existing 138 kV switching station, including the installation of one 138/69 kV autotransformer. | 2022-06-14 | 2022-12-17 |  |  | 6694493 |  |  | 78 | 138 | 138/69 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45123 0PT43070 | Rosemont Sub : Establish station with a double tap arrangement with two transformers and eight circuit breakers. | City of Fort Worth, Tarrant County | Establish station with a double tap arrangement with two transformers and eight circuit breakers. | 2022-09-05 | 2022-12-31 |  |  | 8568084 |  |  | 44 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46414 | Rosedale Sub : Establish substation with two transformers | City of Fort Worth, Tarrant County | Establish substation with two transformers and six feeder breakers | 2022-11-15 | 2023-05-15 |  |  | 6478207 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46725 (M5222) | Handley Switch : Remove transformers #1 and #2 with the removal of the associated switchgear | City of Fort Worth, Tarrant County | Remove transformers #1 and #2 with the removal of the associated switchgear. | 2023-02-01 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41468 (R6195) | Fort Smith Switch : Establish 345 kV ring bus station for point-of-interconnection (POI). | City of Hillsboro, Hill County | Establish new station by installing three 345 kV, 3200 A circuit breakers in a 3-breaker ring bus arrangement for a point-of interconnection (POI). | 2022-06-28 | 2022-11-10 |  |  | 7159942 |  |  | 98 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40880 0PT47840 (R6184) | Russell Gap Switch : Establish 3-breaker ring bus for POI | City of Star, Mills County | Establish 345 kV 3-breaker ring bus for point-of-interconnection. | 2022-07-18 | 2022-11-17 |  |  | 8089374 |  |  | 70 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40139 (R6183) | Ash Creek Switch : Establish 138 kV station for POI | Hill County | Establish 138 kV station for Point-of-Interconnection (POI), by installing three 138 kV, 3200 A circuit breakers in a 3-breaker ring bus arrangement | 2022-08-23 | 2023-04-20 |  |  | 4320758 |  |  | 13 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46093 | Graford Sub : Rebuild existing substation to rural substation skid | City of Graford, Palo Pinto County | Rebuild existing substation to rural substation skid | 2022-11-29 | 2023-03-31 |  |  | 2989585 |  |  | 0 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42249 (M4346) | Hawk Hollow Switch : Establish 5-breaker ring POI station | City of Paris, Lamar County | Install five 138 kV, 3200 A circuit breakers in a ring bus arrangement and install one 138 kV point-of-interconnection (POI). | 2022-06-22 | 2022-12-15 |  |  | 6613388 |  |  | 93 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46156 (R6116) | Sandow Switch: Install 138 kV air core reactors on auto #1 and auto #2 | City of Rockdale, Milam County | Install 138 kV air core reactors on auto #1 and auto #2 | 2022-08-17 | 2023-01-31 |  |  | 2964529 |  |  | 73 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43690 0PT47058 (M3009) | Crossroads Switch : Establish station for POI | City of Enloe, Delta County | Establish a POI switching station by installing three 138 kV, 3200 A circuit breakers in a ring bus arrangement to provide a single POI. | 2022-06-28 | 2022-11-17 |  |  | 4377683.09 |  |  | 88 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46716 | Moorehead Sub : Install two transformers with two feeder breakers | City of Garland, Dallas County | Install two transformers with two feeder breakers | 2022-05-09 | 2022-12-01 |  |  | 5136068 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44322 (M4320) | Bardwell Lake Switch: Disconnect two 69 kV line terminals & upgrade line terminals | Ellis County | Disconnect two 69 kV line terminals & upgrade line terminals. | 2022-11-10 | 2022-12-15 |  |  | 274037 |  |  | 0 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46771 0PT47830 0PT47832 0PT45669 (R8498) | Consavvy Switch: Establish as a 10-breaker and a half bus arrangement. | Midland County | Establish as a 10-breaker and a half bus arrangement. Install two autotransformers and four MVAR reactors | 2022-04-20 | 2022-12-15 |  |  | 42462890 |  |  | 53 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46998 | Collin Switch : Regasket Auto #2 | City of Frisco, Collin County | Regasket Auto #2 at Collin Switch. | 2022-09-12 | 2022-11-15 |  |  | 264022 |  |  | 70 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47266 | Sherry Switch : Regasket Auto #1 and Replace Barrier Board | City of Arlington, Tarrant County | Regasket Auto #1 & barrier board at Sherry Switch. | 2022-09-16 | 2022-12-30 |  |  | 306147 |  |  | 60 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42929 | Compton Street Sub : Replace transformers #1 & #2 | City of Dallas, Dallas County | Rebuild substation with two transformers and eight feeder breakers and remove existing switchgear station. | 2022-06-06 | 2022-12-21 |  |  | 6133672 |  |  | 63 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43226 0PT44828 (R4015) | Tower One Sub: Establish substation | City of Bowie, Montague County | Establish substation using two 69 kV, 2000 A circuit breakers and three sectionalizing switches. | 2022-07-15 | 2023-03-01 |  |  | 4880808 |  |  | 36 | na | 69 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43646 (M4292) | Royse Switch: Upgrade one circuit breaker line terminal upgrade | City of Royse City, Rockwall County | Upgrade one circuit breaker line terminal | 2022-09-23 | 2022-12-15 |  |  | 700683 |  |  | 97 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44233 | Bangs Sub : Rebuild station by installing transformer #2 and two feeder breakers and decommission transformer #1 | City of Bangs, Brown County | Rebuild station by installing transformer #2 and two feeder breakers and decommission transformer #1 | 2022-07-21 | 2022-12-05 |  |  | 3676844 |  |  | 44 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44267 (R6140) | Rockdale Sub : Install transformer #2 with two feeders | City of Rockdale, Milam County | Install a second transformer with two feeders and add FID to the existing substation. | 2022-07-27 | 2022-12-15 |  |  | 2743160 |  |  | 97 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45445 (M4702) | Saltillo Switch : Establish a 3-breaker ring bus for POI station | City of Saltillo, Hopkins County | Establish a 3-breaker ring bus for POI station | 2022-05-12 | 2022-11-17 |  |  | 6954657 |  |  | 96 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46419 | Centralia Sub : Install transformer #4 with two feeder breakers | Upton County | Install transformer #4 with two feeder breakers | 2022-09-20 | 2022-12-01 |  |  | 2780019 |  |  | 97 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46638 | Mount Enterprise Switch : Replace two 345 kV circuit breakers | City of Henderson, Rusk County | Replace two 345 kV circuit breakers | 2022-10-18 | 2022-12-31 |  |  | 1135637 |  |  | 71 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46640 | East Levee Switch : Replace one 138 kV circuit breaker | City of Dallas, Dallas County | Replace one 138 kV circuit breaker | 2022-10-05 | 2022-12-31 |  |  | 449976 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46729 | Hemphill Sub : Replace one 138 kV circuit breaker | City of Fort Worth, Tarrant County | Replace one 138 kV circuit breaker | 2022-10-18 | 2022-12-31 |  |  | 383934 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45361 (R6185) | Long Prairie Switch : Establish 3-breaker ring bus for POI station | Navarro County | Establish 3-breaker ring bus for POI station | 2022-05-03 | 2022-11-17 |  |  | 5376538 |  |  | 83 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44313 0PT44748 (R4022) | Short Grass Sub: Establish new substation | City of Archer, Archer County | Establish a new substation to replace the existing Archer City Sub. | 2022-08-01 | 2022-12-15 |  |  | 3647282 |  |  | 63 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43089 0PT44822 (R4015) | Hopewell Switch: Establish 4-breaker 69 kV ring bus station | City of Bowie, Montague County | Establish with a 4-breaker ring bus using 69 kV, 2000A breakers. | 2022-06-06 | 2022-12-15 |  |  | 5142682 |  |  | 84 | na | 69 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46333 0PT47029 (M3010) | Rose Hill Switch : Rebuild Rose Hill Sub Tap to 3-breaker ring | City of Kaufman, Kaufman County | Rebuild the existing 138 kV Rose Hill Tap into a three position 138 kV ring bus configuration. | 2022-07-05 | 2022-11-23 |  |  | 4855264 |  |  | 90 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46413 | Mountain Branch Sub : Establish new sub with one transformer and three 12.5 kV feeders | Eastland County | Establish new sub with one transformer and three 12.5 kV feeders. | 2022-06-06 | 2023-05-15 |  |  | 5755341 |  |  | 46 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46508 | Dollarhide Sub : Upgrade relaying on capacitor bank #1 | City of Kermit, Winkler County | Upgrade relaying on capacitor bank #1. | 2022-09-26 | 2022-12-31 |  |  | 683101 |  |  | 80 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46587 | Mustang Sub : Install one transformer with two feeder breakers on bank #2 | City of Andrews, Andrews County | Install one transformer with two feeder breakers on bank #2. | 2022-06-26 | 2022-12-01 |  |  | 4065847 |  |  | 48 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44257 | Cleburne West Sub : Install bank #2 with one transformer and two feeder breakers | City of Cleburne, Johnson County | Install bank #2 with one transformer and two feeder breakers. | 2022-08-08 | 2022-12-17 |  |  | 2080917 |  |  | 88 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46207 | Copperas Cove East Switch : Install bank #2 with a one transformer | City of Copperas Cove, Coryell County | Install bank #2 with a one transformer. | 2022-07-29 | 2022-12-15 |  |  | 2883866 |  |  | 83 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44343 (M4071) | Cedar Crest Sub : Convert substation to 138 kV operation and rebuild 13.8 kV substation | City of Dallas, Dallas County | Convert the 69 kV substation to 138 kV operation by installing a new loop in - loop out configuration and removing the 69 kV equipment. | 2022-07-15 | 2023-05-15 |  |  | 5122938 |  |  | 29 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46619 | Tule Canyon Switch : Install three 345 kV SSVTs | City of Silverton, Briscoe County | Install three 345 kV SSVTs that were removed from Abernathy Switch. | 2022-09-13 | 2022-12-15 |  |  | 288581.63 |  |  | 99 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46875 0PT47739 (R8611) | Yantis Ranch POD : Establish 138 kV point of delivery | City of Wink, Winkler County | Establish 138 kV point of delivery. | 2022-11-07 | 2022-12-15 |  |  | 1911568 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44304 (R6141) | Peppervine Switch: 138 kV Station Rebuild | City of Waco, McLennan County | Rebuild the 138 kV Switch with ten 3200 A or greater, 138 kV circuit breakers in a breaker-and-a-half arrangement. | 2022-08-12 | 2023-05-15 |  |  | 11566138 |  |  | 10 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47344 (M4330) | Haggerty Switch : Establish breaker-and-a-half station | City of Sherman, Grayson County | Establish breaker-and-a-half station. | 2022-07-26 | 2023-05-15 |  |  | 17642817 |  |  | 6 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44232 0PT44749 0PT47519 | Apple Sub (formerly Pleasant Farms Sub) : Establish station with one 47 MVA, 138/69 kV and two feeder breakers | City of Odessa, Ector County | Establish station with one transformer and two feeder breakers. | 2022-07-11 | 2022-12-01 |  |  | 5171021.24 |  |  | 89 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46695 0PT47758 0PT47760 (R6215) | Mallard Switch : Establish breaker-and-a-half station | City of Hutto, Williamson County | Establish Breaker-and-a-half Station for SAS. | 2022-08-19 | 2023-05-01 |  |  | 16173527.7 |  |  | 12 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47343 0PT47759 (R6216) | Pintail Switch : Establish Breaker-and-a-half Station for SAS | City of Hutto, Williamson County | Establish breaker-and-a-half station. | 2022-09-09 | 2023-05-01 |  |  | 13890108 |  |  | 3 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46874 (R8609) | Meyers Draw POD : Establish 138 kV point of delivery | City of Odessa, Midland County | Establish 138 kV point of delivery | 2022-12-12 | 2023-01-27 |  |  | 1120615 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44416 (M5216) | Hurst Sub: 138 kV line terminal upgrade | City of Hurst, Tarrant County | Upgrade all line terminal and associated equipment to meet or exceed 2000 A. | 2022-11-07 | 2022-12-15 |  |  | 486819 |  |  | 14 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44414 (M5216) | Euless South Sub: 138 kV line terminal upgrade | City of Euless, Tarrant County | Upgrade all line terminal and associated equipment to meet or exceed 2000 A. | 2022-10-07 | 2022-12-15 |  |  | 485178 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45131 | Grand Prairie Sub : Rebuild substation | City of Grand Prairie, Dallas County | Rebuild substation with eight distribution feeders, new transformers and modify 138 kV bus work to configure a loop in loop out arrangement. | 2022-09-19 | 2023-05-08 |  |  | 7673504 |  |  | 2 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44229 | Trinity Sub : Install second transformer with two feeder breakers | City of Fort Worth, Tarrant County | Install second transformer with two feeder breakers | 2022-10-12 | 2022-12-26 |  |  | 2978368 |  |  | 30 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43163 (R4015) | Smith Creek (Formerly Bellevue Sub): Rebuild 69 kV station with a rural design | City of Bellevue, Clay County | Rebuild 69 kV station with a rural design | 2022-08-08 | 2022-12-15 |  |  | 2200977 |  |  | 43 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42928 0PT44208 | Antler Hollow Sub : Establish with two transformers and three feeder breakers | City of Stephenville, Erath County | Establish with two transformers and three feeder breakers | 2022-08-29 | 2022-12-16 |  |  | 7687918 |  |  | 28 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46970 | Taylor West Sub : Install bank #4 with one transformer and two feeder breakers | City of Hutto, Williamson County | Install bank #4 with one transformer and two feeder breakers | 2022-08-18 | 2022-12-22 |  |  | 3023259 |  |  | 63 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46844 (R8610) | Schumm POD : Establish 138 kV point of delivery | City of Monahans, Crane County | Establish 138 kV point of delivery | 2022-11-14 | 2022-12-01 |  |  | 1091580 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46726 | Salt Lake Substation : Install bank #2 with one transformer and two feeder breakers | City of Midland, Midland County | Install bank #2 with one transformer and two feeder breakers and decommission transformer #1. | 2022-09-01 | 2022-12-01 |  |  | 2876816 |  |  | 98 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45394 | Midlothian South Sub : Replace transformers #1 and #2 | City of Midlothian, Ellis County | Replace transformers #1 and #2 and relay upgrades on two feeder breakers | 2022-09-11 | 2022-12-01 |  |  | 7048748 |  |  | 40 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44870 (R8581) | Wink Switch : Convert line terminal with 138 kV circuit breakers | City of Wink, Winkler County | Convert line terminal with 138 kV circuit breakers | 2022-11-07 | 2022-12-29 |  |  | 1335615 |  |  | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44341 (M4064) | Buntin Drive Sub : Convert station to 138 kV operation | City of Dallas, Dallas County | Convert station to 138 kV operation by replacing transformer and install eight feeder switchgears. | 2022-09-13 | 2023-04-04 |  |  | 7608844 |  |  | 2 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46628 0PT47096 (R985) | Caddo Mills Explorer Tap : Rebuild tap to support line conversion upgrade | City of Caddo Mills, Hunt County | Rebuild tap to support line conversion upgrade and utilize motor operated switches. | 2022-11-01 | 2022-12-15 |  |  | 878313 |  |  | 2 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46873 0PT47636 | Hardy Morgan POI : Establish 138 kV point of interconnection | City of Ackerly, Dawson County | Establish 138 kV point of interconnection | 2023-01-09 | 2023-03-31 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47523 | Jewett Switch : Replace leaking HoXo bushing on auto #3 | City of Jewett, Leon County | Replace bushing on autotransformer at Jewett Switch | 2022-09-19 | 2022-12-28 |  |  | 333128 |  |  | 95 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47533 0PT48287 (R8612) | Dry Wind Tap : Establish new tap to Sandhills Substation | City of Monahans, Crane County | Establish new tap to Sandhills Substation. | 2022-11-07 | 2022-12-30 |  |  | 867633 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47567 (R4028) | Baylor Switch : Add motor operator and transclosure for line switch | City of Seymour, Baylor County | Add a motor operator and transclosure to facilitate line upgrades. | 2022-07-12 | 2022-11-15 |  |  | 521974 |  |  | 38 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41807 0PT48762 (R8619) | Meteor Switch: Establish 345 kV ring bus station for point of interconnection (POI). | City of Odessa, Ector County | Establish a 3-breaker, 345 kV, 5000 A ring bus station for point of interconnection (POI). | 2023-01-02 | 2023-05-18 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45683 (M5324) | Bird Dog Switch: Establish a 345 kV for point of interconnection (POI) | City of Denton, Denton County | Establish a 345 kV, 3-breaker ring bus switchyard for point of interconnection (POI). | 2023-01-16 | 2023-05-18 |  |  | 7865658 |  |  | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46327 (R6190) | Pepper Creek Switch : Establish for point of delivery POD | City of Temple, Bell County | Establish with thirteen 138 kV circuit breakers to provide three point of delivery's to adjacent customer station. | 2023-11-01 | 2023-11-03 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46153 (R8027) | Ozark Trail Switch : Establish 3-breaker ring bus station for point of interconnection (POI) | City of Tulia, Swisher County | Establish 3-breaker ring bus station for point of interconnection (POI) | 2023-10-23 | 2024-04-18 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41699 (R1752) | Marlin Switch : Rebuild station by installing three 2000 A or greater 69 kV circuit breakers | City of Marlin, Falls County | Rebuild station by installing three 2000 A or greater 69 kV circuit breakers. | 2023-01-03 | 2023-12-15 | [5 empty] | 0 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46641 | Allen Switch : Replace two 138 kV circuit breakers | City of Plano, Collin County | Replace two 138 kV circuit breakers | 2022-11-01 | 2022-12-31 |  |  | 567961 |  |  | 68 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46892 0PT47001 | Sandhills Sub : Replace transformer #1 and two feeder breakers | Crane County | Replace bank #1 and two feeder breakers. | 2022-07-16 | 2022-12-28 |  |  | 5919552.54 |  |  | 47 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47736 | Sandhills Sub : Install transformer #3 with one feeder breaker | Crane County | Install transformer #3 with one feeder breaker | 2022-08-15 | 2023-04-01 |  |  | 3892590 |  |  | 37 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46507 | Twin Oaks Switch: Upgrade relaying on 345 kV North and South bus | Robertson County | Upgrade 345 kV North and South bus protection to provide redundancy for three phase faults. | 2022-09-22 | 2023-05-15 |  |  | 538402 |  |  | 99 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46639 | Century Switch : Replace one 345 kV circuit breaker | City of Arlington, Tarrant County | Replace one 345 kV circuit breaker | 2022-10-25 | 2022-12-31 |  |  | 559878 |  |  | 16 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46883 | Deen Switch : Install security measures | City of Fort Worth, Tarrant County | Install security measures | 2022-08-01 | 2022-12-16 |  |  | 1444434.84 |  |  | 99 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47494 0PT49132 (R8622) | Ashby POD : Establish a 138 kV point of delivery (POD). | City of Wink, Winkler County | Establish a 138 kV for point of delivery (POD). | 2022-11-14 | 2023-02-01 |  |  | 2075348 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41706 (R8607) | Red Sand POD : Establish 138 kV point of delivery (POD) | City of Stanton, Martin County | Establish 138 kV point of delivery (POD). | 2022-10-21 | 2022-12-05 |  |  | 1133424 |  |  | 9 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44139 (M5323) | Pacific Switch : Establish 3-breaker ring bus for POI | City of Brookston, Lamar County | Establish 345 kV, 3 breaker ring bus for point of interconnection. | 2023-01-09 | 2023-05-18 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46606 (R8621) | Delaware River Switch : Establish 3-breaker ring bus for point of interconnection (POI) | Culberson County | Establish 138 kV, 3-breaker ring bus for point of interconnection (POI). | 2023-01-02 | 2023-05-18 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46971 | Parker Maxwell Creek Sub : Install transformer #2 with two feeder breakers | City of Parker, Collin County | Install transformer #2 with two feeder breakers | 2022-08-19 | 2022-12-01 |  |  | 2618162 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48057 | Burnett Switch : Oil Containment | City of Wichita Falls, Wichita County | Install station oil containment | 2022-11-21 | 2022-12-15 |  |  | 481070 |  |  | 0 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44324 (M4320) | Italy Sub: 69 kV line terminal upgrade | City of Italy, Ellis County | 69 kV line terminal upgrade. | 2022-10-11 | 2022-12-15 |  |  | 1296090 |  |  | 87 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44273 | Terrell Switch: Establish 138 kV terminal and retire 69 kV station | City of Terrell, Kaufman County | Establish 138 kV line terminal and retire 69 kV station | 2023-01-02 | 2023-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47406 | Temple Pecan Creek Switch : Replace MDAR relay panels for four circuit breakers | City of Temple, Bell County | Replace MDAR relay panels for four circuit breakers | 2022-10-10 | 2022-12-31 |  |  | 599952 |  |  | 50 | 138 | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47010 | Rocky Creek Switch : Install HV Breaker and Transformer monitors and associated communications equipment | City of Crowley, Tarrant County | Install HV Breaker and Transformer monitors and associated communications equipment at Rocky Creek Switch. | 2022-09-24 | 2022-12-15 |  |  | 600000 |  |  | 85 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46988 (R8616) | Buchanan Ranch Sub : Add two transformers with four feeder breakers and replace existing transformer | City of Midland, Midland County | Add two transformers with four feeder breakers and replace existing transformer | 2023-02-01 | 2023-10-06 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45165 (M3015) | Krum West Switch : Establish a 345 kV point of interconnection (POI) | City of Krum, Denton County | Modify to provide one 345 kV point of interconnection. | 2023-01-02 | 2023-05-11 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46491 | Wilmer Switch : Upgrade relaying on auto #1 |  | Upgrade auto #1 panels and add 3V0 equipment | 2022-11-07 | 2022-12-31 |  |  | 370478 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47709 (M5326) | Lavender Switch : Establish a new 138 kV, 4 breaker ring bus station for point of interconnection (POI). | City of Wilmer, Dallas County | Establish the 138 kV switch in a 4-breaker-ring bus arrangement by installing four 138 kV, 3200 A circuit breakers to provide two 138 kV points of delivery (PODs). | 2022-12-01 | 2023-05-15 |  |  | 6480932 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47987 | Roanoke Sub: Install transformer #4 and two feeder breakers | City of Roanoke, Denton County | Install transformer #4 and two feeder breakers | 2022-10-20 | 2023-04-01 |  |  | 3253326 |  |  | 1 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46894 0PT47833 0PT47813 0PT46566 (R8593) | Expanse Switch: Establish 345/138 kV station | City of Stanton, Martin County | Establish as a 6-breaker, 138 kV breaker-and-a-half bus arrangement with 3200 A terminals, and a 3-breaker 345 kV single breaker arrangement. Install two autotransformers and four MVAR reactors. | 2022-10-07 | 2023-05-15 |  |  | 31195698 |  |  | 9 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46199 | Stephen F. Austin Sub : Relocate substation demarcation | City of Nacogdoches, Nacogdoches County | Relocate substation demarcation | 2022-12-05 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48180 (M5329 ) | Elizabethtown : Establish 138 kV point of interconnection (POI). | City of Roanoke, Denton County | Establish 138 kV point of interconnection (POI). | 2022-12-07 | 2023-03-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46620 | DFW Northwest Sub : Reconfigure 138 kV lines and bus configuration. | City of Grapevine, Tarrant County | Add two138 kV breakers to the tie bus connecting these lines. | 2022-10-27 | 2023-05-15 |  |  | 3284670 |  |  | 24 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46909 (R8614) | Rock Lake POD: Establish 138 kV point of delivery | City of Stanton, Martin County | Establish a 138 kV for point of interconnection (POI) | 2023-01-30 | 2023-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48459 | China Grove Switch : Replace two 69 kV circuit breakers | City of Colorado City, Mitchell County | Replace two 69 kV circuit breakers | 2023-02-13 | 2023-04-15 | [5 empty] | 0 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44245 0PT44780 | Horseman Sub (formerly Saginaw SE Sub) : Establish 138 kV station with two transformers and four breakers | City of Fort Worth, Tarrant County | Establish 138 kV station with two transformers and four breakers | 2022-11-14 | 2023-05-01 |  |  | 9046995 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45387 (R6208) | Bell County East Switch : Establish a 345 kV POI for point of interconnection | City of Temple, Bell County | Establish a 345 kV point of interconnection (POI) | 2022-10-13 | 2023-05-11 |  |  | 5206702 |  |  | 10 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46340 (R6219) | Rookie Switch : Establish 138 kV station for point of interconnection | City of Thorndale, Milam County | Establish new station by installing three 138 kV, 3200 A circuit breakers in a 3-breaker ring bus arrangement. | 2023-06-01 | 2023-11-16 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46171 (R6207)) | Riesel Switch : Establish 138 kV point of interconnection | City of Riesel, Falls County | Establish new station by installing three 138 kV, 3200 A circuit breakers in a 3-breaker ring bus arrangement. | 2022-11-04 | 2023-04-13 |  |  | 4998964 |  |  | 1 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45041 (R6210) | Hog Creek Switch: Establish 345 kV point of interconnection | City of Cameron, Milam County | Establish a 345 kV point of interconnection (POI) | 2022-11-14 | 2023-05-11 |  |  | 8486799 |  |  | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47360 | Coyote Sub: Install station #2 | City of Big Spring, Howard County | Install station #2 in a loop-in, loop-out arrangement with one transformer and two feeder breakers. | 2023-01-16 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45040 (R6217) | Brangus Switch: Establish 345 kV point of interconnection | Bell County | Establish a 345 kV point of interconnection (POI) | 2023-01-09 | 2023-05-18 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45039 (R6218) | Gibson Switch: Establish 345 kV point of interconnection | Milam County | Establish a 345 kV point of interconnection (POI) | 2023-04-01 | 2023-05-18 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45035 (R6188) | Little Pond Switch: Establish 345 kV point of interconnection | Milam County | Establish a 345 kV point of interconnection (POI) | 2023-04-24 | 2023-05-15 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46828 (R8606) | Grey Well Draw Switch: Rebuild 3-breaker ring bus | City of Midland, Midland County | Establish 138 kV three breaker ring bus station. | 2023-11-02 | 2023-05-15 |  |  | 6108950 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45535 0PT48288 (R6213) | Belfalls Switch - Establish a 345 kV point of interconnection | City of Troy, Bell County | Establish a 345 kV, 3-breaker ring bus switchyard for point of interconnection (POI). | 2022-12-12 | 2023-05-11 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48011 (M4352) | Greenville Ave Sub : Rebuild station to install new 138 kV bus and two transformers #3 & #4 | City of Dallas, Dallas County | Rebuild station to install new 138 kV bus and two transformers #3 & #4. | 2023-01-15 | 2023-12-01 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47692 | Collin Switch 345: replace Failed HOXO Bushing on Auto #2 | City of Frisco, Collin County | Bushing replacement on Auto #2 at Collin Switch. | 2022-09-16 | 2022-11-01 |  |  | 205814 |  |  | 70 | 345 | na | na | na | na | na | na | na | na | 25.83(d)
0PT45006 | Odessa EHV: Replace Oil Pumps and Regasket | City of Odessa, Ector County | Replacement of oil pumps and regasket at Odessa EHV. | 2021-08-01 | 2022-06-03 | 2022-06-03 |  | 502189 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(d)
0PT43530 | Eiland Switch : Relay protection upgrade | City of Big Spring, Howard County | Relay protection upgrade | 2022-10-31 | 2022-12-31 |  |  | 336780 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46509 | Elm Mott Switch : Upgrade relaying for capacitor bank #1 | City of Elm Mott, McLennan County | Upgrade relaying for capacitor bank #1 | 2022-12-23 | 2022-12-31 |  |  | 341627 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47310 | Rhome Sub: Replace 138 kV transformer | City of Rhome, Wise County | Replace 138 kV transformer and 138 kV motor operated switches | 2023-01-25 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46242 | Dry Fork Sub : Establish substation with two transformers and three feeder breakers | City of Wichita Falls, Wichita County | Establish substation with two transformers and three feeder breakers | 2023-03-27 | 2023-07-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46981 0PT47071 | Navigation Sub : Establish substation with one transformer and two feeder breakers | City of Big Spring, Howard County | Establish substation with one transformer and two feeder breakers | 2022-09-26 | 2023-03-31 |  |  | 5480525 |  |  | 10 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48479 | Aroya Switch : Replace six overdutied breakers | City of Monahans, Ward County | Replace six overdutied breakers. | 2023-01-02 | 2023-05-31 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48351 (R8625) | Stephenson Lake POD : Establish 138 kV point of delivery (POD) | City of Midland, Midland County | Establish 138 kV point of delivery (POD). | 2023-03-20 | 2023-05-12 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48090 (R8621) | Chimney Well POD : Remove equipment for replacement by new Delaware River Switch point of Delivery (POD) | Culberson County | Remove existing line connections and associated equipment for point of delivery (POD). | 2023-01-09 | 2023-05-18 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47886 (M4335) | Pebble Creek Switch : Install two 138 kV line terminals for point of delivery (POD) | City of Red Oak, Ellis County | Provide two 138 kV point of delivery (POD) line terminals by installing four 138 kV circuit breakers. | 2023-01-09 | 2023-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47579 0PT47812 0PT47816 (M4327) | Loop Nine Switch : Establish two 345 kV autos. | City of Red Oak, Ellis County | Establish switch with a 345 kV six breaker ring bus with two autotransformers, and six 138 kV breakers in a breaker-and-a-half configuration. | 2023-02-10 | 2023-12-15 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47295 | Beals Creek Sub: Install transformer #3 and three feeder breakers | City of Big Spring, Howard County | Install transformer and three feeder breakers. | 2022-11-12 | 2023-05-15 |  |  | 2988118 |  |  | 2 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46402 0PT45497 (R6136) | Ranchland Switch: Establish 138 kV ring bus | City of Fairfield, Freestone County | Establish 138 kV ring bus with three feeder breakers. | 2022-11-14 | 2023-05-15 |  |  | 5835865 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47363 0PT47880 0PT46957 | Plano Sub: Rebuild station | City of Plano, Collin County | Rebuild transformers and eight new switchgear type feeder breakers. | 2023-08-15 | 2023-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46403 (R6136) | Fairfield West Sub: Reconfigure high side | City of Fairfield, Freestone County | Reconfigure the high side of the substation. | 2022-12-05 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48257 | Seagoville Switch : Replace gasket & bladder on 345 kV Auto #2 | City of Seagoville, Dallas County | Replace gasket & bladder on 345 kV Auto #2 at Seagoville Switch. | 2022-10-10 | 2022-12-30 |  |  | 356336 |  |  | 40 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48835 | Graham Plant SES Switch : Regasket Auto #1 | City of Graham, Young County | Regasket Auto #1 at Graham Plant SES Switch. | 2022-10-03 | 2022-12-15 |  |  | 391436 |  |  | 15 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47761 (M4327) | Pebble Creek Switch: Install breakers on rung to establish line terminals | City of Red Oak, Ellis County | Install two 138 kV breakers on rungs 5 and 6 to establish the line terminals | 2023-01-01 | 2023-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47526 | Oran Sub : Rebuild existing substation with rural substation skid | City of Graford, Palo Pinto County | Rebuild existing substation with rural substation skid | 2023-02-01 | 2023-05-31 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46328 (M4205) | Carrollton Northwest Switch : Terminate Carrollton East and Northlake Switch | City of Carrollton, Dallas County | Terminate existing Carrollton East Switch | 2023-01-16 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46493 | Anna Switch: Upgrade relaying on auto #2 | City of Anna, Collin County | Upgrade 345 kV auto #2 protection to provide redundancy for three phase faults. Install one 345 kV circuit breaker on auto #2 | 2023-01-02 | 2023-05-15 | [5 empty] | 0 | 138 | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47618 (M4701) | Cedar Hill Switch : Replace 138 kV overdutied breaker | City of Cedar Hill, Dallas County | Replace overdutied 345 kV circuit breakers as part of providing one 345 kV point of interconnection (POI) | 2023-01-01 | 2023-04-13 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46857 (M4094) | Liggett Switch: Upgrade 138 kV circuit breaker | City of Irving, Dallas County | Upgrade circuit breakers to meet or exceed 3200 A. | 2023-02-13 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46514 | Temple Switch : Upgrade relaying on capacitor bank #1 | City of Temple, Bell County | Upgrade relaying on capacitor bank #1 | 2023-01-01 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46510 | Garland Bobtown Road Sub : Upgrade relaying on capacitor bank #1 | City of Garland, Dallas County | Upgrade relaying on capacitor bank #1 | 2023-03-27 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46092 0PT47752 (R4021) | Bowman Switch : Replace existing autotransformer #1 | City of Wichita Falls, Wichita County | Replace existing auto on transformer #1 | 2023-10-23 | 2023-12-01 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47086 (M3011) | Southlake Sub: Install 138 kV capacitor bank | City of Southlake, Tarrant County | Install capacitors on the 138 kV bus. | 2022-11-21 | 2023-05-15 |  |  | 4439746 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47154 (M5101) | Sherry Switch: Upgrade circuit breakers to 3200 A | City of Arlington, Tarrant County | Upgrade circuit breakers to 3200 A | 2023-04-03 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47702 (M4330) | Sherman TI Sub : Yard Expansion | City of Sherman, Grayson County | Expand station for new lines from Haggerty Switch and remove slip bus. | 2022-12-01 | 2023-05-05 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47044 | Graham Plant Switch : Replace two circuit breakers | City of Graham, Young County | Replace two circuit breakers | 2023-01-09 | 2023-05-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47142 (R6191) | Lorena Sub: Rebuild to 138 kV substation with one transformer | City of Lorena, McLennan County | Rebuild station and convert to 138 kV operation with one transformer. | 2023-01-01 | 2023-12-01 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47745 (R8618) | Buffalo Sub: Upgrade 138 kV circuit breaker | City of Stanton, Martin County | Upgrade 138 kV circuit breaker. Modify 138 kV bus protection to provide redundancy. | 2023-02-13 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47525 | South Bend Sub : Rebuild station with Delta-Star skid mount | City of Graham, Young County | Rebuild existing substation utilizing a skid mounted substation. | 2023-02-01 | 2023-09-29 | [5 empty] | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44227 0PT48227 0PT48161 | DFW Mid Cities Sub : Establish station with two transformers and four feeder breakers | City of Euless, Tarrant County | Establish station with two transformers and four feeder breakers | 2023-04-03 | 2023-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43100 R4015) | Fisher Road Switch: Add new 138 kV terminal | City of Wichita Falls, Wichita County | Add new 138 kV terminal with 2000 A terminal rating | 2023-01-10 | 2023-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47225 (M4331) | Newton Branch Sub: Establish station with one transformer and two feeder breakers | City of Midlothian, Ellis County | Establish station with one transformer and two feeder breakers | 2023-01-18 | 2023-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49440 (R6187) | Tin Roof POD: Install 2nd Capacitor Bank for POD | Bell County | Install second 110 MVAR capacitor bank for POD. | 2023-03-06 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48480 | Carrollton Northwest Switch : Replace overdutied breakers | City of Carrollton, Dallas County | Replace four overdutied breakers | 2023-02-06 | 2023-05-31 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48077 | Salt Lake Sub : Install transformer #3 47 MVA 138/25 kV | City of Midland, Midland County | Install transformer #3 47 MVA 138/25 kV and one feeder breaker | 2023-02-01 | 2023-06-16 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47325 | Millers Ferry Road Sub : Install transformer #2 with one transformer and two feeder breakers | City of Forney, Kaufman County | Install transformer #2 with one transformer and two 12.5 kV feeder breakers | 2023-01-02 | 2023-03-31 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47205 (M4137) | Mesquite North Sub : Upgrade Terminal to 3200A | City of Mesquite, Dallas County | Upgrade the line terminals to 3200 A at Mesquite North Sub. | 2023-02-01 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47199 (M4137) | Thornton East Sub : Add Line Switches and FID | City of Dallas, Dallas County | Add line switches and FID | 2023-02-01 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47126 (M5519) | Weatherford West Switch : Upgrade CB#4375 Terminal to 3200A | City of Weatherford, Parker County | Upgrade circuit breaker terminal to 3200A | 2023-02-01 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46769 (M4127) | Centerville Road Sub: Upgrade 138 kV line switches | City of Dallas, Dallas County | Upgrade 138 kV line switches to meet or exceed 2000 A | 2023-04-10 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46296 (R8564) | Skywest : Upgrade 138 kV driver line terminal to be rated at 3200 A | City of Midland, Midland County | Remove wave trap and upgrade line communication to fiber. | 2023-03-15 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46295 (R8564) | Driver : Upgrade 138 kV Skywest line terminal to meet or exceed 3200 A | Midland County | Remove wave trap and upgrade line communication to fiber. | 2023-02-01 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46003 (R8595) | Lamesa Switch : Rebuild/convert existing substation to 138 kV with two transformers | City of Lamesa, Dawson County | Disconnect the existing substation and rebuild to operate at 138 kV. | 2023-01-02 | 2023-06-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46511 | Centerville Switch : Upgrade relaying on capacitor bank #1 | City of Garland, Dallas County | Upgrade relaying on capacitor bank #1 | 2023-06-30 | 2023-12-31 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47350 0PT47102 (R8649) | Vincent Sub : Establish substation with one transformer | City of Big Spring, Howard County | Establish station with one transformer and two feeder breakers | 2023-01-02 | 2023-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47322 | Ennis Southeast Sub : Install transformer #2 with two feeders | City of Ennis, Ennis County | Install transformer #2 with with two feeder breakers. | 2023-01-02 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44231 0PT47655 0PT48829 (R6224) | Double Creek Sub : Establish substation with two transformers and four feeder breakers | City of Round Rock, Williamson County | Establish substation with two transformers and four feeder breakers | 2023-01-13 | 2023-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46861 (R4025) | Wichita Falls PPG Sub: Upgrade 138 kV line terminals and equipment | City of Wichita Falls, Wichita County | Upgrade 138 kV line terminals and equipment | 2023-03-01 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44259 0PT44210 (M5310) | Padera Sub : Establish substaion with two transformers and four feeder breakers | City of Midlothian, Ellis County | Establish substation two transformers and four feeder breakers | 2022-12-01 | 2023-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46879 (R8304) | Adobe Meadows Sub: 138 kV line terminal upgrade | City of Midland, Midland County | Replace three 138 kV air switches and three 138 kV lightning arresters on transformer #2 | 2023-01-27 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47201 (M4137) | Sunnyvale Sub : Upgrade terminals to 3200A | City of Sunnyvale, Dallas County | The upgrade will replace all 138 kV switches, bus, and terminal equipment to meet 3200A. | 2023-02-01 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47124 (R8659) | Sloan Switch : Establish 138 kV 3-breaker ring-bus point of interconnection (POI) for station | City of Midland, Midland County | Establish 138 kV 3-breaker ring-bus point of interconnection (POI) for station | 2023-02-10 | 2023-11-16 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47828 (R8624) | Moser Canyon POD: Establish 138 kV point of delivery (POD) for station | City of Colorado City, Mitchell County | Establish 138 kV point of delivery (POD) for station | 2023-02-20 | 2023-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47532 0PT48955 (R8612) | Sandhills Tap : Upgrade existing terminal equipment | City of Monahans, Ector County | Upgrade all line terminal and associated equipment to meet or exceed 3200 A. | 2023-02-20 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47207 (M4137) | Mesquite East Switch : Upgrade one circuit breaker terminal to 3200A and add two new terminals | City of Mesquite, Dallas County | Upgrade one circuit breaker terminal to 3200A and add two new terminals | 2023-02-20 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44255 (M5283) | Wilshire Sub : Establish substation with one transformer and two feeder breakers | Johnson County | Establish substation with one transformer and two feeder breakers | 2023-02-01 | 2023-12-01 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48441 (R8606) | Cottonfield Sub: 138 kV line terminal upgrade | City of Midland, Midland County | Replace three 138 kV air switches and associated bus work for 3200 A capability | 2023-03-01 | 2023-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48938 (R8660) | Captain Jack POD : Establish 138 kV point of delivery (POD) | City of Wink, Winkler County | Establish 138 kV point of delivery (POD) | 2023-03-15 | 2023-05-31 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49046 (R8669) | White Dune POD : Establish 138 kV point of delivery (POD) | City of Wink, Winkler County | Establish 138 kV point of delivery (POD) | 2023-03-15 | 2023-05-31 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48618 | Blue Mound Sub : Install SODG on one feeder breaker | City of Fort Worth, Tarrant County | Install a distribution and transmission transfer trip protection scheme. | 2023-01-09 | 2023-03-14 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48483 | Moss Switch : Replace two overdutied breakers | Ector County | Replace two overdutied breakers | 2023-01-15 | 2023-05-31 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48482 | Kirkland Park Switch : Replace four overdutied breakers | City of Dallas, Dallas County | Replace four overdutied breakers | 2023-01-15 | 2023-05-31 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48481 | Hutto Switch : Replace three overdutied breakers | City of Hutto, Williamson County | Replace three overdutied breakers | 2023-01-16 | 2023-05-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48124 (R6141) | Waco West Switch: Remove 138 kV yard and reconfigure auto connection | City of Waco, McLennon County | Remove all equipment in the 138 kV yard and reconfigure autotransformer #2 | 2023-02-01 | 2023-05-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46683 (R6172) | McGregor Phillips Sub: Rebuild 138 kV station | City of McGregor, McLennan County | Remove the existing autotransformer equipment and structures. Establish a new 138 kV distribution station with two transformers. | 2023-02-17 | 2023-06-15 | [6 empty] | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44568 (R6183) | Hillsboro Sub : Modify relaying for connecting terminal to Ash Creek Switch for point of interconnection (POI) | City of Hillsboro, Hill County | Modify relaying for connecting terminal to Ash Creek Switch for point of interconnection (POI) | 2023-02-25 | 2022-11-10 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48200 (R6223) | Tiger Creek Switch : Establish 3-breaker ring -bus arrangement point of interconnection (POI) | McLennan County | Establish 3-breaker ring-bus arrangement point of interconnection (POI) | 2023-02-17 | 2023-12-14 | [6 empty] | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48070 | Thorndale North Sub: Install bank #2 with one transformer and two feeder breakers | City of Thorndale, Milam County | Install bank #2 with one transformer and two feeder breakers | 2023-02-15 | 2023-12-01 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47351 | Mason Sub: Replace two transformers | Reeves County | Replace transformer #1 and #2 | 2023-02-13 | 2023-05-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47410 (R8616) | Buchanan Ranch Sub: Install 110.4 MVAR capacitor bank | City of Midland, Midland County | Install 110.4 MVAR capacitor bank | 2023-02-01 | 2023-10-06 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47778 | Westmoreland North Sub: Install transformer #2 and one feeder breaker | City of Dallas, Dallas County | Install transformer #2 and one feeder breaker | 2023-01-04 | 2023-05-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47741 (M4330) | Sherman South Sub : Remove one 138 kV circuit breaker | City of Sherman, Grayson County | Remove one 138 kV circuit breaker | 2023-04-17 | 2023-05-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46303 (R944) | Cumby Sub: Convert station to 138 kV operation | City of Cumby, Hopkins County | Convert station to 138 kV operation | 2023-05-15 | 2023-12-01 | [6 empty] | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46293 | Euless South Sub : Replace Transformer #1 and #2 failed HU relays | City of Euless, Tarrant County | Replace Transformer #1 and #2 HU relays. | 2023-03-18 | 12/15/2022 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41021 | Marrs Switch: Terminate 138 kV Duval Switch Line | City of Forest Hill, Tarrant County | Terminate the new 138 kV Duval Switch Line | 2023-01-02 | 05/15/2023 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48541 0PT48590 (R8634) | Tesoro Switch: Establish station as a 10-breaker 345 kV breaker-and-a-half bus arrangement | City of Odessa, Midland County | Establish station as a 10-breaker 345 kV breaker-and-a-half bus arrangement | 2023-01-01 | 2023-12-01 | [6 empty] | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
CCN APPLICATIONS - APPROVED
13T80013 16T80061 | New Bethel 345 kV Loop Line | Anderson, Freestone, Navarro and Henderson Counties | This project is to construct the new double-circuit New Bethel 345 kV Line connecting the proposed New Bethel Switching station to a connection along one of four existing 345 kV transmission line segments in the region. | 2021-12-31 | 2022-12-31 |  | 26,499,000 (t-line) 7,232,000 (stations) |  |  |  |  | na | 345 | 27 | 1926.9 kcmil ACSS/TW | Lattice Steel Towers | na | na | 160 | 13.5 | 44672 | Application Filed 7/10/2015. Administrative Approval received on 09/25/2015.
17T80077 0PT38181 0PT38182 0PT38179 0PT38178 0PT38426 (97.31%) 19T63008 0PT38517 0PT38518 0PT38372 0PT38838 (R8356) (R8429) (R8351) | Odessa EHV - Riverton and Moss - Riverton 345 kV Line | Crane, Ector, Loving, Reeves, Ward, and Winkler Counties | This project is to construct the new double-circuit 345 kV line connecting the Odessa EHV Switching Station and the Moss Switching Station to the Riverton Switching Station. | 2019-03-06 | 2020-12-20 | 2020-12-20 | 199,729,000 (t-line) 23,832,000 (stations) | 248,571,042 (t-line) 18,840,070 (stations) |  |  | 100 | 345 | 345 | 216.7 | 1926.9 kcmil ACSS/TW | Lattice Steel Towers | 150 | 15.9 | 160 | 100.4 | 48095 | Application Filed 3/16/2018. Final Order issued on 9/17/2018.
0PT37302 0PT38601 0PT04138 0PT38858 (50%) 0PT37751 (50%) (R8428) | Owl Hills - Tunstill POD 138 kV Line | Culberson and Reeves Counties | Construct the new single-circuit 138 kV line connecting the proposed Owl Hills Substation to the Tunstill POD. | 2019-05-04 | 2020-12-10 | 2020-12-10 | 20,628,000 (t-line) 1,847,000 (stations) | 27,244,439 (t-line) 3,100,331 (stations) |  |  | 100 | na | 138 | 18.7 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 18.7 | 48582 | Application Filed 8/31/2018. Administrative Approval received on 11/20/2018.
NA | Stiles - Coates 138 kV Line | Reagan County | Construct the new 138 kV transmission line connecting the existing Stiles station to the proposed Coates station. | 2021-12-31 | 2023-12-31 |  | 9682000 |  |  |  |  | na | 138 | 8 | 959.6 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 100 | 8 | 46726 | Application Filed 1/17/2017. Final Order issued on 9/29/2017.
0PT37182 0PT40453 0PT38505 0PT38427 (95.57%) 0PT39348 0PT39349 (R8380) (R8420) | Sand Lake - Solstice 345 kV Line | Pecos, Reeves, and Ward Counties | This project is to construct the new double-circuit 345 kV line connecting the Oncor Sand Lake Switch to the AEP Texas Solstice Switch. | 2019-06-21 | 2020-12-28 | 2020-12-28 | 49,110,000 (t-line) 17,600,000 (stations) (Oncor Portion) | 68,922,778 (t-line) 22,523,721 (stations) (Oncor Portion) |  |  | 100 | na | 345 | 89 | 1926.9 kcmil ACSS/TW | Lattice Steel Towers | na | na | 160 | 44.5 | 48785 | Application Filed 11/7/2018. Final Order issued on 6/26/2019.
0PT38174 0PT40267 0PT04144 (50%) 0PT40670 0PT40867 (50%) (R8427) | Riverton - Kyle Ranch 138 kV Line | Loving and Reeves Counties | Construct the new single-circuit 138 kV line connecting the Riverton Switch station to the Kyle Ranch Substation. | 2020-06-08 | 2020-12-10 | 2020-12-10 | 19,207,000 (t-line) 3,040,000 (stations) | 21,226,008 (t-line) 3,301,428 (stations) |  |  | 99.5 | na | 138 | 15.2 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 15.2 | 49304 | Application Filed 3/28/2019. Administrative Approval received on 7/17/2019. This project covers the work necessary to construct the PUCT approved route, as well as an additional three (3) miles of line between the Kyle Ranch endpoint as described in this CCN and the relocated Kyle Ranch station as described in Docket No. 49302.
0PT41156 0PT42396 0PT40679 0PT41331 0PT41511 (R8534) | Johnson Draw POD - Salt Flat Road 138 kV Line | Midland County | Construct the new single-circuit 138 kV line connecting the Salt Flat Road Switch to the proposed Johnson Draw POD. | 2020-11-11 | 2021-06-29 | 2021-06-29 | 5,257,000 (t-line) 1,461,000 (stations) | 5,257,000 (t-line) 1,502,572 (stations) | 6708878.79 | -0.01% | 100 | na | 138 | 2.8 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 2.8 | 50560 | Application Filed 3/5/2020. Notice of approval issued on 5/26/2020. Final Actual Costs Reported. CCN Tab corrected from previous month. Project will be removed from next month’s report.
0PT39531 0PT44980 0PT45164 0PT42867 (R9057) | Bearkat - Longshore 345 kV Line | Glasscock and Howard Counties | Construct the new single-circuit 345 kV line connecting the WETT Bearkat Switch to the Oncor Longshore Switch. | 2022-06-10 | 2022-12-15 |  | 29,339,500 (t-line) 1,700,000 (station) (Oncor Portion) | 34,827,900 (t-line) 1,685,394 (Station) (Oncor Portion) |  |  | 38 | na | 345 | 30.8 | 1926.9 kcmil ACSS/TW | Steel Poles or Lattice Steel Towers | na | na | 160 | 30.8 | 50410 | Application Filed 1/14/2020. Final order issued on 5/7/2021.
0PT44498 0PT04088 0PT42631 (R8384) | Kyle Ranch - Quarry Field 138 kV Line (Modification of route approved in Docket No. 49302) | Loving County | Construct the new single-circuit 138 kV line connecting the relocated Kyle Ranch Substation to the Quarry Field Switch station. | 2022-07-20 | 2022-12-15 |  | 17,161,000 (t-line) | 22510282 |  |  | 47 | na | 138 | 11.3 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 11.3 | 51737 | Administrative approval received on 9/8/2021. Application Filed 2/4/2021.This project covers the work necessary to obtain PUCT approval for a modified route between the relocated Kyle Ranch station location in Docket No. 49302 and the Quarry Field switch.
0PT44880 0PT45654 0PT46013 0PT46133 0PT43859 (M4172) | Old Country Switch 345 kV Tap Line | Ellis County | Construct the new single-circuit 345 kV line connecting the proposed Old Country Switch to Oystercatcher Solar's proposed substation. | 2023-10-31 | 2024-04-30 |  | 10,392,000 (t-line) 7,825,000 (station) |  |  |  |  | na | 345 | 3.2 | 1926.9 kcmil ACSS/TW | Lattice Steel Towers | na | na | 160 | 3.2 | 52455 | Application Filed 8/26/2021. Application approved on 6/30/22 and final order issued on 7/14/22.
0PT46371 0PT46696 0PT46746 0PT46984 0PT46983 0PT46728 0PT46818 0PT47825 (R8574) | Flat Iron Substation – Barr Ranch Switch – Quickriver Tap 138 kV Line | Midland County | Construct the new single-circuit 138 kV line connecting the planned Flat Iron Substation to the proposed Quickriver Tap. The new line will be routed through a proposed intermediate station called Barr Ranch Switch. | 2022-10-03 | 2023-05-31 |  | 35,106,020 (t-line) 8,602,965 (station) | 31,803,179 (LINE) 9,754,393 (STATION) |  |  | 25 | na | 138 | 19 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 19 | 53491 | Application Filed 4/28/2022. Notice of approval on 8/3/2022. Completed Project scope to install single span and structure outside of Flat Iron substation to maximize crew safety from energized facilities. No further work will be performed until a Final Order is issued.
CCN APPLICATIONS - PENDING
0PT45017 0PT42342 0PT42455 0PT42146 | Ivy League 138 kV Line | Collin County | Construct the new single-circuit 138 kV line connecting the proposed Ivy League Substation to TNMP's existing Longneck Substation. | 2024-01-14 | 2024-04-30 |  | 9,196,000 (t-line) 4,325,000 (station) |  |  |  |  | na | 138 | 2.8 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 2.8 | 53053 | Application Filed 1/18/2022.
CCN APPLICATIONS - Oncor / LP&L: The following projects are being reported on behalf of Oncor and the City of Lubbock, by and through Lubbock Power & Light
0PT39835 0PT39844 0PT39623 0PT39631 0PT39632 (56.2%) (R3005) (R3002) (R3003) | Ogallala - Abernathy 345 kV Line | Castro, Hale and Swisher Counties | Construct the new single-circuit 345 kV line connecting the existing Ogallala station to the existing Abernathy station. This project is part of the LP&L integration into the ERCOT system. | 2020-01-15 | 2021-03-22 | 2021-03-22 | 87,876,048 (t-line) 8,304,600 (stations) | 88,807,431 (t-line) 9,122,137 (stations) |  |  | 100 | na | 345 | 57.9 | 959.6 kcmil ACSS/TW | Steel Poles or Lattice Steel Towers | na | na | 175 | 57.9 | 48625 | Application Filed 9/6/2018. Final Order issued on 9/26/2019.
0PT39896 0PT40341 0PT39625 0PT41983 0PT39632 (25.7%) 0PT39633 (55.3%) 0PT40608 0PT44515 0PT44516 (R3008) (R3003) (R3001) | Abernathy - Wadsworth 345 kV Line | Hale and Lubbock Counties | Construct the new single-circuit 345 kV line connecting the existing Abernathy station to the existing Wadsworth station. This project is part of the LP&L integration into the ERCOT system. | 2020-01-15 | 2021-05-12 | 2021-05-12 | 56,736,759 (t-line) 9,403,700 (stations) | 56,702,358 (t-line) 9,635,269 (stations) |  |  | 100 | na | 345 | 32.9 | 959.6 kcmil ACSS/TW | Steel Poles or Lattice Steel Towers | na | na | 175 | 32.9 | 48668 | Application Filed 9/20/2018. Final Order issued on 10/14/19. This is a Sharyland acquired project for the LP&L ERCOT integration. Originally filed under the NTU predecessor report.
0PT39845 0PT41440 0PT41442 0PT39634 0PT39635 0PT39628 0PT39626 0PT41832 0PT39633 (44.7%) 0PT41847 0PT44486 0PT44487 (R3006) (R3004) (R3010) (R3009) (R3001) | Wadsworth - New Oliver - Farmland 345 kV Line (WNF) | Lubbock and Lynn Counties | Construct the new single-circuit 345 kV line connecting the existing Wadsworth station to the existing Farmland station, routed through one of two options for the proposed New Oliver station. This project is part of the LP&L integration into the ERCOT system. | 2020-03-24 | 2021-05-15 | 2021-05-15 | 67,769,000 (t-line) 20,638,000 (stations) | 77,538,361 (t-line) 24,168,146 (stations) |  |  | 100 | na | 345 | 41.9 | 959.6 kcmil ACSS/TW | Steel Poles or Lattice Steel Towers | na | na | 175 | 41.9 | 48909 | Application Filed 12/19/2018. Originally filed under the NTU predecessor report. Final Order issued on 1/23/20. This is a Sharyland acquired project for the LP&L ERCOT integration. Originally filed under the NTU predecessor report.
0PT39845 0PT41452 0PT39732 0PT39967 0PT39629 0PT39630 (R3006) (R3001) (R3014) (R3013) | Southeast - New Oliver - Oliver 115 kV Line (SNO) | Lubbock County | Construct the new single-circuit 115 kV line connecting the existing Southeast station to the existing Oliver station, routed through one of two options for the proposed New Oliver station. This project is part of the LP&L integration into the ERCOT system. | 2020-01-20 | 2021-05-15 | 2021-05-15 | 20,688,000 (t-line) 31,248,000 (stations) | 21,452,317 (t-line) 27,949,110 (stations) |  |  | 100 | na | 115 | 17.8 | 959.6 kcmil ACSS/TW | Steel Poles | na | na | 60 | 17.8 |  | Application Filed 12/19/2018. Originally filed under the NTU predecessor report. Final Order issued on 1/23/20. This is a Sharyland acquired project for the LP&L ERCOT integration. Originally filed under the NTU predecessor report.
0PT39846 0PT41891 0PT39637 0PT39968 0PT39636 0PT41986 0PT39632 (18.1%) 0PT44518 0PT44519 (R3007) (R3011) (R3003) | Abernathy - North - North Loop 345/115 kV Line | Hale and Lubbock Counties | Construct the new transmission line connecting the existing Abernathy station to the northern portion of LP&L's planned 115 kV loop line, routed through one of three options for the proposed North station. Depending on which North station is used, this line will be either a single-circuit 345 kV line or a combination of single-circuit 345 kV and double-circuit 115 kV line. This project is part of the LP&L integration into the ERCOT system. | 2019-12-21 | 2021-05-16 | 2021-05-16 | 39,782,000 (t-line) 33,367,000 (stations) | 44,361,677 (t-line) 20,274,578 (stations) |  |  | 100 | na | 115/345 | 34.3 | 959.6 kcmil ACSS/TW | Steel Poles or Lattice Steel Towers (345 kV) Steel Poles (115 kV) | na | na | 175 (345 kV) 60 (115 kV) | 24.6 | 49151 | Application Filed 2/19/2019. Final Order issued on 3/12/2020. Originally filed under the NTU predecessor report. Project was inadvertently overwritten by a duplicate project last month and is being re-added.

## EntryInstructions
General Instructions for Entering Information
1. Please use "na" whenever appropriate to reduce ambiguity, except in the "Costs," "Percent Complete," and "Percent Variance" columns. 2. Any new or revised entry must be entered using a red font and highlighted in yellow. In the month following the red font entry, change the previous month's red entries back to black and make any new entries for the new month in red. This aids PUCT staff in quickly identifying any changes from the previous month's report. 3. On the final monthly report on an existing line in which one of the attributes as listed in the attribute spreadsheets below has changed, enter that data in a bolded green font.
Utility's Project Number | Enter the Utility's Project Number. No duplicate numbers are allowed in this column.
Project Name | Enter the name of the project. If possible, use the same name as was reported to ERCOT in any reports.
Location (City/County) | Enter the names of the counties where the project is located. Also enter the names of cities, if appropriate. Please delineate all county and city names with commas only. (e.g., Liberty, Chambers, Anahuac, etc.)
Description | Describe the project in enough detail to allow the Commission to ensure that the work does not require a CCN, if the utility does not intend to apply for a CCN. Include any significant or relevant detail not being reported in other columns. Do not include Point of Delivery and add periods to all sentences.
Estimated (or Actual) Start Date | Enter the estimated project starting date. When construction begins, please replace the estimated date with the actual date of the start of construction
Finish Date (Construction Complete) | Enter the date (mm/dd/yy) when the construction related to the project has been completed.
Date Energized (If Applicable) | Enter the date (mm/dd/yy) the project was energized or restored to service (if applicable).
Initial Estimated Project Cost | CCN Projects Only: Enter the estimated cost from the CCN application. When reporting both T-Line and Substation Costs, enter them separately in the same cell. (e.g., "$3,946,000 T-Line; $1,768,000 Substation") This number shall not be changed in future months unless the Application is amended. Please DO NOT use links to other sheets within the workbook. Non-CCN Projects Only: No entry is needed; Enter the estimated cost in the
Final Estimated Project Cost | CCN Projects: Enter the latest available estimated cost for the month that construction starts. This number shall not be changed after construction begins. and a cost variance explanation is not required unless requested by PUC Staff For Non-CCN Projects: Enter the initial estimated cost. Estimate revisions are not necessary
Final Actual Project Cost | Enter the actual, final project cost after the project has been energized and all costs have been recorded. Omit the project from all following reports.
% Variance | The cells contain a formula for calculating the percent variance of the final actual cost with respect to the final estimated cost. This is essentially a calculation of the percent of the cost over-run or under-run. Please do not change these cells.
Percent Complete | State the construction progress of the project as a percent. Please use only an integer and do not write"%." Do not report the percent of money spent.
Existing Voltage | Enter the nominal system existing voltage, if any. In the event of a voltage upgrade, this will be the "before" voltage. If the project is for a new line, enter "na." For projects involving multiple voltages, please delineate the voltages by a comma, (e.g., "69,138"). Please do not write "volts."
Upgraded or New Voltage | Enter the nominal system voltage after upgrading or if new line construction is involved. Please use the same practices described in the "Existing Voltage" column. Please do not write "volts."
Circuit Length (Miles) | Enter the total circuit length. Example: For a new double-circuit line using 10 miles of new ROW, the circuit length would be 20 miles. Please enter only a number, if possible. Please do not write "miles."
Conductor Type & Size & Bundling | Describe the conductor characteristics, including whether double or single circuit or mixed. Lengthy explanations shall be made in the Project Description column. (Format should be Quantity - Conductor Size and Type). Do not include quotations for supplier given code words or the word bundled.
Structure Type(s) | Describe structure types and materials used.
Existing ROW Width (Feet) | Enter width of existing ROW. The entry type is unrestricted. If the project is only for new line and no old ROW exists, enter "na." Entries such as "60,80,100" or "60 - 100" or "centerline" are permissible. Make detailed explanations, if needed, elsewhere. Please do not write "feet."
Existing ROW Length (Miles) | Enter length of existing ROW. The entry type is unrestricted. If the project is only for new line and no old ROW exists, enter "na." Make detailed explanations, if needed, elsewhere. Please do not write "miles."
New ROW Width (Feet) | Enter width of new ROW. The entry type is unrestricted. Entries such as "60,80,100" or "60 - 100" or "centerline" or "railroad" or "street" are permissible. Make detailed explanations, if needed, elsewhere. Please do not write "feet."
New ROW Length (Miles) | Enter new (additional) ROW length, in miles. Please do not write "miles."
Rule Section or PUC Control Number | Enter the PUC Substantive Rule 25.101 section(s) which are applicable. For multiple section applicability, please delineate by commas, e.g., "25.101(c)(5)(A), 25.101(c)(5)(B)" for a project incorporating a line extension (A) and a voltage upgrade on the existing line which is being extended (B). If the project involves a CCN Application, enter ONLY the .5-digit control number. Please do not write "docket," "CCN" or other text, except when needed in citing Rule 25.101. Should the project include work done under both CCN and 25.101(c)(5), follow the same practices and delineate with commas.
Comments | Enter information not included elsewhere, including reimbursed costs. A cost variance explanation is no longer required for non-CCN projects. However, utilities will be required to submit a Cost Analysis only for CCN Projects. See Note below.
139510
0PT39030 SB

## 16T80061 & 16T64136
Project No. 16T80061 & 16T64136 - New Bethel 345 kV Loop Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 1963) | Estimated cost once a route is approved and CCN granted (Route 1963) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 2952000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 601000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 2959000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 8324000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 11663000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 26499000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 26499000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | N/A | N/A
Engineering and Design (Utility) | 0 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 499000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 3341000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 338000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 2467000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 6645000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 587000 | Costs not yet available | Costs not yet available
Estimated Project Total | 7232000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 33731000
139510
0PT39030 SB |  | City of Tyler, Bell County

## 17T80077
Project No. 17T80077, 0PT38181, 0PT38182, 0PT38179, 0PT38178, 0PT38426, 19T63008, 0PT38517, 0PT38518 - Odessa EHV - Riverton and Moss - Riverton 345 kV Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 1180) | Estimated cost once a route is approved and CCN granted (Route 1180) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 21540000 | 29205738 | Costs not yet available
Engineering and Design (Utility) | 5322000 | 0 | Costs not yet available
Engineering and Design (Contract) | 2269000 | 2877377 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 74495000 | 76498142 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 96103000 | 103610002 | Costs not yet available
Estimated Total Cost | 199729000 | 212191259 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 36379783 | Costs not yet available
Estimated Project Total | 199729000 | 248571042 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | N/A
Engineering and Design (Utility) | 245000 | 166800 | Costs not yet available
Engineering and Design (Contract) | 922857 | 908706 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 15969607 | 9781320 | Costs not yet available
Construction of Facilities (Utility) | 2270494 | 479109 | Costs not yet available
Construction of Facilities (Contract) | 4424042 | 5436125 | Costs not yet available
Estimated Total Cost | 23832000 | 0 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 2068010 | Costs not yet available
Estimated Project Total | 23832000 | 18840070 | Costs not yet available
Reported on Monthly Construction Report | 223561000 | 267411112
139510
0PT39030 SB |  | City of Tyler, Bell County

## 17T80032 (hidden)
Project No. 17T80032 & 0PT04024 - Cogdell - Clairemont 138 kV Line - Transmission Line Project
*THIS IS A JOINT PROJECT WITH BRAZOS ELECTRIC POWER - ALL COSTS SHOWN IN TABLE BELOW ARE ONCOR'S PORTION OF THE PROJECT
| Estimated cost included in CCN Application (Route 125) | Estimated cost once a route is approved and CCN granted (Route 39) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1226000 | 2189374 | 1642208.41
Engineering and Design (Utility) | 378500 | 900000 | 981388
Engineering and Design (Contract) | 438000 | 900000 | 724705.87
Procurement of Material & Equipment (including Stores) | 2930000 | 3925000 | 3229859.42
Construction of Facilities (Utility) | 0 | 1685000 | 0
Construction of Facilities (Contract) | 5225000 | 8990000 | 6321041.07
Estimated Total Cost | 10197500 | 18589374 | 12899202.77
Other (all costs not included in the above categories) | 0 | 0
Estimated Project Total | 10197500 | 18589374 | 12899202.77
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | N/A | N/A | N/A
Engineering and Design (Utility) | N/A | N/A | N/A
Engineering and Design (Contract) | N/A | N/A | N/A
Procurement of Material & Equipment (including Stores) | N/A | N/A | N/A
Construction of Facilities (Utility) | N/A | N/A | N/A
Construction of Facilities (Contract) | N/A | N/A | N/A
Estimated Total Cost | N/A | N/A | N/A
Other (all costs not included in the above categories) | N/A | N/A | N/A
Estimated Project Total | N/A | N/A | N/A
Reported on Monthly Construction Report | 10197500 | 18589374 | 12899202.77
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT37302
Project No. OPT37302, 0PT38601 - Owl Hills - Tunstill POD 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 15) | Estimated cost once a route is approved and CCN granted (Route 15) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1769000 | 4038047 | Costs not yet available
Engineering and Design (Utility) | 607000 | 0 | Costs not yet available
Engineering and Design (Contract) | 830000 | 3505474 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 5734000 | 8210994 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 11688000 | 11489924 | Costs not yet available
Estimated Total Cost | 20628000 | 27244439 | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | Costs not yet available
Estimated Project Total | 20628000 | 27244439 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | N/A | N/A
Engineering and Design (Utility) | 90000 | 0 | Costs not yet available
Engineering and Design (Contract) | 0 | 14301 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 1250000 | 1862654.45 | Costs not yet available
Construction of Facilities (Utility) | 155000 | 309438.41 | Costs not yet available
Construction of Facilities (Contract) | 352000 | 913937.48 | Costs not yet available
Estimated Total Cost | 1847000 | 3100331.34 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 1847000 | 3100331.34 | Costs not yet available
Reported on Monthly Construction Report | 22475000 | 30344770.34
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT37182
Project No. 0PT37182, 0PT40453, OPT38505, 0PT38427- Sand Lake - Solstice 345 kV Line - Transmission Line Project
*THIS IS A JOINT PROJECT WITH AEP TEXAS - ALL COSTS SHOWN IN TABLE BELOW ARE ONCOR'S PORTION OF THE PROJECT
| Estimated cost included in CCN Application (Route 320) | Estimated cost once a route is approved and CCN granted (Modified Route 320) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 4561500 | 10739693 | Costs not yet available
Engineering and Design (Utility) | 1058500 | 694256 | Costs not yet available
Engineering and Design (Contract) | 1348000 | 1105909 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 16793500 | 13285278 | Costs not yet available
Construction of Facilities (Utility) | 500 | 0 | Costs not yet available
Construction of Facilities (Contract) | 25348000 | 38847631 | Costs not yet available
Estimated Total Cost | 49110000 | 64672767 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 4250011 | Costs not yet available
Estimated Project Total | 49110000 | 68922778 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | N/A
Engineering and Design (Utility) | 0 | 0 | Costs not yet available
Engineering and Design (Contract) | 400000 | 444635 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 13200000 | 17005560 | Costs not yet available
Construction of Facilities (Utility) | 1210000 | 1065160 | Costs not yet available
Construction of Facilities (Contract) | 2026000 | 4008366 | Costs not yet available
Estimated Total Cost | 16836000 | 22523721 | Costs not yet available
Other (all costs not included in the above categories) | 764000 | 0 | Costs not yet available
Estimated Project Total | 17600000 | 22523721 | Costs not yet available
Reported on Monthly Construction Report | 66710000 | 91446499
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT38174
Project No. 0PT38174 ,0PT40267 & 0PT04144 - Riverton - Kyle Ranch 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 7) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1694000 | 2387508 | Costs not yet available
Engineering and Design (Utility) | 517000 | 1258500 | Costs not yet available
Engineering and Design (Contract) | 876000 | 1300000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4866000 | 7416500 | Costs not yet available
Construction of Facilities (Utility) | 0 | 708500 | Costs not yet available
Construction of Facilities (Contract) | 11254000 | 8155000 | Costs not yet available
Estimated Total Cost | 19207000 | 21226008 | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | Costs not yet available
Estimated Project Total | 19207000 | 21226008 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 70000 | 194717 | Costs not yet available
Engineering and Design (Utility) | 0 | 115906.71 | Costs not yet available
Engineering and Design (Contract) | 200000 | 13288.25 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 1900000 | 1852954.57 | Costs not yet available
Construction of Facilities (Utility) | 120000 | 0 | Costs not yet available
Construction of Facilities (Contract) | 750000 | 1124561.47 | Costs not yet available
Estimated Total Cost | 3040000 | 3301428 | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | Costs not yet available
Estimated Project Total | 3040000 | 3301428 | Costs not yet available
Reported on Monthly Construction Report | 22247000 | 24527436
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT38176 (hidden)
Project No. 0PT38176, 0PT04088, 0PT04087, 0PT04144 - Kyle Ranch - Quarry Field 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 11) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1382000 | * | * | *Application Filed 3/28/2019. Final Order issued on 3/2/2020. This project had three (3) miles moved to project (0PT38174) Riverton - Kyle Ranch 138 kV Line Docket No. 49304 and the remainder is superseded it by project (0PT44498) Kyle Ranch - Quarry Field 138 kV Line Docket No. 51737. Final Actual Costs Reported. Project will be removed from next month’s report.
Engineering and Design (Utility) | 422000 | * | *
Engineering and Design (Contract) | 834000 | * | *
Procurement of Material & Equipment (including Stores) | 4424000 | * | *
Construction of Facilities (Utility) | 0 | * | *
Construction of Facilities (Contract) | 9770000 | * | *
Estimated Total Cost | 16832000 | * | *
Other (all costs not included in the above categories) | 0 |  | -
Estimated Project Total | 16832000 | * | *
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 2270000 | 2282394 | 2860720
Engineering and Design (Utility) | 0 | 300000 | 363057.29
Engineering and Design (Contract) | 500000 | 390782 | 402738.77
Procurement of Material & Equipment (including Stores) | 7700000 | 7837492 | 8212085.94
Construction of Facilities (Utility) | 585000 | 2363273 | 0
Construction of Facilities (Contract) | 4800000 | 5766660 | 7023790.58
Estimated Total Cost | 15855000 | 18940601 | 18862392.58
Other (all costs not included in the above categories) | 0 | 19300 | 0
Estimated Project Total | 15855000 | 18959901 | 18862392.58
Reported on Monthly Construction Report | 32687000 | 18959901 | 18862392.58
139510
0PT39030 SB |  | City of Tyler, Bell County

## NA
Project No. NA - Stiles - Coates 138 kV Line - NTU Transmission Line Project
| Estimated cost included in CCN Application (Route B4) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 3347000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 249000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 733000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 2070000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 222000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 2915000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 9536000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 146000 | Costs not yet available | Costs not yet available
Estimated Project Total | 9682000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 161000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 84000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 893000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4376000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 432000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 2780000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 8726000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 8726000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 18408000 | Costs not yet available
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT39835
Project No. 0PT39835, 0PT39623, 0PT39631, 0PT39632 - Ogallala - Abernathy 345 kV Line - NTU Transmission Line Project (Dkt. 48625)
| Estimated cost included in CCN Application (Route 4) | Estimated cost once a route is approved and CCN granted (Route 4a) | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 13575702 | 14502458.3192 | Costs not yet available
Engineering and Design (Utility) | 165760 | 186171.1163 | Costs not yet available
Engineering and Design (Contract) | 3430680 | 3126596.9787 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 35371142 | 33506760.9081 | Costs not yet available
Construction of Facilities (Utility) | 356601 | 0 | Costs not yet available
Construction of Facilities (Contract) | 34795274 | 37485443.6777 | Costs not yet available
Estimated Total Cost | 87695159 | 88807431 | Costs not yet available
Other (all costs not included in the above categories) | 180889 | 0 | Costs not yet available
Estimated Project Total | 87876048 | 88807431 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | Costs not yet available
Engineering and Design (Utility) | 0 | 0 | Costs not yet available
Engineering and Design (Contract) | 507200 | 441197.96 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4883800 | 4431568.67 | Costs not yet available
Construction of Facilities (Utility) | 0 | 302334.32 | Costs not yet available
Construction of Facilities (Contract) | 2913600 | 3947036.33 | Costs not yet available
Estimated Total Cost | 8304600 | 9122137.28 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 8304600 | 9122137.28 | Costs not yet available
Reported on Monthly Construction Report | 96180648 | 97929568.28
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT39896
Project No. 0PT39896 - Abernathy - Wadsworth 345 kV Line - NTU Transmission Line Project (Dkt. 48668)
| Estimated cost included in CCN Application (Route 1) | Estimated cost once a route is approved and CCN granted (Route 1) | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 7979470 | 9543014.7112 | Costs not yet available
Engineering and Design (Utility) | 110471 | 150723.6435 | Costs not yet available
Engineering and Design (Contract) | 1917538 | 1785293.9269 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 21275928 | 19474125.3795 | Costs not yet available
Construction of Facilities (Utility) | 202943 | 0 | Costs not yet available
Construction of Facilities (Contract) | 25127504 | 25749200.3389 | Costs not yet available
Estimated Total Cost | 56613854 | 56702358 | Costs not yet available
Other (all costs not included in the above categories) | 122905 | 0 | Costs not yet available
Estimated Project Total | 56736759 | 56702358 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 77935 | Costs not yet available
Engineering and Design (Utility) | 0 | 0 | Costs not yet available
Engineering and Design (Contract) | 605500 | 359797 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 5266900 | 4710275.06 | Costs not yet available
Construction of Facilities (Utility) | 0 | 236755.19 | Costs not yet available
Construction of Facilities (Contract) | 3531300 | 4250506.42 | Costs not yet available
Estimated Total Cost | 9403700 | 9635268.67 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 9403700 | 9635268.67 | Costs not yet available
Reported on Monthly Construction Report | 66140459 | 66337626.67

## 0PT39845
Project No. 0PT39845 - Wadsworth - New Oliver - Farmland 345 kV Line (WNF) and Southeast - New Oliver - Oliver 115 kV Line (SNO) - NTU Transmission Line Projects (Dkt. 48909)
| Wadworth - New Oliver - Farmland 345 kV Line |  |  |  | Southeast - New Oliver - Oliver 115 kV Line
| Estimated cost included in CCN Application (Route 20) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 12 months after construction is complete |  | Estimated cost included in CCN Application (Route 9) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs: |  | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 8257000 | 11775886.9771 | Costs not yet available | Right-of-Way and Land Acquisition | 4471000 | 5164970.0609 | Costs not yet available
Engineering and Design (Utility) | 117000 | 178363.3316 | Costs not yet available | Engineering and Design (Utility) | 120000 | 62760.5556 | Costs not yet available
Engineering and Design (Contract) | 2794000 | 3791870.5499 | Costs not yet available | Engineering and Design (Contract) | 1530000 | 1649065.0706 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 27393000 | 27464811.7198 | Costs not yet available | Procurement of Material & Equipment (including Stores) | 4298000 | 5126788.2332
Construction of Facilities (Utility) | 314000 | 0 | Costs not yet available | Construction of Facilities (Utility) | 216000 | 0 | Costs not yet available
Construction of Facilities (Contract) | 28726000 | 34327428.4216 | Costs not yet available | Construction of Facilities (Contract) | 9921000 | 9448733.0797 | Costs not yet available
Estimated Total Cost | 67601000 | 77538361 | Costs not yet available | Estimated Total Cost | 20556000 | 21452317 | Costs not yet available
Other (all costs not included in the above categories) | 168000 | 0 | Costs not yet available | Other (all costs not included in the above categories) | 132000 | 0 | Costs not yet available
Estimated Project Total | 67769000 | 77538361 | Costs not yet available | Estimated Project Total | 20688000 | 21452317 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities |  | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 564000 | 1376048 | Costs not yet available | Right-of-Way and Land Acquisition | 0 | 152894.2 | Costs not yet available
Engineering and Design (Utility) | 0 | 21830.19 | Costs not yet available | Engineering and Design (Utility) | 105000 | 27328.31 | Costs not yet available
Engineering and Design (Contract) | 1617000 | 1000798.39 | Costs not yet available | Engineering and Design (Contract) | 1075000 | 635862.34 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 10517000 | 10394558.73 | Costs not yet available | Procurement of Material & Equipment (including Stores) | 25465000 | 21705484.59 | Costs not yet available
Construction of Facilities (Utility) | 0 | 497613.72 | Costs not yet available | Construction of Facilities (Utility) | 170000 | 523401.98 | Costs not yet available
Construction of Facilities (Contract) | 7940000 | 10877297.09 | Costs not yet available | Construction of Facilities (Contract) | 4433000 | 4904138.78 | Costs not yet available
Estimated Total Cost | 20638000 | 24168146.12 | Costs not yet available | Estimated Total Cost | 31248000 | 27949110.2 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available | Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 20638000 | 24168146.12 | Costs not yet available | Estimated Project Total | 31248000 | 27949110.2 | Costs not yet available
Reported on Monthly Construction Report | 88407000 | 101706507.12 | Costs not yet available | Reported on Monthly Construction Report | 51936000 | 49401427.2 | Costs not yet available

## 0PT39846
Project No. 0PT39846 - Abernathy - North - North Loop 345/115 kV Line - NTU Transmission Line Project (Dkt. 49151)
| Estimated cost included in CCN Application (Route 25) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 4871000 | 8342781.3539 | Costs not yet available
Engineering and Design (Utility) | 237000 | 95753.4343 | Costs not yet available
Engineering and Design (Contract) | 2720000 | 1799694.4634 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 13414000 | 14554335.7083 | Costs not yet available
Construction of Facilities (Utility) | 230000 | 0 | Costs not yet available
Construction of Facilities (Contract) | 18124000 | 19569112.0401 | Costs not yet available
Estimated Total Cost | 39596000 | 44361677 | Costs not yet available
Other (all costs not included in the above categories) | 186000 | 0 | Costs not yet available
Estimated Project Total | 39782000 | 44361677 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 300000 | Costs not yet available
Engineering and Design (Utility) | 115000 | 0 | Costs not yet available
Engineering and Design (Contract) | 2141000 | 610437.2 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 21621000 | 13689359.68 | Costs not yet available
Construction of Facilities (Utility) | 150000 | 506821.26 | Costs not yet available
Construction of Facilities (Contract) | 9340000 | 5167959.8 | Costs not yet available
Estimated Total Cost | 33367000 | 20274577.94 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 33367000 | 20274577.94 | Costs not yet available
Reported on Monthly Construction Report | 73149000 | 64636254.94

## 0PT38573 (hidden)
Project No. 0PT38573, 0PT38506, 0PT38427 (4.43%), 0PT38426 (2.69%) - Riverton - Sand Lake 345 kV Line Circuit Addition - Transmission Line Project (Phase 2)
| Estimated cost included in CCN Application | Estimated cost once a route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 0 | 648304 | 429866.77
Engineering and Design (Utility) | 1400000 | 281000 | 135933.24
Engineering and Design (Contract) | 1900000 | 485000 | 497002.67
Procurement of Material & Equipment (including Stores) | 12500000 | 11332089 | 10738792
Construction of Facilities (Utility) | 0 | 0
Construction of Facilities (Contract) | 13400000 | 11815254 | 13073734.13
Estimated Total Cost | 29200000 | 24561647 | 24875328.81
Other (all costs not included in the above categories) | 0 | 0 | 0
Estimated Project Total | 29200000 | 24561647 | 24875328.81
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | 0
Engineering and Design (Utility) | 0 | 0 | 22568.36
Engineering and Design (Contract) | 155000 | 82677 | 41463.16
Procurement of Material & Equipment (including Stores) | 665000 | 785964 | 518739.35
Construction of Facilities (Utility) | 78000 | 140876 | 0
Construction of Facilities (Contract) | 287000 | 414784 | 413628.6
Estimated Total Cost |  | 1424301 | 996399.47
Other (all costs not included in the above categories) | 0 | 29866 | 0
Estimated Project Total | 1185000 | 1454167 | 996399.47
Reported on Monthly Construction Report | 30385000 | 26015814 | 25871728.28

## 0PT39531
Project No. 0PT39531 - Bearkat (WETT) - Longshore 345 kV Line Transmission Line Project
*THIS IS A JOINT PROJECT WITH WETT - ALL COSTS SHOWN IN TABLE BELOW ARE ONCOR'S PORTION OF THE PROJECT
| Estimated cost included in CCN Application (Route 102) | Estimated cost once a route is approved and CCN granted (Route 69) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 3125500 | 4344273.75 | Costs not yet available
Engineering and Design (Utility) | 771500 | 807985.51 | Costs not yet available
Engineering and Design (Contract) | 1170000 | 2952589 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 8803500 | 11251734.71 | Costs not yet available
Construction of Facilities (Utility) | 0 | 31875 | Costs not yet available
Construction of Facilities (Contract) | 15469000 | 15596226.81 | Costs not yet available
Estimated Total Cost | 29339500 | 34984684.78 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 29339500 | 34984684.78 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | N/A
Engineering and Design (Utility) | 0 | 0 | Costs not yet available
Engineering and Design (Contract) | 150000 | 150000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 810000 | 810000 | Costs not yet available
Construction of Facilities (Utility) | 60000 | 60000 | Costs not yet available
Construction of Facilities (Contract) | 390000 | 390000 | Costs not yet available
Estimated Total Cost | 1410000 | 1410000 | Costs not yet available
Other (all costs not included in the above categories) | 290000 | 275394.44 | Costs not yet available
Estimated Project Total | 1700000 | 1685394.44 | Costs not yet available
Reported on Monthly Construction Report | 31039500 | 34984684.78 | Costs not yet available

## 0PT41156 (hidden)
Project No. 0PT41156, 0PT42396, 0PT40679, 0PT41331, 0PT41511 & 0PT42120 - Johnson Draw POD - Salt Flat Road Switch 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 62000 | 175000 | 255856.63
Engineering and Design (Utility) | 50000 | 50000 | 60237.57
Engineering and Design (Contract) | 795000 | 662000 | 393450.54
Procurement of Material & Equipment (including Stores) | 1600000 | 1600000 | 1689352.81
Construction of Facilities (Utility) | 150000 | 150000 | 0
Construction of Facilities (Contract) | 2600000 | 2620000 | 2370161.77
Estimated Total Cost | 5257000 | 5257000 | 4769059.32
Other (all costs not included in the above categories) | 0 | 0 | -
Estimated Project Total | 5257000 | 5257000 | 4769059.32
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 1000 | 0
Engineering and Design (Utility) | 0 | 0 | 148521
Engineering and Design (Contract) | 210000 | 219023 | 218940
Procurement of Material & Equipment (including Stores) | 610000 | 602796 | 614397
Construction of Facilities (Utility) | 170000 | 104446 | 0
Construction of Facilities (Contract) | 470000 | 576307 | 957962
Estimated Total Cost | 1461000 | 1502572 | 1939820
Other (all costs not included in the above categories) | 0 | 0 | -
Estimated Project Total | 1461000 | 1502572 | 1939820
Reported on Monthly Construction Report | 6718000 | 6759572 | 6708879.32

## 0PT44498
Project No. 0PT44498, 0PT04088, 0PT42631 - Kyle Ranch - Quarry Field 138 kV Line - Transmission Line Project (Modification Of Route Approved In Docket No. 49302)
| Estimated cost included in CCN Application (Modified Route) | Estimated cost once a route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1260000 | 2265599.4 | Costs not yet available
Engineering and Design (Utility) | 386000 | 134847.1 | Costs not yet available
Engineering and Design (Contract) | 827000 | 974166.61 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4077000 | 8868772.83 | Costs not yet available
Construction of Facilities (Utility) | 0 | 277.24 | Costs not yet available
Construction of Facilities (Contract) | 10611000 | 10266619.29 | Costs not yet available
Estimated Total Cost | 17161000 | 22510282.47 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 17161000 | 22510282.47 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | 0
Engineering and Design (Utility) | 0 | 0 | 0
Engineering and Design (Contract) | 0 | 0 | 0
Procurement of Material & Equipment (including Stores) | 0 | 0 | 0
Construction of Facilities (Utility) | 0 | 0 | 0
Construction of Facilities (Contract) | 0 | 0 | 0
Estimated Total Cost | 0 | 0 | 0
Other (all costs not included in the above categories) | 0 | 0 | 0
Estimated Project Total | 0 | 0 | 0
Reported on Monthly Construction Report | 17161000 | 22510282.47 | Costs not yet available
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT44880
Project No. 0PT44880 - Old Country Switch 345 kV Tap Line - Transmission Line Project
| Estimated cost included in CCN Application - Route 54 | Estimated cost included in CCN Application of PUC Approved Route 152 | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1765000 | 2315000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 153000 | 199000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 1470000 | 1499000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 1842000 | 2336000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 5162000 | 6389000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 10392000 | 12738000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | Costs not yet available | Costs not yet available
Estimated Project Total | 10392000 | 12738000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 393000 | 393000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 584000 | 584000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 370000 | 370000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 3491000 | 3491000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 351000 | 351000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 2636000 | 2636000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 7825000 | 7825000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | Costs not yet available | Costs not yet available
Estimated Project Total | 7825000 | 7825000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 18217000 | 20563000 | Costs not yet available | Costs not yet available

## 0PT45017
Project No. 0PT45017, 0PT42342, 0PT42455, 0PT42146 - Ivy League Substation 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application - Route 4626 | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 2096000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 135000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 1536000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 1978000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 3451000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 9196000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 9196000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 100000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 339000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 42000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 2151000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 78000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 1615000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 4325000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 4325000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 13521000 | Costs not yet available | Costs not yet available

## 0PT46371
Project No. 0PT46371,0PT46696, 0PT46746, 0PT46984,0PT46983, 0PT46728, 0PT46818, 0PT47825 - Flat Iron Substation - Barr Ranch Switch - Quickriver Tap 138 kV Line - Transmission Line Project
| Estimated cost included in CCN | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1244020 | 1492400 | Costs not yet available
Engineering and Design (Utility) | 693000 | 40000 | Costs not yet available
Engineering and Design (Contract) | 862000 | 1525936 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 11657000 | 11914352 | Costs not yet available
Construction of Facilities (Utility) | 120000 | 0 | Costs not yet available
Construction of Facilities (Contract) | 20530000 | 16830491 | Costs not yet available
Estimated Total Cost | 35106020 | 31803179 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 35106020 | 31803179 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 101230 | 110656 | Costs not yet available
Engineering and Design (Utility) | 0 | 337736 | Costs not yet available
Engineering and Design (Contract) | 525000 | 1532505 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 3437408 | 3674205 | Costs not yet available
Construction of Facilities (Utility) | 423700 | 0 | Costs not yet available
Construction of Facilities (Contract) | 4115627 | 4099291 | Costs not yet available
Estimated Total Cost | 8602965 | 9754393 | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | Costs not yet available
Estimated Project Total | 8602965 | 9754393 | Costs not yet available
Reported on Monthly Construction Report | 43708985 | Costs not yet available | Costs not yet available