## Sheet1
Utility’s Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | % Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Project Manager | Rule Section or PUC Control Number
T-0275/S-0885 | Scenic Loop 138kV Transmission Line and Substation | Bexar | Construct new 138kV transmission line to provide a transmission point of interconnection to a new substation. | 2024-01-01 | 2025-01-31 | n/a | $37.6M | n/a | n/a | n/a | 0% | 138 | 138 | 4.46 | Bundled 795 Kcmil Drake ACSS/TW | Double Cir Steel Monopoles | n/a | n/a | 100 | 4.46 | Daniel Otto | 51023
T-0303/S-0940 | Old Hickory | Jackson | Construction of a 345kV switchyard for the Old Hickory photovoltaic generating plant. (3) 345kV single circuits, dead end monopoles to loop into 345kv switchyard. | 2023-03-13 | 2024-05-10 | n/a | $11.0M | n/a | n/a | n/a | 0% | 345 | 345 | 0.1 | Bundled 795 Kcmil ACSR | Single Circuit Steel Structures | n/a | n/a | n/a | n/a | Antonio DeMendonca | 25.101.(c)(5)(A)
T-0313/S-0966 | Cachena | Wilson | Install a new 345kV transmission loop and switchyard to connect new Cachena Solar PV Generation. | 2023-04-03 | 2024-10-04 | n/a | $3.7M | n/a | n/a | n/a | 0% | 345 | 345 | 0.1 | Bundled 795 Kcmil ACSR | Single Circuit Steel Structures | 100 | 0.1 | n/a | n/a | Kevin Philips | 25.101.(c)(5)(A)
T-0323/S-0968 | Libra BESS | Guadalupe | Install (2) new 345kV H-frame transmission structures to connect battery generation into Elm Creek Substation. Install Gen-Tie to Libra BESS. | 2023-06-05 | 2023-09-29 | n/a | $4.7M | n/a | n/a | n/a | 0% | 345 | 345 | 0.15 | Single 795 Kcmil ACSR | Single Circuit Steel Structures | n/a | n/a | n/a | n/a | Antonio DeMendonca | 25.101.(c)(5)(A)
T-0327/S-0969 | Padua BESS Transmission Interconnect | Bexar | Install a new 138kV transmission line approximately two (2) miles long to connect the customer’s battery generation into Sommers Switchyard. | 2023-06-05 | 2023-11-17 | n/a | $4.4M | n/a | n/a | n/a | 0% | 138 | 138 | 1.96 | Single 1272 Kcmil ACSS/TW | Single Circuit Steel Structures | n/a | n/a | n/a | n/a | Antonio DeMendonca | 54308
T-0328/S0973 | Shaula I | DeWitt | Switchyard designed and built to connect the Shaula I solar photovotaic generation. 345kv transmission loop. | 2023-05-05 | 2024-11-21 | n/a | $7.9M | n/a | n/a | n/a | 0% | 345 | 345 | 0.1 | Bundled 795 Kcmil ACSR | Single Circuit Steel Structures | 100 | 0.1 | n/a | n/a | Darcy Ralston | 25.101.(c)(5)(A)
T-0334/S-0976 | Ebony BESS | Bexar | Install a Gen-Tie to Plus Power Ebony Battery Energy Storage System (BESS). | 2023-11-16 | 2023-11-16 | n/a | $2.3M | n/a | n/a | n/a | n/a | 138 | 138 | 0.01 | Single 795 Kcmil ACSS/TW | Single Circuit Steel Structures | n/a | n/a | 50 | 0.01 | Darcy Ralston | 25.101.(c)(5)(A)