## Sheet1
Aqua Water Supply Corporation
Distribution System Improvement Projects Under Construction
Project Name | Project Description | Project Location | Start Date | Estimate End Date | Project Completion Percentage | Estimated Project Costs
Bartsch Lane Improvement Project | Project to connect Sand Hills Road distribution to Basrtch Lane to improve system pressure. 3,086 LF 6" PVC water line. | Intersection of Bartsch Lane and Sand Hills Road in Red Rock, Texas. | 2022-07-20 | 2022-08-20 | 1% | 208465.5
24" New Sweden Transmission Main | Project to transmit water from east to west within the County Line Pressure Plane to serve new development. 27,344 LF 24" ductile iron water line. | From Giese Lane to New Sweden Church Road (along Manda Road and Jacobson Road) in Manor, Texas. | 2022-04-01 | 2022-10-28 | 5% | 5554032.5
FM 1854 12" Water Transmission Main | Project to connect the Pittman Pump Station to the Pittman Elevated Storage Tank. 37,774 LF 12" PVC water line. | From HWY 21 to FM 1854 (along Lytton Lane and Tamahawk Trail) in Dale, Texas. | 2022-01-25 | 2023-01-15 | 12% | 4334967.75
Pittman Elevated Storage Tank | 0.5 MG Elevated Storage Tank to serve future development near FM 1854. | 10546 FM 1854 in Dale, Texas. | 2021-11-01 | 2022-09-27 | 65% | 1857852.82
Pittman Pump Station | Project to install a pump station equipped to pump water from the Texas Hill Pressure Plane to the Pittman Pressure Plane. | 3350 Lytton Lane in Dale, Texas. | 2022-07-11 | 2023-04-22 | 5% | 1860264