## UPSHUR (hidden)
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 0 | 0
[24 empty] | 0 | 0 | 0 | Project Count
[24 empty] | Completed | Active | Total

## NEW3 (hidden)
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 0 | 0
[24 empty] | 0 | 0 | 0 | Project Count
[24 empty] | Completed | Active | Total

## NEW4 (hidden)
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 0 | 0
[24 empty] | 0 | 0 | 0 | Project Count
[24 empty] | Completed | Active | Total

## NEW (hidden)
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 0 | 0
[24 empty] | 0 | 0 | 0 | Project Count
[24 empty] | Completed | Active | Total

## 4.12.2023
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) | Last Month: | Current minus last month: | Cumulative Sum
LST2020001 | Reata Station to Roadrunner Crossing Wind 345 kV Transmission Line Project | Eastland | Construction of the new Reata 345 kV Station and new 2.3-mile 345 kV transmission line to the Roadrunner Crossing Wind, LLC collector station | 2022-02-01 |  | 2023-04-07 | Transmission Line Costs - $3,420,000; Station Costs - $21,560,000 | Transmission Line Costs - $6,340,000; Station Costs - $18,100,000 |  |  | 99% | 345 | 345 | 1 | Twin-bundled 795 kcmil "Drake" ACSR | Pre-stressed spun concrete poles | NA | NA | 100-150 | 1 | 50910; PURA sec. 37.052(c)(1)(B) | Project was rescheduled due to customer change in in-service date. Construction of the Reata Station commenced on Feb. 1, 2022. Construction of the Reata to Roadrunner transmission line will commence in Sept. 2022. Line length has been shortened from 2.3 miles to 1 mile with agreement of all directly affected landowners.
LST2021002 | Liberty Station and Transmission Line Extension Project | Hill | Construction of new 345 kV Liberty Station and new 0.8-mile 345 kV transmission line extension from end of existing Sam Switch to Hubbard Wind 345 kV Transmission Line to the Liberty Station | 2022-01-17 |  | 2022-11-17 |  | Transmission Line - $1,522,200 Station Facilities - $15,072,900 |  |  | 99% | 345 | 345 | 0.8 | Twin-bundled 1590 kcmil "Falcon" ACSR | Pre-stressed spun concrete and steel poles | NA | NA | 150-200 | 0.8 | 25.101(c)(2) 25.101(c)(5)(A) 25.83(c) 25.198 | Extension of existing Sam Switch to Hubbard 345 kV Transmission Line to new Liberty 345 kV Station, which will interconnect both the Hubbard Wind and Waco Solar generation facilities.
LST2021003 | Liberty to Waco Solar 345 kV Transmission Line Project | Hill and Limestone | Construction of new, 3-mile 345 kV single circuit transmission line from Liberty Station to Waco Solar, LLC-owned collector station and interconnection facilities at Liberty Station; project to interconnect Waco Solar, LLC | 2022-06-01 |  | 2022-11-17 | Transmission Line Costs - $4,890,000; Station Costs - $1,660,000 | Transmission Line Costs - $4,890,000; Station Costs - $1,660,000 |  |  | 99% | 345 | 345 | 3 | Twin-bundled 1590 kcmil "Falcon" ACSR | Pre-stressed spun concrete and steel poles | NA | NA | 150-200 | 3 | 52853 | CCN Notice of Approval issued 03/28/2022
LST2021004 | Reata to Century Oak Wind 345 kV Transmission Line Project | Eastland and Callahan | Construction of new, 3.6-mile 345 kV single circuit transmission line from Reata Station to Century Oak Wind, LLC-owned collector station and interconnection facilities at Reata Station; project to interconnect Century Oak Wind, LLC | 2022-10-01 |  |  | Transmission Line Costs - $5,081,000; Station Costs - $5,180,000 | Transmission Line Costs - $3,630,000; Station Costs - $13,370,000 |  |  | 75% | 345 | 345 | 3.6 | Twin-bundled 795 kcmil "Drake" ACSR | Pre-stressed spun concrete and steel poles | NA | NA | 100-150 | 3.6 | 52854 | CCN Notice of Approval issued 03/25/2022; construction start date for the transmission line adjusted to October 2022; percentage complete reflects construction progress of Reata Station
LST2022001 | Navarro to Lefty Data Center 345 kV Transmission Line Project | Navarro | Construction of new 345kV Navarro Station upgrades and new 0.1-mile 345 kV single circuit transmission line from Navarro Station to PPM Data, LLC-owned collector station | 2023-06-26 |  |  |  | Transmission Line Costs - $2,010,000; Station Costs - $2,660,000 |  |  | 0% | 345 | 345 | 0.1 | Twin-bundled 1590 kcmil "Falcon" ACSR | Pre-stressed spun concrete and steel poles | NA | NA | 100-150 | 0.1 | 25.101(c)(2) 25.101(c)(5)(A)(I) 25.83(c) | Adding a breaker, CVT, and line exit at Navarro Station and 937 feet of new 345 kV transmission line to connect interconnection customer; all work will occur on Lone Star's or the customer's property