## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
21038 | Flat Rock Switch-Flat Rock Rebuild | Parker | Rebuild 4.15 miles of double circuit, single pole from Flat Rock Switch to Flat Rock | 2022-04-01 |  | 2022-11-22 | 3719635 | 3719635 |  |  | 0% | 138 | 138 | 4.15 | 1926.9 ACSS/TW | Single Pole Concrete or Steel | 70 | 4.15 | 0 | 0 | 25.101(c)(5)(D) | Affidavit to be filed upon request
1904810 | Hilltop-West Weatherford Rebuild | Parker | Rebuild 12.93 miles of single pole, double circuit from Hilltop Substation to West Weatherford Substation | 2022-09-19 |  |  | 9817000 | 12568116.69 |  |  | 85% | 138 | 138 | 12.93 | 1433 ACSS/TW | Single Pole Concrete or Steel | 60 | 12.93 | 0 | 0 | 25.101(c)(5)(B) | Affidavit to be filed upon request
1902510 | India-DWU Southside Rebuild | Dallas/ Ellis | Rebuild 10.11 miles of single pole, single circuit from India Substation to DWU Southside Substation | 2022-10-24 |  |  | 6950000 | 13798344.88 |  |  | 60% | 69 | 138 | 10.11 | 1433 ACSS/TW | Single Pole Concrete or Steel | 60 | 10.11 | 0 | 0 | 25.101(c)(5)(B) | Affidavit to be filed upon request
20025 | Bosque Transmission | McLennan | Construction and removal of temporary shoo fly needed to perform work at Bosque substation | 2022-09-12 |  |  | 400000 |  |  |  | 50% | 138 |  | 0.35 | 795 ACSR | Wood H-Frames | NA | NA | NA | NA | 25.83(a)(3) | Affidavit to be filed upon request
17016 | Windsor Switch Transmission | McLennan | Construction and removal of temporary shoo fly needed to perform work at Windsor Switch Station | 2022-09-19 |  |  | 550000 | 1078297.72 |  |  | 60% | 138 |  | 0.28 | 795 ACSR | Wood H-Frames | NA | NA | NA | NA | 25.83(a)(3) | Affidavit to be filed upon request
19014 | Downing Transmission | Comanche | Remove existing steel deadend and install new single pole deadend and HF1 tower at Downing Substation | 2023-04-24 |  |  | 600000 | 747738.5 |  |  | 40% | 138 | 138 | 0.04 | 1033 ACSR | Single Pole Concrete or Steel | 60 | 0.04 | NA | NA | 25.101(c)(5)(A) | Affidavit to be filed upon request
19054 | Bankhead P.O.I. | Parker | Construct P.O.I. in the Hudson Oaks to Railroad 138kV line | 2023-01-16 |  |  | 1500000 | 1847603.57 |  |  | 95% | 138 | 138 | 0.15 | 795 ACSR | Single Pole Concrete or Steel | 60 | 0.15 | NA | NA | 25.101(c)(5)(A) | Affidavit to be filed upon request
1653003 | Sardis-Reagor Springs Reroute | Ellis | Re-route 1 mile of single pole, single circuit from Sardis Substation to Reagor Springs Substation | 2023-03-20 |  | 2023-05-11 | 1209585.6 | 1575762.67 |  |  | 90% | 138 | 138 | 1 | 959 ACSS/TW | Single Pole Concrete or Steel | 60 | 0.7 | 60 | 1 | 25.101 (C)(5)(D) | Affidavit to be filed upon request
216002 | Rector Rd to Denton North Line Mods | Denton | Remove and replace two structures to accommodate TxDOT's IH-35 widening | 2023-04-03 | 2023-05-02 | 2023-04-25 | 392056.8 | 431275 |  |  | 100% | 138 | 138 | 0.3 | 1033 ACSR | Single Pole Concrete or Steel | 60 | 0.3 | NA | NA | 25.101 (C)(5)(D) | Affidavit to be filed upon request
1004120 | Gibbs Transmission | Walker | Construct 0.11 miles of single circuit 138kV transmission line to connect Gibbs and ETEC substations |  |  |  | 374099.46 | 367741.46 |  |  | 0% | NA | 138 | 0.11 | 959 ACSS/TW | Single Pole Concrete or Steel | NA | NA | NA | NA | 25.101(c)(5)(A) | Affidavit to be filed upon request
19014 | Holder Line Mods | Brown | Rerouting two 138kV transmission lines into the Holder Substation, Rising Star-Holder and Holder - Brownwood. |  |  |  | 431715 |  |  |  | 0% | 138 | 138 | 0.21 | 959 ACSS/TW & 477 ACSR | Single Pole Concrete or Steel | 60 & 100 | 60 & 100 | NA | NA | 25.101(c)(5)(B) | Affidavit to be filed upon request
Note on H2: aboling: Please enter only a single integer, if possible.
Note on I2: aboling: Please enter only a single integer, if possible.
Note on M2: aboling: If applicable.
Note on N2: aboling: If applicable.