## LCRA TSC MCPR May 2023
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
1017348 | Cooks Point TL Addition (CCN) | Burleson | Construct a new 138-kV transmission line to provide a transmission point of interconnection to a new load-serving substation | 2020-07-01 | 2021-06-30 | 2021-06-30 | T-Line $ 26.5 - 34.1M; Substation $ 6.1 - 6.7M |  |  |  | 100 | 0 | 138 | 17-23 | 2x1- 795 ACSR "Drake" | TBD; Poles and/or H-Frames | 0 | 0 | Varies; 80 | 17-23 | 48358 | 6/17/19 - PUC Approved Route 12; approved route cost estimate in CCN application for transmission line $29M; substation $6.2M
1017394 | Mountain Home TL Addition (CCN) | Kerr, Gillespie | Construct a new 138-kV transmission line to provide a transmission point of interconnection to a new load-serving substation | 2021-08-27 | 2022-12-27 17:00 |  | T-line $46.5 - $58.5M; Substation $7.1 - $7.5M |  |  |  | 100 | 0 | 138 | 21-29 | 795 Kcl 26/7 ACSR “Drake” | tbd; steel or concrete poles | 0 | 0 | varies; 100 | 21-29 | 49523 | 7/6/20 - PUC Approved Route Hunt 37A; approved route cost estimate in CCN application for transmission line $47M; substation $7.3M
1019114 | Zorn - Pooley Rd TL Addition (T158) [Luling-Zorn TL Overhaul - 1019113] | Guadalupe | Increase the reliability of transmission facilities on the T373 Schulenburg - Glidden 20.25- | 2020-02-03 | 2021-08-31 | 2021-05-06 |  | 7228000 |  |  | 100 | 138 | 138 | 28.02 | 795 ACSR Drake | Concrete and Steel poles | 100 | 28.02 | n/a | 28.02 | 25.101 (C)(5)(B)
1019285 | T271 TL Addition (T271) [Pinnacle Substation Addition - 1019007] | Culberson | LCRA TSC will build a new substation (Pinnacle) adjacent to T271 to interconnect the new 186.3 MW solar generation facility. Replace transmission structures to allow for substation cut-in and upgraded conductor and OPGW. | 2020-01-29 | 2020-10-14 17:00 | 2020-10-14 17:00 |  | 10800000 |  |  | 100 | 69 | 138 | 18.1 | Single 1433 ACSS/TW Merrimack | Steel monopole | 100 | 18.1 | 100 | n/a | 25.101 (C)(5)(B)
1023677 | Asherton - Bevo TL Addition (T603) [Asherton - Bevo TL Relocation - 1022882] | Dimmit | Relocate dead-end structure #1 on the T603 Bevo to Asherton 138-kV transmission line to outside of the AEP-owned Asherton Substation. Re-route and re-ternate T603 to a new point-of-interconnection (POI) structure owned by AEP and installed by AEP outside of the Asherton Substation. | 2022-02-07 | 2022-04-01 | 2022-04-01 |  | 447000 | 523916 | 17.21% | 100 | 138 | 138 | 8.05 | (1) 795 Drake ACSR | Steel monopoles | AEP owned | AEP owned | AEP owned | AEP owned | 25.101 (C)(5)(B)
1023668 | Gabriel - Glasscock TL Addition (T359) [Gabriel Substation Upgrade - 1020410] | Williamson | LCRA TSC will upgrade the configuration of 138-kV from Single Bus/Single Breaker to the breaker and a half bus configuration and replace five existing CBs at Gabriel Substation. | 2021-05-19 | 2022-05-13 | 2022-05-13 |  | 361000 | 353715.61 | -2.018% | 100 | 138 | 138 | 6.59 | Single 795 ACSR Drake | Steel Pole | 80 | 6.59 | n/a | n/a | 25.101 (C)(5)(B)
1021176 | Gabriel - Jarrell TL Addition (T224) [Gabriel Substation Upgrade - 1020410] | Williamson | Upgrade the configuration of 138-kV from Single Bus/Single Breaker to the breaker and a half bus configuration and replace five existing CBs at Gabriel Substation. | 2020-08-17 | 2022-05-13 | 2022-05-13 |  | 1083000 | 1051753.6 | -2.885% | 100 | 138 | 138 | 1.26 | Single 795 ACSR Drake | Steel Pole | 60 | 1.26 | n/a | n/a | 25.101 (C)(5)(B)
1021174 | Gabriel - Georgetown East TL Addition (T223) [Gabriel Substation Upgrade - 1020410] | Williamson | Upgrade the configuration of 138-kV from Single Bus/Single Breaker to the breaker and a half bus configuration and replace five existing CBs at Gabriel Substation. | 2020-08-17 | 2022-05-13 | 2022-05-13 |  | 1083000 | 1082134.2 | -0.07994% | 100 | 138 | 138 | 1.26 | Single 795 ACSR Drake | Steel Pole | 60 | 1.26 | n/a | n/a | 25.101 (C)(5)(B)
1023667 | Gabriel - Rivery TL Addition (T457) [Gabriel Substation Upgrade - 1020410] | Williamson | Upgrade the configuration of 138-kV from Single Bus/Single Breaker to the breaker and a half bus configuration and replace five existing CBs at Gabriel Substation. | 2021-05-19 | 2022-05-13 | 2022-05-13 |  | 361000 | 363243.9 | 0.6216% | 100 | 138 | 138 | 2.43 | Bundled 795 ACSR Drake | Steel Pole | Varies | 2.43 | n/a | n/a | 25.101 (C)(5)(B)
1021428 | Sherwood Shores - Coronado TL Addition (T635) [Coronado-Sherwood Shores TL SH - 1021211] | Burnet | Increase the reliability of circuit T635 on the Coronado – Sherwood Shores 12.2-le 138-kV transmission line | 2021-09-16 | 2022-05-11 | 2022-05-11 |  | 12145000 | 15665771.38 | 28.99% | 100 | 138 | 138 | 12.15 | Single 795 Drake ACSR | Steel Poles/Steel Lattice | Centerline | 12.15 | n/a | n/a | 25.101 (C)(5)(B)
1021973 | T723 Motorman-Upton TL Addition (T723) [Motorman Substation Addition - 1021552] | Upton, Crane | Construct a 3-breaker ring bus cut in to the existing T441 Crane East to Upton 138-kV transmission line. | 2022-02-07 | 2022-06-09 | 2022-06-29 |  | 679000 |  |  | 100 | 138 | 138 | 17.97 | 1233.6 Yukon ACSS/TW & Single | Concrete Pole | Centerline; 80 | 17.97 | Centerline; 80 | n/a | 25.101 (C)(5)(A)
1023799 | T441 LCRA Crane-Motorman TL Addition (T441) [Motorman Substation Addition - 1021552] | Upton, Crane | Construct a 3-breaker ring bus cut in to the existing T441 Crane East to Upton 138-kV transmission line. | 2022-02-07 | 2022-06-09 | 2022-06-29 |  | 16000 |  |  | 100 | 138 | 138 | 12.16 | 1233.6 Yukon ACSS/TW & Single | Concrete Pole | Centerline; 80 | 30.14 | Centerline; 80 | n/a | 25.101 (C)(5)(A)
1022221 | T635 TL Addition [LCRA Fiber Backbone FY20 - 1021196] | Burnet, Llano | Increase the reliability of the fiber network by replacing deteriorated OPGW and All-Dielectric Self -Supporting (ADSS) fiber to improve telecommunications system reliability. | 2021-09-16 | 2022-05-06 | 2022-05-06 |  | 821000 |  |  | 100 | 138 | 138 | 12.15 | Single 795 ACSR Drake | Steel Monopole | Centerline | 12.15 | n/a | n/a | 25.101 (C)(5)(B)
1024192 | Gilleland-Silicon Hill TL Addition (T734) [Gilleland Creek Circuit Breaker Addition - 1024005] | Travis | Upgrade 138-kV bay to breaker-and-a-half to accommodate new circuit termination. | 2021-01-04 | 2022-06-30 | 2021-05-13 |  | 389000 | 262181.52 | -32.6% | 100 | 138 | 138 | .04 | 795 ACSR | Steel DE Monopole | 80' | n/a | 80' | n/a (POI) | 25.101 (C)(5)(A)
1020856 | Clearfork-Robert Brown TL Addition (T519) [Clear Fork-Robert Brown Jr TL Overhaul - 1020855] | Caldwell | Increase the reliability and capability of circuit T519 on the Clear Fork – Robert Brown Jr 8.8-mile 69-kV transmission line. | 2021-11-15 | 2022-04-19 | 2022-04-19 |  | 7550000 |  |  | 100 | 69 | 138 | 8.75 | (2)959.6kcmil ACSS/TW/HS "Suwannee" | Steel Monopole | Centerline | 8.75 | 80 | 8.75 | 25.101 (C)(5)(B) | ROW per Easement Enhancement FY19 System Upgrade - 1019090
1023652 | Hilltop-RR 12 TL Addition (T375) [Hilltop - Ranch Road 12 TL Upgrade - 1023190] | Hays | Increase the reliability of transmission facilities on the T375: Hilltop – Ranch Road 12 3.95-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. | 2021-09-20 | 2022-06-30 | 2022-05-18 |  | 9300000 |  |  | 100 | 138 | 138 | 3.97 | 3x1 ~ 1433.6 ACSS/TW "Merrimack" | Steel Poles | Varies | 3.97 | n/a | n/a | 25.101 (C)(5)(B)
1020868 | TurtleCreek-VerdeCreek TL Addition (T221) [Turtle Crk-Verde Crk TL OH-1020867] | Kerr | Increase the reliability of transmission facilities on the T221 Turtle Creek – Verde Creek 10.3-mile 138-kV transmission line. | 2021-08-01 | 2022-09-26 | 2022-03-26 |  | 8851000 | 7151630.28 | -19.2% | 100 | 138 | 138 | 10.26 | Single 795 ACSR "Drake" & DNO-11243 OPGW & 3/8 EHS Static Wire | Steel Monopoles | 100, Meets & Bounds | 10.26 | n/a | n/a | 25.101 (C)(5)(B)
1024946 | Plum-Muldoon TL Addition (T133) [Muldoon Substation Addition - 1024679] | Fayette | New three breaker ring bus substation to provide a 138-kV line termination for a 240 MW solar generation facility. | 2022-11-18 | 2023-01-13 | 2023-01-13 |  | 6400000 |  |  | 100 | 138 | 138 | 11.07 | (1) 959.6 ACSS/TW "Suwannee" (1) DNO-11243 (1) 3/8" EHS & (1) 3/8" HS | Steel poles, H-frames, Lattice tower | 100 | 19.64 | n/a | n/a | 25.101 (C)(5)(A)
1020123 | Magnolia Mercer-Luling TL Addition (T701) [Magnolia Mercer CB Addition - 1018915] | Caldwell | Increase the reliability of substation equipment at the Magnolia Mercer Substation | 2021-10-01 | 2022-04-21 | 2022-04-21 |  | 186000 | 25530.47 | -86.27% | 100 | 69 | 138 | 15.83 | (1) 795 ACSR /GA2 "Drake" Conductor (1) DNO-11243 Shield Wire | Wood H-frames, Tower | Centerline | 15.83 | n/a | n/a | 25.101 (C)(5)(B)
1019178 | Luling-Mercer TL Addition (T157) [Magnolia Mercer CB Addition - 1018915] | Caldwell | Increase the reliability of substation equipment at the Magnolia Mercer Substation | 2021-10-01 | 2022-04-21 | 2022-04-21 |  | 557000 | 660335.31 | 18.55% | 100 | 69 | 69 | 15.83 | (1) 336 ACSR "Linnet" Conductor (1) 4/0 ACSR "Penguin" Shield Wire | Tower | Centerline | 15.83 | n/a | n/a | 25.101 (C)(5)(B)
1019331 | Schulenburg-Glidden TL Addition (T373) [LCRA TSC FIBER BUILD OUT FY19 - 1019097] | Fayette, Colorado | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2021-11-03 | 2022-03-25 | 2022-03-25 |  | 6500000 | 9411858.15 | 44.8% | 100 | 138 | 138 | 7.57 | (1) 795 ACSR "Drake" (1) DNO-11243 (1) 3/8" EHS STEEL | Steel, Concrete, and Hybrid Monopoles | Blanket; 20 | 7.57 | n/a | 7.57 | 25.101 (C)(5)(B)
1023940 | Weimar-Glidden TL Addition(T704) [LCRA TSC Fiber Build Out FY19 - 1019097] | Colorado | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2022-09-15 | 2023-06-30 |  |  | 8646000 |  |  | 80 | 138 | 138 | 12.86 | (1) 795 ACSR "Drake" (1) DNO-11243 (1) 3/8" EHS STEEL | Steel, Concrete, and Hybrid Monopoles | Blanket; 20 | 12.86 | n/a | 12.86 | 25.101 (C)(5)(B)
1024827 | Cedar Canyon-HiLonesm BESS TL Addition (T741) [Cedar Canyon Circuit Breaker Addition - 1024678] | Iraan, Crockett | This project provides a point of interconnection for a new 50.6 MW Battery Energy Storage at the 345-kV Cedar Canyon Substation by adding a new bay into a double bus/double breaker configuration to accommodate the new interconnection. | 2022-04-11 | 2022-05-02 | 2022-05-02 |  | 702000 | 497220.4 | -29.17% | 100 | n/a | 345 | <1mi (374ft) | Bundled 959 Suwannee | Steel Monopole | n/a | n/a | 200 X 200 plot | 200' X 200 plot | 25.101 (C)(5)(A)
1023353 | King Mountain - Crane II TL Addition (T732) [King Mountain Substation Upgrade - 1023073] | Crane | Provide transmission service to a generator. Add a 138-kV bay and associated circuit breaker to the existing substation. | 2021-12-01 | 2023-06-15 |  |  | 2301000 |  |  | 95 | n/a | 138 | 0.13 | (1) 959.6 KCMIL ACSS "Suwannee" | Steel Monopole | n/a | n/a | 80 | 0.13 | 25.101 (C)(5)(A)
1020853 | San Marcos-Robert Brown TL Addition (T220) [Robert Brown Jr-San Marcos TL Overhaul -1020852] | Hays, Caldwell | Increase the reliability and capability of circuit T220 on the Robert Brown Jr – San Marcos 4.91-mile 69-kV transmission line. | 2022-04-19 | 2022-07-29 |  |  | 5187000 |  |  | 100 | 69 | 138 | 4.9 | (2)959.6 ACSS/TW/HS "Suwannee" (2)995.0 T13 ACSS/TW/C7-TP (1)AFL DNO-11243 | Steel Monopole | Varies | 4.9 | 100 | 4.9 | 25.101 (C)(5)(B)
1019323 | Flatonia-Schulenburg TL Addition (T112) [LCRA TSC Fiber Build Out FY19 - 1019097] | Fayette | Increase the reliability and capability of the fiber network by adding Optical Grounding Wire (OPGW) and related telecommunications equipment. | 2021-12-01 | 2023-06-29 |  |  | 7300000 |  |  | 65 | 138 | 138 | 11.99 | (1) 795 ACSR "Drake" | Steel Poles | 100 CL/ Blanket | 11.92 | n/a | n/a | 25.101 (C)(5)(B)
1026973 | Coronado-Buchanan TL Addition (T107) [FY22 G-T107 Coronado-Buch Fbr Repl - 1026972] | Burnet | Replace existing OPGW on T107 between STR's #137 to #138A and the underground fiber from STR#138A to Buchanan Plant with updated 72-count standard all dielectric fiber cable. | 2021-12-01 | 2022-04-08 | 2022-04-08 |  | 246000 | 141446.49 | -42.5% | 100 | 69 | 69 | 2.35 | (1) 795 ACSR Drake | Lattice, H-frame | M&B 190/CL100/Blanket | 2.35 | n/a | n/a | 25.101 (C)(5)(B)
1024711 | HiCross-Marshall Ford TL Addition (T142) [HiCross-Marshall Ford Transmission Line Relocation - 1024589] | Travis | Relocate LCRA TSC elements on the T142 Hi Cross – Marshall Ford 138-kV transmission line that cross Austin Energy (AEN) bus work at Barton and Salem Walk substations. | 2023-03-01 | 2023-05-15 |  |  | 1616000 |  |  | 0 | 138 | 138 | 16.5 | (1) 1433.6 ACSS/TW Merrimack | Steel Poles, Steel H-Frames, Lattice Towers | 100 | 16.5 | n/a | n/a | 25.101 (C)(5)(E)
1025540 | Kendall-Mountain Top TL Addition (T342) [Kendall - Mountain Top Fiber Restoration and Upgrade -1025820] | Blanco, Kendall | Upgrade the T342 Optical Ground Wire (OPGW) between Kendall Substation (S241) and Mountaintop (PEC) Substation (S265)to improve reliability and capacity of the subtending CREZ East Fiber Route. | 2022-02-07 | 2022-04-29 | 2022-04-27 |  | 4562000 |  |  | 100 | 138 | 138 | 43.62 | (1) 1433.6 ACSS/TW Merrimack | Steel Poles | 100 , Centerline | 43.62 | n/a | n/a | 25.101 (C)(5)(B) | The Costs associated with this project have moved from the Failed Equipment project to a Capital Improvement Project.
1025066 | Hunt-Ingram SH TL Addition (T487/T521) [Hunt - Ingram TL Storm Hardening - 1024843] | Kerr | LCRA TSC will perform a Storm Hardening on structures and conductors on the 6.4-mile Hunt – Ingram (T487) transmission line | 2022-08-22 | 2023-05-15 |  |  | 11900000 |  |  | 70 | 138 | 138 | 4.48 | (1) 959.6 ACSS SUWANNEE | Steel Monopole | Varies 60, 100 | 4.48 | n/a | n/a | 25.101 (C)(5)(B)
1025028 | HarperRd-Jack Frmn TL Addition (T368) [Harper Road - Jack Furman TL Storm Hardening - 1024842] | Kerr | LCRA TSC will perform a Storm Hardening on structures and conductors on the 6.4-mile Hunt – Ingram (T487) transmission line | 2022-08-22 | 2023-01-05 | 2023-01-18 |  | 4500000 |  |  | 95 | 138 | 138 | 4.64 | (1) 959.6 ACSS SUWANNEE | Steel Monopole | Varies (100, 80, 20) | 4.64 | n/a | n/a | 25.101 (C)(5)(B)
1025059 | Ingram-Jack Furman Storm Hardening TL Addition (T521) [Ingram - Jack Furman TL Storm Hardening - 1024844] | Kerr | LCRA TSC will perform a Storm Hardening on structures and conductors on the 6.4-mile Hunt – Ingram (T487) transmission line | 2022-08-22 | 2023-02-15 |  |  | 3000000 |  |  | 20 | 138 | 138 | 3.25 | (1) 959.6 ACSS SUWANNEE | Steel Monopole | Varies | 3.25 | n/a | n/a | 25.101 (C)(5)(B)
1025008 | Buchanan-Buchanan CTEC TL Addition (T106) [Buchanan (CTEC) - Buchanan TL Overhaul - 1024835] | Llano County | Increase reliability of the structures and conductor | 2022-02-14 | 2022-06-06 |  |  | 7500000 |  |  | 100 | 69 | 69 | 2.8 | (1) 336.4 ACSR LINNET (1) 959.6 ACSS SUWANNEE | Steel Lattice Tower/ Steel Monopole | M&B/100 | 2.8 | n/a | n/a | 25.101 (C)(5)(B)
1025479 | Bakersfield Substation Addition [Bakersfield-Big Hill TL Addition - 1024834] | Pecos County | Upgrade substation equipment to interconnect another TSP’s 345-kV circuit from Big Hill to Bakersfield | 2022-11-28 | 2023-06-15 |  |  | 593800 |  |  | 95 | 345 | 345 | n/a | n/a | A-Frame | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B)
1025502 | Cedar Canyon Substation Addition [Bakersfield-Big Hill TL Addition - 1024834] | Crockett County | Upgrade substation equipment to interconnect another TSP’s 345-kV circuit from Big Hill to Bakersfield | 2022-03-07 | 2024-05-15 |  |  | 634000 |  |  | 8 | 345 | 345 | n/a | n/a | A-Frame | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B)
1025506 | Noelke Substation Addition [Bakersfield-Big Hill TL Addition - 1024834] | Crockett County | Upgrade substation equipment to interconnect another TSP’s 345-kV circuit from Big Hill to Bakersfield | 2022-08-01 | 2023-10-31 |  |  | 728000 |  |  | 80 | 345 | 345 | n/a | n/a | A-Frame | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B)
1025507 | Schneeman Draw Substation Addition [Bakersfield-Big Hill TL Addition - 1024834] | Schleicher County | Upgrade substation equipment to interconnect another TSP’s 345-kV circuit from Big Hill to Bakersfield | 2022-03-07 | 2023-06-15 |  |  | 960000 |  |  | 80 | 345 | 345 | n/a | n/a | A-Frame | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B)
1025509 | Big Hill Substation Addition [Bakersfield-Big Hill TL Addition - 1024834] | Schleicher County | Upgrade substation equipment to interconnect another TSP’s 345-kV circuit from Big Hill to Bakersfield | 2022-02-01 | 2023-06-15 |  |  | 1220000 |  |  | 80 | 345 | 345 | n/a | n/a | A-Frame | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B)
1026453 | Austrop-Garfield TL Addition (T182) [TL Clearance Mitigation FY22 - 1025813] | Bastrop | Strengthen structures to support clearance mitigation. | 2022-03-29 | 2022-05-10 | 2022-05-10 |  | 375000 |  |  | 100 | 345 | 345 | 8.34 | (2) 795 DRAKE ACSR | Lattice Tower | 170 | 8.34 | n/a | n/a | 25.101 (C)(5)(B)
1026454 | Garfield-Lytton Spg TL Addition (T352) [TL Clearance Mitigation FY22 - 1025813] | Bastrop | Strengthen structures to support clearance mitigation. | 2022-03-29 | 2022-05-10 | 2022-05-10 |  | 375000 |  |  | 100 | 345 | 345 | 12.31 | (2) 795 DRAKE ACSR | Lattice Tower | 170 | 12.31 | n/a | n/a | 25.101 (C)(5)(B)
1026455 | Lytton Spg-Zorn TL Addition (T246) [TL Clearance Mitigation FY22 - 1025813] | Bastrop | Strengthen structures to support clearance mitigation. | 2022-03-29 | 2022-05-10 | 2022-05-10 |  | 375000 |  |  | 100 | 345 | 345 | 23.05 | (2) 795 DRAKE ACSR | Lattice Tower | 170 | 23.05 | n/a | n/a | 25.101 (C)(5)(B)
1026445 | Austrop-Zorn TL Addition (T185) [TL Clearance Mitigation FY22 - 1025813] | Bastrop | Strengthen structures to support clearance mitigation. | 2022-03-29 | 2022-05-15 | 2022-05-10 |  | 375000 |  |  | 100 | 345 | 345 | 43.75 | (2) 795 DRAKE ACSR | Lattice Tower | 170 | 43.75 | n/a | n/a | 25.101 (C)(5)(B)
1026823 | Harwood-Bluestem TL Addition (T145) [Bluestem Substation Addition - 1023910] | Gonzales | Construct the new 69-kV (138-kV capable) Bluestem Substation with a 3-breaker ring bus configuration off the T145 Harwood – Thompsonville– Waelder transmission line | 2022-02-12 | 2022-06-16 | 2022-06-16 |  | 106000 |  |  | 100 | 138 | 138 | 13.53 | (1) 795 DRAKE ACSR | Steel Monopole | 100 | 13.53 | n/a | n/a | 25.101 (C)(5)(A)
1026825 | Bluestem-Delhi TL Addition (T748) [Bluestem Substation Addition - 1023910] | Gonzales | Construct the new 69-kV (138-kV capable) Bluestem Substation with a 3-breaker ring bus configuration off the T145 Harwood – Thompsonville– Waelder transmission line | 2022-02-12 | 2022-06-16 | 2022-06-16 |  | 139000 |  |  | 100 | 138 | 138 | 0.04 | (1) 795 DRAKE ACSR | Steel Monopole | 100 | 0.04 | n/a | n/a | 25.101 (C)(5)(A)
1026824 | Bluestem-Thompsonville (T749) TL Addition [Bluestem Substation Addition - 1023910] | Gonzales | Construct the new 69-kV (138-kV capable) Bluestem Substation with a 3-breaker ring bus configuration off the T145 Harwood – Thompsonville– Waelder transmission line | 2022-02-12 | 2022-06-16 | 2022-06-16 |  | 139000 |  |  | 100 | 138 | 138 | 8.27 | (1) 795 DRAKE ACSR | Steel Monopole | 100 | 8.27 | n/a | n/a | 25.101 (C)(5)(A)
1020862 | Lockhart - Red Rock TL Addition (T578) [Lockhart - Red Rock TL Overhaul - 1020861] | Bastrop, Caldwell | Increase the reliability of transmission facilities on the T578 Lockhart structure #301- Red Rock 11.3 mile 138-kV transmission line | 2023-01-03 | 2023-05-15 |  |  | 13500000 |  |  | 90 | 138 | 138 | 17.1 | (1) 959.6 ACSS/TW/MA3 "SUWANNEE" | Steel Monopole | 100 | 17.1 | n/a | n/a | 25.101 (C)(5)(B)
1020469 | Gonzales - Hocheim TL Addition (T542) [Gonzales - Hocheim TL Overhaul - 1020411] | Gonzales, Dewitt | Tear down and rebuild of the 19.3 mile section. Replace wood structures with concrete and steel structures and 795 ASCR "Drake" and DNO-11243 fiber. | 2022-06-15 | 2023-04-06 | 2023-04-06 |  | 24900000 |  |  | 100 | 69 | 69 | 53.4 | (1) 2/0 QUAIL ACSR (1) 795 DRAKE ACSR | Steel Monopole | Blanket, Varies | 53.4 | n/a | n/a | 25.101 (C)(5)(B)
1027309 | Schkade Fiber TL Addition (T429) [GA FY22-Schkade Fbr Add-1027306] | Tom Green | Replace existing telecom systems used for transmission operations functionality at Schkade Substation | 2022-05-02 | 2023-01-13 |  |  | 180000 | 69542.11 | -61.37% | 100 | 138 | 138 | 16.82 | (2) 795 ACSR "DRAKE" | Steel Poles | Centerline, 80 | 16.82 | n/a | n/a | 25.101 (C)(5)(B)
1024787 | Bastrop W-Split TL Addition (T410) [Bastrop West-Split T410 TL SH - 1024579] | Bastrop | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2023-04-28 |  |  | 3507000 |  |  | 95 | 138 | 138 | 2.37 | (1) 959.6 ACSS/TW/MA3 "SUWANNEE" | Steel Poles | Centerline, 100 | 2.37 | n/a | n/a | 25.101 (C)(5)(B)
1024720 | Sim Gideon-Tahitian Village TL Addition (T648) Phase 1 [Sim Gideon - Tahitian Village TL Storm Hardening - 1024600] | Bastrop | Phase 1: Storm Hardening of T648 from the Bastrop Split (old STR#27) to Sim Gideon | 2022-07-01 | 2023-12-31 |  |  | 9483000 |  |  | 10 | 138 | 138 | 5.05 | (1) 959.6 ACSS/TW/MA3 "SUWANNEE" | Steel Poles | Varies, 100, 150, 200 | 5.05 | n/a | n/a | 25.101 (C)(5)(B)
1028936 | BWSplit-Tahitian Village TL Addition (T648) Phase 2 [Sim Gideon-Tahitian Village TL SH - 1024600] | Bastrop | Phase 2 Storm Hardening of T648 from the Bastrop Split (old STR#27) to Tahitian Village | 2022-07-01 | 2022-12-30 |  |  | 1293000 |  |  | 100 | 138 | 138 | 5.05 | (1) 959.6 ACSS/TW/MA3 "SUWANNEE" | Steel Poles | Varies, 100, 150, 200 | 5.05 | n/a | n/a | 25.101 (C)(5)(B) | Project work split into two phases - entire circuit was noticed and reported on February 2022 MCPR
1025803 | BWSplit-Sim GideonTL Addition (T410) [Sim Gideon - Tahitian Village TL Storm Hardening - 1024600] | Bastrop | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2023-04-28 |  |  | 3464000 |  |  | 10 | 138 | 138 | 4.37 | (1) 959.6 ACSS/TW/MA3 "SUWANNEE" | Steel Poles | Varies, 100, 150, 200 | 4.37 | n/a | n/a | 25.101 (C)(5)(B)
1022978 | Lockhart-Luling TL Addition (T184) [Lockhart-Luling TL Overhaul - 1022800] | Bastrop, Caldwell | Increase the reliability of transmission facilities on the T184 Lockhart structure #301 - Luling 10.9 mile 138-kV transmission line. | 2023-02-01 | 2023-05-15 |  |  | 1438000 |  |  | 80 | 138 | 138 | 11.1 | 3X1 795 ACSR Drake | Wood H-Frame | 85 & 100 | 11.1 | n/a | n/a | 25.101 (C)(5)(B)
1027663 | Settlers Substation Addition Ph. 1 [Settlers Substation Addition -1027353] | Bastrop, Travis | Construct a temporary hard tap on the LCRA TSC's T171 Austrop to Sim Gideon and T231 Bastrop to Webberville transmission lines | 2023-04-24 | 2023-05-15 |  |  | 1393000 |  |  | 10 | (T171)(T231) 138 | (T171)(T231) 138 | (T171) 15.61 & (T231) 14.67 | (T171)(T231) 795 DRAKE ACSR (1) | (T171)(T231) Towers & Tower Poles | (T171)(T231) 125 | (T171) 15.61 & (T231) 14.67 | n/a | n/a | 25.101 (C)(5)(B)
1024727 | Antler-Bergheim TL Add (T493) [Antler-Bergheim Transmission Line Upgrade 1024576] | New Braunfels, Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2024-09-09 | 2024-12-12 |  |  | 9499000 |  |  | 0 | 138 | 138 | 7.17 | (2) 959.6 Suwannee/ACSS/TW/HS | Steel Monopole | 100 | 7.17 | n/a | n/a | 25.101 (C)(5)(B)
1024728 | Antler Flyover-Bergheim TL Add (T389) [Antler-Bergheim Transmission Line Upgrade 1024576] | New Braunfels, Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-11-28 | 2024-12-12 |  |  | 47554000 |  |  | 0 | 138 | 138 | 7.17 | (2) 1433.6 Merrimack/ACSS/TW/HS | Steel Monopole | 100 | 7.17 | n/a | n/a | 25.101 (C)(5)(B)
1024736 | Hays Energy-Henne Split Structure TL Addition (T389) [Hays Energy-Henne Split Transmission Line Upgrade - 1024587] | Hays, Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-11-28 | 2022-12-01 |  |  | 33708000 |  |  | 30 | 138 | 138 | 5.37 | (2) 1433.6 Merrimack/ACSS/TW/HS | Steel Monopole | 100 | 5.37 | n/a | n/a | 25.101 (C)(5)(B)
1024740 | Henne Split Structure-River Oaks Flyover TL Add (T389) [Henne-River Oaks Transmission Line Upgrade - 1024588] | Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-11-28 | 2022-12-01 |  |  | 9716000 |  |  | 10 | 138 | 138 | 2.28 | (2) 1433.6 Merrimack/ACSS/TW/HS | Steel Monopole | 100 | 2.28 | n/a | n/a | 25.101 (C)(5)(B)
1024738 | Henne-River Oaks (T237) TL Addition [Henne-River Oaks Transmission Line Upgrade - 1024588] | Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-09-01 | 2022-12-01 |  |  | 17754000 |  |  | 10 | 138 | 138 | 3.79 | (2) 959.6 Suwannee/ACSS/TW/HS | Steel Monopole | 100 | 3.79 | n/a | n/a | 25.101 (C)(5)(B)
1024743 | River Oaks Flyover-Hwy 46 Flyover TL Add (389) [Highway 46-River Oaks Transmission Line Upgrade - 1024590] | Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-09-01 | 2022-12-01 |  |  | 45392000 |  |  | 0 | 345 | 345 | 8.64 | (2) 1433.6 Merrimack/ACSS/TW/HS | Steel Monopole | 100 | 8.64 | n/a | n/a | 25.101 (C)(5)(B)
1024745 | River Oaks-Hwy 46 TL Addition (T518) [Highway 46-River Oaks Transmission Line Upgrade - 1024590] | Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-09-01 | 2022-12-01 |  |  | 8465000 |  |  | 0 | 138 | 138 | 8.64 | (2) 959.6 Suwannee/ACSS/TW/HS | Steel Monopole | 100 | 8.64 | n/a | n/a | 25.101 (C)(5)(B)
1027017 | Clear Springs Cir Bkr Add (T752) TL OH- 1027017 [Clear Springs Generator Circuit Breaker Addition - 1026518] | Seguin, Guadalupe | Upgrade the (S454) Clear Springs Substation to facilitate an interconnection project | 2022-07-19 | 2024-10-31 |  |  | 3026000 |  |  | 47 | n/a | 138 | 0.1 | (1) 959.6 ACSS Suwannee | Steel Monopole | Substation property & POI 80' x 80' plot | Substation property | 80' x 80' plot | 80' x 80' plot | 25.101 (C)(5)(A)
1021446 | Crane Sub Add [Crane Circuit Breaker Addition - 1021215] | Crane, Crane | Provide transmission service to the Crane Substation. | 2024-07-15 | 2024-12-31 |  |  | 1185000 |  |  | 0 | n/a | 138 | 0.5 | (1) 1233.6 Yukon ACSS/TW | Steel Monopole | n/a | n/a | 100 | 0.5 | 25.101 (C)(5)(A)
1018947 | Odlaw - Uvalde TL Addition (T570) [Asphalt Mines Sub Upgrade - 1018944] | Uvalde, Kinney | Increase transmission service reliability to the Asphalt Mines Substation. | 2022-08-15 | 2023-12-29 |  |  | 447000 |  |  | 0 | 138 | 138 | 26.2 | (1) 795 DRAKE ACSS/MA2 | Steel Monopole | Undefined Centerline | 26.2 | n/a | n/a | 25.101 (C)(5)(B)
1025078 | Starcke-Wirtz TL Addition (T654) [Starcke - Wirtz TL Storm Hardening - 1024854] | Burnet | Phase 1 - Perform storm hardening on the Starcke – Wirtz (T654) transmission line from Starcke Substation to current STR#92. | 2022-07-11 | 2023-05-15 | 2023-02-16 |  | 5531000 |  |  | 95 | 138 | 138 | 6.65 | (1) 795 ACSR "Drake" | Steel Monopole | Varies | 6.65 | n/a | n/a | 25.101 (C)(5)(B)
1029191 | Starcke-Wirtz T654 TL Add Ph. 2 - 1029191 [Starcke - Wirtz TL Storm Hardening - 1024854] | Burnet | Phase 2 - Perform storm hardening on the Starcke – Wirtz (T654) from current STR#92 to Wirtz Substation. | 2022-07-11 | 2024-05-15 |  |  | 3610000 |  |  | 8 | 138 | 138 | 6.65 | (1) 795 ACSR "Drake" | Steel Monopole | Varies | 6.65 | n/a | n/a | 25.101 (C)(5)(B) | Project work split into two phases - entire circuit was noticed and reported on April 2022 MCPR
1023686 | Hilltop-Strahan TL Add (T445) [Hilltop - Strahan TL Upgrade - 1023192] | Hays | Increase the reliability of transmission facilities on the T445: Hilltop – Strahan 1.25-mile 138-kV transmission line by upgrading the conductor and increasing the transmission capacity. | 2022-09-15 | 2023-05-15 | 2023-01-20 |  | 4677000 |  |  | 98 | 138 | 138 | 0.82 | (1) 1433 ACSS/TW "Merrimack" | Steel Poles | Varies | 0.82 | n/a | n/a | 25.101 (C)(5)(B)
1024012 | Fayetteville - Salem TL Addition (T177) [Fayetteville - Salem Transmission Line Upgrade - 1023804] | Washington, Fayette | Rebuilding of the existing 19.3 Miles 345/138 KV Double Circuit TL T177 & T211 from Fayetteville Substation to the Salem Substation. | 2022-07-05 | 2023-05-15 |  |  | 77800000 |  |  | 95 | 138 | 138 | 19.34 | (1) 959.6 ACSS/TW HS "SUWANNEE" | Steel Poles | 85-100 | 19.34 | n/a | n/a | 25.101 (C)(5)(B)
1024013 | FPP Yard 1 - Salem TL Addition (T211) [Fayetteville - Salem Transmission Line Upgrade - 1023804] | Washington, Fayette | Rebuilding of the existing 19.3 Miles 345/138 KV Double Circuit TL T177 & T211 from Fayetteville Substation to the Salem Substation. | 2022-07-05 | 2023-05-15 |  |  | 62519000 |  |  | 95 | 345 | 345 | 27.45 | 959.6 ACSS/TW HS "SUWANNEE" | Steel Poles | 85-100 | 27.45 | n/a | n/a | 25.101 (C)(5)(B)
1023873 | Fairland-Lago Vista TL Addition (T414) [Fairland -Lago Vista TL Upgrade 1023803] | Travis, Burnet | Increase the reliability of transmission facilities on the T414 Fairland – Lago Vista 21-mile 138-kV transmission line by replacing the existing Condor conductor. | 2022-08-01 | 2023-05-15 |  |  | 26962000 |  |  | 90 | 138 | 138 | 21.04 | (1) 795 ACSR "Drake" | Steel Towers & Galvanized Steel Pole | 100 | 21.04 | n/a | n/a | 25.101 (C)(5)(B)
1026437 | Eckert-Nebo TL Addition (T126) [Eckert Power Transformer Upgrade - 1025306] | Gillespie | Increase the reliability of substation equipment at the Eckert Substation. | 2023-08-23 | 2024-04-17 |  |  | 89000 |  |  | 0 | 69 | 138 | 0.7 | (1) 795 ACSR "Drake" | Steel Poles | 100 | 0.7 | n/a | n/a | 25.101 (C)(5)(B)
1026439 | Sandstone Mtn-Gillespie TL Addition (T130) [Eckert Power Transformer Upgrade - 1025306] | Gillespie, Llano | Increase the reliability of substation equipment at the Eckert Substation. | 2023-08-23 | 2024-04-17 |  |  | 428000 |  |  | 0 | 69 | 138 | 36.33 | (1) 959 SUWANNEE ACSS | Steel H-Frames | 100 | 36.33 | n/a | n/a | 25.101 (C)(5)(B)
1025850 | Ferguson-Sherwood TL Addition (T187) [Starcke-Wirtz TL Storm Hardening - 1024854] | Burnet | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2024-05-15 |  |  | 57000 |  |  | 60 | 138 | 138 | 9.35 | (1) 795 ACSR "Drake" | Steel Poles and Lattice Towers | Varies | 9.35 | n/a | n/a | 25.101 (C)(5)(B)
1025852 | Marble F-Granite Mtn TL Addition (T195) [Starcke-Wirtz TL Storm Hardening - 1024854 | Burnet | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2023-01-02 | 2023-01-02 |  | 52000 |  |  | 100 | 138 | 138 | 4.08 | (1) 795 ACSR "Drake" | Steel Poles and Lattice Towers | Varies | 4.08 | n/a | n/a | 25.101 (C)(5)(B)
1025851 | Ferguson-GraniteMtn TL Addition Ph. 1 (T376) [Starcke-Wirtz TL Storm Hardening - 1024854 | Burnet | Phase 1 - Perform storm hardening on the Granite Mountain - Wirtz (T376) transmission line from Granite Mountain to current STR#92. | 2022-07-01 | 2023-02-16 | 2023-02-16 |  | 1541000 |  |  | 100 | 138 | 138 | 5.75 | (1) 795 ACSR "Drake" | Steel Poles and Lattice Towers | Varies | 5.75 | n/a | n/a | 25.101 (C)(5)(B)
1029190 | Ferg-GranMtn TL Addition (T376) Ph. 2 [Starcke - Wirtz TL Storm Hardening - 1024854] | Burnet | Phase 2 - Perform storm hardening on the Granite Mountain - Wirtz (T376) transmission line from STR#92 to Wirtz Substation. | 2022-07-01 | 2024-05-15 |  |  | $1,240,00 |  |  | 8 | 138 | 138 | 5.75 | (1) 795 ACSR "Drake" | Steel Poles and Lattice Towers | Varies | 5.75 | n/a | n/a | 25.101 (C)(5)(B) | Project work split into two phases - entire circuit was noticed and reported on May 2022 MCPR
1026089 | Wirtz-Burnet TL Addition (T218) [Starcke-Wirtz TL Storm Hardening - 1024854 | Burnet | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2024-05-15 |  |  | 52000 |  |  | 10 | 138 | 138 | 16.08 | (1) 795 ACSR "Drake" | Steel Poles and Lattice Towers | Varies | 16.08 | n/a | n/a | 25.101 (C)(5)(B)
1025012 | Buchanan CTEC-Pitsburg TL Addition (T267) [Buchanan (CTEC) - Pitsburg TL Overhaul - 1024836] | Llano County | Overhaul T267 to increase reliability of the structures and conductor | 2022-08-04 | 2023-06-15 |  |  | 20518000 |  |  | 100 | 69 | 69 | 14.49 | (1) 336.4 ACSR "LINNET" (1) 4/0 ACSR "PENGUIN" (1) 959.6 ACSS/TW/MA3 "SUWANNEE" (1) 4/0 ACSR "PENGUIN" (1) 959.6 ACSS/TW/MA3 "SUWANNEE" | Steel Lattice & Steel Poles | 100 | 14.49 | n/a | n/a | 25.101 (C)(5)(B)
1026798 | Chief Brady TL Addition (T378) [Chief Brady Substation Upgrade – 1025303] | Williamson | Chief Brady Substation will be upgraded to increase the bus rating and replace equipment identified as obsolete. The substation upgrade will also install Tier 3 Physical Security Measures | 2022-08-08 | 2023-04-19 | 2023-04-19 |  | 820000 |  |  | 100 | 138 | 138 | 5.12 | 795 ASCR Drake, single | Steel H-frames, Steel Poles, Steel Lattice | Varies, 80 - 100 | 5.12 | n/a | n/a | 25.101 (C)(5)(B)
1027302 | T336 Fiber Replacement Project [PI Switch-Loop 337 Fiber Restoration - 1027886] | Comal | Replace and restore OPGW fiber on T336 | 2022-01-10 | 2022-05-13 | 2022-05-13 | 1800000 |  | 1441161.85 | -19.94% | 100 | 138 | 138 | 3.5 | (1) 959.6 ACSS/TW/M3A “SUWANNEE” | Concrete Poles | n/a | 3.5 | n/a | n/a | 25.101 (C)(3)
1024072 | Lockhart-Red Rock TL Addition (T578/T184) [Lockhart-Split TL Upgrade - 1023809] | Bastrop, Caldwell | Increase the reliability and capability of transmission facilities on the T184 Lockhart – Luling and T578 Lockhart – Red Rock 5.7-mile 138-kV double-circuit section of transmission line from Lockhart Substation to structure #75 (previously structure #301). | 2023-02-01 | 2023-05-15 |  |  | 5469000 |  |  | 80 | 138 | 138 | 5.7 | (1) 959.6 ACSS/TW/M3A “SUWANNEE” | Steel Poles | 85 | 5.7 | n/a | n/a | 25.101 (C)(5)(B) | Parent Project Budget had been utilized in previous report. Updated to Sub-Project Final Estimated Cost
1023899 | Lockhart - Luling TL Addition (T184) [Lockhart-Split TL Upgrade - 1023809] | Bastrop, Caldwell | Increase the reliability and capability of transmission facilities on the T184 Lockhart – Luling and T578 Lockhart – Red Rock 5.7-mile 138-kV double-circuit section of transmission line from Lockhart Substation to structure #75 (previously structure #301). | 2023-02-01 | 2023-05-15 |  |  | 2385000 |  |  | 80 | 138 | 138 | 5.7 | (1) 959.6 ACSS/TW/M3A “SUWANNEE” | Steel Poles | 85 | 5.7 | n/a | n/a | 25.101 (C)(5)(B) | Parent Project Budget had been utilized in previous report. Updated to Sub-Project Final Estimated Cost
1027616 | Muldoon-Flatonia TL Addition (T739)[Muldoon Substation Addition - 1024679] | Fayette | New three breaker ring bus substation to provide a 138-kV line termination for a 240 MW solar generation facility. | 2022-11-18 | 2023-01-13 | 2023-01-13 |  | 207000 |  |  | 100 | 138 | 138 | 8.6 | (1) 959.6 SUWANNEE ACSS/TW | Steel Pole, Steel H-frame | 100; Centerline | 8.6 | n/a | n/a | 25.101 (C)(5)(A)
1027617 | Muldoon-7V Slr Ranch TL Addition (T740)[Muldoon Substation Addition - 1024679] | Fayette | New three breaker ring bus substation to provide a 138-kV line termination for a 240 MW solar generation facility. | 2022-11-18 | 2023-01-13 | 2023-01-13 |  | 188000 |  |  | 100 | n/a | 138 | 0.02 | (1) 959.6 SUWANNEE ACSS/TW | Steel Pole | n/a | n/a | 100 | 0.02 | 25.101 (C)(5)(A)
1024297 | Hornsby TL Addition (T511) [Hornsby Substation Addition - 1023852] | Travis | Provide Transmission service to a load serving substation | 2022-09-26 | 2023-04-05 | 2023-05-04 |  | 10700000 |  |  | 100 | 345 | 345 | 57.15 | (2) 959.6 SUWANNEE ACSS/TW | Lattice Towers | Varies | 57.15 | 120 | 0.15 | 25.101 (C)(5)(A) | Parent Project Budget had been utilized in previous report. Updated to Sub-Project Final Estimated Cost
1024549 | Hornsby TL Addition (T738) [Hornsby Substation Addition - 10235852] | Austin/Travis | Provide Transmission service to a load serving substation | 2022-09-26 | 2023-04-05 | 2023-05-04 |  | 2500000 |  |  | 100 | 345 | 345 | 14.22 | (2) 959.6 SUWANNEE ACSS/TW | Lattice Towers | Varies | 14.22 | 120 | 0.15 | 25.101 (C)(5)(A) | Parent Project Budget had been utilized in previous report. Updated to Sub-Project Final Estimated Cost
1024783 | Brenham-Hwy 36 TL Addition (T468) [Flood Mitigation FY 2022 System Upgrade - 1024586] | Brenham/ Washington | Reduce the risk of erosion and flooding to transmission facilities | 2023-01-22 | 2023-03-22 |  |  | 130000 |  |  | 0 | 138 | 138 | 2.29 | (1) 959.6 SUWANNEE ACSS/TW | Concrete H-Frame and Concrete Monopole | 75 | 2.29 | n/a | n/a | 25.101 (C)(5)(B)
1024785 | Gilleland-Clear Spr TL Addition (T511)[Flood Mitigation FY 2022 System Upgrade - 1024586] | Manor/Travis | Reduce the risk of erosion and flooding to transmission facilities | 2022-12-22 | 2023-02-22 |  |  | 2914000 |  |  | 0 | 345 | 345 | 71 | (2) 959.6 SUWANNEE ACSS/TW | Towers, Poles & H-Frames | 120; 125 | 71 | n/a | n/a | 25.101 (C)(5)(B)
1027544 | Crane - Upton TL Addition (T723) [Crane East Substation Upgrade - 1026913] | Upton | Install circuit breakers and capacitor banks at Crane East Substation | 2022-10-17 | 2023-05-15 |  |  | 1800000 |  |  | 20 | 138 | 138 | 27 | (1) 1233.6 YUKON/TW/MA2 | Steel Pole Dead ends/Delta braced post steel pole tangents | Centerline | 27 | n/a | n/a | 25.101 (C)(5)(B) | Parent Project Budget had been utilized in previous report. Updated to Sub-Project Final Estimated Cost
1029072 | Motorman - Crane East TL Addition (T764) [Crane East Substation Upgrade - 1026913] | Upton | Add circuit breakers in a Ring Bus arrangement at Crane East 138-kV Substation | 2023-04-29 | 2023-06-30 | 2023-04-24 |  | 674500 |  |  | 0 | 138 | 138 | 27 | (1) 1233.6 YUKON/TW/MA2 | Steel Pole Dead ends/Delta braced post steel pole tangents | Centerline | 27 | n/a | n/a | 25.101 (C)(5)(B) | Project work split into two sub-projects - entire circuits were noticed and reported on July 2022 MCPR
1024797 | Esperanza - Boerne TL Add (T657) [Boerne-Esperanza TL Upgrade -1024583 ] | Kendall | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-12-01 | 2023-10-31 |  |  | 13679000 |  |  | 5 | 138 | 138 | 3.9 | (2) 959 ACSS/TS Suwannee | Steel Monopole | 35 / 70 / 85 / 100 / Undefined | 3.9 | n/a | n/a | 25.101 (C)(5)(B)
1024795 | Esperanza Bypass-Boerne Split Structure TL Add (T656) [Boerne-Esperanza TL Upgrade -1024583 ] | Kendall | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-12-01 | 2023-10-31 |  |  | 12428000 |  |  | 5 | 345 | 345 | 1.5 | (2) 1433 ACSS/TW Merrimack | Steel Monopole | 85' / 100' | 1.5 | n/a | n/a | 25.101 (C)(5)(B)
1024805 | Fair Oaks Flyover-Esperanza Bypass TL Add (T656) [Esperanza-Fair Oaks TL Upgrade - 1024585] | Comal, Kendall | This project will increase the reliability of the transmission facilities by replacing the aging conductor. | 12/1/2022 | 2023-08-31 |  |  | 22634000 |  |  | 15 | 345 | 345 | 4.36 | (2) 1433 ACSS/TW Merrimack | Steel Monopole | 75' / 100' | 4.36 | n/a | n/a | 25.101 (C)(5)(B)
1024732 | Bergheim-Fair Oaks TL Addition (T238) [Bergheim-Fair Oaks Ranch Transmission Line Upgrade -1024581] | Comal, Kendall | This project will increase the reliability of the transmission facilities by replacing the aging conductor. | 2024-02-01 | 2024-11-28 |  |  | 7653000 |  |  | 5 | 138 | 138 | 4.08 | (2) 959 ACSS/TS Suwannee | Steel Monopole | 100' | 4.08 | n/a | n/a | 25.101 (C)(5)(B)
1024733 | Bergheim-Fair Oaks Flyover TL Addition (T656) [Bergheim-Fair Oaks Ranch Transmission Line Upgrade -1024581] | Kendall | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2024-02-01 | 2024-11-28 |  |  | 20000000 |  |  | 0 | 345 | 345 | 4.08 | (2) 1433 ACSS/TW Merrimack | Steel Monopole | 100' | 4.08 | n/a | n/a | 25.101 (C)(5)(B)
1024799 | Boerne-Welfare TL Addition (T228) [Boerne Split-Welfare TL Upgrade - 1024582] | Kendall | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-12-01 | 2025-05-31 |  |  | 15800000 |  |  | 0 | 138 | 138 | 9.51 | (2) 959 ACSS/TS Suwannee | Steel Monopole | 35 / 70 / 85 / 100 / Undefined | 9.51 | n/a | n/a | 25.101 (C)(5)(B)
1024801 | Boerne Split Structure-Welfare Flyover (T656) [Boerne Split-Welfare TL Upgrade - 1024582] | Kendall | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-12-01 | 2025-05-31 |  |  | 39061000 |  |  | 0 | 345 | 345 | 7.25 | (2) 1433 ACSS/TW Merrimack | Steel Monopole | 85/100 | 7.25 | n/a | n/a | 25.101 (C)(5)(B)
1026324 | Bellville - Hwy. 36 TL Addition (T467) [Containment Structures Transmission Line Upgrade 1025812] | Washington, Austin | Containment structures installed along transmission line(s) will improve system reliability | 2023-09-15 | 2024-05-15 |  |  | 2419000 |  |  | 0 | 138 | 138 | 13.11 | (1) 959.6 ACSS/TW "SUWANNEE" | Steel Poles and Steel H-Frames | CL width undefined | 13.11 | n/a | n/a | 25.101 (C)(5)(B)
1024984 | Headwaters-Doss TL Addition (T508) [Mountain Home Substation Addition 1024902] | Gillespie | Relocate T508 to cut in to the new Headwaters Substation. LCRA TSC acquired T508 from CTEC. | 2022-11-01 | 2023-01-11 | 2023-01-11 |  | 584000 |  |  | 100 | 69 | 69 | 14.1 | (1) 4/0 ACSR "PENGUIN" | Wood Poles | Blanket | 14.1 | n/a | n/a | 25.101 (C)(5)(B)
1028700 | F-T130 TL Addition | Gillespie | Replacing T130 structures burned by the Big Sky wildfire crossing ROW on 8/2/2022 | 2022-11-30 | 2023-04-21 |  | 31000 |  |  |  | 100 | 69 | 69 | 36.26 | (1) 4/0 ACSR "PENGUIN" (1) 211.3 ACSR "COCHIN" (1) 959 ACSS "SUWANNEE" (1) 336.4 ACSR/GA2 "LINNET" (1) 795 ACSR/GA2 "DRAKE" | Wood H-Frames, Wood Poles, Steel Poles & Steel Lattice | 100 | 36.26 | n/a | n/a | 25.101 (C)(3)
1024803 | Fair Oaks - Esperanza TL Add (T503) [Esperanza-Fair Oaks TL Upgrade - 1024585] | Kendall | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-12-01 | 2023-08-21 |  |  | 9625000 |  |  | 15 | 138 | 138 | 4.36 | (2) 959 ACSS/TS Suwannee | Steel Monopole | 75-100 | 4.36 | n/a | n/a | 25.101 (C)(5)(B)
1024742 | Bastrop W-Bluebonnet (T516) TL Addition [Bastrop West-Bluebonnet (T516) TL Relocation - 1024616] | Bastrop | Relocate T516 within existing ROW to accommodate TxDOT widening of State Hwy. 71 | 2023-10-15 | 2024-02-15 |  |  | 2923000 |  |  | 5 | 138 | 138 | 6.1 | (1) Drake 795 ACSR | STEEL MONOPOLES & WOOD H-FRAME | 100 | 6.1 | n/a | n/a | 25.101 (C)(5)(F)
1027512 | Hornsby-Giga Tx En TL Addition (T755) [Hornsby Circuit Breaker Addition - 1027350] | Travis | Provide a point of interconnection for a new battery energy storage system at the 345-kV Hornsby Substation by adding an additional breaker-and-a-half bay to accommodate the new interconnection. | 2022-12-01 | 2023-04-15 |  |  | 1124000 |  |  | 90 | n/a | 345 | 0.06 | (2) 959 ACSS/TW SUWANNEE | Steel Poles | n/a | n/a | 120 | 0.06 | 25.101 (C)(5)(A)
1027241 | Dimmit-Rosita Creek TL Addition (T697) [Containment Structures Transmission Line Upgrade 1025812] | Dimmit, Maverick | Containment Structures installed along Transmission lines will improve system reliability | 2023-03-01 | 2023-05-15 |  |  | 5999000 |  |  | 15 | 138 | 138 | 40.18 | (1) 795 ACSR DRAKE | Steel Poles | 75-95; Blanket | 40.18 | n/a | n/a | 25.101 (C)(5)(B)
1017679 | Peach-Headwaters TL Addition (T288) [T288 CTEC Transfer] [Mountain Home Substation Addition 1017394] | Gillespie | Remove existing 69kV structures and conductor with 138 kV structures and 795 ACSR Drake. Will also install OPGW. | 2023-01-16 | 2023-12-31 |  |  | 42300000 |  |  | 15 | 69 | 138 | 21.72 | (1) 795 ACSR DRAKE | Steel Poles | Varies | 21.72 | n/a | n/a | 25.101 (C)(5)(B)
1027871 | Gillespie-Kerrville Stadium TL Addition (T207) [Mountain Home Substation Addition - 1017394] | Gillespie | Modification of two spans on T207 to accommodate the upgrade of T288 | 2023-01-01 | 2023-12-01 |  |  | 198000 |  |  | 0 | 138 | 138 | 22.8 | (1) 795 ACSR "Drake" (2) 3/8" EHS | Steel and Wood H-Frames | 75 - 100 | 22.8 | n/a | n/a | 25.101 (C)(5)(B)
1028971 | Pinto Creek TL Addition (T746) [Pinto Creek Circuit Breaker Addition - 1024913] | Kinney | Provide a transmission point of interconnection for a new solar generator and battery energy storage system at Pinto Creek Substation | 2023-03-10 | 2023-05-15 |  |  | 352000 |  |  | 90 | 138 | 138 | 0.03 | (1) 795 ACSR "Drake" (2) DNO-11243 OPGW | Steel Pole | n/a | n/a | 100' | 0.03 | 25.101 (C)(5)(A)
1028795 | Pleasant Farms POI Upg. Addition [Pleasant Farms POI Upgrade - 1028794] | Ector | Accommodate an Oncor transmission line upgrade at Pleasant Farms Substation by relocating POI. | 2023-01-01 | 2023-03-31 |  |  | 949799 |  |  | 0 | 138 | 138 | 0.04 | (2) 959.6 ACSSS SUWANEE; (1) DNO-11243; (1) 3/8" EHS Steel | Steel Pole | 100 | 0.04 | n/a | n/a | 25.101 (C)(5)(A)
1027153 | T626 Str 103 TL Addition [HiddenVly-McNeil St103 TL Upg - 1027059] | Travis | Replace Structure # 103 of the Hidden Valley - McNeil (T626) transmission line to accommodate AT&T cell-site and radio attachments. | 2023-04-01 | 2023-04-28 |  |  | 291000 |  |  | 0 | 138 | 138 | 12.97 | (2) 795 ACSR "Drake" DNO-72-5152 AC-34-52-646 OPGW | Steel Pole | 100 | 12.97 | n/a | n/a | 25.101 (C)(5)(B)
1027381 | Twin Buttes - Angelo Solar TL Addition (T758) [Twin Buttes 345-kV Circuit Breaker Addition- 1027351] | Tom Green | Install transmission interconnection facilities for Twin Buttes Substation and Angelo Solar | 2023-02-06 | 2023-05-12 |  |  | 4367000 |  |  | 0 | n/a | 345 | 1 | (2) 959.6 ACSS "Suwanee"; (2)DNO-11243 | Steel Monopoles & H-Frames | n/a | n/a | 165 | 1 | 25.101 (C)(5)(A)
1022855 | El Campo-Ricebird TL Addition (T589) [El Campo- Ricebird TL Storm Hardening - 1022797] | Wharton | Perform storm hardening to increase the reliability of transmission facilities on the T589. | 2023-01-30 | 2023-06-05 |  |  | 11561000 |  |  | 13 | 138 | 138 | 4.63 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole | 50 | 4.63 | n/a | n/a | 25.101 (C)(5)(B)
1028593 | Luling-Gonzales TL Addition (T173)[Birdhouse Substation Addition - 1027349] | Gonzales | Provide a point of interconnection for a new 123 MW solar system at the new 138-kV Birdhouse Substation by adding an initial three breaker ring bus. | 2023-04-05 | 2023-05-12 |  |  | 1629000 |  |  | 0 | 138 | 138 | 19.45 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole | 75 | 19.45 | n/a | n/a | 25.101 (C)(5)(B)
1028595 | Cuero-Luling City TL Addition (T542)[Birdhouse Substation Addition - 1027349] | Gonzales | Provide a point of interconnection for a new 123 MW solar system at the new 138-kV Birdhouse Substation by adding an initial three breaker ring bus. | 2023-04-10 | 2023-05-12 |  |  | 30000 |  |  | 0 | 138 | 138 | 52.9 | (1) 795 ACSR "DRAKE" | Steel Pole | 80 | 52.9 | n/a | n/a | 25.101 (C)(5)(B)
1027443 | FPP-La Grande OPGW Addition (T263) [FPP Switchyard - La Grange Fiber Restoration - 1026640] | Fayette | Install one (1) 72-count of Optical Ground Wire (OPGW) | 2023-02-24 | 2023-05-11 |  |  | 1500000 |  |  | 0 | 138 | 138 | 7.89 | (1) 795 ACSR "DRAKE" | Wood H-Frame | 50 | 7.89 | n/a | n/a | 25.101 (C)(5)(B)
1027457 | Guadalupe - Hochheim Tap Fiber TL Addition (T542) - 1027457 [Guadalupe-Hochheim Tap Fiber Upgrade - 1027057] | De Witt | Increase reliability by installing new 10.9 miles of Optical Ground Wire (OPGW) | 2023-06-01 | 2023-12-30 |  |  | 5450000 |  |  | 0 | 69 | 69 | 11.21 | (1) 795 ACSR "DRAKE" | Steel Pole | 80 | 11.21 | n/a | n/a | 25.101 (C)(5)(B)
1025012 | Sandstone Mtn - Pitsburg (T267) [Buchanan (CTEC) - Pitsburg TL Overhaul - 1024836] | Llano | Perform an overhaul of T267 to increase reliability of the structures and conductor. | 2023-03-15 | 2023-06-15 |  |  | 20392000 |  |  | 60 | 69 | 69 | 14.5 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole | 100 | 14.5 | n/a | n/a | 25.101 (C)(5)(B)
1028861 | Noelke - Schneemn D TL Addition [Bakersfield-Big Hill TL Addition - 1024834] | Crockett | String conductor and shield wire to STEC owned POI structures. | 2023-04-12 | 2024-05-15 |  |  | 285000 |  |  | 50 | n/a | 345 | 0.15 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B) | STEC Owned ROW
1028860 | C Canyon - Noelke TL Addition [Bakersfield-Big Hill TL Addition - 1024834] | Crockett | String conductor and shield wire to STEC owned POI structures. | 2023-09-01 | 2024-05-15 |  |  | 264000 |  |  | 0 | n/a | 345 | 0.14 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B) | STEC Owned ROW
1028863 | Schneeman - BigHill TL Addition [Bakersfield-Big Hill TL Addition - 1024834] | Crockett/Schlechter | String conductor and shield wire to STEC owned POI structures. | 2023-04-12 | 2023-06-15 |  |  | 146000 |  |  | 95 | n/a | 345 | 0.14 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B) | STEC Owned ROW
1028864 | BakerFld-CCanyon TL Addition [Bakersfield-Big Hill TL Addition - 1024834] | Pecos/Crockett | Re-terminate existing circuit at Cedar Canyon Substation and install new conductor and shield wire. | 2023-09-01 | 2024-05-15 |  |  | 128000 |  |  | 0 | n/a | 345 | 0.06 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B) | STEC Owned ROW
1028859 | Bksfield-CCanyon TL Addition [Bakersfield-Big Hill TL Addition - 1024834] | Pecos/Crockett | String conductor and shield wire to STEC owned POI structures. | 2023-09-01 | 2024-05-15 |  |  | 291000 |  |  | 0 | n/a | 345 | 0.15 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B) | STEC Owned ROW
1029595 | Birdhouse-Starling Solar (T757) [Birdhouse Substation Addition - 1027349] | Gonzales | Provide a point of interconnection for a new 123 MW solar system at the new 138-kV Birdhouse Substation by adding an initial three breaker ring bus. | 2023-04-19 | 2023-05-12 |  |  | 317000 |  |  | 0 | n/a | 138 | 0.07 | (1) 959.6 ACSS Suwannee | Steel Pole | n/a | n/a | 100 | 0.07 | 25.101 (C)(5)(A)
1029596 | Birdhouse-Gonzales (T756)[Birdhouse Substation Addition - 1027349] | Gonzales | Provide a point of interconnection for a new 123 MW solar system at the new 138-kV Birdhouse Substation by adding an initial three breaker ring bus. | 2023-04-19 | 2023-05-12 |  |  | 288000 |  |  | 0 | 138 | 138 | 6.67 | (1) 795 ACSR Drake | Steel Pole, HF, Lattice | 75 | 6.67 | n/a | n/a | 25.101 (C)(5)(B)
1029819 | F-T510 TL Add [Gen Add FY23 Failed Equipment - 1028653] | Williamson | Increase the reliability of LCRA TSC transmission facilities and substation equipment related to Winter Storm Mara. | 2023-02-01 | 2023-02-04 |  | 185000 |  |  |  | 100 | 345 | 345 | 74.55 | (2) 959.6 ACSS "SUWANNEE" | Steel Lattice | Varies | 74.55 | n/a | n/a | 25.101 (C)(3)
1029820 | F-T512 TL Add [Gen Add FY23 Failed Equipment - 1028653] | Williamson | Increase the reliability of LCRA TSC transmission facilities and substation equipment related to Winter Storm Mara. | 2023-02-02 | 2023-02-05 |  | 183000 |  |  |  | 100 | 345 | 345 | 14.16 | (2) 959.6 ACSS "SUWANNEE" | Steel Lattice | Varies | 14.16 | n/a | n/a | 25.101 (C)(3)
1029826 | F-T260 TL Add [Gen Add FY23 Failed Equipment - 1028653] | Bastrop | Increase the reliability of LCRA TSC transmission facilities and substation equipment related to Winter Storm Mara. | 2023-02-02 | 2023-02-03 |  | 21700 |  |  |  | 100 | 138 | 345 | 2.81 | (1) 795 ACSR/GA2 "DRAKE" | Wood H-Frames & Steel Lattice | 100' | 2.81 | n/a | n/a | 25.101 (C)(3)
1029828 | F-T161 TL Add [Gen Add FY23 Failed Equipment - 1028653] | Travis | Increase the reliability of LCRA TSC transmission facilities and substation equipment related to Winter Storm Mara. | 2023-02-03 | 2023-02-03 |  | 21700 |  |  |  | 100 | 69 | 345 | 13.38 | (1) 4/0 ACSR "PENGUIN" | Steel H-Frames & Steel Poles | 100' | 13.38 | n/a | n/a | 25.101 (C)(3)
1024717 | Lakeway - Marble Falls Ph. 1(T497) TL Addition [Lakeway - Marble Falls TL Storm Hardening - 1024594] | Travis | Replace structures and conductor | 2023-07-01 | 2024-05-15 |  |  | 54717000 |  |  | 0 | 138 | 138 | 22.97 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole | 100 | 22.97 | n/a | n/a | 25.101 (C)(5)(B)
1024718 | Paleface - Bee Creek (T458) TL Addition [Lakeway - Marble Falls TL Storm Hardening - 1024594] | Travis | Replace structures and conductor | 2023-07-01 | 2024-05-15 |  |  | 21648900 |  |  | 0 | 138 | 138 | 8.47 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole | 100 | 8.47 | n/a | n/a | 25.101 (C)(5)(B)
1024719 | Bee Creek - Lakeway (T525) TL Addition [Lakeway - Marble Falls TL Storm Hardening - 1024594] | Travis | Replace structures and conductor | 2023-07-01 | 2024-05-15 |  |  | 10229700 |  |  | 0 | 138 | 138 | 4.26 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole | 100 | 4.26 | n/a | n/a | 25.101 (C)(5)(B)
1025505 | Marshall Ford - Lakeway (T180) TL Add [Lakeway - Marble Falls TL Storm Hardening - 1024594] | Travis | Replace structures and conductor | 2023-07-01 | 2024-05-15 |  |  | 7137000 |  |  | 0 | 138 | 138 | 5.03 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole | 100 | 5.03 | n/a | n/a | 25.101 (C)(5)(B)
1029888 | T161 TL Addition [Marshall Ford - McNeil TL Storm Hardening -1024596] | Austin/Travis | Replace one structure | 2023-07-15 | 2023-12-31 |  |  | 248600 |  |  | 0 | 69 | 69 | 12.9 | (1) 795 ACSR/GA2 "DRAKE" | Wood H-Frames and Steel H-Frames | 100 | 13.3 | n/a | n/a | 25.101 (C)(5)(B)
1024734 | Spicewood-McNeil Storm Hardening TL Addition (T242) [Marshall Ford - McNeil TL Storm Hardening -1024596] | Austin/Travis | Replace structures conductor and OPGW | 2023-10-01 | 2024-05-15 |  |  | 4580500 |  |  | 0 | 138 | 138 | 8.7 | (1) 795 ACSR/GA2 "DRAKE" | Steel Poles and Steel H-Frames | 100 | 8.7 | n/a | n/a | 25.101 (C)(5)(B)
1024731 | Marshall Ford-Spicewood Storm Hardening TL Addition (T162) [Marshall Ford - McNeil TL Storm Hardening -1024596] | Austin/Travis | Replace structures conductor and OPGW | 2023-07-15 | 2023-12-31 |  |  | 684200 |  |  | 0 | 138 | 138 | 8.04 | (1) 795 ACSR/GA2 "DRAKE" | Steel Poles and Steel H-Frames | 100 | 8.04 | n/a | n/a | 25.101 (C)(5)(B)
1024726 | Marshall Ford-McNeil Storm Hardening TL Addition (T197) [Marshall Ford - McNeil TL Storm Hardening -1024596] | Austin/Travis | Replace structures conductor and OPGW | 2023-07-15 | 2024-05-15 |  |  | 23299300 |  |  | 0 | 138 | 138 | 15.5 | (1) 795 ACSR/GA2 "DRAKE" | Steel Poles and Steel H-Frames | 100 | 15.5 | n/a | n/a | 25.101 (C)(5)(B)
1026908 | Altair-Nada TL Addition (T545) [Altair-Garwood TL Overhaul - 1020884] | Colorado | Replace eight existing structures on T545 at intersection with T546 to maintain operating clearance. | 2023-08-01 | 2024-06-30 |  |  | 3988500 |  |  | 0 | 138 | 138 | 14.17 | (1) 795 ACSR/GA2 "DRAKE" | Steel Pole and Steel H-frame | 60' | 14.17 | n/a | n/a | 25.101 (C)(5)(B)
1020885 | Altair-Garwood OH TL Addition (T546) [Altair-Garwood TL Overhaul - 1020884] | Colorado | Perform overhaul of T546 (including all tapped lines) to improve reliability of structures and conductors. | 2023-08-01 | 2024-06-30 |  |  | 28418800 |  |  | 0 | 69 | 69 | 8.59 | (1) 795 ACSR/GA2 "DRAKE" | Steel Pole and Steel H-frame | 75 | 8.59 | n/a | n/a | 25.101 (C)(5)(B)
1025208 | Nada - Ricebird TL Addition (T588) Nada - Ricebird TL Overhaul - 1024849] | Wharton, Colorado | LCRA TSC will perform an overhaul on the 13.1-mile Nada - Ricebird (T588) 138-kV transmission line. This project will increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. | 2023-08-28 | 2024-12-17 |  |  | 16905400 |  |  | 0 | 138 | 138 | 13.1 | (1) 959.6 ACSS "SUWANNEE" | Steel Poles | 60/50 | 13.1 | n/a | n/a | 25.101 (C)(5)(B)
1027162 | FPP Lytton Springs (T255) TL Addition -[FPP Yard 2 - Lytton Springs Transmission Line Overhaul - 1024839] | Caldwell, Bastrop, and Fayette | Evaluate T255 structures and clearances using the existing conductor and shield wire while adding containment dead-end structures per L4100. Insulators and hardware on existing towers will need to be removed and replaced. 8 structure insulators were previously replaced and will only need hardware replaced 30 32 structures will be removed and replaced with 60 64 new dead-end single circuit steel poles. | On-hold | On-hold |  |  | 46000000 |  |  | 0 | 345 | 345 | 61.32 | (2) 795 ACSR/GA2 DRAKE (2) 715.5 ACSR REDWING | Steel Pole and Lattice Tower | 100 | 61.32 | n/a | n/a | 25.101 (C)(5)(B)
1028960 | Cuero - Guadalupe TL Addition (T609) [Cuero Substation Upgrade - 1026635] | De Witt | LCRA TSC will improve the bus at Cuero substation by reconfiguring the existing bus from single bus single breaker to a breaker and a half configuration. This bus improvement will include the upgrade of bus work, switches, breakers, instrument transformers, surge arresters, protective schemes, the replacement of Cuero AT3, and facility structures as required. A new control enclosure is also called for in order to meet high wind requirements. New circuit breakers and switches should meet LCRA TSC minimum 138-kV design standards (3000 amps or higher). Other improvements identified during the engineering analysis of the facility should be considered. | 2023-07-03 | 2024-05-15 |  |  | 842500 |  |  | 0 | 138 | 138 | 2.75 | (1) 959.6 ACSS "SUWANNEE" | Steel Poles and Lattice Towers | 85 | 2.75 | n/a | n/a | 25.101 (C)(5)(B)
1028961 | Cuero - Yoakum TL Addition (T198) [Cuero Substation Upgrade - 1026635] | De Witt | LCRA TSC will improve the bus at Cuero substation by reconfiguring the existing bus from single bus single breaker to a breaker and a half configuration. This bus improvement will include the upgrade of bus work, switches, breakers, instrument transformers, surge arresters, protective schemes, the replacement of Cuero AT3, and facility structures as required. A new control enclosure is also called for in order to meet high wind requirements. New circuit breakers and switches should meet LCRA TSC minimum 138-kV design standards (3000 amps or higher). Other improvements identified during the engineering analysis of the facility should be considered. | 2023-07-03 | 2024-05-15 |  |  | 576500 |  |  | 0 | 138 | 138 | 13.83 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole and Steel H-Frame | 100 | 13.84 | n/a | n/a | 25.101 (C)(5)(B)
1029822 | F-T197 TL Add [Gen Add FY23 Failed Equipment - 1028653] | Travis | Increase the reliability of LCRA TSC transmission facilities and substation equipment related to Winter Storm Mara. | 2023-02-24 | 2023-02-28 |  | 1425000 |  |  |  | 100 | 138 | 138 | 14.01 | (1) 795 ACSR/GA2 DRAKE (1) 927.2 AAAC GREENLEY | Steel Lattice, Steel Pole, Steel H-Frames & Wood H-Frames | 100 | 14.01 | n/a | n/a | 25.101 (C)(3)
1029827 | F-T244 TL Add [Gen Add FY23 Failed Equipment - 1028653] | Kendall | Increase the reliability of LCRA TSC transmission facilities and substation equipment related to Winter Storm Mara. | 2023-03-13 | 2023-03-19 |  | 150000 |  |  |  | 10 | 138 | 138 | 4.57 | (2) 795 ACSR/GA2 "DRAKE" | Steel Poles | 100 | 4.57 | n/a | n/a | 25.101 (C)(3)
1029824 | F-T642 TL Add [Gen Add FY23 Failed Equipment - 1028653] | Williamson | Increase the reliability of LCRA TSC transmission facilities and substation equipment related to Winter Storm Mara. | 2023-03-14 | 2023-03-22 |  | 250000 |  |  |  | 100 | 138 | 138 | 7.84 | (2) 795 ACSR/GA2 DRAKE (2) 959.6 ACSS SUWANNEE | Steel Poles | 80/100 | 7.84 | n/a | n/a | 25.101 (C)(3)
1029821 | F-T255 TL Add [Gen Add FY23 Failed Equipment - 1028653] | Bastrop | Increase the reliability of LCRA TSC transmission facilities and substation equipment related to Winter Storm Mara. | 2023-03-20 | 2023-03-26 |  | 665000 |  |  |  | 100 | 345 | 345 | 61.32 | (2) 795 ACSR/GA2 DRAKE (2) 715.5 ACSR REDWING | Steel Pole and Lattice Tower | 100 | 61.32 | n/a | n/a | 25.101 (C)(3)
1029825 | F-T421 TL Add [Gen Add FY23 Failed Equipment - 1028653] | Travis | Increase the reliability of LCRA TSC transmission facilities and substation equipment related to Winter Storm Mara. | 2023-06-05 | 2023-07-31 |  | 200000 |  |  |  | 100 | 138 | 138 | 7.01 | (1) 1433 ACSS/TW Merrimack | Wood H-Frames | 100 | 7.01 | n/a | n/a | 25.101 (C)(3)
1029485 | F-T237 TL Add [Gen Add FY23 Failed Equipment - 1028653] | Comal | Increase the reliability of LCRA TSC transmission facilities and substation equipment related to Winter Storm Mara. | 2023-05-15 | 2023-05-18 |  | 355000 |  |  |  | 0 | 138 | 138 | 3.76 | (1) 959.6 ACSS "SUWANNEE" | Steel Lattice & Steel Pole | 100 | 3.76 | n/a | n/a | 25.101 (C)(3)
1029484 | F-T610 TL Add [Gen Add FY23 Failed Equipment - 1028653] | Comal | Increase the reliability of LCRA TSC transmission facilities and substation equipment related to Winter Storm Mara. | 2023-05-19 | 2023-06-09 |  | 950000 |  |  |  | 0 | 138 | 138 | 10.41 | (1) 795 ACSR/SD Condor | Steel Lattice | 100 | 10.41 | n/a | n/a | 25.101 (C)(3)
1029482 | F-T493 TL Add [Gen Add FY23 Failed Equipment - 1028653] | Comal | Increase the reliability of LCRA TSC transmission facilities and substation equipment related to Winter Storm Mara. | 2023-06-12 | 2023-07-14 |  | 2300000 |  |  |  | 0 | 138 | 138 | 7.17 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole | 100 | 7.17 | n/a | n/a | 25.101 (C)(3)
1029816 | F-T238 TL Add [Gen Add FY23 Failed Equipment - 1028653] | Comal | Increase the reliability of LCRA TSC transmission facilities and substation equipment related to Winter Storm Mara. | 2023-07-19 | 2023-07-20 |  | 245000 |  |  |  | 0 | 138 | 138 | 4.07 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole | 100 | 4.07 | n/a | n/a | 25.101 (C)(3)
1029818 | F-T657 TL Add [Gen Add FY23 Failed Equipment - 1028653] | Kendall | Increase the reliability of LCRA TSC transmission facilities and substation equipment related to Winter Storm Mara. | 2023-07-25 | 2023-07-28 |  | 175000 |  |  |  | 0 | 138 | 138 | 3.9 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole | 85/ 100 | 3.9 | n/a | n/a | 25.101 (C)(3)
1029823 | F-T162 TL Add [Gen Add FY23 Failed Equipment - 1028653] | Travis | Increase the reliability of LCRA TSC transmission facilities and substation equipment related to Winter Storm Mara. | 2023-02-24 | 2023-03-05 |  | $25,000 |  |  |  | 100 | 138 | 138 | 8.04 | (1) 795 ACSR/GA2 "DRAKE" | Steel Lattice | 85/ 100 | 8.04 | n/a | n/a | 25.101 (C)(3)
1029833 | F-T497 TL Add [Gen Add FY23 Failed Equipment - 1028653] | Burnet | Increase the reliability of LCRA TSC transmission facilities and substation equipment related to Winter Storm Mara. | 3/9/2023 | 3/19/23 |  | $22,000 |  |  |  | 100 | 138 | 138 | 22.99 | (1) 795 ACSR/GA2 "DRAKE" | Steel Lattice | 100 | 22.99 | n/a | n/a | 25.101 (C)(3)
1029832 | F-T180 TL Add [Gen Add FY23 Failed Equipment - 1028653] | Travis | Increase the reliability of LCRA TSC transmission facilities and substation equipment related to Winter Storm Mara. | 3/9/2023 | 3/19/23 |  | $22,000 |  |  |  | 100 | 138 | 138 | 5.05 | (1) 795 ACSR/SD Condor (1) 795 ACSR/GA2 "DRAKE" | Steel Lattice | 100 | 5.05 | n/a | n/a | 25.101 (C)(3)
1030105 | Cooks Point-Lyle Wolz (T680) Transmission Line Upgrade - 1030105 | Burleson | Conduct railway mitigation | 2023-06-01 | 2023-12-30 |  |  | 2000000 |  |  | 0 | 138 | 138 | 18.4 | (2) 795 ACSR/GA2 "DRAKE" | Steel Poles | 80 | 18.4 | n/a | n/a | 25.101 (C)(5)(B)
1022919 | Hallettsville-Mont TL Addition (T593) [Hallettsville-Mont TL Overhaul - 1024841] | Lavaca | Increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards | 2023-09-18 | 2024-05-15 |  |  | 8400000 |  |  | 0 | 138 | 138 | 2.32 | (1) 959.6 ACSS/TW-HS "SUWANNEE" | Steel Pole | 100 | 2.32 | n/a | n/a | 25.101 (C)(5)(B)
1024782 | Guadalupe - Lost Creek TL Addition (T541) [Guadalupe - Lost Creek TL Upgrade - 1027911] | De Witt, Fayette | Increase transmission service reliability by replacing the current conductors | 2023-09-01 | 2023-12-31 |  |  | 446000 |  |  | 0 | 138 | 138 | 6.08 | (1) 795 ACSR "DRAKE" | Steel Pole | 60 | 6.08 | n/a | n/a | 25.101 (C)(5)(B)
1024729 | Highway 46-Antler TL Add (T610) [Antler-Highway 46 Transmission Line Upgrade - 1024577] | Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2023-09-01 | 2024-06-01 |  |  | 11925500 |  |  | 0 | 138 | 138 | 10.4 | (1) 959.6 ACSS/TW-HS "SUWANNEE" | Steel Pole | 100 | 10.4 | n/a | n/a | 25.101 (C)(5)(B)
1024730 | Highway 46 Flyover-Antler Flyover TL Add (T389) [Antler-Highway 46 Transmission Line Upgrade - 1024577] | Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2023-09-01 | 2024-06-01 |  |  | 49443000 |  |  | 0 | 345 | 345 | 34.17 | (2) 959.6 ACSS/TW-HS "SUWANNEE" | Steel Pole | 100 | 34.17 | n/a | n/a | 25.101 (C)(5)(B)
1024807 | Welfare - Kendall TL Addition (T584) - [Kendall-Welfare TL Upgrade -1024592] | Kendall | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2023-10-01 | 2025-08-31 |  |  | 18102000 |  |  | 0 | 138 | 138 | 10.55 | (1) 959.6 ACSS/TW-HS "SUWANNEE" | Steel Pole | 100 | 10.55 | n/a | n/a | 25.101 (C)(5)(B)
1024809 | Welfare Flyover - Kendall TL Addition (T656)[Kendall-Welfare TL Upgrade -1024592] | Kendall | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2023-10-01 | 2025-08-31 |  |  | 49168000 |  |  | 0 | 345 | 345 | 27.22 | (2) 959.6 ACSS/TW-HS "SUWANNEE" | Steel Pole | 100 | 27.22 | n/a | n/a | 25.101 (C)(5)(B)
1027015 | Howard Lane (AE) - McNeil Transmission Line Addition (T163)[Howard Lane (AE) - McNeil Transmission Line Addition Storm Hardening - 1026914 | Travis | Perform storm hardening on the 2.7 mile Howard Lane – McNeil (T163) 138-kV transmission line | 2023-07-15 | 2024-05-15 |  |  | 8100000 |  |  | 0 | 138 | 138 | 2.65 | (1) 795 ACSR "DRAKE" | Steel Pole, Steel Lattice | 100/120 | 2.65 | n/a | n/a | 25.101 (C)(5)(B)