## MonthlyReportForm-SWEPCO
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
42941298 (P18222001) | New Quitman 69-kV Substation | Wood | Construct a new 69-kV, 40kA, 2000A, (4) four-breaker ring bus design substation on a new station pad on 10 acres of purchased property located about 0.6 miles to the northeast of existing Quitman Substation. | 2020-06-15 | 2021-11-24 | 2021-11-19 |  | 5674838 | 5894859 | 3.877% | 100 |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
42941390 (P18215001) | Lydia 345-kV Station | Bowie | Convert the Lydia 345kV station to a ring bus configuration, eliminating the 3-terminal line by adding breakers. A new station will be built in the clear on newly purchased property; the existing station will be retired. | 2020-09-14 | 2022-05-11 | 2022-12-08 |  | 15843030 |  |  | 99 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Property Purchased
T10068530 (DP20S05D0) | Alba 69-kV Substation Upgrade: T-Station | Alba/Wood | Rebuild Alba substation with new station deadend, bus work, SSVT, and relaying. | 2020-10-04 | 2020-12-15 | 2020-12-29 |  | 658792.77 |  |  | 90 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10068526 (DP20S05C0) | Alba 69-kV Substation Upgrade: T-Line | Alba/Wood | Install one transmission structure to feed the new station rebuild | 2020-10-04 | 2020-12-15 | 2020-12-29 |  | 425355 |  |  | 90 | 69 |  | 0.02 | T2 477 KCM ACSR | Steel Dead-End |  |  |  |  | 16 TAC 25.83(a)(3) | Within Station Property
42952896 (A18106011) | N Marshall 69-kV Substation: Construct Box Bay | Marshall/Harrison | The 69-kV portion of the station will be replaced with a box bay. Breaker 7570 with be replaced with new 2000 A breaker as part of this rebuild. A DICM will be installed to house all of the new transmission relay equipment. | 2021-02-01 | 2022-03-15 | 2022-02-10 |  | 3940359 |  |  | 99 |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Within AEP Property
42963433 (A18106017) | N Marshall - Marshall 69-kV Retermination | Marshall/Harrison | Terminate the existing N Marshall to Marshall 69-kV line into new Box Bay as part of the Jefferson station rebuild | 2021-02-01 | 2021-12-31 | 2021-12-30 |  | 514806 |  |  | 99 | 69 |  | 0.02 | 795 KCM ACSR "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP Property
42952898 (A18106002) (A18106004) | Woodlawn - N Marshall 69-kV Rebuild | Marshall/Harrison | Rebuild and reconductor the Woodlawn to N. Marshall 69-kV transmission line to 138-kV standards but will continue to operate at 69 kV. | 2021-02-01 | 2021-12-31 | 2021-12-30 |  | 8098078 |  |  | 99 | 69 |  | 7.55 | 795 KCM ACSR "Drake" | Steel Mono Pole | Centerline | 7.55 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easement Landowners Noticed
42939973 (P18231001) (P18231002) | Carthage T 138-kV Box Bay | Panola | Install 3 new138-kV breakers in current box bay. Expand station site to accommodate DICM. Install line relaying and breakers controls in new control house. | 2021-04-14 | 2021-12-01 |  |  | 3830879 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Property Purchased for Expansion
T10236276 (A15713062) | Rock Hill - Marshall 69-kV Line | Marshall/Harrison, Rusk | Telecom Modernization Program: Install 18.5 miles of 96 count ADSS fiber via Transmission between Marshall 69-kV Station and Rock Hill Station. For connectivity at Marshall 69kV Station, Rosborough Station and Rock Hill Station to support CES and ICON network. | 2021-03-06 | 2021-06-01 |  |  | 1309447 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3)
T10236194 (A15713129) | LeBrock-Roseborough Telecom Fiber | Harrison | Telecom Modernization Program: Install 3.58 miles of 48 count ADSS via Distribution between LeBrock Station and Rosborough Station. For connectivity at LeBrock Station and Rosborough Station to support CES and ICON network. | 2021-04-26 | 2021-05-15 |  |  | 361888 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3)
T10236204 (A15713187) | Lydia 345-kV Switch Station Fiber Extension North | Bowie | Telecom Modernization Program: Install 5.5 miles of 48 count ADSS fiber via underground build between Lydia station and an existing splice point into fiber on the "Mount Pleasant‐New Boston 138-kV transmission line." For connectivity at Lydia Station. | 2021-03-06 | 2021-06-30 |  |  | 1607011 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3)
T10236272 (A15713189) | Lydia 345-kV Switch Station Fiber Extension South | Bowie | Telecom Modernization Program: Install 5.6 miles of 48 count ADSS fiber via underground build between Lydia station and an existing splice point into fiber on the "Mount Pleasant‐New Boston 138-kV transmission line." For connectivity at Lydia Station. | 2021-03-06 | 2021-06-30 |  |  | 914863 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3)
T10236307 (A19351067) | Marshall - Pirkey 138-kV Line | Marshall/Harrison | Telecom Modernization Program: Install 7.5 miles of 96 count ADSS fiber between Marshall Station and Pirkey Station. For connectivity at Marshall Station and Pirkey Station to support CES and ICON network. | 2021-05-17 | 2021-08-19 |  |  | 662819 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3)
T10180035 (A18806075) | Lone Star South 138-kV Substation | Lone Star/Morris | Replace Line Relaying with AEP standard panels and a breaker control panel. | 2021-04-26 | 2021-10-20 | 2022-04-27 |  | 362215 | 648418.77 | 79.01% | 100 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10180047 (A18806076) | Pittsburg 138-kV Substation | Pittsburg/Camp | Replace Line Relaying with AEP standard panels and a breaker control panel. | 2021-04-26 | 2021-10-20 | 2022-04-27 |  | 355252 | 524033.55 | 47.51% | 100 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42907518 (A18093001) | Bann - Red Springs REA 138-kV T-Line | Bowie | Rebuild and Reconductor the Bann to Red Springs REA 138-kV transmission line. | 2021-10-01 | 2022-05-25 | 2022-05-26 |  | 5778818 |  |  | 99 | 138 |  | 3.08 | 1590 ACSR/AW 54/19 "Falcon" | Steel, Single Pole | 100 | 3.08 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowners noticed
42907529 (A18093003) | IPC Domino - Red Springs REA 138-kV T-Line | Bowie,Cass | Rebuild and Reconductor the IPC Domino to Red Springs REA 138-kV transmission line. | 2021-08-01 | 2022-02-25 | 2022-02-25 |  | 16929647 |  |  | 99 | 138 |  | 8.29 | 1590 ACSR/AW 54/19 "Falcon" | Steel, Single Pole | 100 | 8.29 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowners noticed
T10319108 (A18093009) | Telecomm fiber transitions from T-line into stations | Bowie,Cass | Install telecomm fiber transitions from T-line into station at Bann Station, Red Springs Station, and IPC Domino Station | 2021-08-01 | 2022-05-25 | 2022-06-30 |  | 335489 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10169344 (A18089003) | Frederick Junction (Str. 8/6) - Vernon Main St. 69-kV Rebuild | Wilbarger | Rebuild and reconductor the Texas portion (beginning at Structure 8/6) of the Frederick Junction to Vernon Main St. 69-kV transmission line to 138-kV standards but will continue to operate at 69 kV. | 2021-08-02 | 2021-12-31 |  |  | 5192281 |  |  | 0 | 69 |  | 7.6 | 1272 ACSR 54/19 "Pheasant" | Steel, Single Pole | Centerline | 7.6 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easement Landowners Noticed
42964990 42939973 (P18225001) (P18225003) | Bruton 69-kV Box Bay | Morris | Install three 69-kV breakers at Bruton Box Bay. New DICM will be installed to accommodate relaying. | 2021-09-03 | 2022-03-27 | 2022-12-08 |  | 3169448 | 3250166.99 | 2.547% | 100 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Corrected Project Number Property Purchased for Expansion
42941398 (P18215002) | Lydia - Valiant 345-kV Line: Retermination | Bowie | Reterminate the Lydia - Valliant 345-kV transmission line into the newly reconstructed Lydia 345-kV Station. | 2021-09-27 | 2022-05-11 | 2022-12-08 |  | 994017 |  |  | 99 | 345 |  |  |  | Steel, Single Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
42941406 (P18215005) | Lydia - NW Texarkana 345-kV Line: Retermination | Bowie | Reterminate the Lydia - NW Texarkana 345-kV transmission line into the newly reconstructed Lydia 345-kV Station. | 2021-09-27 | 2022-05-11 | 2022-12-08 |  | 1263867 |  |  | 99 | 345 |  |  |  | Steel, Single Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
42941408 (P18215006) | Lydia - Welsh 345-kV Line: Retermination | Bowie | Reterminate the Lydia - Welsh 345-kV transmission line into the newly reconstructed Lydia 345-kV Station. | 2021-09-27 | 2022-05-11 | 2022-12-06 |  | 996635 |  |  | 99 | 345 |  |  |  | Steel, Single Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
43003713 (A19020001) | MidValley - Longview Tap 69-kV Line | Greg | Relocate three structures along the MidValley - Longview Tap 69-kV transmission line to accommodate the widening of FM 2206 as requested by the Texas Department of Transportation (TxDOT) | 2021-09-06 | 2021-10-12 | 2021-10-12 |  | 1384842.39 | 938329.94 | -32.24% | 100 | 69 |  | 0.08 | 2/0 ACSR 6/1 "Quail" | Steel Pole Mono | Centerline | 0.08 | 100 | 0.08 | 16 TAC 25.101 (c)(5)(F) | Landowner consent obtained
T10277140 (P20215003) | Avinger 138-kV Tap: Install 138-kV Temporary Tap | Cass | Replace two (2) dead-end structures and install temporary bypass line and customer (NTEC POD) tap terminated at the SWEPCO Petty - Wilkes 138-kV transmission line. | 2021-10-04 | 2021-11-29 | 2021-11-29 |  | 317002 |  |  | 99 | 138 |  | 0.1 | 1272 ACSR 54/19 "Pheasant" | Three-Pole Wooden Structure | 100 | 0.1 | 175 | 0.1 | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained for Temporary Easement
TL0043281 (A21065503) | Longwood - Wilkes 345-kV Transmission Line | Marion | Install one galvanized steel, H-frame structure on the Longwood-Wilkes 345 kV transmission line between structures 169 & 170. | 2021-10-04 | 2021-10-09 |  |  | 305065 |  |  | 0 | 345 |  | 0.1 | 2-1024 ACAR | H-Frame Steel | 100 | 0.1 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowner Noticed No new easement necessary
T10365950 (A21062001) | NW Texarkana - Welsh 345-kV Transmission Line | Cass,Bowie | Install two 3-Pole mid-span structures consisting of one laminated wood pole supporting each phase independently at two locations between spans 161-162 and 162-163. | 2021-12-06 | 2021-12-31 | 2021-12-13 |  | 1839321 |  |  | 99 | 345 |  | 0.1 | 1-2156 Bluebird 84/19 ACSR | Laminated Wood Poles | varies | 0.1 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowner Noticed No new easement necessary
T10224575 (A18806086) | Red Springs 138-kV Station: Bann - IPC Domino Relay Replacement | Bowie | Replace line relaying at Red Springs 138-kV Station to match relaying at Bann station. | 2021-12-06 | 2022-02-25 |  |  | 684857 |  |  | 80 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10224577 (A18806087) | IPC Domino 138-kV Station Bann - IPC Domino Relay Replacement | Cass | Replace line relaying at IPC Domino 138-kV Station to match relaying at Bann station. | 2022-01-10 | 2022-02-25 | 2023-02-25 |  | 663726 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42963930 (P19057001) (P19057002) | Morton to E Burges 138-kV Transmission Line | Van Zandt | Construct a new 2.57 mile 138-kV transmission line from a cut-in near the SWEPCO Morton 138-kV Substation to a cut-in near the WCEC E Burges 138-kV Substation. | 2022-08-01 | 2022-11-02 | 2023-10-27 | 4185088 | 4700779.67 |  |  | 99 |  | 138 | 2.57 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel Mono Pole |  |  | 100 | 2.57 | 50669 | PUCT Docket 50669 Approved on 05/07/2021
T10329431 (P20025001) (P20025003) | Murvaul 138-kV Box Bay | Panola | Construct a new 138-kV box bay with Scada controlled switches. | 2022-01-31 | 2022-09-23 | 2022-11-10 |  | 1548080 |  |  | 99 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Landowner consent obtained
T10356096 (P20025002) | Carthage T - Tenaha 138-kV T-Line | Panola | Construct a temporary tap prior to the permanent box bay installation. Re-terminate the existing Carthage T to Tenaha transmission line into new Murvaul Tap 138-kV Box Bay. | 2022-01-17 | 2022-11-30 | 2022-12-13 |  | 1348733 |  |  | 99 |  | 138 | 0.2 | 1272 KCM 54/19 ACSR | Steel Mono Pole |  |  | 100 | 0.2 | 16 TAC 25.101 (c)(5)(A) | Landowner consent obtained
42965029 (P18231006) | Carthage Connection 138/69-kV POD | Panola | Update relay settings and tuner at Carthage 69/138kV POD. | 2023-03-20 | 2023-04-19 |  |  | 224032 |  |  | 0 | 138 / 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42908317 (A15706581) | Childress Airport 69-kV Substation | Childress | Replace switches 6147 and 6153 with 2000 A switches. Upgrade upper and lower bus. | 2023-01-25 | 2023-03-08 |  |  | 443841 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
43002631 (A16806635) | Clarendon - W. Childress 69-kV T-Line | Childress | Add Fiber Transitions at the substations along the Clarendon to NW Memphis to W Childress 69-kV transmission line. | 2022-01-10 | 2023-06-14 |  |  | 755188 |  |  | 25 | 69 | [8 empty] | 16 TAC 25.83(a)(3)
T10052253 (P18251001) (P18251002) (P18251015) | West Atlanta 138/69-kV Substation | Cass | Demo the existing West Atlanta station and rebuild it on an adjacent piece of property. Convert the 138-kV and 69-kV portions to a ring bus configuration with all of the necessary relaying. The 90MVA auto will be re-used at the new W. Atlanta station. | 2022-03-07 | 2022-12-01 |  |  | 10344453 |  |  | 99 | 138 / 69 | [8 empty] | 16 TAC 25.83(a)(3) | Property purchased for expansion
T10052341 (P18251004) | West Atlanta - Linden 69-kV T-Line | Cass | Reterminate the West Atlanta to Linden 69-kV transmission line into the newly rebuilt W. Atlanta Substation. | 2022-03-07 | 2022-12-01 |  |  | 882380 |  |  | 99 | 69 |  | 0.12 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP purchased property
T10052462 (P18251005) | West Atlanta - Atlanta 69-kV T-Line | Cass | Reterminate the West Atlanta to Atlanta 69-kV transmission line into the newly rebuilt W. Atlanta Substation. | 2022-03-07 | 2022-12-01 |  |  | 374269 |  |  | 99 | 69 |  | 0.15 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP purchased property
T10052470 (P18251006) | West Atlanta - Wilkes 138-kV T-Line | Cass | Reterminate the West Atlanta to Wilkes 138-kV transmission line into the newly rebuilt W. Atlanta Substation. | 2022-03-07 | 2022-12-01 | 2022-12-15 |  | 1087384 |  |  | 99 | 138 |  | 0.1 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP purchased property
T10052503 (P18251007) | West Atlanta - IPC Domino 138-kV T-Line | Cass | Reterminate the West Atlanta to IPC Domino 138-kV transmission line into the newly rebuilt W. Atlanta Substation. | 2022-03-07 | 2022-12-01 | 2022-12-15 |  | 962250 |  |  | 99 | 138 |  | 0.1 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP purchased property
T10052511 (P18251010) | Linden 69-kV Substation | Cass | Install Circuit Breaker, Switches, and Relaying for Atlanta line. | 2022-03-07 | 2022-12-01 | 2022-12-07 |  | 1553818 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10277105 (P20215001) | Avinger 138-kV Permanent Tap: Install POP Switch | Cass | Construct a permanent tap with three 138-kV motor operated and SCADA controlled switches at the Avinger 138-kV Temporary Tap along the Petty to Wilkes 138-kV transmission line. Install revenue metering. | 2022-05-09 | 2022-11-29 | 2022-10-10 |  | 2053111 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Landowner Consent Obtained
T10277164 (P20215005) (P20215007) | Avinger 138-kV Permanent Tap: Petty - Wilkes 138-kV T-Line Cut-In | Cass | Terminate the Petty to Wilkes 138-kV transmission line into the new Avinger Tap POP Switch. Install a single span from the new Avinger 138-kV Tap POP Switch to NTEC’s Avinger POD. | 2022-05-09 | 2022-11-29 | 2022-10-10 |  | 556168 |  |  | 99 | 138 |  | 0.1 | 1272 ACSR 54/19 "Pheasant" | Three-Pole Wooden Structure | 100 | 0.1 | 175 | 0.1 | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
T10378224 (P20215009) | Avinger 138-kV Permanent Tap: TFC | Cass | Provide 3.3 miles of ADSS of 96ct fiber via Transmission at the new Avinger Tap on the Wilkes and Petty 138-kV Line between the Wilkes and Welsh Tap Stations. | 2022-05-09 | 2022-11-29 | 2023-04-21 |  | 361648 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3)
42908318 (A15706582) | Childress AMOCO 69-kV Substation | Childress | Replace switches 2092 and 2485 with 2000A Phase-Over-Phase (POP) switches | 2022-10-11 | 2022-11-08 | 2022-12-21 |  | 684649 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42908314 (A15706579) | Estelline 69-kV Substation | Hall | Replace switches 151 and 152 with 2000A switches. | 2022-06-27 | 2022-08-19 | 2022-09-15 |  | 456769 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10256129 (A18806017) | Jefferson 138-kV Switch Station | Marion | Replace 138-kV Marshall line relaying. Replace 138-kV CB-3650 controls with SEL451S relay. Add 3 new CCVTs. | 2022-06-04 | 2022-11-17 |  |  | 263000 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10256135 (A18806020) | Marshall 138-kV Substation | Marshall/Harrison | Replace 138-kV Jefferson SW line relaying. Replace 138-kV CB-1730 controls with SEL451S relay. Add 3 new CCVTs. | 2022-06-04 | 2022-11-17 |  |  | 296000 |  |  | 5 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10476409 (A20006004) | IPC Domino - West Atlanta 138-kV T-Line: Telecomm Fiber Transitions | Cass | Install telecomm fiber transitions from T-line into station at IPC Domino, IPC Tap, Cass Tap, and West Atlanta | 2022-08-15 | 2023-12-20 |  |  | 255965 |  |  | 10 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10162138 (A20006003) (A20006013) | Cass Tap - West Atlanta 138-kV T-Line | Cass | Rebuild and Reconductor the Cass Tap to West Atlanta 138-kV transmission line. | 2022-08-15 | 2022-11-22 |  |  | 3187425 |  |  | 99 | 138 |  | 1.81 | 795 KCM ACSR "Drake" | Steel, Single Pole | 100 | 1.81 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowners noticed
T10162127 (A20006001) (A20006011) | IPC Domino - IPC Tap Switch 138-kV T-Line | Cass | Rebuild and Reconductor the IPC Domino to IPC Tap Switch 138-kV transmission line. | 2022-09-15 | 2023-03-03 |  |  | 7389905 |  |  | 99 | 138 |  | 2.67 | 795 KCM ACSR "Drake" | Steel, Single Pole | 100 | 2.67 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowners noticed
42966143 (P18215009) | NW Texarkana 345-kV Station: Carrier Tuner | Bowie | Remote end upgrades to support the newly upgraded Lydia 345-kV station. | 2022-09-20 | 2022-11-08 | 2022-12-08 |  | 438880 |  |  | 99 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10130478 (A20006005) | IPC Domino Relay Upgrade | Cass | IPC Domino Substation: Replace line relays on line to West Atlanta and complete associated terminal upgrades. | 2022-11-01 | 2023-03-03 |  |  | 912876 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42965027 (P18231005) | Tenaha 138-kV Substation | Tenaha/Shelby | Update settings and tuner | 2022-11-10 | 2022-11-29 | 2022-12-12 |  | 295543 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10162129 (A20006002) (A20006012) | IPC Tap Switch - Cass Tap 138-kV T-Line | Cass | Rebuild and Reconductor the IPC Tap Switch to Cass Tap 138-kV transmission line. | 2022-12-01 | 2023-12-20 |  |  | 14196277 |  |  | 0 | 138 |  | 14.11 | 795 KCM ACSR "Drake" | Steel, Single Pole | 100 | 14.11 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowners noticed
42907620 (A15706585) | Clarendon REC 69-kV Tap | Donley | Install phase-over-phase (POP) switch | 2023-03-12 | 2023-04-27 |  |  | 1440112 |  |  | 25 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42907595 (A15706583) | Memphis LHEC 69-kV Tap | Hall | Install phase-over-phase (POP) switch | 2023-04-24 | 2023-06-08 |  |  | 1438861 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42908315 (A15706580) | Carey 69-kV Substation | Childress | Install phase-over-phase (POP) switch | 2023-06-02 | 2023-07-18 |  |  | 682491 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10171890 (A20063001) (A20063002) (A20063003) | Mineola - N. Mineola 69-kV T-Line: Rebuild | Mineola/Wood | Rebuild and reconductor the Mineola to N. Mineola 69-kV transmission line to 138-kV standards but will continue to operate at 69 kV. Reconductor-only a 0.80 mile segment of this transmission line on existing concrete structures. | 2023-02-27 | 2023-05-31 |  |  | 5870000 |  |  | 20 | 69 |  | 2.98 | 556.5 ACSR 26/7 "Dove" | Steel, Single Pole | Centerline | 2.98 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowners noticed
T10130443 (A20007001) (A20007002) (A20007005) | Knox Lee - Rock Hill 138-kV Rebuild | Gregg, Rusk, Panola | Rebuild a 7.6-mile section of the Knox Lee to Rock Hill 138-kV transmission line and install OPGW. Replace conductor only on separate 3.7-mile section of the same transmission line. | 2023-04-15 | 2023-12-14 |  |  | 10689701 |  |  | 15 | 138 |  | 11.3 | 795 KCM ACSR "Drake" | Steel, Single Pole | Centerline | 11.3 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowners noticed
A18125001 (T10405233) | Scottsville 138-kV Switch Station Rebuild | Scottsville/Harrison | Rebuild the existing Scottsville 138-kV Switch Station approximately 200 feet to the east of the existing station. | 2023-04-06 | 2023-08-27 |  |  | 4803093 |  |  | 45 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
A18125004 (T10487847) | Pirkey - Scottsville 138-kV T-Line: Retermination | Scottsville/Harrison | Reterminate the Pirkey to Scottsville 138-kV transmission line into the rebuilt Scottsville 138-kV Switch Station. | 2023-04-06 | 2023-08-27 |  |  | 495598 |  |  | 10 | 138 |  | 0.02 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
A18125007 (T10296219) | Longwood - Scottsville 138-kV T-Line Retermination | Scottsville/Harrison | Reterminate the Longwood to Scottsville 138-kV transmission line into the rebuilt Scottsville 138-kV Switch Station. | 2023-04-06 | 2023-08-27 |  |  | 534946 |  |  | 10 | 138 |  | 0.02 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
42635328 (A16926040) (A16926042) | Jefferson Switch - Marshall 138-kV T-Line | Marion, Marshall/Harrison | Rebuild and reconductor the existing Jefferson Switch to Marshall 138-kV transmission line. | 2023-04-21 | 2023-10-04 |  |  | 21651112 |  |  | 0 | 138 |  | 16.6 | 1590 ACSR/AW 54/19 "Falcon" | Steel Mono Pole | 16.6 | Centerline |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowners Noticed
4296267 (A18105003) | Marshall 138-kV Substation | Marshall/Harrison | Upgrade relays to Jefferson Switching Station. | 2023-04-21 | 2023-10-04 |  |  | 1727081 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42963946 (P18246005) | Atlanta - Bloomburg 69-kV T-Line | Cass | Install a permanent shoe-fly along the Atlanta to Bloomburg 69-kV transmission line to contruct the new Bloomburg 69-kV Substation. | 2023-05-08 | 2024-08-08 |  |  | 1201497 |  |  | 0 | 69 |  | 0.14 | 1590 ACSR/AW 54/19 "Falcon" | Steel Mono Pole |  |  | 100 | 0.14 | 16 TAC 25.101 (c)(5)(A) | Landowner consent obtained
T10150662 (A20007012) | Tatum Tap 138-kV Switch | Panola | Replace switches 10594 and 10655 with new 2000A switches. | 2023-06-04 | 2023-12-31 |  |  | 780510 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3)
42907618 (A15706584) | Hedley 69-kV Substation | Childress | Replace existing switch with phase-over-phase (POP) switch | 2023-06-04 | 2023-07-18 |  |  | 457918 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3)