## MonthlyReportForm
Utility Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
0PT04329 (R8444) | Installation for Canyon Wind POI, Scurry County South Switch-Canyon Wind 138 kV Line | City of Dunn, Scurry County | Installation with new single-circuit, steel monopole dead end structures. The installation is at the request of the Canyon Wind. | 2021-07-22 | 2023-11-17 |  | 1412752 | 1483494 |  |  | 99 | na | 138 | 0.28 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | Varies | 0.28 | 25.101(c)(5)(A)
0PT40515 | Gainesville North Switch - Spring 138 kV Line : I-35 Relocation for TxDOT | City of Gainesville, Cooke County | Relocate structures 41/8, 41/9, 42/1, 42/2 and 42/3 adjacent to I-35 in Gainesville, TX. The relocated structures will utilize single circuit concrete or steel H-frames. | 2024-02-05 | 2024-05-15 | [5 empty] | 0 | 138 | na | 0.4 | 795 ACSR Drake | Concrete H-Frame, Steel H-Frame | 100 | 0.4 | na | na | 25.101(c)(5)(F)
0PT40577 | Stone Creek Switch - Gainesville Sub 69 kV Line : I-35 Relocation for TxDOT | City of Gainesville, Cooke County | Relocate structures 4/5, 4/6, 4/7 and 4/8 adjacent to I-35 in Gainesville, TX. | 2024-02-08 | 2024-05-15 | [5 empty] | 0 | 69 | na | 0.3 | 1/0 ACSR Raven | Concrete H-Frame, Steel H-Frame | 147 | 0.3 | na | na | 25.101(c)(5)(F)
0PT38110 (M5278) | Everman Switch - Venus Switch 345 kV Line : Reterminate at Timberview Switch | City of Everman, Tarrant County | Reterminate the Everman Switch - Venus Switch 345 kV Line from Everman Switch to new Timberview Switch. | 2021-08-25 | 2022-05-31 | 2022-05-31 |  | 6350000 |  |  | 100 | 345 | na | 1.18 | 2-1926.9 ACSS/TW Cumberland | Steel 3-Pole, Steel Pole | 150 | 0.28 | 150 | 0.45 | 25.101(c)(5)(A)
0PT38112 (M5278) | Benbrook Switch - Everman Switch 345 kV Line : Retermination at Timberview Switch | City of Everman, Tarrant County | Reterminate the Benbrook Switch - Everman Switch 345 kV Line from the Everman Switch to new Timberview Switch. | 2021-08-26 | 2021-12-22 | 2021-12-22 |  | 3150000 |  |  | 100 | 345 | na | 0.84 | 2- 1926.9 ACSS/TW Cumberland | Steel Pole | 150 | 0.1 | 150 | 0.32 | 25.101(c)(5)(A)
0PT38113 (M5278) | Everman Switch - Cedar Hill Switch 345 kV Line : Retermination at Timberview Switch | City of Everman, Tarrant County | Reterminate the Everman Switch - Cedar Hill Switch 345 kV Line from the Everman Switch to new Timberview Switch | 2021-08-25 | 2022-05-31 | 2022-05-31 |  | 3550000 |  |  | 100 | 345 | na | 1 | 2-1926.9 ACSS/TW Cumberland | Steel Pole | 150 | 0.2 | 150 | 0.3 | 25.101(c)(5)(A)
0PT38114 (M5278) | Everman Switch - DeCordova Switch 345 kV Line : Retermination at Timberview Switch | City of Everman, Tarrant County | Retermination the Everman Switch - DeCordova Switch 345 kV Line from Everman Switch to new Timberview Switch | 2021-08-20 | 2022-05-31 | 2022-05-31 |  | 3150000 |  |  | 100 | 345 | na | 0.92 | 2-1926.9 ACSS/TW Cumberland | Steel Pole | 150 | 0.1 | 150 | 0.36 | 25.101(c)(5)(A)
0PT41810 (R984) | Allen Sw - Monticello Sw 345kV Line: Stouts Creek Cut In | City of Sulphur Springs, Hopkins County | Line work associated with connecting the 345 kV Stouts Creek Switch | 2024-10-15 | 2024-11-14 | [5 empty] | 0 | 345 | na | 0.1 | 2-1926.9 ACSS/TW Cumberland | Steel Pole | 160 | 0.1 | na | na | 25.101(c)(5)(A)
18T65206 (M3047) | Renner Switch- Allen Switch/Plano Tennyson Switch 138 kV Line: Rebuild STR 11/4D - Plano Tennyson | City of Plano, Collin County | Rebuild the existing Renner - Allen/Plano Tennyson 138 kV line with double circuit, bundled conductor | 2021-08-02 | 2021-12-16 | 2021-12-16 |  | 6028557 |  |  | 100 | 138 | na | 3.4 | 2- 959.6 ACSS/TW Suwannee | Steel Pole | 100 | 1.7 | na | na | 25.101(c)(5)(B)
17T62191 0PT39212 0PT45873 0PT45874 0PT45875 (M5155) | Handley SES - Lakewood Sub - Pantego Sub 138 kV Line: Rebuild North and South Circuits | City of Arlington, Tarrant County | Rebuild the Handley SES - Lakewood Sub - Pantego Sub North and South Circuits (Phase 1) of the Handley SES - Sherry 138 kV Line. | 2021-07-01 | 2021-12-29 | 2021-12-29 |  | 9533605 |  |  | 100 | 138 | na | 3.8 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 3.8 | na | na | 25.101(c)(5)(B)
0PT38695 (R463) | Waco West Switch – Waco East Switch 138kV Line: Rebuild Waco West Switch - Structure 1/8 Line Section | City of Waco, McLennan County | Rebuild the 10.6-mile Waco West Switch - Structure 1/8 138 kV line section of the Waco West Switch – Waco East Switch 138 kV Line. | 2021-02-10 | 2021-12-16 | 2021-12-16 |  | 20528867 |  |  | 100 | 138 | na | 10.6 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 10.6 | na | na | 25.101(c)(5)(B)
0PT42378 | Handley-Liggett 138 kV: SE Connector Relocation For TxDOT | City of Fort Worth, Tarrant County | Relocation with new double circuit, steel monopole, tangent & dead end structures. | 2021-04-21 | 2022-03-02 | 2022-03-02 |  | 2474886 |  |  | 100 | 138 | na | 2 | 959.6 ACSS/TW Suwannee | Steel 2-Pole, Steel Pole | varies | 1.0021 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT42380 | Handley-Saginaw 138 kV: SE Connector Relocation For TxDOT | City of Fort Worth, Tarrant County | Relocation with new double circuit, steel monopole, tangent & dead end structures. | 2021-04-26 | 2021-11-19 | 2021-11-19 |  | 2560873 |  |  | 100 | 138 | na | 2 | 1926.9 ACSS/TW Cumberland | Steel Pole | varies | 0.99527 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT42381 | Handley-Richland Hills 69 kV: SE Connector Relocation For TxDOT | City of Fort Worth, Tarrant County | Relocation with new single circuit, steel monopole, tangent & dead end structures. | 2021-05-14 | 2021-11-03 | 2021-11-03 |  | 2236717 |  |  | 100 | 69 | na | 0.99 | 959.6 ACSS/TW Suwannee | Steel 2 - Pole. Steel 3 - Pole, Steel Pole | varies | 0.98902 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT42090 (R6097) | Eustace Sub - Pauline Sub 138 kV Line : Rebuild | City of Mabank, Henderson County | Rebuild the 3.8-mile Eustace Sub - Pauline Sub 138 kV Line Section of the 9.3-mile Eustace Southeast Switch (RCEC) - Mabank 138 kV Line Section using a conductor rated for 2071A or greater. New 138 kV double-circuit structures with one circuit in place will be installed. | 2021-09-29 | 2021-11-21 | 2021-11-21 |  | 4835000 |  |  | 100 | 138 | na | 3.8 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 3.8 | na | na | 25.101(c)(5)(B)
0PT40622 (M5222) | Forest Hill Switch - Handley Switch 69 kV Line : Line Conversion To 138 kV (Handley Switch-Duval Section) | City of Fort Worth, Tarrant County | Reterminate the Forest Hill Switch - Handley Switch 69 kV Line at its new terminal location at the Handley Switch Station and at the Duval Switch Station for the 138 kV line conversion. | 2022-10-13 | 2024-05-15 |  |  | 2993815 |  |  | 49 | 69 | 138 | 1.1 | 1233.6 ACSS/TW Yukon, 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 0.8 | 50 | 0.3 | 25.101(c)(5)(B) | Upgrade to 138 kV and extend alignment to Handley 138 kV Station.
0PT40627 (R8523) | Andrews County South Switch - Fullerton Switch 138 kV Line : POI for point of interconnection | Andrews County | Install one span of wire to connect the customer owned transmission line for point of interconnection (POI) | 2024-10-01 | 2025-12-15 | [5 empty] | 0 | 138 | na | 0.03 | 1590 ACSR Falcon | Steel Pole | na | na | 60 | 0.03 | 25.101(c)(5)(A)
0PT43686 (M4323) | Ferris Switch - Waxahachie OCF 69kV Line: Rebuild Ferris - Str 28/253 | City of Waxahachie, Ellis County | Rebuild the structure 17/458 to structure 28/353 section of the Ferris Switch to Waxahachie OCF 69kV Line. | 2022-06-15 | 2022-11-12 | 2022-11-12 |  | 15856613 |  |  | 100 | 69 | na | 11.5 | 959.6 ACSS/TW Suwannee | Steel Lattice Tower, Steel Pole | Varies | 11.5 | na | na | 25.101(c)(5)(B)
0PT43492 0PT44173 0PT44830 (R8563) | North Andrews Switch - Means 138 kV Line: Install Landfill POD to Re-terminate Exxon Means POD | City of Andrews, Andrews County | Establish the Landfill Point of Delivery (POD) by disconnecting the existing Exxon Means Tap from the Andrews North Sw. - McKenzie Draw Sw. 138 kV line and connecting to the Andrews North Sw. - Fullerton Sw. 138 kV line. | 2021-09-15 | 2021-12-20 | 2021-12-20 |  | 1907266 |  |  | 100 | 138 | na | 0.39 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel H-Frame, Steel Pole | 50 | varies | 90 | 0.24 | 25.101(c)(5)(A)
0PT43597 (R8573) | Dermott Switch - Endurance Park Storage POI 138 kV Line : Install line for point of interconnection (POI) | City of Dermott, Scurry County | Install a 138 kV Point of Interconnection (POI). | 2022-01-21 | 2022-09-01 | 2022-09-01 |  | 1027784 |  |  | 100 | na | 138 | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 800 | 0.2 | na | na | 25.101(c)(5)(A)
0PT38463 (R9015) | Big Spring - Buzzard Draw 69 kV: Rebuild the line to operate at 138kV | Howard County | This project is to rebuild the 21 mile section of Big Spring to Buzzard Draw 69 kV Line. | 2021-06-01 | 2021-12-17 | 2021-12-17 |  | 25000000 |  |  | 100 | 69 | 138 | 21.3 | 959.6 ACSS/TW Suwannee | Concrete Pole, Steel H-Frame, Steel Pole | 50 | 21.3 | na | na | 25.101(c)(5)(B) | Temporary work
0PT43543 | Watermill Switch - Seagoville Switch 138 kV Line : Relocate Str. 3/3 and 3/1 | City of Lancaster, Dallas County | The scope of this project entails relocating structures 3/3 and 3/1 on Watermill Switch - Seagoville Switch 138 kV Line. | 2022-09-28 | 2022-12-01 | 2022-12-01 |  | 1193911 |  |  | 100 | 138 | na | 0.5 | 795 ACSR Drake | Steel Pole | 90 | 0.1 | na | na | 25.101(c)(5)(B)
0PT44750 (R8538) | Midland East Switch - Midessa South Switch 138 kV Line : Reterminate | City of Midland, Midland County | Reterminate the Midland East Switch - Midessa South Switch 138 kV Line to the Midland East Switch Station. | 2021-11-17 | 2022-12-07 | 2022-12-07 |  | 462521 |  |  | 100 | 138 | na | 0.25 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 0.25 | na | na | 25.101(c)(5)(A)
0PT44472 (R6151) | Temple Sub - Little River Sub 69 kV Line: Reroute for Little River Road Expansion | City of Temple, Bell County | This project is to re-route and rebuild the section of line affected by the Little River Road Expansion and Blackland Road Extension projects. | 2021-08-22 | 2021-12-21 | 2021-12-21 |  | 785651 |  |  | 100 | 69 | na | 0.35 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 0.35 | na | na | 25.101(c)(5)(B)
0PT45010 (R8581) | Wink Basin Tap No 1 East 69 kV Line: Wink Basin Sub - Wink Gulf Tap 69 kV Section Rebuild | City of Kermit, Winkler County | Rebuild the Wink Basin Sub - Wink Gulf Tap 69 kV section on the Wink Basin Tap No 1 East 69 kV line | 2021-08-03 | 2022-12-15 | 2022-12-15 |  | 3000000 |  |  | 100 | 69 | 138 | 0.91 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 0.91 | na | na | 25.101(c)(5)(B)
0PT44327 0PT46292 (R8581) | Wink Switch - Keystone No 1 East 69 kV Line: Shifting Sands Sub - Wink Gulf Tap 69 kV Section Rebuild | City of Kermit, Winkler County | Rebuild the Shifting Sands Sub - Wink Gulf Tap 69 kV section on the Wink Switch - Keystone No 1 East 69 kV line. | 2021-07-20 | 2022-07-08 | 2022-07-08 |  | 10000000 |  |  | 100 | 69 | 138 | 4 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 4 | na | na | 25.101(c)(5)(B)
0PT44585 (R3023) | Blackwater Draw – Paleo Bess Solar 345 kV Line: Line Interconnection | Hale County | Install a new, single-circuit 345 kV transmission line from Blackwater Draw Switch station dead-end to a Point of Interconnection (“POI”) on a dead-end structure located near the Blackwater Draw Switch east property boundary. | 2022-02-10 | 2023-12-16 |  |  | 976885 |  |  | 99 | na | 345 | 0.2 | 2-959.6 ACSS/TW Suwannee | Steel Pole | na | na | 150 | 0.2 | 25.101(c)(5)(A)
0PT43960 0PT46326 (R985) | Commerce Switch - Scatter Branch Sub 138 kV Line: Rebuild and convert 69 kV Line to 138 kV operation | City of Commerce, Hunt County | Rebuild a section from Commerce Switch to Scatter branch (Str 56/3) of the Commerce Switch - Royse Switch 69 kV Line and convert to 138 kV operation. | 2021-12-17 | 2022-05-09 | 2022-05-09 |  | 12433688 |  |  | 100 | 69 | 138 | 7.4 | 959.6 ACSS/TW Suwannee | Steel Pole | 70 | 7.4 | na | na | 25.101(c)(5)(B)
0PT40680 (M5222) | Forest Hill Switch - Handley Switch 69 kV Line: Convert Bryan Ave Tap to Forest Hill to 138 kV | City of Fort Worth, Tarrant County | Reterminate the Forest Hill Switch - Handley Switch 69 kV Line at its new terminal location at the Marrs Switch Station | 2023-10-30 | 2024-05-15 |  |  | 1148058.55 |  |  | 0 | 69 | 138 | 0.5 | 959.6 ACSS/TW Suwannee | Steel Pole | 100 | 0.5 | na | na | 25.101(c)(5)(C)
0PT38085 (M364) | Plano West Switch - Richardson 138 kV Line : Rebuild | City of Richardson, Dallas County | Upgrade the 3-miles Plano West Switch - Richardson 138 kV Line | 2022-03-01 | 2022-06-20 | 2022-06-20 |  | 12107865 |  |  | 100 | 138 | na | 3 | 2 - 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 3 | na | na | 25.101(c)(5)(C)
0PT04017 (M4250) | Cedar Hill Switch 138 kV Line - Camp Wisdom 138 kV Line (Camp Wisdom - Love Bird Tap) | City of Cedar Hill, Dallas County | Upgrade the 4-mile Love Bird Tap - Camp Wisdom 138 kV Line | 2021-09-23 | 2021-12-16 | 2021-12-16 |  | 6448027 |  |  | 100 | 138 | na | 4 | 2- 959.6 ACSS/TW Suwanee | Steel Pole | 80 | 4 | na | na | 25.101(c)(5)(C)
15T64033 | Mary Avenue 138 kV Line Cut-in | City of Waco, McLennan County | Line Work Associated with Mary Avenue Substation | 2023-09-15 | 2023-10-15 |  |  | 1480576.68 |  |  | 34 | 138 | na | 0.1 | 2-1926.9 ACSS/TW Suwanee | Steel Pole | na | na | varies | 0.1 | 25.101(c)(5)(A)
0PT45248 (R8147) | Midland East Switch - Midland Downtown Sub 138 kV Line : Install Second Circuit From Midland East - Str. 13/8 | City of Midland, Midland County | Install a second circuit onto new double-circuit structures from Midland East Switch to Str. 13/8 for the Midland East Switch - Midland Downtown Sub 138 kV Line. | 2021-10-28 | 2022-06-01 | 2022-06-01 |  | 1076287 |  |  | 100 | 138 | na | 1.05 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 1.05 | na | na | 25.101(c)(5)(C)
0PT43986 (M4324) | Kemp Ranch Switch - Cedar Hill Switch 138 kV Line : Cut-In to Establishing Soap Creek Sw | City of Midlothian, Ellis County | Line work associated with connecting the 138 kV Soap Creek Switch | 2021-12-03 | 2022-06-01 | 2022-06-01 |  | 2150000 |  |  | 100 | 138 | na | 0.58 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 80 | 0.29 | 25.101(c)(5)(A)
0PT38107 0PT45301 (R8147) | Midland East Switch - Spraberry Switch 138 kV Line : Rebuild | City of Midland, Midland County | Rebuild the Midland East Switch - Spraberry Switch 138 kV Line on double-circuit structures with one circuit in place from Midland East Switch to Spraberry Switch. | 2021-10-29 | 2022-06-01 | 2022-06-01 |  | 21717063 |  |  | 100 | 138 | na | 13.7 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 13.7 | na | na | 25.101(c)(5)(B)
0PT45276 | Handley-Lancaster 138 kV: SE Connector Relocation for TxDOT | City of Fort Worth, Tarrant County | Relocation with new double circuit, steel monopole, tangent and angle structures on Handley-Lancaster 138 kV Line. | 2021-10-29 | 2021-11-19 | 2021-11-19 |  | 550521 |  |  | 100 | 138 | na | 0.18 | 795 ACSR Drake | Steel Pole | varies | 0.09 | na | na | 25.101(C)(5)(F) | Relocation is a request and 100% reimbursable by the Texas Department of Transportation.
0PT45221 | Liggett Switch - Norwood Switch 138 kV Line: OPGW | City of Irving, Dallas County | Install OPGW on the Liggett to Norwood 138kV Line. | 2022-02-10 | 2022-04-01 | 2022-04-01 |  | 826932 |  |  | 100 | 138 | na | 12.8 | 959.6 ACSS/TW Suwannee | Steel Lattice Tower | 50 | 6.4 | na | na | 25.101(c)(5)(A)
0PT42892 | Norwood-NW Carrollton 138 kV: I-35 E Phase 2 Relocation for TxDOT | City of Carrollton, Dallas County | Relocation with new double circuit, steel monopole, tangent and dead end structures on Norwood-NW Carrollton 138 kV Line. | 2021-12-27 | 2022-02-02 | 2022-02-02 |  | 793317 |  |  | 100 | 138 | na | 0.22 | 959.6 ACSS/TW Cumberland | Steel 2 - Pole, Steel Pole | 100 | 0.11 | na | na | 25.101(C)(5)(F) | Relocation is a request and 100% reimbursable by the Texas Department of Transportation.
0PT42888 | Liggett-Collin 138 kV: I-35 E Phase 2 Relocation for TxDOT | City of Carrollton, Dallas County | Relocation with new double circuit, steel monopole, tangent structure on Liggett-Collin 138 kV Line. | 2021-10-20 | 2021-11-12 | 2021-11-12 |  | 434549 |  |  | 100 | 138 | na | 0.21 | 2-1590 ACSR Falcon | Steel 2-Pole | 100 | 0.21 | na | na | 25.101(C)(5)(F) | Relocation is a request and 100% reimbursable by the Texas Department of Transportation.
18T65208 (M4088) | Northaven Switch - Morrison Lane Switch 138 kV Line: Rebuild Marsh Lane-Morrison Lane | City of Dallas, Dallas County | Rebuild 3.2 mile section of Northaven Switch - Morrison Lane Switch 138 kV Double Circuit Line from Morrison Lane Switch to Marsh Lane Sub. | 2022-01-10 | 2022-05-16 | 2022-05-16 |  | 10745318 |  |  | 100 | 138 | na | 6.4 | 1926.9 ACSS/TW Cumberland | Steel H-Frame, Steel Pole | 100 | 3.2 | na | na | 25.101(c)(5)(B)
0PT45399 0PT45955 (R8594) | Horseshoe Springs Switch - Riverton Switch 138 kV Line : Install Old Michigan point of delivery (POD) | City of Pecos, Culberson County | Establish Old Michigan POD to Cimarex’s Triple Crown Substation. | 2022-02-16 | 2022-04-01 | 2022-04-01 |  | 1444467 |  |  | 100 | 138 | na | 0.09 | 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 0.03 | 70 | 0.06 | 25.101(c)(5)(A)
0PT45371 | Handley-Duval 138 kV: SE Connector Relocation for TxDOT | City of Fort Worth, Tarrant County | Relocation with new double circuit, steel monopole, tangent structure on Handley-Duval 138 kV Line. | 2021-11-15 | 2021-11-19 | 2021-11-19 |  | 357832 |  |  | 100 | 138 | na | 0.18 | 959.6 ACSS/TW Suwannee | Steel Pole | varies | 0.18 | na | na | 25.101(C)(5)(F) | Relocation is a request and 100% reimbursable by the Texas Department of Transportation.
0PT45108 (M4236) | Royse Switch - Rowlett Sub 138 kV Line : Reconductor Royse Switch to Fate Sub | Royse City, Rockwall County | Reconductor the Royse Switch - 10/10C (Fate Sub) section of the Royse Switch - Rowlett Sub 138 kV Line. | 2022-04-14 | 2022-05-12 | 2022-05-12 |  | 4355202 |  |  | 100 | 138 | na | 3.29 | 2- 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 3.29 | na | na | 25.101(c)(5)(B)
0PT45033 0PT46670 (M5172) | Flat Rock BEPC Switch - Azle Switch 138 kV Line : Rebuild 138 kV Line Section | City of Fort Worth, Tarrant County | Rebuild Oncor’s 5.1 mile portion of the 11.5 mile Weatherford Switch – Flat Rock BEPC POI – Azle Switch 138 kV Line. | 2021-11-23 | 2022-05-15 | 2022-05-15 |  | 5370613 |  |  | 100 | 138 | na | 5.08 | 2 - 959.6 ACSS/TW SUWANNEE, 2 - 959.6 ACSS/TW/E3X SUWANNEE, 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | 5.08 | na | na | 25.101(c)(5)(B) | This line is a shared ownership with Brazos and Brazos will reimburse Oncor for their portion of the cost.
0PT44895 (R8601) | Buzzard Draw Switch - Getty Vealmoor Tap 138 kV Line : Install point of delivery (POD) | City of Big Spring, Howard County | Buzzard Draw Switch - Getty Vealmoor Tap 138 kV Line : Install Wildhorse point of delivery (POD) | 2022-04-06 | 2022-06-01 | 2022-06-01 |  | 1631712 |  |  | 100 | 138 | na | 0.25 | 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H-Frame | 75 | 0.25 | na | na | 25.101(c)(5)(A)
0PT44514 (R8583) | Flintkote South Tap - Flintkote Switch 69 kV Line : Cut-in for Beacon Hill Sub | City of Sweetwater, Nolan County | Line work associated with connecting the 69 kV Beacon Hill Substation | 2021-12-10 | 2022-02-01 | 2022-02-01 |  | 655834 |  |  | 100 | 69 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | 50 | 0.1 | 25.101(c)(5)(A)
0PT44127 (M4320) | Waxahachie Switch - Bardwell Switch 69 kV Line : Rebuild | City of Waxahachie, Ellis County | Rebuild the Waxahachie Switch – Bardwell Lake Switch section of the Hillsboro - Waxahachie 69 kV Line. | 2022-02-01 | 2022-12-31 | 2022-12-31 |  | 12949145 |  |  | 100 | 138 | 69 | 7.9 | 959.6 ACSS/TW Suwannee | Steel Pole | 80 | 7.9 | na | na | 25.101(c)(5)(B)
0PT43899 (R8570) | Eskota Switch - Sweetwater No. 2 Sub 69 kV Line: Rebuild the Flintkote Tap 69 kV section | City of Sweetwater, Nolan County | Upgrade the Flintkote Tap 69 kV Line from the Eskota Switch - Sweetwater No. 2 Sub 69kV Line. | 2021-12-14 | 2022-02-01 | 2022-02-01 |  | 1300842 |  |  | 100 | 69 | na | 1 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 0.5 | na | na | 25.101(c)(5)(B)
0PT43251 (R8258) | Midland East Switch - Falcon Seaboard Switch 345 kV Line : Reterminate at Midland East Switch | City of Midland, Midland County | Reterminate the Midland East Switch - Falcon Seaboard Switch 345 kV Line to the Midland East Switch Station. | 2022-04-12 | 2022-08-01 | 2022-08-01 |  | 1558975 |  |  | 100 | 345 | na | 0.22 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 150 | 0.22 | na | na | 25.101(c)(5)(A)
0PT43250 (R8258) | NTUSU Midland East Switch - Midland County Northwest Switch 345 kV Line : Reterminate | City of Midland, Midland County | Reterminate the Midland East Switch - Midland County Northwest Switch 345 kV Line to the Midland East Switch Station. | 2022-04-06 | 2022-08-01 | 2022-08-01 |  | 2147515 |  |  | 100 | 345 | na | 0.17 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 150 | 0.17 | na | na | 25.101(c)(5)(A)
0PT42416 0PT44921 (M4292) | Payne Switch - Royse City 138 kV Line : Rebuild Audie Murphy POI to Royse Switch | City of Royse, Rockwall County | Rebuild the Audie Murphy POI to Royse Switch section of the Payne Switch - Royse City 138 kV line. | 2022-01-11 | 2022-12-16 | 2022-12-16 |  | 28941915 |  |  | 100 | 138 | na | 13.9 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 13.9 | na | na | 25.101(c)(5)(B)
0PT02808 (M4250) | Cedar Hill Switch 138 kV Line - Camp Wisdom 138 kV Line: Rebuild Cedar Hill Switch - Love Bird Tap Section | City of Cedar Hill, Dallas County | Rebuild a section of the Cedar Hill Switch – Love Bird Tap 138 kV Line. | 2022-01-18 | 2022-12-16 | 2022-12-16 |  | 8189827 |  |  | 100 | 138 | 138 | 5.4 | 2-959.6 ACSS/TW Suwannee | Steel Pole | 80 | 5.4 | na | na | 25.101(c)(5)(B)
0PT44435 (R6159) | Establish Outlaw Switch in the Navarro SW (LST) -Limestone (CNP) 345 kV Line | Cities of Richland, Pursley, and Currie, Navarro County | Cut in the (LST) Navarro SW - (CNP) Limestone 345 kV Line to establish the new Outlaw Switch | 2022-03-05 | 2022-06-01 | 2022-06-01 |  | 1761913 |  |  | 100 | 345 | na | 0.45 | 2 -1926.9 ACSS/TW Cumberland | Steel Lattice Tower | na | na | 335 | 0.45 | 25.101(c)(5)(A)
0PT45887 (R8602) | Buzzard Draw Switch – Getty Vealmoor Tap 138 kV Line: Install High Plains point of delivery (POD) | City of Big Spring, Howard County | Establish High Plains point of delivery (POD) | 2022-09-22 | 2022-12-01 | 2022-12-01 |  | 1335866 |  |  | 100 | 138 | na | 0.3 | 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H-Frame, Steel Pole | na | na | 70 | 0.3 | 25.101(c)(5)(A)
0PT44765 (R6152) | Mankin Switch – Kaufman Northwest Switch 138 kV Line: Will White point of interconnection (POI) | City of Tool, Henderson County | Establish the Will White point of interconnection (POI) | 2022-02-21 | 2022-04-01 | 2022-04-01 |  | 1730834 |  |  | 100 | 138 | na | 0.03 | 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H-Frame | 70 | 0.03 | na | na | 25.101(c)(5)(A)
0PT44767 0PT45247 (R6170) | Iron Bridge Tap - Ables Springs Tap West 138 kV Line: Kitsee POI for Rayburn's Duck Cove Sub | City of Terrell, Kaufman County | Establish Kitsee POI for Rayburn Country Electric Cooperative’s Duck Cove substation. | 2022-03-23 | 2022-10-20 | 2022-10-20 |  | 1483316 |  |  | 100 | 138 | na | 0.29 | 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H-Frame, Steel Pole | 70 | 0.04 | varies | 0.25 | 25.101(c)(5)(A)
0PT43905 0PT46229 (R6137) | Duck Cove Tap #1 - Wills Point Sub 69 kV Line: Rebuild | City of Wills Point, Van Zandt County | Rebuild the Duck Cove Tap #1 - Wills Point Sub 69 kV | 2022-03-17 | 2022-09-28 | 2022-09-28 |  | 7808064 |  |  | 100 | 69 | 138 | 6.2 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 3.1 | na | na | 25.101(c)(5)(B)
0PT44253 0PT46213 (R3021) | Windmill Switch - AJ Swope Switch 345 kV Line : Wallaby Switch Cut In for point of interconnection (POI) | City of Hereford, Deaf Smith County | Cut in the Windmill Switch - AJ Swope Switch 345 kV Line to establish Wallaby Switch. | 2023-11-27 | 2024-10-17 | [5 empty] | 0 | 345 | na | 0.45 | 2-1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 175 | 0.4 | 410 | 0.05 | 25.101(c)(5)(A)
0PT45834 0PT46000 (R8569) | SL Salt Flat Road - SkyWest 138 kV Line: Rebuild | Midland County | Rebuild the Salt Flat Road - SkyWest 138 kV line to 1926 ACSS/TW capable structures. | 2022-04-01 | 2022-07-20 | 2022-07-20 |  | 2630091 |  |  | 100 | 138 | na | 1 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 1 | na | na | 25.101(c)(5)(B)
0PT44967 (M4122) | Sterrett Switch - Sardis Switch 138kV Line: Reconfigure Str 31/6 to 31/11 to accommodate Desoto to Sterrett Rebuild | Waxahachie and Ellis County | To accommodate the Desoto to Sterrett Rebuild, structures 31/6 - 31/11 will need to be upgraded and wire transferred to the new structures. | 2022-01-19 | 2022-03-02 | 2022-03-02 |  | 919869 |  |  | 100 | 138 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.2 | na | na | 25.101(c)(5)(B)
0PT44873 0PT47804 (R8600) | McDonald Rd Switch - Spraberry Switch 138 kV Line : Cut-in to Desert Wind Sub | City of Garden City, Glasscock County | Cut-in the McDonald Rd- Switch-Spraberry Switch 138 kV line and the Spraberry Switch-Garden City 69 kV into the new Desert Wind Sub and decommission Garden City | 2022-04-14 | 2022-07-20 | 2022-07-20 |  | 545011 |  |  | 100 | 69/138 | 138 | 0.8 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 0.8 | na | na | 25.101(c)(5)(A)
0PT45324 | China Grove Switch - Paint Creek Sub 138 kV Line : Install new H-Frame Switch at Radium Substation | Jones County | Replace the existing wood 3-pole switch POI structure with a steel H-frame switch re-used from the Ennis Creek project. Install new 3-pole deadend "outrigger" structure. Replace adjacent wood H-frame suspension structures with new wood H-frame suspension structures. | 2022-04-05 | 2022-04-29 | 2022-04-29 |  | 996929 |  |  | 100 | 138 | na | 0.3 | 636 ACSR Grosbeak | Steel H-Frame, Wood H-Frame | 100 | 0.25 | na | na | 25.101(c)(5)(B)
0PT42891 | Norwood-Denton-Bowie 138 kV: I-35 E Phase 2 Relocation for TxDOT | City of Carrollton, Dallas County | Relocation with new double circuit, steel monopole, deadend structures on Norwood-Denton-Bowie 138 kV Line. | 2022-01-08 | 2022-03-02 | 2022-03-02 |  | 3188087 |  |  | 100 | 138 | na | 0.22 | 1926.9 ACSS/TW Cumberland | Steel Pole | varies | 0.11 | na | na | 25.101(C)(5)(F) | Relocation is a request and 100% reimbursable by the Texas Department of Transportation.
0PT44966 (M4122) | Desoto Switch - Sterrett Switch 138kV Line: Rebuild Glenn Heights (BEC) to Sterrett SW | Waxahachie and Ellis County | Upgrade Glenn Heights to Sterrett section of the Desoto Sw- Sterrett Sw 138kV Line. | 2022-01-24 | 2022-05-02 | 2022-05-02 |  | 9629545 |  |  | 100 | 138 | na | 6.2 | 1926.9 ACSS/TW Cumberland | Steel 2 - Pole, Steel Pole | 100 | 6.2 | na | na | 25.101(c)(5)(B)
0PT50023 0PT41140 0PT41166 | Lufkin Switch - Redland Switch 345 kV Line | Angelina County | Construct the new single circuit 345 kV line connecting the existing Lufkin Switch to the existing Redland Switch on double circuit capable structures to accommodate a future 345 kV circuit. | 2025-10-01 | 2026-05-31 |  | 29,250,000 (t-line) 8,252,000 (station) |  |  |  | 0 | na | 345 | 7.92 | 1926.9 ACSS/TW Cumberland | Lattice Steel Towers or Steel Poles | na | na | varies | 7.92 | 55172 | Application Filed 7/13/2023.
0PT44154 (R790) | McGregor Phillips-Harris Creek 69 kV Rebuild | City of McGregor, McLennan County | Rebuild section of Waco West to McGregor Phillips 69kV to establish new Harris Creek Station. | 2022-12-09 | 2022-12-29 | 2022-12-29 |  | 711416 |  |  | 100 | 69 | na | 1.5 | 336.4 ACSR Linnett | Wood 3 - Pole, Wood Pole | Varies | 1.5 | na | na | 25.101(c)(5)(A)
0PT46336 (R990) | Farmersville Switch - Monticello Switch 345 kV North Circuit Line : Install a 345 kV point of interconnection (POI) | Sulphur Springs County | Installing two single circuit 3-pole structures to cut in the Farmersville Switch - Monticello Switch 345kV Line to the new Birthright Switch creating a 345 kV point-of-interconnection (POI) | 2023-03-22 | 2023-05-05 | 2023-05-05 |  | 2122208 |  |  | 100 | 345 | na | 0.9 | 2 - 1590 ACSR Falcon | Steel 3-Pole | 170 | 0.9 | na | na | 25.101(c)(5)(A)
0PT46334 (M5155) | Handley - Sherry 138 kV Line: Rebuild Pantego Sub - Sherry Line Section (North Circuit) | City of Arlington, Tarrant County | Rebuild the Handley-Sherry 138kV Line: Pantego Sub to Sherry Sub | 2022-03-16 | 2022-12-29 | 2022-12-29 |  | 2966653 |  |  | 100 | 138 | na | 5.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 5.1 | na | na | 25.101(c)(5)(C)
0PT37599 0PT39320 (M5155) | Handley - Sherry 138 kV Line: Rebuild Pantego Sub - Sherry Line Section (South Circuit) | City of Arlington, Tarrant County | Rebuild the Handley-Sherry 138kV Line: Pantego Sub to Sherry Sub | 2022-03-18 | 2022-12-28 | 2022-12-28 |  | 10533506 |  |  | 100 | 138 | na | 5.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 5.1 | na | na | 25.101(c)(5)(C)
0PT45598 (M4230) | Venus Switch - Cedar Hill Switch 345 kV Line: Reconductor Britton Road - STR 14/4 | City of Mansfield, Tarrant County | Reconductor the portion of the 345kV Venus Switch - Cedar Hill Switch circuit that goes from Britton Road station to structure 14/4 using a conductor rated for 3200 A or greater. | 2022-03-29 | 2022-11-16 | 2022-11-16 |  | 4461425 |  |  | 100 | 345 | na | 6.2 | 2 -959.6 ACSS/TW Suwannee | Lattice Tower | 150 | 6.2 | na | na | 25.101(c)(5)(B)
0PT43019 (M4230) | Venus Switch - Cedar Hill Switch 345 kV Line: Reconductor Venus Switch - Britton Road | City of Venus, Ellis County | Reconductor the portion of the 345kV Venus Switch - Cedar Hill Switch circuit that goes from Britton Road station to structure 14/4 using a conductor rated for 3200 A or greater. | 2022-12-13 | 2022-12-29 | 2022-12-29 |  | 5674693 |  |  | 100 | 345 | na | 7.4 | 2-959.6 ACSS/TW Suwannee | Lattice Tower | 150 | 7.4 | na | na | 25.101(c)(5)(B)
0PT44572 (R6160) | Hillsboro Substation to Navarro Substation 138 kV Retermination/Shoo-Fly | City of Navarro, Navarro County | Line work associated with new 138kV Revolution Switch Station | 2025-01-20 | 2025-04-17 | [5 empty] | 0 | 138 | na | 0.15 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | na | na | 100 | 0.15 | 25.101(c)(5)(A)
0PT44730 (M4071) | Cedar Crest Switch - Wall Street Sub 138 kV Line: 69 kV to 138 kV Line Conversion | City of Dallas, Dallas County | Line work associated with the conversion of the Cedar Crest - Wall Street Line from 69 kV to 138 kV operation. | 2022-04-06 | 2022-06-17 | 2022-06-17 |  | 514751 |  |  | 100 | 69 | 138 | 0.2 | 959.6 ACSS/TW Suwannee | Steel Pole | 100 | 0.2 | na | na | 25.101(c)(5)(B)
0PT43618 (R990) | Farmersville Switch - Monticello Switch 345 kV South Circuit Line : Install a 345 kV point-of-interconnection (POI) | Sulphur Springs County | Replacing structures 29/4 - 30/2 on the Farmersville Switch - Monticello Switch 345kV Line to allow the north circuit to cut in to the new Birthright Switch station | 2023-03-29 | 2023-05-05 | 2023-05-05 |  | 2570250 |  |  | 100 | 345 | na | 0.9 | 2 -795 ACSR Drake | Steel Lattice Tower | 170 | 0.9 | na | na | 25.101(c)(5)(B)
0PT46322 | Wolf Switch - General Tire Switch 138 kV Line: Judkins Sub Cut-In | Ector County | Reterminate for the rebuild of Judkins substation. | 2022-01-05 | 2022-10-05 | 2022-10-05 |  | 1921953 |  |  | 100 | 138 | na | 0.3 | 1926.9 ACSS/TW Cumberland | Steel Pole, Wood H-Frame | 50 | 0.3 | na | na | 25.101(c)(5)(A)
0PT43467 (M4701) | Monticello Switch - Farmersville Switch 345 kV Line : Line Cut-In to Cyclone Switch | Hopkins County | Cut in the Monticello - Farmersville 345 kV Line to establish the new Cyclone Switching Station | 2022-04-06 | 2022-12-01 | 2022-12-01 |  | 4594824 |  |  | 100 | 345 | na | 0.96 | 2-1926.9 ACSS/TW Cumberland, 2 - 795 ACSR Drake | Steel 3-Pole, Steel Lattice Tower, Steel Pole | 170 | 0.45 | 478 | 0.03 | 25.101(c)(5)(A)
0PT44782 0PT46251 (R6153) | Brushy Creek Switch - Taylor Switch 138kV Line: Rebuild | City of Taylor, Williamson County | Rebuild the Brushy Creek - Taylor 138 kV line. | 2022-02-21 | 2022-12-29 | 2022-12-29 |  | 18400000 |  |  | 100 | 138 | na | 11.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 11.4 | na | na | 25.101(c)(5)(B)
0PT44118 0PT44363 0PT44874 (R8580) | Johnson Draw POD - Flat Iron 138 kV Line | Midland County | Construct the new single-circuit 138 kV line connecting the Johnson Draw POD to the proposed Flat Iron Substation. | 2022-04-27 | 2022-08-10 | 2022-08-10 |  | 5,257,000 (t-line) |  |  | 100 | na | 138 | 2.8 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 70 | 2.8 | 25.101(c)(5)(A) | CCN Application Withdrawn on 10/21/21. Project is proceeding under 25.101(c)(5)(A) as an exempt project under SB 1281. Initial costs have been removed in accordance with the MCPR entry instructions.
0PT46586 | Preston North Sub - Meadow Creek Sub 138 kV Line : Rebuild/Replace Cathodic Protection System | City of Dallas, Dallas County | Replace the cathodic protection system on the Preston North - Meadow Creek 138 kV Line. | 2022-09-30 | 2022-10-01 | 2022-10-01 |  | 284469 |  |  | 100 | 138 | na | na | 1500 AL HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT45398 | Farmersville Switch - Anna Switch 345 kV Line : Insulator Replacement | Collin County | Replace 411 existing polymer insulator assemblies with toughened glass insulator assemblies on the Farmersville - Anna Switch 345 kV Line. | 2022-11-28 | 2023-05-11 | 2023-05-11 |  | 2244627 |  |  | 100 | 345 | na | 25 | 2 - 1590 ACSR Falcon | Steel Lattice Tower | 160 | 25 | na | na | 25.101(c)(5)(B)
0PT39816 | Stanton East Switch - Spraberry Switch 69 kV Line : CMPC Line Hardening (Str. 40/7 - 40/9) | City of Stanton, Martin County | Rebuild the section of the Stanton East Switch - Spraberry Switch 69 kV Line that crosses Interstate 20 in Martin County. | 2022-03-17 | 2022-04-07 | 2022-04-07 |  | 1191328 |  |  | 100 | 69 | na | 0.22 | 959.6 ACSS/TW Suwannee | Steel Pole, Wood Pole | 50 | 0.22 | na | na | 25.101(c)(5)(B)
0PT46197 (R6187) | Sandow Switch - Temple Switch 138 kV Line: Install Tin Roof POD | City of Temple, Bell County | Provide a 138 kV point of delivery (POD) | 2022-03-18 | 2022-06-15 | 2022-06-15 |  | 1037180 |  |  | 100 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland, 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel H-Frame | 100 | 0.3 | 70 | 0.1 | 25.101(c)(5)(A)
0PT46236 (R8581) | Wink Basin Tap No 1 East 69 kV Line: Structure 3/2 - Structure 4/1 69 kV Section Rebuild to 138 kV | City of Kermit, Winkler County | Rebuild the 1.0 mile Structure 3/2 - Structure 4/1 section of the Wink Switch - Keystone No 1 East 69 kV line. | 2022-03-15 | 2022-12-15 | 2022-12-15 |  | 1555655 |  |  | 100 | 69 | 138 | 0.96 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 0.96 | na | na | 25.101(c)(5)(B) | Project previously placed on hold due to permitting; estimated start date updated to reflect initial date of project construction.
0PT46062 (R8581) | Wink Switch - Keystone No 1 East 69 kV Line: Shifting Sands Sub - Wink Gulf Tap 69 kV section rebuild structure 8/7 to Shifting Sands Sub | City of Kermit, Winkler County | Rebuild the 4.0 mile structure 8/7 to Shifting Sands section of the Wink Switch-Keystone No 1 East 69 kV line. | 2022-07-20 | 2022-12-15 | 2022-12-15 |  | 6227141 |  |  | 100 | 69 | 138 | 4 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 4 | na | na | 25.101(c)(5)(B)
0PT45023 (M4071) | Cedar Crest Switch - Industrial Blvd Switch 138 kV Line : Reterminate at Compton Sub | City of Dallas, Dallas County | Reterminate the existing Cedar Crest Switch – Industrial Blvd Switch 138 kV Line into Compton Street Substation. The adjacent Cedar Crest Switch - Dealey Substation 138 kV Line will also have a structure replaced. | 2022-04-05 | 2022-05-16 | 2022-05-16 |  | 679452 |  |  | 100 | 138 | na | 0.2 | 959.6 ACSS/TW Suwannee | Steel Pole | 100 | 0.2 | na | na | 25.101(c)(5)(B)
0PT43740 | Nacogdoches-Chireno 138 kV: SH 21 @ Carizzo Creek Relocation for TxDOT | City of Lufkin, Angelina County | Replace existing wood pole H-frames with two (2) new single-circuit, concrete H-frame tangent structures (Str. 4/2 and 4/3). | 2022-05-26 | 2022-06-08 | 2022-06-08 |  | 591144 |  |  | 100 | 138 | na | 0.36 | 336.4 ACSR Linnett | Concrete H-Frame | 100 | 0.36 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT43246 | East Waco-West Waco, M&M Tap 138 kV: TxDOT Relocation for SH 6 @ Loop 340 | City of Waco, McLennan County | Relocation with new single circuit, steel monopole, tangent & swing angle structures. | 2022-04-04 | 2022-04-26 | 2022-04-26 |  | 1285252 |  |  | 100 | 138 | na | 0.33 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.33 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT45707 0PT47747 (R8581) | Wink Switch - Wink Basin Sub 138 kV Line : 69 kV Conversion to 138 kV | City of Wink, Winkler County | Rebuild Wink Switch - Wink Basin 69 kV section on the Wink Switch - Keystone No 1 East 69 kV Line. | 2023-09-19 | 2023-10-31 |  |  | 3853819 |  |  | 1 | 69 | 138 | 2.9 | 1926.9 ACSS/TW Cumberland | Steel 3-Pole, Steel Pole | 50 | 2.9 | na | na | 25.101(c)(5)(B)
0PT42081 | DFW C East - DFW B East 138 kV Line: Rebuild Cathodic Protection System | City of Dallas, Dallas County | Rebuild the Cathodic Protection System on the DFW C East - DFW B East 138 kV Line. | 2022-10-03 | 2022-10-08 | 2022-10-08 |  | 358970 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.101(c)(5)(B)
0PT43897 0PT43896 0PT48828 (R8570) | Eskota Switch - Sweetwater No. 2 Sub 69 kV Line: Rebuild | City of Sweetwater, Nolan County | Rebuilding 12.2 miles of double circuit wood poles with new steel poles. Installing one circuit. | 2022-06-05 | 2023-05-01 | 2023-05-01 |  | 18576188 |  |  | 100 | 69 | na | 24.2 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 12.2 | na | na | 25.101(c)(5)(B)
0PT43959 0PT46325 (R985) | Caddo Mills Explorer Tap - Caddo Mills Explorer Sub 69 kV Line Rebuild | City of Caddo Mills, Hunt County | Rebuild the Caddo Mills Explorer Tap 69 kV Line. | 2022-06-09 | 2022-12-14 | 2022-12-14 |  | 6069434 |  |  | 100 | 69 | 138 | 3 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 3 | na | na | 25.101(c)(5)(B)
0PT43958 (R985) | Burrow POI - Caddo Mills Explorer Tap 69 kV Line Rebuild | City of Caddo Mills, Hunt County | Rebuild a section from Caddo Mills Explorer Tap to Burrow POI of the Commerce Switch - Royse Switch 69 kV Line. | 2022-05-26 | 2022-12-15 | 2022-12-15 |  | 10835669 |  |  | 100 | 69 | 138 | 4.5 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel H-Frame, Steel Pole | Varies | 4.5 | na | na | 25.101(c)(5)(B)
0PT43548 0PT49066 (R4028) | Baylor - Seymour 69 kV Line : Rebuild | Cities of Mabelle and Seymour, Baylor County | Rebuild the existing 15 mile single circuit wood pole Baylor - Seymour 69 kV line utilizing 138 kV double circuit steel poles with one circuit in place. | 2022-05-08 | 2022-12-06 | 2022-12-06 |  | 25016336 |  |  | 100 | 69 | 138 | 15.1 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | 50 | 15.1 | na | na | 25.101(c)(5)(B)
0PT45995 (R2014) | Big Brown Switch - Richland Chambers Switch 345 kV Line : Raise Line for Pin Oak Switch 138 kV | City of Fairfield, Freestone County | Install one lattice tower to raise line for new Pin Oak Station. | 2022-04-18 | 2022-06-03 | 2022-06-03 |  | 871651 |  |  | 100 | 345 | na | 0.2 | 2-795 ACSR Drake | Steel Lattice Tower | 375 | 0.1 | na | na | 25.101(c)(5)(A)
0PT46736 (M3010) | Rose Hill Switch - Rose Hill Tap 138 kV Line: Reterminate Rose Hill Station | City of Terrell, Kaufman County | Reterminate Rose Hill Switch - Rose Hill Tap 138 kV Line into new Rose Hill Switch Station. | 2022-03-18 | 2022-12-13 | 2022-12-13 |  | 1007982 |  |  | 100 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.3 | 50 | 0.1 | 25.101(c)(5)(A)
0PT46332 0PT47028 (M3010) | Terrell South Switch-Rose Hill Switch 138 kV Line: Reterminate Rose Hill Station | City of Terrell, Kaufman County | Reterminate Terrell South Switch - Rose Hill Switch 138 kV Line into new Rose Hill Switch Station. | 2022-04-01 | 2022-12-13 | 2022-12-13 |  | 879157 |  |  | 100 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT43898 (R8570) | Eskota Switch - Sweetwater No. 2 Sub 69 kV Line: Rebuild the U.S. Gypsum Sub Tap section | City of Sweetwater, Nolan County | Rebuild the 1.37 mile U.S. Gypsum Sub Tap section of the Eskota Switch - Sweetwater No. 2 Sub 69 kV line to DCSP with both circuits installed. | 2022-08-04 | 2022-12-12 | 2022-12-12 |  | 2668839 |  |  | 100 | 69 | na | 2.8 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 1.4 | na | na | 25.101(c)(5)(B)
0PT45724 0PT47700 (R8596) | Andrews North Sub - Mustang Sub 138 kV Line : Rebuild | Andrews County | Rebuild Andrews North Sub - Mustang Sub 138 kV Line. | 2022-06-17 | 2022-12-21 | 2022-12-21 |  | 22845646 |  |  | 100 | 138 | na | 12.9 | 2 - 1926.9 ACSS/TW Cumberland | Steel Pole, Wood 3 - Pole | varies | 12.9 | na | na | 25.101(c)(5)(B)
16T64147 (R6151) | Little River-Holland 69 kV Line: Rebuild | City of Little River-Academy, Bell County | Rebuild the 9.1 mile Little River - Holland 69 kV Line | 2022-06-29 | 2022-11-01 | 2022-11-01 |  | 11553238 |  |  | 100 | 69 | na | 9.1 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 9.1 | na | na | 25.101(c)(5)(B)
0PT46594 | Rivercrest Switch - Clarksville Switch 69 kV Line : Refurbish | Sulphur Springs County | Replacing cross-arms and insulators on the Rivercrest Switch - Clarksville Switch 69 kV Line. | 2022-09-19 | 2023-02-10 | 2023-02-10 |  | 4979413 |  |  | 100 | 69 | na | 18.5 | 336.4 ACSR Linnett | Steel 3-Pole, Steel H-Frame, Steel Pole, Wood H-Frame | 100 | 18.5 | na | na | 25.101(c)(5)(B)
0PT45117 (R5156) | SL Clear Crossing (ETT) - Willow Creek Switch 345 kV Line: Cut-In to establish Thomas Price Switch | Young County | Cut-In to establish Thomas Price Switch. | 2022-10-27 | 2022-12-21 | 2022-12-21 |  | 2626362 |  |  | 100 | 345 | na | 0.2 | 2- 1926.9 ACSS Cumberland | Steel Lattice Tower, Steel Pole | Varies | 0.1 | na | na | 25.101(c)(5)(A)
0PT46658 (R6143) | Sandow Switch - Taylor Sub 138 kV Line: Taylor Sub Retermination | City of Taylor, Williamson County | Reterminate the Sandow - Taylor 138 kV line at the Taylor Station | 2022-11-03 | 2022-12-05 | 2022-12-05 |  | 795232 |  |  | 100 | 138 | na | 0.13 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.13 | na | na | 25.101(c)(5)(A)
0PT46739 (R8605) | Buzzard Draw – Lamesa Switch 138 kV line: Install Hardy Morgan point of interconnection (POI) | City of Lamesa, Dawson County | Establish Hardy Morgan point of interconnection (POI) | 2023-02-23 | 2023-05-31 | 2023-05-31 |  | 1538675 |  |  | 100 | 138 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT43900 (R6142) | Trinidad Sub - Navarro Switch 69 kV Line: Retermination into Creslenn Ranch Switch | City of Trinidad, Henderson County | Reterminate the Trinidad Switch - Navarro Switch from Trinidad Switch to the new Creslenn Ranch Switch | 2022-09-16 | 2022-12-22 | 2022-12-22 |  | 1340348 |  |  | 100 | 69 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H-Frame | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT44949 (R6142) | Trinidad Switch - Palestine Switch 69 kV Line : Retermination into Creslenn Ranch | City of Trinidad, Henderson County | Reterminate the Trinidad Switch - Palestine Switch from Trinidad Sw to the new Creslenn Ranch Switch | 2022-09-15 | 2022-12-22 | 2022-12-22 |  | 1121398 |  |  | 100 | 69 | na | 0.2 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole | 70 | 0.2 | na | na | 25.101(c)(5)(A)
0PT46339 0PT47740 (R8611) | Quarry Field Switch - Wink Switch 138 kV Line : Install Yantis Ranch point of delivery (POD) | City of Wink, Winkler County | Establish Yantis Ranch point of delivery (POD) | 2022-10-14 | 2022-12-04 | 2022-12-04 |  | 2175798 |  |  | 100 | 138 | na | 0.3 | 1926.9 ACSS/TW Cumberland, 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel H-Frame, Steel Pole | 50 | 0.1 | 100 | 0.2 | 25.101(c)(5)(A)
0PT43312 0PT46324 (R8558) | Midland County Northwest Switch - Texaco Mabee Tap 138 kV Line : Rebuild | City of Midland, Midland County | Rebuild the Midland County NW Switch - Texaco Mabee Tap 138 kV Line. | 2022-08-24 | 2022-12-19 | 2022-12-19 |  | 13082826 |  |  | 100 | 138 | na | 13 | 1926.9 ACSS/TW/E3X Cumberland | Steel 2 - Pole, Steel 3 - Pole, Steel H-Frame, Steel Pole | 75 | 6.55 | na | na | 25.101(c)(5)(B)
0PT42879 0PT47805 (R4015) | Bellevue Sub - Bowie Sub 69 kV Line: Rebuild Smith Creek Sub - Tower One Sub 138 kV Line | City of Bowie, Montague County | Rebuild the 10-mile Smith Creek - Tower One 138 kV Line Section of the Burnett - Bowie 69 kV Line using a conductor rated 1649 A or greater. New 138 kV double-circuit structures with one circuit in place will be installed. | 2022-06-20 | 2023-05-26 | 2023-05-26 |  | 11036755 |  |  | 100 | 69 | 138 | 10 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | 50 | 10 | na | na | 25.101(c)(5)(B)
0PT45364 0PT44946 | Wedgwood Switch - Pafford St Switch 138 kV Line : Line Retermination Into New Rosemont Switch | City of Fort Worth, Tarrant County | Reterminate the Wedgwood Switch – Pafford Street Switch 138 kV Line at its new terminal location at the Rosemont Switch. | 2022-11-04 | 2023-10-31 |  |  | 2591809 |  |  | 89 | 138 | na | 0.5 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 55 | 0.25 | 25.101(c)(5)(D)
OPT47396 (R4028) | Seymour Tap - Olney BEPC Switch 69 kV Line : Relocation of 3 Structures | City of Seymour, Baylor County | Relocation and replacement of structure on Seymour Tap - Olney BEPC Switch 69 kV Line. | 2022-10-21 | 2022-12-07 | 2022-12-07 |  | 597852 |  |  | 100 | 69 | na | 0.11 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | 50 | 0.11 | 25.101(c)(5)(B) | This line is a shared ownership with Brazos and Brazos will reimburse Oncor for their portion of the cost.
0PT44759 (M4320) | Bardwell Switch - Italy Sub 69 kV Line : Rebuild | City of Forreston, Ellis County | Rebuild the Bardwell Lake Switch - Italy section of the Hillsboro - Waxahachie 69 kV Line. Bundle existing circuits of the Italy - Hillsboro section of the Hillsboro - Waxahachie 69 kV Line. | 2022-07-25 | 2022-12-31 | 2022-12-31 |  | 11790246 |  |  | 100 | 69 | 138 | 6.1 | 959.6 ACSS/TW Suwannee | Steel Pole | 80 | 6.1 | na | na | 25.101(c)(5)(B)
0PT45495 0PT43815 (M5172) | Handley Switch - Executive Parkway Switch 138 kV Line : Reconductor the Hurst Sub - International Airport Sub 138 kV Line | City of Fort Worth, Tarrant County | Reconductor the Handley Switch - Executive Parkway Switch 138 kV Line between the Hurst Substation - International Airport Substation. | 2022-09-12 | 2022-12-30 | 2022-12-30 |  | 6709213 |  |  | 100 | 138 | na | 11.2 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | 100 | 11.2 | na | na | 25.101(c)(5)(B)
0PT46733 0PT48788 (M5172) | BEPC Flat Rock Tap Switch – BEPC Flat Rock Substation: Rebuild 138 kV Line Section using a conductor rated 2569 A or greater. | City of Weatherford, Parker County | Rebuild the 4.1 mile Oncor owned section of the 6.4-mile Weatherford – BEPC Flat Rock Substation 138 kV Line. | 2022-08-02 | 2022-12-12 | 2022-12-12 |  | 7584140 |  |  | 100 | 138 | na | 8.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 4.1 | na | na | 25.101(c)(5)(B) | This line is a shared ownership with Brazos and Brazos will reimburse Oncor for their portion of the cost.
0PT43481 0PT45336 (M5172) | Weatherford Switch – BEPC Flat Rock Tap Switch 138 kV Line: Rebuild 138 kV Line Section using a conductor rated 2569 A or greater. | City of Weatherford, Parker County | Rebuild the 2.3-mile Oncor owned section of the 6.4-mile Weatherford – BEPC Flat Rock Substation 138 kV Line. | 2022-07-07 | 2022-12-10 | 2022-12-10 |  | 4046458 |  |  | 100 | 138 | na | 2.3 | 1926.9 ACSS/TW Cumberland | Steel H-Frame, Steel Pole | 50 | 2.3 | na | na | 25.101(c)(5)(B) | This line is a shared ownership with Brazos and Brazos will reimburse Oncor for their portion of the cost.
0PT43447 0PT46560 (R2014) | Trinidad Switch - Fairfield West - Long Lake Sub 138 kV Line : Rebuild from Big Brown Tap to Pin Oak Switch 138 kV | City of Trinidad, Henderson County | Rebuild Trinidad Switch-Fairfield West-Long Lake from Big Brown Tap over to structure 4/9 and new cut-in for Pin Oak Switch. | 2022-09-15 | 2023-02-07 | 2023-02-07 |  | 9101916 |  |  | 100 | 138 | na | 8 | 1926.9 ACSS/TW Cumberland | Steel H-Frame, Steel Pole | 225 | 3.5 | 225 | 0.5 | 25.101(c)(5)(B)
0PT46569 | Big Spring Switch - Gunsight Switch 138 kV Line : Crossarm Replacement | City of Big Spring, Howard County | Replace 80 structures on and all crossarms on Big Spring - China Grove - Gunsight 138 kV line. | 2022-09-22 | 2022-12-20 | 2022-12-20 |  | 8846141 |  |  | 100 | 138 | na | 57 | 636 ACSR Grosbeak | Wood H-Frame | Varies | 57 | na | na | 25.101(c)(5)(B)
0PT45684 | D East 1- D East 2 138 kV Line: Rebuild Cathodic Protection | City of Dallas, Dallas County | Rebuild the Cathodic Protection System on the D East 1- D East 2 138 kV Line. | 2022-10-27 | 2022-12-05 | 2022-12-05 |  | 347454 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.101(c)(5)(B)
0PT46166 (R6142) | Trinidad Switch 69 kV Line to Power Plant | City of Trinidad, Henderson County | Reterminate the Luminant Power Plant 69kV from Trinidad Switch to a new POI from the Navarro Switch - Creslenn Ranch Switch 69kV Line | 2022-09-23 | 2022-12-22 | 2022-12-22 |  | 508558 |  |  | 100 | 69 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT46165 (R6142) | Trinidad Switch 138 kV Interconnection Line to Trinidad Autotransformer | City of Trinidad, Henderson County | Line work associated to demolish the Trinidad Switch 69 kV yard, connections remain the same, new structures needed | 2022-09-09 | 2022-12-22 | 2022-12-22 |  | 787396 |  |  | 100 | 138 | na | 0.1 | 795 ACSR Drake | Steel 3 - Pole | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT46163 (6142) | Creslenn Ranch Switch - Trinidad Switch 69 kV Line :New Interconnection | City of Trinidad, Henderson County | Reterminate the Trinidad Switch 69kV Auto Line, create new Creslenn Ranch Switch to Trinidad Switch 69kV Line | 2022-09-07 | 2022-12-22 | 2022-12-22 |  | 536847 |  |  | 100 | 69 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT45941 | Wichita Falls South Switch - Burnett Switch 138 kV Line : CMPC Line Hardening (Str. 7/3 - 7/8) | City of Wichita Falls, Wichita County | Rebuild a section of the Wichita Falls South—Burnett 138 kV line that crosses US-287 in Wichita County. | 2022-11-08 | 2022-12-09 | 2022-12-09 |  | 1874557 |  |  | 100 | 138 | na | 0.9 | 959.6 ACSS/TW Suwannee | Steel Pole, Wood H-Frame | 50 | 0.9 | na | na | 25.101(c)(5)(B)
0PT44950 (R6142) | Trinidad Switch - Athens Switch 69 kV Line : Retermination into Creslenn Ranch | City of Trinidad, Henderson County | Reterminate the Trinidad Switch - Athens Switch from Trinidad Switch to the new Creslenn Ranch Switch | 2022-11-02 | 2022-12-22 | 2022-12-22 |  | 478539 |  |  | 100 | 69 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel Pole | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT46950 0PT48085 (R8612) | Odessa EHV Switch - Monahans - Wolf Switch: Line work for Dry Wind Tap to Sandhills Sub | City of Monahans, Crane County | Establish the Dry Wind Tap and install the new circuit from Dry Wind Tap to Sandhills Sub | 2022-11-12 | 2022-12-16 | 2022-12-16 |  | 3706579 |  |  | 100 | 138 | na | 8.5 | 1926.9 ACSS/TW Cumberland | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 8.1 | varies | 0.4 | 25.101(c)(5)(A)
0PT46954 0PT48954 (R8612) | Wolf Switch - General Tire Switch: Rebuild Sandhills Tap – Sandhills Substation 138 kV line section using double-circuit structures | City of Monahans, Crane County | Rebuild the Sandhills Tap – Sandhills Sub 138 kV line | 2022-09-12 | 2022-12-28 | 2022-12-28 |  | 11133776 |  |  | 100 | 138 | na | 8 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | 50 | 7.8 | varies | 0.2 | 25.101(c)(5)(B)
0PT47613 0PT48959 (R8612) | Wolf Switch - General Tire Switch: Rebuild Sandhills Tap – Dry Wind Tap 138 kV line section using double-circuit structures | City of Monahans, Ector and Crane County | Rebuild the Sandhills Tap - Dry Wind Tap line section on the Wolf Switch - General Tire Switch 138 kV line | 2023-01-13 | 2023-05-30 | 2023-05-30 |  | 7446053 |  |  | 100 | 138 | na | 3.5 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | 50 | 3.3 | varies | 0.2 | 25.101(c)(5)(B)
0PT46660 (R6143) | Temple Sub - Taylor Sub 69 kV Line: Taylor Sub Retermination | City of Taylor, Williamson County | Reterminate the Temple - Taylor 69 kV line at the Taylor Station | 2022-11-03 | 2022-12-05 | 2022-12-05 |  | 1002659 |  |  | 100 | 69 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel Pole, Wood Pole | Varies | 0.1 | na | na | 25.101(c)(5)(A)
0PT46830 (R8610) | Sandhills Tap - Sandhills Sub 138 kV Line: Schumm point of delivery (POD) | City of Monahans, Crane County | Provide a 138 kV point of delivery (POD) on the Sandhills Tap - Sandhills 138 kV Line Section. | 2022-10-12 | 2022-12-28 | 2022-12-28 |  | 2089938 |  |  | 100 | na | 138 | 0.2 | 1926.9 ACSS/TW Cumberland | Steel 3-Pole, Steel H-Frame, Steel Pole | na | na | 70 | 0.2 | 25.101(c)(5)(A)
0PT46632 (R8604) | Horseshoe Springs Switch - Three Mile Draw Switch 138 kV Line : Install Crater Rock Switch for Hayhurst Texas Solar's Allen Sub | City of Orla, Culberson County | Cut-in for Crater Rock 138 kV Switch on the Horseshoe Springs Switch - Three Mile Draw Switch 138 kV Line. | 2022-11-18 | 2022-12-16 | 2022-12-16 |  | 1437763 |  |  | 100 | na | 138 | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | varies | 0.2 | 25.101(c)(5)(A)
0PT46847 (R8609) | Spraberry Switch - Polecat Switch 138 kV line: Establish Meyers Draw point of delivery (POD) | City of Midland, Midland County | Establish Meyers Draw Point of Delivery (POD) | 2023-08-16 | 2023-11-15 |  |  | 3375632 |  |  | 99 | 138 | na | 0.5 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel H-Frame, Steel Pole | 50 | 0.3 | varies | 0.2 | 25.101(c)(5)(A)
0PT46323 | Valley South Sub - Farmersville Switch 345 kV Line: Erosion Control at Structure 24/2 | City of Blue Ridge, Collin County | Relocate structure 24/2 on the Valley South Sub - Farmersville Switch 345 kV Line | 2022-10-18 | 2022-12-21 | 2022-12-21 |  | 819869 |  |  | 100 | 345 | na | 0.2 | 795 ACSR Drake | Steel Lattice Tower | 170 | 0.1 | na | na | 25.101(c)(5)(B)
0PT47169 (R8622) | Quarry Field Switch - Wink Switch 138 kV Line : Install Ashby point of delivery (POD) | Winkler County | Establish the point of delivery (POD) on the Quarry Field Switch – Wink Switch 138 kV Line | 2022-10-25 | 2022-12-01 | 2022-12-01 |  | 2392691 |  |  | 100 | 138 | na | 0.5 | 1926.9 ACSS/TW Cumberland | Steel H-Frame, Steel Pole | 50 | 0.3 | 70 | 0.2 | 25.101(c)(5)(A)
0PT39815 0PT43848 | Stanton East Switch - Spraberry Switch 69 kV Line : CMPC Line Hardening (Str. 26/11 & 26/12) | City of Stanton, Martin County | Rebuild the section of the Stanton East Switch - Spraberry Switch 69 kV Line that crosses IH-20 in Midland, TX. | 2022-12-14 | 2022-12-16 | 2022-12-16 |  | 386820 |  |  | 100 | 69 | na | 0.23 | 4/0 ACSR Penguin | Concrete Pole, Wood Pole | 50 | 0.23 | na | na | 25.101(C)(5)(B)
0PT43962 (R985) | Scatter Branch Sub - Caddo Mills Explorer Tap 69 kV Line: Rebuild Scatter Branch - Caddo Mills Explorer Tap | City of Greenville, Hunt County | Rebuild from Scatter Branch Sub to Caddo Mills Explorer Tap of the Commerce Switch - Royse Switch 69 kV Line. | 2022-10-17 | 2023-05-31 | 2023-05-31 |  | 30785002 |  |  | 100 | 69 | na | 19.1 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 19.1 | na | na | 25.101(c)(5)(B)
0PT46946 (M5222) | Marrs Switching Station – Rolling Hills Substation 138 kV Line: Re-terminate the Marrs Switching Station – Rolling Hills Substation 138 kV Line at Marrs Switching Station | City of Fort Worth, Tarrant County | Re-terminate the Marrs Switching Station – Rolling Hills Substation 138 kV Line at a new terminal location in the Marrs Switching Station to accommodate the for the new Marrs Switching Station | 2024-05-21 | 2024-06-30 |  |  | 877203 |  |  | 0 | 138 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 0.2 | na | na | 25.101(c)(5)(B)
0PT46934 (R8498) | Midland East Sub - Spraberry Switch 138 kV Line : Cut in to Consavvy Switch | City of Midland, Midland County | Loop in the existing Midland East Sub - Spraberry Switch 138 kV Line into Consavvy 138 kV Switch. | 2022-11-01 | 2022-12-14 | 2022-12-14 |  | 1278057 |  |  | 100 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel 2 - Pole, Steel Pole | Station Property | 0.1 | na | na | 25.101(c)(5)(A)
0PT46033 | Kemp Ranch Switch - Sardis Switch 138 kV Line : Reterminate at Midlothian South Sub | City of Midlothian, Ellis County | Reterminate the Kemp Ranch Switch - Sardis Switch 138 kV Line at Midlothian South Sub | 2022-11-17 | 2023-04-24 | 2023-04-24 |  | 1502626 |  |  | 100 | 138 | na | 0.7 | 959.6 ACSS/TW Suwannee | Steel Pole, Wood H-Frame | 100 | 0.7 | na | na | 25.101(c)(5)(A)
0PT45940 | Wichita Falls North Switch - Pleasant Valley Switch 69 kV Line : CMPC Line Hardening (Str. 2/12 - 2/15) | City of Wichita Falls, Wichita County | Rebuild a section of the Wichita Falls North Switch to Pleasant Valley Switch 69 kV across Interstate 44 in Wichita County. | 2022-10-13 | 2022-12-01 | 2022-12-01 |  | 704094 |  |  | 100 | 69 | na | 0.2 | 336.4 ACSR Linnett | Steel Pole, Wood Pole | 40 | 0.2 | na | na | 25.101(c)(5)(B)
0PT45939 | Burnett Switch - Pleasant Valley Switch 69 kV Line : CMPC Line Hardening (Str. 4/11 - 4/14) | City of Wichita Falls, Wichita County | Rebuild the section of the Burnett Switch - Pleasant Valley Switch 69 kV Line that crosses Interstate 44. | 2022-10-26 | 2022-12-01 | 2022-12-01 |  | 1139681 |  |  | 100 | 69 | na | 0.32 | 636 ACSR Grosbeak | Steel Pole, Wood Pole | varies | 0.32 | na | na | 25.101(c)(5)(B)
0PT45538 | Audelia Termination- Lake Highlands 138 kV Line: U.G. Termination Replacement | City of Dallas, Dallas County | Replace the 138 kV Underground Transmission Terminations at Audelia and Lake Highlands Sub. | 2022-11-07 | 2022-11-22 | 2022-11-22 |  | 785485 |  |  | 100 | 138 | na | na | 600 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT45138 (R6164) | Brownwood - Coleman Co. 69 kV and 138 kV Line : Reterminate 138 kV line into Bangs Sub due to Station Rebuild | City of Bangs, Brown County | Line work associated with converting Bangs substation to 138 kV. The work is occurring on the Brownwood - Coleman County 69 kV and 138 kV line. | 2022-11-17 | 2023-03-09 | 2023-03-09 |  | 1199052 |  |  | 100 | 138 | na | 0.6 | 336.4 ACSR LINNETT, 959.6 ACSS/TW SUWANNEE | Steel Pole | varies | 0.3 | na | na | 25.101(c)(5)(A)
0PT44570 (R6160) | Corsicana Sub to Navarro Sub 138 kV Line: Re-terminate at Revolution Switch | City of Corsicana, Navarro County | Modify the Corsicana Substation CB 15015/15020 – Navarro Substation 138 kV transmission line. | 2025-02-05 | 2025-04-17 | [5 empty] | 0 | 138 | na | 0.15 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 100 | 0.15 | 25.101(c)(5)(B)
0PT44528 0PT44520 (R3022) | SL Ogallala - Tule Canyon 345 kV Line: Kress Switch Interconnection | City of Kress, Kress County | Cut-In the Ogallala - Tule Canyon 345 kV Line to establish the new Kress Switch. | 2022-10-13 | 2023-05-26 | 2023-05-26 |  | 1891641 |  |  | 100 | 345 | na | 0.1 | 2 -1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 160 | 0.1 | na | na | 25.101(c)(5)(A)
0PT43720 (R6141) | Lake Creek Switch - Waco West Switch 138 kV Line : Reterminate at Peppervine Switch | City of Waco, McLennon County | Retermination into new Peppervine Switch | 2023-05-01 | 2023-10-15 |  |  | 911267.53 |  |  | 99 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 80 | 0.1 | na | na | 25.101(c)(5)(A)
0PT43678 (R6144) | Brownwood Sub - Dublin Sub 69 kV Line : Proctor Removal | City of Proctor, Comanche County | Remove connector to Proctor Substation to accommodate the removal and decommissioning of Proctor Station | 2023-02-11 | 2023-05-15 | 2023-05-15 |  | 250000 |  |  | 100 | 69 | na | 0.1 | #1 Cu | Wood Pole | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT43477 (M4122) | Desoto Switch - Sterrett Switch 138 kV Line: Rebuild Desoto to Glenn Heights (BEC) | City of Glenn Heights, Dallas and Ellis County | Rebuild the Desoto to Glenn Heights section of the Desoto to Sterrett 138 kV line | 2022-09-27 | 2022-12-06 | 2022-12-06 |  | 4013639 |  |  | 100 | 138 | na | 2.1 | 1926.9 ACSS/ TW Cumberland | Steel 3 - Pole, Steel Pole | 100 | 2.1 | na | na | 25.101(c)(5)(B)
0PT43948 0PT46138 (M4236) | Royse Switch - Rowlett Sub 138 kV Line : Reconductor Fate Sub to Rockwall Sub | Royse City, Rockwall County | Reconductor the Fate Sub - Rockwall Sub section of the Royse Switch - Rowlett 138 kV Line. | 2022-09-30 | 2022-12-01 | 2022-12-01 |  | 13223812 |  |  | 100 | 138 | na | 3.85 | 2-959.6 ACSS/TW Suwannee | Steel H-Frame, Steel Pole | Varies | 3.85 | na | na | 25.101(c)(5)(B)
0PT46763 (M4175) | Lancaster Sub - Desoto Pleasant Run 138 kV Line Reconductor | City of Desoto, Dallas County | Reconductor the 3.6-mile Lancaster Sub - Desoto Pleasant Run section of the Watermill - Cedar Hill 138 kV Line | 2022-11-09 | 2023-01-20 | 2023-01-20 |  | 4973307 |  |  | 100 | 138 | na | 3.6 | 959.6 ACSS/TW/E3X Suwannee | Steel Pole | Varies | 3.6 | na | na | 25.101(c)(5)(B)
0PT45103 (M4175) | Reindeer Sub - Lancaster Sub 138 kV Line: Reconductor | City of Lancaster, Dallas County | Reconductor the Reindeer Sub - Lancaster Sub 138 kV line section | 2022-09-06 | 2022-12-10 | 2022-12-10 |  | 3604361 |  |  | 100 | 138 | na | 2.6 | 959.6 ACSS/TW/E3X Suwannee | Steel Pole | Varies | 2.6 | na | na | 25.101(c)(5)(B)
0PT46762 (M4175) | Watermill Switch - Reindeer Sub 138 kV Line: OPGW Replacement | City of Lancaster, Dallas County | Replace the existing shield wire on the Watermill Switch - Reindeer Sub section of the Watermill Switch - Cedar Hill Switch Sub 138 kV Line. | 2022-09-19 | 2022-11-10 | 2022-11-10 |  | 757645 |  |  | 100 | 138 | na | 2.6 | na | Concrete Pole | Varies | 2.6 | na | na | 25.101(c)(5)(B)
0PT46646 (R6183) | Hillsboro Switch - Navarro Switch 138 kV Line: Install Ash Creek Switch for Pitts Dudik Solar | City of Hubbard, Hill County | Cut in the Navarro - Hillsboro 138 kV Line to establish the new Ash Creek Switch Station. | 2023-03-29 | 2023-04-18 | 2023-04-18 |  | 1163236 |  |  | 100 | 138 | na | 0.31 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.25 | 195 | 0.06 | 25.101(c)(5)(A)
0PT46529 (R6185) | Trinidad Switch - Navarro Switch 138 kV Line : Cut-In for Long Prairie Switch | City of Navarro, Navarro County | Cut in the Trinidad Switch - Navarro Switch 138 kV Line to establish the new Long Prairie Switch Station. | 2022-10-20 | 2022-12-05 | 2022-12-05 |  | 1426002 |  |  | 100 | 138 | na | 0.26 | 1926.9 ACSS/TW Cumberland | Steel Pole | 190 | 0.2 | 180 | 0.06 | 25.101(c)(5)(A)
0PT42423 (M4346) | Rivercrest Switch - Paris Switch 138 kV Line : Eiffel Solar Interconnect at Hawk Hollow Switch | City of Paris, Lamar County | Cut in the Rivercrest Switch - Paris Switch and Paris Switch - Tenaska - Lamar Blossom 138kV Lines to establish the new Hawk Hollow Switch Station. | 2022-09-29 | 2022-12-13 | 2022-12-13 |  | 2121374 |  |  | 100 | 138 | na | 0.16 | 959.6 ACSS/TW Suwannee | Steel Pole | 100 | 0.06 | 340 | 0.02 | 25.101(c)(5)(A)
0PT46497 (M3009) | Paris Switch - Commerce Switch 138 kV Line: Cut-in to establish Crossroads Switch | City of Enloe, Delta County | Cut in the Paris Switch - Commerce Switch 138 kV Line to establish Crossroads Switch Station. | 2022-10-25 | 2022-12-21 | 2022-12-21 |  | 1656164 |  |  | 100 | 138 | na | 0.14 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.01 | 180 | 0.04 | 25.101(c)(5)(A)
0PT39029 | Hurst - Bell 138 kV Line: Bell Helicopter point of delivery (POD) | City of Hurst, Tarrant County | This project will reterminate the Hurst to Bell 138 kV Line into the new Bell Helicopter Owned Sub. | 2022-08-05 | 2023-05-01 | 2023-05-01 |  | 729841 |  |  | 100 | 138 | na | 0.15 | 336.4 ACSR Linnett, 795 ACSR Drake | Steel Pole | 40 | 0.1 | 70 | 0.05 | 25.101(c)(5)(A)
0PT46901 (R8574) | Pegasus South Tap - Quickriver Tap 138 kV Line | City of Odessa, Midland County | Rebuild the Pegasus South Tap - Quickriver Tap 138 kV Line on double-circuit structures with one circuit in place from Pegasus South Tap to Quickriver tap. Cut in the Pegasus South Tap to Pegasus South 138 kV Line to establish the new Quickriver Tap. | 2022-10-05 | 2023-05-26 | 2023-05-26 |  | 8987319 |  |  | 100 | 138 | na | 5.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 5.1 | na | na | 25.101(c)(5)(B)
0PT46966 (R8574) | Pleasant Farms - Pegasus South Tap 138 kV Line | City of Odessa, Midland County | Rebuild the Pleasant Farms - Pegasus South Tap 138 kV Line on double-circuit structures with one circuit in place from Pleasant Farms - Pegaus South Tap. | 2022-12-07 | 2023-05-26 | 2023-05-26 |  | 8454264 |  |  | 100 | 138 | na | 4 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | Varies | 4 | na | na | 25.101(c)(5)(B)
0PT41809 0PT47334 (R8607) | Glass Ranch Switch - Sale Ranch Switch 138 kV Line : Red Sand point of delivery (POD) | City of Midland, Martin County | Establish Red Sand Point of Delivery (POD) | 2022-09-26 | 2022-12-01 | 2022-12-01 |  | 2116406 |  |  | 100 | 138 | na | 0.81 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel H-Frame, Steel Pole | 100 | 0.5 | Varies | 0.34 | 25.101(c)(5)(A)
0PT47762 0PT48228 (R6174) | McGregor Phillips-Harris Creek 138 kV : Rebuild | City of McGregor, McLennan County | Rebuild section of Waco West to McGregor Phillips 69 kV to establish new Harris Creek Station. | 2022-10-17 | 2022-12-31 | 2022-12-31 |  | 3647064 |  |  | 100 | 69 | 138 | 1.35 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 1.35 | na | na | 25.101(c)(5)(A)
0PT43677 0PT48461 (R6144) | Stephenville Switch - Comanche Switch 138 kV Line : Sabana Substation Cut-In | City of Proctor, Comanche County | Line work associated with connecting the new 138kV Sabana Substation. | 2022-10-05 | 2022-11-01 | 2022-11-01 |  | 1194221 |  |  | 100 | 138 | na | 0.25 | 959.6 ACSS/TW Suwannee | Steel Pole | 100 | 0.25 | na | na | 25.101(c)(5)(A)
0PT43718 (R6141) | Waco West Switch - Waco East Switch - Elm Mott Switch 138 kV Line : Reterminate at Peppervine Switch | City of Waco, McLennan County | Retermination into new Peppervine Switch | 2023-07-04 | 2023-10-15 |  |  | 994911.21 |  |  | 99 | 138 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 80 | 0.2 | na | na | 25.101(c)(5)(B)
0PT43719 (R6141) | Waco West Switch - McGregor Phillips - Temple Elm Creek Switch 138 kV Line: Reterminate at Peppervine Switch | City of Waco, McLennon County | Retermination into new Peppervine Switch | 2023-06-05 | 2023-10-15 |  |  | 931322.69 |  |  | 34 | 138 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 80 | 0.2 | na | na | 25.101(c)(5)(B)
0PT43721 (R6141) | Waco East Sub - Waco West Switch 138 kV Line : Reterminate at Peppervine Switch | City of Waco, McLennon County | Retermination into new Peppervine Switch | 2023-06-07 | 2023-10-15 |  |  | 775379.88 |  |  | 67 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | 80 | 0.2 | na | na | 25.101(c)(5)(B)
0PT43727 (R6141) | Waco West Switch - Waco West Sub 138 kV Line : Reterminate at Peppervine Switch | City of Waco, McLennan County | Retermination into new Peppervine Switch | 2023-06-08 | 2023-10-15 |  |  | 954515.47 |  |  | 34 | 138 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 80 | 0.2 | na | na | 25.101(c)(5)(C)
0PT43691 0PT48058 (R6147) | Waco East Switch - Bellmead Sub 69kV Line: Conversion to 138 kV | City of Waco, McLennan County | Conversion to 138 kV as a part of rebuilding the Waco East Switch - Elm Mott Switch 69 kV line conversion to 138 kV operation | 2022-09-11 | 2023-05-26 | 2023-05-26 |  | 9173498 |  |  | 100 | 69 | 138 | 3.8 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 3.8 | na | na | 25.101(c)(5)(B)
0PT47250 | Oakland Sub - Medill Terminal Sub 138 kV Line : Add OPGW | City of Dallas, Dallas County | Install OPGW and 4 splice boxes from Oakland Sub to Medill Terminal Sub. | 2022-12-20 | 2022-12-29 | 2022-12-29 |  | 613962 |  |  | 100 | 138 | na | 2.53 | 336.4 ACSR Linnet | Steel Pole | Varies | 2.53 | na | na | 25.101(c)(5)(A)
0PT47314 (R8498) | Longshore Switch - Odessa EHV Sub 345 kV Line: Cut-In to establish Consavvy Switch | City of Midland, Midland County | Cut-in the Longshore Switch - Odessa EHV Sub double circuit 345 kV line to establish the new Consavvy Switch. | 2022-08-20 | 2022-12-30 | 2022-12-30 |  | 1748991 |  |  | 100 | 345 | na | 0.1 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 120 | 0.1 | na | na | 25.101(c)(5)(A)
0PT46941 (R8498) | Morgan Creek Switch - Quail Switch 345 kV Line : Cut-In to establish Consavvy Switch | City of Midland, Midland County | Cut-In the Morgan Creek Switch - Quail Switch double circuit 345 kV line into the new Consavvy Switch. | 2022-10-07 | 2022-12-28 | 2022-12-28 |  | 2351854 |  |  | 100 | 345 | na | 0.1 | 2- 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 120 | 0.1 | na | na | 25.101(c)(5)(A)
0PT46936 (R8498) | Spraberry Switch - Stanton East Switch 69 kV Line : Reroute around Consavvy Switch | City of Midland, Midland County | Rebuild 0.6 miles of the Spraberry Switch - Stanton East Switch 69kV line around Consavvy 138 kV Switch Station. | 2022-10-25 | 2022-12-14 | 2022-12-14 |  | 2104393 |  |  | 100 | 69 | na | 0.6 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 0.6 | na | na | 25.101(c)(5)(B)
0PT47089 (R6206) | Leon Switch - Cisco 138 kV Line: Retermination into Mountain Branch Sub | City of Eastland, Eastland County | Re-terminate into the New Mountain Branch Sub | 2022-11-22 | 2023-05-01 | 2023-05-01 |  | 499908 |  |  | 100 | 138 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0.1 | na | na | 25.101(c)(5)(B)
0PT44965 (R8479) | Sargent Road Switch - Industrial Blvd Switch 138 kV Line : Rebuild | City of Dallas, Dallas County | Yucca Drive Switching Station – Northern Natural Sub 69 kV Line to establish the new Courtney Creek 138 kV Switching Station | 2024-11-01 | 2025-05-15 | [5 empty] | 0 | 69 | 138 | 1.6 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 0.3 | 70 | 0.5 | 25.101(c)(5)(C)
0PT48355 0PT49178 (R8530) | Moss Switch - Red Lakes Switch 138 kV Line : Rebuild | Odessa County | Rebuild the 14.0 mile Moss Switch - Red Lakes Switch 138 kV line. | 2023-02-20 | 2023-11-15 |  |  | 21838771 |  |  | 94 | 138 | na | 14 | 1926.9 ACSS/TW Cumberland | Steel H-Frame, Steel Pole | 70 | 14 | na | na | 25.101(c)(5)(A)
0PT46925 (R8624) | Barber Lake Switch - Morgan Creek Switch 138 kV Line : Install Moser Canyon point of delivery (POD) | City of Colorado City, Mitchell County | Rebuild 0.4-miles of the Barber Lake Switch - Morgan Creek Switch 138kV Line East Circuit to establish the Moser Canyon point of delivery (POD) | 2023-10-03 | 2023-12-15 |  |  | 2216404.28 |  |  | 6 | 138 | na | 0.39 | 1926.9 ACSS/TW Cumberland, 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel H-Frame, Steel Pole | na | na | 50 | 0.39 | 25.101(c)(5)(A) | The existing ROW width is centerline only easement. This will remain in place to allow for a future circuit. An additional centerline only easement will be acquired, on which the new POD line section will be placed.
0PT48360 0PT49382 (R8606) | SL Consavvy Switch - Pronghorn Switch 138 kV Line: Rebuild | City of Odessa, Odessa County | Rebuild of the Consavvy - Pronghorn section of the S Midland - Pronghorn 138 kV Line | 2022-12-05 | 2023-05-25 | 2023-05-25 |  | 10445048 |  |  | 100 | 138 | na | 7.1 | 1926.9 ACSS/TW Cumberland | Steel 2 - Pole, Steel Pole | 70 | 7.1 | na | na | 25.101(c)(5)(B)
0PT46565 (M4071) | Watermill Switch - Cedar Crest Switch 138 kV Line : Reterminate at Cedar Crest Sub (West) | City of Dallas, Dallas County | Reterminate the Watermill Switch - Cedar Crest Switch 138 kV Line on the east side of Cedar Crest Sub. | 2022-11-15 | 2023-05-10 | 2023-05-10 |  | 631905 |  |  | 100 | 138 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel Pole | 90 | 0.1 | na | na | 25.101(c)(5)(B)
0PT46759 0PT46760 (R8606) | SL South Midland Switch - Cottonfield 138 kV Line: Rebuild | City of Odessa, Odessa County | Rebuild the SL South Midland Switch - Cottonfield 138 kV Line. | 2023-01-27 | 2023-05-26 | 2023-05-26 |  | 4682906 |  |  | 100 | 138 | na | 2.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 1.1 | na | na | 25.101(c)(5)(B)
0PT48075 (R6136) | Fairfield West - Mexia Main 138 kV Line: Retermination into Fairfield West Switch | City of Fairfield, Freestone County | Reterminate the Fairfield West - Mexia Main 138 kV Line at its new terminal location at Fairfield West Switch. | 2022-11-01 | 2023-05-26 | 2023-05-26 |  | 858013 |  |  | 100 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT46882 (R8479) | Yucca Drive Switch - Northern Natural Gas Sub 69 kV Line: Cut-in Courtney Creek Switch - Fort Stockton Switch (AEP) 138 kV Line | City of Grand Falls, Ward County | Cut in the Yucca Drive Switching Station – Northern Natural Sub 69 kV Line to establish the new Courtney Creek 138 kV Switching Station | 2023-01-16 | 2023-05-30 | 2023-05-30 |  | 4178631 |  |  | 100 | 69 | 138 | 0.8 | 1926.9 ACSS/TW Cumberland | Steel 3-Pole, Steel H-Frame, Steel Pole, Wood Pole | 70 | 0.3 | 70 | 0.5 | 25.101(c)(5)(C)
0PT00208 (M3038) | Blackland Switch - Terrell Switch 138 kV Line: Establish Lawrence Substation | City of Terrell, Kaufman County | Establish the Lawrence Substation on the Blackland Switch - Terrell Switch 138 kV Line | 2022-10-19 | 2022-12-15 | 2022-12-15 |  | 1077026 |  |  | 100 | 138 | na | 0.25 | 959.6 ACSS/TW Suwannee | Steel Pole | 70 | 0.25 | na | na | 25.101(c)(5)(A)
0PT45022 (M4071) | Watermill Switch - Cedar Crest Switch 138 kV Line : Reterminate at Cedar Crest Sub (East) | City of Dallas, Dallas County | Reterminate the Watermill Switch - Cedar Crest Switch 138 kV Line on the west side of Cedar Crest Sub. | 2022-11-15 | 2022-12-20 | 2022-12-20 |  | 776715 |  |  | 100 | 138 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel Pole | 90 | 0.1 | na | na | 25.101(c)(5)(B)
0PT47097 (M5136) | Sherry Switch - Fish Creek Switch 138 kV Line : Grand Prairie Associated Line Work (North Circuit) | City of Grand Prairie, Dallas County | Line Work Associated with connecting Grand Prairie Substation for the Sherry Switch - Fish Creek 138 kV Line. | 2022-09-20 | 2023-05-01 | 2023-05-01 |  | 669782 |  |  | 100 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 0.4 | na | na | 25.101(C)(5)(B)
0PT46691 (M5136) | Sherry Switch - Cedar Hill Switch 138 kV Line : Grand Prairie Associated Line Work (South Circuit) | City of Grand Prairie, Dallas County | Line Work Associated with connecting Grand Prairie Substation with Sherry Switch - Cedar Hill Switch 138 kV Line. | 2022-09-16 | 2023-05-30 | 2023-05-30 |  | 1583604 |  |  | 100 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 0.4 | na | na | 25.101(c)(5)(A)
0PT46747 (R6195) | Venus Switch - Sam Switch 345 kV Line : Cut-in to establish Fort Smith Switch | City of Hillsboro, Hill County | Cut in to the Venus Switch - Sam Switch 345 kV Line to establish Fort Smith Switch | 2022-09-26 | 2022-11-16 | 2022-11-16 |  | 1317149 |  |  | 100 | 345 | na | 0.2 | 2-1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 170 | 0.1 | na | na | 25.101(c)(5)(A)
0PT46319 (R788) | Whitney Switch - Stephenville Switch 138 kV Line: Antler Hollow Associated Line Work (North Circuit) | City of Stephenville, Erath County | Line work associated with establishing Antler Hollow Substation. | 2022-10-22 | 2022-12-19 | 2022-12-19 |  | 1003868 |  |  | 100 | 138 | na | 0.2 | 959.6 ACSS/TW Suwannee | Steel Pole | 70 | 0.2 | na | na | 25.101(c)(5)(A)
0PT47477 (R4022) | Holliday Sub - Bowman Switch 138 kV Line : Cut-In to Establish Pecan Tree Sub | City of Holliday, Archer County | This project is to cut-in the Holliday Sub - Bowman Switch 138 kV Line to the planned Pecan Tree Sub. | 2022-12-13 | 2023-04-01 | 2023-04-01 |  | 1579933 |  |  | 100 | 138 | na | 0.33 | 959.6 ACSS/TW Suwannee | Steel 2- Pole | varies | 0.33 | na | na | 25.101(c)(5)(A)
0PT47460 (R4015) | Hopewell - Johnson SS (BEPC) 138 kV Line: Reterminate to establish Hopewell Switch | City of Bowie, Montague County | Reterminate the existing Montague - Johnson SS (BEPC) 69 kV Line at its new terminal location at the new Hopewell Switch. | 2022-10-11 | 2022-12-28 | 2022-12-28 |  | 297610 |  |  | 100 | 69 | 138 | 0.2 | 959.6 ACSS/TW Suwannee | Steel Pole | varies | 0.2 | na | na | 25.101(c)(5)(B) | This line is a shared ownership with Brazos and Brazos will reimburse Oncor for their portion of the cost.
0PT47321 | Mountain Creek Switch - West Levee Switch 138 kV Line : Line Hardening | City of Dallas, Dallas County | Replace 5 poles along the Mountain Creek Switch - West Levee Switch 138 kV Line | 2022-10-20 | 2022-11-07 | 2022-11-07 |  | 1504761 |  |  | 100 | 138 | na | 0.23 | 1926.9 ACSS/TW Cumberland | Steel Pole | 10 | 0.23 | na | na | 25.101(c)(5)(B)
0PT45396 | Graham Switch - Burwick Switch 345 kV Line : Insulator Replacement | City of Graham, Young County | Replacing polymer insulators with toughened glass insulators. | 2022-10-17 | 2022-12-08 | 2022-12-08 |  | 1320366 |  |  | 100 | 345 | na | 18 | 1590 ACSR Falcon | Steel Lattice Tower | Varies | 18 | na | na | 25.101(c)(5)(B)
0PT40247 | EPDC Sub - SOUTH MAIN TERMINAL Sub 138 kV Line : Replace Terminations & Rebuild Cathodic Protection System | City of Fort Worth, Tarrant County | Replace 138 kV Underground Transmission Terminations and rebuild Cathodic Protection System at EPDC SUB. | 2022-09-26 | 2022-10-10 | 2022-10-10 |  | 738236 |  |  | 100 | 138 | na | na | 600 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT46781 (M4702) | Farmersville Switch - Monticello Switch 345 kV Line : Cut-in Saltillo Switch | Hopkins County | Cut in to the Farmersville Switch - Monticello Switch 345 kV Line to establish Saltillo Switch | 2022-09-29 | 2022-11-17 | 2022-11-17 |  | 1656513 |  |  | 100 | 345 | na | 0.35 | 2 -1926.9 ACSS/TW Cumberland | Steel Pole | 170 | 0.31 | 170 | 0.04 | 25.101(c)(5)(A)
0PT46610 0PT48345 (R6184) | Brown Switch - Killeen Switch 345 kV Line : Cut-in to establish Russell Gap Switch | Mills County | Cut - In to Brown - Killeen Switch 345 kV Line to Establish Russell Gap Switch | 2022-11-14 | 2022-12-22 | 2022-12-22 |  | 1999500 |  |  | 100 | 345 | na | 0.21 | 2 -1926.9 ACSS Cumberland | Steel Lattice Tower | 80 | 0.21 | na | na | 25.101(c)(5)(A)
0PT44731 (R788) | Comanche Peak Switch - Stephenville Switch 138 kV Line: Antler Hollow Associated Line Work (South Circuit) | City of Stephenville, Erath County | Line work associated with establishing Antler Hollow Substation | 2022-10-22 | 2022-12-19 | 2022-12-19 |  | 746949 |  |  | 100 | 138 | na | 0.2 | 959.6 ACSS/TW Suwannee | Steel Pole | 70 | 0.2 | na | na | 25.101(c)(5)(A)
0PT43881 (R4022) | Bowman- Graham Switch 138 kV Line: Cut-in to Short Grass Sub | City of Archer, Archer County | Cut in to the Bowman - Graham Switch 138 kV line to establish the new Short Grass Substation | 2022-12-14 | 2022-12-20 | 2022-12-20 |  | 359938 |  |  | 100 | 138 | na | 0.1 | 2- 795 ACSR Drake | Steel Lattice Tower | 120 | 0.1 | na | na | 25.101(c)(5)(A)
0PT47719 | Allen Switch - Plano West Sub 138 kV Line : Structure Replacement | City of Richardson, Collin County | Project will be to replace Structure 1/1C which is located outside of Plano West Substation on the Allen Switch – Plano West 138 kV Line | 2023-04-06 | 2023-04-12 | 2023-04-12 |  | 357732 |  |  | 100 | 138 | na | 0.1 | 795 ACSR Drake | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT48230 0PT49393 (R8326) | Crane Switch - Odessa North Sub 69 kV Line : Cut In to Establish Apple Sub | City of Odessa, Ector County | Cut in to the Crane Switch - Odessa North Sub 69 kV Line to establish Apple Sub | 2022-10-18 | 2022-12-09 | 2022-12-09 |  | 1491907 |  |  | 100 | 69 | na | 0.15 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 0.15 | na | na | 25.101(c)(5)(A)
0PT47462 (R4015) | Hopewell - Joy (BEPC) 138 kV Line: Reterminate to establish Hopewell Switch | City of Bowie, Montague County | Reterminate the existing Montague - Joy SS (BEPC) 69 kV Line at its new terminal location at the new Hopewell Switch. | 2022-10-11 | 2022-12-28 | 2022-12-28 |  | 407914 |  |  | 100 | 69 | 138 | 0.2 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0.2 | na | na | 25.101(c)(5)(B) | This line is a shared ownership with Brazos and Brazos will reimburse Oncor for their portion of the cost.
0PT44238 0PT46722 (R6215) | Taylor Switch - Hutto Switch 138 kV Line: Mallard Switch Cut-in | City of Taylor, Williamson County | Construct the cut-in line for the new Mallard Sw station. | 2022-12-09 | 2023-05-31 | 2023-05-31 |  | 9053879 |  |  | 100 | na | 138 | 1.63 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 140 | 1.63 | 25.101(c)(5)(A)
0PT46992 (R6215) | Brushy Creek Switch - Mallard Switch 138 kV Line: Add Second Circuit from Str. 1/5 to Mallard Switch | City of Taylor, Williamson County | Install a second circuit on the Brushy Creek - Mallard 138 kV line from 1/5A to Mallard | 2023-01-17 | 2023-05-31 | 2023-05-31 |  | 6518660 |  |  | 100 | na | 138 | 6.51 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 6.51 | na | na | 25.101(c)(5)(C)
0PT47713 (R6216) | Pintail Switch - Hutto Switch 138 kV Line: Pintail Switch Cut-in | City of Taylor, Williamson County | Construct the cut-in line for the new Pintail Sw station. | 2023-01-05 | 2023-05-31 | 2023-05-31 |  | 4386190 |  |  | 100 | na | 138 | 1.54 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 140 | 1.54 | 25.101(c)(5)(A)
0PT47710 (R6211) | Pintail Switch - Hutto Switch 138 kV Line: Add Second Circuit from Pintail to Taylor West | City of Taylor, Williamson County | Install a second circuit on the Pintail - Hutto 138 kV line from Pintail to Taylor West | 2023-01-05 | 2023-05-30 | 2023-05-30 |  | 3641439 |  |  | 100 | na | 138 | 2.26 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 2.26 | na | na | 25.101(c)(5)(C)
0PT47934 (R6215) | Mallard Switch - Pintail Switch 138 kV Line : Tie Lines | City of Taylor, Williamson County | Construct the tie line between the Mallard and Pintail switching stations. | 2022-12-05 | 2023-05-30 | 2023-05-30 |  | 756106 |  |  | 100 | na | 138 | 0.16 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | Varies | 0.16 | 25.101(c)(5)(A)
0PT47711 (R6216) | Pintail Switch - SAS FAB1 138 kV Line: Construct New Double Circuit POD Line | City of Taylor, Williamson County | Construct the POD line from Pintail to SAS FAB1 | 2022-12-14 | 2023-05-30 | 2023-05-30 |  | 4627932 |  |  | 100 | na | 138 | 2 | 1926.9 ACSS/TW Cumberland | Steel 2 - Pole, Steel Pole | na | na | Varies | 1 | 25.101(c)(5)(A)
0PT46975 (R6215) | Mallard Switch - SAS FAB1 138kV Line: Construct New Double Circuit POD Line | City of Taylor, Williamson County | Construct the POD line from Mallard to SAS FAB1 | 2022-12-29 | 2023-05-30 | 2023-05-30 |  | 2664714 |  |  | 100 | na | 138 | 1.62 | 1926.9 ACSS/TW Cumberland | Steel 2 - Pole, Steel Pole | na | na | Varies | 0.81 | 25.101(c)(5)(A)
0PT45225 0PT49226 (M4292) | Payne Switch - Royse City 138 kV Line: Rebuild Greenbrier Switch for point of interconnection (POI) | City of Farmersville, Collin County | Rebuild the Greenbrier Switch point of interconnection (POI) | 2023-02-13 | 2023-05-12 | 2023-05-12 |  | 11537572 |  |  | 100 | 138 | na | 3.5 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 3.5 | na | na | 25.101(c)(5)(B)
0PT46074 0PT46072 (R8565) | SL East Stiles Sub - St. Lawrence Sub 138 kV Line: Rebuild | Glasscock and Reagan Counties | Rebuild 13.1 miles of East Stiles – St. Lawrence 138kV Line | 2023-02-24 | 2023-06-29 | 2023-06-29 |  | 15574364 |  |  | 100 | 138 | na | 13.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 90 | 13.1 | na | na | 25.101(c)(5)(B)
0PT46744 (M4126) | Centerville Switch - Centerville Road - Lake Hubbard Switch 138 kV Double-Circuit Line: Reconductor | City of Dallas, Dallas County | Reconductor the Centerville Switch to Lake Hubbard 138 kV Double Circuit line | 2023-01-27 | 2023-12-15 |  |  | 7913000 |  |  | 27 | 138 | na | 13.6 | 959.6 ACSS/TW/E3X Suwannee | Steel Lattice Tower | Varies | 6.8 | na | na | 25.101(c)(5)(B)
0PT43949 0PT46562 (M4236) | Rowlett Sub - Oates Sub 138 kV Line : Rebuild | City of Rowlett & Garland, Dallas County | Rebuild the Rowlett Sub -Oates 138 kV Line. | 2023-08-28 | 2023-12-15 |  |  | 20338645.84 |  |  | 16 | 138 | na | 5.7 | 959.6 ACSS/TW SUWANNEE | Steel Pole | Varies | 5.7 | na | na | 25.101(c)(5)(b)
0PT46764 0PT50786 (M4175) | Desoto Pleasant Run - Desoto Hampton Road 138-kV Line Reconductor | City of Desoto, Dallas County | Reconductor the 2.1 mile Desoto Pleasant Run - Cedar Hill section of the Watermill - Cedar Hill 138 kV Line | 2023-01-23 | 2023-12-31 |  |  | 7987985 |  |  | 19 | 138 | na | 2.1 | 959.6 ACSS/TW/E3X Suwannee | Steel Pole | Varies | 2.1 | na | na | 25.101(c)(5)(B)
0PT45726 0PT48485 (R8596) | Mustang Sub - Paul Davis Tap 138 kV Line : Rebuild | City of Andrews, Andrews County | Rebuild the Mustang Sub - Paul Davis Tap 138 kV Line. | 2023-01-13 | 2023-06-09 | 2023-06-09 |  | 14717483 |  |  | 100 | 138 | na | 12.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 12.1 | 80 | na | na | 25.101(c)(5)(B)
0PT48275 | Hurst - Bell Helicopter 138 kV Line: Structure Modification | City of Hurst, Tarrant County | Replace a structure on the Hurst - Bell Helicopter 138-kV Line | 2022-12-27 | 2022-12-30 | 2022-12-30 |  | 251906 |  |  | 100 | 138 | na | 0.1 | 336.4 ACSR LINNETT | Wood Pole | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT48509 0PT49817 0PT50835 (R4015) | Burnett Switch - Old Lake Switch 69 kV Line: Rebuild Fisher Road - Lanham Tap section to 138 kV | City of Wichita Falls, Wichita County | Rebuild Burnett - Lanham Tap section of the Burnett Switch - Old Lake Switch 69 kV Line to 138 kV. | 2023-01-28 | 2023-12-31 |  |  | 15051629 |  |  | 9 | 69 | 138 | 10.4 | 959.6 ACSS/TW SUWANNEE | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 10.4 | na | na | 25.101(c)(5)(B)
0PT46826 | Trinidad Switch - Eustace Southeast Sub 138 kV Line : Replace Structure 61/8A | City of Trinidad, Henderson County | Replace structure 61/8A due to corrosion of structure leg. | 2024-09-15 | 2024-12-31 |  |  | 489490 |  |  | 0 | 138 | na | 0.01 | 1033.5 ACSR Curlew | Steel H-Frame | 160 | 0.01 | na | na | 25.101(c)(5)(B)
0PT46145 | SL AJ Swope Sub - Alibates Sub 345 kV Line : Galloping Device Installation | Carson County and Potter County | Install spacer dampers and replace hardware on AJ Swope Sub - Alibates Sub 345 kV Line | 2022-12-06 | 2023-03-01 | 2023-03-01 |  | 1592160 |  |  | 100 | 345 | na | 33.8 | 2-1926.9 ACSR/TW Cumberland | Steel Lattice Tower | 175 | 16.9 | na | na | 25.101(c)(5)(B)
0PT46842 0PT48981 (R8304) | Texaco Mabee Tap - Midland East Switch 138 kV Line : Double Circuit Line Rebuild | City of Midland, Midland County | Rebuild the Texaco Mabee Tap to Midland East 138 kV Line. | 2023-02-09 | 2023-12-15 |  |  | 13902212 |  |  | 56 | 138 | na | 15.4 | 1926.9 ACSS/TW Cumberland | Steel 3-Pole, Steel H-Frame, Steel Pole | 75 | 7.7 | na | na | 25.101(c)(5)(B)
0PT46945 (M5222) | Handley Switch – Handley Sub 69 kV Strain Bus: Rebuild and Reconfigure as the Handley Switch - Rosedale Sub 138 kV Line | City of Fort Worth, Tarrant County | Re-terminate the Handley Switching Station – Handley Substation 69 kV Strain Bus at its new terminal location at the Handley Switching Station | 2022-10-13 | 2024-05-15 |  |  | 1602887 |  |  | 1 | 69 | 138 | 0.3 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel H-Frame, Steel Pole | 50 | 0.3 | na | na | 25.101(c)(5)(B)
0PT47517 | NW Carrollton Sub - Gainesville Sub 138 kV Line : Relocation for City of Denton Hickory Creek Road | City of Denton, Denton County | Relocate the NW Carrollton - Gainesville 138 kV Line at the request of the City of Denton | 2022-11-29 | 2022-12-03 | 2022-12-03 |  | 1077549 |  |  | 100 | 138 | na | 0.5 | 795 ACSR Drake | Concrete H-Frame | 100 | 0.5 | n/a | n/a | 25.101(c)(5)(F) | Relocation is at the request of the City of Denton and is 100% reimbursable by the City of Denton.
0PT47380 (R8625) | Spraberry Switch - Polecat Switch 138 kV Line: Install Stephenson Lake point of delivery (POD) | City of Midland, Midland County | Establish Stephenson Lake Point of Delivery (POD) on the Spraberry-Polecat 138 kV Line | 2023-02-15 | 2023-05-12 | 2023-05-12 |  | 2205610 |  |  | 100 | 138 | na | 0.7 | 1926.9 ACSS/TW Cumberland | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 0.4 | varies | 0.3 | 25.101(c)(5)(A)
0PT47315 (R6207) | Lake Creek Switch - Jewett Switch 138 kV Line: Install Riesel Switch | City of Riesel, Falls County | Cut into the Lake Creek - Jewett 138 kV Line to establish the new Riesel Switch | 2023-04-18 | 2023-05-11 | 2023-05-11 |  | 1438247.25 |  |  | 100 | 138 | na | 0.3 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.2 | varies | 0.1 | 25.101(c)(5)(A)
0PT47771 (R6213) | Temple Switch - Lake Creek Switch 345 kV Line: Cut-in to Establish Belfalls Switch | City of Temple, Bell County | Cut into the Temple - Lake Creek 345 kV Line to establish the new Belfalls Switch. | 2023-09-20 | 2023-11-16 |  |  | 2642326.09 |  |  | 59 | 345 | na | 0.34 | 2-1926.9 ACSS/TW Cumberland | Steel Lattice Tower, Steel Pole | 125 | 0.34 | na | na | 25.101(c)(5)(A)
0PT47738 (R6210) | Bell County East Switch - TNP One (TNMP) Switch 345 kV Line : Cut-in to establish Hog Creek Switch | Milam County | Cut into the Bell County East-TNP One (TNMP) 345 kV Line to establish the new Hog Creek Switch | 2023-03-21 | 2023-05-12 | 2023-05-12 |  | 2548516 |  |  | 100 | 345 | na | 0.2 | 2 -1926.9 ACSS/TW Cumberland | Steel Lattice Tower, Steel Pole | 160 | 0.1 | varies | 0.1 | 25.101(c)(5)(A)
0PT46644 0PT47903 (R8614) | Sale Ranch Switch - Natural Dam Switch 138 kV Line : Install Rock Lake point of delivery (POD) | City of Stanton, Martin County | Provide a 138 kV point of delivery (POD) on the Sale Ranch - Natural Dam 138 kV Line | 2024-02-19 | 2024-04-01 | [5 empty] | 0 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel 3-Pole, Steel H-Frame, Steel Pole | na | na | 70 | 0.4 | 25.101(c)(5)(A)
0PT47431 | Medill Sub - East Network Sub 138 kV Line: Rebuild/Replace Cathodic Protection | City of Dallas, Dallas County | Replace the cathodic protection system on the Medill Sub-East Network Sub 138 kV Line. | 2023-02-08 | 2023-03-09 | 2023-03-09 |  | 300985 |  |  | 100 | 138 | na | na | 1250 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT49021 | NTUSU Luther - Vealmoor 138 kV: High Temp Upgrade | Howard County | Install shunts required to increase the 9.84 mile Luther - Vealmoor 138 kV line maximum operating temperature. | 2022-12-28 | 2023-01-02 | 2023-01-02 |  | 294567 |  |  | 100 | 138 | na | 9.84 | 795 ACSR Drake | Steel Pole | varies | 9.84 | na | na | 25.101(c)(5)(A)
0PT47706 (M4330) | Haggerty Switch Station - MEMC Southwest Substation (North) 138 kV Line | City of Sherman, Grayson County | Reroute the North MEMC Southwest Tap 138kV single circuit line 0.6 miles into the new Haggerty 138 kV Switch Station. | 2023-03-07 | 2023-10-15 |  |  | 1876123 |  |  | 83 | 138 | na | 0.6 | 2-959.6 ACSS/TW Suwannee | Steel Pole | na | na | 100 | 0.6 | 25.101(c)(5)(B)
0PT47674 (M4330) | Haggerty Switch Station: Sherman TI 138 kV Tie Line to XFMR #2 | City of Sherman, Grayson County | Build the new tie line between the new Haggerty 138 kV Switch Station and existing Sherman TI Substation (XFMR #2) | 2023-01-18 | 2023-04-14 | 2023-04-14 |  | 935544 |  |  | 100 | na | 138 | 0.1 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | varies | 0.1 | 25.101(c)(5)(B)
0PT47676 (M4330) | Haggerty Switch Station: Sherman TI 138 kV Tie Line to XFMR #1 | City of Sherman, Grayson County | Build the new tie line between the new Haggerty 138 kV Switch Station and existing Sherman TI Substation (XFMR #1) | 2023-01-17 | 2023-04-13 | 2023-04-13 |  | 875782 |  |  | 100 | na | 138 | 0.1 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | varies | 0.1 | 25.101(c)(5)(B)
0PT47705 (M4330) | Valley-Anna 138 kV Line: Establish Haggerty 138 kV Switch | City of Sherman, Grayson County | Reroute the Valley/Anna 138kV double circuit line 0.3 miles into the new Haggerty 138 kV Switch Station | 2023-01-23 | 2023-05-24 | 2023-05-24 |  | 3333681 |  |  | 100 | 138 | na | 1.2 | 2-959.6 ACSS/TW Suwannee | Steel Pole | 80 | 0.3 | varies | 0.3 | 25.101(c)(5)(B)
0PT48310 (M4330) | Haggerty Switch Station: 138kV Line to TI SM1-1 | City of Sherman, Grayson County | Build the new line between the new Haggerty 138 kV Switch Station and new TI SM1-1 | 2023-05-09 | 2023-11-28 |  |  | 2019065 |  |  | 96 | na | 138 | 1 | 2-959.6 ACSS/TW Suwannee | Steel Pole | na | na | varies | 1 | 25.101(c)(5)(B)
0PT48311 (M4330) | Haggerty Switch Station: 138 kV Line to TI SM1-2 | City of Sherman, Grayson County | Build the new line between the new Haggerty 138 kV Switch Station and new TI SM1-2 | 2023-05-10 | 2023-11-28 |  |  | 2025804 |  |  | 93 | na | 138 | 1 | 2-959.6 ACSS/TW Suwannee | Steel Pole | na | na | varies | 1 | 25.101(c)(5)(B)
0PT47391 (R8619) | Wolf Switch - Moss Switch 345 kV Line : Cut-in Meteor Switch 345 kV | City of Odessa, Ector County | Cut in the Wolf Switch - Moss Switch 345 kV Line to establish the new Meteor Switch 345 kV | 2024-09-02 | 2024-12-12 | [5 empty] | 0 | 345 | na | 0.1 | 2-1926.9 ACSS/TW Cumberland | Steel Lattice Tower | na | na | 180 | 0.1 | 25.101(c)(5)(A)
0PT47792 (M5324) | Jacksboro Switch - Krum West Switch 345 kV Line : Cut-in Bird Dog Switch | Denton County | Cut in the Jacksboro Switch - Krum West Switch 345 kV Line to establish the new Bird Dog Switch | 2023-02-13 | 2023-05-16 | 2023-05-16 |  | 1381905 |  |  | 100 | 345 | na | 0.1 | 2- 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | na | na | 366 | 0.1 | 25.101(c)(5)(A)
0PT47803 (M5326) | Watermill Switch - Parkdale Switch 138 kV Line: Cut-in Lavender Switch | Dallas County | Cut in the Watermill Switch - Parkdale Switch 138 kV Line to establish the new Lavender Switch | 2023-03-04 | 2023-05-30 | 2023-05-30 |  | 1675797 |  |  | 100 | 138 | na | 0.8 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | 100 | 0.4 | 25.101(c)(5)(A)
0PT48967 (M5326) | Lavender Switch – SDC Wilmer (Focus) 138kV Line: Station Tie Lines Build | Dallas County | Built the two (2) new tie lines between Oncor's Lavender station and Stream's Focus station | 2023-03-15 | 2023-11-15 |  |  | 784840 |  |  | 99 | na | 138 | 0.2 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | varies | 0.1 | 25.101(c)(5)(A)
0PT48536 0PT49159 (R8642) | SL Pronghorn - Salt Flat Road 138 kV Line: Rebuild | Midland County | Rebuild the Pronghorn-Salt Flat Road 138 kV line to 1926 ACSS/TW capable structures. | 2023-08-14 | 2023-12-01 |  |  | 13100797 |  |  | 27 | 138 | na | 7.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | varies | 7.2 | na | na | 25.101(c)(5)(B)
0PT47467 | DFW B East - DFW C East 138 kV Line: Replace U.G Terminations | City of Dallas, Dallas County | Replace six 138 kV Underground Transmission Terminations at DFW B East - DFW C East. | 2024-05-08 | 2024-06-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.101(c)(5)(B)
0PT49323 0PT49343 (R8606) | Grey Well Draw - Consavvy 138 kV Line: Install 2nd Circuit | City of Midland, Midland County | Establish a line section between Grey Well Draw and Consavvy by adding a second circuit to the existing Midland E – Spraberry 138 kV Line. | 2022-11-14 | 2022-12-21 | 2022-12-21 |  | 3018279 |  |  | 100 | 138 | na | 2.9 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 2.8 | 70 | 0.1 | 25.101(c)(5)(C)
0PT47279 (M4331) | Kemp Ranch Switch - Sardis Switch 138 kV Line : Cut-in Newton Branch Sub | City of Midlothian, Ellis County | Cut in the Kemp Ranch Switch - Sardis Switch 138 kV Line to establish the new Newton Branch Substation. | 2023-10-16 | 2024-01-15 |  |  | 1420628.9 |  |  | 0 | 138 | na | 0.06 | 2-959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0.06 | na | na | 25.101(c)(5)(A)
0PT49020 (M4236) | Royse Switch - Rowlett Sub 138 kV Line : Reconductor Rockwall Sub to Rowlett Sub | City of Royse, Rockwall County | Reconductor the Rockwall Sub - Rowlett Sub section of the Royse Switch - Rowlett 138 kV Line. | 2023-01-17 | 2023-05-15 | 2023-05-15 |  | 4630726 |  |  | 100 | 138 | na | 6.03 | 2-959.6 ACSS/TW Suwannee | Steel Pole | Varies | 6.03 | na | na | 25.101(c)(5)(B)
0PT47545 | North Network Sub - Bryan Sub 138 kV Line | City of Dallas, Dallas County | Replace six 138 kV Underground Transmission Terminations at North Network-Bryan Sub 138kV. | 2024-11-22 | 2024-12-15 | [5 empty] | 0 | 138 | na | na | 1500 AL HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT48531 (M3015) | Krum West Switch - Hummingbird Storage POI 345 kV Line: Install Line | Denton County | Build a 345 kV Point of Interconnection (POI) to KCE TX 10, LLC Hummingbird Storage from Krum West Switch | 2023-02-23 | 2023-12-15 |  |  | 1132115 |  |  | 99 | na | 345 | 0.18 | 2-1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 160 | 0.18 | na | na | 25.101(c)(5)(A)
0PT48339 0PT48464 (R6094) | Athens - Tyler Switch 69 kV: Rebuild Murchison to Str 33/1 to 138 kV | City of Murchison, Henderson County | Rebuild a 6.7 miles section of the Athens to Tyler Switch 69 kV line as a 138 kV double circuit line with only one circuit installed. | 2023-03-07 | 2023-06-28 | 2023-06-28 |  | 12690433 |  |  | 100 | 69 | 138 | 6.7 | 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H-Frame, Steel Pole | Centerline | 6.7 | na | na | 25.101(c)(5)(B)
0PT48089 (M5359) | Hicks Switch - Roanoke Switch 138 kV Line : Install Elizabethtown point of interconnection (POI) | City of Fort Worth, Denton County | Cut in the Hicks Switch - Roanoke Switch 138 kV Line to establish the new Elizabethtown POI | 2023-03-06 | 2024-03-15 |  |  | 1665582 |  |  | 87 | 138 | na | 0.22 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 60 | 0.11 | 25.101(c)(5)(A)
0PT48102 (M4352) | Greenville Avenue Switch - Lomo Alto Sub 138 kV Line : Relocate Line Section for Station Rebuild | City of Dallas, Dallas County | Relocate 4 structures of the Greenville Avenue Switch - Lomo Alto 138 kV Line. | 2023-02-13 | 2023-05-01 | 2023-05-01 |  | 1773939 |  |  | 100 | 138 | na | 0.28 | 1926.9 ACSS/TW Cumberland | Steel Pole, Wood Pole | Station Property | Station Property | na | na | 25.101(c)(5)(D)
0PT47753 (R6208) | Bell County East Switch - Chillingham POI 345 kV Line: Install Line for point of interconnection (POI) | Bell County | Establish a 345 kV point of interconnection (POI). | 2024-01-15 | 2024-05-15 | [5 empty] | 0 | na | 345 | 0.21 | 2-959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel Pole | na | na | 120 | 0.21 | 25.101(c)(5)(A)
0PT47754 (R6209) | Bell County East Switch - Five Wells POI 345 kV Line: Install Line for point of interconnection (POI) | Bell County | Establish a 345 kV point of interconnection (POI). | 2023-02-28 | 2023-05-18 | 2023-05-18 |  | 2176480 |  |  | 100 | 345 | na | 0.3 | 2-959.6 ACSS/TW Suwannee | Steel 3-Pole | na | na | 160 | 0.21 | 25.101(c)(5)(A)
0PT47990 (R6209) | Bell County East Switch - TNP ONE Switch 345 kV Line : Raise Structure 1/2 | Bell County | Modify a section of BCE-TNP ONE 345 kV line. | 2023-03-10 | 2023-05-12 | 2023-05-12 |  | 1287749 |  |  | 100 | 345 | na | 0.82 | 2-1590 ACSR Falcon | Steel Lattice Tower | 160 | 0.41 | na | na | 25.101(c)(5)(B)
0PT49337 (M3019) | Decordova Switch – Carmichael Bend Switch 138 kV Line: Reconductor | City of Granbury, Hood County | Reconductor the Decordova Switch - Carmichael Bend Switch 138 kV line where it crosses Lake Granbury. | 2023-04-18 | 2023-05-12 | 2023-05-12 |  | 1744456 |  |  | 100 | 138 | na | 0.5 | 954 ZTACCR/TW C7 - TS | Steel Lattice Tower | varies | 0.5 | na | na | 25.101(c)(5)(B)
0PT49060 | Sargent Road Switch - West Levee Sub 345 kV Line : Replace OPGW | City of Dallas, Dallas County | The existing OPGW between West Levee and Sargent Road is damaged and no spare fibers exist. This project is to replace the existing OPGW. | 2024-02-16 | 2024-06-15 | [5 empty] | 0 | 345 | na | 5.1 | 1590 ACSR Falcon | Steel Pole | Varies | 5.1 | na | na | 25.101(c)(5)(B)
0PT49001 | Graham Plant Switch - Cook Field Road Switch 345 kV Line : Relocate structure 27/6 | Stephens County | Rebuild a section of the Graham Plant Switch - Cook Field Road Switch 345 kV Line | 2024-04-01 | 2024-06-15 | [5 empty] | 0 | 345 | na | 1.4 | 2 - 795 ACSR Drake | Steel Lattice Tower | 120 | 0.7 | na | na | 25.101(c)(5)(B)
0PT48650 | Odessa EHV – Spraberry 138 kV Line: Salt Lake Substation Cut-In | City of Midland, Midland County | Line work associated with establishing a new transformer on Salt Lake Substation | 2023-04-10 | 2023-06-30 | 2023-06-30 |  | 807217 |  |  | 100 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 75 | 0.1 | na | na | 25.101(c)(5)(A)
0PT48629 | Watermill Switch - Sargent Road Switch 345 kV Line : Replace OPGW | City of Dallas, Dallas County | Replace the OPGW on the Watermill Switch - Sargent Road Switch 345 kV Line. | 2024-01-17 | 2024-06-15 | [5 empty] | 0 | 345 | na | 12.6 | 1590 ACSR Falcon | Steel Pole | varies | 12.6 | na | na | 25.101(c)(5)(B)
0PT47591 | Watermill Switch - Seagoville Switch 138 kV Line : Replace Structures 9/1 and 9/4 | City of Wilmer, Dallas County | Replace structures on Watermill Switch - Seagoville Switch 138 kV Line | 2024-01-09 | 2024-12-01 | [5 empty] | 0 | 138 | na | 0.3 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.3 | na | na | 25.101(c)(5)(B)
0PT48745 | Jewett Switch - Lake Creek Switch 138 kV Line : Replace structure 31/2 with steel H-frame | Limestone County | Replace structure on Jewett Switch - Lake Creek Switch 138 kV Line. | 2023-02-15 | 2023-03-01 | 2023-03-01 |  | 298350 |  |  | 100 | 138 | na | 0.5 | 795 ACSR Drake | Steel H-Frame | 100 | 0.5 | na | na | 25.101(c)(5)(B)
0PT48983 | Krum Switch - Jacksboro Switch 345 kV Line : Increase Foundation Reveal Cap | City of Chico, Wise County | Increase foundation caps on structures for Krum Switch - Jacksboro Switch 345 kV Line. | 2024-05-15 | 2024-06-15 | [5 empty] | 0 | 345 | na | 0.9 | 2-1590 ACSR Falcon | Steel Lattice Tower | 160 | 0.9 | na | na | 25.101(c)(5)(B)
0PT48506 (R4015) | Bellevue Sub - Bowie Sub 69 kV Line: Reconfiguration Remove Bowie Sub Connection | City of Bowie, Montague County | Reconfiguration remove Bowie Sub connection on the Bellevue Sub - Bowie Sub 69 kV Line. | 2023-04-13 | 2023-05-22 | 2023-05-22 |  | 262528.8 |  |  | 100 | 69 | na | 0.1 | 336.4 ACSR Linnett | Steel Pole | 50 | 0.1 | na | na | 25.101(c)(5)(B)
0PT47718 0PT49097 | Jewett-Long Lake-Palestine South 138 kV Line: Relocate Structure 2/9 | City of Jewett, Leon County | Relocate structure on Jewett - Long Lake - Palestine South 138 kV Line | 2025-11-24 | 2025-12-01 | [5 empty] | 0 | 138 | na | 0.1 | 795 ACSR Drake | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT46085 0PT48258 (R6138) | Pin Oak Switch - Fairfield West Switch 138 kV Line: Rebuild from Fairfield West to Fairfield Switch (BEPC) 138 kV | City of Fairfield, Freestone County | Rebuild the Pin Oak Switch – Fairfield West Switch 138 kV Line section from Fairfield West to Fairfield Switch (BEPC) using double circuit structures with one circuit in place. | 2023-02-09 | 2023-12-15 |  |  | 9413391 |  |  | 61 | 138 | na | 4.8 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 4.8 | na | na | 25.101(c)(5)(B)
0PT48054 0PT48267 (R944) | Commerce Switch - Sulphur Springs Switch 138 kV Line: Reterminate at Cumby Tap | City of Cumby, Hopkins County | Reterminate the Commerce Switch - Sulphur Springs Switch 138 kV line at Cumby Tap. | 2023-10-02 | 2023-12-15 |  |  | 996477.52 |  |  | 0 | 138 | na | 0.2 | 795 ACSR Drake | Steel 3- Pole | varies | 0.2 | na | na | 25.101(c)(5)(A)
0PT48971 | Stryker Creek Switch - Lufkin Switch 345 kV Line : Replace and relocate tower 23/2 | Nacogdoches County | Replacing Structure on Stryker Creek Switch - Lufkin Switch 345 kV Line. | 2024-05-05 | 2024-06-15 | [5 empty] | 0 | 345 | na | 0.5 | 2 - 795 ACSR Drake | Steel Lattice Tower | 150 | 0.5 | na | na | 25.101(c)(5)(B)
0PT48508 (R4015) | Fisher Road Switch - Riley 345 kV Line: Raise Structure 1/1 | City of Wichita Falls, Wichita County | Replace one structure of the Fisher Road - Oklaunion 345 kV line | 2023-01-16 | 2023-05-26 | 2023-05-26 |  | 871584 |  |  | 100 | 345 | na | 0.1 | 2-795 ACSR Drake | Steel Lattice Tower | 150 | 0.1 | na | na | 25.101(c)(5)(B)
0PT48780 0PT47487 (R8027) | SL Ogallala Switch - Tule Canyon Switch 345 kV Line : Cut-in for Ozark Trail Switch | Swisher County | The work required to loop the Ogallala Switch - Tule Canyon Switch 345 kV line into Ozark Trail Switch. | 2024-02-19 | 2024-05-15 | [5 empty] | 0 | 345 | na | 0.1 | 2 -1926.9 ACSS/TW Cumberland | Steel Lattice Tower | na | na | 175 | 0.1 | 25.101(c)(5)(A)
0PT43468 (M4205) | Carrollton Northwest Switch - Carrollton East Switch 138 kV Line : Line Termination at Carrollton Northwest | City of Carrollton, Dallas County | Establish the Carrollton East Switch - Carrollton Northwest Switch 138 kV Double-Circuit Line and Carrollton Northwest Switch - Northlake Switch 138 kV Line by terminating the existing Carrollton East Switch - Northlake Switch 138 kV Line at Carrollton Northwest Switch. | 2023-09-18 | 2023-12-25 |  |  | 2101040.58 |  |  | 49 | 138 | na | 1.8 | 959.6 ACSS/TW Suwannee | Steel Pole | varies | 0.9 | na | na | 25.101(c)(5)(A)
0PT46982 0PT49815 (R8615) | Morgan Creek Switch - McDonald Road 138 kV Line : Install Navigation Sub | Mitchell County | Cut-in to the Morgan Creek Switch-McDonald Road 138 kV Line to establish the new Navigation Substation. | 2023-02-15 | 2023-03-01 | 2023-03-01 |  | 1138112 |  |  | 100 | 138 | na | 0.3 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 0.3 | na | na | 25.101(c)(5)(A)
0PT42619 (R8591) | Wolfcamp Tap - Courtney Creek Switch 69 kV Line: Add 2nd Circuit | Pecos County | Rebuild the 9.3-mile Wolfcamp Tap - Courtney Creek Switch 69 kV Line section of the 51.7-mile Yucca Drive Switch - Northern Natural 69 kV Line. | 2023-06-30 | 2023-09-30 |  |  | 4205659 |  |  | 76 | 69 | 138 | 9.3 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole | 50 | 9.3 | na | na | 25.101(c)(5)(B)
0PT47513 | Killeen Taft Sub - Killeen Switch 138 kV Line : Install OPGW | City of Killeen, Bell County | Installing OPGW from Killeen Taft Sub to Killeen Switch. Leave splice drop at Killeen Elms Road. | 2024-04-03 | 2024-05-15 | [5 empty] | 0 | 138 | na | 12 | 1590 ACSR Falcon | Steel Pole | 100 | 6 | na | na | 25.101(c)(5)(B)
0PT02607 (R9022) | Graham - Morgan Creek 345 kV line (South): Reterminate at Mulberry Creek due to Station Rebuild | City of Abilene, Jones County | Line work associated with rebuilding Mulberry Creek 345 kV Switch Station | 2024-09-23 | 2025-05-15 |  |  | 6772651 |  |  | 0 | 345 | na | 1.2 | 2 -1926.9 ACSS/TW Cumberland | Steel Lattice Tower, Steel Pole | 120 | 0.4 | varies | 0.2 | 25.101(c)(5)(A)
0PT47795 (M5323) | Valley Switch - Paris Switch 345 kV Line : Cut-in for Pacific Switch | Lamar County | To provide service to the Customer’s generating facility, modifications to one circuit of the double circuit 345 kV transmission line will be necessary. The work required to loop the Valley Switch - Paris Switch 345 kV line into Pacific Switch. | 2023-09-28 | 2023-11-16 |  |  | 2244840.8 |  |  | 0 | 345 | na | 0.6 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 250 | 0.4 | 300 | 0.1 | 25.101(c)(5)(A)
0PT42093 0PT42844 (R8591) | Blair Lake Substation-Courtney Creek Switch 69 kV Line: Conversion to 138 kV | Pecos County | Rebuild 13.8 miles of the Yucca Drive Switch – Northern Natural Substation 69 kV Line between Blair Lake Substation – the new Courtney Creek Switch and convert the circuit to 138 kV. | 2023-06-29 | 2023-10-30 |  |  | 16108141 |  |  | 14 | 69 | 138 | 13.83 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 13.6 | 50 | 0.23 | 25.101(c)(5)(B)
0PT44564 (M5310) | Venus Switch Sta. - Cedar Hill 138 kV Line: Padera Sub Cut In | City of Midlothian, Ellis County | Cut-In to Venus Switch - Cedar Hill 138 kV Line to Establish Padera Substation | 2023-05-03 | 2023-05-12 | 2023-05-12 |  | 1271660.48 |  |  | 100 | 138 | na | 0.18 | 1926.9 ACSS/TW/E3X Cumberland | Steel Pole | 100 | 0.12 | 100 | 0.06 | 25.101(c)(5)(A)
0PT44557 (M5314) | Hicks Switch - Deen Switch 138 kV Line : Cut in to Horseman Sub (formerly Saginaw SE Sub) | City of Fort Worth, Tarrant County | Cut in the Hicks Switch - Deen Switch 138 kV line to the Horseman Sub. | 2023-03-16 | 2023-06-28 | 2023-06-28 |  | 1594954 |  |  | 100 | 138 | na | 0.2 | 959.6 ACSS/TW/E3X Suwannee | Steel Pole | 75 | 0.1 | na | na | 25.101(c)(5)(A)
0PT48603 (M5330) | Roanoke Switch - Euless Switch 138 kV Line : Retermination at Roanoke Switch | City of Roanoke, Denton County | Line work associated with the retermination of both the Deen Sw - Roanoke Sw and Roanoke Sw - Euless Sub 138 kV Lines. | 2023-02-25 | 2023-05-12 | 2023-05-12 |  | 1593630 |  |  | 100 | 138 | na | 0.4 | 2 - 959.6 ACSS/TW/E3X Suwannee | Steel Pole | Varies | 0.2 | na | na | 25.101(c)(5)(A)
0PT46932 0PT48703 (R8593) | NTUSU Brown Sub - Grady Sub 138 kV Line: Expanse Switch Cut In | Martin County | Loop in the Brown Sub - Grady Sub 138 kV line into the new Expanse 345/138 kV Switch | 2023-03-13 | 2023-12-25 |  |  | 1774555 |  |  | 99 | 138 | na | 0.51 | 1926.9 ACSS/TW/E3X Cumberland | Steel Pole | 70 | 0.5 | 100 | 0.01 | 25.101(c)(5)(A)
0PT48643 (R8595) | McKenzie Draw - Lamesa Sub 138 kV Line: Lamesa Sub Cut - In | Dawson County | Line Work Associated with Retermination of Lamesa Sub | 2023-02-12 | 2023-10-15 |  |  | 386236 |  |  | 99 | 138 | na | 0.01 | 959.6 ACSS/TW Suwannee | Steel A-Frame | 100 | 0.01 | na | na | 25.101(c)(5)(B)
0PT47106 0PT47929 (R8617) | SL Blue Acres Sub - Grey Well Draw Sub 138 kV Line : Rebuild | City of Midland, Midland County | Rebuild the 5.5 mile SL Blue Acres Sub - Grey Well Draw Sub 138 kV Line with double circuit capable structures. | 2023-04-27 | 2023-08-31 |  |  | 12400488 |  |  | 99 | 138 | na | 5.5 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | 70 | 5.5 | na | na | 25.101(c)(5)(B)
0PT48642 (R8649) | Getty Vealmoor 138 kV Tap Line: Cut-In to Establish Vincent Sub | City of Big Spring, Howard County | Cut in the Big Spring Switch - China Grove Switch - Gunsight Switch 138 kV Line to establish the new Vincent substation. | 2023-03-22 | 2023-10-15 |  |  | 1700172 |  |  | 99 | 138 | na | 0.6 | 1926.9 ACSS/TW Cumberland | Steel Pole, Wood H-Frame, Wood Pole | 75 | 0.6 | na | na | 25.101(c)(5)(A)
0PT46985 | Temple Switch - Temple Sub 138 kV Line : Install OPGW | City of Temple, Bell County | Install OPGW from Temple Switch to Temple Substation | 2023-03-15 | 2023-03-31 | 2023-03-31 |  | 368433 |  |  | 100 | 138 | na | 1.7 | 795 ACSR Drake | Steel Pole | 100 | 1.7 | na | na | 25.101(c)(5)(A)
0PT43540 (M5317) | Tyson Nick Solar: Establish a 138kV POI for customer's generator at Toco Switch | City of Paris, Lamar County | Establish 138 kV point of interconnection of the Tyson Nick Solar generating facility | 2024-02-26 | 2024-05-15 | [5 empty] | 0 | na | 138 | 0.1 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | varies | 0.1 | 25.101(c)(5)(A)
0PT47231 | Handley - Lancaster 138 kV: Replace STR 2/6 due to Erosion | City of Fort Worth, Tarrant County | Replacing structure on Handley - Lancaster 138 kV Line. | 2023-02-22 | 2023-05-10 | 2023-05-10 |  | 794882 |  |  | 100 | 138 | na | 0.4 | 1534.0 ACAR, 795 ACSR DRAKE | Steel Pole | 50 | 0.2 | na | na | 25.101(c)(5)(B)
0PT48309 (M4330) | Haggerty Switch Station - MEMC Southwest Substation (South) 138 kV Line | City of Sherman, Grayson County | Reroute the South MEMC Southwest Tap 138 kV single circuit line 0.6 miles into the new Haggerty 138 kV Switch | 2023-06-27 | 2023-11-15 |  |  | 1741500 |  |  | 50 | na | 138 | 0.6 | 2 - 959.6 ACSS/TW SUWANNEE | Steel Pole | na | na | 50 | 0.6 | 25.101(c)(5)(A)
0PT48118 (M4322) | Mountain Creek Switch - West Levee 138 kV Line: Line Reroute for Campion 138 kV Sub | City of Dallas, Dallas County | Line Reroute for Campion 138 kV Sub. | 2023-03-14 | 2023-05-22 | 2023-05-22 |  | 1401334 |  |  | 100 | 138 | na | 0.3 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 0.3 | na | na | 25.101(c)(5)(A)
0PT48116 (M4322) | Mountain Creek Switch - Norwood Switch 138 kV Line: Establish Transmission Loop Feed for Campion 138 kV Sub | City of Dallas, Dallas County | Establish Transmission Loop Feed for Campion 138 kV Sub. | 2023-03-20 | 2023-05-26 | 2023-05-26 |  | 1611278 |  |  | 100 | 138 | na | 0.25 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 70 | 0.25 | 25.101(c)(5)(A)
0PT43639 (M4322) | Mountain Creek Switch - West Dallas 138 kV Line: Establish Transmission Loop Feed for Campion 138 kV Sub | City of Dallas, Dallas County | Establish the transmission loop feed into the new Campion 138 kV Sub. | 2023-03-13 | 2023-05-22 | 2023-05-22 |  | 1548979 |  |  | 100 | 138 | na | 0.25 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 70 | 0.25 | 25.101(c)(5)(A)
0PT48845 (R8621) | Delaware River Switch - Delaware Ranch Sub 138 kV Line: Build | Culberson County | Build the tie line between the new Delaware River Switch and existing Delaware Ranch Sub. | 2024-01-15 | 2024-04-16 | [5 empty] | 0 | na | 138 | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 0.1 | varies | 25.101(c)(5)(A)
0PT48229 (R6182) | Palestine - Palestine South 138 kV line: Reterminate at Palestine South | City of Palestine, Anderson County | Reterminate the Palestine - Palestine South 138 kV line at Palestine South. | 2023-03-27 | 2023-12-15 |  |  | 628258 |  |  | 99 | 138 | na | 0.4 | 959.6 ACSS/TW Suwannee | Steel Pole | varies | 0.4 | na | na | 25.101(c)(5)(A)
0PT48223 (R6182) | Palestine South - Long Lake 138 kV line: Reterminate at Palestine South | City of Palestine, Anderson County | Reterminate the Palestine South - Long Lake 138 kV line at Palestine South. | 2023-03-23 | 2023-12-15 |  |  | 1159099 |  |  | 99 | 138 | na | 0.2 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | varies | 0.2 | na | na | 25.101(c)(5)(A)
0PT47787 (R8621) | Horseshoe Spring Switch - Riverton Switch 138 kV Line : Cut-in for Delaware River Switch | Culberson County | Cut-in the Horseshoe Springs Switch - Riverton Switch 138 kV Line to establish the new Delaware River Switch | 2024-01-15 | 2024-04-16 | [5 empty] | 0 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 75 | 0.4 | 25.101(c)(5)(A)
0PT46888 (M4137) | Mesquite East Switch - Sunnyvale 138 kV Line: Rebuild | City of Mesquite, Dallas County | Rebuild the Mesquite East Switch - Sunnyvale 138 kV Line. | 2023-02-21 | 2023-12-15 |  |  | 7179241 |  |  | 99 | 138 | na | 4.08 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | 2.04 | na | na | 25.101(c)(5)(b)
0PT47790 0PT48725 (R6182) | Palestine - Crockett 69 kV Line: Rebuild Palestine Switch - Elkhart Switch | City of Palestine, Anderson County | Rebuild the Palestine - Crockett 69 kV line from Palestine Switch - Elkhart Switch. | 2023-03-21 | 2025-09-15 |  |  | 16621693 |  |  | 1 | 69 | 138 | 10 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | varies | 10 | na | na | 25.101(c)(5)(B)
0PT41200 0PT51456 (R944) | Cumby Tap Switch - Cumby Sub 69 kV Line : Conversion to 138 kV | City of Cumby, Hopkins County | Reterminate the Cumby Tap Switch - Cumby Sub 69 kV line at Cumby Sub. | 2023-04-05 | 2023-12-15 |  |  | 2367244 |  |  | 1 | 69 | 138 | 0.2 | 336.4 ACSR Linnett | Steel Pole | varies | 0.2 | na | na | 25.101(c)(5)(A)
0PT48098 0PT49115 (R6172) | McGregor Phillips Tap Switch - Waco West Switch 69 kV Line : Rebuild Structure 24/4B to McGregor Phillips Switch | City of McGregor, McLennan County | Rebuild McGregor Phillips Tap Switch - Waco West Switch 69 kV Line from Structure 24/4B to McGregor Phillips Switch. | 2023-05-02 | 2024-12-31 |  |  | 3443330.22 |  |  | 99 | 69 | 138 | 2 | 1926.9 ACSS/TW/E3X Cumberland | Steel Pole, Wood Pole | 100 | 1 | na | na | 25.101(c)(5)(B)
0PT47983 (R8669) | Wink Switch - Aroya Switch 138 kV Line : Establish White Dune 138 kV point of delivery (POD) | City of Wink, Winkler County | Provide a 138 kV point-of-delivery (POD) on the Wink Switch - Aroya Switch 138 kV Line Section. | 2024-09-09 | 2025-05-15 | [5 empty] | 0 | 138 | na | 0.23 | 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 0.2 | Varies | 0.03 | 25.101(c)(5)(A)
0PT47982 (R8660) | Wolf Switch - Wink Switch 138 kV Line : Establish Arenosa 138 kV point of delivery (POD) | City of Wink, Winkler County | Provide a 138 kV point-of-delivery (POD) on the Wolf Switch - Wink Switch 138 kV Line Section. | 2024-08-15 | 2024-12-15 | [5 empty] | 0 | 138 | na | 0.23 | 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 0.2 | Varies | 0.03 | 25.101(c)(5)(A)
0PT48973 | Martin Lake Switch - Stryker Creek Switch 345 kV Line : Replace and relocate Str. 41/1 | City of Tatum, Rusk County | Replacing Structure on Martin Lake Switch - Stryker Creek Switch 345 kV Line. | 2024-05-26 | 2024-06-15 | [5 empty] | 0 | 345 | na | 1 | 2-1590 ACSR Falcon | Steel Lattice Tower | 150 | 0.5 | na | na | 25.101(c)(5)(B)
0PT48376 (R6224) | Hutto Switch - Gilleland Creek Switch 138 kV Line : Cut-in to establish Double Creek Sub | City of Round Rock, Williamson County | Build new line section to cut in Double Creek 138 kV Sub. | 2023-04-27 | 2023-12-15 |  |  | 2379553 |  |  | 34 | 138 | na | 0.6 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 95 | 0.3 | 25.101(c)(5)(A)
0PT48556 0PT48577 (R8597) | SL East Stiles – Rocky Road 138 kV Line: Rebuild | City of Stiles, Reagan Country | Rebuild the SL East Stiles – Rocky Road 138 kV Line. | 2023-06-15 | 2023-09-15 |  |  | 13809085 |  |  | 47 | 138 | na | 7.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 58 | 7.1 | na | na | 25.101(c)(5)(B)
0PT47802 (R6217) | Bell County East Switch-TNP One (TNMP) Switch 345 kV Line: Cut-in to establish Brangus Switch | Milam County | Cut into the Bell County East - TNP One (TNMP) 345 kV Line to establish the new Brangus Switch. | 2023-03-25 | 2023-05-31 | 2023-05-31 |  | 3801745 |  |  | 100 | 345 | na | 1.34 | 2-1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 160 | 0.1 | varies | 0.57 | 25.101(c)(5)(A)
0PT48608 | Bell County East Switch - Sandow Switch 345 kV Line : Replacement of Insulators and Installation of Varmit Guards | City of Rockdale, Milam County | Replace Insulators and Varmit Guards on various structures of Bell County East Switch - Sandow Switch 345 kV Line. | 2023-10-11 | 2023-12-15 |  |  | 231555.25 |  |  | 0 | 345 | na | 5.87 | 959.6 ACSS/TW Suwannee | Steel Lattice Tower | 125 | 5.87 | na | na | 25.101(c)(5)(a)
0PT48522 (M4352) | Greenville Avenue Switch - Kirkland Park Switch 138 kV Line : Retermination | City of Dallas, Dallas County | Re-terminate the Greenville Avenue Switch - Kirkland Park Switch 138 kV Line to the new Greenville Avenue Substation Dead Ends. | 2023-10-13 | 2023-10-16 |  |  | 693018.26 |  |  | 0 | 138 | na | 0.28 | 2- 959.6 ACSS/TW Suwannee | Steel Pole | Station Property | 0.14 | na | na | 25.101(c)(5)(A)
0PT48359 0PT49344 (R8530) | Penwell POD - Wolf Switch 138 kV Line : Rebuild | Ward County | Rebuild/Reconductor the 9.5 mile Moss Switch - Red Lakes Switch 138 kV Line. | 2024-04-15 | 2024-09-20 | [5 empty] | 0 | 138 | na | 9.53 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 9.53 | na | na | 25.101(c)(5)(B)
0PT47103 0PT47345 (R8618) | SL Buffalo Switch - Triangle Switch 138 kV Line : Rebuild | City of Stanton, Martin County | Rebuild the Buffalo Switch - Triangle Switch138 kV Line on double-circuit structures with one circuit in place from Buffalo - Triangle. | 2023-06-15 | 2023-09-30 |  |  | 7913408 |  |  | 38 | 138 | na | 3.5 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | Varies | 3.5 | na | na | 25.101(c)(5)(B)
0PT47022 (R6136) | Trinidad - Mexia 138 kV Line: Retermination at Ranchland Switch | City of Fairfield, Freestone County | Reterminate the Fairfield West - Jewett 138 kV Line at its new terminal location at Ranchland Switch. | 2023-01-23 | 2023-05-26 | 2023-05-26 |  | 1139613.5 |  |  | 100 | 138 | na | 0.25 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.25 | na | na | 25.101(c)(5)(A)
0PT46851 0PT47714 0PT48213 (R6211) | Brushy Creek Switch - Mallard Switch 138 kV Line : 69 kV Line Rebuild from Brushy Creek to Str. 1/5 | City of Taylor, Williamson County | Rebuild the Taylor - Elgin 69 kV line from Brushy Creek - Structure 1/5 as the Brushy Creek - Mallard 138 kV Line | 2023-03-22 | 2023-10-15 |  |  | 19985182.47 |  |  | 34 | 69 | 138 | 10.7 | 1926.9 ACSS/TW CUMBERLAND | Steel H-Frame, Steel Pole | Varies | 10.6 | 70 | 0.1 | 25.101(c)(5)(B)
0PT46785 0PT49067 (M4326) | Italy Sub - Hillsboro Switch 69 kV Line: Rebuild Milford Exxon Tap - Hillsboro Switch | City of Hillsboro, Hill County | Rebuild the Milford Exxon Tap - Hillsboro section of the Italy Sub - Hillsboro Switch 69 kV | 2023-06-08 | 2023-12-15 |  |  | 23726345 |  |  | 56 | 69 | na | 14.4 | 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel Pole | Varies | 14.4 | na | na | 25.101(c)(5)(b)
0PT46136 0PT48269 (R6094) | Chandler West Switch to Murchison Switch 69 kV: Rebuild to 138 kV | City of Brownsboro, City of Chandler, Henderson County | Rebuild a 9.2 miles section of the Athens to Tyler Switch 69 kV line as a 138 kV double circuit line with only one circuit installed. | 2023-06-22 | 2023-09-30 |  |  | 18559930.84 |  |  | 49 | 69 | 138 | 9.2 | 959.6 ACSS/TW Suwannee | Steel H-Frame, Steel Pole | Centerline | 9.2 | na | na | 25.101(c)(5)(B) | Line will be operating as 69kV initially when it's back in service, once other associated line/station projects are finalized it will be converted to 138kV
0PT45889 (R6173) | Holland Sub - Bartlett Tap 69kV Line: Rebuild from Holland Sub to Str. 62/5 | City of Holland, Bell County | Rebuild the Holland Sub - Str 62/5 section of the Taylor Switch - Holland 69 kV Line. | 2023-06-13 | 2023-10-30 |  |  | 8791887.09 |  |  | 97 | 69 | na | 5.6 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 5.6 | na | na | 25.101(c)(5)(B)
0PT44429 0PT44430 (R8564) | SL Driver Switch - SkyWest Switch 138 kV Line : Rebuild | Midland County | Rebuild 11.9 miles from T37 - SkyWest Switch section of the Driver Switch - SkyWest Switch 138 kV Line. | 2023-08-03 | 2023-12-15 |  |  | 18259397 |  |  | 17 | 138 | na | 11.9 | 1926.9 ACSS/TW Cumberland | Steel Pole | 90 | 11.9 | na | na | 25.101(c)(5)(B)
0PT43937 (R6146) | Waco West - Waco East Switch - Elm Mott 138 kV Line: Retermination at McLane Switch | City of Waco, Waco County | Reterminate the Waco West - Waco East Switch - Elm Mott 138 kV Line at its new terminal location at McLane Switch. | 2024-03-15 | 2024-05-01 | [5 empty] | 0 | 138 | na | 1 | 1926.9 ACSS/TW Cumberland | Steel Pole | varies | 0.5 | na | na | 25.101(c)(5)(A)
0PT43936 (R6146) | Lake Creek Switch - Waco East Switch 138 kV Line : Retermination at McLane Switch. | City of Waco, Waco County | Reterminate the Lake Creek Switch - Waco East Switch 138 kV Line at its new terminal location at McLane Switch. | 2024-03-15 | 2024-05-01 | [5 empty] | 0 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | varies | 0.4 | na | na | 25.101(c)(5)(A)
0PT43935 (R6146) | Waco East Switch - Waco West Sub 138 kV Line : Retermination at McLane Switch. | City of Waco, Waco County | Reterminate the Waco East Switch - Waco West Sub 138 kV Line at its new terminal location at McLane Switch. | 2024-02-16 | 2024-05-01 | [5 empty] | 0 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | varies | 0.4 | na | na | 25.101(c)(5)(A)
0PT43770 | Liggett-Collin 138 kV: Panther Creek Parkway Relocation for City of Frisco | City of Frisco, Collin County | Relocation with new double circuit, steel monopole, tangent structures. | 2023-05-02 | 2023-05-15 | 2023-05-15 |  | 1839272 |  |  | 100 | 138 | na | 0.96 | 2-1590 ACSR Falcon | Steel Pole | 100 | 0.48 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the City of Frisco and is 100% reimbursable by the City of Frisco.
0PT43768 | Collin-Frisco (BEC) 138 kV: Panther Creek Parkway Relocation for City of Frisco | City of Frisco, Collin County | Relocation with new double circuit, steel monopole, tangent structures. | 2023-04-10 | 2023-05-15 | 2023-05-15 |  | 964647 |  |  | 100 | 138 | na | 0.72 | 1590 ACSR Falcon | Steel Pole | 100 | 0.36 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the City of Frisco and is 100% reimbursable by the City of Frisco.
0PT43747 | Collin-Renner 138 kV: Panther Creek Parkway Relocation for City of Frisco | City of Frisco, Collin County | Relocation with new double circuit, steel monopole, tangent structure. | 2023-04-18 | 2023-05-15 | 2023-05-15 |  | 516383 |  |  | 100 | 138 | na | 0.34 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.17 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the City of Frisco and is 100% reimbursable by the City of Frisco.
0PT43159 0PT49345 (R8530) | Red Lakes Switch - Penwell POD 138 kV Line: Rebuild | Ward, Winkler and Ector Counties | Rebuild the 11.0 mile Red Lakes Switch - Penwell POD 138 kV line | 2023-10-06 | 2024-04-12 |  |  | 18306531 |  |  | 0 | 138 | na | 11 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 11 | na | na | 25.101(c)(5)(B)
0PT42525 (R4015) | Burnett Switch - Old Lake Switch 69 kV Line : Rebuild Lanham Tap - Old Lake Section to 138 kV | City of Wichita Falls, Clay County | Rebuild Lanham Tap - Old Lake section of the Burnett Switch - Old Lake Switch 69 kV Line to 138 kV. | 2023-05-03 | 2024-03-28 |  |  | 19604624 |  |  | 58 | 69 | 138 | 10.8 | 959.6 ACSS/TW Suwannee | Steel Pole | 100 | 10.8 | na | na | 25.101(c)(5)(B)
0PT42092 0PT49409 (R8591) | Royalty Substation – Blair Lake Substation 69 kV Line : Conversion to 138 kV | Ward and Pecos Counties | Rebuild the Royalty Substation – Blair Lake Substation section of the Yucca Drive Switch – Northern Natural 69 kV Line and convert the circuit to 138 kV. | 2023-10-16 | 2024-02-29 |  |  | 13756725.8 |  |  | 0 | 69 | 138 | 11.84 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | 11.84 | na | na | 25.101(c)(5)(B)
0PT50224 0PT49040 (R6165) | Hutto - Taylor 138 kV Line: Cut In Teal Switch | City of Hutto, Williamson County | Construct the cut-in line for the new Teal Switch station. | 2023-09-15 | 2023-12-15 |  |  | 6286166.72 |  |  | 31 | na | 138 | 0.7 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 140 | 0.7 | 25.101(c)(5)(A)
0PT48946 0PT49111 | SL Coyote – Luther 138 kV Line: Coyote Retermination | City of Big Spring, Howard County | Line work associated with reterminating the Coyote - Luther 138 kV Line at its new terminal location at Coyote Substation. | 2023-02-01 | 2023-10-15 |  |  | 583278 |  |  | 50 | 138 | na | 0.01 | 795 ACSR Drake | Steel Pole | 0.01 | 40 | na | na | 25.101(c)(5)(A)
0PT47577 (M4327) | Watermill Switch - Desoto Switch 345 kV Line : Cut-In Loop Nine Switch | City of Red Oak, Ellis County | Cut-in Watermill - Desoto and Waltermill - Cedar Hill 345 kV lines to establish the new Loop Nine Switch. | 2023-10-09 | 2023-12-08 |  |  | 12324127.93 |  |  | 0 | 345 | na | 1.2 | 2 - 1926.9 ACSS/TW Cumberland | Steel 2 - Pole, Steel Pole | na | na | varies | 0.3 | 25.101(c)(5)(A)
0PT47850 (M4335) | Pebble Creek Switch - Red Mesquite 138 kV Lines: Install 2 single circuit POD lines | City of Red Oak, Ellis County | Build a new Pebble Creek Switch - Red Mesquite Substation 138 kV Line. | 2023-09-12 | 2024-03-01 |  |  | 3259301.28 |  |  | 62 | na | 138 | 1 | 959.6 ACSS/TW Suwannee | Steel 2 - Pole, Steel 3 - Pole, Steel Pole | na | na | varies | 0.5 | 25.101(c)(5)(A)
0PT47041 (M4327) | Pebble Creek Switch - Loop Nine Switch 138 kV Line: Construct Line | City of Red Oak, Ellis County | Build a new Pebble Creek Switch - New Loop 9 Station 138 kV Line. | 2023-10-23 | 2023-12-15 |  |  | 9458796.14 |  |  | 0 | na | 138 | 3.6 | 2 - 959.6 ACSS/TW Suwannee | Steel 2-Pole | na | na | varies | 1.8 | 25.101(c)(5)(A)
0PT48553 0PT49641 0PT51256 (R8640) | SL South Midland – Pecan Grove 138 kV Line: Rebuild | City of Midland, Midland County | Rebuild the South Midland - Pecan Grove 138 kV line. | 2023-08-28 | 2023-12-15 |  |  | 20949939 |  |  | 2 | 138 | na | 7.8 | 1926.9 ACSS/TW Cumberland, 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H-Frame, Steel Pole | 70 | 7.3 | 70 | 0.5 | 25.101(c)(5)(B)
0PT40890 0PT50173 0PT51209 (R9047) | Yucca Drive Switch - Moss Switch 138 kV Line: Rebuild Section from Moss Switch to Future Oxy POD | City of Odessa, Ector County | Rebuild the first 12.7 miles of the Yucca Drive Switch - Moss Switch 138 kV Line, starting at Moss Switch. | 2023-10-01 | 2024-05-15 |  |  | 24119836 |  |  | 0 | 138 | na | 12.7 | 1926.9 ACSS/TW Cumberland | Steel 2-Pole, Steel 3 - Pole, Steel Pole | varies | 12.7 | na | na | 25.101(c)(5)(B)
0PT47500 0PT51397 (R6228) | Waco West Switch - Temple Elm Creek Switch 138 kV Line: Install McGuffey point of delivery (POD) | City of McGregor, McLennan County | Provide a 138 kV point of delivery (POD) | 2023-06-19 | 2024-02-16 |  |  | 6163600 |  |  | 50 | 69 | 138 | 5 | 1926.9 ACSS/TW Cumberland | Steel 2-Pole, Steel 3-Pole, Steel H-Frame, Steel Pole | 100 | 1.8 | 70 | 0.7 | 25.101(c)(5)(A)
0PT44611 0PT52026 0PT50495 (R8633) | Flat Iron Substation - Barr Ranch Switch - Quickriver Tap 138 kV Line: Install Bull Head point of delivery (POD) | Midland and Upton Counties | Provide a 138 kV point of delivery (POD) | 2023-09-29 | 2023-12-01 |  |  | 6252425 |  |  | 0 | 138 | na | 2.7 | 1926.9 ACSS/TW Cumberland | Steel 3-Pole, Steel Pole | na | na | 70 | 2.7 | 25.101(c)(5)(A)
0PT45437 (R6190) | Temple Elm Creek Switch - Belton Switch 138 kV Line : Install Pepper Creek Switch | City of Temple, Bell County | Cut in Pepper Creek Switch on the Temple Elm Creek Switch - Belton Switch 138 kV DCKT Line. | 2024-08-15 | 2024-11-15 | [5 empty] | 0 | 138 | na | 2.6 | 1926.9 ACSS/TW Cumberland , 959.6 ACSS/TW Suwannee | Steel Pole | na | na | Varies | 1.3 | 25.101(c)(5)(A)
0PT50313 | Terrell SWT Switch - Seagoville SWT Switch 138 kV Line : Reject Pole Replacements(GLT) | City of Kaufman, Kaufman County | Pole replacements on the Terrell SWT Switch - Seagoville SWT Switch 138 kV Line. | 2023-03-13 | 2023-10-31 |  |  | 173565 |  |  | 95 | 138 | na | 7.75 | 795 ACSR Drake | Wood H-Frame | 100 | 7.75 | na | na | 25.101(c)(5)(B)
0PT50298 | Ennis West Switch - Sterrett Switch 138 kV Line : Replace (13) Wood Poles, (2) X-Arms, (4) X-Braces & (15) Insulators. | City of Ennis, Ellis County | Replacement of crossarms and poles on the Ennis West Switch - Sterrett Switch 138 kV Line. | 2023-09-19 | 2023-11-30 |  |  | 312552 |  |  | 90 | 138 | na | 12.4 | 795 ACSR Drake | Wood 3-Pole, Wood H-Frame | 100 | 12.4 | na | na | 25.101(c)(5)(B)
0PT50387 | Morgan Creek - Spraberry (138KV): Replace cross arms, insulators and cross braces - 32 frames | Glasscock County | Replacement of crossarms, insulators and braces on the Morgan Creek - Spraberry 138 kV line. | 2023-11-09 | 2023-12-31 |  |  | 602756 |  |  | 0 | 138 | na | 14.9 | 636 ACSR Grosbeak | Wood H-Frame | 50 | 14.9 | na | na | 25.101(c)(5)(B)
0PT46209 (R1743) | Lake Creek Switch - Marlin Switch 69kV Line: Conversion to 138kV | City of Marlin, Falls County | Rebuild the 13.7-mile Lake Creek Switch - Marlin Switch 69 kV Line, using 138 kV double-circuit structures with one circuit in place. | 2025-06-01 | 2025-09-15 | [5 empty] | 0 | 69 | 138 | 13.7 | 959.6 ACSS/TW Suwannee | Steel 2- Pole, Steel Pole | varies | 13.7 | na | na | 25.101(c)(5)(B)
0PT48698 0PT48727 (M4330) | Stone Creek Sw - Anna Sw 138 kV Line: Cut In Haggerty Switch | City of Sherman, Grayson County | The project will cut in the Stone Creek - Anna Switch 138 kV line into the new Haggerty Switch. | 2023-05-07 | 2023-10-01 |  |  | 9770654.45 |  |  | 98 | na | 138 | 4 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | na | na | 100 | 2 | 25.101(c)(5)(A)
0PT50394 | Terrell Switch - Kaufman Northwest - Seagoville: 138kV Reject Pole Replacements (GLT) | Kaufman County | Replace Various Poles on the Terrell Switch - Kaufman Northwest - Seagoville 138kV line. | 2023-04-24 | 2023-10-31 |  |  | 297715 |  |  | 95 | 138 | na | 4.04 | 4/0 ACSR Penguin | Wood H-Frame | Varies | 4.04 | na | na | 25.101(c)(5)(B)
0PT50514 | Temple Switch - Minerva Sub 69 kV Line : Replace Multiple Structures, Cross Arms and insulators (GLT) | Milam County | Replace Various Structures, Cross Arms and Insulators on the Temple Switch - Minerva Sub 69 kV Line. | 2023-06-19 | 2023-12-15 |  |  | 237587 |  |  | 20 | 69 | na | 20.31 | 4/0 ACSR Penguin | Wood H-Frame | Varies | 20.31 | na | na | 25.101(c)(5)(B)
0PT50529 | Yucca Drive Switch - Moss Switch 138 kV Line: Replace Wood Poles, Insulators and Crossarms (GLT) | Ector County, Ward County, Winkler County | Replace Various Wood Poles, Insulators and Crossarms on the Yucca Drive Switch - Moss Switch 138 kV Line. | 2023-08-14 | 2024-02-29 |  |  | 288106 |  |  | 95 | 138 | na | 26.26 | 795 ACSR Drake | Wood H-Frame | 75 | 26.26 | na | na | 25.101(c)(5)(B)
0PT50557 | Terrell Switch - Terrell South 138kV Line : Replace 7 poles (GLT Project) | Kaufman County | Replace Various Poles on the Terrell Switch - Terrell South 138kV Line. | 2023-04-11 | 2023-10-31 |  |  | 255273 |  |  | 95 | 138 | na | 4.05 | 795 ACSR Drake | Wood H-Frame | 100 | 4.05 | na | na | 25.101(c)(5)(B)
0PT50761 | Gainesville Tap 69 SWT 210 - Gainesville Camp Howze SWT 206: Replace H-Frame 3/9, 5/6, 6/5, 6/6, 7/3, 7/11, 7/12, 8/1, 8/6, 8/7 (GLT) | Cooke County | Replace Various H-Frames on the Gainesville Tap - Gainesville Camp Howze 69kV Line. | 2023-06-05 | 2023-12-28 |  |  | 274014 |  |  | 95 | 69 | na | 4.98 | 1/0 ACSR Raven | Wood H-Frame | 100 | 4.98 | na | na | 25.101(c)(5)(B)
0PT50793 | Watermill to Parkdale: 138Kv GLT Pole Replacement - Line Section: Southside Filtration Tap West - Southside Filtration | Dallas County | Replace Various Poles on the Watermill to Parkdale 138kV Line. | 2023-07-15 | 2023-11-30 |  |  | 299189 |  |  | 10 | 138 | na | 4.3 | 336.4 ACSR Linnett | Single Wood Pole | Varies | 4.3 | na | na | 25.83(a)(3)
0PT50159 (R6191) | Waco West Switch - Temple 69 kV Line: Cut-In to Establish Bronze Age 138 kV Switch | City of Troy, Bell County | Cut in the Waco West Switch - Temple 69 kV Line to the establish the new Bronze Age Switch. | 2023-10-18 | 2023-12-15 |  |  | 959294.86 |  |  | 0 | 69 | 138 | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 40 | 0.2 | na | na | 25.101(c)(5)(A)
0PT50158 (R6191) | Waco West Switch - Temple 69 kV Line: Cut-In to Establish Eddy 138 kV Switch | City of Bruceville-Eddy, McLennan County | Cut in the Waco West Switch - Temple 69 kV Line to the establish the new Eddy Switch. | 2023-10-04 | 2023-12-15 |  |  | 625763.33 |  |  | 0 | 69 | 138 | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 45 | 0.1 | na | na | 25.101(c)(5)(A)
0PT50157 (R6191) | Waco West Switch - Temple 69 kV Line: Cut-In to Establish Lorena 138 kV Switch | City of Lorena, McLennan County | Cut in the Waco West Switch - Temple 69 kV Line to the establish the new Lorena Switch. | 2023-10-23 | 2023-12-15 |  |  | 1119200.8 |  |  | 0 | 69 | 138 | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 40 | 0.1 | na | na | 25.101(c)(5)(A)
0PT49982 (R6094) | Sam Switch - Tradinghouse Switch 345 kV Line : Cut-in to establish Tiger Creek Switch | City of Waco, Bell County | Cut in tiger Creek Switch on the Sam Switch - Tradinghouse Switch 345 Line. | 2024-09-18 | 2024-11-14 | [5 empty] | 0 | 345 | na | 0.25 | 2-1926.9 ACSS/TW Cumberland | Steel Lattice Tower, Steel Pole | na | na | varies | 0.25 | 25.101(c)(5)(A)
0PT49849 | Martin Lake Switch - Stryker Creek Switch 345 kV Line : Replace and relocate tower 29/1 | City of Henderson, Rusk County | Replacing Structure on Martin Lake Switch - Stryker Creek Switch 345 kV Line. | 2023-10-02 | 2023-12-15 |  |  | 665391.75 |  |  | 0 | 345 | na | 1.4 | 2 - 1590 ACSR Falcon | Steel Lattice Tower | 150 | 0.7 | na | na | 25.101(c)(5)(B)
0PT49807 0PT51085 (R8626) | Falcon Seaboard - Midland East 345 kV Line: Replace Structures 61/2-61/5 | City of Midland, Midland County | Rebuild a section of the Falcon Seaboard - Midland East 345 kV line. | 2023-10-06 | 2023-12-25 |  |  | 4633089 |  |  | 0 | 345 | na | 1.6 | 2-1926.9 ACSS/TW Cumberland | Steel 2-Pole, Steel 3-Pole, Steel Pole | 150 | 1 | 150 | 0.6 | 25.101(c)(5)(B)
0PT49766 (R8634) | Odessa Sub - Midessa South Switch 138 kV Line : Establish Tesoro Switch | Midland County | Cut into the Odessa Sub- Midessa South Sw. 138 kV Line to establish the new Tesoro Sw. | 2023-10-04 | 2023-12-15 |  |  | 2510464.08 |  |  | 0 | 138 | na | 0.7 | 1926.9 ACSS/TW Cumberland | Steel 3-Pole, Steel Pole | 50 | 0.1 | 50 | 0.6 | 25.101(c)(5)(A)
0PT49478 | Edwards Tap - Edwards Sub 138 kV Line : Cut In | City of Crane, Crane County | Cut in for Edwards Tap - Edwards Sub 138 kV Line. | 2023-07-11 | 2023-12-22 |  |  | 559671 |  |  | 1 | 138 | na | 0.01 | 336.4 ACSR Linnett | Wood Multi - Pole | 75 | 0.01 | na | na | 25.101(c)(5)(A)
0PT49464 | Venus Switch - Sam Switch 345 kV Line : Insulator Replacement | Ellis and Hill Counties | Replace 555 polymer insulator assemblies on the Venus Switch to Sam Switch 345kV line with 555 glass bell insulator assemblies. | 2024-10-16 | 2025-12-15 | [5 empty] | 0 | 345 | na | 20.4 | 795 ACSS Drake | Steel Lattice Tower | 170 | 20.4 | na | na | 25.101(c)(5)(B)
0PT49406 | Liggett Switch - Hackberry Switch 138 kV Line : Replace Trigas Tap Structure 6/3A | City of Irving, Dallas County | Replace Trigas Tap Structure 6/3A on Liggett Switch - Hackberry Switch 138 kV Line | 2023-09-28 | 2023-12-29 |  |  | 2038367.24 |  |  | 34 | 138 | na | 0.5 | 795 ACSR Drake | Steel 3 - Pole | 140 | 0.5 | na | na | 25.101(c)(5)(B)
0PT48554 0PT49571 0PT50862 (R8646) | SL Einstein – St. Lawrence 138 kV Line: Rebuild | Glasscock County | Rebuild the SL Einstein – St. Lawrence 138 kV Line | 2023-09-26 | 2023-12-15 |  |  | 11264371 |  |  | 1 | 138 | na | 4.6 | 1926.9 ACSS/TW Cumberland | Steel Pole | 75 | 4.6 | na | na | 25.101(c)(5)(B)
0PT48544 0PT48742 0PT50861 (R8638) | Blue Acres- Yosemite 138 kV Line: Rebuild | City of Midland, Midland County | Rebuild of the Yosemite - Blue Acres 138 kV Line. | 2023-10-02 | 2023-12-15 |  |  | 13566439 |  |  | 0 | 138 | na | 5.9 | 1926.9 ACSS/TW Cumberland | Steel 2-Pole, Steel Multi-pole, Steel Pole | varies | 5.9 | na | na | 25.101(c)(5)(B)
0PT48029 | Ferris Sub - Wilmer Sub 69 kV Line : Ferris Sub Cut In | City of Ferris, Ellis County | Reconfigure and reterminate the Ferris Sub - Wilmer Sub 69 kV Line at the two (2) new terminals at Ferris Sub. | 2023-08-01 | 2023-12-15 |  |  | 1610298.35 |  |  | 1 | 69 | na | 0.2 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 0.2 | na | na | 25.101(c)(5)(A)
0PT47905 (R8616) | Buchanan Ranch Sub - Blue Acres Sub 138 kV Line : Rebuild | City of Midland, Midland County | Rebuild the Blue Acres - Buchanan Ranch 138 kV line. | 2023-09-11 | 2023-10-09 |  |  | 1156815 |  |  | 85 | 138 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | varies | 0.2 | na | na | 25.101(c)(5)(B)
0PT47911 0PT47900 0PT50219 (R8626) | SL Triangle - Yosemite 138kV Line: Rebuild | Martin and Midland Counties | Rebuild the Triangle - Yosemite 138 kV line. | 2023-08-30 | 2023-12-15 |  |  | 23686900 |  |  | 3 | 138 | na | 11.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 11.2 | na | na | 25.101(c)(5)(B)
0PT48846 0PT50051 (M4354) | Allen Switch - Anna Switch 138 kV Line : Install POI for RCEC at Bloomdale 138 kV Switch | City of McKinney, Collin County | Cut-in the Allen Switch - Anna Switch 138 kV Line to establish Bloomdale 138 kV Switch | 2024-03-04 | 2024-04-17 | [5 empty] | 0 | 138 | na | 0.13 | 2-1926.9 ACSS/TW Cumberland | Steel Pole | na | na | varies | 0.13 | 25.101(c)(5)(A)
0PT48802 0PT45446 (R6146) | Waco East Switch - Bellmead Sub 138 kV Line: Retermination at Waco East | City of Waco, McLennan County | Reterminate the Waco East Switch - Bellmead Sub 138 kV Line at its new terminal location at McLane Switch. | 2024-03-11 | 2024-05-01 | [5 empty] | 0 | 138 | na | 0.3 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.3 | na | na | 25.101(c)(5)(A)
0PT45958 0PT49410 (R8591) | Structure 3/6 – Thorntonville Sub – Ward Switch 69 kV Conversion to 138 kV | Monahans, Ward and Reeves Counties | Rebuild the Yucca Drive Switch – Crane Substation 69 kV Line between Structure 3/4 – Thorntonville Substation – Ward Switch and convert the circuit to 138 kV. | 2024-01-01 | 2024-06-30 | [5 empty] | 0 | 69 | 138 | 10.53 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 10.53 | na | na | 25.101(c)(5)(B)
0PT40562 0PT49411 (R8591) | Yucca Drive Switch - Structure 3/6 - 69 kV Line Conversion to 138 kV | Monahans, Ward County | Rebuild Yucca Drive Switch – Structure 3/6 – Thorntonville Sub – Ward Switch – Royalty – Coyanosa – Blair Lake Sub – Wolfcamp Tap – Courtney Creek 69 kV line and convert the circuit to 138 kV. | 2024-04-22 | 2024-06-30 | [5 empty] | 0 | 69 | 138 | 2.32 | 1926.6 ACSS/TW Cumberland | Steel Pole | 50 | 2.32 | na | na | 25.101(c)(5)(B)
0PT47024 (R6191) | Waco West Switch - Temple 69 kV Line: Convert to 138 kV | City of Waco, McLennan County | Convert the 31.4 mile existing 69 kV Line to 138 kV operations. This conversion contains a rebuild of the Eddy - Troy line section. | 2024-01-02 | 2024-06-15 | [5 empty] | 0 | 69 | 138 | 6.7 | 1926.9 ACSS/TW Cumberland | Steel 3-Pole, Steel H-Frame, Steel Pole | 40 | 6.7 | na | na | 25.101(c)(5)(B)
0PT47665 (M4329) | Pebble Creek Switch - Compass's Station: Install PODs #3 & #4 | City of Red Oak, Ellis County | Build two additional points of delivery from Pebble Creek Switch-Compass Station 138kV | 2023-10-11 | 2023-11-03 |  |  | 226505.98 |  |  | 0 | na | 138 | 0.08 | 959.6 ACSS/TW Suwannee | na | Station Property | 0.04 | na | na | 25.101(c)(5)(A)
0PT41466 (R1752) | Marlin Switch - Lott Sub 69 kV Line : Retermination | City of Marlin, Falls County | Line work associated to Reterminating Marlin Switch. | 2025-01-29 | 2025-05-15 | [5 empty] | 0 | 69 | na | 0.09 | 959.6 ACSS/TW SUWANNEE | Steel Pole | Centerline | 0.09 | na | na | 25.101(c)(5)(A)
0PT41465 (R1752) | Marlin Switch - Groesbeck Sub 69 kV Line : Retermination | City of Marlin, Falls County | Line work associated to Reterminating Marlin Switch. | 2025-01-29 | 2025-05-15 | [5 empty] | 0 | 69 | na | 0.06 | 959.6 ACSS/TW SUWANNEE | Steel 3 - Pole | 50 | 0.06 | na | na | 25.101(c)(5)(A)
0PT41464 (R1752) | Lake Creek Switch - Marlin Switch 69 kV Line : Retermination | City of Marlin, Falls County | Line work associated to Reterminating Marlin Switch. | 2025-01-29 | 2025-05-15 | [5 empty] | 0 | 69 | na | 0.25 | 959.6 ACSS/TW SUWANNEE | Steel Pole | 50 | 0.25 | na | na | 25.101(c)(5)(A)
0PT44505 (M5283) | Everman Sw. - Cleburne Sw. 138 kV Line: Wilshire Sub Cut-In | City of Burleson, Johnson County | Line work associated to Cutting In Wilshire Substation. The work is occurring on the Everman Switch - Cleburne Switch 138 kV line. | 2023-09-26 | 2023-12-01 |  |  | 1186297.17 |  |  | 0 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 0.4 | na | na | 25.101(c)(5)(A)
0PT48805 R8593 | Expanse Switch - Volta Switch 345 kV Line: Tie Lines | Martin County | Install two 345 POIs to connect Oncor's Expanse Switch to WETT's Volta Switch. | 2023-10-11 | 2023-12-11 |  |  | 513300.15 |  |  | 0 | na | 345 | 0.26 | 2 - 1926.9 ACSS/TW Cumberland | na | na | na | 160 | 0.26 | 25.101(c)(5)(A)
0PT43963 (R985) | Burrow POI - Royse Switch 138 kV Line: Rebuild and convert 69 kV Line to 138 kV operation | City of Royse City, Hunt & Collin Counties | Rebuild the 69 kV Line using a conductor rated 1649 A or greater as a part of the Commerce - Royse 69 kV line conversion to 138 kV | 2023-06-26 | 2023-12-15 |  |  | 11913848.83 |  |  | 48 | 69 | 138 | 5.2 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 5.2 | na | na | 25.101(c)(5)(B)
0PT45420 (M3223) | Royse Switch - Terrell Switch 138/69 kV Line: Re-terminate at Terrell Switch | City of Terrell, Kaufman County | Re-terminate the Royse Switch - Terrell Switch 138 kV and 69 kV Lines to the Terrell Switch Station. | 2023-09-18 | 2023-12-15 |  |  | 2820213 |  |  | 34 | 69/138 | 138 | 0.25 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.25 | na | na | 25.101(c)(5)(A)
0PT45229 0PT48785 (M3223) | Terrell Switch - Kaufman Northwest - Seagoville Switch 138 kV Line: Retermination at Terrell Switch | City of Terrell, Kaufman County | Re-terminate the Terrell Switch - Kaufman Northwest - Seagoville Switch 138 kV Line to the Terrell Switch Station. | 2023-09-11 | 2023-12-15 |  |  | 1864912.7 |  |  | 50 | 138 | na | 0.27 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 0.14 | 70 | 0.13 | 25.101(c)(5)(A)
0PT45228 (M3223) | Royse Switch - Blackland - Terrell Switch 138 kV Line: Re-termination at Terrell Switch | City of Terrell, Kaufman County | Re-terminate the Royse Switch - Blackland - Terrell Switch 138 kV Line to the Terrell Switch Station. | 2023-09-15 | 2023-12-15 |  |  | 1173408.65 |  |  | 34 | 138 | na | 0.12 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.12 | na | na | 25.101(c)(5)(A)
0PT48019 (R8672) | Morgan Creek Switch - Barber Lake Switch 138 kV Line : Rebuild the East circuit | City of Colorado City, Mitchell County | Rebuild the East Circuit of the Morgan Creek Switch - Barber Lake Switch 138 kV Line. | 2023-09-27 | 2023-12-15 |  |  | 9436571 |  |  | 0 | 138 | na | 4.83 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 4.83 | na | na | 25.101(c)(5)(B)
0PT48008 | Marrs Switch - Rolling Hills 138 kV Line: Rolling Hills Substation Cut In | City of Fort Worth, Tarrant County | Cut into the Marrs Switch - Rolling Hills 138 kV Line to establish the new Rolling Hills Substation. | 2023-12-01 | 2023-12-15 | [5 empty] | 0 | 138 | na | 0.2 | 1926.9 ACSS/TW Cumberland, 795 ACSR Drake | Steel Lattice Tower | varies | 0.2 | na | na | 25.101(c)(5)(A)
0PT48004 | Watermill Switch - Parkdale Switch 138 kV Line : Erosion Mitigation | City of Wilmer, Dallas County | Relocate a structure on the Watermill Switch - Parkdale Switch 138 kV Line. | 2024-02-12 | 2024-06-15 | [5 empty] | 0 | 138 | na | 0.1 | 336.4 ACSR Linnett | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT47962 0PT49372 (R6220) | Waco West Switch - Temple Elm Creek Switch 138 kV Line : Waco Sanger Avenue Sub Cut In | City of Waco, McLennan County | Cut in the Waco West Switch - Temple Elm Creek Switch 138 kV Line at the Waco Sanger Avenue Sub. | 2023-09-25 | 2023-12-15 |  |  | 180666.19 |  |  | 0 | 138 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 150 | 0.2 | na | na | 25.101(c)(5)(A)
0PT47961 0PT49224 (R6220) | Waco North Sub - Waco West Sub 138 kV Line : Waco Sanger Avenue Sub Cut In | City of Waco, McLennan County | Terminate the idle Waco North Tap - Waco West Sub 138 kV Line on new steel monopole deadends to accommodate the new Waco Sanger Avenue Sub configuration | 2023-09-08 | 2023-12-15 |  |  | 839736.37 |  |  | 17 | 138 | na | 0.12 | 1926.9 ACSS/TW Cumberland | Steel 2-Pole | 150 | 0.12 | na | na | 25.101(c)(5)(A)
0PT47958 0PT49225 (R6220) | Waco West - Waco East Switch - Elm Mott Switch 138 kV Line : Waco Sanger Cut In | City of Waco, McLennan County | Reterminate the Waco West - Waco East Switch - Elm Mott 138 kV Line at its new terminal location at Waco Sanger Avenue Sub. | 2023-09-18 | 2023-12-15 |  |  | 988490.45 |  |  | 17 | 138 | na | 0.12 | 1926.9 ACSS/TW Cumberland | Steel 2- Pole | 150 | 0.12 | na | na | 25.101(c)(5)(A)
0PT47634 (M3205) | Greenbrier Switch - Royse Switch 138 kV Line: Blackstock Substation Cut-In | Collin County | Cut in the Greenbrier Switch - Royse Switch 138 kV Line to establish the new Blackstock Substation. | 2024-04-01 | 2024-05-01 | [5 empty] | 0 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT47417 | Preston North Sub - Meadow Creek Sub 138 kV Line : Pumping Plant Replacement | City of Dallas, Dallas County | Replacing the one existing UG Transmission HPFF Pressurization Plants at Preston North Sub with a new HPFF Pressurization Plant. | 2024-02-15 | 2024-06-15 | [5 empty] | 0 | 138 | na | na | 1500 AL HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT46976 (M4336) | Payne – MEMC Southwest Tap 138 kV Line: Rebuild | City of Sherman, Grayson County | Rebuild the Payne-MEMC Southwest Tap 138 kV Line | 2023-10-05 | 2023-12-15 |  |  | 6,474,360 |  |  | 0 | 138 | na | 3.28 | 2-959.6 ACSS/TW Suwannee | Steel Pole | 100 | 3.28 | na | na | 25.101(c)(5)(B)
0PT46563 (M4071) | Cedar Crest Switch - Wall Street Sub 138 kV Line: Reterminate at Cedar Crest Switch | City of Dallas, Dallas County | Line work associated with the conversion of the Cedar Crest-Wall Street Line from 69 kV to 138 kV operation. Reterminate line from Cedar Crest Sub to Cedar Crest Switch. | 2023-10-15 | 2023-12-15 |  |  | 283643.65 |  |  | 0 | 69 | 138 | 0.2 | 959.6 ACSS/TW Suwannee | Steel Lattice Tower | 100 | 0.2 | na | na | 25.101(c)(5)(B)
0PT46499 (R985) | Commerce Switch - Royse Switch 69 kV Line: Re-termination at Commerce Switch and Line conversion to 138 kV Operation | City of Commerce, Hunt County | Re-terminate the Commerce Substation - Royse Switch 69 kV Line into Commerce Switch. | 2023-12-01 | 2023-12-29 | [5 empty] | 0 | 69 | 138 | 0.1 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0.1 | na | na | 25.101(c)(5)(B) | Project does not meet reporting criteria and will be removed on next month's report.
0PT45938 0PT51211 | Bennett Road Switch - Bowie Switch 69 kV Line : CMPC Line Hardening (Str. 86/3 - 86/4) | City of Bowie, Montague County | Line work associated with the hardening of the Bennett Road Switch – Bowie Switch 69 kV Line. | 2023-08-11 | 2023-10-09 |  |  | 698288 |  |  | 99 | 69 | na | 0.5 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 0.5 | na | na | 25.101(c)(5)(B)
0PT47928 | Mountain Creek Switch-West Dallas Sub-West Levee Switch 138kV Line: Structure Replacement | City of Dallas, Dallas County | Rebuild 0.7 miles of the Mountain Creek Switch - West Dallas Sub 138 kV Line and 0.93 miles of the Mountain Creek Switch - West Levee Switch 138 kV Line. | 2024-02-05 | 2024-06-15 | [5 empty] | 0 | 138 | na | 1.68 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | 1.68 | na | na | 25.101(c)(5)(B)
0PT44573 (R6160) | Revolution Switch – Generator 138 kV Transmission Line Addition | City of Navarro, Navarro County | Oncor to establish Revolution 138 kV Switch to provide a point-of-interconnection for a solar generator | 2025-02-05 | 2025-04-17 | [5 empty] | 0 | na | 138 | 0.07 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 50 | 0.07 | 25.101(c)(5)(A)
0PT49552 (M3228) | Royse Switch - Shamburger Switch 345 kV Line : Cut-in to establish Poetry Switch | Kaufman County | Cut in the Royse Switch - Shamburger Switch 345 kV Line to establish the new Poetry Switch. | 2023-10-23 | 2024-04-18 |  |  | 3498479.93 |  |  | 0 | 345 | na | 0.9 | 2 -1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 230 | 0.8 | na | na | 25.101(c)(5)(A)
0PT47963 (R6220) | Waco West Switch - McGregor Phillips Switch 69 kV Line : Waco Sanger Avenue Sub Cut In | City of Waco, McLennan County | Reroute the Waco West Switch - McGregor Phillips Switch 69 kV Line around the rebuilt Waco Sanger Avenue Sub | 2023-08-30 | 2023-12-15 |  |  | 3498479.93 |  |  | 20 | 69 | na | 0.23 | 1926.9 ACSS/TW Cumberland | Steel Pole | 150 | 0.23 | na | na | 25.101(c)(5)(A)
0PT45417 (M3223) | Royse Switch - Terrell Switch 138/69 kV Line: Re-terminate at Royse Switch | City of Royse City, Rockwall County | Re-terminate the Royse Switch - Terrell Switch 138 kV and 69 kV Line to the Royse Switch Station. | 2023-09-11 | 2023-12-15 |  |  | 2887344.92 |  |  | 67 | 69/138 | na | 0.36 | 1926.9 ACSS/TW Cumberland | Steel Pole | Station Property | 0.36 | na | na | 25.101(c)(5)(A)
0PT48909 0PT49546 (R6138) | Pin Oak Switch - Fairfield West Switch 138 kV Line: Rebuild Fairfield Switch (BEPC) - Big Brown Tap | City of Fairfield, Freestone County | Rebuild the 2.8 mile Pin Oak Switch – Fairfield West Switch 138 kV Line section from Fairfield Switch (BEPC) to Big Brown Tap using double circuit structures with one circuit in place. | 2023-11-20 | 2024-01-31 | [5 empty] | 0 | 138 | na | 2.8 | 1926.9 ACSS/TW Cumberland | Steel H-Frame, Steel Pole | 100 | 2.8 | na | na | 25.101(c)(5)(B) | This line is a shared ownership with Brazos and Brazos will reimburse Oncor for their portion of the cost.
0PT48044 (M5231) | Everman Switch - Burleson Switch 138 kV Line: Cut-in to Est Rendon Sub | City of Burleson, Tarrant County | Cut in the Everman Switch - Burleson Switch 138 kV line to establish the new Rendon Substation. | 2024-09-09 | 2024-12-15 | [5 empty] | 0 | 138 | na | 0.18 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 0.18 | na | na | 25.101(c)(5)(A)
0PT48279 (M4326) | Italy Sub - Hillsboro Switch 69 kV Line: Rebuild Italy Sub - Milford Exxon Tap | City of Italy, Ellis County | Rebuild the Italy Sub - Milford Exxon Tap section of the Italy Sub - Hillsboro Switch 69 kV Line. | 2025-01-06 | 2025-12-15 | [5 empty] | 0 | 69 | na | 5 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 5 | na | na | 25.101(c)(5)(b)
0PT50482 (R6211) | Pintail Switch - Teal Switch 138 kV Line : Add Second Circuit from Taylor West to Teal | City of Hutto, Williamson County | Install a second circuit on the Pintail - Teal 138 kV line from Taylor West to Teal | 2023-09-18 | 2023-12-15 |  |  | 3361493.52 |  |  | 8 | 138 | na | 2.67 | 1926.9 ACSS/TW Cumberland | Steel Pole | varies | 2.67 | na | na | 25.101(c)(5)(C)
0PT50250 (R6260) | Leon Switch - Dublin Sub 69 kV Line: Establish Ellison Springs 69 kV point of interconnection (POI) | City of Gorman, Comanche County | Establish a Point of Interconnect on the Leon Switch - Dublin Sub 69 kV line. | 2023-09-30 | 2023-12-01 |  |  | 2561680.01 |  |  | 0 | 69 | na | 0.5 | 1926.9 ACSS/TW Cumberland, 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H –Frame Switch, Steel Pole | varies | 0.3 | varies | 0.2 | 25.101(c)(5)(A)
0PT48097 0PT49201 (R6172) | McGregor Phillips Tap Switch - Waco West Switch 69 kV Line : Rebuild Structure 15/2 to Harris Creek Sub | City of McGregor, McLennan County | Rebuild from structure 15/2 to Harris Creek Sub on double circuit monopoles with one circuit installed. | 2023-09-04 | 2023-12-31 |  |  | 12561670 |  |  | 15 | 69 | 138 | 8 | 1926.9 ACSS/TW Cumberland | Steel 2-Pole, Steel 3-Pole, Steel Pole | varies | 8 | na | na | 25.101(c)(5)(B)
0PT50792 | Gainesville Tap 69 SWT 211(N.O) - Gainesville East Tap 69 SWT 205: Replace H Frame 27/4, 27/7, 27/11, 28/1, 30/1, 30/2, 30/3, 30/4, 30/5, 30/6, 31/5, 31/7, 31/8 (GLT) | City of Gainesville, Cooke County | Replace various H frames on Gainesville Tap 69 SWT 211(N.O)-Gainesville East Tap 69 SWT 205. | 2023-06-05 | 2023-10-31 |  |  | 393908 |  |  | 95 | 69 | na | 37.22 | 1/0 ACSR Raven, 3/0 ACSR Pigeon, | Wood H-Frame | Varies | na | na | na | 25.101(c)(5)(B)
0PT50897 (R8672) | Morgan Creek Switch - Sun Switch 138 kV Line : Structure Replacement | City of Colorado City, Mitchell County | Replace and restring structure to accommodate Morgan Creek - Barber Lake 138 kV Line. | 2023-10-03 | 2023-12-15 |  |  | 481791.77 |  |  | 0 | 138 | na | 0.15 | 636 ACSR Grosbeak | Steel 3-Pole | 100 | 0.15 | na | na | 25.101(c)(5)(B)
0PT50618 | Breckenridge - Graham 69 kV Line : South Bend Station Re-termination | City of Graham, Young County | Cut in the Breckenridge - Graham line 69 kV to re-establish Southbend Sub. | 2024-05-06 | 2024-06-30 | [5 empty] | 0 | 69 | na | 0.2 | 4/0 ACSR Penguin | Wood H - Frame | 0.2 | 50 | na | na | 25.101(c)(5)(A)
0PT50414 (R8703) | Upton Sub - Goodnight Sub 138 kV Line : Establish 138 kV Point of Interconnect for point of interconnection (POI) | City of Midkiff,Upton County | Establish 138 kV point of interconnection (POI) | 2023-10-07 | 2023-12-01 |  |  | 949357.32 |  |  | 0 | 138 | na | 0.04 | 1926.9 ACSS/TW Cumberland | Steel Pole | Station Property | 0.04 | na | na | 25.101(c)(5)(A)
0PT49480 | Graham Plant Switch - Breckenridge-Leon Switch 138 kV Line : Substation reconfiguration | City of Graham, Young County | Retermination of the Graham Plant Switch - Breckenridge-Leon Switch 138 kV Line to establish the higher voltage of South bend Sub. | 2024-05-06 | 2024-06-30 | [5 empty] | 0 | 138 | na | 0.1 | 636 ACSR Grosbeak | Wood H-Frame | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT49258 0P48066 (R3028) | SL Alibates Switch - Tule Canyon Switch 345 kV Line: Establish Midpoint Switch for point of interconnection (POI) | Armstrong County | Cut in the Alibates Switch - Tule Canyon Switch 345 kV Line to establish the new Midpoint Switch. | 2023-09-19 | 2023-11-16 |  |  | 1564121 |  |  | 17 | 345 | na | 0.1 | 2-1926.9 ACSS/TW Cumberland | Steel Lattice Towers | na | na | 300 | 0.1 | 25.101(c)(5)(A)
0PT50337 (M3205) | Royse Switch - Nevada 138 kV Line: Blackstock Substation Cut-In | Collin County | Cut in the Royse Switch - Nevada 138 kV Line to establish the new Blackstock Substation. | 2024-04-01 | 2024-05-01 | [5 empty] | 0 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT48041 (M4322) | Ennis West Switch - Sterrett Switch 138 kV Line: Cut In Templeton Substation | City of Waxahachie, Ellis County | Cut-in the Templeton Substation into the Ennis West Switch - Sterrett Switch 138 kV Line | 2023-11-27 | 2023-12-15 | [5 empty] | 0 | 138 | na | 0.39 | 2-959.6 ACSS/TW Suwannee | Steel Pole, Wood H-Frame | 80 | 0.39 | na | na | 25.101(c)(5)(A)
0PT49251 (R3029) | AJ Swope Switch - Carol Wind POI 345 kV Line : Install Line for point of interconnection (POI) | Potter County | Establish 345 kV point of interconnection (POI) | 2023-12-11 | 2024-04-18 | [5 empty] | 0 | na | 345 | 0.2 | 2-1926.9 ACSS/TW Cumberland | Steel Pole | Station Property | 0.2 | na | na | 25.101(c)(5)(A)
0PT49236 (M4338) | Stone Creek Switch - Whitesboro Jordan Sub 138 kV Line : Cut-in Southmayd Switch | Grayson County | Cut in the Stone Creek Switch - Whitesboro Jordan Sub 138 kV Line to establish the new Southmayd Switch. | 2024-03-27 | 2025-04-15 | [5 empty] | 0 | 138 | na | 0.04 | 2-959.6 ACSS/TW Suwannee | Steel Pole | na | na | 100 | 0.02 | 25.101(c)(5)(A)
0PT48645 R8634 | Odessa EHV Switch - Spraberry Switch 138 kV Line : Establish Tesoro Switch | Midland County | Cut into the Odessa EHV Switch - Spraberry Switch 138 kV Line to establish the new Tesoro Switch. | 2023-10-09 | 2023-12-01 |  |  | 2298381.93 |  |  | 0 | 138 | na | 0.7 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | 50 | 0.6 | 200 | 0.1 | 25.101(c)(5)(A)
0PT47633 (R6178) | Hutto Switch - Gilleland Creek Switch 138 kV line: Cut-In to Establish Star Ranch Sub | City of Hutto, Williamson County | Cut-in the Hutto Switch - Gilleland Creek 138 kV line to establish the new Starr Ranch Sub. | 2023-10-23 | 2023-12-11 |  |  | 2592531.45 |  |  | 0 | 138 | na | 0.6 | 1926.9 ACSS/TW Cumberland | Steel Pole | 40 | 0.3 | na | na | 25.101(c)(5)(A)
0PT46152 0PT52027 0PT51317 (R8630) | McDonald Road Switch - Spraberry Switch 138 kV Line : Install Oncor Wrage Ranch POD | City of Garden City, Glasscock County | Establish a 138 kV point of delivery (POD) | 2023-10-23 | 2023-12-01 |  |  | 4158265.18 |  |  | 0 | 138 | na | 1.5 | 1926.9 ACSS/TW Cumberland | Steel 3-pole, Steel Pole, Steel H-Frame, Steel Pole | 50 | 0.2 | varies | 1.3 | 25.101(c)(5)(A)
0PT47794 (R6219) | Taylor Switch - Sandow Switch 138 kV Line : Cut-in for Rookie Switch | Milam County | Cut in the Taylor Switch - Sandow Switch 138 Line to establish the new Rookie Switch. | 2024-01-15 | 2024-05-08 | [5 empty] | 0 | 138 | na | 0.5 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 100 | 0.25 | 25.101(c)(5)(A)
0PT48667 0PT49223 (M4137) | Mesquite E Station - Mesquite N Station 138 kV Line: Rebuild Mesquite Town East Station -Mesquite North Station - Mesquite North Tap | City of Mesquite, Dallas County | Rebuild the Mesquite Town East Station - Mesquite North Station - Mesquite North Tap 138 kV Line. | 2024-09-18 | 2025-05-15 | [5 empty] | 0 | 138 | na | 4.5 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 2.25 | na | na | 25.101(c)(5)(B)
0PT46380 (M4212) | Cedar Crest Switch - Dealey Street - West Levee Switch 138 kV Line: Reconductor | City of Dallas, Dallas County | Reconductor the T27 - Dealey Street - West Levee Switch section of the Cedar Crest Switch - Dealey Street - West Levee Switch 138 kV line. | 2025-01-02 | 2025-05-15 | [5 empty] | 0 | 138 | na | 2.4 | 1590 ACSR Falcon | Steel Pole | 80 | 2.4 | na | na | 25.101(c)(5)(A)
0PT49765 R8634 | Consavvy Switch - Quail Switch 345 kV Line : Establish Tesoro Switch | Midland County | Cut into the Consavvy Switch - Quail Switch 345 kV Line to establish the new Tesoro Switch. | 2023-10-10 | 2023-12-15 |  |  | 2605656.42 |  |  | 0 | 345 | na | 0.3 | 2-1926.9 ACSS/TW Cumberland | Steel Pole | 120 | 0.3 | na | na | 25.101(c)(5)(A)
0PT48648 R8634 | Midessa South Switch - Odessa EHV Switch 345 kV Line : Establish Tesoro Switch | Midland County | Cut into the Midessa South Switch - Odessa EHV Switch 345 kV Line to establish the new Tesoro Switch. | 2023-09-20 | 2023-12-01 |  |  | 3167643.39 |  |  | 1 | 345 | na | 0.3 | 2-1926.9 ACSS/TW Cumberland | Steel Pole | 120 | 0.3 | na | na | 25.101(c)(5)(A)
0PT48664 (M4137) | Mesquite E Station - Mesquite N Station 138 kV Line: Rebuild Sunnyvale Station to Mesquite Town East Station | City of Mesquite, Dallas County | Rebuild the Sunnyvale - Mesquite Town East Station 138 kV Line. | 2023-07-14 | 2023-12-15 |  |  | 10338011 |  |  | 84 | 138 | na | 6.3 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 3.15 | na | na | 25.101(c)(5)(B)
0PT50372 (R8581) | Dooley Sub - Wink Switch 69 kV Line : Re-termination of Structure 20/9 - Wink Switch | City of Kermit, Winkler County | Re-terminate the Dooley Sub - Wink Switch 69 kV Line on the Structure 20/8 - Wink Switch section. | 2023-06-15 | 2023-08-30 | 2023-08-30 |  | 366194.53 |  |  | 100 | 69 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole | 80 | 0.1 | na | na | 25.101(c)(5)(A)
0PT50371 (R8581) | Wink Switch Autotransformer #1 - Wink Switch 69 kV Line: Re-termination | City of Kermit, Winkler County | Re-terminate the Wink Switch Autotransformer #1 - Wink Switch 69 kV Line on the Structure 1/2 - Wink Switch section. | 2023-06-07 | 2023-08-30 | 2023-08-30 |  | 396687.22 |  |  | 100 | 69 | na | 0.2 | 959.6 ACSS/TW Suwannee | Wood 3 - Pole, Wood H-Frame | 80 | 0.2 | na | na | 25.101(c)(5)(A)
0PT51479 | Watermill BKR 45 Switch - Parkdale BKR 590 Switch 138 kV Line : Install Insulator on 52 Structures | City of Hutchins and Wilmer, Dallas County | Install insulators on various poles on Watermill - Parkdale 138 kV line. | 2023-06-01 | 2023-10-31 |  |  | 263564 |  |  | 95 | 138 | na | 9.69 | 1431 ACSR Plover | Single Steel Pole | varies | 9.69 | na | na | 25.101(c)(5)(B)
0PT49517 (R8674) | Driver Sub - DJ Hutt 138 kV: Station Tie Line Build | Midland County | Establish 138 kV point of interconnection (POI) | 2023-10-08 | 2023-12-14 |  |  | 703577.38 |  |  | 0 | na | 138 | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | varies | 0.1 | na | na | 25.101(c)(5)(A)
0PT45019 (M4071) | Cedar Crest Switch - Sargent RD Sub 138 kV Line : Reterminate at Cedar Crest SW | City of Dallas, Dallas County | Reterminate the Cedar Crest SW – Sargent Road Sub 138 kV Line from its existing bay to its new bay. | 2023-09-07 | 2023-12-15 |  |  | 571160.71 |  |  | 66 | 138 | na | 0.2 | 959.6 ACSS/TW Suwannee | Steel Pole | 100 | 0.2 | na | na | 25.101(c)(5)(B)
0PT45959 0PT49227 (R8591) | Ward Switch - Royalty Sub 69 kV Line : Conversion to 138 kV | City of Grandfalls, Ward County | Rebuild the Ward Switch – Royalty Substation section of the Yucca Drive Switch – Crane Substation 69 kV Line. | 2023-12-04 | 2024-06-30 | [5 empty] | 0 | 69 | 138 | 5.06 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 5.06 | na | na | 25.101(c)(5)(B)
0PT48043 (R6226) | Cut-In to Establish South Hewitt Sub | City of Waco, McLennan County | Cut in the Waco West - Temple 69 kV Line at the newly established Castleman Sub | 2023-11-09 | 2023-12-15 | [5 empty] | 0 | 69 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 40 | 0.2 | na | na | 25.101(c)(5)(A)
0PT46488 | Lufkin Switch - Redland Switch 138 kV Line: Kolb Lake POD | City of Lufkin, Angelina County | Provide a 138 kV point of delivery to Kolb Lake POD | 2024-09-11 | 2024-12-15 | [5 empty] | 0 | 138 | na | 0.22 | 959.6 ACSS/TW Suwannee | Steel 3-pole, Steel Pole, Steel H-Frame, | 100 | 0.1 | 70 | 0.12 | 25.101(c)(5)(A)
0PT49588 | Calmont Switch - Benbrook Switch 138 kV Line: Add OPGW | City of Fort Worth, Tarrant County | Install OPGW from Calmont Switch to Benbrook Switch. | 2023-10-30 | 2023-12-15 |  |  | 1721324.86 |  |  | 0 | 138 | na | 4.7 | 1233.6 ACSS/TW Yukon | Steel Lattice Tower | Varies | 4.7 | na | na | 25.101(c)(5)(A)
0PT51082 | Stone Creek Switch BKR 15445 and BKR 15450 - Gainesville East Tap 69 kV SWT 205 | City of Southmayd, Cooke County and Grayson County | Replace various H-Frames on Stone Creek - Gainesville 69 kV line. | 2023-08-23 | 2023-12-29 |  |  | 473611.76 |  |  | 10 | 69 | na | 26.16 | 3/0 ACSR Pigeon | Wood H Frame | Varies | 26.16 | na | na | 25.101(c)(5)(B)
0PT50561 | Montfort - Shankle 138 kV Line: Replaced all poles for 5 structures(GLT) | Ellis County & Navarro County | Replace various structures on Montfort - Shankle 138 kV Line. | 2023-02-03 | 2023-07-28 | 2023-07-28 |  | 229490 |  |  | 100 | 138 | na | 8.72 | 336.4 ACSR Linnet | Wood H Frame | 100 | 8.72 | na | na | 25.10(c)(5)(B)
0PT47806 (R6218) | Bell County East Switch - TNP One (TNMP) Switch 345 kV Line : Cut-in to establish Gibson Switch | City of Cameron, Milam County | Cut into the Bell County East - TNP One (TNMP) 345 kV Line to establish the new Gibson Switch. | 2023-09-29 | 2023-12-14 |  |  | 1707517.11 |  |  | 34 | 345 | na | 0.2 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 160 | 0.1 | Varies | 0.1 | 25.101(c)(5)(A)
0PT47807 (R6188) | Bell County East Switch - TNP One (TNMP) Switch 345 kV Line : Cut-in to establish Little Pond Switch | City of Burlington, Milam County | Cut into the Bell County East - TNP One (TNMP) 345 kV Line to establish the new Little Pond Switch. | 2023-09-22 | 2023-12-14 |  |  | 2074518.49 |  |  | 34 | 345 | na | 0.2 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 160 | 0.1 | Varies | 0.1 | 25.101(c)(5)(A)
0PT48986 (R8659) | Midland East Switch - Midessa South Switch 138 kV Line : Cut-In Sloan Switch for Point of Interconnection | Midland County | Cut in the Midland East Switch - Midessa South Switch 138 kV Line to establish Sloan Switch | 2025-01-01 | 2025-05-08 | [5 empty] | 0 | 138 | na | 0.08 | 1926.9 ACSS/TW Cumberland | Steel Pole | Station Property | 0.08 | na | na | 25.101(c)(5)(A)
0PT48994 (R8659) | Sloan Switch - Holzer Sub 138 kV Line : Install Point of Interconnection | Midland County | Establish a 138 kV Point of Interconnection from Sloan Switch to customer. | 2025-01-01 | 2025-05-08 | [5 empty] | 0 | na | 138 | 0.14 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 70 | 0.14 | 25.101(c)(5)(A)
0PT50379 | Hawk Hollow Switch BKR 20915 and BKR 20920 - Lamar Blossom FID-S 376 and SWT 373 (N.O.) - Tenaska BKR 5035: Replace H Frame 1/3, 2/5, 2/7, 3/4 (GLT) | Lamar County | Replace various H-Frames on Hawk Hollow Switch - Lamar Blossom - Tenaska 138 kV Line. | 2023-09-11 | 2023-12-30 |  |  | 215185 |  |  | 85 | 138 | na | 9.68 | 959.6 ACSS/TW Suwannee | Wood H Frame | 100 | 9.68 | na | na | 25.101(c)(5)(B)
0PT51252 | Lake Arrowhead Tap - Newport (BEPCO) 138 kV Line : Replace Bad Structures 55/6, 63/2, 65/9, 69/9, 71/1, 71/3, 90/3. (GLT) | Montague and Clay County | Replace various H-Frames on Lake Arrowhead Tap - Newport (BEPCO) 138 kV Line. | 2023-10-15 | 2023-12-15 |  |  | 239000 |  |  | 0 | 138 | na | 33.87 | 636 ACSR Grosbeak | Wood H Frame | 50 | 33.87 | na | na | 25.101(c)(5)(B)
0PT46786 (R4015) | Old Lake Switch - Bellevue Sub 69 kV Line: Rebuild to Old Lake Switch - Smith Creek Sub | City of Henrietta, Clay County | Rebuild the Old Lake Switch - Bellevue Sub. Bellevue Sub will be rebuilt as Smith Creek Sub. | 2024-06-10 | 2024-11-15 | [5 empty] | 0 | 69 | 138 | 10.8 | 959.6 ACSS/TW SUWANNEE | Steel Pole | 50 | 10.8 | na | na | 25.101(c)(5)(B)
0PT46977 (M4330) | Payne - Valley 138 kV Line: Add OPGW | Grayson County | Add OPGW to the Payne (16/10) to Valley 138 kV line. | 2024-01-02 | 2024-05-15 | [5 empty] | 0 | 138 | na | 19.19 | 1590 ACSR FALCON | Steel Pole | varies | 19.19 | na | na | 25.101(c)(5)(B)
0PT47658 0PT51210 (M4328) | Pebble Creek Switch - Desoto Switch 138 kV Line : Rebuild | City of Desoto, Ellis County | Rebuild the Red Oak to Desoto Switch 138 kV line. | 2024-01-06 | 2024-05-15 | [5 empty] | 0 | 138 | na | 3 | 2 - 959.6 ACSS/TW SUWANNEE | Steel 3 - Pole, Steel Pole | 100 | 3 | na | na | 25.101(c)(5)(B)
0PT48559 0PT51390 0PT51921 (R8637) | SL Driver – Hadacol Corner 138 kV Line: Rebuild | Glasscock County | Rebuild the Driver – Hadacol Corner 138 kV line. | 2024-01-01 | 2024-05-15 | [5 empty] | 0 | 138 | na | 3.2 | 1926.9 ACSS/TW Cumberland | Steel 3- Pole, Steel H-Frame Switch, Steel Pole | 90 | 3.2 | na | na | 25.101(c)(5)(B)
0PT48561 (R8303) | Big Spring West Switch – Stanton East Switch 138 kV Line: Rebuild | Howard County | Rebuild the Onemile Switch (Big Spring West) – Stanton East Switch 138 kV Line. | 2023-11-01 | 2024-09-13 | [5 empty] | 0 | 138 | na | 16.5 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 70 | 16.5 | na | na | 25.101(c)(5)(B)
0PT48562 0PT49583 (R8635) | SL Tall City – Pecan Grove 138 kV Line: Rebuild | Midland County | Rebuild SL Tall City – Pecan Grove 138 kV Line. | 2023-11-27 | 2024-05-15 | [5 empty] | 0 | 138 | na | 7.5 | 1926.9 ACSS/TW CUMBERLAND | Steel 3- Pole, Steel pole | 70 | 7.45 | 70 | 0.05 | 25.101(c)(5)(B)
0PT48567 0PT43110 0PT52074 (R8636) | SL Luther – Vealmoor 138 kV Line: Rebuild | Borden and Lamar County | Rebuild the SL Luther - Vealmoor 138 kV Line | 2023-12-01 | 2024-05-15 | [5 empty] | 0 | 138 | na | 10 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | Varies | 10 | na | na | 25.101(c)(5)(B)
0PT48570 0PT51255 (R8360) | McDonald Road Sub - Morgan Creek Switch 138 kV Line: Rebuild Navigation Sub to Morgan Creek Switch | City of Colorado City, Mitchell County | Rebuild the Navigation Sub - Morgan Creek Switch 138 kV section on the McDonald Road Switch - Morgan Creek Switch 138 kV line. | 2024-06-01 | 2024-12-15 | [5 empty] | 0 | 138 | na | 20.3 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 20.3 | na | na | 25.101(c)(5)(B)
0PT48571 0PT51254 (R8360) | McDonald Road Switch - Morgan Creek Switch 138 kV Line: Rebuild McDonald Road to Navigation Sub | City of Big Spring, Howard County | Rebuild the McDonald Road Switch - Navigation Sub 138 kV section on the McDonald Road Switch - Morgan Creek Switch 138 kV line. | 2024-01-01 | 2024-05-15 | [5 empty] | 0 | 138 | na | 7.7 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 7.7 | na | na | 25.101(c)(5)(B)
0PT48572 (R8645) | Spraberry Switch – Polecat Creek Switch 138 kV Line: Rebuild Spraberry Switch to Quartz Sand Switch | City of Odessa, Midland County | Rebuild the line from Spraberry Switch to the newly established Quartz Sand Switch. | 2023-11-27 | 2024-05-15 | [5 empty] | 0 | 138 | na | 16.1 | 1926.9 ACSS/TW CUMBERLAND, 636 ACSR GROSBEAK | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 16.1 | na | na | 25.101(c)(5)(B)
0PT49378 | Wichita Falls South Switch - Alvord Sub 138 kV Line : Replace Lake Arrowhead Tap | City of Wichita Falls, Wichita County | Replace POD switch structure on Wichita Falls South Switch - Alvord Sub 138 kV Line | 2024-01-18 | 2024-03-15 | [5 empty] | 0 | 138 | na | 0.22 | 636 ACSR GROSBEAK | Steel H –Frame Switch, Steel Multi-pole | 50 | 0.22 | na | na | 25.101(c)(5)(B)
0PT49596 0PT51519 (R8475) | Lamesa Switch - McKenzie Draw Switch 138 kV Line : Rebuild from Jim Payne POI - Lamesa Switch | City of Lamesa, Dawson County | Rebuild the Lamesa Switch - Jim Payne POI 138 kV Line. | 2024-01-01 | 2024-05-15 | [5 empty] | 0 | 138 | na | 7.82 | 1926.9 ACSS/TW CUMBERLAND | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 7.82 | na | na | 25.101(c)(5)(B)
0PT45633 (R6246) | Graham Plant Switch - Breckenridge - Leon Switch 138 kV Line: Cut-in to establish Ghost Town Switch | City of Breckenridge, Stephens County | Cut in the Graham Plant Switch - Breckenridge - Leon Switch 138 kV line to establish the new Ghost Town Switch. | 2024-03-21 | 2024-05-09 | [5 empty] | 0 | 138 | na | 0.3 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 60 | 0.1 | 120 | 0.1 | 25.101(c)(5)(A)
0PT50441 (R8679) | Lamesa Switch - POI 138 kV Line: Install Line | City of Lamesa, Dawson County | Establish 138 kV point of interconnection (POI) | 2024-01-08 | 2024-05-15 | [5 empty] | 0 | na | 138 | 0.1 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | na | na | 100 | 0.1 | 25.101(c)(5)(A)
0PT50440 (R6253) | Temple Pecan Creek Switch - POI 138 kV Line: Install Line | City of Temple, Bell County | Establish 138 kV point of interconnection (POI) | 2024-01-22 | 2024-05-09 | [5 empty] | 0 | na | 138 | 0.1 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | na | na | 100 | 0.1 | 25.101(c)(5)(A)
0PT50335 (R6256) | Jewett Switch - St. Johns Switch 345 kV Line: Cut-in to establish Bale Switch | Falls County | Cut in the Jewett Switch - St. Johns Switch 345 kV line to establish the new Bale Switch. | 2024-01-08 | 2024-05-15 | [5 empty] | 0 | 345 | na | 0.1 | 2 -1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 225 | 0.1 | na | na | 25.101(c)(5)(A)
0PT50370 (R6257) | Lufkin Switch - Crockett Switch 138 kV Line: Cut-in to establish Rowan Creek Switch | City of Lufkin, Angelina County | Cut in the Lufkin Switch - Crockett Switch 138 kV line to establish the Rowan Creek Switch. | 2024-09-01 | 2024-12-05 | [5 empty] | 0 | 138 | na | 0.1 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT48020 (R8623) | Morgan Creek Switch - Barber Lake Switch 138 kV Line: Rebuild the West circuit | City of Colorado City, Mitchell County | Rebuild the West circuit of Morgan Creek Switch - Barber Lake Switch 138 kV Line. | 2024-01-01 | 2024-05-13 | [5 empty] | 0 | 138 | na | 4.75 | 1926.9 ACSS/TW Cumberland | Steel 2 - Pole, Steel 3 - Pole, Steel Pole | Varies | 4.75 | na | na | 25.101(c)(5)(B)
0PT47551 (R8709) | Paint Creek Switch - China Grove Switch 138 kV Line: Install Raven POI | City of Sylvester, Fisher County | Establish the Raven POI | 2024-01-08 | 2024-03-15 | [5 empty] | 0 | 138 | na | 0.55 | 1926.9 ACSS/TW CUMBERLAND, 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel H –Frame Switch, Steel Pole | 50 | 0.4 | 100 | 0.15 | 25.101(c)(5)(A)
0PT50272 (M4356) | Tri Corner Switch - Anole BESS 345 kV Line : Establish 345 kV POI | City of Combine, Dallas County | Cut in the Tri Corner Switch – Anole BESS 345 kV line | 2024-01-04 | 2024-04-18 | [5 empty] | 0 | na | 345 | 0.13 | 2-1926.9 ACSS/TW Cumberland | Steel Lattice Tower | na | na | varies | 0.13 | 25.101(c)(5)(A)
0PT48505 (R8528) | Odessa EHV Switch - Edwards Tap 138 kV Line: Rebuild | City of Odessa, Ector County | Rebuild the Odessa EHV Switch to Edwards Tap 138kV Line | 2024-02-15 | 2024-12-31 | [5 empty] | 0 | 138 | na | 16.2 | 1926.9 ACSS/TW CUMBERLAND, 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 16.1 | varies | 0.1 | 25.101(c)(5)(B)
0PT48038 (M3504) | Wise County Switch - Jack County Switch 138 kV Line: Cut - In to Establish Runaway Bay Substation | City of Runaway Bay, Wise County | Cut into the Brazos Electric-owned line to establish Oncor Electric-owned Runaway Bay Substation. | 2023-11-13 | 2023-12-15 | [5 empty] | 0 | na | 138 | 0.06 | 1926.9 ACSS/TW CUMBERLAND | na | 0.06 | Station Property | na | na | 25.101(c)(5)(A)
0PT51953 | Sandow Switch - Taylor Sub 138 kV Line : Thorndale North Sub Re-termination | City of Thorndale, Milam County | Re-terminate existing Sandow Switch - Taylor 138 kV Line at its new location inside Thorndale North Sub. | 2023-10-02 | 2023-12-01 |  |  | 452731.74 |  |  | 0 | 138 | na | 0.1 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT50281 | Brownwood Switch - Goldthwaithe Sub 138 kV Line : Replace 18 Poles identified during GLT | Brown and Mills County | Replace various poles identified during GLT on Brownwood Switch - Goldthwaithe Sub 138 kV Line. | 2023-05-01 | 2023-11-30 | [5 empty] | 77 | 138 | na | 29.52 | 959.6 ACSS/TW SUWANNEE | Wood H-Frame | 100 | 29.52 | NA | NA | 25.101(c)(5)(B)
0PT47755 (R6214) | Temple Switch - Minerva Switch 69 kV Line : Cut-in to establish McFall Switch | City of Cameron, Milam County | Cut into the Temple Switch - Minerva Switch 69 kV Line to establish the new McFall Switch | 2024-02-19 | 2024-05-16 | [5 empty] | 0 | 69 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | varies | 0.1 | 25.101(c)(5)(A)
0PT48361 (M4001) | Venus Switch - Liggett Switch 345 kV Line : Cut-in Endeavor Switch | City of Midlothian, Ellis County | Cut in the Venus - Liggett 345 kV Line to establish the new Desert Willow Switching Station. | 2024-02-12 | 2024-05-15 | [5 empty] | 0 | 345 | na | 0.2 | 2 -1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | 160 | 0.2 | na | na | 25.101(c)(5)(A)
0PT49484 | Hutto Switch - Round Rock Sub 138 kV Line : Relocation for Old Settlers Blvd | City of Round Rock, Williamson County | Relocate structure 13/4 to 13/11 due to city expansion of roadway. | 2024-01-15 | 2024-05-15 | [5 empty] | 0 | 138 | na | 0.9 | 1590 ACSR Falcon | Steel Pole | 100 | 0.9 | na | na | 25.101(c)(5)(F)
0PT50059 (R8667) | Vincent Sub - Wildhorse POD 138 kV Line : Rebuild | Howard County | Rebuild the Vincent Sub - Wildhorse POD 138 kV Line. | 2023-12-04 | 2024-05-15 | [5 empty] | 0 | 138 | na | 4.13 | 1926.9 ACSS/TW Cumberland | Steel Pole | 75 | 4.13 | na | na | 25.101(c)(5)(B)
0PT50347 (R8678) | Yucca Drive Switch - Moss Switch 138 kV Line : Cut-in to establish Raceway Switch | City of Odessa, Ector County | Cut into the Yucca Drive Switch - Moss Switch 138 kV Line to establish the new Raceway Switch. | 2024-01-08 | 2024-05-15 | [5 empty] | 0 | 138 | na | 0.19 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 75 | 0.19 | 25.101(c)(5)(A)
0PT50418 (M3500) | Bennett Road Switch - Krum Tap Switch 138 kV Line: Cut-In Denton Creek Switch | City of Decatur, Wise County | Cut in the new Denton Creek Switch. | 2024-02-15 | 2024-05-15 | [5 empty] | 0 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | Centerline | 0.1 | na | na | 25.101(c)(5)(A)
0PT50909 (R985) | Commerce Sub - Commerce Switch 138 kV Line : Re-termination at Commerce Switch | City of Commerce, Hunt County | Re-terminate the Commerce Substation - Commerce Switch 138 kV line at Commerce Switch. | 2024-02-26 | 2024-05-15 | [5 empty] | 0 | 138 | na | 0.15 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0.15 | na | na | 25.101(c)(5)(B)
0PT51088 (M5281) | Roanoke Switch - Euless /Deen Switch 138 kV Line: Retermination at Keller Wall Price (East) | City of Keller, Tarrant County | Reterminate both circuits from Euless and Deen into the East side of Keller Wall Price | 2024-02-05 | 2024-05-15 | [5 empty] | 0 | 138 | na | 0.2 | 1926.9 ACSS/TW/E3X Cumberland | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT51143 (R8691) | Tall City Sub - Glass Ranch Sub 138 kV Line : Cut-In to Establish Lazy Ranch Sub | City of Stanton, Martin County | Cut into City Sub - Glass Ranch Sub 138 kV Line to establish Mustang Spring Sub. | 2024-02-16 | 2024-05-15 | [5 empty] | 0 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 0.1 | na | na | 25.101(c)(5)(A)
0PT48142 (R6252) | Sam Switch - Fort Smith Switch 345 kV Line : Cut-in to establish Files Valley Switch | City of Itasca, Hill County | Cut into the Sam Switch - Fort Smith Switch 345 kV Line to establish the new Files Valley Switch | 2024-02-19 | 2024-05-16 | [5 empty] | 0 | 345 | na | 0.16 | 2-1926.9 ACSS/TW Cumberland | Steel Lattice Tower, Steel Pole | na | na | varies | 0.16 | 25.101(c)(5)(A)
0PT50766 (R8697) | Midkiff Switch - Shaw POD 138 kV line: Shaw POD | Midland County | Cut into the Midkiff Switch - Spraberry 138 kV Line to establish the new Shaw POD | 2024-02-01 | 2024-05-15 | [5 empty] | 0 | 138 | na | 0.83 | 1926.9 ACSS/TW Cumberland & 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 0.23 | Varies | 0.22 | 25.101(c)(5)(A)
0PT46342 | Sherry Switch - Mountain Creek Switch 138 kV Line: OPGW Only | City of Arlington, Tarrant County | Install OPGW on the Timberview Switch - Cedar Hill Switch 138 kV Line. | 03/06/2024 | 05/15/2024 | [5 empty] | 0 | 345 | na | 10.9 | 795 ASCR Drake | Steel Lattice Tower | 220 | 10.9 | na | na | 25.101(c)(5)(A)
0PT48049 0PT48236 (R6094) | Athens Switch - Murchison Sub 69 kV: Rebuild to 138 kV | Henderson County | Rebuild a section of the Athens to - Tyler Switch 69 kV line as a 138 kV double circuit line with one circuit installed. | 06/03/2024 | 09/15/2024 | [5 empty] | 0 | 69 | 138 | 5.40 | 959.6 ACSS/TW SUWANNEE | Steel H-Frame, Steel Pole | Varies | 5.40 | na | na | 25.101(c)(5)(B)
0PT48568 (R8641) | Midkiff Switch – Pemkiff 138 kV Line: Rebuild | Upton County | Rebuild the line from Midkiff Switch – Pemkiff with double circuit steel poles with one circuit installed. | 02/26/2024 | 05/15/2024 | [5 empty] | 0 | 138 | na | 0.31 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 150 | 0.31 | na | na | 25.101(c)(5)(B)
0PT49445 0PT50541 (R8671) | SL Expanse Switch - Brown Switch 138 kV Line : Install Merrick Tap | Martin County | Provide a 138 kV POD on the SL Expanse Switch - Brown Switch 138 kV Line. | 2024-02-05 | 04/15/2024 | [5 empty] | 0 | 138 | na | 0.23 | 1926.9 ACSS/TW CUMBERLAND | Steel H-Frame, Steel Pole | na | na | 70 | 0.23 | 25.101(c)(5)(A)
0PT49594 (R8635) | Tall City - Glass Ranch 138 kV Line: Rebuild | City of Odessa, Midland County | Reconductor from Tall City - Glass Ranch 138 kV line. | 02/12/2024 | 05/15/2024 | [5 empty] | 0 | na | 138 | 4.05 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 70 | 4.05 | na | na | 25.101(c)(5)(B)
0PT50901 (R8699) | Buffalo Sub - Sale Ranch Sub 138 kV Line : Establish POD for customer | City of Stanton, Martin County | Establish Wishbone POD on the Buffalo - Sale Ranch 138 kV Line. | 2024-02-01 | 05/15/2024 | [5 empty] | 0 | 138 | na | 0.15 | 1926.9 ACSS/TW CUMBERLAND, 959.6 ACSS/TW SUWANNEE | Steel Pole | na | na | 70 | 0.15 | 25.101(c)(5)(A)
0PT51154 (R8670) | Quartz Sand Switch - Dewey Lake Sub 138 kV Line: Build New Line | City of Stanton, Glasscock County | This project will construct the Quartz Sand Switch - Dewey Lake Sub 138 kV Line. | 02/05/2024 | 05/15/2024 | [5 empty] | 0 | 138 | na | 0.10 | 959.6 ACSS/TW SUWANNEE | Steel Pole | Station Property | 0.10 | na | na | 25.101(c)(5)(A)
0PT51155 (R8670) | Spraberry Sub - Polecat Creek Sub 138 kV Line: Cut in to establish Quartz Sand Switch | City of Stanton, Glasscock County | The Spraberry Sub - Polecat Creek Sub 138 kV line will cut-in Quartz Sand Switch. | 01/15/2024 | 05/15/2024 | [5 empty] | 0 | 138 | na | 0.20 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 50 | 0.20 | na | na | 25.101(c)(5)(A)
0PT51454 (R8677) | Horseshoe Springs Switch - Riverton Switch 138 kV Line: Cut in to Establish Roadrunner Capacitor Bank | City of Orla, Reeves County | Retermination of wire into Roadrunner Cap Bank from existing structure 5/5. | 01/08/2024 | 05/15/2024 | [5 empty] | 0 | 138 | na | 0.80 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 70 | 0.80 | na | na | 25.101(c)(5)(A)
0PT49950 (R8671) | Merrick Tap - Merrick POD 138 kV Line : Install POI Line to Customer | Martin County | Build a 2.45 mile 138 kV line from Merrick POD to customer. | 2024-01-04 | 2024-04-15 | [5 empty] | 0 | na | 138 | 2.45 | 959.6 ACSS/TW SUWANNEE | Steel Pole | na | na | 70 | 2.45 | 25.101(c)(5)(A)
0PT51967 (M4368) | Colin Switch - Stone Creek Switch 138 kV Line: Install 138kV POI for Rayburn's Celina Sub | City of Celina, Collin County | Line modifications to the Collin Switch - Stone Creek Switch 138 kV transmission line to establish POI for Rayburns Celina Sub. | 2024-02-15 | 12/13/2024 | [5 empty] | 0 | 138 | na | .27 | 1926.9 ACSS/TW CUMBERLAND, 795 ACSR DRAKE | Steel Pole, Wood Pole | 100 | .27 | na | na | 25.101(c)(5)(A)
0PT52164 (M4370) | Anna Switch - Sherman South Sub 138 kV Line: Establish POI for REC Waldrip | City of Anna, Collin County | Line modifications to the Anna Switch - Sherman South 138 kV transmission line near Str. 18/1 to establish POI for Rayburns Waldrip Sub. | 2023-11-27 | 12/15/2024 | [5 empty] | 0 | 138 | na | .5 | 2 - 959.6 ACSS/TW Suwannee, 795 ACSR Drake | Steel Pole, Wood 3 Pole | varies | .07 | .43 | varies | 25.101(c)(5)(A)
Line Clearance Review Program (LCRP)
Projects Relating to HB 4150 (HB 4150) | TBD | TBD | TBD | 2022-07-01 | TBD |  |  | TBD |  |  |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | Projects related to efforts required under HB 4150.
0PT48834 (HB4150) | Big Spring Switch - Gunsight Switch 138 kV Line : Clearance Improvement | Howard County | Replace 6 structures along Big Spring - Gunsight 138 kV Line, approximately .5 miles, and raise 16 crossarms. | 2022-09-30 | 2022-12-20 | 2022-12-20 |  | 462445 |  |  | 100 | 138 | na | 57 | 336 ACSR Linnet, 636 ACSR Grosbeak | Wood H-Frame | Varies | 57 | na | na | 25.101(c)(5)(b)
0PT49662 (HB4150) | Monticello Switch - Woodard Switch 345 kV Line : Clearance Improvement | City of Mount Vernon, Franklin County | Replace 11 structures on the Monticello Switch - Woodard Switch 345 kV to improve clearances | 2024-01-22 | 2024-05-15 | [5 empty] | 0 | 345 | na | 33 | 2- 795 ACSR Drake | Steel Lattice Tower | varies | 33 | na | na | 25.101(c)(5)(B)
0PT49798 (HB4150) | Yucca Drive Switch - Sand Lake Switch 138 kV Line : Clearance Improvement | City of Wickett, Ward County | Replace structure on Yucca Switch - Sand Lake Switch 138 kV Line to improve clearances. | 2023-08-31 | 2023-09-03 |  |  | 357497 |  |  | 0 | 138 | na | 0.18 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 0.09 | na | na | 25.101(c)(5)(B)
0PT50697 (HB4150) | Graham Plant Switch - Leon Switch 138 kV Line : Clearance Improvement | City of Graham, Young County | Replace structures on Graham Plant Switch - Leon Switch 138 kV Line | 2023-10-12 | 2023-12-31 | [5 empty] | 0 | 138 | na | 0.4 | 636 ACSR Grosbeak | Wood H-Frame | 50 | 0.4 | na | na | 25.101(c)(5)(B)
0PT52198 (HB4150) | Graham Plant Switch - Cook Field Road Switch 345 kV Line: Clearance Improvement | City of Graham, Young and Shackelford County | Replace structures to improve clearance. | 2023-11-15 | 2023-12-31 | [5 empty] | 0 | 345 | na | 1 | 2 - 795 ACSR Drake | Steel Lattice Tower | 120 | 0.5 | na | na | 25.101(c)(5)(B)
0PT52205 (HB4150) | Watermill Switch - Seagoville Switch 138 kV Line: Clearance Improvement | City of Seagoville, Dallas County | Replace 4 - Wood H-frames along the Watermill Switch - Seagoville Switch 138 kV Line to improve clearances. | 2023-10-31 | 2023-12-31 | [5 empty] | 0 | 138 | na | 0.4 | 795 ACSR Drake | Wood H-Frame | 100 | 0.4 | na | na | 25.101(c)(5)(B)
STATIONS
0PT03981 (M5155) | Sherry Switch: Two Line Terminal Upgrade | City of Arlington, Tarrant County | Upgrade line terminal and associated equipment to meet as a part of upgrading the Handley Sherry 138 kV Double-circuit Line | 2022-04-19 | 2022-12-27 | 2022-12-27 |  | 406246 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT04155 0PT38702 | Blagg Sub: Establish Substation with one Transf. and Two Feeder Breakers: | City of Denton, Denton County | Establish Substation with one Transf. and Two Feeder Breakers | 2020-07-28 | 2020-12-31 | 2020-12-31 |  | 4832694 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40876 0PT39914 | Triangle Sub : Install one Transformer on #2 | City of Stanton, Martin County | Install a second transformer and remove transformers #1 and #2 at Stanton Substation. Complete installation of fiber for line protection, modify 138 kV bus protection to provide redundancy. | 2022-01-31 | 2022-12-01 | 2022-12-01 |  | 3625120 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40615 (R8523) | Nelson Switch : Establish a 138 kV point of interconnection (POI) | City of Odessa, Ector County | Establish a 138 kV point of interconnection (POI) by installing one 138 kV, 3200 A circuit breaker in existing ring-bus. | 2020-09-18 | 2025-12-15 |  |  | 1240255 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | Cost and project was updated to include ROW estimates in November 2020. This was not accurate and the project is being revised back to its original values.
0PT40650 (R8540) | Manning POD: Establish a 138 kV POD | City of Odessa, Ector County | Establish a 138 kV POD on the LCRA Crane East - Crane 138 kV line. | 2020-12-11 | 2022-08-16 | 2022-08-16 |  | 922339 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
19T63016 (R8444) | Scurry County South Switch: Add 138 kV line terminal for Canyon Wind | City of Snyder, Scurry County | Install a new 138 kV bay with two 138 kV, 3200 A circuit breakers and associated equipment to install a 138 kV POI for customer's generator. | 2021-07-16 | 2023-11-17 |  |  | 1995325 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40937 0PT42656 | Blair Lake Sub : Establish station with 47 MVA, 138/69-21.6 kV Transformer and Install Distribution Automation on Feeder 6321 | City of Pecos, Reeves County | Replace Bank #1 with 47 MVA, 138/69-21.6 kV transformer. Also includes all work associated with PETE 40783 (Install Distribution Automation on Feeders 6321). | 2021-07-11 | 2021-12-30 | 2021-12-30 |  | 3439065 |  |  | 100 | na | 69/138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40648 (R8544) | Dillon POD : Establish 138 kV POD | Martin County | Provide a 138 kV (POD) on the Andrews North McKenzie Draw 138 kV line by installing three138 kV 3200 A motor operated sectionalizing switches and low-voltage metering. | 2021-01-12 | 2023-03-07 | 2023-03-07 |  | 764363 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41627 (R984) | Stouts Creek Switch : Establish Station for (POI) | Hopkins County | Establish station by installing three 345 kV, 3200 A circuit breakers in a 3-breaker ring bus arrangement for a (POI). Station will connect to the Allen Switch- Monticello Switch 345 kV line. | 2024-06-16 | 2024-11-14 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41218 (M4311) | Ennis West Switch: Install 138 kV circuit breakers | City of Ennis, Ellis County | Install 138 kV circuit breakers and re-terminate Oncor line terminals | 2021-01-12 | 2021-05-09 | 2021-05-09 |  | 2281324 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42794 | Plano Shiloh Road Sub : Install a third transformer at Plano Shiloh Rd and three breakers | City of Plano, Collin County | Install a third transformer at Plano Shiloh Rd and three breakers | 2021-03-30 | 2021-06-30 | 2021-06-30 |  | 6182250 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42143 | Driver Sub : Install transformer #4 with one transformer and two feeders | City of Odessa, Midland County | Install transformer #2 with one transformer and two UG feeder breakers | 2021-01-05 | 2021-12-19 | 2021-12-19 |  | 2640072 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41447 (M5317) | Toco Switch: Add a single line terminal to establish POI | City of Toco, Lamar County | Add a single line terminal to the existing ring-bus for the POI. | 2024-02-27 | 2024-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42139 | Celina Southeast Sub : Install transformer #2 with one transformer and two UG feeder breakers | City of Celina, Collin County | Install transformer #2 with one transformer and two 25 kV feeder breakers. | 2024-01-15 | 2025-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | On hold
0PT42176 | Brookhollow Sub : Install transformer #3 with one transformer and two feeder breakers | City of Arlington, Tarrant County | Install transformer #3 with one transformer and two feeder breakers. | 2021-02-28 | 2021-12-13 | 2021-12-13 |  | 2900455 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41016 (M5222) | Duval Sub: Remove 69 kV station and establish 138-12.5 kV station | City of Fort Worth, Tarrant County | 69 kV station and establish 138-12.5 kV station | 2022-07-15 | 2022-12-21 | 2022-12-21 |  | 8309347 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40560 (R6132) | Four Brothers Switch : Establish 345 kV switch bus with a 3-breaker arrangement | City of Waco, Hill County | Establish 345 kV switch bus with a 3-breaker arrangement | 2021-10-13 | 2022-05-09 | 2022-05-09 |  | 6227825 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT03978 (M5155) | Handley Switch: Upgrade line terminal and associated equipment | City of Fort Worth, Tarrant County | Upgrade line terminal and associated equipment as a part of upgrading the Handley – Sherry 138 kV double-circuit line. | 2021-12-01 | 2022-12-27 | 2022-12-27 |  | 580434 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41031 18T80022 (M5278) | Timberview Switch: Establish 345 kV Switch | City of Everman, Tarrant County | Establish 345 kV switch bus with a 15-breaker and-a-half bus arrangement. | 2021-06-07 | 2021-12-22 | 2021-12-22 |  | 20561331 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43602 0PT43314 | Prosper Sub : Establish substation with one transformer and two feeder breakers | City of Prosper, Collin County | Establish substation with one transformer and two feeder breakers. | 2021-04-27 | 2021-06-29 | 2021-06-29 |  | 8512765 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42179 | Campion (formerly Bluebonnet Lakes) Sub : Establish station with one transformer and two feeder breakers | City of Grand Prairie, Dallas County | Establish station with one transformer and two feeder breakers. | 2022-12-07 | 2023-08-07 | 2023-08-07 |  | 8473410 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42377 (M4247) | Carrollton Northwest Switch : Replace the existing autotransformer | City of Carrollton, Denton County | Replace the existing autotransformer and install one 345 kV, 3200A circuit breaker on the 345 kV bus. | 2021-07-12 | 2021-12-21 | 2021-12-21 |  | 8135469 |  |  | 100 | 138/345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41599 (M4093) | Mountain Creek Switch : Install two 138 kV, 3200 A circuit breakers | City of Dallas, Dallas County | Install two 138 kV, 3200 A circuit breakers for Mountain Creek Switch- Cedar Crest Switch 138 kV double-circuit line. | 2021-08-14 | 2021-12-15 | 2021-12-15 |  | 1361266 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41754 0PT40063 | Oil Mill Lake Sub : Rebuild Marlin sub on new site | City of Marlin, Walls County | Establish station to replace Marlin with two transformers. Connect the station to the Marlin Switch – Groesbeck Switch 69 kV line and install three 138 kV line sectionalizing switches. | 2021-04-19 | 2021-12-10 | 2021-12-10 |  | 5356546 |  |  | 100 | 69 | 69/138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43555 (R8492) | Rexall Switch : Replace two 138 kV circuit breakers with auto sectionalizing switches | City of Odessa, Midland County | Replace two 138 kV circuit breakers with auto sectionalizing switches | 2021-10-13 | 2021-12-22 | 2021-12-22 |  | 1055811 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42651 | Kennedale Sub : Remove the existing 345 kV transformers from substation and install a 3rd transformer | City of Kennedale, Tarrant County | Remove the existing 345 kV transformers from substation and install a 3rd transformer and complete distribution feeder exit work | 2021-06-10 | 2021-12-17 | 2021-12-17 |  | 3600695 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39293 17T80045 0PT40089 | Elkhart Sub : Install transformer #2 with one transformer and one feeder breaker | Elkhart County | Install transformer #2 with one transformer and one feeder breaker | 2021-08-18 | 2021-12-16 | 2021-12-16 |  | 3379346 |  |  | 100 | na | 69 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39290 | Lake Brownwood Sub : Establish a new substation with one transformer and two feeder breakers | City of Brownwood, Brown County | Establish a new substation with one transformer and two feeder breakers and demolish the existing station. | 2021-06-07 | 2021-12-15 | 2021-12-15 |  | 2485000 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43638 | Midland Downtown Sub : Replace two existing transformers and add one feeder breakers to bank #1. | City of Midland, Midland County | Replace two existing transformers and add one feeder breakers to bank #1 | 2021-08-09 | 2021-12-01 | 2021-12-01 |  | 3594743 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39494 0PT38777 (M4275) | Greenbrier Switch (formerly Princeton) : Establish Switching Station | City of Princeton, Collin County | Establish switching station adjacent to the existing Princeton POD by installing six 138 kV circuit breakers in a breaker-and-a-half arrangement as part of the line upgrade from Anna Tap - Princeton Switch. | 2021-11-09 | 2022-06-23 | 2022-06-23 |  | 7283918 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40959 0PT41841 | Reindeer Sub : Establish substation with one transformers and two feeder breakers | City of Lancaster, Dallas County | Establish substation with one transformers and two feeder breakers | 2021-07-30 | 2021-12-29 | 2021-12-29 |  | 4893263 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44371 | Goddard Sub : Replace switchgear with outdoor feeder breakers and install distribution automation on two feeders | City of Midland, Midland County | Replace switchgear with outdoor feeder breakers and install distribution automation on two feeders | 2021-07-20 | 2021-12-15 | 2021-12-15 |  | 3088405 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41041 0PT42306 (R8479) | Courtney Creek (Pecos) Switch: Establish 138/69 kV Switching Station | Pecos County | Establish the Courtney Creek 138/69 kV Switch in order to tie into AEP's Rio Pecos Switch - Fort Stockton Switch 138 kV line. The switching station will be installed initially as a 5-breaker 138 kV breaker-and-a-half arrangement with one 138/69 kV autotransformer and one 69 kV line terminal. | 2022-09-15 | 2023-05-31 | 2023-05-31 |  | 10020859 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41032 (M5278) | Everman Switch: Reconfigure 345 kV station by constructing a 4-breaker 345 kV in a ring bus arrangement | City of Fort Worth, Tarrant County | Reconfigure 345 kV station by constructing a 4-breaker 345 kV in a ring bus arrangement. | 2021-06-28 | 2022-06-01 | 2022-06-01 |  | 4728468 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43953 (R8538) | Midland East Switch: 138 kV station rebuild | City of Midland, Midland County | Rebuild the 138 kV switch as an 13-breaker initial, 18-breaker ultimate breaker-and-a-half arrangement. | 2021-06-10 | 2021-12-15 | 2021-12-15 |  | 10097944 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44443 0PT44618 | Blain (formerly known as Dew) Sub : Establish substation with one transformer and two feeder breakers | City of Dew, Freestone County | Establish substation with one transformer and two feeder breakers | 2021-08-11 | 2022-11-01 | 2022-11-01 |  | 4802523 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41017 0PT41805 | Stuart (formerly Bryan Avenue) Substation: Convert Station from 69 kV to 138 kV operation by rebuilding a new substation to replace the existing station | City of Fort Worth, Tarrant County | Rebuild a new substation to replace the four existing transformers and switchgear feeder breakers with two transformers and eight new switchgear type feeder breakers. | 2021-04-12 | 2023-12-15 |  |  | 8238720 |  |  | 72 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | Station grading began prior to reporting on the MCPR. All construction work has ceased and will resume 45 days from the reporting date on June 28.
0PT41229 0PT39325 | Bell Mountain (formerly Hudson Oaks) Substation : Establish substation with one transformer and two feeder breakers | City of Hudson Oaks, Parker County | Establish substation with one transformer and two feeder breakers | 2022-10-17 | 2023-09-29 |  |  | 6859188 |  |  | 92 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41015 (M5222) | Handley Switch: Remove 69 kV station, and add 138 kV terminal by using the existing autotransformer position | City of Fort Worth, Tarrant County | Remove all existing 69 kV equipment from the station and add 138 kV terminal by using the existing autotransformer position. | 2022-10-22 | 2024-05-15 |  |  | 2131413 |  |  | 1 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40561 (R990) | Birthright Switch: Establish 3 breaker ring bus switch and modify relaying at Monticello Switch and Farmersville Switch | Birthright County | Establish 345 kV ring-bus switch in the Farmersville Switch-Monticello Switch 345 kV line and give generator one point-of-interconnection | 2023-01-04 | 2023-05-05 | 2023-05-05 |  | 6648534 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44089 | Beacon Hill Substation : Establish station with one transformer and two feeder breakers | City of Sweetwater, Nolan County | Establish substation with one transformer and two feeder breakers | 2021-07-08 | 2022-06-21 | 2022-06-21 |  | 4266750 |  |  | 100 | na | 138/69 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43961 0PT44072 0PT48344 (R2014) | Pin Oak (formerly known as Big Brown Tap) Switch: Establish 138 kV substation using a 5-breaker 138 kV breaker-and-a-half arrangement | City of Fairfield, Freestone County | Establish 138 kV substation using a 5-breaker 138 kV breaker-and-a-half arrangement as part of rebuilding the Big Brown Tap 138 kV Switch. | 2022-06-09 | 2023-05-31 | 2023-05-31 |  | 9206433 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43957 0PT44928 0PT44608 (R8258) | Midland East Switch: 345 kV substation rebuild | City of Midland, Midland County | Rebuild the Midland East 345 kV Switch as a 7-breaker 345 kV breaker-and-a-half bus arrangement. Install two 3200 A, 138 kV circuit breakers and two new autotransformers as apart of rebuilding the Midland East Switch 345/138 kV Switch. | 2021-09-17 | 2022-12-06 | 2022-12-06 |  | 20264435 |  |  | 100 | na | 345/138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43082 (R8573) | Dermott Switch : Establish a line terminal | City of Snyder, Scurry County | Add one 3200 A, 138 kV circuit breaker to establish a point-of-interconnection. | 2022-01-24 | 2022-11-01 | 2022-11-01 |  | 1325428 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41741 (R3021) | Wallaby Switch : Install three 3200 A ,345 kV circuit breakers in a ring bus configuration | City of Dawn, Deaf Smith County | Establish switching station by installing three 3200 A, 345 kV circuit breakers in a ring bus configuration. | 2023-11-14 | 2024-10-17 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43707 (M4324) | Soap Creek Switch: Establish a new 138 kV, 3 breaker ring bus station for point-of-interconnection | City of Midlothian, Ellis County | Establish substation by installing three 3200 A, 138 kV circuit breakers in a 3-breaker ring bus arrangement for a point-of-interconnection. | 2021-11-15 | 2022-06-01 | 2022-06-01 |  | 4317006 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44263 (M4236) | Royse Switch: 138 kV terminal upgrade | City of Royse City, Rockwall County | Upgrade line equipment as a part of rebuilding the 138 kV line | 2021-11-05 | 2022-05-13 | 2022-05-13 |  | 1148524 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44234 | Taylor West Sub : Install transformer #3 with one transformer and two feeder breakers | City of Hutto, Williamson County | Install transformer #3 with one transformer and two feeder breakers | 2021-09-27 | 2022-06-20 | 2022-06-20 |  | 2381361 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44244 | Inwood Road Sub : Install transformer #3 with one transformer and three switchgear style breakers | City of Dallas, Dallas County | Install transformer #3 with one transformer and three switchgear style breakers | 2022-01-11 | 2022-12-28 | 2022-12-28 |  | 4794016 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44633 0PT44809 0PT47809 (R6170) | Kitsee POI : Establish 138 kV point-of-interconnection | City of Terrell, Kaufman County | Establish a 138 kV point-of-interconnection including the installation of three 138 kV, 2000 A motor operated sectionalizing switches. | 2022-03-17 | 2022-11-01 | 2022-11-01 |  | 658784 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44632 0PT45249 (R6152) | Will White POI : Establish 138 kV point-of-interconnection | City of Tool, Henderson County | Establish a 138 kV point -of-interconnection including the installation of three 138 kV 2000 A motor operated sectionalizing switches. | 2022-02-09 | 2023-06-27 | 2023-06-27 |  | 811168 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44266 (R797) | Killeen Switch : Replace 345/138 kV autotransformer #1 | City of Killeen, Bell County | Replace the existing autotransformer #1 and install two 37.5 MVAR reactor banks on the tertiary of the new autotransformer. Install one 345 kV, 3200 A circuit breaker. | 2022-01-09 | 2022-05-17 | 2022-05-17 |  | 3243212 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43651 (R8558) | Mockingbird Sub: Reconfigure for double tap connection to 138 kV lines. | City of Midland, Midland County | Reconfigure for double tap connection to 138 kV lines | 2022-10-25 | 2022-12-20 | 2022-12-20 |  | 248277 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43642 (R3023) | Blackwater Draw Switch : Add rung with two 345 kV breakers | City of Abernathy, Hale County | Install two 3200 A, 345 kV circuit breakers as part of installing a 345 kV point-of-interconnection. | 2022-01-03 | 2023-12-16 |  |  | 3838169 |  |  | 99 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT39309 | Sycamore Creek Sub : Install transformer #4 with two feeder breakers | City of Benbrook, Tarrant County | Install transformer #4 with two feeder breakers and also add two feeder breakers on transformer #3 | 2021-09-13 | 2023-06-30 | 2023-06-30 |  | 2988557 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44887 0PT50208 0PT39254 | Waco M&M Mars Sub : Install transformer #3 with 2 feeder breakers | City of Waco, McLennan County | Install transformer #3 with two feeder breakers | 2022-04-29 | 2024-05-31 |  |  | 6227656 |  |  | 70 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44317 (R4022) | Pecan Tree Sub: Establish 138 kV substation and install one transformer with three feeder breakers | City of Holliday, Archer County | Establish 138 kV substation and install one transformer with three feeder breakers | 2022-07-15 | 2023-03-01 | 2023-03-01 |  | 5882174 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44296 (M5172) | Azle Sub : Upgrade 138 kV line terminals | City of Fort Worth, Tarrant County | Upgrade 138 kV line terminal and associated equipment | 2023-03-19 | 2023-05-31 | 2023-05-31 |  | 694686 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43989 (R8568) | Centralia: Install 55.2 MVAR 138 kV capacitor bank | Upton County | Install one capacitor bank consisting of three 18.4 MVAR stages of 138 kV voltage and supervisory controlled emergency transmission capacitors. | 2021-12-20 | 2022-05-24 | 2022-05-24 |  | 2141814 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43970 | Loy Lake Sub : Establish station with one transformer, two feeder breakers and three18.4 MVAR 138 kV capacitors | City of Denison, Grayson County | Establish station with one transformer, two feeder breakers and three18.4 MVAR 138 kV capacitors | 2022-02-03 | 2022-12-28 | 2022-12-28 |  | 6731530 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43655 (R8561) | Lamesa Switch: Replace existing 138/69 kV autotransformer #1 | City of Lamesa, Dawson County | Replace existing 138/69 kV autotransformer #1 | 2022-03-31 | 2022-06-20 | 2022-06-20 |  | 867512 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41261 (R6157) | Cow Bayou Switch : Establish a 138 kV POI 4-breaker ring bus switchyard | City of North Prairie, Falls County | Establish a 138 kV POI 4-breaker ring bus switchyard | 2022-03-03 | 2022-12-17 | 2022-12-17 |  | 5992225 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43978 0PT44757 (R8551) | Brown: Install 55.2 MVAR 138 kV capacitors and relay modifications for Buzzard Draw Switch 138 kV line terminal | City of Ackerly, Martin County | Install one capacitor bank consisting of three 18.4 MVAR stages of 138 kV voltage and supervisory controlled emergency transmission capacitors. | 2022-01-01 | 2022-05-12 | 2022-05-12 |  | 2105080 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43591 (M4230) | Venus Switch: Upgrade line terminal and associated equipment on two circuit breakers | City of Venus, Ellis County | Upgrade line terminal and associated equipment on two circuit breakers | 2022-12-04 | 2022-12-22 | 2022-12-22 |  | 458141 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45122 | Calmont Sub : Add transformer #8 with 3 feeders and rework 138 bus, and remove transformer #2 and #3 along with switchgear | City of Fort Worth, Tarrant County | Add transformer #8 with 3 feeders and rework 138 bus, and remove transformer #2 and #3 along with LV switchgear | 2022-06-24 | 2022-12-31 | 2022-12-31 |  | 5218758 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44264 0PT44838 (R6139) | Battleground (formerly known as Coupland) Sub : Establish substation with one transformer and one feeder breaker | Williamson County | Establish a new substation with one transformer and one feeder breaker | 2022-02-10 | 2022-06-29 | 2022-06-29 |  | 4929534 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44243 | Kleberg Sub : Replace transformer #2 and rebuild LV bus with two feeder breakers per transformer | City of Dallas, Dallas County | Replace transformer #2 and rebuild LV bus with two feeder breakers per transformer | 2022-01-10 | 2022-06-01 | 2022-06-01 |  | 2862907 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44230 0PT46714 | Kimball Road Sub : Install bank #3 with one transformer and one feeder breaker | City of Grapevine, Tarrant County | Install bank #3 with one transformer and one feeder breaker | 2022-01-04 | 2022-05-31 | 2022-05-31 |  | 4018618 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44228 | Bird Nest Sub : Install bank #2 with one transformer and two feeder breakers | City of Pflugerville, Travis County | Install bank #2 with one transformer and two feeder breakers | 2022-01-14 | 2022-06-01 | 2022-06-01 |  | 2170661 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42132 (R3022) | Kress Switch : Establish station and install three 345 kV, 3200 A circuit breakers in a ring bus configuration | Swisher County | Establish station and install three 345 kV, 3200 A circuit breakers in a ring bus configuration | 2022-08-14 | 2023-05-31 | 2023-05-31 |  | 7986575 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45124 | Lakecrest Sub : Add station #2 with one transformer and four feeder breakers | City of Grand Prairie, Dallas County | Add station #2 with one transformer and four feeder breakers | 2022-02-12 | 2022-06-30 | 2022-06-30 |  | 2582476 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45742 | Prairie Creek Sub : Replace transformers #1 and #2 | City of Dallas, Dallas County | Replace transformers #1 and #2 and add six circuit breakers | 2022-04-05 | 2022-12-01 | 2022-12-01 |  | 6444164 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43983 0PT44754 0PT47107 (R8562) | Aquifer Tap : Install 110.4 MVAR 138 kV capacitors | Reeves County | Install two capacitor banks each consisting of three 18.4 MVAR stages of 138 kV voltage and supervisory controlled transmission capacitors. | 2022-02-28 | 2022-07-05 | 2022-07-05 |  | 5072146 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43598 (R468) | Marlin South Sub: Install 27.6 MVAR 69 kV capacitor bank | City of Marlin, Falls County | Install a bank consisting of three 9.2 MVAR stages of 69 kV voltage and supervisory controlled transmission capacitors. | 2022-02-07 | 2022-12-27 | 2022-12-27 |  | 1983299 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43028 (M4701) | Cyclone Switch : Establish 3 breaker ring bus station | Hopkins County | Install three 345 kV, 3200 A circuit breakers in a ring bus arrangement to establish station. | 2021-12-17 | 2022-10-18 | 2022-10-18 |  | 9495167 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43026 0PT45543 (R6159) | Outlaw Switch: Establish four breaker ring bus station | City of Richland, Navarro County | Establish four breaker ring bus station. | 2021-12-28 | 2022-06-08 | 2022-06-08 |  | 9503939 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43592 (M4122) | Desoto Switch: Line terminal upgrade for one circuit breaker | City of Dallas, Dallas County | Upgrade terminal equipment on one circuit breaker to 2000A, and upgrade the line relaying communications to fiber. | 2022-10-15 | 2022-12-29 | 2022-12-29 |  | 326944 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42269 (R6160) | Revolution Switch: Rebuild 138 kV station in a 10-breaker 138 kV breaker-and-a-half arrangement | City of Navarro, Navarro County | Rebuild existing Navarro 138 kV station in a 10-breaker 138 kV breaker-and-a-half arrangement. | 2025-01-05 | 2025-04-17 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45741 | Wichita Falls Riverbend Sub : Upgrade both transformers | City of Wichita Falls, Wichita County | Upgrade both transformers | 2022-01-19 | 2022-07-11 | 2022-07-11 |  | 4940165 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44242 0PT44554 (R6144) | Sabana Sub : Establish station with one transformer and two feeder breakers | City of Proctor, Comanche County | Establish station with one transformer and two feeder breakers. | 2022-01-27 | 2022-12-19 | 2022-12-19 |  | 4557630 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45121 | Wall Street Sub : Replace station #2 transformer and replace existing oil low voltage circuit breakers | City of Dallas, Dallas County | Replace station #2 transformer and replace existing oil low voltage circuit breakers. | 2022-01-05 | 2022-06-30 | 2022-06-30 |  | 4968473 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42594 | Caddo Mills Hwy 66 Sub - Establish a new 138-25 kV substation with two transformers | City of Caddo Mills, Hunt County | Establish substation with two transformers to replace Caddo Mills Sub. | 2022-04-08 | 2023-05-26 | 2023-05-26 |  | 6922256 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44260 | Rowlett Sub: Upgrade line equipment | City of Rowlett, Rockwall County | Upgrade line equipment. | 2023-03-16 | 2023-05-24 | 2023-05-24 |  | 1854298 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45227 (R6160) | Navarro Sub : Reconfigure 138 kV bus & relocate line terminals to Revolution Switch | City of Navarro, Navarro County | Reconfigure 138 kV bus & relocate line terminals to Revolution Switch. | 2025-03-10 | 2025-04-17 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44254 | Dalrock Sub: Upgrade line equipment | City of Rowlett, Rockwall County | Upgrade line equipment. | 2022-07-29 | 2022-12-21 | 2022-12-21 |  | 889654 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44337 0PT46862 | Frow Sub: Establish substation with one transformer and two feeder breakers | City of Waco, McLennan County | Establish station with one transformer and two feeders | 2023-06-01 | 2023-12-15 |  |  | 2992104 |  |  | 76 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45025 | Odessa EHV Switch : Relay upgrades for 138 kV and auto# 2 | City of Odessa, Ector County | Upgrade relaying for 138 kV, 345/138 kV and auto # 2 | 2022-03-07 | 2022-07-26 | 2022-07-26 |  | 732642 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43824 (R6142) | Creslenn Ranch: Rebuild 69 kV station to a four position ring bus | City of Trinidad, Henderson County | Establish a new 69 kV four position ring bus to replace the existing 69 kV at Trinidad Switch. | 2022-05-20 | 2022-12-22 | 2022-12-22 |  | 4354061 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44226 | White Settlement West Sub : Install a 138-25 kV transformer #2 with one feeder breaker | City of Fort Worth, Tarrant County | Install 138-25 kV transformer #2 with one feeder breaker | 2022-08-05 | 2022-12-16 | 2022-12-16 |  | 2316447 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44246 | Temple Northwest Sub : Replace two 138-12.5 kV transformers | City of Temple, Bell County | Replace two 138-12.5 kV transformers | 2022-06-06 | 2022-12-20 | 2022-12-20 |  | 5313490 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Start date updated to reflect initial construction date.
0PT44258 | Temple Southeast Sub : Replace 138-12.5 kV transformer #1 and replace station #1 circuit breakers | City of Temple, Bell County | Replace 138-12.5kV transformer #1 and replace station #1 circuit breakers | 2022-09-02 | 2022-12-06 | 2022-12-06 |  | 1663935 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44850 (R51561) | Thomas Price Switch: Establish new station by installing three 345 kV, 5000 A circuit breakers in a 3-breaker ring bus arrangement. | City of Graham, Young County | Establish new station by installing three 345 kV, 5000 A circuit breakers in a 3-breaker ring bus arrangement. | 2022-05-09 | 2022-12-01 | 2022-12-01 |  | 7861206 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45886 | Judkins Sub : Replace transformers #1 and #2 with two transformers | Ector County | Replace transformers #1 and #2 with two transformers | 2022-01-11 | 2022-12-09 | 2022-12-09 |  | 5543166 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46052 0PT46421 (R8602) | High Plains POD: Establish a 138 kV point of delivery (POD) | City of Big Spring, Howard County | Establish a 138 kV point of delivery (POD) | 2022-09-26 | 2022-12-21 | 2022-12-21 |  | 897944 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46409 0PT50103 | Parker Switch : Replace two overdutied breakers | City of Weatherford, Parker County | Replace two breakers | 2022-10-21 | 2023-08-15 |  |  | 1171492 |  |  | 99 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46384 | Carrollton Northwest Switch : Replace three overdutied breakers | City of Carrollton, Denton County | Replace three breakers | 2022-09-19 | 2022-12-06 | 2022-12-06 |  | 1568439 |  |  | 100 | 138 |  | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46386 | Kirkland Park Switch : Replace two overdutied breakers | City of Dallas, Dallas County | Kirkland Park Switch : Replace two breakers | 2022-10-03 | 2022-11-01 | 2022-11-01 |  | 696589 |  |  | 100 | 138 |  | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46134 (R6187) | Tin Roof POD: Establish 138 kV point of delivery with capacitor bank | Bell County | Establish point of delivery with installation of three stages of 36.8 MVAR 138 kV capacitor banks. | 2022-02-18 | 2022-08-15 | 2022-08-15 |  | 3570723 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44295 (M5172) | Weatherford Switch : Upgrade 138 kV line terminal | City of Weatherford, Parker County | Upgrade all line terminal and associated equipment for the 138 kV circuit breaker. | 2022-11-29 | 2022-12-27 | 2022-12-27 |  | 384571 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45737 0PT46724 (R8604) | Crater Rock Switch : Establish three breaker ring POI station | Culberson County | Establish three breaker ring POI station. | 2022-08-07 | 2023-12-15 |  |  | 6077188 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
13T65029 | Lawrence Sub : Establish with one transformer and two 25 kV feeder breakers | Kaufman County | Establish with one transformer and two feeder breakers . | 2022-07-15 | 2022-12-16 | 2022-12-16 |  | 4603754 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43825 (R6143) | Taylor Sub: Establish 138 kV ring bus and upgrade distribution station | City of Taylor, Williamson County | Establish a new four position 138 kV ring bus to replace the existing 138 kV switching station, including the installation of one 138/69 kV autotransformer. | 2022-06-14 | 2022-12-22 | 2022-12-22 |  | 6694493 |  |  | 100 | 138 | 138/69 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45123 0PT43070 | Rosemont Sub : Establish station with a double tap arrangement with two transformers and eight circuit breakers. | City of Fort Worth, Tarrant County | Establish station with a double tap arrangement with two transformers and eight circuit breakers. | 2022-09-05 | 2023-09-22 |  |  | 8568084 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46414 0PT50443 | Rosedale Sub : Establish substation with two transformers | City of Fort Worth, Tarrant County | Establish substation with two transformers and six feeder breakers | 2022-12-29 | 2023-12-31 |  |  | 6478207 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46725 (M5222) | Handley Switch : Remove transformers #1 and #2 with the removal of the associated switchgear | City of Fort Worth, Tarrant County | Remove transformers #1 and #2 with the removal of the associated switchgear. | 2023-11-01 | 2023-12-15 |  |  | 2105456 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41468 (R6195) | Fort Smith Switch : Establish 345 kV ring bus station for point-of-interconnection (POI). | City of Hillsboro, Hill County | Establish new station by installing three 345 kV, 3200 A circuit breakers in a 3-breaker ring bus arrangement for a point-of interconnection (POI). | 2022-06-28 | 2022-11-11 | 2022-11-11 |  | 7159942 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40880 0PT47840 (R6184) | Russell Gap Switch : Establish 3-breaker ring bus for POI | City of Star, Mills County | Establish 345 kV 3-breaker ring bus for point-of-interconnection. | 2022-07-18 | 2022-12-22 | 2022-12-22 |  | 8089374 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40139 (R6183) | Ash Creek Switch : Establish 138 kV station for POI | Hill County | Establish 138 kV station for Point-of-Interconnection (POI), by installing three 138 kV, 3200 A circuit breakers in a 3-breaker ring bus arrangement | 2022-08-23 | 2023-05-01 | 2023-05-01 |  | 4320758 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46093 | Graford Sub : Rebuild existing substation to rural substation skid | City of Graford, Palo Pinto County | Rebuild existing substation to rural substation skid | 2023-03-20 | 2024-05-15 |  |  | 2989585 |  |  | 99 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42249 (M4346) | Hawk Hollow Switch : Establish 5-breaker ring POI station | City of Paris, Lamar County | Install five 138 kV, 3200 A circuit breakers in a ring bus arrangement and install one 138 kV point-of-interconnection (POI). | 2022-06-22 | 2022-12-14 | 2022-12-14 |  | 6613388 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46156 (R6116) | Sandow Switch: Install 138 kV air core reactors on auto #1 and auto #2 | City of Rockdale, Milam County | Install 138 kV air core reactors on auto #1 and auto #2 | 2022-08-17 | 2023-04-01 | 2023-04-01 |  | 2964529 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43690 0PT47058 (M3009) | Crossroads Switch : Establish station for POI | City of Enloe, Delta County | Establish a POI switching station by installing three 138 kV, 3200 A circuit breakers in a ring bus arrangement to provide a single POI. | 2022-06-28 | 2022-12-21 | 2022-12-21 |  | 4377683 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46716 | Moorehead Sub : Install two transformers with two feeder breakers | City of Garland, Dallas County | Install two transformers with two feeder breakers | 2022-05-09 | 2022-12-20 | 2022-12-20 |  | 5136068 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44322 (M4320) | Bardwell Lake Switch: Disconnect two 69 kV line terminals & upgrade line terminals | Ellis County | Disconnect two 69 kV line terminals & upgrade line terminals. | 2022-11-18 | 2022-12-09 | 2022-12-09 |  | 274037 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46771 0PT47830 0PT47832 0PT45669 (R8498) | Consavvy Switch: Establish as a 10-breaker and a half bus arrangement. | Midland County | Establish as a 10-breaker and a half bus arrangement. Install two autotransformers and four MVAR reactors | 2022-04-20 | 2023-02-14 | 2023-02-14 |  | 42462890 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42929 | Compton Street Sub : Replace transformers #1 & #2 | City of Dallas, Dallas County | Rebuild substation with two transformers and eight feeder breakers and remove existing switchgear station. | 2022-06-06 | 2022-12-27 | 2022-12-27 |  | 6133672 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43226 0PT44828 (R4015) | Tower One Sub: Establish substation | City of Bowie, Montague County | Establish substation using two 69 kV, 2000 A circuit breakers and three sectionalizing switches. | 2022-07-15 | 2023-04-12 | 2023-04-12 |  | 4880808 |  |  | 100 | na | 69 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43646 (M4292) | Royse Switch: Upgrade one circuit breaker line terminal upgrade | City of Royse City, Rockwall County | Upgrade one circuit breaker line terminal | 2022-09-23 | 2022-12-27 | 2022-12-27 |  | 700683 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44233 | Bangs Sub : Rebuild station by installing transformer #2 and two feeder breakers and decommission transformer #1 | City of Bangs, Brown County | Rebuild station by installing transformer #2 and two feeder breakers and decommission transformer #1 | 2022-07-21 | 2023-03-02 | 2023-03-02 |  | 3676844 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44267 (R6140) | Rockdale Sub : Install transformer #2 with two feeders | City of Rockdale, Milam County | Install a second transformer with two feeders and add FID to the existing substation. | 2022-07-27 | 2022-12-29 | 2022-12-29 |  | 2743160 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45445 (M4702) | Saltillo Switch : Establish a 3-breaker ring bus for POI station | City of Saltillo, Hopkins County | Establish a 3-breaker ring bus for POI station | 2022-05-12 | 2022-12-28 | 2022-12-28 |  | 6954657 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46419 | Centralia Sub : Install transformer #4 with two feeder breakers | Upton County | Install transformer #4 with two feeder breakers | 2022-09-20 | 2022-12-19 | 2022-12-19 |  | 2780019 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46638 | Mount Enterprise Switch : Replace two 345 kV circuit breakers | City of Henderson, Rusk County | Replace two 345 kV circuit breakers | 2022-10-18 | 2022-12-27 | 2022-12-27 |  | 1135637 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46640 | East Levee Switch : Replace one 138 kV circuit breaker | City of Dallas, Dallas County | Replace one 138 kV circuit breaker | 2022-10-05 | 2022-11-01 | 2022-11-01 |  | 449976 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46729 | Hemphill Sub : Replace one 138 kV circuit breaker | City of Fort Worth, Tarrant County | Replace one 138 kV circuit breaker | 2022-10-18 | 2022-12-01 | 2022-12-01 |  | 383934 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45361 (R6185) | Long Prairie Switch : Establish 3-breaker ring bus for POI station | Navarro County | Establish 3-breaker ring bus for POI station | 2022-05-03 | 2022-12-28 | 2022-12-28 |  | 5376538 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44313 0PT44748 (R4022) | Short Grass Sub: Establish new substation | City of Archer, Archer County | Establish a new substation to replace the existing Archer City Sub. | 2022-08-01 | 2022-12-22 | 2022-12-22 |  | 3647282 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43089 0PT44822 (R4015) | Hopewell Switch: Establish 4-breaker 69 kV ring bus station | City of Bowie, Montague County | Establish with a 4-breaker ring bus using 69 kV, 2000A breakers. | 2022-06-06 | 2022-12-21 | 2022-12-21 |  | 5142682 |  |  | 100 | na | 69 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46333 0PT47029 (M3010) | Rose Hill Switch : Rebuild Rose Hill Sub Tap to 3-breaker ring | City of Kaufman, Kaufman County | Rebuild the existing 138 kV Rose Hill Tap into a three position 138 kV ring bus configuration. | 2022-07-05 | 2022-12-22 | 2022-12-22 |  | 4855264 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46413 | Mountain Branch Sub : Establish new sub with one transformer and three 12.5 kV feeders | Eastland County | Establish new sub with one transformer and three 12.5 kV feeders. | 2022-06-06 | 2023-06-30 | 2023-06-30 |  | 5755341 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46508 | Dollarhide Sub : Upgrade relaying on capacitor bank #1 | City of Kermit, Winkler County | Upgrade relaying on capacitor bank #1. | 2022-09-26 | 2022-12-27 | 2022-12-27 |  | 683101 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46587 | Mustang Sub : Install one transformer with two feeder breakers on bank #2 | City of Andrews, Andrews County | Install one transformer with two feeder breakers on bank #2. | 2022-06-26 | 2022-12-30 | 2022-12-30 |  | 4065847 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44257 | Cleburne West Sub : Install bank #2 with one transformer and two feeder breakers | City of Cleburne, Johnson County | Install bank #2 with one transformer and two feeder breakers. | 2022-08-08 | 2022-12-14 | 2022-12-14 |  | 2080917 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46207 | Copperas Cove East Switch : Install bank #2 with a one transformer | City of Copperas Cove, Coryell County | Install bank #2 with a one transformer. | 2022-07-29 | 2022-12-15 | 2022-12-15 |  | 2883866 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44343 (M4071) | Cedar Crest Sub : Convert substation to 138 kV operation and rebuild 13.8 kV substation | City of Dallas, Dallas County | Convert the 69 kV substation to 138 kV operation by installing a new loop in - loop out configuration and removing the 69 kV equipment. | 2022-07-15 | 2023-05-18 | 2023-05-18 |  | 5122938 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46619 | Tule Canyon Switch : Install three 345 kV SSVTs | City of Silverton, Briscoe County | Install three 345 kV SSVTs that were removed from Abernathy Switch. | 2022-09-13 | 2022-12-20 | 2022-12-20 |  | 288582 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46875 0PT47739 (R8611) | Yantis Ranch POD : Establish 138 kV point of delivery | City of Wink, Winkler County | Establish 138 kV point of delivery. | 2022-11-14 | 2023-06-28 | 2023-06-28 |  | 1911568 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44304 (R6141) | Peppervine Switch: 138 kV Station Rebuild | City of Waco, McLennan County | Rebuild the 138 kV Switch with ten 3200 A or greater, 138 kV circuit breakers in a breaker-and-a-half arrangement. | 2022-08-12 | 2023-10-15 |  |  | 11566138 |  |  | 92 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47344 (M4330) | Haggerty Switch : Establish breaker-and-a-half station | City of Sherman, Grayson County | Establish breaker-and-a-half station. | 2022-10-29 | 2023-04-25 | 2023-04-25 |  | 17642817 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44232 0PT44749 0PT47519 | Apple Sub (formerly Pleasant Farms Sub) : Establish station with one 47 MVA, 138/69 kV and two feeder breakers | City of Odessa, Ector County | Establish station with one transformer and two feeder breakers. | 2022-07-11 | 2022-12-14 | 2022-12-14 |  | 5171022 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46695 0PT47758 0PT47760 (R6215) | Mallard Switch : Establish breaker-and-a-half station | City of Hutto, Williamson County | Establish Breaker-and-a-half Station for SAS. | 2022-08-19 | 2023-05-03 | 2023-05-03 |  | 16173528 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47343 0PT47759 (R6216) | Pintail Switch : Establish Breaker-and-a-half Station for SAS | City of Hutto, Williamson County | Establish breaker-and-a-half station. | 2022-09-09 | 2023-05-08 | 2023-05-08 |  | 13890108 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46874 (R8609) | Meyers Draw POD : Establish 138 kV point of delivery | City of Odessa, Midland County | Establish 138 kV point of delivery | 2023-08-03 | 2023-11-15 |  |  | 1120615 |  |  | 81 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44416 (M5216) | Hurst Sub: 138 kV line terminal upgrade | City of Hurst, Tarrant County | Upgrade all line terminal and associated equipment to meet or exceed 2000 A. | 2022-11-07 | 2023-04-25 | 2023-04-25 |  | 486819 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44414 (M5216) | Euless South Sub: 138 kV line terminal upgrade | City of Euless, Tarrant County | Upgrade all line terminal and associated equipment to meet or exceed 2000 A. | 2022-10-07 | 2022-12-09 | 2022-12-09 |  | 485178 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45131 | Grand Prairie Sub : Rebuild substation | City of Grand Prairie, Dallas County | Rebuild substation with eight distribution feeders, new transformers and modify 138 kV bus work to configure a loop in loop out arrangement. | 2022-09-19 | 2023-05-01 | 2023-05-01 |  | 7673504 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44229 | Trinity Sub : Install second transformer with two feeder breakers | City of Fort Worth, Tarrant County | Install second transformer with two feeder breakers | 2022-10-12 | 2022-12-30 | 2022-12-30 |  | 2978368 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43163 (R4015) | Smith Creek (Formerly Bellevue Sub): Rebuild 69 kV station with a rural design | City of Bellevue, Clay County | Rebuild 69 kV station with a rural design | 2022-08-08 | 2022-12-20 | 2022-12-20 |  | 2200977 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42928 0PT44208 0PT49193 | Antler Hollow Sub : Establish with two transformers and three feeder breakers | City of Stephenville, Erath County | Establish with two transformers and three feeder breakers | 2022-08-29 | 2023-04-01 | 2023-04-01 |  | 7687918 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46970 | Taylor West Sub : Install bank #4 with one transformer and two feeder breakers | City of Hutto, Williamson County | Install bank #4 with one transformer and two feeder breakers | 2022-08-18 | 2022-12-30 | 2022-12-30 |  | 3023259 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46844 (R8610) | Schumm POD : Establish 138 kV point of delivery | City of Monahans, Crane County | Establish 138 kV point of delivery | 2022-11-20 | 2023-01-05 | 2023-01-05 |  | 1091580 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46726 | Salt Lake Substation : Install bank #2 with one transformer and two feeder breakers | City of Midland, Midland County | Install bank #2 with one transformer and two feeder breakers and decommission transformer #1. | 2022-09-01 | 2023-07-01 | 2023-07-01 |  | 2876816 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45394 | Midlothian South Sub : Replace transformers #1 and #2 | City of Midlothian, Ellis County | Replace transformers #1 and #2 and relay upgrades on two feeder breakers | 2022-09-11 | 2022-12-30 | 2022-12-30 |  | 7048748 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44870 (R8581) | Wink Switch : Convert line terminal with 138 kV circuit breakers | City of Wink, Winkler County | Convert line terminal with 138 kV circuit breakers | 2022-11-10 | 2023-10-31 |  |  | 1335615 |  |  | 80 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44341 (M4064) | Buntin Drive Sub : Convert station to 138 kV operation | City of Dallas, Dallas County | Convert station to 138 kV operation by replacing transformer and install eight feeder switchgears. | 2022-09-13 | 2023-05-26 | 2023-05-26 |  | 7608844 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46628 0PT47096 (R985) | Caddo Mills Explorer Tap : Rebuild tap to support line conversion upgrade | City of Caddo Mills, Hunt County | Rebuild tap to support line conversion upgrade and utilize motor operated switches. | 2022-11-01 | 2022-12-29 | 2022-12-29 |  | 878313 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47533 0PT48287 (R8612) | Dry Wind Tap : Establish new tap to Sandhills Substation | City of Monahans, Crane County | Establish new tap to Sandhills Substation. | 2022-11-21 | 2023-05-05 | 2023-05-05 |  | 867633 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47567 (R4028) | Baylor Switch : Add motor operator and transclosure for line switch | City of Seymour, Baylor County | Add a motor operator and transclosure to facilitate line upgrades. | 2022-07-12 | 2023-03-01 | 2023-03-01 |  | 521974 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41807 0PT48762 (R8619) | Meteor Switch: Establish 345 kV ring bus station for point of interconnection (POI). | City of Odessa, Ector County | Establish a 3-breaker, 345 kV, 5000 A ring bus station for point of interconnection (POI). | 2024-01-01 | 2024-12-12 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45683 (M5324) | Bird Dog Switch: Establish a 345 kV for point of interconnection (POI) | City of Denton, Denton County | Establish a 345 kV, 3-breaker ring bus switchyard for point of interconnection (POI). | 2023-02-24 | 2023-05-15 | 2023-05-15 |  | 7865658 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46327 0PT49964 (R6190) | Pepper Creek Switch : Establish for point of delivery POD | City of Temple, Bell County | Establish with thirteen 138 kV circuit breakers to provide three point of delivery's to adjacent customer station. | 2024-01-02 | 2024-11-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46153 (R8027) | Ozark Trail Switch : Establish 3-breaker ring bus station for point of interconnection (POI) | City of Tulia, Swisher County | Establish 3-breaker ring bus station for point of interconnection (POI) | 2023-10-03 | 2024-05-15 |  |  | 8175933.92 |  |  | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41699 (R1752) | Marlin Switch : Rebuild station by installing three 2000 A or greater 69 kV circuit breakers | City of Marlin, Falls County | Rebuild station by installing three 2000 A or greater 69 kV circuit breakers. | 2025-01-02 | 2025-05-15 | [5 empty] | 0 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46641 | Allen Switch : Replace two 138 kV circuit breakers | City of Plano, Collin County | Replace two 138 kV circuit breakers | 2022-11-01 | 2022-12-28 | 2022-12-28 |  | 567961 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46892 0PT47001 | Sandhills Sub : Replace transformer #1 and two feeder breakers | Crane County | Replace bank #1 and two feeder breakers. | 2022-07-16 | 2022-12-29 | 2022-12-29 |  | 5919552 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47736 | Sandhills Sub : Install transformer #3 with one feeder breaker | Crane County | Install transformer #3 with one feeder breaker | 2022-08-15 | 2023-05-19 | 2023-05-19 |  | 3892590 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46507 | Twin Oaks Switch: Upgrade relaying on 345 kV North and South bus | Robertson County | Upgrade 345 kV North and South bus protection to provide redundancy for three phase faults. | 2022-09-22 | 2023-04-04 | 2023-04-04 |  | 538402 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46639 | Century Switch : Replace one 345 kV circuit breaker | City of Arlington, Tarrant County | Replace one 345 kV circuit breaker | 2022-10-25 | 2022-12-06 | 2022-12-06 |  | 559878 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46883 | Deen Switch : Install security measures | City of Fort Worth, Tarrant County | Install security measures | 2022-08-01 | 2022-12-15 | 2022-12-15 |  | 1444435 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47494 0PT49132 (R8622) | Ashby POD : Establish a 138 kV point of delivery (POD). | City of Wink, Winkler County | Establish a 138 kV for point of delivery (POD). | 2022-11-18 | 2023-06-01 | 2023-06-01 |  | 2075348 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41706 (R8607) | Red Sand POD : Establish 138 kV point of delivery (POD) | City of Stanton, Martin County | Establish 138 kV point of delivery (POD). | 2022-10-21 | 2023-07-19 | 2023-07-19 |  | 1133424 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44139 0PT51654 (M5323) | Pacific Switch : Establish 3-breaker ring bus for POI | City of Brookston, Lamar County | Establish 345 kV, 3 breaker ring bus for point of interconnection. | 2023-06-28 | 2023-11-16 |  |  | 6924290.09 |  |  | 34 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46606 (R8621) | Delaware River Switch : Establish 3-breaker ring bus for point of interconnection (POI) | Culberson County | Establish 138 kV, 3-breaker ring bus for point of interconnection (POI). | 2023-08-30 | 2024-04-16 |  |  | 8155593 |  |  | 2 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46971 | Parker Maxwell Creek Sub : Install transformer #2 with two feeder breakers | City of Parker, Collin County | Install transformer #2 with two feeder breakers | 2022-08-19 | 2022-12-29 | 2022-12-29 |  | 2618162 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48057 | Burnett Switch : Oil Containment | City of Wichita Falls, Wichita County | Install station oil containment | 2022-11-21 | 2022-12-28 | 2022-12-28 |  | 481070 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44324 (M4320) | Italy Sub: 69 kV line terminal upgrade | City of Italy, Ellis County | 69 kV line terminal upgrade. | 2022-10-11 | 2022-12-12 | 2022-12-12 |  | 1296090 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44273 | Terrell Switch: Establish 138 kV terminal and retire 69 kV station | City of Terrell, Kaufman County | Establish 138 kV line terminal and retire 69 kV station | 2023-03-13 | 2023-12-15 |  |  | 6274501 |  |  | 34 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47406 | Temple Pecan Creek Switch : Replace MDAR relay panels for four circuit breakers | City of Temple, Bell County | Replace MDAR relay panels for four circuit breakers | 2022-10-10 | 2022-12-19 | 2022-12-19 |  | 599952 |  |  | 100 | 138 | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47010 | Rocky Creek Switch : Install HV Breaker and Transformer monitors and associated communications equipment | City of Crowley, Tarrant County | Install HV Breaker and Transformer monitors and associated communications equipment at Rocky Creek Switch. | 2022-09-24 | 2023-03-07 | 2023-03-07 |  | 600000 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46988 (R8616) | Buchanan Ranch Sub : Add two transformers with four feeder breakers and replace existing transformer | City of Midland, Midland County | Add two transformers with four feeder breakers and replace existing transformer | 2023-02-13 | 2023-10-01 |  |  | 8788730 |  |  | 94 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45165 (M3015) | Krum West Switch : Establish a 345 kV point of interconnection (POI) | City of Krum, Denton County | Modify to provide one 345 kV point of interconnection. | 2023-03-11 | 2023-12-15 |  |  | 2035427 |  |  | 93 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46491 | Wilmer Switch : Upgrade relaying on auto #1 | City of Wilmer, Dallas County | Upgrade auto #1 panels and add 3V0 equipment | 2022-11-08 | 2023-02-01 | 2023-02-01 |  | 370478 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47709 (M5326) | Lavender Switch : Establish a new 138 kV, 4 breaker ring bus station for point of interconnection (POI). | City of Wilmer, Dallas County | Establish the 138 kV switch in a 4-breaker-ring bus arrangement by installing four 138 kV, 3200 A circuit breakers to provide two 138 kV points of delivery (PODs). | 2023-01-27 | 2023-06-01 | 2023-06-01 |  | 6480932 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47987 | Roanoke Sub: Install transformer #4 and two feeder breakers | City of Roanoke, Denton County | Install transformer #4 and two feeder breakers | 2022-10-20 | 2023-05-12 | 2023-05-12 |  | 3253326 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46894 0PT47833 0PT47813 0PT46566 (R8593) | Expanse Switch: Establish 345/138 kV station | City of Stanton, Martin County | Establish as a 6-breaker, 138 kV breaker-and-a-half bus arrangement with 3200 A terminals, and a 3-breaker 345 kV single breaker arrangement. Install two autotransformers and four MVAR reactors. | 2022-10-07 | 2023-12-25 |  |  | 31195698 |  |  | 98 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46199 | Stephen F. Austin Sub : Relocate substation demarcation | City of Nacogdoches, Nacogdoches County | Relocate substation demarcation | 2024-05-15 | 2024-10-01 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48180 (M5329 ) | Elizabethtown : Establish 138 kV point of interconnection (POI). | City of Roanoke, Denton County | Establish 138 kV point of interconnection (POI). | 2023-12-29 | 2024-03-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46620 | DFW Northwest Sub : Reconfigure 138 kV lines and bus configuration. | City of Grapevine, Tarrant County | Add two138 kV breakers to the tie bus connecting these lines. | 2022-10-27 | 2023-05-12 | 2023-05-12 |  | 3284670 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46909 (R8614) | Rock Lake POD: Establish 138 kV point of delivery | City of Stanton, Martin County | Establish a 138 kV for point of interconnection (POI) | 2024-02-12 | 2024-04-01 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44245 0PT44780 | Horseman Sub (formerly Saginaw SE Sub) : Establish 138 kV station with two transformers and four breakers | City of Fort Worth, Tarrant County | Establish 138 kV station with two transformers and four breakers | 2022-12-07 | 2023-06-28 | 2023-06-28 |  | 9046995 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45387 (R6208) | Bell County East Switch : Establish a 345 kV POI for point of interconnection | City of Temple, Bell County | Establish a 345 kV point of interconnection (POI) | 2022-10-13 | 2023-05-18 | 2023-05-18 |  | 5206702 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46340 (R6219) | Rookie Switch : Establish 138 kV station for point of interconnection | City of Thorndale, Milam County | Establish new station by installing three 138 kV, 3200 A circuit breakers in a 3-breaker ring bus arrangement. | 2024-01-02 | 2024-05-08 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46171 (R6207)) | Riesel Switch : Establish 138 kV point of interconnection | City of Riesel, Falls County | Establish new station by installing three 138 kV, 3200 A circuit breakers in a 3-breaker ring bus arrangement. | 2022-11-01 | 2023-05-11 | 2023-05-11 |  | 4998964 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45041 0PT49586 (R6210) | Hog Creek Switch: Establish 345 kV point of interconnection | City of Cameron, Milam County | Establish a 345 kV point of interconnection (POI) | 2023-01-07 | 2023-05-12 | 2023-05-12 |  | 8486799 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47360 | Coyote Sub: Install station #2 | City of Big Spring, Howard County | Install station #2 in a loop-in, loop-out arrangement with one transformer and two feeder breakers. | 2023-01-25 | 2023-10-15 |  |  | 5525519 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45040 (R6217) | Brangus Switch: Establish 345 kV point of interconnection | Bell County | Establish a 345 kV point of interconnection (POI) | 2022-11-03 | 2023-05-12 | 2023-05-12 |  | 7734602 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45039 (R6218) | Gibson Switch: Establish 345 kV point of interconnection | Milam County | Establish a 345 kV point of interconnection (POI) | 2023-02-13 | 2023-12-14 |  |  | 7823643 |  |  | 96 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45035 (R6188) | Little Pond Switch: Establish 345 kV point of interconnection | Milam County | Establish a 345 kV point of interconnection (POI) | 2023-04-11 | 2023-12-14 |  |  | 7764705 |  |  | 97 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46828 (R8606) | Grey Well Draw Switch: Rebuild 3-breaker ring bus | City of Midland, Midland County | Establish 138 kV three breaker ring bus station. | 2022-11-11 | 2023-05-19 | 2023-05-19 |  | 6108950 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45535 0PT48288 (R6213) | Belfalls Switch - Establish a 345 kV point of interconnection | City of Troy, Bell County | Establish a 345 kV, 3-breaker ring bus switchyard for point of interconnection (POI). | 2023-04-12 | 2023-11-16 |  |  | 7911903 |  |  | 98 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48011 (M4352) | Greenville Ave Sub : Rebuild station to install new 138 kV bus and two transformers #3 & #4 | City of Dallas, Dallas County | Rebuild station to install new 138 kV bus and two transformers #3 & #4. | 2023-03-03 | 2023-12-22 |  |  | 8850144 |  |  | 91 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43530 | Eiland Switch : Relay protection upgrade | City of Big Spring, Howard County | Relay protection upgrade | 2024-05-01 | 2024-05-15 |  |  | 336780 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46509 | Elm Mott Switch : Upgrade relaying for capacitor bank #1 | City of Elm Mott, McLennan County | Upgrade relaying for capacitor bank #1 | 2023-01-16 | 2024-04-01 |  |  | 341627 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47310 | Rhome Sub: Replace 138 kV transformer | City of Rhome, Wise County | Replace 138 kV transformer and 138 kV motor operated switches | 2023-02-15 | 2023-05-26 | 2023-05-26 |  | 3342223 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46242 | Dry Fork Sub : Establish substation with two transformers and three feeder breakers | City of Wichita Falls, Wichita County | Establish substation with two transformers and three feeder breakers | 2023-08-17 | 2024-05-15 |  |  | 7438715 |  |  | 8 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46981 0PT47071 | Navigation Sub : Establish substation with one transformer and two feeder breakers | City of Big Spring, Howard County | Establish substation with one transformer and two feeder breakers | 2022-09-26 | 2023-04-03 | 2023-04-03 |  | 5480525 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48479 | Aroya Switch : Replace six overdutied breakers | City of Monahans, Ward County | Replace six overdutied breakers. | 2023-04-07 | 2023-12-15 |  |  | 2279147 |  |  | 52 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48351 (R8625) | Stephenson Lake POD : Establish 138 kV point of delivery (POD) | City of Midland, Midland County | Establish 138 kV point of delivery (POD). | 2023-04-05 | 2023-05-15 | 2023-05-15 |  | 956969 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48090 (R8621) | Chimney Well POD : Remove equipment for replacement by new Delaware River Switch point of Delivery (POD) | Culberson County | Remove existing line connections and associated equipment for point of delivery (POD). | 2024-02-28 | 2024-04-16 |  |  | 291043 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47886 (M4335) | Pebble Creek Switch : Install two 138 kV line terminals for point of delivery (POD) | City of Red Oak, Ellis County | Provide two 138 kV point of delivery (POD) line terminals by installing four 138 kV circuit breakers. | 2023-06-02 | 2024-03-01 |  |  | 4404845.61 |  |  | 96 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47579 0PT47812 0PT47816 (M4327) | Loop Nine Switch : Establish two 345 kV autos. | City of Red Oak, Ellis County | Establish switch with a 345 kV six breaker ring bus with two autotransformers, and six 138 kV breakers in a breaker-and-a-half configuration. | 2023-08-21 | 2023-12-15 |  |  | 38570962 |  |  | 9 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47295 | Beals Creek Sub: Install transformer #3 and three feeder breakers | City of Big Spring, Howard County | Install transformer and three feeder breakers. | 2022-11-12 | 2023-06-29 | 2023-06-29 |  | 2988118 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46402 0PT45497 (R6136) | Ranchland Switch: Establish 138 kV ring bus | City of Fairfield, Freestone County | Establish 138 kV ring bus with three feeder breakers. | 2022-11-14 | 2023-05-22 | 2023-05-22 |  | 5835865 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47363 0PT46957 | Plano Sub: Rebuild station | City of Plano, Collin County | Rebuild transformers and eight new switchgear type feeder breakers. | 2023-07-10 | 2023-12-15 |  |  | 10581061 |  |  | 35 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46403 (R6136) | Fairfield West Sub: Reconfigure high side | City of Fairfield, Freestone County | Reconfigure the high side of the substation. | 2022-12-15 | 2023-05-05 | 2023-05-05 |  | 1458170 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47761 (M4327) | Pebble Creek Switch: Install breakers on rung to establish line terminals | City of Red Oak, Ellis County | Install two 138 kV breakers on rungs 5 and 6 to establish the line terminals | 2023-03-13 | 2023-12-15 |  |  | 4461165 |  |  | 90 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47526 | Oran Sub : Rebuild existing substation with rural substation skid | City of Graford, Palo Pinto County | Rebuild existing substation with rural substation skid | 2025-01-01 | 2025-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46328 (M4205) | Carrollton Northwest Switch : Terminate Carrollton East and Northlake Switch | City of Carrollton, Dallas County | Terminate existing Carrollton East Switch | 2023-09-26 | 2023-12-15 |  |  | 1902158.1 |  |  | 32 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46493 | Anna Switch: Upgrade relaying on auto #2 | City of Anna, Collin County | Upgrade 345 kV auto #2 protection to provide redundancy for three phase faults. Install one 345 kV circuit breaker on auto #2 | 2023-09-16 | 2023-12-15 |  |  | 1953723 |  |  | 38 | 138 | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47618 (M4701) | Cedar Hill Switch : Replace 138 kV overdutied breaker | City of Cedar Hill, Dallas County | Replace overdutied 345 kV circuit breakers as part of providing one 345 kV point of interconnection (POI) | 2023-01-17 | 2023-04-06 | 2023-04-06 |  | 934417 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46857 (M4094) | Liggett Switch: Upgrade 138 kV circuit breaker | City of Irving, Dallas County | Upgrade circuit breakers to meet or exceed 3200 A. | 2023-03-17 | 2023-05-30 | 2023-05-30 |  | 970614 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46514 | Temple Switch : Upgrade relaying on capacitor bank #1 | City of Temple, Bell County | Upgrade relaying on capacitor bank #1 | 2024-04-03 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46510 | Garland Bobtown Road Sub : Upgrade relaying on capacitor bank #1 | City of Garland, Dallas County | Upgrade relaying on capacitor bank #1 | 2024-03-27 | 2024-06-15 |  |  | 453474 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46092 0PT47752 (R4021) | Bowman Switch : Replace existing autotransformer #1 | City of Wichita Falls, Wichita County | Replace existing auto on transformer #1 | 2023-09-15 | 2023-12-15 |  |  | 8095355.11 |  |  | 18 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47086 (M3011) | Southlake Sub: Install 138 kV capacitor bank | City of Southlake, Tarrant County | Install capacitors on the 138 kV bus. | 2022-11-30 | 2023-05-26 | 2023-05-26 |  | 4439746 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47154 (M5101) | Sherry Switch: Upgrade circuit breakers to 3200 A | City of Arlington, Tarrant County | Upgrade circuit breakers to 3200 A | 2023-09-26 | 2023-10-13 |  |  | 408756 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47702 (M4330) | Sherman TI Sub : Yard Expansion | City of Sherman, Grayson County | Expand station for new lines from Haggerty Switch and remove slip bus. | 2023-01-20 | 2023-04-17 | 2023-04-17 |  | 1915057 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47044 | Graham Plant Switch : Replace two circuit breakers | City of Graham, Young County | Replace two circuit breakers | 2023-01-09 | 2023-05-31 | 2023-05-31 |  | 457842 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47142 (R6191) | Rosenthal Sub: Establish one transformer with two feeder breakers and one tie breaker | City of Lorena, McLennan County | Establish one transformer with two feeder breakers and one tie breaker. | 2023-08-28 | 2023-12-01 |  |  | 5451267.38 |  |  | 8 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47745 0PT49243 (R8618) | Buffalo Sub: Upgrade 138 kV circuit breaker | City of Stanton, Martin County | Upgrade 138 kV circuit breaker. Modify 138 kV bus protection to provide redundancy. | 2023-05-01 | 2023-09-01 |  |  | 560304 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47525 0PT50782 | South Bend Sub : Rebuild station with Delta-Star skid mount | City of Graham, Young County | Rebuild existing substation utilizing a skid mounted substation. | 2024-02-05 | 2024-06-30 | [5 empty] | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44227 0PT48161 | DFW Mid Cities Sub : Establish station with two transformers and four feeder breakers | City of Euless, Tarrant County | Establish station with two transformers and four feeder breakers | 2024-09-03 | 2024-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43100 R4015) | Fisher Road Switch: Add new 138 kV terminal | City of Wichita Falls, Wichita County | Add new 138 kV terminal with 2000 A terminal rating | 2023-02-14 | 2023-04-20 | 2023-04-20 |  | 1190508 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47225 (M4331) | Newton Branch Sub: Establish station with one transformer and two feeder breakers | City of Midlothian, Ellis County | Establish station with one transformer and two feeder breakers | 2023-09-18 | 2024-01-15 |  |  | 5567773.71 |  |  | 2 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49440 (R6187) | Tin Roof POD: Install 2nd Capacitor Bank for POD | Bell County | Install second 110 MVAR capacitor bank for POD. | 2023-02-27 | 2023-05-22 | 2023-05-22 |  | 2398734 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48480 | Carrollton Northwest Switch : Replace four overdutied breakers | City of Carrollton, Dallas County | Replace four overdutied breakers | 2023-04-10 | 2023-05-02 | 2023-05-02 |  | 1692321 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48077 | Salt Lake Sub : Install transformer #3 | City of Midland, Midland County | Install transformer #3 and one feeder breaker | 2023-02-24 | 2023-06-30 | 2023-06-30 |  | 5043197 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47325 | Millers Ferry Road Sub : Install transformer #2 with one transformer and two feeder breakers | City of Forney, Kaufman County | Install transformer #2 with one transformer and two 12.5 kV feeder breakers | 2023-01-21 | 2023-05-11 | 2023-05-11 |  | 1732895 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47205 (M4137) | Mesquite North Sub : Upgrade Terminal to 3200A | City of Mesquite, Dallas County | Upgrade the line terminals to 3200 A at Mesquite North Sub. | 2024-01-15 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47199 (M4137) | Thornton East Sub : Add Line Switches and FID | City of Dallas, Dallas County | Add line switches and FID | 2024-01-15 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47126 (M5519) | Weatherford West Switch : Upgrade CB#4375 Terminal to 3200A | City of Weatherford, Parker County | Upgrade circuit breaker terminal to 3200A | 2023-10-10 | 2023-12-04 |  |  | 712617.31 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46769 (M4127) | Centerville Road Sub: Upgrade 138 kV line switches | City of Dallas, Dallas County | Upgrade 138 kV line switches to meet or exceed 2000 A | 2023-10-10 | 2023-12-15 |  |  | 328861.86 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46296 0PT48273 0PT47588 (R8564) | SkyWest : Upgrade 138 kV driver line terminal to be rated at 3200 A | City of Midland, Midland County | Remove wave trap and upgrade line communication to fiber. | 2023-10-17 | 2023-12-15 |  |  | 616609 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46295 0PT48759 (R8564) | Driver : Upgrade 138 kV SkyWest line terminal to meet or exceed 3200 A | Midland County | Remove wave trap and upgrade line communication to fiber. | 2023-10-08 | 2023-12-01 |  |  | 906192.32 |  |  | 2 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46003 (R8595) | Lamesa Switch : Rebuild/convert existing substation to 138 kV with two transformers | City of Lamesa, Dawson County | Disconnect the existing substation and rebuild to operate at 138 kV. | 2023-02-01 | 2023-10-01 |  |  | 7588290 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46511 | Centerville Switch : Upgrade relaying on capacitor bank #1 | City of Buffalo, Leon County | Upgrade relaying on capacitor bank #1 | 2024-05-17 | 2024-06-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47350 0PT47102 (R8649) | Vincent Sub : Establish substation with one transformer | City of Big Spring, Howard County | Establish station with one transformer and two feeder breakers | 2023-01-31 | 2023-09-15 |  |  | 5650762 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47322 | Ennis Southeast Sub : Install transformer #2 with two feeders | City of Ennis, Ellis County | Install transformer #2 with two feeder breakers. | 2023-01-20 | 2023-05-29 | 2023-05-29 |  | 1884960 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44231 0PT47655 0PT48829 (R6224) | Double Creek Sub : Establish substation with two transformers and four feeder breakers | City of Round Rock, Williamson County | Establish substation with two transformers and four feeder breakers | 2023-08-30 | 2023-12-15 |  |  | 12237395 |  |  | 7 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46861 (R4025) | Wichita Falls PPG Sub: Upgrade 138 kV line terminals and equipment | City of Wichita Falls, Wichita County | Upgrade 138 kV line terminals and equipment | 2023-04-17 | 2023-05-11 | 2023-05-11 |  | 489484 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44259 0PT44210 (M5310) | Padera Sub: Establish substation with two transformers and four feeder breakers | City of Midlothian, Ellis County | Establish two transformers and four feeder breakers | 2022-12-23 | 2023-09-30 |  |  | 7665758 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46879 (R8304) | Adobe Meadows Sub: 138 kV line terminal upgrade | City of Midland, Midland County | Replace three 138 kV air switches and three 138 kV lightning arresters on transformer #2 | 2023-03-28 | 2023-12-15 |  |  | 657187 |  |  | 93 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47201 (M4137) | Sunnyvale Sub : Upgrade terminals to 3200A | City of Sunnyvale, Dallas County | The upgrade will replace all 138 kV switches, bus, and terminal equipment to meet 3200A. | 2023-10-17 | 2023-10-31 |  |  | 443757 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47124 0PT51570 (R8659) | Sloan Switch : Establish 138 kV 3-breaker ring-bus point of interconnection (POI) for station | City of Midland, Midland County | Establish 138 kV 3-breaker ring-bus point of interconnection (POI) for station | 2025-01-01 | 2025-05-08 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47828 (R8624) | Moser Canyon POD: Establish 138 kV point of delivery (POD) for station | City of Colorado City, Mitchell County | Establish 138 kV point of delivery (POD) for station | 2023-09-20 | 2024-05-15 |  |  | 1156883 |  |  | 9 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47532 0PT48955 (R8612) | Sandhills Tap : Upgrade existing terminal equipment | City of Monahans, Ector County | Upgrade all line terminal and associated equipment to meet or exceed 3200 A. | 2023-05-05 | 2023-05-19 | 2023-05-19 |  | 857678 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47207 (M4137) | Mesquite East Switch : Upgrade one circuit breaker terminal to 3200A and add two new terminals | City of Mesquite, Dallas County | Upgrade one circuit breaker terminal to 3200A and add two new terminals | 2023-01-27 | 2023-12-15 |  |  | 2876107 |  |  | 63 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44255 0PT44779 (M5283) | Wilshire Sub : Establish substation with one transformer and two feeder breakers | Johnson County | Establish substation with one transformer and two feeder breakers | 2023-06-10 | 2023-12-01 |  |  | 7816660 |  |  | 46 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48441 (R8606) | Cottonfield Sub: 138 kV line terminal upgrade | City of Midland, Midland County | Replace three 138 kV air switches and associated bus work for 3200 A capability | 2023-10-25 | 2023-12-15 |  |  | 318599.19 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48938 (R8660) | Captain Jack POD : Establish 138 kV point of delivery (POD) | City of Wink, Winkler County | Establish 138 kV point of delivery (POD) | 2024-09-15 | 2024-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49046 (R8669) | White Dune POD : Establish 138 kV point of delivery (POD) | City of Wink, Winkler County | Establish 138 kV point of delivery (POD) | 2024-10-07 | 2024-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48618 | Blue Mound Sub : Install SODG on one feeder breaker | City of Fort Worth, Tarrant County | Install a distribution and transmission transfer trip protection scheme. | 2023-01-22 | 2023-12-15 |  |  | 373613 |  |  | 61 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48483 | Moss Switch : Replace two overdutied breakers | Ector County | Replace two overdutied breakers | 2023-10-16 | 2023-12-15 |  |  | 601943 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48482 | Kirkland Park Switch : Replace four overdutied breakers | City of Dallas, Dallas County | Replace four overdutied breakers | 2023-03-06 | 2023-12-01 |  |  | 2077589 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48481 | Hutto Switch : Replace three overdutied breakers | City of Hutto, Williamson County | Replace three overdutied breakers | 2023-03-13 | 2023-05-17 | 2023-05-17 |  | 742830 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48124 (R6141) | Waco West Switch: Remove 138 kV yard & reconfigure auto connection | City of Waco, McLennon County | Remove all equipment in the 138 kV yard and reconfigure autotransformer #2 | 2023-10-16 | 2023-12-15 |  |  | 1930107 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46683 (R6172) | McGregor Phillips Sub: Rebuild 138 kV station | City of McGregor, McLennan County | Remove the existing autotransformer equipment and structures. Establish a new 138 kV distribution station with two transformers. | 2024-05-01 | 2024-06-15 | [5 empty] | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44568 (R6183) | Hillsboro Sub : Modify relaying for connecting terminal to Ash Creek Switch for point of interconnection (POI) | City of Hillsboro, Hill County | Modify relaying for connecting terminal to Ash Creek Switch for point of interconnection (POI) | 2023-03-13 | 2023-04-20 | 2023-04-20 |  | 270503 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48200 (R6223) | Tiger Creek Switch : Establish 3-breaker ring -bus arrangement point of interconnection (POI) | City of McLennan, McLennan County | Establish 3-breaker ring-bus arrangement point of interconnection (POI) | 2024-06-15 | 2024-11-14 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48070 | Thorndale North Sub: Install bank #2 with one transformer and two feeder breakers | City of Thorndale, Milam County | Install bank #2 with one transformer and two feeder breakers | 2023-08-14 | 2023-12-01 |  |  | 5786203.12 |  |  | 61 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47351 | Mason Sub: Replace two transformers | Reeves County | Replace transformer #1 and #2 | 2023-03-29 | 2023-06-24 | 2023-06-24 |  | 3888689 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47410 (R8616) | Buchanan Ranch Sub: Install 110.4 MVAR capacitor bank | City of Midland, Midland County | Install 110.4 MVAR capacitor bank | 2023-02-13 | 2023-10-01 |  |  | 3137931 |  |  | 97 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47778 | Westmoreland North Sub: Install transformer #2 and one feeder breaker | City of Dallas, Dallas County | Install transformer #2 and one feeder breaker | 2023-06-08 | 2023-12-01 |  |  | 4471785 |  |  | 47 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46303 (R944) | Cumby Sub: Convert station to 138 kV operation | City of Cumby, Hopkins County | Convert station to 138 kV operation | 2023-05-29 | 2023-12-01 |  |  | 3453066.64 |  |  | 87 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46293 | Euless South Sub : Replace Transformer #1 and #2 failed HU relays | City of Euless, Tarrant County | Replace Transformer #1 and #2 HU relays. | 2022-03-18 | 2022-12-20 | 2022-12-20 |  | 291328 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41021 (M5222) | Marrs Switch: Terminate 138 kV Duval Switch Line | City of Forest Hill, Tarrant County | Terminate the new 138 kV Duval Switch Line | 2023-10-12 | 2023-12-15 |  |  | 269523 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48541 0PT46372 0PT47882 0PT48590 (R8634) | Tesoro Switch: Establish station as a 10-breaker 345 kV breaker-and-a-half bus arrangement | City of Odessa, Midland County | Establish station as a 10-breaker 345 kV breaker-and-a-half bus arrangement | 2023-03-21 | 2023-12-01 |  |  | 51315612 |  |  | 57 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49951 (R6172) | Bewley Sub : Rebuild 138 kV substation | City of McGregor, McLennan County | Rebuild 138 kV substation. | 2023-03-27 | 2023-09-01 | 2023-09-01 |  | 5112873 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49268 | Roanoke West Sub : Replace failed transformer #1 | City of Roanoke, Denton County | Replace transformer #1 and the associated relay panel due to transformer failure. | 2022-08-19 | 2022-11-18 | 2022-11-18 |  | 781122 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(d) | Failed Equipment
0PT48783 | Paris Switch : Replace three 345 kV circuit breaker | City of Paris, Lamar County | Replace three 345 kV circuit breaker | 2024-04-02 | 2024-06-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47255 0PT47105 | Starr Ranch Sub (Norman Crossing): Establish station | City of Hutto, Williamson County | Establish substation with one transformer and two feeder breakers. | 2023-09-12 | 2023-12-15 |  |  | 12035583.3 |  |  | 6 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47143 (R6191) | Eddy Sub: Rebuild substation with two transformers | City of Bruceville-Eddy, Falls County | Rebuild substation with two transformers . | 2023-05-04 | 2023-12-01 |  |  | 7674888.26 |  |  | 69 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
16T64009 0PT47317 | Mary Avenue Sub : Establish with one transformer and four feeder breakers | City of Waco, McLennan County | Establish with one transformer and four feeder breakers | 2023-03-20 | 2023-10-15 |  |  | 6881328 |  |  | 93 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49960 | Odessa EHV 138 kV: Replace seven oil pumps on Auto #2 | City of Odessa, Ector County | Replace various oil pumps on Auto #2. | 2024-01-24 | 2024-03-01 |  |  | 242336 |  |  | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47323 | Forest Hill Sub: Install bank #3 with one transformer and three feeder breakers | City of Fort Worth, Tarrant County | Install bank #3 with one transformer and three feeder breakers. | 2023-08-01 | 2023-12-15 |  |  | 5634503 |  |  | 30 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47931 (R8633) | Bull Head POD: Establish 138 kV point of delivery (POD) | Odessa County | Establish 138 kV point of delivery (POD) | 2023-09-18 | 2023-12-01 |  |  | 1284511.28 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47671 (M3228) | Poetry Switch - Establish 345 kV, 3200 A Switch for point of interconnection (POI) | City of Terrell, Kaufman County | Establish 345 kV, 3200 A switch for point of interconnection (POI) | 2023-08-08 | 2024-04-18 |  |  | 8918238 |  |  | 46 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47407 | Rendon Sub: Establish station | City of Mansfield, Tarrant County | Establish station with two transformers and four feeder breakers. | 2024-02-21 | 2024-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44344 (M4071) | Cedar Crest 138 kV Switch : Remove auto's and reconfigure line terminal layout and upgrade circuit breaker | City of Dallas, Dallas County | Remove auto's and reconfigure line terminal layout and upgrade circuit breaker. | 2023-05-08 | 2023-12-15 |  |  | 6059890.78 |  |  | 55 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47542 | Shafter Lake Sub : Establish stations #3 & #4 each with one transformer one feeder breaker | Odessa County | Establish stations #3 & #4 each with one transformer one feeder breaker | 2023-05-20 | 2023-12-01 |  |  | 6718470.06 |  |  | 83 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45607 (R6213) | Lake Creek Switch: Transfer trip addition, line terminal upgrade for the addition of point of interconnection (POI) | City of Waco, McLennan County | Transfer trip addition, line terminal upgrade for the addition of point of interconnection (POI) | 2023-09-19 | 2023-11-16 |  |  | 257123.23 |  |  | 99 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47136 0PT45862 0PT51132 0PT47111 (R6165) | Teal Switch: Establish a new switching station | City of Hutto, Williamson County | Establish a new switching station with fifteen 138 kV breakers, two 345 kV breakers, two autotransformers, and four reactors. | 2023-07-24 | 2023-12-15 |  |  | 37104354.76 |  |  | 7 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44328 (R8570) | Eskota Switch: Circuit breaker line terminal upgrade | City of Sweetwater, Nolan County | Circuit breaker line terminal upgrade | 2023-04-10 | 2023-05-30 | 2023-05-30 |  | 372799 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50268 (R6146) | McLane Switch : Rebuild station into a six breaker ring bus | City of Waco, McLennan County | Rebuild station into a six breaker ring bus | 2023-11-01 | 2024-05-01 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49260 (M3013) | Valley South: Install two 345 kV reactors | Fannin County | Install two 345 kV reactors, two 3200 A circuit breakers and two 3200 A sectionalizing switches. | 2023-07-05 | 2023-12-29 |  |  | 11479356 |  |  | 51 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48779 (R8674) | SL Driver Sub : Addition of 138 kV line terminal | Midland County | Addition of 138 kV line terminal | 2023-10-06 | 2023-12-14 |  |  | 1766020 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48249 | Goodnight Sub: Establish station with one transformer and two feeder breakers | Upton County | Establish station with one transformer and two feeder breakers | 2023-07-27 | 2023-12-01 |  |  | 5202980.59 |  |  | 37 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48182 (R8623) | Morgan Creek Switch : Upgrade terminal to 3200 A as part of establishing a 138 kV point of delivery (POD). | City of Colorado City, Mitchell County | Upgrade terminal to 3200 A as part of establishing a 138 kV point of delivery (POD). | 2023-10-23 | 2023-12-15 |  |  | 467843.65 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48181 (R8623) | Barber Lake Switch : Upgrade terminal to 3200 A as part of establishing a 138 kV point of delivery (POD) | Mitchell County | Upgrade terminal to 3200 A as part of establishing a 138 kV point of delivery (POD). | 2023-10-11 | 2023-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Project does not meet reporting criteria and will be removed on next month's report.
0PT47932 (R6228) | McGuffey POD : Establish 138 kV point of delivery (POD) | City of McGregor, McLennan County | Establish 138 kV point of delivery (POD) | 2023-05-22 | 2024-02-16 |  |  | 1132098 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47799 (R6143) | Elgin Switch : Retire assets associated with autotransformer. | Temple County | Remove autotransformer as part of relocating the autotransformer to Taylor Switch. | 2023-10-20 | 2024-05-15 | [5 empty] | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | Project does not meet reporting criteria and will be removed on next month's report.
0PT47775 | Hutto Switch : Replace electromechanical relays for auto #1 | City of Hutto, Williamson County | Replace electromechanical relays for auto #1. | 2023-09-13 | 2023-12-31 |  |  | 2294627.9 |  |  | 27 | 345 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47717 (R6211) | Brushy Creek Switch : Install 138 kV line terminal for Mallard Switch | City of Elgin, Temple County | Install 138 kV line terminal for Mallard Switch | 2023-07-17 | 2023-10-15 |  |  | 1487748 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47531 | Waco Sanger Avenue Sub: Install transformer #2 | City of Waco, McLennan County | Install one transformer #2 and three feeder breakers. Replace existing control center with one pre-wired control center. | 2023-07-01 | 2023-12-15 |  |  | 4454481 |  |  | 93 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47518 | Western Hills Sub: Install feeder on station #3 and upgrade relaying | City of Fort Worth, Tarrant County | Install feeder on station #3 and upgrade relaying. | 2023-09-16 | 2023-12-15 |  |  | 6000000 |  |  | 3 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47439 | Ferris Sub: Rebuild station | City of Ferris, Ellis County | Rebuild station for a 4 transformer or 3 transformers & capacitor bank ultimate. | 2023-07-07 | 2023-12-15 |  |  | 7696775.17 |  |  | 1 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47404 0PT46924 | Blackstock Sub: Establish substation with one transformer and two feeder breakers | Collin County | Establish substation with one transformer and two feeder breakers | 2023-11-01 | 2024-05-01 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47362 | Venus Switch: Remove station #4, and install station #6 with three feeders and install one feeder on station #5 | City of Venus, Ellis County | Remove station #4, and install station #6 with three feeders and install one feeder on station #5 | 2023-07-13 | 2023-12-15 |  |  | 5066451 |  |  | 35 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46623 (M4338) | Southmayd Switch: Establish 138 kV station for point of interconnection (POI) | City of Southmayd, Grayson County | Establish 138 kV station for point of interconnection (POI) | 2024-11-18 | 2025-04-17 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43108 0PT44821 (R4015) | Old Lake Switch: Establish station with an autotransformer and a 3-breaker 69 kV ring bus | City of Henrietta, Clay County | Establish station with a 100 MVA autotransformer and a 3-breaker 69 kV ring bus. | 2023-07-17 | 2023-11-15 |  |  | 8224356 |  |  | 18 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45155 (R3028) | Midpoint Switch : Establish 3 breaker ring arrangement point of interconnection (POI) | Armstrong County | Establish 3 breaker ring arrangement point of interconnection (POI) | 2023-05-12 | 2023-11-16 |  |  | 8256917.48 |  |  | 74 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44863 (R6246) | Ghost Town Switch: Establish 138 kV point of interconnection (POI) | City of Caddo, Stephens County | Establish 138 kV point of interconnection (POI) | 2024-01-01 | 2024-05-09 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49561 | Fisher Rd Switch : Re-gasket Auto#1 | City of Wichita Falls, Wichita County | Re-gasket Auto #1 at Fisher Rd Switch. | 2023-04-01 | 2023-05-31 | 2023-05-31 |  | 417144 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT02608 0PT44837 (R9022) | Mulberry Creek Switch: Rebuild the existing station | City of Abilene, Taylor County | Rebuild the existing 345 kV switching station as a 4-breaker ring bus. | 2023-11-01 | 2025-05-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42592 (R985) | Royse Switch: Remove 69 kV yard and establish 138 kV terminal to Commerce Switch | City of Royse City, Rockwall County | Remove 69 kV yard and establish 138 kV terminal to Commerce Switch | 2023-09-30 | 2023-12-15 |  |  | 799329.21 |  |  | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44209 0PT44619 (M5261) | Base Camp Switch : 138 kV station rebuild | City of Saginaw, Tarrant County | Rebuild the existing 138 kV Eagle Mountain switching station. | 2023-05-08 | 2025-12-15 |  |  | 25331071.08 |  |  | 6 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44256 0PT44755 | Charca Sub : Establish with one transformer and one feeder breaker and relay upgrade | Johnson County | Establish with one transformer and one feeder breaker and relay upgrade | 2023-08-01 | 2023-12-01 |  |  | 6441930.3 |  |  | 23 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46203 (R6214) | McFall Switch : Establish 69 kV station for point of interconnection (POI) | City of Cameron, Milam County | Establish 69 kV station for point of interconnection (POI) | 2024-01-02 | 2024-05-16 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46302 (R944) | Cumby Tap Switch: Remove auto #1 & 69 kV equipment and reconfigure as 138 kV ring bus | City of Cumby, Hopkins County | Remove autotransformer #1, 69 kV equipment and reconfigure station as a 138 kV ring bus and install deadend. | 2023-06-09 | 2023-12-15 |  |  | 7014280.55 |  |  | 5 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46500 0PT48949 (R985) | Burrow POI : Convert from 69 kV to 138 kV for point of interconnection (POI) | City of Royse City, Rockwall County | Convert from 69 kV to 138 kV for point of interconnection (POI) | 2023-09-15 | 2023-11-17 |  |  | 1160565.62 |  |  | 9 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46621 | DFW Southwest Sub : Reconfigure high side bus with breakers and FIDs | City of Dallas, Dallas County | Reconfigure high side bus with breakers and FIDs | 2023-06-26 | 2023-12-15 |  |  | 4028834 |  |  | 76 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47402 | Robinson Northwest Sub: Install bank #2 and two feeder breakers | City of Waco, McLennan County | Install bank #2 and two feeder breakers | 2024-06-17 | 2024-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47786 | Harris Creek Sub : Establish substation with one transformer | City of McGregor, McLennan County | Establish substation with one transformer and two feeder breakers for replacement project for the failed McGregor Sub. | 2022-06-20 | 2022-12-31 | 2022-12-31 |  | 5320157 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(d) | Emergency Project
0PT48387 | Yarborough Sub : Install bank #2 and upgrade bank #1 transformer | City of Odessa, Ector County | Install bank #2 and upgrade bank #1 with one transformer | 2023-07-28 | 2023-12-01 |  |  | 4684435 |  |  | 67 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48458 | Snyder Switch : Replace one 138 kV circuit breaker | City of Snyder, Scurry County | Replace one 138 kV circuit breaker. | 2024-04-22 | 2024-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48716 | Edwards Sub : Rebuild station with replacing bank #1 & installing new bank #2 for point of interconnection (POI) | City of Odessa, Crane County | Rebuild station with replacing bank #1 & installing new bank #2 with one transformer for point of interconnection (POI) | 2023-06-09 | 2023-12-15 |  |  | 7746476.38 |  |  | 26 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49102 (M4354) | Bloomdale Switch : Establish four breaker ring bus | City of McKinney, Collin County | Establish three breaker 138 kV ring bus (ultimate four breaker) for point of interconnection (POI). | 2023-11-13 | 2024-04-17 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46505 | Lake Creek Switch : Upgrade relaying on auto #2 | City of Riesel, McLennan County | Upgrade relaying on auto #2. | 2024-01-05 | 2024-06-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47269 | Sherry Switch : Regasket Auto #2 | City of Arlington, Tarrant County | Regasket Auto #2 at Sherry Switch. | 2023-04-01 | 2023-05-26 | 2023-05-26 |  | 280545 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48105 (M4323) | Paris Switch : Modify relaying for new line terminal | City of Paris, Lamar County | Modify relaying for new line terminal for point of interconnection (POI). | 2023-10-02 | 2023-11-16 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3) | Project does not meet reporting criteria and will be removed on next month's report.
0PT47930 (R8624) | Wrage Ranch : Establish 138 kV Point of Delivery (POD) | Glasscock County | Establish 138 kV point of delivery (POD) | 2023-11-15 | 2023-12-01 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50100 | Judkins Sub : Install feeder for Distributed Energy Storage Resource (DESR) | City of Odessa, Ector County | Install new feeder for Distributed Energy Storage Resource, including a transmission overvoltage protection scheme with three 138 kV CCVTs. | 2023-09-21 | 2023-11-15 |  |  | 522194.67 |  |  | 95 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46378 (M4212) | Dealey Street Sub : Upgrade line terminal to 3200A | City of Dallas, Dallas County | Upgrade main through line terminals to 3200A. | 2023-09-26 | 2023-12-01 |  |  | 1584343 |  |  | 1 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50253 0PT50769 (R8626) | Roughneck Tap: 138 kV line terminal upgrade | City of Stanton, Martin County | Upgrade all associated terminal equipment to meet or exceed 3200A. | 2023-10-06 | 2023-12-15 |  |  | 459939.13 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49759 (R6208) | Bell County East Switch : Establish 345 kV point of interconnection (POI) | City of Temple, Bell County | Establish 345 kV point of interconnection (POI) | 2024-01-01 | 2024-05-15 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49854 | Killeen Clear Creek Sub : Upgrade relaying to suburban IV | City of Killeen, Bell County | Upgrade relaying to suburban IV and replace feeder breakers. | 2023-10-23 | 2024-02-29 |  |  | 2926358.35 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47359 | Pantego Sub: Replace two transformers | City of Arlington, Tarrant County | Replace two transformers and control center with a pre-wired control center. | 2024-07-15 | 2024-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47356 0PT46922 | Runaway Bay Sub: Establish substation with one transformer | Wise County | Establish substation with one transformer and two feeder breakers. | 2023-10-16 | 2023-12-15 |  |  | 5865337 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48013 | Lemmon Ave Sub : Install transformers #3 and #4 | City of Dallas, Dallas County | Establish stations #3 and #4 with two transformers and eight new switchgear type feeder breakers. | 2023-09-02 | 2024-04-15 |  |  | 8648622 |  |  | 39 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48078 | Salt Lake Sub : Install transformer #4 and one feeder breaker | Midland County | Install transformer #4 and one feeder breaker | 2023-10-02 | 2023-12-01 |  |  | 2721475.03 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47543 | Gasland Sub: Install transformer #2 with one transformer and two feeder breakers | City of Andrews, Andrews County | Install transformer #2 with one transformer and two feeder breakers. | 2023-07-12 | 2023-12-01 |  |  | 5440827 |  |  | 99 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49790 0PT47302 (R6191) | Bronze Age Sub : Establish substation with one transformer | City of Troy, Bell County | Establish substation with one transformer and two feeder breakers. | 2023-10-01 | 2023-12-01 |  |  | 6280985 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49494 (M4013) | Anna Switch : Install two reactors on the tertiary of autotransformer #2 | City of Celina, Collin County | Install two reactors on the tertiary of autotransformer #2. | 2023-09-08 | 2023-12-01 |  |  | 1679418 |  |  | 37 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48718 | Barr Ranch Sub: Install bank #3 with one transformer and two feeder breakers | City of Midland, Midland County | Install bank #3 with one transformer and two feeder breakers for point of interconnection (POI). | 2023-08-18 | 2023-12-01 |  |  | 4934341 |  |  | 39 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47204 | Mesquite Town East Sub : Upgrade terminal to 3200A | City of Mesquite, Dallas County | Upgrade the 138 kV line terminal and associated equipment to meet or exceed 3200 A. | 2023-11-01 | 2023-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47045 | Burwick Switch : Replace three circuit breakers | City of Bryson, Jack County | Replace three circuit breakers. | 2023-09-18 | 2023-12-31 |  |  | 1061203.54 |  |  | 20 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44272 (M3223) | Royse Switch: Establish new 138 kV line terminal and disconnect existing Terrell 69 kV line | City of Royse, Rockwall County | Establish new 138 kV line terminal and disconnect existing Terrell 69 kV line | 2023-09-29 | 2023-12-15 |  |  | 1269094.91 |  |  | 28 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42598 (R985) | Commerce Switch : Add 138 kV terminal addition for 138 kV Royse line conversion | City of Commerce, Hunt County | Add line terminal by installing a new 138 kV single-breaker terminal position. | 2023-08-06 | 2023-12-15 |  |  | 1488433.79 |  |  | 10 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40856 (R3029) | AJ Swope Switch : Establish 345 kV terminal | Potter County | Establish 345 kV terminal. | 2023-12-11 | 2024-04-18 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48723 | Wall Street Sub : Convert Cedar Crest line terminal to 138 kV operation | City of Dallas, Dallas County | Upgrade existing bus to 3200A and convert Cedar Crest Line to 138 kV operation. | 2023-09-25 | 2023-12-15 |  |  | 1278081.55 |  |  | 1 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46506 | Cedar Hill Switch : Upgrade relaying on auto #2 | City of Cedar Hill, Dallas County | Upgrade 345 kV auto #2 protection to provide redundancy for three phase faults. | 2024-01-08 | 2024-06-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47647 | Taylor West Sub : Install bank #2 with one transformer and two feeder breakers | Williamson County | Install bank #2 with one transformer and two feeder breakers. | 2023-08-13 | 2023-12-01 |  |  | 3088708.21 |  |  | 92 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49495 (M4014) | Collin Switch : Install two reactors on the tertiary of autotransformer #2 | City of Frisco, Collin County | Install two 37.5 MVAR reactors on the tertiary of autotransformer #2. | 2023-09-20 | 2023-12-01 |  |  | 1352233 |  |  | 48 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47405 0PT46905 | Castleman Sub: Establish substation with one transformer and two feeder breakers | City of Hewitt, McLennan County | Establish substation with one transformer and two feeder breakers. | 2023-08-03 | 2023-12-15 |  |  | 6220625 |  |  | 23 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48014 | Matilda Sub : Install transformer #3, #4, and associated switchgear | City of Dallas, Dallas County | Establish stations #3 and #4 with two transformers and eight switchgear feeder breakers. | 2023-06-07 | 2024-03-15 |  |  | 8573178 |  |  | 40 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49483 | NTUSU Farmland Sub (345KV): Replace Failed Station Service XFR | Lynn County | Replace Station Service Transformer at Farmland 345kV Sub. | 2023-10-30 | 2023-12-29 |  |  | 202615 |  |  | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(d)
0PT47361 0PT47104 (M4332) | Templeton Sub: Establish substation with one transformer | City of Waxahachie, Ellis County | Establish substation with one transformer and two feeder breakers | 2023-07-18 | 2023-12-15 |  |  | 6068762 |  |  | 9 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50249 (R6260) | Ellison Springs POI: Establish 69 kV point of interconnection (POI) | City of De Leon, Comanche County | Establish 69 kV point of interconnection (POI). | 2023-10-02 | 2023-12-01 |  |  | 995,388.66 |  |  | 0 | na | 69 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44334 (R6147) | Elm Mott Switch: Add a line terminal | City of Elm Mott, McLennan County | Add a line terminal to convert 69 kV Waco East Switch line to 138 kV | 2023-10-01 | 2023-12-15 |  |  | 1150308 |  |  | 4 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46385 | Industrial Blvd Switch : Replace three overdutied breakers | City of Dallas, Dallas County | Replace 138 kV overdutied circuit breakers | 2023-10-23 | 2023-12-15 |  |  | 1511565.61 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48773 (R8606) | South Midland Switch : Reconfigure the 138 kV high side | City of Midland, Midland County | Reconfigure the 138 kV high side | 2023-11-01 | 2023-12-15 |  |  | 679897 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47856 | Lake Texoma Sub : Replace transformer #1 and install transformer #2 | City of Denison, Grayson County | Replace transformer #1 and install transformer #2 | 2023-09-14 | 2024-05-01 |  |  | 5113741 |  |  | 7 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49660 0PT48928 (R8670) | Quartz Sand Switch: Establish 138 kV station | City of Stanton, Glasscock County | Establish as a 5-breaker 138 kV breaker-and-a-half bus arrangement. | 2023-11-06 | 2024-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49486 (R8678) | Raceway Switch : Establish 138 kV, 3 breaker ring bus station for point of interconnection (POI) | City of Odessa, Ector County | Establish 138 kV, 3 breaker ring bus station for point of interconnection (POI). | 2024-01-08 | 2024-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47093 (M3063) | Bear Pen Switch: Establish 345 kV station for point of interconnection (POI) | City of Mt Vernon, Franklin County | Establish 345 kV station for point of interconnection (POI) | 2024-06-07 | 2024-11-14 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49018 (R6231) | Dos Rios Switch: Establish 138 kV station for point of interconnection (POI) | Milam County | Establish 138 kV station for point of interconnection (POI). | 2024-03-18 | 2024-11-17 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50003 | Comanche Switch : Replace two 138 kV circuit breakers | City of Comanche, Comanche County | Replace two 138 kV circuit breakers | 2023-10-30 | 2023-12-31 |  |  | 658291.59 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49981 (M3500) | Denton Creek Switch: Establish 138 kV station for point of interconnection (POI) | City of Decatur, Wise County | Establish 138 kV station for point of interconnection (POI). | 2024-01-02 | 2024-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51535 | Fairfield West Sub: Install settlement only distribution generator (SODG) on one feeder | City of Fairfield, Freestone County | Install settlement only distribution generator (SODG) on one feeder. | 2024-03-04 | 2024-04-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50089 | Webb Sub : Replace failed transformer #3 | City of Arlington, Tarrant County | Replace failed transformer #3 | 2023-02-28 | 2023-03-07 | 2023-03-07 |  | 931806.81 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(d)
0PT49664 (M4001) | Endeavor Switch : Establish 345 kV station for a point of interconnection (POI) | City of Midlothian, Ellis County | Establish 345 kV station for a point of interconnection (POI) | 2024-01-22 | 2024-05-15 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47779 (R6255) | Cannon Switch : Establish 138 kV station for a point of interconnection | City of Milano, Milam County | Establish 138 kV station for point of interconnection (POI) | 2024-09-18 | 2025-05-08 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46105 (R6094) | Tyler Switch : Upgrade one circuit breaker terminal to 2000A | City of Tyler, Smith County | Upgrade jumpers on one circuit breaker terminal to be rated 2000A. | 2026-06-05 | 2026-09-15 | [5 empty] | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45620 (M3232) | Nautilus Switch : Establish 345 kV station for a point of interconnection (POI) | City of Glen Rose, Somervell County | Establish 345 kV station for point of interconnection (POI). | 2025-12-15 | 2026-05-07 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47268 (M4356) | Tri Corner Switch : Add a breaker and a half rung to existing station for new point of interconnection (POI) | City of Seagoville, Dallas County | A breaker-and-a-half rung will be added to the existing station for point of interconnection (POI). | 2024-01-05 | 2024-04-18 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51063 | Comanche Switch: Auto 1 Re-Gasket | City of Comanche, Comanche County | Regasket Auto 1 at Comanche Switch | 2023-09-18 | 2023-10-20 |  |  | 370936 |  |  | 20 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50292 | Moss Switch 345/138 kV: Replace (6) Oil Pumps on Auto #1 | Ector County | Replace oil pumps on Auto #1 at Moss Switch 345/138 kV | 2024-02-26 | 2024-03-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50734 | Royse City Switch : Replace Pumps & Regasket Auto Transformer #3 | City of Royse City, Rockwall County | Replace pumps and regasket Auto #3 at Royse City Switch. | 2024-01-22 | 2024-03-01 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49492 | Anna Switch : Replace existing SSVTs | City of Anna, Collin County | Replace existing SSVTs and upgrade grounding grid | 2024-02-01 | 2024-05-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50485 (M4356) | Carrollton Northwest : Replace one overdutied 138 kV circuit breaker | City of Carrollton, Dallas County | Replace one overdutied 138 kV circuit breaker | 2024-01-08 | 2024-04-18 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48106 (R6252) | Files Valley Switch: Establish 345 kV ring bus station for a point of interconnection (POI) | City of Itasca, Hill County | Establish a 345 kV ring bus station for a point of interconnection (POI). | 2023-12-01 | 2024-05-16 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46515 (R8530) | Moss Switch: 138 kV circuit breaker line terminal upgrade | City of Odessa, Ector County | Upgrade the 138 kV circuit breaker line terminal to 3200 A. | 2023-11-13 | 2024-05-31 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50806 | Roanoke West Sub: Install transformer #3 | City of Roanoke, Denton County | Install transformer #3, two 25 kV feeder breakers, one 25 kV bus tie breaker, 25 kV feeder ties, and new control center. | 2023-11-06 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47403 0PT47108 | Vanguard Sub: Establish station with two transformers and five circuit breakers | City of Mesquite, Dallas County | Establish substation with two transformers and five circuit breakers. | 2023-11-01 | 2024-05-01 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50805 | Kaufman South Sub: Upgrade transformer #1 and install transformer #2 | City of Kaufman, Kaufman County | Replace existing transformer #1, remove associated voltage regulators, and install transformer #2 with one feeder breaker. | 2023-11-27 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47524 (R4026) | Bowman Switch : Replace auto transformer #2 | City of Wichita Falls, Wichita County | Replace existing auto transformer #2 | 2024-01-30 | 2024-05-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49746 0PT48318 | Steer Sub : Establish station with two transformers | City of Big Spring, Howard County | Establish station with two transformers and four feeder breakers. | 2023-11-20 | 2024-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48489 0PT46856 | Floyd Branch Sub: Establish station with one transformer and three feeder breakers | City of Dallas, Dallas County | Establish station with one transformer and three feeder breakers | 2024-02-26 | 2024-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48694 (R8528) | Olefin Switch: 138 kV line terminal modifications | City of Odessa, Ector County | Modify 138 kV line terminals | 2024-04-08 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47660 (M4328) | Red Oak Sub : Upgrade existing terminal and associated equipment to meet or exceed 3200 A | City of Red Oak, Ellis County | Upgrade existing terminal and associated equipment to meet or exceed 3200 A. | 2024-03-11 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47440 0PT47099 | Dorchester Sub: Establish station with one transformer and two feeder breakers | Grayson County | Establish station with one transformer and two feeder breakers. | 2023-11-01 | 2024-05-01 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49446 (R8671) | Merrick POD : Establish 138 kV point of delivery (POD) | City of Stanton, Martin County | Establish 138 kV point of delivery (POD) | 2024-01-08 | 2024-04-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50900 (R8699) | Wishbone POD : Establish 138 kV point of delivery (POD) | City of Stanton, Martin County | Establish 138 kV point of delivery (POD) | 2024-02-15 | 2024-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51638 (R6141) | Temple Elm Creek Switch : Replace relaying for Peppervine Switch | City of Temple, Bell County | Modify relaying as a part of establishing Peppervine Switch. | 2023-08-18 | 2023-10-16 |  |  | 265416.98 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47355 0PT46906 | Circle Point Sub: Establish station with one transformer and two feeder breakers | City of Waco, McLennan County | Establish station with one transformer and two feeder breakers | 2023-12-04 | 2024-06-28 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49104 (R8679) | Lamesa Switch : Add 138 kV rung and line terminal addition | Dawson County | Add 138 kV rung and line terminal, two-breaker rung in breaker and a half arrangement with minimum terminal and equipment rating of 3200 A | 2024-01-02 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48528 (R6256) | Bale Switch POI : Establish 345 kV station for a point of interconnection (POI) | Falls County | Establish 345 kV station for a point of interconnection (POI). | 2024-01-01 | 2024-05-15 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51492 | Hartring Sub : Establish substation with one transformer and install two feeder breakers | City of Big Lake, Reagan County | Establish substation with one transformer and install two feeder breakers. | 2024-01-15 | 2024-06-30 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48778 (M4352) | Greenville Ave Sub : Install two transformers | City of Dallas, Dallas County | Install two transformers | 2023-12-19 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49834 (R8360) | McDonald Road Switch: Upgrade 138 kV line terminal | City of Ross, Glasscock County | Upgrade 138 kV circuit breaker line terminal and associated equipment to meet or exceed 3200 A. | 2024-01-15 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50837 (M4347) | Hackberry Switch: Upgrade 138 kV line terminal | City of Irving, Dallas County | Upgrade 138 kV line terminals and associated equipment to meet or exceed 3200 A. | 2024-01-05 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50080 | Frankel City Sub : Upgrade bank#1 and install bank #2 with one transformer | City of Andrews, Andrews County | Upgrade bank #1 with one transformer and install one feeder breaker and install bank #2 with one transformer and four feeder breakers. | 2024-01-05 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50817 0PT51504 | Lazy Ranch Sub : Establish station with two 138 kV transformers | City of Stanton, Martin County | Establish station with two transformers, four feeder breakers, one bus tie breaker, and five sectionalizing switches. | 2023-11-01 | 2024-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51092 (M5281) | Kingsridge Switch: Establish 138 kV station | City of Keller, Tarrant County | Establish station as a 138 kV ring bus arrangement with 3200 A terminals. | 2023-10-09 | 2024-05-15 |  |  | 9209567 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44297 (R6146) | Waco East Substation: Rebuild substation with two transformers | City of Waco, McLennan County | Rebuild substation with two transformers and retire switching station | 2024-06-17 | 2024-10-31 | [5 empty] | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50194 0PT49507 (R6239) | Temple Pecan Creek Switch: Install auto #2 and two 345 kV line terminals | City of Temple, Bell County | Install auto #2, two 345 kV line terminals, and one 138 kV line terminal. | 2023-11-06 | 2024-05-31 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50838 (M4347) | DFW B East: 138 kV line terminal upgrades | City of Irving, Dallas County | Upgrade 138 kV line terminal and associated equipment to meet or exceed 3200 A. | 2024-01-05 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46113 (R8591) | Yucca Drive Switch: 138 kV line terminal addition | City of Monahans, Ward County | Disconnect two line terminals and remove one autotransformer to add one line terminal. | 2024-04-26 | 2024-06-30 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46516 (R8530) | Ector Harper Sub: 138 kV line terminal upgrade | Odessa County | Upgrade the 138 kV line terminal to 3200 A. | 2024-01-08 | 2024-05-31 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46654 0PT50465 | Tyre Park Sub : Establish new substation | City of Grand Prairie, Dallas County | Establish station with two transformers, two fault interrupting devices and five motor operated sectionalizing switches. | 2024-01-08 | 2024-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48697 (R8528) | Odessa EHV Switch: Upgrade circuit breaker line terminal | City of Odessa, Ector County | Upgrade circuit breaker line terminal and associated equipment to meet or exceed 3200 A. | 2024-01-19 | 2024-09-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49025 (R6173) | Cathey Creek Sub: Install transformer #1 and two feeder breakers | City of Holland, Bell County | Install station with one transformer and two feeder breakers. | 2024-01-01 | 2024-05-15 | [5 empty] | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50076 | Maverick Draw Sub : Install bank #2 with one transformer and two feeder breakers | City of Salt Flat, Culberson County | Install bank #2 with one transformer and two feeder breakers | 2024-01-08 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50077 | Alcatraz Sub : Install bank #3 with one transformer and install two feeder breakers | City of Mentone, Loving County | Install bank #3 with one transformer and install two feeder breakers. | 2024-01-08 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50079 | China Lake Sub : Install bank #2 with one transformer and install two feeder breakers | City of Monahans, Ward County | Install bank #2 with one transformer and install two feeder breakers. | 2024-01-08 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50810 | Mariensfield Sub: Install bank #2 with one transformer and two feeder breakers | City of Midland, Martin County | Install bank #2 with one transformer and install two feeder breakers. | 2024-01-05 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50811 | Kyle Ranch Sub: Install bank #3 and two feeder breakers | City of Mentone, Loving County | Install bank #3 with one transformer and install two feeder breakers. | 2024-01-08 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50813 | Crandall Sub: Install transformer #2 with one transformer and two feeder breakers | City of Crandall, Kaufman County | Install transformer #2 with one transformer and two feeder breakers. | 2023-11-27 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50815 | Willow Wells Sub: Install bank #3 with one transformer and two feeder breakers | Winkler County | Install bank #3 with one transformer and install two feeder breakers. | 2024-01-08 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50818 | Shifting Sands Sub : Install bank #2 with one transformer and two feeder breakers | Winkler County | Install bank #2 with one transformer and install two feeder breakers. | 2024-01-08 | 2024-05-15 | [5 empty] | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50850 | Britton Road Sub: Install transformer #3 and #4 with a feeder breaker on each station | City of Mansfield, Tarrant County | Install transformer #3 and #4 and include a feeder breaker on each station. | 2024-03-04 | 2024-05-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50966 | Ivy League Sub: Install bank #2 with one transformer and two feeder breakers | Collin County | Install bank #2 with one transformer and install two feeder breakers. | 2024-03-04 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51117 | Ennis South Sub: Rebuild station with two transformers and with eight feeder breakers | City of Ennis, Ellis County | Rebuild station with two transformers and with eight feeder breakers. | 2024-01-08 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51217 0PT48501 | Ridgeview Sub: Establish station with two transformers and four feeder breakers | City of Allen, Collin County | Establish 138 kV station with two transformers and four feeder breakers. | 2024-01-01 | 2024-09-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51523 0PT50035 (R8677) | Roadrunner POD: Install 138 kV capacitor bank | Ector County | Install one capacitor bank, including one circuit breaker, three circuit switchers, and three motor-operated air switches. | 2024-03-04 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51524 (R8693) | East Stiles Sub: Install 138 kV capacitor bank | City of Big Lake, Reagan County | Install one capacitor bank, including one circuit breaker, three circuit switchers, and one motor-operated air switch. | 2023-12-15 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51540 | Tex Harvey Sub : Install bank #2 with one transformer and two feeder breakers | Midland County | Install bank #2 with one transformer and two feeder breakers. | 2024-03-04 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51547 (R8678) | Slingshot POD : Establish 138 kV point of delivery (POD) | City of Odessa, Ector County | Establish a 138 kV point of delivery (POD). | 2024-01-15 | 2024-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51623 (R8700) | Centralia Sub: Install 138 kV capacitor Bank #2 | Odessa County | Install one capacitor bank, including one circuit breaker, three circuit switchers, and one motor-operated air switch. | 2024-01-15 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51635 | Century Sub: Install feeder for Distributed Energy Storage Resource (DESR) | City of Arlington, Tarrant County | Install new feeder for Distributed Energy Storage Resource, including a transmission overvoltage protection scheme. | 2024-01-05 | 2024-04-30 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51560 | Melton Branch POD : Install LV metering on twelve customer owned transformers | Navarro County | Install LV metering on twelve customer owned transformers for point of delivery (POD). | 2023-12-18 | 2024-02-15 | [5 empty] | 0 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50733 | Trinidad Switch : Replace Three 138kV bushings on Auto #6 | Henderson County | Replace bushings on Auto #6 at Trinidad Switch | 2023-01-26 | 2023-06-28 | 2023-06-28 |  | 338391 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(d)
0PT42599 (R985) | Commerce Sub: Remove 69 kV yard | City of Commerce, Hunt County | Remove 69 kV yard which includes one autotransformer, one circuit breaker, and all associated equipment and structures. | 2024-02-26 | 2024-09-15 | [5 empty] | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46114 (R8591) | Thorntonville Sub: Convert station to 138 kV operation | City of Monahans, Ward County | Convert station operation from 69 kV to 138 kV. | 2024-04-08 | 2024-06-30 | [5 empty] | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47140 (R6191) | Peppervine Switch: Install one 138 kV line terminal | City of Waco, McLennan County | Install one 138 kV breaker to an existing rung as part of converting the existing line associated. | 2024-01-05 | 2024-06-30 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47354 0PT52384 (R6236) | Thorndale North Sub: Install 138 kV capacitor bank | City of Thorndale, Milam County | Install 138 kV capacitor bank. | 2024-02-12 | 2024-06-28 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49745 (R8303) | Stanton East Switch: 138 kV circuit breaker line terminal modifications | City of Stanton, Martin County | Modify two 138 kV circuit breaker line terminals. | 2024-02-01 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49833 (R8360) | Morgan Creek Switch: Upgrade one circuit breaker line terminal | City of Colorado City, Mitchell County | Upgrade one line terminal and associated equipment. | 2024-02-12 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50261 (R6241) | Carroll Springs Sub: 138 kV capacitor bank replacement | City of Palestine, Anderson County | Replace the existing single stage 69 kV capacitor bank. | 2024-03-04 | 2024-05-15 | [5 empty] | 0 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50571 (R6277) | Beulah Switch : Establish 345 kV station for a point of interconnection (POI) | Milam County | Establish 345 kV station for point of interconnection (POI). | 2024-05-20 | 2024-11-14 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50765 (R8697) | Shaw POD : Establish 138 kV point of delivery (POD) | City of Midland, Midland County | Establish 138 kV point of delivery (POD). | 2024-02-09 | 2024-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50809 | Cottonfield Sub: Install transformer #2 | City of Midland, Midland County | Install transformer #2 with two feeder breakers and one motor-operated sectionalizing switch. | 2024-01-05 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50816 | Knott Sub: Install Transformer #2 | City of Big Springs, Howard County | Install transformer #2 with two feeder breakers. | 2023-11-01 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50970 | Taylor Sub: Replace transformer #1 & transformer #2 | City of Taylor, Williamson County | Replace transformer #1 and transformer #2 with one transformer and install one feeder breaker on bank #1. | 2024-01-05 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50975 0PT49550 | Ten Mile Sub: Establish station with two transformers | City of Lancaster, Dallas County | Establish station with two transformers and four feeder breakers. | 2024-01-05 | 2024-10-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51045 (R6187) | Tin Roof POD : Establish carrier blocking terminal for point of delivery (POD) | Bell County | Establish carrier blocking terminal for point of delivery (POD). | 2024-01-15 | 2024-04-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51142 (R8697) | Desert Wind Sub : Add 55.2 MVAR reactive compensation | City of Garden City, Glasscock County | Add 55.2 MVAR three stage capacitor bank for point of delivery (POD). | 2024-02-05 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51598 0PT50908 | Rosen Heights Sub : Rebuild station with three transformers | City of Fort Worth, Tarrant County | Rebuild with three transformers and ten feeder breakers. | 2024-01-05 | 2024-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51826 | Mesquite East Switch : Replace overduited 138 kV circuit breaker | City of Mesquite, Dallas County | Replace overdutied 138 kV circuit breaker. | 2024-02-15 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51836 | Hutto Switch : Replace overdutied 138 kV circuit breaker | City of Hutto, Williamson County | Replace overdutied 138 kV circuit breaker. | 2024-02-28 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47662 | Desoto Switch : Terminal upgrades | City of Red Oak, Ellis County | Modify relaying for Loop Nine Switch. | 2023-10-30 | 2023-12-15 |  |  | 301610.47 |  |  | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51029 | Paris Switch: Replace Three Reactors at Breaker R1 Due to Failure & Age | City of Paris, Lamar County | Replace reactors, circuit breaker and disconnect switches at Paris Switch. | 2023-03-15 | 2023-08-18 | 2023-08-18 |  | 554500 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(d)
0PT51070 | Graham Switch : Replace LTC Contacts and Four Bushings on Auto #1 | Young County | Replace LTC contacts and bushings on Auto #1 at Graham Switch. | 2023-02-27 | 2023-07-28 | 2023-07-28 |  | 216119 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(d)
0PT41321 (R6257) | Rowan Creek Switch : Establish 138 kV ring bus station for a point of interconnection (POI) | Angelina County | Establish 138 kV ring bus station for a point of interconnection (POI). | 2024-02-19 | 2024-11-14 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46111 0PT48726 (R6094) | Brownsboro Sub : Rebuild substation with two transformers and three feeder breakers | City of Brownsboro, Henderson County | Rebuild station with two transformers, three feeder breakers and one feeder tie breaker. | 2024-03-01 | 2024-09-01 | [5 empty] | 0 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47141 (R6191) | Temple Elm Creek Switch: Establish new rung with two 138 kV breakers | City of Temple, Bell County | Install one 138 kV breaker as part of a new breaker-and-a-half rung. | 2024-01-05 | 2024-06-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47657 (M4328) | Desoto Switch : Upgrade existing terminal | City of Dallas, Dallas County | Upgrade existing terminal and associated equipment to meet or exceed 3200 A. | 2024-01-05 | 2024-05-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47764 0PT48860 (R3024) | Ranger Camp Switch: Establish 345 kV station | City of Colorado City, Mitchell County | Establish new station as an 18-breaker 345 kV breaker-and-a-half bus arrangement with two autotransformers. | 2023-12-04 | 2024-12-01 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49829 0PT50008 (R8658) | Lean Clay Switch: Establish 138 kV station | City of Pecos, Reeves County | Establish as a 10-breaker, 138 kV breaker-and-a-half bus arrangement with 3200 A terminals. | 2024-04-01 | 2024-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50279 (M4367) | Shorthorn POD: Establish underground termination station for two point of delivery (POD) | City of Irving, Dallas County | Establish underground termination station with two points of delivery (POD). | 2024-02-01 | 2024-12-31 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51097 0PT44941 0PT49487 (M5281) | Exchange Switch: Establish 138 kV station and install two autotransformers | City of Fort Worth, Tarrant County | Establish station as an 8-breaker 345 kV breaker-and-a-half bus arrangement and install two autotransformers. | 2024-01-15 | 2024-12-01 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51182 0PT48331 (R8680) | Catclaw Switch: Establish 138 kV station | City of Midkiff,Upton County | Establish station as a 10-breaker 138 kV breaker-and-a-half bus arrangement. | 2024-02-01 | 2024-12-01 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51662 0PT50332 (R8694) | Savanna Sub: Establish station with one 138 kV capacitor bank | City of Big Lake, Reagan County | Establish station with one 138 kV capacitor bank | 2024-03-29 | 2024-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51772 | Kirkland Park Switch : Replace one overdutied circuit breaker | City of Dallas, Dallas County | Replace one overdutied circuit breaker | 2024-03-15 | 2024-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51902 | Gainesville Sub : Replace one circuit breaker | City of Gainesville, Cooke County | Replace one circuit breaker. | 2024-02-12 | 2024-06-30 | [5 empty] | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52145 (R6277) | Sandow Switch : Transfer trip replacement, line terminal upgrade for addition, point of interconnection (POI) | Milam County | Transfer trip replacement, line terminal upgrade for addition, point of interconnection (POI) | 2024-03-08 | 2024-11-14 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52274 0PT52275 | SL Ringo Sub : Add deadends for Harting Sub | City of Big Lake, Reagan County | Add deadends for Harting Sub | 2024-04-01 | 2024-06-30 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52427 (R8709) | Raven POI : Establish 138 kV point of interconnection (POI) | City of McCaulley, Fisher County | Establish 138 kV point of interconnection (POI). | 2024-02-29 | 2024-12-13 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
CCN APPLICATIONS - APPROVED
13T80013 16T80061 | New Bethel 345 kV Loop Line | Anderson, Freestone, Navarro and Henderson Counties | This project is to construct the new double-circuit New Bethel 345 kV Line connecting the proposed New Bethel Switching station to a connection along one of four existing 345 kV transmission line segments in the region. | 2021-12-31 | 2022-12-31 |  | 26,499,000 (t-line) 7,232,000 (stations) |  |  |  |  | na | 345 | 27 | 1926.9 ACSS/TW Cumberland | Lattice Steel Towers | na | na | 160 | 13.5 | 44672 | Application Filed 7/10/2015. Administrative Approval received on 09/25/2015.
17T80077 0PT38181 0PT38182 0PT38179 0PT38178 0PT38426 (97.31%) 19T63008 0PT38517 0PT38518 0PT38372 0PT38838 (R8356) (R8429) (R8351) | Odessa EHV - Riverton and Moss - Riverton 345 kV Line | Crane, Ector, Loving, Reeves, Ward, and Winkler Counties | This project is to construct the new double-circuit 345 kV line connecting the Odessa EHV Switching Station and the Moss Switching Station to the Riverton Switching Station. | 2019-03-06 | 2020-12-20 | 2020-12-20 | 199,729,000 (t-line) 23,832,000 (stations) | 248,571,042 (t-line) 18,840,070 (stations) |  |  | 100 | 345 | 345 | 216.7 | 1926.9 ACSS/TW Cumberland | Lattice Steel Towers | 150 | 15.9 | 160 | 100.4 | 48095 | Application Filed 3/16/2018. Final Order issued on 9/17/2018.
0PT37302 0PT38601 0PT04138 0PT38858 (50%) 0PT37751 (50%) (R8428) | Owl Hills - Tunstill POD 138 kV Line | Culberson and Reeves Counties | Construct the new single-circuit 138 kV line connecting the proposed Owl Hills Substation to the Tunstill POD. | 2019-05-04 | 2020-12-10 | 2020-12-10 | 20,628,000 (t-line) 1,847,000 (stations) | 27,244,439 (t-line) 3,100,331 (stations) | 23,408,761 (t-line) 6,086,116 (station) | -3% | 100 | na | 138 | 18.7 | 1926.9 ACSS/TW Cumberland | Steel or Concrete Poles | na | na | 70 | 18.7 | 48582 | Application Filed 8/31/2018. Administrative Approval received on 11/20/2018.
NA | Stiles - Coates 138 kV Line | Reagan County | Construct the new 138 kV transmission line connecting the existing Stiles station to the proposed Coates station. | 2021-12-31 | 2023-12-31 |  | 9682000 |  |  |  | 0 | na | 138 | 8 | 959.6 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 100 | 8 | 46726 | Application Filed 1/17/2017. Final Order issued on 9/29/2017.
0PT37182 0PT40453 0PT38505 0PT38427 (95.57%) 0PT39348 0PT39349 (R8380) (R8420) | Sand Lake - Solstice 345 kV Line | Pecos, Reeves, and Ward Counties | This project is to construct the new double-circuit 345 kV line connecting the Oncor Sand Lake Switch to the AEP Texas Solstice Switch. | 2019-06-21 | 2020-12-28 | 2020-12-28 | 49,110,000 (t-line) 17,600,000 (stations) (Oncor Portion) | 68,922,778 (t-line) 22,523,721 (stations) (Oncor Portion) |  |  | 100 | na | 345 | 89 | 1926.9 ACSS/TW Cumberland | Lattice Steel Towers | na | na | 160 | 44.5 | 48785 | Application Filed 11/7/2018. Final Order issued on 6/26/2019.
0PT38174 0PT40267 0PT04144 (50%) 0PT38426 (2.69%) 0PT40670 0PT40867 (50%) (R8427) | Riverton - Kyle Ranch 138 kV Line | Loving and Reeves Counties | Construct the new single-circuit 138 kV line connecting the Riverton Switch station to the Kyle Ranch Substation. | 2020-06-08 | 2020-12-10 | 2020-12-10 | 19,207,000 (t-line) 3,040,000 (stations) | 21,226,008 (t-line) 3,301,428 (stations) |  |  | 100 | na | 138 | 15.2 | 1926.9 ACSS/TW Cumberland | Steel or Concrete Poles | na | na | 70 | 15.2 | 49304 | Application Filed 3/28/2019. Administrative Approval received on 7/17/2019. This project covers the work necessary to construct the PUCT approved route, as well as an additional three (3) miles of line between the Kyle Ranch endpoint as described in this CCN and the relocated Kyle Ranch station as described in Docket No. 49302.
0PT39531 0PT44980 0PT45164 0PT42867 (R9057) | Bearkat - Longshore 345 kV Line | Glasscock and Howard Counties | Construct the new single-circuit 345 kV line connecting the WETT Bearkat Switch to the Oncor Longshore Switch. | 2022-06-10 | 2023-12-01 |  | 29,339,500 (t-line) 1,700,000 (station) (Oncor Portion) | 34,827,900 (t-line) 1,685,394 (Station) (Oncor Portion) |  |  | 99 | na | 345 | 30.8 | 1926.9 kcmil ACSS/TW | Steel Poles or Lattice Steel Towers | na | na | 160 | 30.8 | 50410 | Application Filed 1/14/2020. Final order issued on 5/7/2021.
0PT44498 0PT04088 0PT42631 (R8384) | Kyle Ranch - Quarry Field 138 kV Line (Modification of route approved in Docket No. 49302) | Loving County | Construct the new single-circuit 138 kV line connecting the relocated Kyle Ranch Substation to the Quarry Field Switch station. | 2022-07-20 | 2022-12-15 | 2022-12-15 | 17,161,000 (t-line) | 22510282 |  |  | 100 | na | 138 | 11.3 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 11.3 | 51737 | Administrative approval received on 9/8/2021. Application Filed 2/4/2021.This project covers the work necessary to obtain PUCT approval for a modified route between the relocated Kyle Ranch station location in Docket No. 49302 and the Quarry Field switch.
0PT44880 0PT45654 0PT49192 0PT46013 0PT46133 0PT43859 0PT50737 (M4172) | Old Country Switch 345 kV Tap Line | Ellis County | Construct the new single-circuit 345 kV line connecting the proposed Old Country Switch to Oystercatcher Solar's proposed substation. | 2023-12-15 | 2024-11-14 |  | 10,392,000 (t-line) 7,825,000 (station) |  |  |  | 0 | na | 345 | 4.2 | 1926.9 ACSS/TW Cumberland | Lattice Steel Towers | na | na | 160 | 4.2 | 52455 | Application Filed 8/26/2021. Application approved on 6/30/22 and final order issued on 7/14/22.
0PT46371 0PT46696 0PT46746 0PT46984 0PT46983 0PT46728 0PT46818 0PT47825 (R8574) | Flat Iron Substation – Barr Ranch Switch – Quickriver Tap 138 kV Line | Midland County | Construct the new single-circuit 138 kV line connecting the planned Flat Iron Substation to the proposed Quickriver Tap. The new line will be routed through a proposed intermediate station called Barr Ranch Switch. | 2022-10-03 | 2023-05-30 | 2023-05-30 | 35,106,020 (t-line) 8,602,965 (station) | 31,803,179 (LINE) 9,754,393 (STATION) |  |  | 100 | na | 138 | 19 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 19 | 53491 | Application Filed 4/28/2022. Notice of approval on 8/3/2022. Completed Project scope to install single span and structure outside of Flat Iron substation to maximize crew safety from energized facilities. No further work will be performed until a Final Order is issued.
0PT45017 0PT42342 0PT42455 0PT42146 0PT50566 | Ivy League 138 kV Line | Collin County | Construct the new single-circuit 138 kV line connecting the proposed Ivy League Substation to TNMP's existing Longneck Substation. | 2023-07-23 | 2023-12-31 |  | 9,196,000 (t-line) 4,325,000 (station) | 7,481,835 (stations) |  |  | 4 | na | 138 | 2.8 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 2.8 | 53053 | Application Filed 1/18/2022. Final Order issued on 12/15/2022.
0PT49039 0PT40468 0PT41164 0PT41070 0PT49515 | Nacogdoches Southeast Switch - Redland Switch 345 kV Line | Nacogdoches and Angelina Counties | Construct the new 345 kV line in the vacant circuit position on the existing Nacogdoches Southeast Switch - Redland Switch 138 kV transmission line. | 2024-08-15 | 2024-12-31 |  | 21,502,000 (t-line) 17,123,000 (station) |  |  |  | 0 | na | 345 | 13.4 | 959.6 kcmil ACSS/TW | Lattice Steel Towers or Steel Poles | 170 | 13.4 | na | na | 54524 | Application Filed 1/12/2023. Received Notice of Approval 4/5/23
0PT49133 0PT51087 0PT51249 0PT51093 0PT51094 0PT51095 0PT51096 | Keller Wall Price - Keller Magnolia 138 kV Transmission Line and Keller Wall Price - Roanoke 138 kV Rebuild | Tarrant County | Construct the new 138 kV transmission line connecting the proposed Keller Wall Price Switch to the existing Keller Magnolia Tap; rebuild the existing 138 kV line from the Keller Wall Price Substation to the existing Keller Magnolia Tap. | 2024-01-01 | 2024-05-31 |  | 5,658,000 (t-line) 6,360,000(stations) |  |  |  | 0 | 138 | 138 | 1.2 | 1926.9 ACSS/TW Cumberland | Steel Poles | 100 | 0.3 | na | na | 54733 | Application Filed 3/23/2023. Received a Revised Notice of Approval on 6/22/23.
CCN APPLICATIONS - PENDING
0PT49056 (M5148) | Ramhorn Hill - Dunham 345 kV Transmission Line | Denton and Tarrant Counties | Construct the new double circuit 345 kV transmission line connecting the proposed Ramhorn Hill Switch to the proposed Dunham Switch on triple circuit capable structures to accommodate a future 138 kV circuit. | 2024-12-01 | 2025-12-31 |  | 175,208,000 (t-line) 74,858,000(stations) |  |  |  | 0 | na | 345 | 43.6 | 1926.9 ACSS/TW Cumberland | Steel Poles | na | na | 100 | 21.8 | 55067 | Application Filed 6/8/2023.
0PT49421 0PT46128 0PT47652 | North McCamey - Sand Lake 345 kV Line | Crane, Crockett, Pecos, Reeves, Upton, and Ward Counties | Construct the new double circuit 345 kV line connecting Oncor's existing Sand Lake Station to LCRA's existing North McCamey Station. | 2024-10-01 | 2026-05-31 |  | 159,264,500 (t-line) 5,534,000 (station) |  |  |  | 0 | na | 345 | 176.06 | 1926.9 ACSS/TW Cumberland | Lattice Steel Towers | na | na | 160 | 88.03 | 55121 | Application Filed 6/22/2023.
0PT49068 (M5281) | Exchange Switch - Keller Magnolia Substation 138 kV Transmission Line | Tarrant County | Construct the new double circuit 138 kV transmission line between the proposed Exchange Switch, the existing Alliance Substation and the existing Keller Magnolia Substation. | 2025-05-01 | 2025-12-31 |  | 16,309,000 (t-line) 49,693,000(stations) |  |  |  | 0 | na | 138 | 5.3 | 1926.9 ACSS/TW Cumberland | Steel Poles | na | na | 70 | 2.65 | 55574 | Application Filed 10/5/2023.
0PT49135 (M5144) | Exchange Switch - Roanoke Switch 138/345 kV Transmission Line Rebuild | Tarrant and Denton Counties | Rebuild the existing double circuit 345 kV transmission line between the proposed Exchange Switch and the existing Roanoke Switch and add a new 138 kV circuit. | 2025-05-01 | 2026-05-31 |  | 34,364,000 (t-line) 1,100,000(stations) |  |  |  | 0 | 345 | 138 | 7.0 (345 kV) 3.5 (138 kV) | 1926.9 ACSS/TW Cumberland (345 kV) 959.6 ACSS/TW (138 kV) | Steel Poles | 160 | 3.5 | na | na | 55575 | Application Filed 10/5/2023.
CCN APPLICATIONS - Oncor / LP&L: The following projects are being reported on behalf of Oncor and the City of Lubbock, by and through Lubbock Power & Light
0PT39835 0PT39844 0PT39623 0PT39631 0PT39632 (56.2%) (R3005) (R3002) (R3003) | Ogallala - Abernathy 345 kV Line | Castro, Hale and Swisher Counties | Construct the new single-circuit 345 kV line connecting the existing Ogallala station to the existing Abernathy station. This project is part of the LP&L integration into the ERCOT system. | 2020-01-15 | 2021-06-21 | 2021-06-21 | 87,876,048 (t-line) 8,304,600 (stations) | 88,807,431 (t-line) 9,122,137 (stations) |  |  | 100 | na | 345 | 57.9 | 959.6 kcmil ACSS/TW | Steel Poles or Lattice Steel Towers | na | na | 175 | 57.9 | 48625 | Application Filed 9/6/2018. Final Order issued on 9/26/2019.
0PT39896 0PT40341 0PT39625 0PT41983 0PT39632 (25.7%) 0PT39633 (55.3%) 0PT40608 0PT44515 0PT44516 (R3008) (R3003) (R3001) | Abernathy - Wadsworth 345 kV Line | Hale and Lubbock Counties | Construct the new single-circuit 345 kV line connecting the existing Abernathy station to the existing Wadsworth station. This project is part of the LP&L integration into the ERCOT system. | 2020-01-15 | 2021-05-12 | 2021-05-12 | 56,736,759 (t-line) 9,403,700 (stations) | 56,702,358 (t-line) 9,635,269 (stations) |  |  | 100 | na | 345 | 32.9 | 959.6 kcmil ACSS/TW | Steel Poles or Lattice Steel Towers | na | na | 175 | 32.9 | 48668 | Application Filed 9/20/2018. Final Order issued on 10/14/19. This is a Sharyland acquired project for the LP&L ERCOT integration. Originally filed under the NTU predecessor report.
0PT39845 0PT41440 0PT41442 0PT39634 0PT39635 0PT39628 0PT39626 0PT41832 0PT39633 (44.7%) 0PT41847 0PT44486 0PT44487 (R3006) (R3004) (R3010) (R3009) (R3001) | Wadsworth - New Oliver - Farmland 345 kV Line (WNF) | Lubbock and Lynn Counties | Construct the new single-circuit 345 kV line connecting the existing Wadsworth station to the existing Farmland station, routed through one of two options for the proposed New Oliver station. This project is part of the LP&L integration into the ERCOT system. | 2020-03-24 | 2021-05-15 | 2021-05-15 | 67,769,000 (t-line) 20,638,000 (stations) | 77,538,361 (t-line) 24,168,146 (stations) |  |  | 100 | na | 345 | 41.9 | 959.6 kcmil ACSS/TW | Steel Poles or Lattice Steel Towers | na | na | 175 | 41.9 | 48909 | Application Filed 12/19/2018. Originally filed under the NTU predecessor report. Final Order issued on 1/23/20. This is a Sharyland acquired project for the LP&L ERCOT integration. Originally filed under the NTU predecessor report.
0PT39845 0PT41452 0PT39732 0PT39967 0PT39629 0PT39630 (R3006) (R3001) (R3014) (R3013) | Southeast - New Oliver - Oliver 115 kV Line (SNO) | Lubbock County | Construct the new single-circuit 115 kV line connecting the existing Southeast station to the existing Oliver station, routed through one of two options for the proposed New Oliver station. This project is part of the LP&L integration into the ERCOT system. | 2020-01-20 | 2021-05-15 | 2021-05-15 | 20,688,000 (t-line) 31,248,000 (stations) | 21,452,317 (t-line) 27,949,110 (stations) |  |  | 100 | na | 115 | 17.8 | 959.6 kcmil ACSS/TW | Steel Pole | na | na | 60 | 17.8 |  | Application Filed 12/19/2018. Originally filed under the NTU predecessor report. Final Order issued on 1/23/20. This is a Sharyland acquired project for the LP&L ERCOT integration. Originally filed under the NTU predecessor report.
0PT39846 0PT41891 0PT39637 0PT39968 0PT39636 0PT41986 0PT39632 (18.1%) 0PT44518 0PT44519 (R3007) (R3011) (R3003) | Abernathy - North - North Loop 345/115 kV Line | Hale and Lubbock Counties | Construct the new transmission line connecting the existing Abernathy station to the northern portion of LP&L's planned 115 kV loop line, routed through one of three options for the proposed North station. Depending on which North station is used, this line will be either a single-circuit 345 kV line or a combination of single-circuit 345 kV and double-circuit 115 kV line. This project is part of the LP&L integration into the ERCOT system. | 2019-12-21 | 2021-05-16 | 2021-05-16 | 39,782,000 (t-line) 33,367,000 (stations) | 44,361,677 (t-line) 20,274,578 (stations) |  |  | 100 | na | 115/345 | 34.3 | 959.6 kcmil ACSS/TW | Steel Poles or Lattice Steel Towers (345 kV) Steel Poles (115 kV) | na | na | 175 (345 kV) 60 (115 kV) | 24.6 | 49151 | Application Filed 2/19/2019. Final Order issued on 3/12/2020. Originally filed under the NTU predecessor report. Project was inadvertently overwritten by a duplicate project last month and is being re-added.

## EntryInstructions
General Instructions for Entering Information
1. Please use "na" whenever appropriate to reduce ambiguity, except in the "Costs," "Percent Complete," and "Percent Variance" columns. 2. Any new or revised entry must be entered using a red font and highlighted in yellow. In the month following the red font entry, change the previous month's red entries back to black and make any new entries for the new month in red. This aids PUCT staff in quickly identifying any changes from the previous month's report. 3. On the final monthly report on an existing line in which one of the attributes as listed in the attribute spreadsheets below has changed, enter that data in a bolded green font.
Utility's Project Number | Enter the Utility's Project Number. No duplicate numbers are allowed in this column.
Project Name | Enter the name of the project. If possible, use the same name as was reported to ERCOT in any reports.
Location (City/County) | Enter the names of the counties where the project is located. Also enter the names of cities, if appropriate. Please delineate all county and city names with commas only. (e.g., Liberty, Chambers, Anahuac, etc.)
Description | Describe the project in enough detail to allow the Commission to ensure that the work does not require a CCN, if the utility does not intend to apply for a CCN. Include any significant or relevant detail not being reported in other columns. Do not include Point of Delivery and add periods to all sentences.
Estimated (or Actual) Start Date | Enter the estimated project starting date. When construction begins, please replace the estimated date with the actual date of the start of construction
Finish Date (Construction Complete) | Enter the date (mm/dd/yy) when the construction related to the project has been completed.
Date Energized (If Applicable) | Enter the date (mm/dd/yy) the project was energized or restored to service (if applicable).
Initial Estimated Project Cost | CCN Projects Only: Enter the estimated cost from the CCN application. When reporting both T-Line and Substation Costs, enter them separately in the same cell. (e.g., "$3,946,000 T-Line; $1,768,000 Substation") This number shall not be changed in future months unless the Application is amended. Please DO NOT use links to other sheets within the workbook. Non-CCN Projects Only: No entry is needed; Enter the estimated cost in the
Final Estimated Project Cost | CCN Projects: Enter the latest available estimated cost for the month that construction starts. This number shall not be changed after construction begins. and a cost variance explanation is not required unless requested by PUC Staff For Non-CCN Projects: Enter the initial estimated cost. Estimate revisions are not necessary
Final Actual Project Cost | Enter the actual, final project cost after the project has been energized and all costs have been recorded. Omit the project from all following reports.
% Variance | The cells contain a formula for calculating the percent variance of the final actual cost with respect to the final estimated cost. This is essentially a calculation of the percent of the cost over-run or under-run. Please do not change these cells.
Percent Complete | State the construction progress of the project as a percent. Please use only an integer and do not write"%." Do not report the percent of money spent.
Existing Voltage | Enter the nominal system existing voltage, if any. In the event of a voltage upgrade, this will be the "before" voltage. If the project is for a new line, enter "na." For projects involving multiple voltages, please delineate the voltages by a comma, (e.g., "69,138"). Please do not write "volts."
Upgraded or New Voltage | Enter the nominal system voltage after upgrading or if new line construction is involved. Please use the same practices described in the "Existing Voltage" column. Please do not write "volts."
Circuit Length (Miles) | Enter the total circuit length. Example: For a new double-circuit line using 10 miles of new ROW, the circuit length would be 20 miles. Please enter only a number, if possible. Please do not write "miles."
Conductor Type & Size & Bundling | Describe the conductor characteristics, including whether double or single circuit or mixed. Lengthy explanations shall be made in the Project Description column. (Format should be Quantity - Conductor Size and Type). Do not include quotations for supplier given code words or the word bundled.
Structure Type(s) | Describe structure types and materials used.
Existing ROW Width (Feet) | Enter width of existing ROW. The entry type is unrestricted. If the project is only for new line and no old ROW exists, enter "na." Entries such as "60,80,100" or "60 - 100" or "centerline" are permissible. Make detailed explanations, if needed, elsewhere. Please do not write "feet."
Existing ROW Length (Miles) | Enter length of existing ROW. The entry type is unrestricted. If the project is only for new line and no old ROW exists, enter "na." Make detailed explanations, if needed, elsewhere. Please do not write "miles."
New ROW Width (Feet) | Enter width of new ROW. The entry type is unrestricted. Entries such as "60,80,100" or "60 - 100" or "centerline" or "railroad" or "street" are permissible. Make detailed explanations, if needed, elsewhere. Please do not write "feet."
New ROW Length (Miles) | Enter new (additional) ROW length, in miles. Please do not write "miles."
Rule Section or PUC Control Number | Enter the PUC Substantive Rule 25.101 section(s) which are applicable. For multiple section applicability, please delineate by commas, e.g., "25.101(c)(5)(A), 25.101(c)(5)(B)" for a project incorporating a line extension (A) and a voltage upgrade on the existing line which is being extended (B). If the project involves a CCN Application, enter ONLY the .5-digit control number. Please do not write "docket," "CCN" or other text, except when needed in citing Rule 25.101. Should the project include work done under both CCN and 25.101(c)(5), follow the same practices and delineate with commas.
Comments | Enter information not included elsewhere, including reimbursed costs. A cost variance explanation is no longer required for non-CCN projects. However, utilities will be required to submit a Cost Analysis only for CCN Projects. See Note below.
139510
0PT39030 SB

## 16T80061 & 16T64136
Project No. 16T80061 & 16T64136 - New Bethel 345 kV Loop Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 1963) | Estimated cost once a route is approved and CCN granted (Route 1963) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 2952000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 601000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 2959000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 8324000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 11663000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 26499000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 26499000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | N/A | N/A
Engineering and Design (Utility) | 0 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 499000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 3341000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 338000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 2467000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 6645000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 587000 | Costs not yet available | Costs not yet available
Estimated Project Total | 7232000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 33731000
139510
0PT39030 SB |  | City of Tyler, Bell County

## 17T80077
Project No. 17T80077, 0PT38181, 0PT38182, 0PT38179, 0PT38178, 0PT38426, 19T63008, 0PT38517, 0PT38518 - Odessa EHV - Riverton and Moss - Riverton 345 kV Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 1180) | Estimated cost once a route is approved and CCN granted (Route 1180) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 21540000 | 29205738 | Costs not yet available
Engineering and Design (Utility) | 5322000 | 0 | Costs not yet available
Engineering and Design (Contract) | 2269000 | 2877377 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 74495000 | 76498142 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 96103000 | 103610002 | Costs not yet available
Estimated Total Cost | 199729000 | 212191259 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 36379783 | Costs not yet available
Estimated Project Total | 199729000 | 248571042 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | N/A
Engineering and Design (Utility) | 245000 | 166800 | Costs not yet available
Engineering and Design (Contract) | 922857 | 908706 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 15969607 | 9781320 | Costs not yet available
Construction of Facilities (Utility) | 2270494 | 479109 | Costs not yet available
Construction of Facilities (Contract) | 4424042 | 5436125 | Costs not yet available
Estimated Total Cost | 23832000 | 0 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 2068010 | Costs not yet available
Estimated Project Total | 23832000 | 18840070 | Costs not yet available
Reported on Monthly Construction Report | 223561000 | 267411112
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT37302
Project No. OPT37302, 0PT38601 - Owl Hills - Tunstill POD 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 15) | Estimated cost once a route is approved and CCN granted (Route 15) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1769000 | 4038047 | Costs not yet available
Engineering and Design (Utility) | 607000 | 0 | Costs not yet available
Engineering and Design (Contract) | 830000 | 3505474 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 5734000 | 8210994 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 11688000 | 11489924 | Costs not yet available
Estimated Total Cost | 20628000 | 27244439 | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | Costs not yet available
Estimated Project Total | 20628000 | 27244439 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | N/A | N/A
Engineering and Design (Utility) | 90000 | 0 | Costs not yet available
Engineering and Design (Contract) | 0 | 14301 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 1250000 | 1862654.45 | Costs not yet available
Construction of Facilities (Utility) | 155000 | 309438.41 | Costs not yet available
Construction of Facilities (Contract) | 352000 | 913937.48 | Costs not yet available
Estimated Total Cost | 1847000 | 3100331.34 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 1847000 | 3100331.34 | Costs not yet available
Reported on Monthly Construction Report | 22475000 | 30344770.34
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT37182
Project No. 0PT37182, 0PT40453, OPT38505, 0PT38427- Sand Lake - Solstice 345 kV Line - Transmission Line Project
*THIS IS A JOINT PROJECT WITH AEP TEXAS - ALL COSTS SHOWN IN TABLE BELOW ARE ONCOR'S PORTION OF THE PROJECT
| Estimated cost included in CCN Application (Route 320) | Estimated cost once a route is approved and CCN granted (Modified Route 320) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 4561500 | 10739693 | Costs not yet available
Engineering and Design (Utility) | 1058500 | 694256 | Costs not yet available
Engineering and Design (Contract) | 1348000 | 1105909 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 16793500 | 13285278 | Costs not yet available
Construction of Facilities (Utility) | 500 | 0 | Costs not yet available
Construction of Facilities (Contract) | 25348000 | 38847631 | Costs not yet available
Estimated Total Cost | 49110000 | 64672767 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 4250011 | Costs not yet available
Estimated Project Total | 49110000 | 68922778 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | N/A
Engineering and Design (Utility) | 0 | 0 | Costs not yet available
Engineering and Design (Contract) | 400000 | 444635 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 13200000 | 17005560 | Costs not yet available
Construction of Facilities (Utility) | 1210000 | 1065160 | Costs not yet available
Construction of Facilities (Contract) | 2026000 | 4008366 | Costs not yet available
Estimated Total Cost | 16836000 | 22523721 | Costs not yet available
Other (all costs not included in the above categories) | 764000 | 0 | Costs not yet available
Estimated Project Total | 17600000 | 22523721 | Costs not yet available
Reported on Monthly Construction Report | 66710000 | 91446499
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT38174
Project No. 0PT38174 ,0PT40267, 0PT38426 & 0PT04144 - Riverton - Kyle Ranch 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 7) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1694000 | 2387508 | Costs not yet available
Engineering and Design (Utility) | 517000 | 1258500 | Costs not yet available
Engineering and Design (Contract) | 876000 | 1300000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4866000 | 7416500 | Costs not yet available
Construction of Facilities (Utility) | 0 | 708500 | Costs not yet available
Construction of Facilities (Contract) | 11254000 | 8155000 | Costs not yet available
Estimated Total Cost | 19207000 | 21226008 | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | Costs not yet available
Estimated Project Total | 19207000 | 21226008 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 70000 | 194717 | Costs not yet available
Engineering and Design (Utility) | 0 | 115906.71 | Costs not yet available
Engineering and Design (Contract) | 200000 | 13288.25 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 1900000 | 1852954.57 | Costs not yet available
Construction of Facilities (Utility) | 120000 | 0 | Costs not yet available
Construction of Facilities (Contract) | 750000 | 1124561.47 | Costs not yet available
Estimated Total Cost | 3040000 | 3301428 | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | Costs not yet available
Estimated Project Total | 3040000 | 3301428 | Costs not yet available
Reported on Monthly Construction Report | 22247000 | 24527436
139510
0PT39030 SB |  | City of Tyler, Bell County

## NA
Project No. NA - Stiles - Coates 138 kV Line - NTU Transmission Line Project
| Estimated cost included in CCN Application (Route B4) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 3347000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 249000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 733000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 2070000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 222000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 2915000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 9536000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 146000 | Costs not yet available | Costs not yet available
Estimated Project Total | 9682000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 161000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 84000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 893000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4376000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 432000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 2780000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 8726000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 8726000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 18408000 | Costs not yet available
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT39835
Project No. 0PT39835, 0PT39623, 0PT39631, 0PT39632 - Ogallala - Abernathy 345 kV Line - NTU Transmission Line Project (Dkt. 48625)
| Estimated cost included in CCN Application (Route 4) | Estimated cost once a route is approved and CCN granted (Route 4a) | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 13575702 | 14502458.3192 | Costs not yet available
Engineering and Design (Utility) | 165760 | 186171.1163 | Costs not yet available
Engineering and Design (Contract) | 3430680 | 3126596.9787 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 35371142 | 33506760.9081 | Costs not yet available
Construction of Facilities (Utility) | 356601 | 0 | Costs not yet available
Construction of Facilities (Contract) | 34795274 | 37485443.6777 | Costs not yet available
Estimated Total Cost | 87695159 | 88807431 | Costs not yet available
Other (all costs not included in the above categories) | 180889 | 0 | Costs not yet available
Estimated Project Total | 87876048 | 88807431 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | Costs not yet available
Engineering and Design (Utility) | 0 | 0 | Costs not yet available
Engineering and Design (Contract) | 507200 | 441197.96 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4883800 | 4431568.67 | Costs not yet available
Construction of Facilities (Utility) | 0 | 302334.32 | Costs not yet available
Construction of Facilities (Contract) | 2913600 | 3947036.33 | Costs not yet available
Estimated Total Cost | 8304600 | 9122137.28 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 8304600 | 9122137.28 | Costs not yet available
Reported on Monthly Construction Report | 96180648 | 97929568.28
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT39896
Project No. 0PT39896 - Abernathy - Wadsworth 345 kV Line - NTU Transmission Line Project (Dkt. 48668)
| Estimated cost included in CCN Application (Route 1) | Estimated cost once a route is approved and CCN granted (Route 1) | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 7979470 | 9543014.7112 | Costs not yet available
Engineering and Design (Utility) | 110471 | 150723.6435 | Costs not yet available
Engineering and Design (Contract) | 1917538 | 1785293.9269 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 21275928 | 19474125.3795 | Costs not yet available
Construction of Facilities (Utility) | 202943 | 0 | Costs not yet available
Construction of Facilities (Contract) | 25127504 | 25749200.3389 | Costs not yet available
Estimated Total Cost | 56613854 | 56702358 | Costs not yet available
Other (all costs not included in the above categories) | 122905 | 0 | Costs not yet available
Estimated Project Total | 56736759 | 56702358 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 77935 | Costs not yet available
Engineering and Design (Utility) | 0 | 0 | Costs not yet available
Engineering and Design (Contract) | 605500 | 359797 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 5266900 | 4710275.06 | Costs not yet available
Construction of Facilities (Utility) | 0 | 236755.19 | Costs not yet available
Construction of Facilities (Contract) | 3531300 | 4250506.42 | Costs not yet available
Estimated Total Cost | 9403700 | 9635268.67 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 9403700 | 9635268.67 | Costs not yet available
Reported on Monthly Construction Report | 66140459 | 66337626.67

## 0PT39845
Project No. 0PT39845 - Wadsworth - New Oliver - Farmland 345 kV Line (WNF) and Southeast - New Oliver - Oliver 115 kV Line (SNO) - NTU Transmission Line Projects (Dkt. 48909)
| Wadworth - New Oliver - Farmland 345 kV Line |  |  |  | Southeast - New Oliver - Oliver 115 kV Line
| Estimated cost included in CCN Application (Route 20) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 12 months after construction is complete |  | Estimated cost included in CCN Application (Route 9) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs: |  | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 8257000 | 11775886.9771 | Costs not yet available | Right-of-Way and Land Acquisition | 4471000 | 5164970.0609 | Costs not yet available
Engineering and Design (Utility) | 117000 | 178363.3316 | Costs not yet available | Engineering and Design (Utility) | 120000 | 62760.5556 | Costs not yet available
Engineering and Design (Contract) | 2794000 | 3791870.5499 | Costs not yet available | Engineering and Design (Contract) | 1530000 | 1649065.0706 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 27393000 | 27464811.7198 | Costs not yet available | Procurement of Material & Equipment (including Stores) | 4298000 | 5126788.2332
Construction of Facilities (Utility) | 314000 | 0 | Costs not yet available | Construction of Facilities (Utility) | 216000 | 0 | Costs not yet available
Construction of Facilities (Contract) | 28726000 | 34327428.4216 | Costs not yet available | Construction of Facilities (Contract) | 9921000 | 9448733.0797 | Costs not yet available
Estimated Total Cost | 67601000 | 77538361 | Costs not yet available | Estimated Total Cost | 20556000 | 21452317 | Costs not yet available
Other (all costs not included in the above categories) | 168000 | 0 | Costs not yet available | Other (all costs not included in the above categories) | 132000 | 0 | Costs not yet available
Estimated Project Total | 67769000 | 77538361 | Costs not yet available | Estimated Project Total | 20688000 | 21452317 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities |  | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 564000 | 1376048 | Costs not yet available | Right-of-Way and Land Acquisition | 0 | 152894.2 | Costs not yet available
Engineering and Design (Utility) | 0 | 21830.19 | Costs not yet available | Engineering and Design (Utility) | 105000 | 27328.31 | Costs not yet available
Engineering and Design (Contract) | 1617000 | 1000798.39 | Costs not yet available | Engineering and Design (Contract) | 1075000 | 635862.34 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 10517000 | 10394558.73 | Costs not yet available | Procurement of Material & Equipment (including Stores) | 25465000 | 21705484.59 | Costs not yet available
Construction of Facilities (Utility) | 0 | 497613.72 | Costs not yet available | Construction of Facilities (Utility) | 170000 | 523401.98 | Costs not yet available
Construction of Facilities (Contract) | 7940000 | 10877297.09 | Costs not yet available | Construction of Facilities (Contract) | 4433000 | 4904138.78 | Costs not yet available
Estimated Total Cost | 20638000 | 24168146.12 | Costs not yet available | Estimated Total Cost | 31248000 | 27949110.2 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available | Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 20638000 | 24168146.12 | Costs not yet available | Estimated Project Total | 31248000 | 27949110.2 | Costs not yet available
Reported on Monthly Construction Report | 88407000 | 101706507.12 | Costs not yet available | Reported on Monthly Construction Report | 51936000 | 49401427.2 | Costs not yet available

## 0PT39846
Project No. 0PT39846 - Abernathy - North - North Loop 345/115 kV Line - NTU Transmission Line Project (Dkt. 49151)
| Estimated cost included in CCN Application (Route 25) | Estimated cost once a route is approved and CCN granted (Route X) | Approximately 12 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 4871000 | 8342781.3539 | Costs not yet available
Engineering and Design (Utility) | 237000 | 95753.4343 | Costs not yet available
Engineering and Design (Contract) | 2720000 | 1799694.4634 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 13414000 | 14554335.7083 | Costs not yet available
Construction of Facilities (Utility) | 230000 | 0 | Costs not yet available
Construction of Facilities (Contract) | 18124000 | 19569112.0401 | Costs not yet available
Estimated Total Cost | 39596000 | 44361677 | Costs not yet available
Other (all costs not included in the above categories) | 186000 | 0 | Costs not yet available
Estimated Project Total | 39782000 | 44361677 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 300000 | Costs not yet available
Engineering and Design (Utility) | 115000 | 0 | Costs not yet available
Engineering and Design (Contract) | 2141000 | 610437.2 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 21621000 | 13689359.68 | Costs not yet available
Construction of Facilities (Utility) | 150000 | 506821.26 | Costs not yet available
Construction of Facilities (Contract) | 9340000 | 5167959.8 | Costs not yet available
Estimated Total Cost | 33367000 | 20274577.94 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 33367000 | 20274577.94 | Costs not yet available
Reported on Monthly Construction Report | 73149000 | 64636254.94

## 0PT39531
Project No. 0PT39531 - Bearkat (WETT) - Longshore 345 kV Line Transmission Line Project
*THIS IS A JOINT PROJECT WITH WETT - ALL COSTS SHOWN IN TABLE BELOW ARE ONCOR'S PORTION OF THE PROJECT
| Estimated cost included in CCN Application (Route 102) | Estimated cost once a route is approved and CCN granted (Route 69) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 3125500 | 4344273.75 | Costs not yet available
Engineering and Design (Utility) | 771500 | 807985.51 | Costs not yet available
Engineering and Design (Contract) | 1170000 | 2952589 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 8803500 | 11251734.71 | Costs not yet available
Construction of Facilities (Utility) | 0 | 31875 | Costs not yet available
Construction of Facilities (Contract) | 15469000 | 15596226.81 | Costs not yet available
Estimated Total Cost | 29339500 | 34984684.78 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 29339500 | 34984684.78 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | N/A
Engineering and Design (Utility) | 0 | 0 | Costs not yet available
Engineering and Design (Contract) | 150000 | 150000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 810000 | 810000 | Costs not yet available
Construction of Facilities (Utility) | 60000 | 60000 | Costs not yet available
Construction of Facilities (Contract) | 390000 | 390000 | Costs not yet available
Estimated Total Cost | 1410000 | 1410000 | Costs not yet available
Other (all costs not included in the above categories) | 290000 | 275394.44 | Costs not yet available
Estimated Project Total | 1700000 | 1685394.44 | Costs not yet available
Reported on Monthly Construction Report | 31039500 | 34984684.78 | Costs not yet available

## 0PT44498
Project No. 0PT44498, 0PT04088, 0PT42631 - Kyle Ranch - Quarry Field 138 kV Line - Transmission Line Project (Modification Of Route Approved In Docket No. 49302)
| Estimated cost included in CCN Application (Modified Route) | Estimated cost once a route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1260000 | 2265599.4 | Costs not yet available
Engineering and Design (Utility) | 386000 | 134847.1 | Costs not yet available
Engineering and Design (Contract) | 827000 | 974166.61 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4077000 | 8868772.83 | Costs not yet available
Construction of Facilities (Utility) | 0 | 277.24 | Costs not yet available
Construction of Facilities (Contract) | 10611000 | 10266619.29 | Costs not yet available
Estimated Total Cost | 17161000 | 22510282.47 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 17161000 | 22510282.47 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | 0
Engineering and Design (Utility) | 0 | 0 | 0
Engineering and Design (Contract) | 0 | 0 | 0
Procurement of Material & Equipment (including Stores) | 0 | 0 | 0
Construction of Facilities (Utility) | 0 | 0 | 0
Construction of Facilities (Contract) | 0 | 0 | 0
Estimated Total Cost | 0 | 0 | 0
Other (all costs not included in the above categories) | 0 | 0 | 0
Estimated Project Total | 0 | 0 | 0
Reported on Monthly Construction Report | 17161000 | 22510282.47 | Costs not yet available
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT44880
Project No. 0PT44880 - Old Country Switch 345 kV Tap Line - Transmission Line Project
| Estimated cost included in CCN Application - Route 54 | Estimated cost included in CCN Application of PUC Approved Route 152 | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1765000 | 2315000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 153000 | 199000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 1470000 | 1499000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 1842000 | 2336000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 5162000 | 6389000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 10392000 | 12738000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | Costs not yet available | Costs not yet available
Estimated Project Total | 10392000 | 12738000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 393000 | 393000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 584000 | 584000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 370000 | 370000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 3491000 | 3491000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 351000 | 351000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 2636000 | 2636000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 7825000 | 7825000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | Costs not yet available | Costs not yet available
Estimated Project Total | 7825000 | 7825000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 18217000 | 20563000 | Costs not yet available | Costs not yet available

## 0PT45017
Project No. 0PT45017, 0PT42342, 0PT42455, 0PT42146 - Ivy League Substation 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application - Route 4626 | Estimated cost included in CCN Application of PUC Approved Route 4626 | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 2096000 | 2096000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 135000 | 135000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 1536000 | 1536000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 1978000 | 1978000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 3451000 | 3451000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 9196000 | 9196000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 9196000 | 9196000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 100000 | 100000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 339000 | 339000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 42000 | 42000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 2151000 | 2151000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 78000 | 78000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 1615000 | 1615000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 4325000 | 4325000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 4325000 | 4325000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 13521000 | 13521000 | Costs not yet available | Costs not yet available

## 0PT46371
Project No. 0PT46371,0PT46696, 0PT46746, 0PT46984,0PT46983, 0PT46728, 0PT46818, 0PT47825 - Flat Iron Substation - Barr Ranch Switch - Quickriver Tap 138 kV Line - Transmission Line Project
| Estimated cost included in CCN | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1244020 | 1492400 | Costs not yet available
Engineering and Design (Utility) | 693000 | 40000 | Costs not yet available
Engineering and Design (Contract) | 862000 | 1525936 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 11657000 | 11914352 | Costs not yet available
Construction of Facilities (Utility) | 120000 | 0 | Costs not yet available
Construction of Facilities (Contract) | 20530000 | 16830491 | Costs not yet available
Estimated Total Cost | 35106020 | 31803179 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 35106020 | 31803179 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 101230 | 110656 | Costs not yet available
Engineering and Design (Utility) | 0 | 337736 | Costs not yet available
Engineering and Design (Contract) | 525000 | 1532505 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 3437408 | 3674205 | Costs not yet available
Construction of Facilities (Utility) | 423700 | 0 | Costs not yet available
Construction of Facilities (Contract) | 4115627 | 4099291 | Costs not yet available
Estimated Total Cost | 8602965 | 9754393 | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | Costs not yet available
Estimated Project Total | 8602965 | 9754393 | Costs not yet available
Reported on Monthly Construction Report | 43708985 | Costs not yet available | Costs not yet available

## 0PT49039
Project No. 0PT49039, 0PT40468, 0PT41164, 0PT41070 - Nacogdoches SE Switch - Redland Switch 345 kV Line - Transmission Line Project
| Estimated cost included in CCN | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 201000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 25000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 1576000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 5354000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 14346000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 21502000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 21502000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 0 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 994000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 8123000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 587000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 7419000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 17123000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 17123000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 38625000 | Costs not yet available | Costs not yet available

## 0PT49133
Project No. 0PT49133 - Keller Wall Price – Keller Magnolia 138 kV Transmission Line Project (“KWP-KM”) and Keller Wall Price – Roanoke 138 kV Rebuild Project (“KWP-R”)
| Estimated cost included in CCN Application |  | Estimated cost once the route is approved and CCN granted |  | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: |  | Initial Estimated Project Costs: |  | Final Estimated Project Costs:
| KWP- KM | KWP - R | KWP- KM | KWP - R | KWP- KM | KWP - R
Right-of-Way and Land Acquisition | 17000 | 0 | 17000 | 0 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 30000 | 30000 | 30000 | 30000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 1079000 | 229000 | 1079000 | 229000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 880000 | 647000 | 880000 | 647000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | 0 | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 1376000 | 1370000 | 1376000 | 1370000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 3382000 | 2276000 | 3382000 | 2276000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | 0 | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 5658000 |  | 5658000 |  | Costs not yet available
| Substation Facilities |  | Substation Facilities |  | Substation Facilities
Right-of-Way and Land Acquisition | 0 |  | 0 |  | Costs not yet available
Engineering and Design (Utility) | 0 |  | 0 |  | Costs not yet available
Engineering and Design (Contract) | 275000 |  | 275000 |  | Costs not yet available
Procurement of Material & Equipment (including Stores) | 3290000 |  | 3290000 |  | Costs not yet available
Construction of Facilities (Utility) | 250000 |  | 250000 |  | Costs not yet available
Construction of Facilities (Contract) | 2545000 |  | 2545000 |  | Costs not yet available
Estimated Total Cost | 6360000 |  | 6360000 |  | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | 0 |  | Costs not yet available
Estimated Project Total | 6360000 |  | 6360000 |  | Costs not yet available
Reported on Monthly Construction Report | 12018000 |  | 12018000 |  | Costs not yet available

## 0PT49056
Project No. 0PT49056 - Ramhorn Hill Switch - Dunham Switch 345 kV Transmission Line Project
| Estimated cost included in CCN Application - Route 179 | Estimated cost included in CCN Application of PUC Approved Route | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 56996000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 309000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 6099000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 60597000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 51207000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 175208000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 175208000 | Costs not yet available | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 25458000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 1000000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 23140000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 500000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 24760000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 74858000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 74858000 | Costs not yet available | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 250066000 | Costs not yet available | Costs not yet available | Costs not yet available

## 0PT49421
Project No. 0PT49421 - North McCamey (LCRA) - Sand Lake (Oncor) 345 kV Transmission Line Project
| Estimated cost included in CCN Application - Route 65 | Estimated cost included in CCN Application of PUC Approved Route | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs*: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 8524500 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 167500 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 6288000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 58462000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 85822500 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 159264500 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 159264500 | Costs not yet available | Costs not yet available | Costs not yet available
| Substation Facilities** | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 200000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 3320000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 200000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 1814000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 5534000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 5534000 | Costs not yet available | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 164798500 | Costs not yet available | Costs not yet available | Costs not yet available
*This is a joint project with LCRA. The transmission line costs shown here are the filed transmission line costs for Route 65 divided by 2.
** Oncor substation costs that were filed with the CCN application. Does not include LCRA substation costs.

## 0PT50023
Project No. 0PT50023 - Lufkin Switch - Redland Switch 345 kV Transmission Line Project
| Estimated cost included in CCN Application - Route 6 | Estimated cost included in CCN Application of PUC Approved Route | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 3699000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 609000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 2092000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 6398000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 16452000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 29250000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 29250000 | Costs not yet available | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 472000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 3671000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 371000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 3738000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 8252000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 8252000 | Costs not yet available | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 37502000 | Costs not yet available | Costs not yet available | Costs not yet available

## 0PT49068
Project No. 0PT49068 - Exchange Switch - Keller Magnolia Sub 138 kV Transmission Line Project
| Estimated cost included in CCN Application - Route 339 | Estimated cost included in CCN Application of PUC Approved Route | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 2435000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 115000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 2015000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4752000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 51207000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 60524000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 60524000 | Costs not yet available | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
| Includes Exchange Sw & Keller Magnolia Sub | Includes Exchange Sw & Keller Magnolia Sub | Includes Exchange Sw & Keller Magnolia Sub | Includes Exchange Sw & Keller Magnolia Sub
Right-of-Way and Land Acquisition | 7080000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 853000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 23305000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 1700000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 16755000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 49693000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 49693000 | Costs not yet available | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 110217000 | Costs not yet available | Costs not yet available | Costs not yet available

## 0PT49135
Project No. 0PT49135 - Exchange Switch - Roanoke Switch 138/345 kV Transmission Line Rebuild Project
| Estimated cost included in CCN | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 684000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 92000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 1772000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 12315000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 19501000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 34364000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 34364000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 50000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 150000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 435000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 465000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 1100000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 1100000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 35464000 | Costs not yet available | Costs not yet available