## MonthlyReportForm-AEPTX Central
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
41913060 | TPCO Dupont Station Relay Upgrades | San Patricio | Dupont Substation Relay/Protection | 2014-10-01 | 2019-10-21 |  |  | 879000 |  |  | 66 | [9 empty] | 16 TAC 25.83(a)(3)
42502134 | Harlingen SS - Raymondville #2 69-kV Rebuild | Cameron Willacy | Rebuild 22.50 miles of 69-kV transmission line 138-kV capability & partial relocation pursuant to previous contractual obligations. | 2017-03-10 | 2017-11-01 | 2017-11-21 |  | 23646065 |  |  | 99 | 69 |  | 22.81 | 959.6 ACSS/TW | Steel Mono Pole | varies | 22.81 | 100 | 1.72 | 16 TAC 25.101 (c)(5)(B) & 16 TAC 25.101 (c)(5)(E) | Landowners Noticed. Consent and new easements & supplements were acquired as necessary.
42499311 | El Campo Station | Wharton | Replace relays (in conjunction w/ Project No. 42501676). | 03/15/2018 | 05/15/2018 |  |  | 6251145.51 |  |  | 75 | 138/69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42501676 | Lane City Station | Wharton | Replace EM Relays and assoc Panel on 138-kV CB 6485 and PVDs relays (in conjunction w/ Project No. 42499311). | 03/15/2018 | 05/15/2018 | 10/28/2018 |  | 1163678 | 1607981 | 38.18% | 100 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42612169 | Westside Substation | Corpus Christi/Nueces | Upgrade breaker and switches. | 2017-11-02 | 03/31/2019 |  |  | 2624458 |  |  | 80 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42623730 | West Oso Substation | Corpus Christi/Nueces | Upgrade breaker and switches. | 11/20/2017 | 02/28/2019 |  |  | 501084 |  |  | 15 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42657137 | Pharr Station Expansion | Pharr/Hidalgo | Expand Station: Add (3) 138-kV breakers, (6) CCVT's, (6) 138-kV arrestors, bus work, deadends, and metering which will provide two independent 138-kV feeds to the ABB STATCOM. Install fourth ring to accommodate the SVC connections. | 2018-02-15 | 2018-12-31 |  |  | 3334240 |  |  | 99 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Within acquired station property
42585400 | Pharr SVC Station | Pharr/Hidalgo | Construct SVC station on new land purchased adjacent to existing station. Install two +150/-75 MVAR SVCs for a total of +300/-150 MVAR. | 2018-01-01 | 2018-12-31 |  |  | 39572390 |  |  | 99 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property purchased
42652433 | Pharr SVC Bus Tie #1 | Pharr/Hidalgo | Construct bus tie #1 from existing 138-kV Pharr substation to SVC Yard. | 2018-02-15 | 2018-12-31 |  |  | 614918 |  |  | 99 |  | 138 | 0.15 | 959.6 ACSS/TW | Steel Mono Pole |  |  |  |  | 16 TAC 25.83(a)(3) | Within station property
42652435 | Pharr SVC Bus Tie #2 | Pharr/Hidalgo | Construct bus tie #2 from existing 138-kV Pharr substation to SVC Yard. | 2018-02-15 | 2018-12-31 |  |  | 573917 |  |  | 99 |  | 138 | 0.15 | 959.6 ACSS/TW | Steel Mono Pole |  |  |  |  | 16 TAC 25.83(a)(3) | Within station property
42652438 | Pharr - Polk Ave Transmission Line Relocate | Pharr/Hidalgo | Relocate the Pharr to Polk Ave 138-kV transmission line, one line position east between Breaks 1705 & 1715 at the Pharr Substation. | 2018-02-15 | 2018-12-31 |  |  | 217180 |  |  | 99 | 138 |  | 0.15 | 959.6 ACSS/TW | Steel Mono Pole |  |  |  |  | 16 TAC 25.83(a)(3) | Within station property
42654266 | Pharr - MVEC Transmission Line Relocate | Pharr/Hidalgo | Relocate the Pharr to MVEC 138-kv transmission line, one line position east of the newly installed fourth ring at the Pharr Substation. | 2018-02-15 | 2018-12-31 |  |  | 217180 |  |  | 99 | 138 |  | 0.15 | 959.6 ACSS/TW | Steel Mono Pole |  |  |  |  | 16 TAC 25.83(a)(3) | Within station property
42612156 | Refugio Substation: Install DICM | Refugio | Install new DICM at Refugio Substation, equipped with new line protection, and bus protection panels, RTU, DME. Purchase Property for Expansion. | 2018-04-15 | 2018-09-30 | 2018-12-21 |  | 2642609 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Property for Expansion Purchased
42629713 | Calallen (STEC) - Banquete 69-kV Rebuild | Corpus Christi/Nueces | Rebuild and reconductor the Calallen (STEC) to Banquete 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-05-28 | 2019-05-28 | 2019-05-28 |  | 8151812.58 | 13899448.52 | 70.51% | 100 | 69 |  | 12.7 | 795 KCM ACCS "Drake" | Concrete Mono Pole | Centerline | 12.7 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners noticed.
42630262 | Premont - Falfurrias 69-kV Rebuild | Jim Wells Falfurrias/Brooks | Rebuild and reconductor the Premont to Falufrrias 69-kV transmission line to 138-kv standards. Will continue to operate at 69 kV. | 2018-06-05 | 2020-06-07 | 2020-05-11 |  | 8000000 | 10731984.98 | 34.15% | 100 | 69 |  | 12.25 | 795 KCM ACCS "Drake" | Concrete Mono Pole | Centerline | 12.25 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners noticed.
42629781 | Three Rivers - Sunniland 69-kV Rebuild | Live Oak | Rebuild and reconductor the Three Rivers to Sunniland 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-07-13 | 2018-12-12 | 2018-12-20 |  | 5039296.6 |  |  | 99 | 69 |  | 7.2 | 795 KCM ACCS "Drake" | Steel Mono Pole | 50 | 7.2 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners noticed.
42629715 | Banquete - Stadium 69-kV Rebuild | Nueces Alice/Jim Wells | Rebuild and reconductor the Banquete to Stadium 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-07-25 | 2020-02-01 | 2020-02-25 |  | 15140894 | 7501788.68 | -50.45% | 100 | 69 |  | 16.96 | 795 KCM ACCS "Drake" | Concrete Mono Pole | Centerline | 16.96 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners noticed.
42736720 | Reading Substation: T-station Assets | Uvalde/Uvalde | Construct the 138-kV side of the Reading Substation including the installation of a 145 kV, 3000A, 40kA, 125VDC circuit switcher, in & out transmission bus work with two motor-operated switches, a manual bus tie switch, a switch on second bus terminal for future transformer, and a Wave Trap. | 2018-07-05 | 2019-04-30 | 2019-06-27 |  | 992451 |  |  | 99 |  | 138 |  | . | [5 empty] | 16 TAC 25.83(a)(3) | Property purchased
42736418 | Reading Substation: T-line Assets | Uvalde/Uvalde | Cut-in the Moore to Uvalde 138-kV transmission line into new Reading Substation. | 2018-07-05 | 2019-04-30 | 2019-06-07 |  | 798381 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42749716 | Whitepoint - STP (Emergency Project) | Refugio Victoria Calhoun | Replace 131 H-Frame Strom-Damaged 345-kV Structures along 27 miles of the AEP Texas Whitepoint to STP 345-kV transmission line. | 2017-12-14 | 2018-05-15 | 2018-05-15 |  | 49500000 |  |  | 99 | 345 |  |  |  | H-Frame Tubular Steel |  |  |  |  | 16 TAC 25.101 (c)(3) | Emergency Project (Hurricane Harvey Storm Damage)
42630260 | N. Ella - Premont 69-kV Rebuild | Jim Wells | Rebuild and reconductor the N. Ella to Premont 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-08-05 | 2021-01-06 | 2020-12-15 |  | 8600000 |  |  | 99 | 69 |  | 10.47 | 795 KCM ACSS "Drake" | Concrete Mono Pole | Centerline | 10.47 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners noticed.
42629736 | Coy City Tap - Sunniland 69-kV Rebuild | Live Oak Atacosa | Rebuild and reconductor the Sunniland to Coy City Tap 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-11-14 | 2019-02-07 | 2019-10-02 |  | 11607446 |  |  | 99 | 69 |  | 16.19 | 795 KCM ACSS "Drake" | Steel Mono Pole | 50 | 16.19 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners noticed.
42629734 | Pleasanton - Coy City Tap 69-kV Rebuild | Pleasanton/Atascosa | Rebuild and reconductor the Pleasanton to Coy City Tap 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-12-03 | 2020-03-21 | 2020-03-27 |  | 18603950 |  |  | 99 | 69 |  | 17.3 | 795 KCM ACSS "Drake" | Steel Mono Pole | 50 | 17.3 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners noticed.
42729406 | Uvalde - Campwood 69-kV Rebuild | Uvalde/Uvalde Campwood/Real | Rebuild and reconductor the Uvalde to Campwood 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-12-02 | 2021-03-01 |  |  | 47846000 |  |  | 75 | 69 |  | 37 | 795 KCM ACSS "Drake" | Steel Mono Pole | varies | 37 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners noticed.
42641112 | Alice - N. Ella 69-kV Rebuild | Alice/Jim Wells | Rebuild and reconductor the Alice to N. Ella 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2018-12-02 | 2021-04-29 | 2021-04-08 |  | 7500000 |  |  | 99 | 69 |  | 14.3 | 795 KCM ACSS "Drake" | Concrete Mono Pole | varies | 14.3 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners noticed.
42620186 | Javelina 138-kV Substation: Replace MLSE equipment | Corpus Christi/Nueces | Upgrade breakers, switches, and jumpers on Westside SW line terminal. Install new CCTV's. | 2019-01-05 | 2019-05-27 |  |  | 1843785 |  |  | 35 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Property
42729705 | Asherton Substation: Transmission Assets Upgrades 69-kV Rebuild | Asherton/Dimmit | Upgrade high-side fuse with circuit switcher at the asherton 138/69-kV Substation. | 2020-02-24 | 2019-03-30 |  |  | 473017 |  |  | 0 | 138/69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42623718 | Airline Substation Rehab | Corpus Christi/Nueces | Add breakers and switches for the Laguna Substation and Naval Base GIS Substation terminals. Add bays for Transformers 1, 2, 3, and 4 for 138-kV conversion. | 2019-03-04 | 2019-05-29 | 2020-12-11 |  | 7245338 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42892575 | Pirate Substation: T-Station Assets | Sinton/San Patricio | Construct the 69-kV side of the Pirate Substation including the in & out transmission line work with two motor-operated switches, a manual bus tie switch, a switch on second bus terminal for futrue transformer, a Wave Trap. | 2019-05-01 | 2020-03-01 | 2020-02-11 |  | 2245202 |  |  | 35 |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Property purchased
42817198 | Gibbs 138-kV Station | San Patricio | Construct a six (6) Breaker Ring Bus expandable to Breaker and a Half configuration to serve for GCGV owned Transformers. | 2019-05-09 | 2019-12-10 |  |  | 8264697 |  |  | 99 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | CIAC to be collected for cost of station. Land provided under long term lease.
42891917 | Gibbs to GCGV Circuit 1 T-Line | San Patricio | Install T-Line Structure outside of Gibbs 138-kV Substation Fence. This T-Line structure will serve as a Point of Interconnect (POI). Install conductor between Gibbs Substation and T-Line Sturcture. | 2019-05-09 | 2019-12-10 |  |  | 377801 |  |  | 99 |  | 138 | 0.01 | 477 ACSR/AW "Hawk" | Steel H-Frame |  |  |  | 0.01 | 16 TAC 25.101 (c)(5)(A) | CIAC to be collected for cost of station. Land provided under long term lease.
42894987 | Gibbs to GCGV Circuit 2 T-Line | San Patricio | Install T-Line Structure outside of Gibbs 138-kV Substation Fence. This T-Line structure will serve as a Point of Interconnect (POI). Install conductor between Gibbs Substation and T-Line Sturcture. | 2019-05-09 | 2019-12-10 |  |  | 377801 |  |  | 99 |  | 138 | 0.01 | 477 ACSR/AW "Hawk" | Steel H-Frame |  |  |  | 0.01 | 16 TAC 25.101 (c)(5)(A) | CIAC to be collected for cost of station. Land provided under long term lease.
42888098 | Gibbs to GCGV Circuit 3 T-Line | San Patricio | Install T-Line Structure outside of Gibbs 138-kV Substation Fence. This T-Line structure will serve as a Point of Interconnect (POI). Install conductor between Gibbs Substation and T-Line Sturcture. | 2019-05-09 | 2019-12-10 |  |  | 377801 |  |  | 99 |  | 138 | 0.01 | 477 ACSR/AW "Hawk" | Steel H-Frame |  |  |  | 0.01 | 16 TAC 25.101 (c)(5)(A) | CIAC to be collected for cost of station. Land provided under long term lease.
42888099 | Gibbs to GCGV Circuit 4 T-Line | San Patricio | Install T-Line Structure outside of Gibbs 138-kV Substation Fence. This T-Line structure will serve as a Point of Interconnect (POI). Install conductor between Gibbs Substation and T-Line Sturcture. | 2019-05-09 | 2019-12-10 |  |  | 377801 |  |  | 99 |  | 138 | 0.01 | 477 ACSR/AW "Hawk" | Steel H-Frame |  |  |  | 0.01 | 16 TAC 25.101 (c)(5)(A) | CIAC to be collected for cost of station. Land provided under long term lease.
42888102 | Gibbs 138-kV Cut-in | San Patricio | Construct approximately 0.87 mile double circuit cut-in to the existing Dupont to White Point Ckt#3 138-kV line from Gibbs 138-kv Station. | 2019-05-09 | 2019-12-10 |  |  | 2288847 |  |  | 99 |  | 138 | 1.74 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  | 100 | 0.87 | 16 TAC 25.101 (c)(5)(A) | Partial CIAC to be collected for cost of station. Land provided under long term lease.
42885861 | Raymond Wind Permanent Interconnection: Bonilla 345-kV Station | Cameron | Construct a new 345-kV expandable breaker and a half configuration station with three (3) breakers and SSO Relay. | 2019-07-14 | 2020-01-19 |  |  | 24500000 |  |  | 0 |  | 345 | [7 empty] | 16 TAC 25.83(a)(3) | Property purchased
42757777 | Causeway 138-kV Substation: T-Station Assets | Port Isabel/Cameron | Replace 138-kV Circuit Switcher, extend bus to install new MOAB and create second terminal. Update remote relay settings. | 2019-06-17 | 2019-11-30 | 2020-03-27 |  | 980106 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42725410 | Hamilton Rd. - Picacho 138-kV Rebuild | DelRio/Val Verde | Rebuild and reconductor the Hamilton Rd. to Picacho 138-kV transmission line. | 2019-07-08 | 2020-03-31 |  |  | 13290374 |  |  | 0 | 138 |  | 8.8 | 795 KCM ACSS/AW "Drake" | Steel Mono Pole | Centerline | 8.8 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners noticed.
42869661 | Weaver Road - Greenlake 69-kV Line Relocate for Port of Victoria | Victoria | Weaver Rd. to Greenlake 69-kV Line: Relocate transmission line structures 11/5, 11/6, and 11/7 for Port of Victoria's McCoy Road improvement project. | 2019-07-29 | 2019-10-18 | 2019-12-31 |  | 1001652 |  |  | 99 | 69 |  |  | 477 ACSR/AW "Hawk" | Steel Two-Pole & Steel Three-Pole | 100 | 0.18 | 100 | 0.18 | 16 TAC 25.101 (c)(5)(F) | Landowner consent obtained
42658083 | Young 138-kV Substation: T-Line Assets | Edinburg/Hidalgo | Terminate the Pharr to Pole Ave 138-kV transmission line into the new Young 138-kV Substation. | 2019-11-15 | 2020-01-31 |  |  | 997917 |  |  | 99 | 138 |  | 0.01 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
42660915 | Young 138-kV Substation: T-Station Assets | Edinburg/Hidalgo | Install (2) 138-kV circuit switcher off of two buses with MOAB switches and associated 138 kV breaker bus work at the new Young 138-kV Substation. | 2019-10-04 | 2020-01-31 |  |  | 1141804 |  |  | 99 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Within station property
42821552 | Bunsen 138-kV Substation: Texstar Epic Y Grade Interconnect | Corpus Christi/Nueces | Construct approximately 0.75 miles of new double-circuit 138-kV transmission line from Bunsen Substation to Texstar's 138-kV Substation (Customer-Owned) to serve Epic Y Grade's Project of 21MW peak load. | 2019-10-28 | 2019-12-31 |  |  | 1085717 |  |  | 95 |  | 138 | 0.9 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  | 100 | 0.9 | 16 TAC 25.101 (c)(5)(A) | Landowner consent obtained
42949972 | Rio Hondo - Majadas 345-kV Transmission Line | Cameron Willacy | Construct a new 9.44 mile 345-kV transmission line from AEP Texas' Rio Hondo Switch Station to generator's (Las Majadas Wind Farm, LLC) Majadas 345-kV Substation. | 2019-12-10 | 2020-09-30 | 2020-08-25 | 18822576 | 27391061 |  |  | 98 |  | 345 | 9.44 | 954 KCM ACSR "Cardinal" | Steel Mono Pole |  |  | 150 | 9.44 | 48710 | CCN Approved 02/06/2019. Project site access found shallow water table throughout porject impaction structure and foundation design and construction cost.
42651863 | Port Isabel - Causeway 69-kV Rebuild | Laguna Vista, Port Isabel/Cameron | Rebuild and reconductor the Port Isabel to Causeway 138-kV transmission line. | 2019-11-04 | 2019-12-31 | 2020-08-08 |  | 21200000 |  |  | 99 | 138 |  | 6.67 | 795 KCM ACSS "Drake" | Steel Mono Pole | varies | 6.67 |  |  | 16 TAC 25.101 (c)(5)(B) | Landownder Noticed
42876413 | Pavlov 138-kV Substation | Matagorda | Construct a new three (3) Switch In & Out 138-kV Switching Substation. Install two(2) Circuit-Switchers, DICM, SCADA, Telecom, communication Equipment, & Relay Panels. | 2019-11-04 | 2020-05-01 |  |  | 1337489 |  |  | 95 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
42921257 (P18209001) (P19209002) (P18209011) | Angstrom 345-kV Station | San Patricio | Construct a new 345-kV station with three (3) breaker ring bus for the future cut-in of the STP to Whitepoint 345 kV transmission line and service to a new customer substation. Added two (2) 50MVA Reactors. | 2020-01-04 | 2021-01-26 | 2021-01-26 |  | 22779000 |  |  | 99 |  | 345 | [7 empty] | 16 TAC 25.83(a)(3) | Customer provided property and access, partial CIAC provided.
42921280 (P18209004) | Whitepoint - STP 345-kV T-Line for Angstorm Cut-in | San Patricio | Terminate the Whitepoint to STP 345-kV transmission line into new Angstrom 345-kV Substation. | 2020-07-05 | 2021-01-26 | 2021-01-26 |  | 6138676 |  |  | 99 | 345 |  | 1 | 2 - 954 ACSR "Cardinal" | Steel Mono Pole |  |  | 300 | 0.5 | 16 TAC 25.101 (c)(5)(A) | Landowner consent obtained Partial CIAC Provided
42761499 | Carrizo Springs - Crystal City 69-kV | Dimmit, Crystal City/Zavala | Rebuild and reconductor the Carrizo Springs to Crystal City 69-kV tranmission line to 138-kV standards. Will continue to operate at 69 kV. | 2020-02-03 | 2021-03-31 |  |  | 23089564 |  |  | 0 | 69 |  | 12.74 | 795 KCM ACSS "Drake" | Steel Mono Pole | varies | 12.74 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
42926334 | Shakes Solar Interconnect: Asherton 138-kV Substation Expansion | Asherton/Dimmit | Expand Substation. Install 138-kV, 3000A, 40kA Breaker, breaker & disconnect switches. Add SSO Relaying, Line Relaying, & EPS Metering. | 2020-02-23 | 2020-04-30 |  |  | 1340347 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42906770 | Cabaniss 138-kV Substation: Add Second Bank T-Station Assets | Corpus Christi/Nueces | Upgrade RTU & Install Circuit Breaker. | 2020-03-06 | 2020-05-12 | 2020-06-09 |  | 622236 | 530462 | -14.75% | 100 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Within station property
42909503 | Resaca 69-kV Substation: T-Station Assets | San Benito/Cameron | Construct 69-kV In &Out bus with manual bus tie switch for singel bank station. Accommodate space on bus on for future installation of breakers. Install (2) 69-kV Circuit Switchers, and all associated material install (2) 69-kV MOABs for the line terminals. Install Transmission RTU. | 2020-03-06 | 2020-06-15 | 2020-06-24 |  | 1377431 | 1489730 | 8.153% | 100 |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Property acquired
42914845 | Resaca 69-kV Substation: T-Line Assets | San Benito/Cameron | Terminate the La Palma to Brownsville SS 69-kV transmission line into new Resaca Substation. | 2020-03-06 | 2020-06-15 | 2020-05-18 |  | 790805 | 1366147 | 72.75% | 100 | 69 |  | 0.02 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Public ROW and Station property
43009650 | Shakes Solar Interconnection: Asherton - Escondido 138-kV T-Line | Asherton/Dimmit | Construct POI for LCRA outside Asherton 138-kV Substation and reterminate the transmission line into the substation. | 2020-04-05 | 2020-04-30 |  |  | 628669 |  |  | 0 |  | 138 | 0.06 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.83(a)(3) | Within station property
42943319 | Primera Substation: T-Station Assets | Harlingen/Cameron | Construct 138-kV In & Out Bus with manual bus tie switch for single bank station. Install 1 - 138-kV circuit switcher, 2 - 138-kV breakers, & transmission RTU. | 2020-04-15 | 2020-06-19 |  |  | 2333263 | 2628239 | 12.64% | 100 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
T10084785 (DP20X07C0) | Pantera 138-kV Substation: T-Line Assets | Weslaco/Hidalgo | Termiinate Weslaco - Wesmer SS 138-kV transmission line into new Pantera 138-kV Substation | 2020-05-04 | 2021-03-23 | 2021-06-18 |  | 1009261 |  |  | 99 |  | 138 | 0.1 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
42977511 (P19034007) | Las Lomas Wind Interconnection: Revilla 138-kV Substation | Zapata | Construct a three-breaker ring bus 138-kV substation with three (3) 3000A, 40kA breakers. Install RTU, DICM, Wave traps. Install SSO relay, EPS metering. | 2020-05-18 | 2020-11-30 | 110/5/2020 |  | 12114379 | 12937194 | 6.792% | 100 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property purchased
42977096 (P19034004) | Las Lomas Wind Interconnection: Lopeno-Falcon 138-kV Line Cut-In | Zapata | Terminate the Lopeno - Falcon SW 138-kV transmission line into new Revilla 138-kV Substation | 2020-05-18 | 2020-11-30 | 110/5/2020 |  | 1854179 | 1292430 | -30.3% | 100 |  | 138 | 0.2 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
42983330 (P19034005) | Las Lomas Wind Interconnection: Revilla-Venado 138-kV Tie-Line | Zapata | Construct approximately 0.10 mile of 138-kV transmisison line span from new Revilla 138-kV Substation to Las Lomas Wind's Venado Substation POI. | 2020-05-18 | 2020-11-30 | 110/5/2020 |  | 1489633 | 1185549 | -20.41% | 100 |  | 138 | 0.1 | 795 KCM ACSS "Drake" | Steel Deadend |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
42907629 (P15177004) (P15177013) | Stewart Rd. 345-kV Station: Expansion | Hidalgo/Hidalgo | Expand the Stewart Road 138-kV Station with two 345-kV autotransformers. Relocate the last spans of Stewart Rd.-Weslaco unit 138-kV line to make room for tie-lines to autotransformers. Install two spans of 138-kV to the new 345-kV yard. | 2020-06-04 | 2021-10-31 | 2021-10-18 | 27945000 | 34282826 |  |  | 99 |  | 345 | [7 empty] | 47603 | PUCT Docket 47973 Approved on 02/14/2019 BPID P15177004 & P15177013 will be summed together for total final costs.
42918594 (P15177007) | North Edinburg 345-kV Station: Multiplexor & Metering | Hidalgo/Hidalgo | Install new SEL Icon multiplexer at North Edinburg 345-kV Station in conjunction with the Stewart Rd. Project. Install new meters at Stewart Road on Palmito 345-kV line. | 2020-10-31 | 2021-04-15 | 2021-12-03 |  | 489376 |  |  | 99 |  | 345 | [7 empty] | 16 TAC 25.83(a)(3) | Within station property
43008627 DP19X18D0 T10093344 (DP19X18C0) | Haisley 138-kV Substation: T-Station Assets | Sinton/San Patricio | Install one (1) 138-kV, 3000A circuit switcher and one (1) 138-kV wave trap. | 2020-07-06 | 2020-11-04 | 2021-09-16 |  | 559673 | 508070 | -9.22% | 100 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Corrected Project Number Within station property
T10161800 (DP19X14D0) | Dimmit 138-kV Substation: T-Station Assets | Carrizo Springs/Dimmit | Install new bus work off the #1 and #2 to tie back into LCRA at station fence line. Work with LCRA to protect high side transformer bus via relay protection. | 2021-01-11 | 2021-07-01 | 2021-11-04 |  | 799872 | 1024085 | 28.03% | 100 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Within station property
T10053977 (DP20X08C0) | Sand Crab 138-kV Substation: T-Line Assets | Port Lavaca/Calhoun | Termiinate Union Carbide - Joslin 138-kV transmission line into new Sand Crab 138-kV Substation | 2021-01-19 | 2021-02-17 | 2021-03-09 |  | 628876 |  |  | 99 |  | 138 | 0.1 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  | 100 | 0.1 | 16 TAC 25.101 (c)(5)(A) | Landowner consent obtained
T10033471 (DP20X08D0) | Sand Crab 138-kV Substation: T-Station Assets | Port Lavaca/Calhoun | Install In & Out transmission bus work with two motor-operated switches and manual bus tie. Install two 3000A, 40kA circuit switchers, and two motor-operated switches for the transformers. Install wave traps. | 2020-07-04 | 2021-03-09 | 2021-04-15 |  | 1801040 |  |  | 99 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
42963078 (DP19X06D0) | Dustdevil 138-kV Substation: T-Station Assets (AEP Texas) | Laredo/Webb | Install one (1) 138-kV circuit switcher and switch for bank #1. Install switch on second bus terminal for future transformer. | 2020-08-15 | 2020-12-15 | 2021-05-14 |  | 1010995 | 863143 | -14.62% | 100 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
42854433 (P17043003) | Raymondville #2 69-kV Substation: Terminal Equipment | Raymondville/Willacy | Rebuild the 138-kV side of the station to a 6 breaker ring, which would convert the newly rebuilt Harlingen SS to Raymondville #2 line to 138 kV. | 2020-08-03 | 2021-12-31 | 2021-12-16 |  | 7557122 |  |  | 99 | 69 | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Within station property
42957957 (P18010001) | Chaparrosa 69-kV POD Box Bay: New Construction | Zavala | Construct a new 138-kV rated POD Box Bay. Install 3-3000A Motor-Operated Switches, metering, 2x2000 AAC jumpers & SCADA. Will be operated at 69 kV. | 2020-08-21 | 2021-02-03 | 2020-12-18 |  | 2700000 |  |  | 99 |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Consent Obtained
T10066092 (P19197001) | Bonilla-El Trueno 345-kV Line: Install DE POI | Cameron | Construct one 0 degree Dead-End engineered steel pole structure on concrete pier Dead End Structure outside of Bonilla 345-kV Station and Terminate 345-kV El Trueno gen-tie line | 2019-09-05 | 2020-12-15 |  |  | 589449 |  |  | 0 | 345 |  | 0.01 | 954 KCM ACSR 54/7 "Cardinal" | Steel Deadend |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP-owned property
T10054462 (P19197004) | Bonilla 345- kV Station | Cameron | Install two (2) 5000A, 50kA, 345-kV breakers, EPS metering, and verify SSO relay requirements are met | 2020-09-03 | 2021-04-30 |  |  | 6111144 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42801057 (A17024001) | Whitepoint - Dupont SW#1 138-kV: Raise Transmission Line | San Patricio | Replace four (4) lattice tower structures with monopoles and ACCC conductor to provide clearance over new TxDOT bridge (approx 0.35 mi) | 2020-09-10 | 2020-11-15 |  |  | 1551779 |  |  | 0 | 138 |  | 0.35 | 795 KCM ACCC "Drake" | Steel Mono Pole | 150 | 0.35 |  |  | 16 TAC 25.101 (c)(5)(F) | Landowners Noticed
42801062 (A17024003) | Whitepoint - Dupont SW#2 138-kV: Raise Transmission Line | San Patricio | Replace four (4) lattice tower structures with monopoles and ACCC conductor to provide clearance over new TxDOT bridge (approx 0.35 mi) | 2020-09-10 | 2020-11-15 |  |  | 1346541 |  |  | 0 | 138 |  | 0.35 | 795 KCM ACCC "Drake" | Steel Mono Pole | 150 | 0.35 |  |  | 16 TAC 25.101 (c)(5)(F) | Landowners Noticed
42801070 (A17024005) | Gregory - Aransas Pass 69-kV: Raise Transmission Line | San Patricio | Replace five (5) existing wood pole structures with monopoles to provide clearance over new TxDOT roadway (approx. 0.21 mi) | 2020-09-10 | 2020-11-15 | 2021-06-15 |  | 758680 |  |  | 99 | 69 |  | 0.21 | 336.4 KCM ACSR "Linnet" | Steel Mono Pole | 75 | 0.21 |  |  | 16 TAC 25.101 (c)(5)(F) | Landowners Noticed
T10065046 (DP20X01D0) | Chocolate Bayou 138-kV Substation: T-Station Assets | Victoria | Upgrade remote end relays & replace transmission RTU with a DM 61.01 | 2020-09-03 | 2021-03-26 |  |  | 785687 |  |  | 2 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10021421 (P18209008) | Angstrom - SDI 345-kV Transmission Line | San Patricio | Construct a new double-circuit 345-kV transmission line from Angstrom 345-kV Station (currently under construction) to the SDI Buffalo 345-kV Station to serve a new SDI steel plant. | 2020-08-03 | 2021-02-05 | 2021-02-25 | 4351000 | 4350047 |  |  | 99 |  | 345 | 1.72 | 2 - 954 ACSR "Cardinal" | Steel Mono Pole |  |  | 150 | 0.86 | 50726 | PUCT Docket 50726 Approved on 07/17/2020.
42651938 (A16002037) | South Padre Island - Sunchase 138-kV Rebuild | South Padre Island/Cameron | Rebuild and reconductor the South Padre Island to Sunchase 138-kV transmission line. | 2020-09-20 | 2021-02-28 | 2021-03-26 |  | 16000000 |  |  | 99 | 138 |  | 3.61 | 795 KCM ACSS "Drake" | Steel Mono Pole | Varies | 3.61 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed Supplemental easements acquired as necessary
43011781 (P18187001) | Aransas Pass - Sea Wall 69-kV Rebuild | Aransas Pass/ San Patricio | Rebuild and reconductor the Aransas Pass to Sea Wall 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV, | 2020-10-15 | 2021-05-15 | 2021-05-12 |  | 15000000 |  |  | 99 | 69 |  | 3.2 | 795 ACSR "Drake" | Steel Mono Pole | Centerline | 3.2 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
42998404 (P18048001) | Esperanza 138-kV Substation: Construction | Matagorda | Construct a new 138-kV 3-breaker ring bus station with DICM and associated equipment. | 2020-10-04 | 2021-01-25 | 2021-03-31 |  | 6046000 |  |  | 99 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Landowner Consent Obtained
T10150180 (P18048010) | Esperanza 138-kV Substation: Capacitor Banks | Matagorda | Install two (2) 28.8 MVAR Capacitor banks and associated breakers in the new Esperanza 138-kV Substation in conjunction with BPID P18048001. | 2020-10-04 | 2021-01-25 | 2021-04-06 |  | 1330000 |  |  | 99 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Within station property
42997581 (P18048003) | Celanese 138-kV Substation Fiber Panel | Matagorda | Update relaying and install Telecom panel to terminate fiber. | 2020-10-04 | 2021-04-11 | 2021-11-04 |  | 360000 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
43018271 (P18048009) | Celanese 138-kV Subtation: Upgrades | Matagorda | Install DICM, Line Relaying, and Breaker Control Panels. | 2020-10-04 | 2021-04-11 | 2021-11-04 |  | 2660000 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42983324 (P19034008) | Las Lomas Wind Interconnection: Falcon SW 138-kV Substation | Starr | Upgrade Remote End Relay Settings | 2020-10-15 | 2020-10-26 | 2020-11-05 |  | 717342 | 570253 | -20.5% | 100 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42983322 (P19034003) | Las Lomas Wind Interconnection: Zapata 138-kV Substation | Zapata | Upgrade Remote End Relay Settings | 2020-10-04 | 2020-11-02 | 2020-11-05 |  | 641464 | 690486 | 7.642% | 100 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10015124 (P19164001) | Hecker - Whitepoint Ckt. #1 138-kV Line | San Patricio | Reconductor the Hecker to Whitepoint Ckt. #1 transmission line. Some lattice structures may require replacement | 10\20\2020 | 2022-01-30 | 2022-02-12 |  | 4123423 |  |  | 99 | 138 |  | 5.61 | 795 KCM ACSS "Drake" | Steel Lattice Structures | Various | 5.61 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
T10060886 (P19164008) | Hecker - Whitepoint Ckt. #2 138-kV Line | San Patricio | Reconductor the Hecker to Whitepoint Ckt. #2 transmission line | 2020-10-20 | 2022-01-30 | 2022-02-12 |  | 3321827 |  |  | 99 | 138 |  | 5.61 | 795 KCM ACSS "Drake" |  | Various | 5.61 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
T10053550 (P19164005) | Whitepoint 138-kV Switching Station | San Patricio | Reterminate jumpers and update relay settings | 2021-12-21 | 2022-01-30 | 2022-02-12 |  | 322668 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10142154 (P20068003) | Lon Hill- Goddard 345-kV Line: Cut-In | San Patricio | Terminate the Lon Hill to Goddard 345-kV line into the new Katoen 345-kV Substation. | 2020-12-01 | 2021-10-15 | 2021-10-15 |  | 2434423 |  |  | 99 | 345 |  | 0.2 | 795 ACSR "Drake" | Steel DE Structure |  |  | 150 | 0.2 | 16 TAC 25.101 (c)(5)(A) | Landowner consent obtained
T10139820 (P20068005) | Katoen - El Algodon 345-kV Line Extension | San Patricio | Construct a 345-kV span with DE Structure to Generator (El Algodon Alto Wind Farm, LLC) Point of Interconnect (POI) | 2020-12-01 | 2021-10-15 | 2021-10-15 |  | 772614 |  |  | 99 |  | 345 | 0.04 | 795 ACSR "Drake" | Steel DE Structure |  |  | 150 | 0.04 | 16 TAC 25.101 (c)(5)(A) | Landowner consent obtained
T10139816 (P20068002) | Katoen 345-kV Substation | San Patricio | Construct a new 345 kV three-breaker ring bus Katoen Substation with two 345-kV rungs for line terminations with appropriate relays. Install three 345-kV, 50 kA, 3000 A breakers & EPS Metering for the El Algodon terminal. Install SSO relaying in monitoring mode for the El Algodon terminal | 2020-12-01 | 2021-10-15 | 2021-10-15 |  | 14092089 |  |  | 99 |  | 345 | [7 empty] | 16 TAC 25.83(a)(3) | Property purchased
42960644 (A19447013) | Equistar 138-kV Substation: Meter Modernization | Corpus Christi/Nueces | Replace existing CTs with metering combo for both XFMR#1 & 2 | 2020-11-03 | 2021-01-25 | 2021-05-18 |  | 757755 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within customer station property
42729418 (P14131004) | Uvalde 69-kV Substation | Uvalde/Uvalde | Replace 69-kv breaker and associated switches and bus work. | 2020-12-01 | 2021-05-01 |  |  | 1516561.9 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10080057 (DR20X04D0) | Black Cat 138-kV Substation: T-Station Assets | Bay City/Matagorda | Construct 138KV In & Out capable bus with manual bus tie switch for double bank station. Install one 138-kV (3000A 40 kA) Circuit switcher, and all associated material. Install two 138-kV MOABs for the line terminals. Install switch on second bus terminal for future transformer. Install wave trap on line. | 2020-12-01 | 2021-05-14 | 2021-05-14 |  | 1420254 |  |  | 99 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
42993359 (P19164002) | Whitepoint SS-Rincon 138-kV Line: Rebuild | San Patricio | Rebuild and reconductor a 4.59 mile portion of the Whitepoint SS to Rincon 138-kV transmission line. Reconductor the remaining 3.15 miles that are already on double-circuit structures. | 2020-11-10 | 2022-01-30 | 2022-05-06 |  | 9099925 |  |  | 99 |  | 138 | 7.74 | 795 KCM ACSS "Drake" | Steel Mono Pole | 100 | 7.74 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed. Consent and new easements & supplements were acquired as necessary.
43018270 (P18048008) | Blessing - Celanese 138-kV T-Line: Cut-In | Matagorda | Terminate the Blessing - Celanese 138-kV transmission line into the new Esperanza 138-kV Substation with double-circuit construction. | 2020-11-14 | 2021-01-25 | 2021-03-31 |  | 2350000 |  |  | 99 |  | 138 | 1.38 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  | 75 | 0.69 | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
43010991 (P17019002) | Resnik 138-kV Substation | San Patricio | Construct a new four-rung breaker and a half 138-kV substation expandable to six rungs | 2020-11-19 | 2022-01-30 | 2022-10-18 |  | 13809441 |  |  | 80 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3)
T10007790 (P17019006) | Resnik North 138-kV Cut-In | San Patricio | Terminate the Resnik North 138-kV transmission line into the new Resnik 138-kV Substation | 2021-10-01 | 2022-01-30 |  |  | 668638 |  |  | 40 |  | 138 | 0.04 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
T10015001 (P17019007) | Resnik South 138-kV Cut-In | San Patricio | Terminate the Resnik South 138-kV transmission line into the new Resnik 138-kV Substation | 2021-10-01 | 2022-01-30 |  |  | 674416 |  |  | 40 |  | 138 | 0.04 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
T10075090 (P19219002) | Whitepoint 345-kV Station: Add 2nd Auto | San Patricio | Expand existing 345-kV to a four-breaker ring, add second 345/138kV Auto, and add a new rung to the 138kV to connect to the Auto. | 2021-01-04 | 2022-01-30 |  |  | 17678000 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Property Purchased
T10171059 (P19219005) | Pelican-Whitepoint 138-kV Relocate | San Patricio | Relocate and reterminate the Pelican-Whitepoint 138-kV line for 2nd Auto addition | 2023-01-23 | 2023-04-07 |  |  | 2242000 |  |  | 0 | 138 |  | 0.04 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
T10171135 (P19219006) | Nueces-Whitepoint 138-kV Relocate | San Patricio | Relocate and reterminate Nueces-Whitepoint 138-kV line for 2nd Auto addition | 2023-01-23 | 2023-04-07 |  |  | 1772000 |  |  | 0 | 138 |  | 0.04 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
42807101 (A17961001) | Kleberg - Loyola 138-kV Relocation | Kingsville/Kleberg | Relocate 12 structures of the 138-kV line adjacent to US 77 due to TxDOT widening the highway and rebuilding a bridge near FM 1717 just south of Kingsville, TX. | 2021-01-04 | 2021-04-01 | 2021-05-04 |  | 3377565 |  |  | 99 | 138 |  | 1.38 | 795 KCM ACSS "Drake" | Steel Mono Pole / Steel 3 Pole Dead-End | Centerline | 1.38 | 100 | 1.38 | 16 TAC 25.101 (c)(5)(F) | Project is 100% Reimburseable from TxDOT. Landowner supplemental easements obtained as necessary.
42983135 (P18043001) | Dilley - Charlotte 69-kV Rebuild | Dilley/Frio Charlotte/Atascosa | Rebuild and reconductor the Dilley to Charlotte 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2021-02-01 | 2022-04-11 | 2022-04-19 |  | 26260304 |  |  | 99 | 69 |  | 34.34 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 34.34 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners noticed.
T101654020 (P20095002) | Bigfoot - Moore (STEC) 138-kV Rebuild | Frio | Rebuild and reconductor the Bigfoot to Moore (STEC) 138-kV transmission line to 138-kV standards. | 2021-02-10 | 2021-05-04 |  |  | 9945311 |  |  | 0 | 138 |  | 6.08 | 795 KCM ACSS "Drake" | Concrete Mono Pole | Varies | 6.08 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners noticed.
42937639 (P18027001) (P18027002) | Dolan Creek 138-kV POD Box Bay | Val Verde | Construct a 138-kV POD Box Bay (3000A ratings for all equipment) on center of the Transmission Line ROW. Install 138-kV revenue metering on the Box Bay. Install wave trap to control Carrier signal bleed by the tap load. | 2021-02-11 | 2021-05-15 |  |  | 1896733 |  |  | 0 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Exclusive Easement Obtained
42937666 (P18027004) (P18027003) | Maxwell - Sonora 138-kV T-Line: Cut-In | Val Verde | Terminate the existing Maxwell to Sonora 138-kV transmission into new Dolan Creek 138-kV POD Box Bay. | 2021-02-11 | 2021-05-15 |  |  | 1657836 |  |  | 0 | 138 |  | 0.36 | 477 KCM ACSR | Steel Mono Pole |  |  | 100 | 0.36 | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
T10165411 (P20095003) | Big Foot 138-kV Switching Station | Frio | Upgrade jumpers to Moore line terminal to a minimum of 2000A. Upgrade any limiting elements on the Moore terminal to a minimum of 2000A. Upgrade relays and settings as necessary. Coordinate remote end settings at Moore with STEC | 2021-04-01 | 2021-10-15 |  |  | 295964 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10148046 (A20059001) | Lon Hill 345-kV Substation: RFL Comm | Corpus Christi/Nueces | Add fiber from ATT to control house, replace old and install new 2411 relay equipment, add 120ac power to ATT interconnect box.D197 | 2021-03-06 | 2021-03-30 |  |  | 274000 |  |  | 95 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10148109 (A20059003) | Westside 138-kV Switching Station: RFL Comm | Corpus Christi/Nueces | Add fiber from ATT to control house, replace old and install new 2411 relay equipment, add 120ac power to ATT interconnect box.D197 | 2021-03-06 | 2021-03-30 |  |  | 232000 |  |  | 1 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10148117 (A20059004) | McKenzie Rd. 138-kV Substation: RFL Comm | Corpus Christi/Nueces | Add fiber from ATT to control house, replace old and install new 2411 relay equipment, add 120ac power to ATT interconnect box.D197 | 2021-03-06 | 2021-03-30 |  |  | 256000 |  |  | 95 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10210657 (A19372013) | Rachal-North Edinburg 138-kV Line | Hidalgo,Brooks | Telecom Modernization Program: Install 40.7 miles of 96 count ADSS fiber via Transmission between North EdinburgStation and Rachal Station. For connectivity at North Edinburg Station, Red Gate Station, and Rachal Station tosupport ICON MUX. | 2021-07-05 | 2021-10-15 |  |  | 1937290 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3)
T10107252 (A19376059) | La Quinta 138-kV Substation | Webb | Telecom Modernization Program: Install 0.2 miles of 48 ct ADSS fiber via underground between La Quinta TS and La QuintaTelecom Shelter. For connectivity at La Quinta TS Telecom Shelter to support DWDM and CES. | 2021-02-15 | 2021-05-24 |  |  | 270592 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10107253 (A19376060) | Zapata 138-kV Substation | Zapata | Telecom Modernization Program: Install 0.2 miles of 48 ct ADSS fiber via underground between Zapata TS and Zapata Telecom Shelter. For connectivity at Zapata TS Telecom Shelter to support DWDM and CES. | 2021-04-19 | 2021-07-22 |  |  | 270592 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10107260 (A19376068) | Uvalde 138-kV Substation | Uvalde/Uvalde | Telecom Modernization Program: Install 2.7 miles of 48 ct ADSS fiber via distribution from Uvalde Telecom Shelter to existing fiber on the Turtle Creek - Uvalde 69-kV Circuit. For connectivity at Uvalde Telecom Shelter to support DWDM. | 2021-04-05 | 2021-06-29 |  |  | 253852 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10094875 (A19376069) | Kenedy 138-kV Substation | Kenedy/Karnes | Telecom Modernization Program: Install 0.2 miles of 48 ct ADSS fiber via underground between Kenedy SW Station and Kenedy SW Telecom Shelter. For connectivity at Kenedy SW Telecom Shelter to support DWDM and CES. | 2021-04-05 | 2021-09-29 | 2021-06-26 |  | 270592 | 222477 | -17.78% | 100 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
43018215 (P17019004) | DuPont-McCampbell North 138-kV Cut-In | San Patricio | Terminate the DuPont-McCampbell North 138-kV transmission line into the new Resnik 138-kV Substation | 2021-04-06 | 2022-01-30 | 2022-10-18 |  | 2438743 |  |  | 99 | 138 |  | 0.5 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  | 200 | 0.5 | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
43018234 (P17019005) | DuPont-McCampbell South 138-kV Cut-In | San Patricio | Terminate the DuPont-McCampbell South 138-kV transmission line into the new Resnik 138-kV Substation | 2021-04-06 | 2022-01-30 | 2022-10-18 |  | 1703102 |  |  | 99 | 138 |  | 0.25 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  | 200 | 0.25 | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
T10015019 (P17019015) | DuPont-Hecker 138-kV Cut-In | San Patricio | Terminate the DuPont-Hecker 138-kV transmission line into the new Resnik 138-kV Substation | 2021-04-06 | 2022-01-30 | 2022-10-18 |  | 1975967 |  |  | 99 | 138 |  | 0.25 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  | 200 | 0.25 | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
T10180506 (P20080002) | Tango 345-kV Station: Build Tango 345-kV Station | Bee | Build new 345-kV Tango station to cut into the Goddard - (STEC) Pawnee line to enable customer generation interconnect. | 2021-04-26 | 2022-02-16 | 2022-02-21 |  | 13400000 |  |  | 99 |  | 345 | [7 empty] | 16 TAC 25.83(a)(3) | Within station property
T10207014 (P20136001) | Tango 345-kV Station: Install Terminal | Bee | Install 345 kV terminal, one (1) 345 kV, 50 kA, 3000 A breaker, EPS metering for Sparta terminal, & SSO relaying in monitoring mode for Sparta terminal. | 2021-04-26 | 2022-02-16 | 2022-02-28 |  | 2400000 |  |  | 99 |  | 345 | [7 empty] | 16 TAC 25.83(a)(3) | Within station property
T10238591 (P20080003) | Goddard 345-kV Station: Upgrades | Bee | Make upgrades and modifications in Goddard station to support the new Tango station. | 2021-10-26 | 2022-01-21 | 2022-02-21 |  | 330000 |  |  | 99 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10238629 (P20080004) | Tango - Foxtrot 345-kV T-Line: Span Outside Tango | Bee | Construct 0.10 mile span of 345-kV T-Line to Foxtrot Wind Interconnection | 2021-11-01 | 2022-01-06 | 2022-02-21 |  | 900000 |  |  | 99 |  | 345 | 0.1 | 795 KCM ACSR "Drake" | Steel Deadend |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
T10177955 (P20080006) | Goddard - (STEC) Pawnee 345-kV T-Line: Cut-In | Bee | Terminate the Goddard to Pawnee (STEC) 345-kV transmission line into the new Foxtrot 345-kV Substation. | 2021-11-01 | 2022-01-21 | 2022-02-21 |  | 2600000 |  |  | 99 | 345 |  | 0.2 | 795 KCM ACSR "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
T10207016 (P20136003) | Tango - Sparta 345-kV T-Line: Build Span | Bee | Construct 0.10 mile span of 345-kV T-Line to Sparta Solar Interconnection | 2021-11-01 | 2021-12-31 | 2022-02-28 |  | 1900000 |  |  | 99 |  | 345 | 0.1 | 795 KCM ACSR "Drake" | Steel Deadend |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
T10261470 (A20141001) (A20141002) | Falfurrias - Rachal 138-kV T-Line | Falfurrias/Brooks | Modify existing mono pole davit arms to braced post construction. | 2021-10-04 | 2021-12-15 | 2021-12-10 |  | 3748680 |  |  | 99 | 138 |  | 25.18 | 795 ACSR "Drake" | Steel Mono Pole | Centerline | 25.18 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners noticed
T10261473 (A20141003) (A20141004) | Rachal - N. Edinburg 138-kV T-Line | Edinburg/Hidalgo | Modify existing mono pole davit arms to braced post construction. | 2021-07-05 | 2021-08-31 | 2021-10-15 |  | 5845320 |  |  | 99 | 138 |  | 39.78 | 795 ACSR "Drake" | Steel Mono Pole | Centerline | 39.78 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners noticed
42651786a (A16002193) | Causeway - Sunchase 138-kV Rebuild | South Padre Island/Cameron | Rebuild and reconductor the Causeway to Sunchase 138-kV transmission line. | 2021-09-15 | 2021-12-31 | 2022-03-23 |  | 21000000 |  |  | 99 | 138 |  | 3.21 | 795 KCM ACSS "Drake" | Steel Pole Mono | Varies | 3.21 |  |  | 16 TAC 25.101 (c)(5)(B) & 16 TAC 25.101 (c)(5)E | Landowners Noticed. Landowner Consent obtained as needed.
43018170 (P19166001) (P19166002) | Port Aransas - Seawall 69-kV UG Sea Cables | Port Aransas /Nueces | Replace 0.48 miles of Undersea Cables and Conduit. | 2021-04-10 | 2021-07-31 | 2021-09-17 |  | 19843136 |  |  | 93 | 69 |  | 0.48 | 795KCM ACSS/AW bundle of 7 cables and ACSS | Undersea Cables |  |  |  |  | 16 TAC 25.101 (c)(5)(B) | Landowner Consent Obtained
T10082775 (DR20X04C0) | Black Cat 138-kV Substation: T-Line Assets | Bay City / Matagorda | Terminate the Bay City to Conoco 138-kV transmission line into the new Black Cat 138-kV Substation. | 2021-04-19 | 2021-05-14 | 2021-05-14 |  | 1192214 |  |  | 99 | 138 |  | 0.02 | 795 ACSS "Drake" | Steel DE Structures |  |  | 100 | 0.02 | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
T10127143 (P19289001) (P19289003) (P19289006) | Markham - Markham Tap 69-kV Line | Markham/Matagorda | Rebuild and reconductor the Markham Substation to Markham Tap 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2021-06-17 | 2021-11-15 | 2021-12-13 |  | 2517071 |  |  | 99 | 69 |  | 1.82 | 795 ACSR "Drake" | Steel Pole Mono | Centerline | 1.82 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
T10405852 (P19289015) (P19289016) | Blessing - Markham 69-kV Line | Markham/Matagorda | Rebuild and reconductor the Blessing Substation to Markham Substation 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2021-06-17 | 2021-11-15 | 2021-12-03 |  | 12350247 |  |  | 99 | 69 |  | 8.93 | 795 ACSR "Drake" | Steel Pole Mono | Centerline | 8.93 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
T10125915 (P19289004) | Blessing 69-kV Substation: Upgrade Terminal | Matagorda | Upgrade 69-kV terminal to 2000 A, 40 kA & Update relay settings at Blessing 69-kV Substation | 2021-06-21 | 2021-11-15 | 2022-02-22 |  | 436516 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10126264 (P19289005) | Markham 69-kV Substation: Upgrade Thru Path | Markham/Matagorda | Upgrade thru-path to 2000 A, 40 kA at Markham 69-kV Substation | 2021-08-23 | 2021-11-15 | 2021-09-10 |  | 153992 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10281928 (A20132008) | Lopeno 138-kV Substation | Zapata | Installing Physical Security to DICM, Telecom Network Splitting, RTAC (Station Data Repository) updates, and Firmware Upgrades. | 2021-08-02 | 2021-10-01 | 2021-08-26 |  | 252719 | 252947 | 0.09022% | 100 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10281949 (A20132011) | N. Edinburg 138-kV Substation | Hidalgo | Installing Physical Security to DICM, Telecom Network Splitting, RTAC (Station Data Repository) updates, and Firmware Upgrades. | 2021-07-19 | 2021-08-24 | 2021-09-28 |  | 278593 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10281961 (A20132014) | Raymondville #2 138-kV Substation | Willacy | Installing Physical Security to DICM, Telecom Network Splitting, RTAC (Station Data Repository) updates, and Firmware Upgrades. | 2021-07-26 | 2021-09-10 | 2021-09-28 |  | 274096 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10214754 (P19312001) | Joslin 138-kV Substation: Install Terminal | Point Comfort/Calhoun | Construct new 138-kV rung with double breakers for existing Dupont lines. Install a new 138-kV breaker on the existing Dupont terminal. Install EPS metering on the terminal for Tres Bahias. Update relaying as necessary to accommodate the new line terminations at the Joslin 138-kV Substation | 2021-07-19 | 2022-02-22 | 2022-02-24 |  | 1495265 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within AEP owned property
T10221296 (P19312002) | Joslin-Tres Bahias 138-kV Line: Install Span | Point Comfort/Calhoun | Install Interconnect deadend structure and one span of 138-kV transmission line into Joslin 138-kV Substation | 2021-07-19 | 2022-02-22 | 2022-02-24 |  | 528715 |  |  | 99 | 138 |  | 0.04 | 795 KCM ACSS "Drake" | Steel Deadend |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP owned property
T10214757 (P19312004) | Joslin-Dupont 138-kV Line: Reterminate Line | Point Comfort/Calhoun | Reterminate the existing Joslin to Dupont 138-kV transmisison line to new rung | 2021-10-12 | 2021-11-02 | 2022-02-01 |  | 256334 |  |  | 99 | 138 |  | 0.04 | 795 KCM ACSS "Drake" | Steel Pole Mono |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP owned property
T10221314 (P19312006) | Joslin-Formosa 138-kV Line: Reterminate Line | Point Comfort/Calhoun | Reterminate the existing Joslin to Formosa 138-kV transmisison line to new rung | 2021-12-17 | 2022-01-20 | 2022-02-01 |  | 324879 |  |  | 99 | 138 |  | 0.04 | 795 KCM ACSS "Drake" | Steel Pole Mono |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP owned property
T10189306 (P19011001) | Brightside 69-kV Temporary Tap: Metering | Live Oak | Install metering & RTU for Brightside Solar Farm | 2021-06-04 | 2020-12-24 | 2021-11-17 |  | 630521 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Solar Farm owned property
T10190061 (P19011002) | Charter-Brightside 69-kV Temporary Tap | Live Oak | Install temporary tap along the Three Rivers to Beeville 69-kV transmission line to serve Brightside Solar Farm | 2021-06-04 | 2020-12-24 | 2021-11-17 |  | 1679657 |  |  | 99 | 69 |  | 0.25 | 4/0 ACSR 6/1 "Penguin" | Steel Pole Mono |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Solar Farm owned property
42912899 (A18044001) | Garza 69-kV Substation | Starr | Install DICM, replace obsolete breakers & relays, & replace RTU & Metering, | 2021-07-30 | 2022-04-19 |  |  | 6264892 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10057021 (P18043002) (P18043004) | Charlotte-Jourdanton 69-kV Rebuild | Charlotte,Jourdanton /Atascosa | Rebuild and reconductor the Charlotte to Jourdanton 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2021-10-25 | 2022-08-29 | 2022-07-15 |  | 17087761 |  |  | 99 | 69 |  | 10.33 | 795 KCM ACCS "Drake" | Steel Mono Pole | Centerline | 10.33 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners noticed.
42994625 (A18018024) | Berclair 69-kV Substation | Bee | Expand existing Berclair 69-kV Substation on existing property, install new box bay structure and communication cabinets, build new station bus to connect to existing distribution transformers. | 2021-10-01 | 2022-05-31 | 2022-06-08 |  | 2383987 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42651786b (A16002193) | Causeway - Sunchase 138-kV Rebuild (Channel Crossing) | South Padre Island/Cameron | Relocate, rebuild and reconductor the 0.13 mile channel crossing portion of the Causeway to Sunchase 138-kV transmission line. | 2021-09-15 | 2021-12-31 | 2022-03-23 |  | 5500000 |  |  | 99 | 138 |  | 0.17 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 0.13 | 100 | 0.17 | 16 TAC 25.101 (c)(5)(B) & 16 TAC 25.101 (c)(5)(E) | Utilizing Existing Easement Landowners Noticed Landowner Consent obtained as needed.
42898119 (A20217009) | Rangerville 138-kV Substation: RTU Reliability | San Benito/Cameron | Rangerville RTU Reliability - Replace existing IBOX RTUs with new Cooper RTUs | 2021-09-01 | 2021-10-01 | 2021-11-30 |  | 292515 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10131836 (P20026001) | Rio Hondo 345/138-kV Switching Station | Cameron | Update E. Rio Hondo terminal to meet 2000A requirement. Replacing jumpers with double 1272 and updating breaker switches to 2000A switches. | 2021-10-04 | 2021-11-17 |  |  | 396000 |  |  | 0 | 345/138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10244830 (P20209001) | Roma Tap 138-kV Station: Install Terminal | Starr | Construct a new 138 kV breaker terminal at the Roma Tap 138-kV station.Install EPS metering at the new 138 kV breaker terminal for the generator. | 2021-10-15 | 2021-04-28 |  |  | 1123544 |  |  | 30 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10244834 (P20209003) | Roma Tap to Starr Solar POI: 138-kV Span | Starr | Construct one 138-kV span from the new breaker terminal at Roma Tap to the POI structure just outside the station fence. | 2021-10-15 | 2021-04-28 |  |  | 362002 |  |  | 0 | 138 |  | 0.17 | 795 KCM ACSS "Drake" | Steel Deadend | Centerline | 0.13 | 100 | 0.17 | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
TL0043273 (A21064006) | Victoria - Coleto Creek (S) 138-kV Transmission Line | Goliad | Install two 3-pole, galvanized steel, tangent, structures and remove two H-Frame, self-weathering steel, structures, to raise the 1590 KCM ACSR “Lapwing”, conductor. Assist Telecom with removal of one mid-span wood pole. | 2021-11-08 | 2021-11-19 |  |  | 467424 |  |  | 0 | 138 |  | 0.1 | 1590 ACSR "Lapwing" | 3-Pole Steel | 100 |  |  |  | 16 TAC 25.101 (c)(5)(B) | Landowner Noticed No new easement necessary.
TL0043272 (A21064007) | Victoria - Coleto Creek (N) 138-kV Transmission Line | Goliad | Install five 3-pole, galvanized steel, tangent, structures and remove five H-Frame, wood, structures, to raise the 1590 KCM ACSR “Lapwing”, conductor. Assist Telecom with removal of one mid-span wood pole | 2021-10-25 | 2021-11-05 |  |  | 816093 |  |  | 0 | 138 |  | 0.5 | 1590 ACSR "Lapwing" | 3-Pole Steel | 100 |  |  |  | 16 TAC 25.101 (c)(5)(B) | Landowner Noticed No new easement necessary.
TL0043270 (A21064008) | Coleto Creek - Kenedy SS 138-kV Transmission Line | Goliad | Install two 3-pole, galvanized steel, structures and remove two H-Frame, wood structures, to raise the 795 KCM ACSR “Drake”, conductor. | 2021-10-11 | 2021-10-22 |  |  | 363293 |  |  | 0 | 138 |  | 0.1 | 795 KCM ACSS "Drake" | 3-Pole Steel | 100 |  |  |  | 16 TAC 25.101 (c)(5)(B) | Landowner Noticed No new easement necessary.
T10368161 (A21057006) | Coleto Creek - Lon Hill 345-kV Transmission Line | Goliad | Increase the height of structures 413, 414, 416 and 417 by installing lattice extensions. Performed to raise the 795 KCM ACSR "Drake" conductor. | 2021-10-04 | 2021-12-11 |  |  | 1186890 |  |  | 0 | 345 |  | 0.5 | 795 ACSR "Drake" | Lattice | 265 |  |  |  | 16 TAC 25.101 (c)(5)(B) | Landowner Noticed No new easement necessary.
T10234298 (P20197001) | Dupont - OxyChem 138-kV Transmission Line | Ingleside/San Patricio | Construct a 0.10 mile cut-in from the Dupont – OxyChem 138-kV transmission line into the new Air Liquide ring bus. | 2021-11-15 | 2022-03-15 |  |  | 1330000 |  |  | 0 | 138 |  | 0.1 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 0.1 |  |  | 16 TAC 25.101 (c)(5)(A) | Utilizing Existing Easement Landowners Noticed
T10234329 (P20197002) | Dupont 138-kV Substation: Relay Upgrade | San Patricio | Add new relays to support to customer owned expansion | 2021-12-15 | 2022-03-15 |  |  | 900000 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10234660 (P20197004) | Air Liquide 138-kV Substation: Upgrade | San Patricio | Add additional CT/PT, metering, RTU, etc. to accommodate customer owned station upgrade | 2021-11-20 | 2022-03-15 |  |  | 500000 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42987384 (P18143001) (P18143002) | Corichi 138-kV Phase-Over-Phase Switch | Wharton | Install 138-kV Phase-Over-Phase (POP) Motor-Operated Switch, install line trap, install B2500 Cabinet, and install RTU & SCADA. | 2021-11-29 | 2022-02-14 | 2022-03-17 |  | 1196662 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Landowner consent obtained
T10051437 (A19508005) | BP Chem 138-kV Station: Meter Modernization 2021 | Calhoun | Replace CT/PT's, install meter panels and NCRL switches. | 2021-12-23 | 2022-02-18 |  |  | 608668 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10151129 (DP20X09D0) | Progreso 69-kV Substation: Consruct Substation | Weslaco/ Hidalgo | Construct a 138-KV In & Out capable bus with manual bus tie switch for double bank station, to be operated at 69kV. Install 1-138-kV circuit switcher, and all associated material, to be operated at 69-kV. Install 2- 138-kV MOABs for the line terminals, to be operated at 69 kV. | 2021-12-04 | 2021-04-22 |  |  | 1305791 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10151135 (DP20X09C0) (DP20X09C1) | Stewart Rd. - La Palma 69-kV T-Line: Cut-In | Weslaco/ Hidalgo | Terminate the Stewart Rd. to La Palma 69-kV transmission line into the new Progreso 69-kV Substation. | 2021-12-04 | 2021-04-22 |  |  | 1008471 |  |  | 50 | 69 |  | 0.05 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
42847545 (A18907015) (A18018021) | Baez 69-kV Substation | Bee | Construct a new 69-kV, 6 breaker ring station on new property purchased 3 miles east of Beeville, TX. New station will have the capability of being expanded to include a 138-kV portion of yard. | 2021-12-16 | 2022-09-15 |  |  | 5851444 |  |  | 85 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Property purchased
T10084357 (A19001056) (A19001059) | Berclair - Goliad 69-kV Transmission Line | Bee,Goliad | Rebuild and reconductor the Berclair to Goliad 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2022-01-13 | 2022-05-31 | 2022-06-08 |  | 21498486 |  |  | 99 | 69 |  | 18.06 | 795 KCM ACCS "Drake" | Steel Mono Pole | Centerline | 17.91 | 100 | 0.41 | 16 TAC 25.101 (c)(5)(B) & 16 TAC 25.101 (c)(5)(E) | Utilizing Existing Easement Landowners Noticed Landowner Consent obtained as needed.
T10083471 (P18143003) (P18142002) | El Campo - Victoria 138-kV Transmission Line: Cut-In | Wharton | Terminate the existing El Campo to Victoria 138-kV transmission line into the new Corichi 138-kV POP Switch. | 2021-12-17 | 2022-02-14 | 2022-03-17 |  | 1316870 |  |  | 99 | 138 |  | 0.2 | 795 KCM ACCS "Drake" | Steel Mono Pole | Centerline | 0.2 | 100 | 0.2 | 16 TAC 25.101 (c)(5)(A) | Utilizing Existing Easement Landowners Noticed
T10302277 (P21023001) | Cebolla 345 kV: Terminal | Willacy | Install one (1) 345-kV, 50 kA, 5000A breaker. Install EPS metering on the El Sauz terminal. Install SSO relaying in monitoring mode and expand bus to the south and partially build new rung. | 2022-01-10 | 2022-05-12 |  |  | 4654655 |  |  | 98 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10317123 (P21023003) (P21023004) | Cebolla - El Sauz 345-kV Span | Willacy | Construct a 0.05 mile 345-kV Span to interconnect Cebolla 345-kV Station to El Sauz Ranch Windfarm Point of Interconnect. Install transmision fiber cable. | 2022-01-10 | 2022-05-12 |  |  | 895297 |  |  | 90 |  | 345 | 0.05 | 954 KCM ACSR 54/7 Bundled "Cardinal" | Steel Deadend |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
T10317388 (P21023002) (P21023005) | Ajo - Cebolla 345-kV Span | Willacy | Construct a 0.05 mile 345-kV Span to reterminate the Cebolla to ETT Ajo 345-kV transmission line. Install transmision fiber cable. | 2022-01-10 | 2022-05-23 |  |  | 1557338 |  |  | 90 |  | 345 | 0.05 | 954 KCM ACSR 54/7 Bundled "Cardinal" | Steel Deadend |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
T10180042 (P20066001) | Magnolia 138-kV Substation | Karnes | Install 15.4 MVAR capacitor bank. Install 138-kV circuit breaker on line side of capacitor bank. | 2022-02-02 | 2022-05-20 |  |  | 975800 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10012648 (A19001048) (A19001054) | Warburton (STEC) - Medio Creek 138-kV Line | Victoria,Refugio | Rebuild and reconductor the Warburton (STEC) to Medio Creek 138-kV transmission line. | 2022-01-24 | 2022-12-31 | 2022-05-13 |  | 36544078 |  |  | 99 | 138 |  | 32.17 | 795 KCM ACSS "Drake" | Steel Mono Pole | Various | 32.17 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners noticed. Landowner consent obtained as necessary.
T10339673 (A21002001) (A21002002) | STP Corridor – HL&P 345-kV T-Line | Wharton | Raise one (1) transmission structure/conductor to resolve ground clearance, allowing uprate 345-kV line to resolve line congestion. | 2022-02-03 | 2022-04-01 | 2022-03-28 |  | 1690801 |  |  | 99 | 345 | [8 empty] | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
42965371 (P17040005) | Coleto Creek 138-kV Substation | Goliad | Replace line relay panels at Coleto Creek 138-kV Substation | 2022-02-03 | 2022-11-18 |  |  | 1579164 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10162771 (P20034001) | Whitepoint 138-kV Substation | San Patricio | Replace existing 10 ohm reactor with a 19.8 ohm reactor on the Nueces Bay 138-kV line. Replace existing 10 ohm reactor with a 19.8 ohm reactor on the Gila 138-kV line. | 2022-02-03 | 2022-12-28 |  |  | 2152538 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10053289 (P19168001) | N Edinburg 345-kV Substation: Add New Rung | Edinburg/Hidalgo | Build new 345-kV rung at North Edinburg 345-kV substation and re-terminate the Lon Hill transmission line into this rung. The removes breaker #125. | 2022-02-07 | 2024-12-31 |  |  | 12450957.41 |  |  | 55 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10352757 (P21246001) | Brackettville Relay Upgrade | Brackettville/Kinney | Install relaying to maintain communications due to breaker upgrades by LCRA at Pinto Creek Station. | 2022-02-17 | 2022-04-30 |  |  | 265101 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42291949 (P14064001) (P14064009) (P14064008) | Champlin 138-kV Substation Expansion | Nueces | Convert Champlin Station to a 4 breaker 138-kV Ring Bus. | 2022-03-07 | 2023-02-21 |  |  | 8390959.8 |  |  | 80 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Landowner consent obtained for expansion
42291968 (P14064002) | Weil Tract 138-kV Substation | Nueces | Upgrade relaying, SCADA, and communications at the Weil Tract substation as necessary to accommodate the Champlin Rehab project. | 2023-03-01 | 2023-05-01 |  |  | 818046 |  |  | 20 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42291960 (P14064003) | Lon Hill 138-kV Substation | Nueces | Upgrade relaying, SCADA, and communications at the Lon Hill substation Tract substation as necessary to accommodate the Champlin Rehab project. | 2023-03-01 | 2023-05-01 |  |  | 702310 |  |  | 10 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42350160 (P14064004) (P14064005) | Champlin - Lon Hill 138-kV T-Line | Nueces | Reterminate the Champlin to Lon Hill 138-kV transmission line into the Champlin 138-kV Substation. | 2022-04-01 | 2023-05-01 |  |  | 985150 |  |  | 95 | 138 |  | 0.022 | 795 KCM ACSS "Drake" | Steel Pole Mono | 50' | 0.02 | 50' | 0.02 | 16 TAC 25.101 (c)(5)(A) | Landowner consent obtained
T10036517 (P16067007) (P16067016) | Champlin 138-kV Substation Ring Bus: Add 5th Breaker | Nueces | Add Champlin Station 5th Breaker to Ring Bus for Valero East Terminal. Install Mono-Pole Station Dead-End Structure. | 2022-03-07 | 2023-02-21 |  |  | 1573895.78 |  |  | 65 | 138 |  |  |  | Steel Pole Mono Dead-End |  |  |  |  | 16 TAC 25.83(a)(3) | Landowner consent/easement obtained for expansion
42954829 (A1805001) | North Padre 69-kV Substation | Corpus Christi / Nueces | Upgrade switch (MLSE). Add MUX and two routers for Wi-Fi. Replace switch 2614 with interruptor. | 2022-04-18 | 2022-05-31 | 2022-04-22 |  | 410568 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10296807 (P14129005) | Poesta 138/69-kV Substation | Bee | Construct a new breaker and a half 69/138-kV substation expandable to four rungs | 2022-04-02 | 2023-08-25 |  |  | 15100000 |  |  | 10 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Within existing station property
T10296348 (P14129006) | Tuleta 138-kV Substation | Bee | Install new terminal for 138-kV line from Poesta | 2022-06-06 | 2023-08-25 |  |  | 271150 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10301146 (P14129007) | Three Rivers 138-kV Substation | Live Oak | Install new terminal for 138-kV line from Poesta | 2022-06-06 | 2023-08-25 | 2022-12-20 |  | 1210000 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T103011477 (P14129008) | Mathis 69-kV Substation | San Patricio | Upgrade terminal and relaying for 138-kV line from Poesta | 2022-06-06 | 2023-08-25 |  |  | 620800 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10304991 (P14129024) | Beeville 69-kV Substation | Bee | Remove circuit breakers, Statcom and update relaying and SCADA | 2022-11-07 | 2023-08-25 |  |  | 554510 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10301152 (P14129011) | Beek 138-kV Substation | Bee | Construct a new 138-kV Box Bay | 2022-05-23 | 2023-08-25 |  |  | 2260000 |  |  | 0 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Within existing station property
T10139760 (P14129018) (P14129019) | Poesta - Three Rivers 138-kV T-Line | Live Oak, Bee | Rebuild and covert the Three river to Beeville 69-kV line to 138-kV and reterminate into the new Poesta 138-69-kV Substatiion. | 2022-07-11 | 2023-08-25 |  | 36691000 | 45038000 |  |  | 50 | 69 | 138 | 29 | 795 KCM ACSS "Drake" | Steel Pole Mono | 50 | 26.2 | 100 | 29 | 49347 | CCN Approved on 03/26/2020. Increase in steel cost is the major cost increase factor. Inflation impact on other cost and cost to remove the old line was not in original estimate.
T10139739 (P14129016) (P14129017) | Poesta - Tuleta 138-kV T-Line | Bee | Construct a new 138-kV transmission line from the new Poesta 138-69-kV Substation to the Tuleta 138-kV Substation | 2022-09-19 | 2023-08-25 |  | 41298000 | 60380000 |  |  | 0 |  | 138 | 22.5 | 795 KCM ACSS "Drake" | Steel Pole Mono |  |  | 100 | 22.5 | 49347 | CCN Approved on 03/26/2020. Increase in steel cost is the major cost increase factor. Inflation impact on other cost and cost to remove the old line was not in original estimate.
42799981 (A19001030) (A19001031) (A19001033) | Naval Base - North Padre 69-kV T-Line | Corpus Christi / Nueces | Rebuild and reconductor the existing Naval Base to North Padre 69-kV transmission line and offet it 50' from its original location. Constructed to 138-kV standards but operated at 69 kV. | 2022-11-03 | 2023-06-30 |  |  | 27388741 |  |  | 35 | 69 |  | 5.13 | 795 KCM ACSS "Drake" | Steel 2-Pole Tangents Steel 3-Pole Deadends | 75 | 5.1 | 100 | 5.13 | 16TAC 25.101 (c)(5)(B) | Landowners Noticed Landowner Consent Obtained as necessary
T10414083 (A18807076) | STP Pump Tap - STP Construction 138-kV T-Line | Matagorda | Replace failed lattice tower structure 19 along the STP Pump Tap to STP Construction 138-kV transmission line. | 2022-05-02 | 2022-06-26 |  |  | 630770 |  |  | 99 | 138 |  |  | 795 KCM ACSS "Drake" | Steel Pole Mono |  |  |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
T10152836 (A19001058) (A19001020) | Berclair - Baez 69-kV Rebuild | Bee | Rebuild the Berclair to Baez 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2022-06-01 | 2022-09-15 |  |  | 7867857 |  |  | 85 | 69 |  | 6.98 | 795 KCM ACCS "Drake" | Steel Mono Pole | Centerline | 6.98 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
T10169661 (A18010005) | Chase Field Tap - Baez 69-kV Rebuild | Bee | Rebuild the Baez to Chase Field 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2022-09-15 | 2022-09-30 |  |  | 1330105 |  |  | 85 | 69 |  | 0.4 | 795 KCM ACCS "Drake" | Steel Mono Pole | Centerline | 0.4 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
T10105500 (A19001061) | Beeville - Goliad Telecom TFC | Bee,Goliad | Transfer existing ADSS over to the newly rebuilt line. Perform any transfers from ADSS to OPGW and make any needed fiber connections is the stations. | 2022-05-02 | 2022-10-15 |  |  | 820595 |  |  | 85 | 69 | [8 empty] | 16 TAC 25.83(a)(3)
T10012713 (A19001050) (A19001051) | Medio Creek - Haisley 138-kV Line | Refugio,San Patricio | Rebuild and reconductor the Haisley to Medio Creek 138-kV transmission line. | 2022-06-20 | 2022-12-23 |  |  | 15989610 |  |  | 60 | 138 |  | 14.74 | 795 KCM ACSS "Drake" | Steel Mono Pole | Various | 14.74 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easemsnts Landowners Noticed
43011799 (A18907004) | Ashpalt Mines 138-kV Substation | Uvalde | Install high side 138-kV circuit switcher & switch at Asphalt Mines 138-kV Substation. | 2022-06-04 | 2023-01-14 |  |  | 555000 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10174509 (P17032025) (P17032026) (P17032027) (P17032028) | Angstrom-Grissom 345-kV T-Line | Bee, Refugio, and San Patricio Counties | Construct a new 345-kV transmission line from the existing Angstrom 345-kV Station to the existing Grissom 345-kV Station. | 2023-03-01 | 2023-10-31 |  | 53266000 |  |  |  | 0 |  | 345 | 17.6 | 2-795 KCM ACSR "Drake" | Steel BOLD Lattice |  |  | 150 | 17.6 | 51912 | PUCT Docket 51912 Approved 03/29/2022
T10174174 (P17032009) | Angstrom 345-kV Station: Termination for Angstrom-Grissom 345-kV T-Line | San Patricio County | Add two line terminals and modify one line terminals for the transmission lines from Grissom, Whitepoint, and Naismith, add relaying, and terminate fiber to Angstrom 345-kV Station | 2023-02-01 | 2023-10-31 |  | 5437000 | 7449111 |  |  | 0 | 345 | [8 empty] | 51912 16TAC 25.83 (a)(3) | PUCT Docket 51912 Approved 03/29/2022 Within Station Property
T10174230 (P17032024) (P17032023) | Grissom 345-kV Station: Termination for Angstrom-Grissom 345-kV T-Line | Bee County | Add one line terminal and modify one line terminal for the transmission lines from Angstrom and Lon Hill, add relaying, and terminate fiber at Grissom 345-kV Station | 2023-02-01 | 2023-10-31 |  | 5143000 | 6779740 |  |  | 0 | 345 | [8 empty] | 51912 16TAC 25.83 (a)(3) | PUCT Docket 51912 Approved 03/29/2022 Within Station Property
T10358046 (P21260001) | Maxwell 138-kV Substation: Install Breaker Terminal | Del Rio/Val Verde | Install one 138-kV, 3000 A, 40 KA circuit breaker. Install EPS Metering. | 2022-08-10 | 2022-12-16 | 2022-12-16 |  | 1010863 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within existing station property
T10358064 (P21260003) (P21260004) | Maxwell - Antlia 138-kV T-Line: Build & TFC | Del Rio/Val Verde | Install one 138-KV deadend structure (POI) outside of Maxwell station along with first span. Install dual fiber path. | 2022-08-15 | 2022-12-16 |  |  | 808166 |  |  | 90 | 138 |  | 0.01 | 795 KCM ACSR "Drake" | Steel Deadend |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within existing station property
T10263191 (DP20X03D0) (DP20X03C6) | Mathis 138-kV Substation: T-Station Assets | San Patricio | Construct 138-KV capable In & Out 4 breaker ring bus operated at 69-kV with manual bus tie switch for double bank station. Install 138-kV power transformer, install 2-138-kV circuit switchers, and all associated material, install 4- 138-kV MOABs for the line terminals, install 4-3000A 40kA circuit breakers, install Transmission RTU, and install Metering for POI with STEC. Install OPGW from cut-in to station. | 2023-05-04 | 2023-06-30 |  |  | 5323441 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Property purchased
T10424641 (P21288001) | Gibbs 138-kV Substation | San Patricio | Add 3rd Rung rated 63 kA, 3000 A, Install two (2) 138-kV, 63 kA, 3000 A Breakers, Expand DICM, Install SSO Relaying, Install EPS Metering for Jackalope Solar Terminal, & Terminate Fiber. | 2022-11-01 | 2023-04-30 |  |  | 1625643 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10424653 (P21288003) (P21288002) (P21288004) | Gibbs - Jackalope 138-kV T-Line | San Patricio | Construct a 0.01 mile 138-kV transmission line from Gibbs 138-kV Substation to Jackalope Solar Point of Interconnect (POI). Install TFC. | 2022-11-01 | 2023-04-30 |  |  | 889020 |  |  | 0 |  | 138 | 0.01 | 795 KCM ACSR "Drake" | Steel Deadend |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
T10092558 (DP20X02C0) (DP20X02C1) | James Rowe 138-kV Substation: T-Line Assets | McAllen/Hidalgo | Terminate the North McAllen to West McAllen 138-kV transmission line into the new James Rowe Substation. Intall TFC. | 2022-08-06 | 2023-07-01 |  |  | 1067155 |  |  | 0 |  | 138 | 0.1 | 795 KCM ACSR "Drake" | Steel Monopole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Landowner consent obtained
T10093562 (DP20X02D0) | James Rowe 138-kV Substation: T-Station Assets | McAllen/Hidalgo | Install 1 – 138 kV circuit switcher. Verify Remote Station Terminals. Multiplexor (ICON & CGR Router). Install in and out transmission bus work with 2 – 138-kV breakers and a manual bus tie switch. | 2022-08-06 | 2023-05-01 |  |  | 2155484 |  |  | 0 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
T10051463 (A19508012) | Formosa Plastics 138-kV Substation: Meter Modernization | Calhoun | Replace CT's with CT/PT Combo units, upgrade communications to Non-Critical LAN for EPS 1 and 2 for the existing metering. | 2022-09-28 | 2022-11-15 |  |  | 329781 |  |  | 0 | 138 | [9 empty] | Within station property
T10051448 (A19508024) | Rio Hondo 138-345-kV Switch Station: Meter Modernization | Cameron | Replace CT's with CT/PT Combo units, Meters, Meter Panel and upgrade communications to Non-Critical LAN on the 138kV Burns and East Rio Hondo lines. | 2022-10-12 | 2022-11-30 |  |  | 393377 |  |  | 0 | 138 | [9 empty] | Within station property
T10051437 (A19508005) | Vistron (BP Chemical) 138-kV Station: Meter Modernization | Calhoun | Replace CT's with CT/PT Combo units, Meters, Meter Panel and upgrade communications to Non-Critical LAN on EPS-1 and 2 at the BP Chem/Vistron station. | 2022-11-02 | 2022-12-30 |  |  | 540422 |  |  | 0 | 138 | [9 empty] | Within station property
T10316123 (DP20X12D0) | Mayo 138-kV Substation | San Patricio | Install 138-kV, 50kVA station service transformer. Install circuit switcher. | 2022-09-22 | 2023-03-15 |  |  | 4579000 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10207007 (P20082002) (P20082001) | Charter 138-kV Substation | Live Oak | Construct a new ring bus 138-kV substation expandable to five breakers | 2022-09-04 | 2022-12-30 | 2022-12-20 |  | 7462727 |  |  | 80 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property purchased
T10213342 (P20082004) (P20082005) | Charter - Brightside 138-kV T-Line | Live Oak | Construct a 0.03 mile 138-kV transmission line from Charter 138-kV Substation to Brightside Solar Point of Interconnect (POI). | 2022-09-09 | 2022-12-30 | 2023-01-10 |  | 1260247 |  |  | 99 |  | 138 | 0.03 | 795 ACSS "Drake" | Steel Deadend |  |  |  |  | 16TAC 25.101 (c)(5)(A) | Utilizing existing easemsnts Landowners Noticed
T10373137 (P21286002) (P21286001) | Arroz 138-kV Switch Station | Wharton | Construct 138-KV Switch Station three 40kA, 3000A breakers, EPS metering for Crawfish terminal. | 2022-09-03 | 2023-05-08 |  |  | 5323766 |  |  | 30 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property purchased
T10478303 (A22031001) | Aransas Pass 69-kV Substation: Replace CAP Bank | Aransas Pass/ San Patricio | Replace 69-kV, 11.5 MVAR Capacitor Bank No. 8887 with the new standard Cap Bank design, as well as replacing the disconnect switch as necessary, and replacing the circuit breaker/ circuit switcher with a new cap bank breaker that includes the CT function. | 2022-09-21 | 2022-11-08 |  |  | 792662.64 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10479893 (A22031013) | Victoria PS 69-kV Station: Replace CAP Bank | Victoria/ Victoria | Replace 69-kV, 28.7 MVAR Capacitor Bank No. 1317 with the new standard Cap Bank design, as well as replacing the disconnect switch as necessary, and replacing the circuit breaker/ circuit switcher with a new cap bank breaker that includes the CT function. | 2022-09-28 | 2022-11-15 |  |  | 892083.13 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T101402020 (P19167001) | North Edinburg 138-kV Station: Install 138-kV Reactor | Edinburg/Hidalgo | Install 138-kV Reactors on Low Side of 345/138 kV Autos to limit fault current at 138 kV. | 2022-09-17 | 2022-10-30 | 2022-12-20 |  | 3591824 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T101918930 (P19167002) | North Edinburg 138-kV Station: Upgrade 138-kV Bus | Edinburg/Hidalgo | Upgrade 138-kV station busses. | 2022-09-17 | 2023-10-28 |  |  | 4774576 |  |  | 10 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10356892 (P17041002) (P17041003) (P17041004) (P17041007) | Brackettville - Escondido 138-kV T-Line | Brackettville/Kinney, Eagle Pass/Maverick | Construct approximately forty-six (46) miles of new 138-kV transmission line from the Brackettville 138-kV Substation to the Escondido 138-kV Substation. | 2022-11-10 | 2024-02-23 |  | 59041000 | 74811842 |  |  | 0 |  | 138 | 45.15 | 795 ACSS "Drake" | Steel Mono Pole & Braced Line Post (BLP) |  |  | 100 | 44.9 | 50545 | PUC Docket 50545 Approved on 05/25/2021
T10356856 (P17041005) | Brackettville 138-kV Substation | Brackettville/Kinney | Add 138-kV Circuit Breaker (3000A, 40KA). All series equipment 2200 amp minimum (Escondido). Necessary relay protection and telecom upgrades (MUX) for new terminal. | 2023-07-12 | 2024-02-23 |  | 1084000 | 835879 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | PUC Docket 50545 Approved on 05/25/2021 Within station property
T10356851 (P17041006) | Escondido 138-kV Substation | Eagle Pass/Maverick | Add (1) 138-kV Circuit Breaker (3000A, 40KA) , convert station from ring to breaker and half layout. All series equipment 2200A minimum (Bracketville). Necessary protection and and telecom upgrades (MUX) for new terminal.. | 2023-07-12 | 2024-02-23 |  | 1748000 | 875918 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | PUC Docket 50545 Approved on 05/25/2021 Within station property
T10479928 (A22031016) | Wormser Road 138-kV Switch Station: Replace CAP Bank | Webb | Replace 138-kV, 11.5 MVAR Capacitor Bank No. 1293 with the new standard Cap Bank design, as well as replacing the disconnect switch as necessary, and replacing the circuit breaker/ circuit switcher with a new cap bank breaker that includes the CT function. | 2023-03-02 | 2023-04-21 |  |  | 910604.8 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10491597 (A22031005) | Frontera 138-kV Switch Station: Replace CAP Bank | Palmview/ Hidalgo | Replace 138-kV, 34.6 MVAR Capacitor Bank No. 975 with the new standard Cap Bank design, as well as replacing the disconnect switch as necessary, and replacing the circuit breaker/ circuit switcher with a new cap bank breaker that includes the CT function. | 2022-11-29 | 2023-04-11 |  |  | 953224.26 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10478079 (A22031006) | Frontera 138-kV Switch Station: Replace CAP Bank | Palmview/ Hidalgo | Replace 138-kV, 34.6 MVAR Capacitor Bank No. 1025 with the new standard Cap Bank design, as well as replacing the disconnect switch as necessary, and replacing the circuit breaker/ circuit switcher with a new cap bank breaker that includes the CT function. | 2022-12-06 | 2023-04-11 |  |  | 953224.26 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10479924 (A22031015) | Weslaco Unit 138-kV Substation: Replace CAP Bank | Weslaco/Hidalgo | Replace 138-kV, 23 MVAR Capacitor Bank No. 908 with the new standard Cap Bank design, as well as replacing the disconnect switch as necessary, and replacing the circuit breaker/ circuit switcher with a new cap bank breaker that includes the CT function. | 2023-03-02 | 2023-04-21 |  |  | 901723 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10479912 (A22031014) | Weslaco 138-kV Switch Station: Replace CAP Bank | Weslaco/Hidalgo | Replace 138-kV, 46.1 MVAR Capacitor Bank No. 6490 with the new standard Cap Bank design, as well as replacing the disconnect switch as necessary, and replacing the circuit breaker/ circuit switcher with a new cap bank breaker that includes the CT function. | 2022-12-13 | 2023-04-17 |  |  | 1004755.4 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42644784 (P16067006) (P16067013) (P16067017) | Valero East 69-kV Substation: Add Box Bay | Nueces | Expand existing Valero East 69-kV substation to add a new box bay and 200MVA, 138/69kV auto transformer, and 1-138-kV breaker before the auto. Add 2 breakers to the new box bay and 1 new breaker to the existing north west box bay. All new equipment will be 138-kV rate at 3000A continuous, 40kA fault current. The Valero East breakers will operate at 69-kV. Install H-Frame Station Dead-End Structure. | 2022-10-24 | 2023-03-07 |  |  | 7364430 |  |  | 60 | 69 | 138/69 |  |  | Steel H-Frame Deadend |  |  |  |  | 16 TAC 25.83(a)(3) | Landowner consent/easement obtained for expansion
T10407513 (P21286009) (P21286010) | Arroz - Crawfish 138-kV T-Line | Wharton | Construct a 0.10 mile 138-kV Span to interconnect Arroz 138-kV Switch Station to Prairie Switch Wind Point of Interconnect. Install transmision fiber cable. | 2022-11-01 | 2023-05-14 |  |  | 1163951 |  |  | 0 |  | 138 | 0.1 | 795 KCM ACCS "Drake" | Steel Deadend |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
T10568711 (P19190010) (P19190011) (P19190003) | Lane City - Magill 138-kV Rebuild | Wharton, Bay City/Matagorda | Rebuild and reconductor the Lane City to Magill 138-kV transmission line. | 2022-10-03 | 2023-03-06 |  |  | 29573087.2438 |  |  | 50 | 138 |  | 13.4 | 795 KCM ACCS "Drake" | Steel Mono Pole | Centerline | 13.4 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easemsnts Landowners Noticed
T10127219 (P19190004) | Lane City 138-kV Substation | Wharton | Terminate fiber from Lane City and Bay City 138-kV stations. Install Telecom equipment. Install new jumpers from bus to line terminal. Add/remove equipment to upgrade the line relaying to fiber base protection. | 2022-11-14 | 2022-12-19 |  |  | 255250 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10124412 (P19190005) | Magill 138-kV Substation | Bay City/Matagorda | Terminate fiber from Lane City and Bay City 138-kV stations. Install Telecom equipment. Install new jumpers from bus to line terminal. Add/remove equipment to upgrade the line relaying to fiber base protection. | 2022-12-19 | 2023-01-16 |  |  | 406320 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10124422 (P19190006) | Bay City 138-kV Substation | Bay City/Matagorda | Install new jumpers from bus to line terminal. Add/remove equipment to upgrade the line relaying to fiber base protection, including DICM expansion module & panel. | 2022-11-14 | 2023-04-17 |  |  | 672372 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10254321 (P20088013) | Premont 69-kV Substation: Upgrade | Calallen/ Nueces | Upgrade Jumpers. Upgrade all the series elements to at least 795 Amps.. | 2022-11-28 | 2023-05-12 |  |  | 8331007 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station property
T10329403 (P20148001) | North Edinburg 138-kV Station:: Add CB's for Red Gate and Rachel Termimations | Edinburg/Hidalgo | Install three 138kV, 63kA, breakers and respective circuit breaker relaying. Install new line relaying on re-terminated Falfurrias Line and Faysville Tap STEC Line. Install metering on Faysville Tap STEC terminal. | 2022-10-17 | 2023-02-24 |  |  | 2603466 |  |  | 25 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
TS0257799 (A18807093) | Lon Hill 138/345-kV Switch Station: 138-kV CB Failure | Calallen/ Nueces | Replace failing 138-kV Circuit Breakers CB-5660, CB-7035, CB-8940, CB-5670 and CB-7075. | 2022-11-08 | 2022-12-27 |  |  | 625000 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station property
T10478088 A22031007 | La Palma PS 138-kV Station: Replace CAP Bank | San Benito/ Cameron | Replace 138-kV, 46.1 MVAR Capacitor Bank No. 2015 with the new standard Cap Bank design, as well as replacing the disconnect switch as necessary, and replacing the circuit breaker/ circuit switcher with a new cap bank breaker that includes the CT function. | 2022-11-04 | 2023-03-20 |  |  | 1014944.9 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station property
T10478090 A22031008 | La Palma PS 138-kV Station: Replace CAP Bank | San Benito/ Cameron | Replace 138-kV, 46.1 MVAR Capacitor Bank No. 55 with the new standard Cap Bank design, as well as replacing the disconnect switch as necessary, and replacing the circuit breaker/ circuit switcher with a new cap bank breaker that includes the CT function. | 2022-11-08 | 2023-03-20 |  |  | 1014945.3 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station property
T10478486 A22031010 | Miltary Highway 138-kV Substation: Replace CAP Bank | Brownsville/ Cameron | Replace 138-kV, 57.6 MVAR Capacitor Bank No. 6485 with the new standard Cap Bank design, as well as replacing the disconnect switch as necessary, and replacing the circuit breaker/ circuit switcher with a new cap bank breaker that includes the CT function. | 2022-11-15 | 2023-04-05 |  |  | 1067343.59 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station property
T10478491 A22031011 | Miltary Highway 138-kV Substation: Replace CAP Bank | Brownsville/ Cameron | Replace 138-kV, 57.6 MVAR Capacitor Bank No. 1145 with the new standard Cap Bank design, as well as replacing the disconnect switch as necessary, and replacing the circuit breaker/ circuit switcher with a new cap bank breaker that includes the CT function. | 2022-11-22 | 2023-01-11 |  |  | 1067343.59 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station property
T10277666 A20082003 | Eagle Pass 138-kV Substation: HVDC Removal | Eagle Pass/ Maverick | Install DICM to house new CFE line relaying panel , breaker #7395 control relaying panel, Block Load Transfer relaying panel, and metering relaying panel. Replace switch #3002 with a solid bus. | 2022-11-07 | 2023-03-31 |  |  | 1300000 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station property
T1016440a (A18050002) (A18050003) | N. Padre Island Tap to N. Padre T-line: Reconductor | N. Padre Island / Nueces | Re-conductor one of the double-circuit conductors along the N. Padre Island Tap to N. Padre Island 69-kV transmission line from 1/A to North Padre Island and back to LCRA’s structure one span north of 1/B. | 2022-11-10 | 2023-02-09 | 2023-02-09 |  | 2491649.94 |  |  | 95 | 69 |  | 7.64 | 795 KCM ACSS "Drake" |  | various | 3.82 | various |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed. Landowner consent obtained as necessary.
T10329365 (P20148002) | Falfurrias - N Edinburg 138-kV T-Line | Edinburg/Hidalgo | Reterminate the Falfurrias to N Edinburg 138-kV transmission line into N Edinburg 138-kV Station. | 2023-01-23 | 2023-02-27 |  |  | 807344 |  |  | 60 | 138 |  | 0.14 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
T10443543 (P20148003) | N Edinburg - Red Gate 138-kV T-Line | Edinburg/Hidalgo | Terminate the N Edinburg to Red Gate 138-kV transmission line into N Edinburg 138-kV Station. | 2023-01-23 | 2023-02-27 |  |  | 589218 |  |  | 60 | 138 |  | 0.08 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
T10316420 (DP21X02D0) | North Weslaco 138-kV Substation: T-Station Assets | Weslaco/Hidalgo | Replace Existing T-RTU: D20MEII to Eaton Cooper SG4250 - Connect T-RTU to D-RTU via Serial Fiber link. Install Transformer DNP Metering: Bitronics M650 3EL - Connect to T-RTU via Serial Fiber Link. | 2023-01-03 | 2023-05-30 |  |  | 223824 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10254307 (P20088001) (P20088007) | Alice - N. Ella 69-kV T-Line | Alice/Jim Wells | Rebuild and reconductor a segment of the existing Alice to N. Ella 69-kV transmission line that was not included in prior rebuild work of this transmission line in prior years. Relocate two segments of this transmission line due to existing building encroachments. The transmission line will be built to 138-kV standards but will continue to operate at 69-kV. | 2022-12-12 | 2023-05-03 |  |  | 8331007 |  |  | 0 | 69 |  | 2.87 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 2.76 | 70 | 0.41 | 16 TAC 25.101 (c)(5)(B) & 16 TAC 25.101 (c)(5)(E) | Utilizing existing easements. Landowners Noticed. Landowner consent obtained as necessary.
T10395700 (P21308001) | Clarkwood 138-kV Substation: Breaker Terminal | Corpus Christi/ Nueces | Install three (3) 3000A, 40kA, 138-kV Breakers. Install one (1) New Terminal for Carina 138-kV Line. Buss should be designed for 3000A. Terminate Fiber. Install EPS metering. Replace Deadend on the Lon Hill 138 kV terminal and (2) wood shield wire poles | 2023-01-17 | 2023-11-29 |  |  | 3509621 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station property
T10395704 (P21308003) | Clarkwood to Carina 138-kV T-Line | Corpus Christi/ Nueces | Construct a 0.04 mile 138-kV dead end structure outside of the Clarkwood station fence along with the first span of the gen-tie line. | 2023-01-17 | 2023-11-29 |  |  | 479978 |  |  | 0 | 138 |  | 0.04 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP property
T10194279 (P20084001) | Laredo Plant 138-kV Station | Laredo/Webb | Upgrade Buss to 2000 A capacity Upgrade Buss #1 & Buss #2 to dual 1272 AAC. Add single Buss supports for long jumpers. Update Jumpers to Buss. Update (1) Disconnect Switch Upgrade the Relay settings as needed | 2023-02-15 | 2023-05-12 |  |  | 500000 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station property
T10358068 (P20164002) (P20164001) | Peregrine Solar Interconenction: Raptor 345-kV Station | Goliad | Construct new 345-kV Station. Three breaker Ring Bus. Install SSO relaying in monitoring mode for the Pergrine Terminal. 3000 A breakers. Install DICM. | 2023-01-02 | 2023-10-30 |  |  | 13612545 |  |  | 20 |  | 345 | [7 empty] | 16 TAC 25.83(a)(3) | Property purchased
T10409831 (P20164011) | Peregrine Solar Interconnection: Chase Field to Raptor Install Fiber | Goliad | Install Fiber Optic cable from nearest telecom fiber route. | 2023-01-02 | 2023-10-30 |  |  | 2101278 |  |  | 20 | 345 | [8 empty] | 16 TAC 25.83(a)(3)
T10254308 (P20088002) | Premont 69-kV Substation | Premont/Jim Wells | Upgrade jumpers. Upgrade all the series elements to at least 795 amps All upgrades performed in Premont Station. | 2023-01-02 | 2023-05-12 |  |  | 802435 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within AEP Property
T10254309 (P20088003) | Falfurrias 69-kV Substation | Falfurrias/Brooks | Upgrade jumpers. Upgrade all the series elements to at least 795 amps All upgrades performed in Falfurrias Station. | 2023-01-02 | 2023-05-12 |  |  | 954985 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within AEP Property
T10373138 (P21286006) (P21286007) | El Campo - Lane City Switch 138-kV T-Line | Wharton | Terminate the El Campo to Lane City 138-kV transmission line into the new Arroz 138-kV Switch Station. Install transmision fiber cable. | 2023-01-02 | 2023-07-01 |  |  | 1961699 |  |  | 0 | 138 |  | 0.3 | 795 KCM ACCS "Drake" | Steel Mono Pole |  |  | 100 | 0.3 | 16 TAC 25.101 (c)(5)(A) | Landowner consent obtained
TL0045561 A22027001 | Crestonio - Falfurrias 138-kV T-Line | Duval, Jim Hogg, Brooks | Replace insulators and install new Bird Guards to reduce animal damages. | 2023-01-03 | 2023-03-09 |  |  | 967052 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3)
TL0045560 A22025001 | Bruni - Crestonio 138-kV T-Line | Webb, Duval | Replace insulators and install new Bird Guards to reduce animal damages. | 2023-03-09 | 2023-04-28 |  |  | 543498 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3)
TL0045559 A22026001 | Lobo - Bruni 138-kV T-Line | Webb | Replace insulators and install new Bird Guards to reduce animal damages. | 2023-09-15 | 2023-11-27 |  |  | 1041302 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3)
T10466221 A22807003 | North Edinburg 138-kV Station | Edinburg/Hidalgo | North Edinburgh - Failed PLC Control Replacement | 2023-02-27 | 2023-03-31 |  |  | 307000 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10466198 A22807004 | Rio Hondo 138-kV Station | Cameron | Rio Hondo - Failed PLC Control Replacement | 2023-02-25 | 2023-03-31 |  |  | 307000 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10412307 (P21286003) | El Campo 138-kV Substation | Wharton | Upgrade relays at the El Campo 138-kV Substation | 2023-04-03 | 2023-05-15 |  |  | 462232.6228 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10412707 (P21286004) | Lane City 138-kV Switch Station | Wharton | Upgrade relays at the Lane City 138-kV Switch Station | 2023-04-03 | 2023-05-15 |  |  | 465719.9037 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10358071 (P20164004) | Peregrine Solar Interconnection: Coleto Creek - Grissom 345-kV Cut-In | Goliad | Terminate the Coleto Creek to Grisson 345-kV transmission line into the new Raptor 345-kV Station. | 2023-04-03 | 2023-10-30 |  |  | 1908878 |  |  | 0 | 345 |  | 0.5 | 795 KCM ACCS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP Property
T10372472 (P20164007) (P20164008) | Peregrine Solar Interconnection: Raptor - Peregrine 345-kV T-Line | Goliad | Construct a 0.05 span of 345-kV transmission line from Raptor 345-kV Station to Peregrine Solar POI. | 2023-04-03 | 2023-10-30 |  |  | 884110 |  |  | 0 |  | 345 | 0.05 | 795 KCM ACCS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP Property
T10372481 (P20164009) | Peregrine Solar Interconnection: Coleto Creek 345-kV Station Relay Work | Goliad | Coleto Creek 345-kV Station: Update carrier equipment on Raptor terminal and terminal name plates. | 2023-04-03 | 2023-10-30 |  |  | 278384 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within AEP Property
T10362984 (P20165001) (P20165002) (P20165011) | Static 345-kV Station: Interconnection for Charger Solar Generator | Refugio | Construct a new 345-kV station with three (3) breaker ring bus for the Cut-In of the Angstrom to STP 345-kV transmission line and interconnection with a new Charger Solar Geneneration Station. | 2023-03-06 | 2024-04-01 |  |  | 16314346 |  |  | 0 |  | 345 | [7 empty] | 16 TAC 25.83(a)(3) | Property Acquired
T10368791 (P20165007) (P20165008) | Static - Charger 345-kV T-Line: Build | Refugio | Construct a 345-kV single-span with DE Structure and EPS meter for Generator (AP Solar 4, LLC) Point of Interconnect. | 2023-07-01 | 2024-04-01 |  |  | 1564510 |  |  | 0 |  | 345 | 0.05 | 2X795 KCM ACCS "Drake" | Steel Mon Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within station property
T10390825 (P20165009) | Angstrom: Relay Work | Refugio | Update relaying and revise line settings for Static line terminal. | 2024-02-15 | 2024-04-01 |  |  | 266251 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
T10393647 (P20165010) | Refugio to Static Fiber Cables & ROW | Refugio | Install 21 miles of 96 count ADSS | 2023-07-01 | 2024-04-01 |  |  | 1745257 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3)
T10277215 DP20X03C2 | Mathis Sub - Sandia STEC 69-kV POI | San Patricio | Install new point of interconnect (POI) structure outside of new Mathis Substation for STEC to interconnect to their existing Sandia 69-kV Substation | 2023-06-30 | 2023-11-18 |  |  | 320244 |  |  | 0 | 69 |  | 0.01 | 795 ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within existing property
T10277523 DP20X03C3 | Mathis - Mathis STEC 69-kV POI | San Patricio | Install new point of interconnect (POI) structure outside of new Mathis Substation for STEC to interconnect to their existing Mathis 69-kV Substation | 2023-06-30 | 2023-11-18 |  |  | 319829 |  |  | 0 | 69 |  | 0.01 | 795 ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within existing property
T10437319 P21260005 | Antlia WSL Metering | Del Rio/Val Verde | Install whole sale metering at Broad Reach Power's Antlia battery facility that will be adjacent to AEPs Maxwell Station | 2024-03-06 | 2025-05-30 |  |  | 301997 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within developers property
TA1904501 P22951001 | Brookhollow 69-kV Substation | Port Lavaca/Calhoun | Install 69-kV Autotransformer | 2023-03-31 | 2023-05-31 |  |  | 1358144 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within AEP Property
TA1904501 P22951002 | Brookhollow 69-kV Substation: 138/69-kV POI | Port Lavaca/Calhoun | Construct a Vertical 138-kV T-Line structure just outside the station. Structure #24 has two anchors that will need to be replaced due to grade improvement. Install jumpers to terminate it to the Brookhollow to Point Comforrt 138-kV transmission line and install jumpers to terminate it to the Brookhollow to Palacios 69-kV transmission line. | 2023-03-15 | 2023-05-31 |  |  | 798331 |  |  | 0 |  | 138/69 | 0.01 | 795 ACSS "Drake" | Wooden Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP Property
42998736 (P19190001) (P19190002) (P19190003) | Magill - Bay City 138-kV Rebuild | Bay City/Matagorda | Rebuild and reconductor the Magill to Lane City 138-kV transmission line. | 2023-03-06 | 2023-04-17 |  |  | 7154779.1719 |  |  | 0 | 138 |  | 1.84 | 795 KCM ACCS "Drake" | Steel Mono Pole | Centerline | 1.37 | 100 | 0.47 | 16 TAC 25.101 (c)(5)(B) & 16 TAC 25.101 (c)(5)(E) | Landowners Noticed Landowner consent obtained as needed
T1016440b (A18050002) (A18050003) | N. Padre Island Tap to N. Padre T-line: Reconductor | N. Padre Island / Nueces | Re-conductor the remaining double circuit conductor along the N. Padre Island Tap to N. Padre Island 69-kV transmission line from 1/A to North Padre Island and back to LCRA’s structure one span north of 1/B. | 2023-02-01 | 2023-03-01 |  |  | 4416350.06 |  |  | 0 | 69 |  | 7.64 | 795 KCM ACSS "Drake" |  | various | 3.82 | various |  | 16 TAC 25.101 (c)(5)(B) | Landowner consent obtained
T10372464 (P20164005) | Coleto Creek to Grissom TFC | Goliad | Install telecom fiber components | 2023-04-06 | 2023-10-31 |  |  | 282190 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within AEP Property
42640431 (P16067001) (P16067005) | Champlin to Valero East 138-kV T-Line | Nueces | Construct a new 138-kV transmission line from the existing AEP Texas Champlin 138-kV Substation to the existing AEP Texas Valero East 138-kV Substation. | 2023-02-20 | 2023-05-31 |  | 5094497 |  |  |  | 0 |  | 138 | 1.52 | 795 KCM ACSS "Drake" | Steel Monopole |  |  | 50' | 1.52 | 54144 | Docket No. 54144 Approved 02/08/2023