## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
1006 | T416 (Dripping Springs to Rutherford) Relocation | Hays | Relocate seven structures as requested and reimbursed by landowner. | 2019-09-01 |  |  |  | 1844000 |  |  | 0% | 138 | 138 | 0.47 | 795 ACSR | Steel Single Pole | 100 | 0.35 | 100 | 0.47 | 25.101(c)(5)(D) | Actual construction start date has been delayed.
200TRL001 | Marshall Ford to Trading Post (T315) | Travis | Storm hardening project to replace existing structures and conductor. | 2022-09-16 |  |  |  | 12600000 |  |  | 87% | 138 | 138 | 7.72 | 2x795 kcmil Drake; 1011 kcmil ACCC Galveston | DC Lattice Tower (existing) and Single Circuit Steel Pole | 100 | 7.72 | n/a | n/a | 25.101(c)(5)(B)
506-001-0001 | Buttercup Double-Bus Double-Breaker Rebuild | Williamson | Rebuild Buttercup Substation to a double-bus double-breaker configuration | 2022-09-26 |  |  |  | 3000000 |  |  | 80% | 138 | 138 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 25.83
1000-001-0011 | Sattler to Fischer (T319) | Comal | Raise the line over Canyon dam outflow area | 2022-10-03 |  |  |  | 2818000 |  |  | 99% | 138 | 138 | 6.70 mi | 795 MCM Drake, 2 cond per phase | Steel Monopoles | Variable | 6.7 | n/a | n/a | 25.101(c)(5)(B)
1000-001-0012 | Miller Creek to Henly (T415) | Blanco | Storm hardening project to replace existing structures and conductor. | 2022-10-17 |  |  |  | 851000 |  |  | 99% | 138 | 138 | 9.45 mi | 795 MCM Drake, 1 cond per phase | Steel Monopoles | 100 | 9..45 | n/a | n/a | 25.101(c)(5)(B)
1000-001-0001 | Paleface to Marshall Ford (T323) | Travis | Conductor change out in double circuit section (3.6 miles being reconductored concurrent with the Marshall Ford to Trading Post Project) | 2022-09-16 |  |  |  | 1900000 |  |  | 99% | 138 | 138 | 11.5 mi | 1011 kcmil ACCC, 2 cond per phase |  | 100 | 11.5 mi | n/a | n/a | 25.101(c)(5)(B) | This scope is being performed as part of the T315 Project # 200TRL001. It is now listed separately to describe the scope associated with T323.
1000-001-0009 | ML-HT Single Circuit (T324) | Hays | Storm hardening project to replace 1.6 miles of existing structures and conductor. | 2023-03-01 |  |  |  | 2600000 |  |  |  | 138 | 138 | 3.11 mi | 795 MCM Drake, 2 cond per phase | Steel Monopoles | 100 | 3.11 mi | n/a | n/a | 25.101(c)(5)(B)
400-001-0001 | Hero Way Substation | Williamson | New 138 kV load-serving substation | 2023-03-01 |  |  |  | 9155000 |  |  |  | 138 | 138 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 25.83
500-001 | Junction North Substation Relocation | Kimble | Relocate PEC Junction Substation 370-ft northeast to the new Junction North Substation | 2023-04-17 |  |  |  | 6746000 |  |  |  | 69 | 69 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 25.83
000-001-0003 | Leander to Hero Way (T327) Nameless to Hero Way (T760) | Williamson / Travis | Overhaul and rebuild the existing T327 to bundled 795 ACSR and provide interconnect for Hero Way Substation | 2023-06-01 |  |  |  | 9600000 |  |  |  | 138 | 138 | 6.9 | 795 MCM Drake, 2 cond per phase | Steel Monopoles | 100 | 6.9 | n/a | n/a | 25.101(c)(5)(A)&(B)
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.