STANDARD APPLICATION FOR A CERTIFICATE OF CONVENIENCE AND NECESSITY FOR A PROPOSED TRANSMISSION LINE

DOCKET NO. 55067

Submit seven (7) copies of the application and all attachments supporting the application.  If the application is being filed pursuant to 16 Tex. Admin. Code §25.101(b)(3)(D) (TAC) or 16 TAC §25.174, include in the application all direct testimony.  The application and other necessary documents shall be submitted to:

Public Utility Commission of Texas 
Attn: Filing Clerk 
1701 N. Congress Ave.

Austin, Texas 78711-3326

Note:  As used herein, the term “joint application” refers to an application for proposed transmission facilities for which ownership will be divided.  All applications for such facilities should be filed jointly by the proposed owners of the facilities.

1.	Applicant (Utility) Name:

For joint applications, provide all information for each applicant.

Applicant (Utility) Name:	Oncor Electric Delivery Company LLC (“Oncor”)

Certificate Number:	30043

Street Address:	1616 Woodall Rodgers Freeway

Dallas, Texas 75202

Mailing Address: 	1616 Woodall Rodgers Freeway

Dallas, Texas 75202-1234

2.	Please identify all entities that will hold an ownership interest or an investment interest in the proposed project but which are not subject to the Commission’s jurisdiction.

Oncor will hold the sole ownership interest in the Ramhorn Hill Switch – Dunham Switch 345 kilovolt (“kV”) Transmission Line Project (the “Proposed Transmission Line Project”).

3.	Person to Contact: 	Chris Reily
Title/Position:	Regulatory Manager 
Phone Number:	(214) 486-4717
Mailing Address:	1616 Woodall Rodgers Fwy, Suite 6A-012

Dallas, Texas  75202-1234

Email Address:	Chris.Reily@oncor.com

3a.	Alternate Contact:	Thomas Yamin
Title/Position:	Director of Regulatory, Transmission & Planning
Phone Number:	(214) 486-3512
Mailing Address:	1616 Woodall Rodgers Fwy, Suite 6B-005

Dallas, Texas  75202-1234

Email Address:	Thomas.Yamin@oncor.com

3b.	Legal Counsel:	Jaren A. Taylor

Jared M. Jones

Phone Number:	(214) 220-7754
Mailing Address:	Vinson & Elkins LLP

Trammell Crow Center

2001 Ross Avenue, Suite 3900

Dallas, Texas 75201

Email Address:	jarentaylor@velaw.com

jjones@velaw.com

Please contact Jaren Taylor with any inquiries regarding the project.

4.	Project Description:

Provide a general description of the project, including the design voltage rating (kV), the operating voltage (kV), the CREZ Zone(s) (if any) where the project is located (all or in part), any substations and/or substation reactive compensation constructed as part of the project, and any series elements such as sectionalizing switching devices, series line compensation, etc.  For HVDC transmission lines, the converter stations should be considered to be project components and should be addressed in the project description.

If the project will be owned by more than one party, briefly explain the ownership arrangements between the parties and provide a description of the portion(s) that will be owned by each party.   Provide a description of the responsibilities of each party for implementing the project (design, Right-Of-Way acquisition, material procurement, construction, etc.).

If applicable, identify and explain any deviation in transmission project components from the original transmission specifications as previously approved by the Commission or recommended by a PURA §39.151 organization.

Name or Designation of Project:		Ramhorn Hill Switch – Dunham Switch 345 kV Transmission Line Project

Design Voltage Rating (kV):		345 kV

Operating Voltage Rating (kV):		345 kV

Normal Peak Operating Current (A):	5,138 A

The Proposed Transmission Line Project is a new double-circuit 345 kV transmission line to be built on triple-circuit capable structures between the proposed Ramhorn Hill Switch and the proposed Dunham Switch. The structures will have two 345 kV circuits initially installed with a vacant third circuit position capable of accommodating a future 138 kV circuit.

The proposed Ramhorn Hill Switch will be located approximately 2 miles south of the intersection of United States Highway (“US”) 287 and State Highway (“SH”) 114 near Rhome, Texas.  The proposed Dunham Switch will be located approximately 1.4 miles southeast of the intersection of US 377 and Farm-to-Market Road (“FM”) 1171 (regionally known as Cross Timbers Road) in Flower Mound, Texas.

The length of the Proposed Transmission Line Project is approximately 20 to 23 miles, depending on which route is selected by the Public Utility Commission of Texas (“PUCT” or “Commission”).

The Proposed Transmission Line Project includes the construction of the proposed Ramhorn Hill Switch and the proposed Dunham Switch.

5.	Conductor and Structures:

Conductor Size and Type:  	1926.9 kcmil Aluminum Conductor Steel Supported Trapezoidal-Shaped Wire (“ACSS/TW”)

Number of conductors per phase: 	2

Continuous Summer Static Current Rating (A):	5,138 A

Continuous Summer Static Line Capacity

at Operating Voltage (MVA):	3,070 MVA

Continuous Summer Static Line Capacity

at Design Voltage (MVA):	3,070 MVA

Type and composition of Structures:	Triple-Circuit Steel Monopole

Height of Typical Structures:	120 – 175 feet*

*This number reflects the approximate visible height of the structure from ground to structure top.  Please see the drawing of the typical structures in Figure 1-2, page 1-7, of the Environmental Assessment and Alternative Route Analysis for the proposed Ramhorn Hill Switch–Dunham Switch 345 kV Transmission Line Project in Denton and Wise Counties, Texas for Oncor Electric Delivery Company LLC (“Environmental Assessment and Routing Study”), prepared by Halff Associates, Inc. (“Halff”) and included as Attachment No. 1.

Explain why these structures were selected; include such factors as landowner preference, engineering considerations, and costs comparisons to alternate structures that were considered.

For joint applications, provide and separately identify the above-required information regarding structures for the portion(s) of the project owned by each applicant.

Oncor selected the triple-circuit capable 345 kV steel monopole for numerous reasons including technical specifications, the compact structure footprint, reduced right-of-way (“ROW”) width requirements, the specific characteristics of the study area, the ability to accommodate a future 138 kV circuit, and other engineering-related reasons.

Provide dimensional drawings of the typical structures to be used in the project.

A drawing of the typical structure is shown in Figure 1-2, page 1-7, of the Environmental Assessment and Routing Study included as Attachment No. 1.

6.	Right-of-way:

For joint applications, provide and separately identify the above-required information for each route for the portion(s) of the project owned by each applicant.

Miles of Right-of-Way	Approximately 19.9 to 22.9 miles 
Miles of Circuit	Approximately 39.8 to 45.8 miles 
Width of Right-of-Way	100 feet
Percent of Right-of-Way Acquired	0%

Provide a brief description of the area traversed by the transmission line.  Include a description of the general land uses in the area and the type of terrain crossed by the line.

The project area is situated within Denton and Wise Counties and has numerous incorporated cities contained within, or extending into, the project area.  A great proportion of the project area is currently vacant land, consisting primarily of grassland and agricultural areas, yet the area is developing rapidly.  Urbanized areas are generally clustered along major transportation corridors such as Interstate Highway (“IH”) 35W, US 377, US 287, FM 156 and SH 114.  Much of the existing vacant property in the project area is being converted to master planned residential communities and for commercial and industrial uses.  Existing residential communities and subdivisions are located in pockets throughout the project area.  Existing commercial and industrial development is also spread throughout the project area, but is mostly concentrated near the IH 35W, US 377, and SH 114 corridors in the southern portion of the project area.

Several federal recreational areas associated with Lake Grapevine, the Denton Creek floodplain, and the Denton Creek’s tributaries extend into the eastern third of the project area.  The United States Army Corps of Engineers (“USACE”) owns and manages Lake Grapevine and the surrounding federal management areas.  The Denton Creek “Environmentally Sensitive Area,” as identified by the USACE, comprises most of the USACE recreational area in the eastern third of the project area.  This area is a large contiguous band of high-quality habitat for numerous species of wildlife.

South and west of the USACE property, in the area surrounding the intersection of IH 35W and SH 114, the project area contains dense urban/suburban development, including numerous residential subdivisions, commercial and industrial business parks, transportation/logistics operations, recreational facilities, the Texas Motor Speedway, Fort Worth Alliance Airport, and the BNSF Railway Company Intermodal Rail Yard.

Specific discussion regarding natural, human, and cultural resources in the project area is set forth in Sections 3.1 through 3.8, pages 3-1 through 3-92, of the Environmental Assessment and Routing Study, included as Attachment No. 1.

7.	Substations or Switching Stations:

List the name of all existing HVDC converter stations, substations or switching stations that will be associated with the new transmission line.  Provide documentation showing that the owner(s) of the existing HVDC converter stations, substations and/or switching stations have agreed to the installation of the required project facilities.

Not Applicable.

List the name of all new HVDC converter stations, substations or switching stations that will be associated with the new transmission line.  Provide documentation showing that the owner(s) of the new HVDC converter stations, substations and/or switching stations have agreed to the installation of the required project facilities.

Oncor Proposed Ramhorn Hill Switch

The proposed Ramhorn Hill Switch will be located approximately 2 miles south of the intersection of US 287 and SH 114 near Rhome, Texas. ln order to establish the new 345 kV switchyard as part of the Proposed Transmission Line Project, Oncor will terminate the existing double-circuit Hicks to Willow Creek 345 kV transmission line into the proposed switch station. The switchyard will initially be constructed in a 12-breaker, breaker-and-a-half bus arrangement. Relay panels, SCADA and controls for the 345 kV switchyard equipment will be housed in a control center. The dimensions of the proposed Ramhorn Hill Switch station will be approximately 700 feet by 750 feet.  Ultimately, the proposed Ramhorn Hill Switch station site could be expanded to accommodate an 18-breaker, 345 kV ring bus arrangement and a potential 138 kV switchyard. The dimensions and additional details regarding the proposed preliminary layout of the Ramhorn Hill Switch station are illustrated in Attachment No. 2.

Oncor Proposed Dunham Switch

The proposed Dunham Switch will be located approximately 1.4 miles southeast of the intersection of US 377 and FM 1171 (regionally known as Cross Timbers Road) in Flower Mound, Texas. ln order to establish the new 345 kV switchyard as part of the Proposed Transmission Line Project, Oncor will terminate the existing Lewisville to Krum West and Lewisville to Roanoke 345 kV transmission lines into the proposed switch station. The switchyard will initially be constructed in a 12-breaker, breaker-and-a-half bus arrangement. Relay panels, SCADA, and controls for the 345 kV switchyard equipment will be housed in a control center. The dimensions of the proposed Dunham Switch station will be approximately 700 feet by 600 feet. Ultimately, the proposed Dunham Switch station site could be expanded to accommodate an 18-breaker, 345 kV ring bus arrangement and a potential 138 kV switchyard.  The dimensions and additional details regarding the proposed preliminary layout of the Dunham Switch station are illustrated in Attachment No. 2.

8.	Estimated Schedule:

| Estimated Dates of: | Start* | Completion* |
| --- | --- | --- |
| Right-of-way and Land Acquisition | 12/2023 | 12/2024 |
| Engineering and Design | 01/2024 | 10/2024 |
| Material and Equipment Procurement | 2/2024 | 10/2024 |
| Construction of Facilities | 12/2024 | 12/2025 |
| Energize Facilities | 12/2025 | 12/2025 |

*Dates are based on 180-day CCN process due to ERCOT critical designation.

9.	Counties: 
For each route, list all counties in which the route is to be constructed.

Wise County

Denton County

10.	Municipalities:

For each route, list all municipalities in which the route is to be constructed.

Portions of the proposed alternative routes will be constructed within the city limits of the following municipalities:

| Cities (East to West) | Routes |
| --- | --- |
| Flower Mound | All Filed Routes |
| Northlake | All Filed Routes |
| Justin | 1, 19, 29, 33, 36, 41, 42, 54, 65, 67, 68, 69, 71, 72, 86, 92, 94, 96, 103, 108, 116, 130, 132, 137, 138, 142, 143, 146, 154, 170, 175, 176, 178, 179, 184, 185, 186, 187, 191, 192, 207, 216, 217, 218, 219, 221 |
| Fort Worth | 3, 5, 10, 11, 13, 14, 15, 16, 18, 22, 23, 24, 25, 26, 28, 29, 43, 44, 58, 61, 63, 70, 78, 87, 116, 117, 119, 130, 132, 164, 179, 199, 200 |
| New Fairview | 67, 68, 69 |
| Rhome | 1, 11, 26, 33, 41, 42, 65, 67, 68, 69, 71, 72, 86, 92, 94, 96, 103, 117, 138, 142, 143, 154, 175, 176, 178, 184, 185, 192, 207, 216, 218 |

For each applicant, attach a copy of the franchise, permit or other evidence of the city's consent held by the utility, if necessary or applicable.  If franchise, permit, or other evidence of the city's consent has been previously filed, provide only the docket number of the application in which the consent was filed.  Each applicant should provide this information only for the portion(s) of the project which will be owned by the applicant.

To the extent necessary or appropriate, evidence of consent for service in this area is publicly available and previously filed in PUCT Docket No. 45.

11.	Affected Utilities: 
Identify any other electric utility served by or connected to facilities in this application.

No other electric utility will be served by or connected to the Proposed Transmission Line Project.

Describe how any other electric utility will be affected and the extent of the other utilities' involvement in the construction of this project.  Include any other electric utilities whose existing facilities will be utilized for the project (vacant circuit positions, ROW, substation sites and/or equipment, etc.) and provide documentation showing that the owner(s) of the existing facilities have agreed to the installation of the required project facilities.

No other electric utility will be involved in the construction of the Proposed Transmission Line Project, and no other electric utility’s facilities will be utilized.

12.	Financing:

Describe the method of financing this project.  For each applicant that is to be reimbursed for all or a portion of this project, identify the source and amount of the reimbursement (actual amount if known, estimated amount otherwise) and the portion(s) of the project for which the reimbursement will be made.

Oncor proposes to finance the facilities included in the Proposed Transmission Line Project with a combination of debt and equity in compliance with its authorized capital structure, which is similar to the means used for previous construction projects.  Oncor plans to utilize internally generated funds (equity) and proceeds received from the issuance of securities.  Oncor will typically obtain short-term borrowings as needed for interim financing of its construction expenditures in excess of funds generated internally.  These borrowings are then repaid through the issuance of long-term debt securities, the type and amount of which are as of yet undetermined.

Oncor is the sole applicant and, therefore, no other party will be reimbursed for any portion of the Proposed Transmission Line Project.

13.	Estimated Costs:

Provide cost estimates for each route of the proposed project using the following table.  Provide a breakdown of “Other” costs by major cost category and amount.  Provide the information for each route in an attachment to this application.

|  | Transmission Facilities | Station Facilities |  |
| --- | --- | --- | --- |
|  |  | Ramhorn Hill Switch | Dunham Switch |
| Right-of-way and Land Acquisition | * | $ 8,810,000 | $ 16,648,000 |
| Engineering and Design (Utility) | * | $ - | $ - |
| Engineering and Design (Contract) | * | $ 500,000 | $ 500,000 |
| Procurement of Material and Equipment (including stores) | * | $ 11,570,000 | $ 11,570,000 |
| Construction of Facilities (Utility) | * | $ 250,000 | $ 250,000 |
| Construction of Facilities (Contract) | * | $ 12,380,000 | $ 12,380,000 |
| Other (all costs not included in the above categories) | * | $ - | $ - |
| Estimated Total Cost | * | $ 33,510,000 | $ 41,348,000 |

*Refer to Attachment No. 3 for cost estimates for each alternative route presented in the    Application.

For joint applications, provide and separately identify the above-required information for the portion(s) of the project owned by each applicant.

Not applicable.

14.	Need for the Proposed Project:

For a standard application, describe the need for the construction and state how the proposed project will address the need.  Describe the existing transmission system and conditions addressed by this application.  For projects that are planned to accommodate load growth, provide historical load data and load projections for at least five years.  For projects to accommodate load growth or to address reliability issues, provide a description of the steady state load flow analysis that justifies the project.  For interconnection projects, provide any documentation from a transmission service customer, generator, transmission service provider, or other entity to establish that the proposed facilities are needed.  For projects related to a Competitive Renewable Energy Zone, the foregoing requirements are not necessary; the applicant need only provide a specific reference to the pertinent portion(s) of an appropriate commission order specifying that the facilities are needed.  For all projects, provide any documentation of the review and recommendation of a PURA §39.151 organization.

Overview

The Proposed Transmission Line Project is needed to address reliability issues identified in post-contingency conditions.  ERCOT designated this project as “critical to reliability” under 16 TAC § 25.101(b)(3)(D).

The Roanoke area, located approximately 15 miles north of Fort Worth, is one of the highest growth areas in the DFW Metroplex.  The 345 kV transmission system in this area is part of a high-power transfer corridor connecting generation in the Panhandle to the DFW load center.  The power transfer and load-serving capabilities of the system in this area depend on facilities developed as part of the Competitive Renewable Energy Zone, many of which are approaching their operating limits at current demand levels.  Capacity limitations in the area are already limiting the development of new large-point loads.  In the last 18 months, Oncor received several requests for interconnection in this area that Oncor was limited in its ability to fulfill due to prospective autotransformer and line overloads.  Growth in the area will continue to increase demand and strain the transmission system.  This necessitates additional transmission capacity to preserve reliability without overloading the existing transmission system or causing voltage support issues that could threaten system stability.

Oncor performed power flow studies and contingency analysis in accordance with NERC Reliability Standard TPL-001-4 and the ERCOT Planning Guide.  This analysis identified post-contingency system performance issues beginning in summer 2023, including thermal overloads, loading limitations, and voltage criteria exceedances.

The Proposed Transmission Line Project is the second in a series of projects, collectively called the “Roanoke Area Upgrades Project,” that will address the identified reliability issues and provide additional operational flexibility on the transmission system in the Roanoke area.  ERCOT reviewed the Roanoke Area Upgrades Project, including the Proposed Transmission Line Project, and endorsed it as a Tier 1 transmission project that is critical to the reliability of the ERCOT system.

Thermal Overloads

Starting in summer 2023, the 345/138 kV autotransformers at Hicks and Roanoke and the Roanoke – Hicks 345 kV transmission line will exceed their emergency ratings under contingency conditions.  Tables 1 and 2 below summarize the current configuration and resulting thermal overloads under N-1 (loss of a single generator or transmission element) and N-1-1 (loss of a generator or transmission element following an N-1 event) contingency events, as respectively defined in NERC TPL-001-4 Reliability Standard and the ERCOT Planning Guide.  Overloading is shown as a percentage of an element’s emergency rating.  These tables were created using ERCOT’s 2021 Regional Transmission Plan for the North and North Central weather zones (“2021 RTP NNC Cases”) and 2021 Steady State Working Group (“SSWG”) cases.

| Monitored Element | Worst Contingency (N-1) | Worst Contingency Loading (% of Emergency Rating) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2021 RTP NNC Cases |  |  | 2021 SSWG Cases |  |  |
|  |  | 2023 | 2024 | 2026 | 2027 | 2024 | 2028 |
| Roanoke 345/138 kV Autotransformer #1 | Roanoke 345/138 kV Autotransformer #2 (P1.3) | 92 | 94 | 96 | 96 | 101 | 110 |
| Roanoke 345/138 kV Autotransformer #2 | Roanoke 345/138 kV Autotransformer #1 (P1.3) | 94 | 95 | 98 | 98 | 101 | 110 |
| Roanoke – Hicks 345 kV double-circuit line | Loss of either Roanoke – Hicks 345 kV circuit (P1.2) | 89 | 87 | 91 | 93 | 99 | 107 |

Table 1 – Pre-project post N-1 contingency loading

| Monitored Element | Worst Contingency (N-1-1) | Worst Contingency Loading (% of Emergency Rating) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2021 RTP NNC Cases |  |  | 2021 SSWG Cases |  |  |
|  |  | 2023 | 2024 | 2026 | 2027 | 2024 | 2028 |
| Roanoke 345/138 kV Autotransformer #1 | Roanoke 345/138 kV Autotransformer + Roanoke – West Denton/Lewisville 345 kV double-circuit line (ERCOT Requirement) | 111 | 110 | 114 | 114 | 124 | 135 |
| Roanoke 345/138 kV Autotransformer #2 |  | 111 | 110 | 114 | 114 | 124 | 135 |
| Hicks 345/138 kV Autotransformer #1 | Hicks 345/138 kV Autotransformer + Hicks – Alliance/Roanoke 345 kV double-circuit line (ERCOT Requirement) | 99 | 98 | 101 | 102 | 113 | 123 |
| Hicks 345/138 kV Autotransformer #2 |  | 100 | 99 | 102 | 104 | 113 | 123 |
| Hicks – Roanoke 345 kV line | Panda Sherman Train and either Hicks – Roanoke 345 kV circuit (P3.2) | 95 | 93 | 97 | 99 | 104 | 113 |

Table 2 – Pre-project post N-1-1 contingency loading

Line Loading Limitations

Under peak load conditions, the Roanoke – Deen/Euless 138 kV double-circuit transmission line currently serves nearly 1,000 MW of load, as shown in Table 3.  Planning criteria exceedances were observed following a NERC P2.1 contingency, where (1) the loss of the Euless Switch – Bedford Woodson Tap 138 kV line (one section of the overall Roanoke – Deen/Euless transmission line) results in the Roanoke – Park Vista line section (east circuit) loading to 102% of its operating limit in the 2021 SSWG 2024 summer peak case, and (2) the loss of the Deen Switch – Watauga 138 kV line (also a section of the overall Roanoke – Deen/Euless transmission line) results in Roanoke – Park Vista line section (west circuit) loading to 102% of its operating limit in the 2021 SSWG 2027 summer peak case.  The Roanoke – Deen/Euless double circuit transmission line is approaching its loading limit, which will restrict Oncor’s ability to serve projected load growth in this area in the coming years.  The coincident peak load in the Roanoke area between 2017 and 2020 has grown at an annual rate of ~3.1%, which is about double the annual growth rate of Oncor’s overall coincident peak during this same period.  Table 3 lists forecasted load on the Roanoke – Deen/Euless double circuit transmission line through 2028.

| Line | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Roanoke – Deen | 471 | 478 | 494 | 500 | 504 | 517 | 527 |
| Roanoke – Euless | 474 | 481 | 509 | 516 | 523 | 536 | 546 |
| Total | 945 | 959 | 1003 | 1016 | 1027 | 1053 | 1073 |

Table 3 – Forecasted load on Roanoke – Deen/Euless double-circuit line (MW)

Voltage Criteria Exceedances

Starting in 2028, with the loss of Handley Unit #5 followed by the Roanoke – Park Vista 138 kV line section, several buses on the Roanoke – Deen 138 kV transmission line experience voltages are nearing or outside their emergency limits as shown in Table 4 (emergency limits for all listed elements are <0.90 or <0.92).

| Bus Number | Bus Name | Post Contingency Voltage (in p.u.) | Voltage Limit |
| --- | --- | --- | --- |
| 15100 | PARKVISTA1_8 | 0.890 | 0.9 |
| 2058 | CIRCLET_P8 | 0.892 | 0.9 |
| 559 | HERITAGE | 0.893 | 0.92 |
| 12033 | HRTAG1_T8 | 0.893 | 0.9 |
| 2036 | KELLER2_T8 | 0.894 | 0.9 |
| 33565 | KELLER2 | 0.894 | 0.9 |
| 2033 | KLR_MAG1_T8 | 0.895 | 0.9 |
| 2037 | WPKELLR1_8 | 0.899 | 0.9 |
| 566 | CHERRYGROV | 0.900 | 0.92 |
| 2035 | BEARCK3_8 | 0.902 | 0.9 |
| 12028 | CLYVIL2_8 | 0.905 | 0.9 |
| 2028 | CLYVIL2_T8 | 0.906 | 0.9 |

Table 4 – Post Contingency Voltage Criteria Exceedances

To address these reliability issues, Oncor recommended the Roanoke Area Upgrades Project to the ERCOT Regional Planning Group (“RPG”). ERCOT conducted an independent review, which also identified reliability issues in the area, including thermal overloads and voltage violations.  Tables 5 and 6 below summarize ERCOT’s findings.

| NERC Contingency Category | Overloaded Element | Voltage Level (kV) | Length (miles) | Loading % |
| --- | --- | --- | --- | --- |
| P1: N-1 | Roanoke Transformer #1 and #2 | 345/138 | - | 101.68 |
| P6: (X-1 + N-1) | Roanoke Transformer #1 and #2 | 345/138 | - | 117.27 |
| P6: (X-1 + N-1) | Hicks Transformer #1 and #2 | 345/138 | - | 100.00 |
| P3: (G-1 + N-1) | Hicks to Roanoke | 345 | 9.6 | 100.73 |
| P3: (G-1 + N-1) | Hicks to Alliance | 345 | 5.8 | 100.28 |
| P6: (X-1 + N-1) | Kennedale to Century | 345 | 10.5 | 100.69 |
| P6: (X-1 + N-1) | Randol Mill Tap East to Randol Mill | 138 | 2.2 | 100.63 |
| P6: (X-1 + N-1) | Liggett Switch to DFW E East | 138 | 3.0 | 100.96 |
| P6: (X-1 + N-1) | Liggett Switch to Irving Valley View | 138 | 1.5 | 104.96 |

Table 5 – Thermal Overloads Observed in the Study Area for 2026 Summer Peak

| NERC Contingency Category | Substation | Voltage Level (kV) | Post-Contingency Voltage (pu) |
| --- | --- | --- | --- |
| P3: (G-1 + N-1) | Park Vista | 138 | 0.89 |
| P3: (G-1 + N-1) | Keller Tap | 138 | 0.90 |
| P3: (G-1 + N-1) | Keller Magnolia Tap | 138 | 0.90 |
| P6: (X-1 + N-1) | Heritage | 138 | 0.90 |
| P3: (G-1 + N-1) | Cherry Grove | 138 | 0.90 |

Table 6 – Voltage Violations Observed in the Study Area for 2026 Summer Peak

After conducting an independent review, ERCOT’s RPG, Technical Advisory Committee, and Board of Directors approved the Roanoke Area Upgrades Project, which included the following:

- Construct a new Ramhorn Hill 345 kV switching station in a 10-breaker, breaker-and-a-half arrangement tapped into the existing double-circuit Hicks to Willow Creek 345 kV line.  The existing Hicks and Willow Creek substations are owned by Oncor.

- Construct a new Dunham 345 kV switching station in a 10-breaker, breaker-and-a-half arrangement tapped into the existing Lewisville to Krum West and Lewisville to Roanoke 345 kV lines.  The existing Lewisville Substation is owned by Brazos Electric Cooperative.  The existing Krum West and Roanoke Substations are owned by Oncor.

- Construct two new Ramhorn Hill to Dunham 345 kV transmission lines, with conductor rated to at least 2987 MVA, in a new (estimated 18.4-mile) right-of-way, installed on new triple-circuit towers leaving one vacant 138 kV position.

- Rebuild Exchange to Roanoke 345 kV double-circuit lines, upgrading both with conductors rated to at least 2987 MVA, using separate double-circuit capable structures for each line.  The line ratings will be 1912/1912 MVA, limited by terminal equipment at Roanoke.

- Construct a new Exchange to Roanoke 138 kV circuit, with conductor rated to at least 764 MVA, using one of the Exchange to Roanoke 345 kV line double-circuit capable structures.

- Construct a new Exchange 345/138 kV Switching Station, adjacent to the Alliance 345 kV substation, with two new 600 MVA (nameplate) transformers in an 8-breaker, 345 kV breaker-and-a-half bus arrangement and a 9-breaker, 138 kV breaker-and-a-half arrangement.  The normal/emergency ratings of the new transformers will be 700/750 MVA.  Exchange will be connected to Hicks and Roanoke with 345 kV lines and connected to the converted Alliance Substation with 138 kV lines. The existing Alliance and Hicks Substations are owned by Oncor.

- Convert the existing Alliance 345 kV load-serving substation to 138 kV load-serving operation.

- Construct a new Exchange to Alliance 138 kV double-circuit line with conductors rated to at least 746 MVA.

- Construct a new Alliance to Keller Magnolia and Alliance to Heritage 138 kV double-circuit line with conductors rated to at least 746 MVA in a new (estimated 1.4-mile) right-of-way.  The existing Keller Magnolia and Heritage Substations are owned by Oncor.

- Upgrade the existing Keller Magnolia to Heritage 138 kV line with conductor rated to at least 746 MVA to be installed on the Alliance to Keller Magnolia and Alliance to Heritage 138 kV double-circuit structures.

- Upgrade the existing Heritage to Keller Magnolia Tap double-circuit lines with conductors rated to at least 746 MVA.

- Construct a new 138 kV switching station at Keller Wall Price in a 6-breaker ring bus arrangement.

- Disconnect the double-circuit Heritage to Keller Magnolia Tap lines at Keller Magnolia Tap and terminate both at Keller Wall Price by constructing two new 0.3-mile, 138 kV transmission lines added to the existing Keller Magnolia Tap to Keller Wall Price right-of-way with both new line conductors rated to at least 746 MVA.  The existing Keller Magnolia Tap and Keller Wall Price Substation are owned by Oncor.

- Retire the Keller Magnolia Tap.

The Proposed Transmission Line Project includes components 1, 2, and 3 of the overall Roanoke Area Upgrades Project, as listed above.  Both the Ramhorn Hill and Dunham switching stations were conceptualized and proposed to have 10 breakers as an initial configuration. However, after finalizing property locations and station layouts, Oncor is proposing to install 12 breakers as an initial configuration at both switching stations.  A 12-breaker initial configuration at Ramhorn Hill and Dunham is better suited to accommodate future system growth while avoiding future line rework, congested 345 kV crossings, and extended outages when the switching stations are expanded to accommodate additional transmission lines in the future.

Oncor filed Commission Docket No. 54733 to amend its CCN for components 12, 13, and 14. Oncor will file separate CCN applications for the remaining components of the Roanoke Area Upgrades Project as required by the Commission.

The complete ERCOT Independent Review, dated July 19, 2022, is included as Attachment No. 4 to the Application.  A system map showing all of the recommended Roanoke upgrades is included as Attachment No. 5.

15.	Alternatives to Project:

For a standard application, describe alternatives to the construction of this project (not routing options).  Include an analysis of distribution alternatives, upgrading voltage or bundling of conductors of existing facilities, adding transformers, and for utilities that have not unbundled, distributed generation as alternatives to the project.  Explain how the project overcomes the insufficiencies of the other options that were considered.

Oncor Review

Oncor evaluated 3 alternatives to address the identified reliability concerns described in response to Question No. 14:

Oncor Option #1 (O1):

- Establish the Exchange 345/138 kV Switching Station, adjacent to Alliance 345 kV Substation, with two 600 MVA Autotransformers in a 8-breaker 345 kV breaker-and-a-half bus arrangement and a 9-breaker 138 kV breaker-and-a-half arrangement

- Convert the existing Alliance 345 kV load-serving substation to 138 kV operation

- Establish the Exchange – Keller Wall Price 138 kV double-circuit line using a conductor rated at least 3121 A or greater with the following upgrades:

- Construct the Exchange – Keller Magnolia 138 kV double-circuit line

- Upgrade the Keller Magnolia – Keller Wall Price Switch 138 kV line using double-circuit capable structures

- Establish a new 138 kV switching station at Keller Wall Price in a 6-breaker ring bus arrangement

- Disconnect the Keller Magnolia Tap – Heritage/Keller Magnolia line at Keller Magnolia Tap and terminate at Keller Wall Price by constructing a new 0.3-mile double-circuit 138 kV transmission line

- Establish the Ramhorn Hill 345 kV switching station in a 10-breaker, breaker-and-a-half arrangement

- Establish Dunham 345 kV switching station with in a 10-breaker, breaker-and-a-half arrangement

- Construct an estimated 18.4-mile triple-circuit line between Ramhorn Hill and Dunham with:

  - Two 345 kV circuits using conductor rated at least 5000 A

  - A vacant position for a future 138 kV circuit to support future load serving substations in growth areas

- Rebuild Exchange – Roanoke 345 kV double-circuit line using separate double-circuit capable structures for each line with conductor rated at least 5000 A and establish the Exchange – Roanoke 138 kV circuit using one of the Exchange – Roanoke 345 kV line double-circuit capable structures rated at least 3200 A

- Ensure all new 345 kV terminals at Exchange, Ramhorn Hill, and Dunham are rated 5000 A and 138 kV terminals at Exchange, Keller Wall Price, and Roanoke are rated 3200 A

Oncor Option #2 (O2):

- Establish Dunham 345 kV switching station in an 8-breaker, breaker-and-a-half arrangement

- Establish Dunham 138 kV switching station in a 5-breaker, breaker-and-a-half arrangement

- Establish two new 345/138 kV autotransformers at the proposed Dunham 345 kV switching station

- Construct an estimated 1-mile, 138 kV double-circuit line from Dunham to Cross Timbers with conductor rated 3200 A or greater

Oncor Option #3 (O3):

- Establish the Ramhorn Hill 345 kV switching station in a 10-breaker, breaker-and-a-half arrangement

- Establish Dunham 345 kV switching station in an 11-breaker, breaker-and-a-half arrangement

- Construct an estimated 18.4-mile, 345 kV double-circuit line from Ramhorn Hill to Dunham with conductor rated 5000 A or greater

- Establish Dunham 138 kV switching station in a 5-breaker, breaker-and-a-half arrangement

- Establish two new 345/138 kV autotransformers at the proposed Dunham 345 kV switching station

- Construct an estimated 1-mile, 138 kV double-circuit line from Dunham to Cross Timbers with conductor rated 3200 A or greater

Of the three alternatives Oncor reviewed, Option #1 best addressed the identified reliability issues.  While both Option #2 and Option #3 would reduce some post-contingency thermal overloads, the steady-state analysis clearly demonstrates that Option #1 would more effectively address thermal overloads, resolving overloads across all case years.  Option #1 also resolves load-serving limitations and voltage criteria exceedances on the Roanoke – Euless/Deen double-circuit transmission line, whereas Options #2 and #3 do not.  The results of Oncor’s analysis are summarized in Tables 7, 8, and 9 below.

| Element | Worst Contingency Loading (% of Emergency Rating) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2021 RTP NNC Cases |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2023 Summer |  |  |  | 2024 Summer |  |  |  | 2026 Summer |  |  |  | 2027 Summer |  |  |  |
|  | Base | O1 | O2 | O3 | Base | O1 | O2 | O3 | Base | O1 | O2 | O3 | Base | O1 | O2 | O3 |
| Roanoke 345/138 kV Autotransformer #1 | 111 | 74 | 107 | 84 | 110 | 73 | 106 | 88 | 114 | 75 | 109 | 91 | 114 | 75 | 109 | 91 |
| Roanoke 345/138 kV Autotransformer #2 | 111 | 74 | 108 | 84 | 110 | 73 | 106 | 88 | 114 | 75 | 109 | 91 | 114 | 75 | 109 | 91 |
| Hicks 345/138 kV Autotransformer #1 | 99 | 66 | 96 | 72 | 98 | 65 | 95 | 71 | 101 | 66 | 98 | 72 | 102 | 66 | 99 | 72 |
| Hicks 345/138 kV Autotransformer #2 | 100 | 66 | 98 | 72 | 99 | 66 | 96 | 72 | 102 | 67 | 99 | 73 | 104 | 67 | 101 | 73 |
| Roanoke – Hicks 345 kV line | 95 | 71 | 97 | 57 | 93 | 71 | 95 | 56 | 97 | 73 | 98 | 58 | 99 | 75 | 100 | 59 |
| Performance Requirements Met |  | Yes | No | Yes |  | Yes | No | Yes |  | Yes | No | Yes |  | Yes | No | Yes |

Table 7 – Post Contingency Loading Comparison using RTP NNC Cases

| Element | Worst Contingency Loading (% of Emergency Rating) in 2021 SSWG Cases |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2024 Summer |  |  |  | 2028 Summer |  |  |  |
|  | Base | O1 | O2 | O3 | Base | O1 | O2 | O3 |
| Roanoke 345/138 kV Autotransformer #1 | 124 | 82 | 121 | 95 | 135 | 89 | 131 | 103 |
| Roanoke 345/138 kV Autotransformer #2 | 124 | 82 | 121 | 95 | 135 | 89 | 131 | 103 |
| Hicks 345/138 kV Autotransformer #1 | 113 | 74 | 110 | 80 | 123 | 79 | 120 | 85 |
| Hicks 345/138 kV Autotransformer #2 | 113 | 74 | 110 | 80 | 123 | 79 | 120 | 85 |
| Roanoke – Hicks 345 kV line | 104 | 79 | 105 | 62 | 113 | 86 | 114 | 67 |
| Performance Requirements Met |  | Yes | No | Yes |  | Yes | No | No |

Table 8 – Post Contingency Loading Comparison using 2021 SSWG Cases

| Bus Number | Bus Name | Worst Contingency Voltage Results (in p.u.) 2028 Summer (2021 SSWG Case) |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Base | O1 | O2 | O3 |
| 15100 | PARKVISTA1_8 | 0.890 | >0.95 | 0.893 | 0.897 |
| 2058 | CIRCLET_P8 | 0.892 | >0.95 | 0.895 | 0.898 |
| 559 | HERITAGE | 0.893 | >0.95 | 0.896 | 0.900 |
| 12033 | HRTAG1_T8 | 0.893 | >0.95 | 0.896 | 0.900 |
| 2036 | KELLER2_T8 | 0.894 | >0.95 | 0.897 | 0.901 |
| 33565 | KELLER2 | 0.894 | >0.95 | 0.897 | 0.901 |
| 2033 | KLR_MAG1_T8 | 0.895 | >0.95 | 0.899 | 0.902 |
| 2037 | WPKELLR1_8 | 0.899 | >0.95 | 0.903 | 0.906 |
| 566 | CHERRYGROV | 0.900 | >0.95 | 0.903 | 0.906 |
| 2035 | BEARCK3_8 | 0.902 | >0.95 | 0.905 | 0.909 |
| 12028 | CLYVIL2_8 | 0.905 | >0.95 | 0.908 | 0.911 |
| 2028 | CLYVIL2_T8 | 0.906 | >0.95 | 0.909 | 0.912 |
| Performance Requirements Met |  |  | Yes | No | No |

Table 9 – Post Contingency Voltage Comparison using 2021 SSWG Case

After identifying Option #1 as the superior option, Oncor prepared a submittal to ERCOT RPG recommending Option #1 as its preferred alternative.

ERCOT Review

In connection with evaluating Oncor’s submittal, ERCOT’s independent review initially evaluated four system improvement options to address the observed reliability issues.  Table 10 shows the components of the four initial options.

Note that the numbering of the options reviewed by ERCOT does not correspond to the numbering of the options reviewed by Oncor.  Oncor Option #1 largely corresponds to ERCOT Option 2, as explained below.

| Transmission Upgrade | Approx. Length of Line (miles) | Normal / Emergency Rating (MVA) | Options |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 1 | 2* | 3 | 4 |
| Construct a new Ramhorn Hill 345-kV switching station in a 10- breaker breaker-and-a-half arrangement tapped into existing double-circuit Hicks to Willow Creek 345-kV lines |  |  |  | ✓ | ✓ | ✓ |
| Construct a new Dunham 345-kV switching station in a 10-breaker breaker-and-a-half arrangement tapped into existing Lewisville to Krum West and Lewisville to Roanoke 345-kV lines |  |  |  | ✓ | ✓ | ✓ |
| Construct two new Ramhorn Hill to Dunham 345-kV transmission lines, with conductor rated to at least 2987 MVA, in a new (estimated 18.4-mile) right-of-way installed on new triple-circuit towers leaving one 138-kV vacant position | 18.4 | 2987/2987 |  | ✓ | ✓ | ✓ |
| Upgrade Hicks to Exchange 345-kV double-circuit line with conductors rated to at least 2987 MVA | 5.8 | 2987/2987 | ✓ |  |  |  |
| Rebuild Exchange to Roanoke 345-kV double-circuit lines, upgrading both with conductors rated to at least 2987 MVA, using separate double-circuit capable structures for each line | 3.6 | 1912/1912** |  | ✓ |  |  |
| Construct a new Exchange to Roanoke 138-kV circuit, with conductor rated to at least 764 MVA, using one of the Exchange to Roanoke 345-kV line double-circuit capable structures | 3.8 | 764/764 |  | ✓ |  |  |
| Upgrade Exchange to Roanoke 345-kV double-circuit lines with conductor rating to at least 2987 MVA | 3.6 | 1912/1912** | ✓ |  | ✓ |  |
| Construct a new Exchange 345/138-kV Switching Station, adjacent to Alliance 345-kV substation, with two new 600 MVA transformers (nameplate) in an 8-breaker 345-kV breaker-and-a-half bus arrangement and a 9-breaker 138-kV breaker-and-a-half arrangement |  | 700/750 | ✓ | ✓ | ✓ | ✓ |
| Convert the existing Alliance 345-kV load serving substation to 138- kV load serving operation |  |  | ✓ | ✓ | ✓ | ✓ |
| Construct a new Exchange to Alliance 138-kV double-circuit line with conductors rated to at least 746 MVA | 0.1 | 746/746 | ✓ | ✓ | ✓ | ✓ |
| Construct a new Alliance to Keller Magnolia and Alliance to Heritage 138-kV double-circuit line with conductors rated to at least 746 MVA | 1.4 Keller Magnolia 2.5 Heritage | 746/746 | ✓ | ✓ | ✓ | ✓ |
| Upgrade the existing Keller Magnolia to Heritage 138-kV line with conductor rated to at least 746 MVA to be installed on the Alliance to Keller Magnolia and Alliance to Heritage 138-kV double-circuit towers | 1.0 | 746/746 | ✓ | ✓ | ✓ | ✓ |
| Upgrade the existing Heritage to Keller Magnolia Tap double-circuit lines with conductors rated to at least 746 MVA | 1.3 | 746/746 | ✓ | ✓ | ✓ | ✓ |
| Construct a new 138-kV switching station at Keller Wall Price in a 6- breaker ring bus arrangement |  |  | ✓ | ✓ | ✓ | ✓ |
| Disconnect the double-circuit Heritage to Keller Magnolia Tap lines at Keller Magnolia Tap and terminate both at Keller Wall Price by constructing two new 0.3-mile 138-kV transmission lines added to the existing Keller Magnolia Tap to Keller Wall Price right-of-way with both new line conductors rated to at least 746 MVA | 0.3 | 746/746 | ✓ | ✓ | ✓ | ✓ |
| Retire the Keller Magnolia Tap |  |  | ✓ | ✓ | ✓ | ✓ |

Table 10 – Components of the Four Initial Options Studied by ERCOT

*ERCOT’s Option 2 is substantially the same as Oncor Option #1.

**Exchange to Roanoke 345-kV conductor will be capable of 2987/2987 MVA, however terminal equipment at Roanoke will limit the line ratings to 1912/1912 MVA.

ERCOT performed reliability assessments on the four initial options based on NERC Reliability Standard TPL-001-4, the applicable ERCOT Nodal Protocols, and Planning Criteria.  ERCOT’s initial reliability assessment identified thermal overload violations under ERCOT Option 1, resulting in its being eliminated from further evaluation.  No reliability criteria violations were identified for ERCOT Options 2, 3, and 4, so ERCOT short-listed these options for further assessment.

To evaluate the operational flexibility of the short-listed options, ERCOT developed an off-peak scenario for planned maintenance outage (N-1-1) analysis.  ERCOT first conducted an N-1-1 contingency analysis based on selected single-circuit prior outages, as well as based on selected double-circuit common tower prior outages for each short-listed option.  As shown in Table 11 below, the performance was similar for each of the three short-listed options.

|  | Planned Maintenance Single Circuit Prior Outage |  | Planned Maintenance Double Circuit Common Tower Prior Outage |  |
| --- | --- | --- | --- | --- |
|  | Thermal Overloads | Voltage Instability | Thermal Overloads | Voltage Instability |
| Option 2 | No | No | No | No |
| Option 3 | No | No | No | No |
| Option 4 | No | No | No | No |

Table 11 – Results of Planned Maintenance N-1-1 Outage Analysis

To further evaluate the operational flexibility provided by the short-listed options, ERCOT conducted an additional prior outage maintenance scenario based on input from Oncor.  As shown in Table 12 below, ERCOT’s Option 2 performed better under this scenario as it was the only short-listed option that did not show a Roanoke 345/138 kV transformer overload.

|  | Planned Maintenance TSP Requested Scenario (X-1 + Double-Circuit Line Segment) |  |
| --- | --- | --- |
|  | Thermal Overloads | Voltage Stability |
| Option 2 | No | Ok |
| Option 3 | Yes | Ok |
| Option 4 | Yes | Ok |

Table 12 – Results of TSP Requested Planned Maintenance Outage Analysis

To estimate and compare the long-term load-serving capabilities of the three short-listed options, ERCOT adjusted load-up in the substations identified in the Roanoke area in Oncor’s submittal to RPG.  To balance power, ERCOT adjusted down conforming load outside of the North Central weather zone and simulated N-1 contingencies.

Because ERCOT Option 2 offered better long-term load-serving capability, better operational flexibility during transformer prior outage conditions, and better flexibility for future utilization associated with transmission between Exchange and Roanoke, ERCOT selected Option 2 as its preferred option.

ERCOT’s analysis revealed that six 138 kV and one 345 kV transmission line thermal overloads would need to be addressed for all three of the short-listed options to increase long-term load-serving capability.  In addition, Options 3 and 4 would require additional transmission improvements to address overloading on the two existing 345/138 kV transformers at Roanoke to further increase load serving capability.  Because Option 2 did not require these additional major transmission improvements, ERCOT selected Option 2 as the most favorable option for increasing long-term load serving capability.

A comparison of the three short listed options is shown in Table 13 below.

| Option 2 Option 3 Option 4 |  |  |  |
| --- | --- | --- | --- |
| Met ERCOT and NERC Reliability Criteria | Yes | Yes | Yes |  |
| Improved Operational Flexibility | Better | Yes | Yes |  |
| Long-term Load Serving Performance | Better | Yes | Yes |  |
| Capital Cost Estimates | $286 M | $264 M | $254 M |  |

Table 13 - Comparison of Short-Listed Options

ERCOT endorsed Option 2, including the Proposed Transmission Line Project, as a Tier 1 transmission project that is critical to the reliability of the ERCOT system pursuant to 16 TAC § 25.101(b)(3)(D).

Distribution alternatives will not resolve the identified reliability issues on the transmission system.

Bundling or upgrading conductor, adding transformers, or upgrading voltages alone will not address the identified reliability issues or provide the necessary level of service to meet electric demand in the Roanoke-Alliance area.

16. 	Schematic or Diagram:

For a standard application, provide a schematic or diagram of the applicant's transmission system in the proximate area of the project.  Show the location and voltage of existing transmission lines and substations, and the location of the construction.  Locate any taps, ties, meter points, or other facilities involving other utilities on the system schematic.

A schematic of the transmission system in the proximate area of the Roanoke Area Upgrades Project, including the Proposed Transmission Line Project, is shown in Attachment No. 6.  The location and voltage of existing transmission lines, substations, taps, ties, meter points or other facilities involving other utilities in relation to the Proposed Transmission Line Project are included.  A map of the project area can be found in Figures 3-1A, 3-1B, 3-1C, and 3-1D of the Environmental Assessment and Alternative Route Analysis in Appendix H included as Attachment No. 1.

17.	Routing Study:

Provide a brief summary of the routing study that includes a description of the process of selecting the study area, identifying routing constraints, selecting potential line segments, and the selection of the routes.  Provide a copy of the complete routing study conducted by the utility or consultant.  State which route the applicant believes best addresses the requirements of PURA and P.U.C. Substantive Rules.

Oncor retained Halff to prepare the Environmental Assessment and Routing Study.  The objective of the Environmental Assessment and Routing Study is to provide information in support of this Application in addressing the requirements of § 37.056(c)(4)(A)-(D) of the Texas Utilities Code, the PUCT’s CCN Application form, and 16 Texas Administrative Code (“TAC”) § 25.101 as these apply to the Proposed Transmission Line Project.

By examining existing environmental conditions, including the human and natural resources that are located in the project area, the Environmental Assessment and Routing Study appraises the environmental effects that could result from the construction, operation, and maintenance of the Proposed Transmission Line Project. The Environmental Assessment and Routing Study may also be used in support of any additional local, state, or federal permitting activities that may be required for the Proposed Transmission Line Project.

To assist Halff in its evaluation, Oncor provided Halff with information regarding the project endpoints, the need for the project, engineering and design requirements, construction practices, and ROW requirements for the Proposed Transmission Line Project.

After considering environmental and geographical data, Halff defined a study area that encompassed the provided endpoints with a sufficient area to identify a diverse set of potential routing alternatives.  See Section 3.0 of the Environmental Assessment and Routing Study, included as Attachment No. 1, for a discussion of the study area.  Routing constraints were identified after collection of area data from many sources (e.g., governmental agencies, evaluation of aerial photography) and consideration of the criteria established in § 37.056(c)(4)(A)-(D) of the Texas Utilities Code, the PUCT’s CCN Application form, and 16 TAC § 25.101.

Potential line segments were identified by evaluating the constraints mapped within the study area and then developing potential pathways, such as existing corridors and other linear features where constraints were minimal.  Corridors were identified and developed into potentially viable routes.  Potential impacts to both the human and natural environment were evaluated by Halff for each identified preliminary alternative route.

Oncor then evaluated the alternative routes and selected Route 179 as the route that best addresses the requirements of PURA § 37.056(c)(4)(A)-(D) and 16 TAC § 25.101.

Specific discussions regarding the study area, identification of constraints, selection of potential line segments, and alternative route analysis are set forth in the Environmental Assessment and Routing Study.  Specific discussion regarding the evaluation and selection of routes filed with the Application and the route that Oncor believes best complies with the requirements of the Texas Utilities Code and the PUCT’s Substantive Rules is contained in an office memorandum from Brenda J. Perkins (included as Attachment No. 7).

18.	Public Meeting or Public Open House:

Provide the date and location for each public meeting or public open house that was held in accordance with 16 TAC §22.52.  Provide a summary of each public meeting or public open house including the approximate number of attendants, and a copy of any survey provided to attendants and a summary of the responses received.  For each public meeting or public open house provide a description of the method of notice, a copy of any notices, and the number of notices that were mailed and/or published.

Oncor hosted two public participation meetings in accordance with 16 TAC § 22.52.  They were attended by personnel from Oncor, Halff, and Integra Realty Resources, a contractor assisting Oncor in property abstracting.  The public participation meetings were held on December 7 and December 8, 2022, from 4:00 p.m. to 7:00 p.m., at the Marriott Hotel & Golf Club Champions Circle in Fort Worth, Texas.

Oncor mailed a total of 2,068 individual written notices of the meetings to all owners of property within 500 feet of the centerline of the preliminary alternative route links for the Proposed Transmission Line Project in accordance with 16 TAC §22.52(a)(4).  In consideration of horizontal accuracy limitations as it relates to appraisal district data and aerial photography interpretation when developing preliminary routes, notification to property owners was over-inclusive, including properties crossed by or within 520 feet of preliminary alternative route centerlines.  Also, public notices were published on November 26 and November 27, 2022, in the Denton Record Chronicle and on November 23, 2022, in the Wise County Messenger announcing the location, time, and purpose of the meetings.  Oncor provided notice of the public meetings to the Department of Defense Siting Clearinghouse in accordance with 16 TAC § 22.54(a)(4). Oncor also provided courtesy notice of the public meetings to identified pipeline companies within the project area.

The meetings were designed to solicit comments and input from residents, landowners, public officials, and other interested parties concerning the Proposed Transmission Line Project.  The objectives of the meetings included promoting an understanding of the Proposed Transmission Line Project, including the purpose, need, and potential benefits and impacts; informing and educating the public with regard to the routing process and schedule; and gathering information about the values and concerns of the public and community leaders.

The meetings were configured in an informal information station format rather than a formal speaker/audience format, with each station assigned to a particular aspect of the project or routing process and staffed with representatives from Oncor and/or Halff.  Each station had exhibits, maps, illustrations, aerial photography, or other information describing certain project aspects and subject matter information.  Attendees were encouraged at the meeting’s outset to visit each station in order, so the entire process could be explained in the general sequence of project development.  Oncor has found this meeting format valuable due to its informality and because it allows attendees to gather information most important to them and to spend as much time as necessary with those particular project aspects.  Additionally, individual discussions allow for and encourage more interaction from attendees who otherwise might be hesitant to participate in a more formal setting.

At the public participation meeting held on December 7, 2022, 77 people signed in and 27 questionnaires were received.  At the public participation meeting held on December 8, 2022, 95 people signed in and 44 questionnaires were received.  Numerous questionnaires and/or letters were submitted to Oncor after the public meetings via email.

Additional discussion concerning the public involvement program and specific information regarding the public participation meetings may be found in the Environmental Assessment and Routing Study, Section 2.5, pages 2-11 through 2-12, Section 5.0, pages 5-1 through 5-22, and Figures 3-0 and 5-1, included as Attachment No. 1.  A representative copy of the notice that was provided to property owners and a copy of the questionnaire provided to meeting attendees is included in Appendix B of Attachment No. 1.

19.	Routing Maps:

Base maps should be a full scale (one inch = not more than one mile) highway map of the county or counties involved, or other maps of comparable scale denoting sufficient cultural and natural features to permit location of all routes in the field.  Provide a map (or maps) showing the study area, routing constraints, and all routes or line segments that were considered prior to the selection of the routes.  Identify the routes and any existing facilities to be interconnected or coordinated with the project.  Identify any taps, ties, meter points, or other facilities involving other utilities on the routing map.  Show all existing transmission facilities located in the study area.  Include the locations of radio transmitters and other electronic installations, airstrips, irrigated pasture or cropland, parks and recreational areas, historical and archeological sites (subject to the instructions in Question 27), and any environmentally sensitive areas (subject to the instructions in Question 29).

Figures 3-1A, 3-1B, 3-1C (one inch = 1,000 feet maps), and Figure 3-1D (one inch = 300 feet map), are included in the Appendix H map pockets of the Environmental Assessment and Routing Study, included as Attachment No. 1.  These base maps denote sufficient cultural and natural features to permit location of all routes in the field.  These maps delineate the study area, routing constraints, and all routes and route links considered in the selection of routes.  These maps also depict the approximate locations of radio transmitters and other electronic installations, airstrips, irrigated pasture or cropland, parks and recreational areas, historical and archeological sites, and environmentally sensitive areas, if any.  Figures 3-1A-D depict existing transmission facilities in the area of the Proposed Transmission Line Project, including taps, ties, meter points, or other utility facilities, as applicable.

Provide aerial photographs of the study area displaying the date that the photographs were taken or maps that show (1) the location of each route with each route segment identified, (2) the locations of all major public roads including, as a minimum, all federal and state roadways, (3) the locations of all known habitable structures or groups of habitable structures (see Question 19 below) on properties directly affected by any route, and (4) the boundaries (approximate or estimated according to best available information if required) of all properties directly affected by any route.

Figures 3-1A-D of the Environmental Assessment and Routing Study, included as Attachment No. 1, depict on an aerial photograph: (1) the location of each link that is used in the alternative routes filed in this CCN, with each link identified; (2) the locations of all major public roads, including all federal and state roadways; (3) the locations of all known habitable structures on properties directly affected by any link used in the alternative routes; and (4) the boundaries (approximate or estimated according to available county tax information) of all properties directly affected by any link used in an alternative route.  In addition, the locations of radio transmitters and other electronic installations, airstrips, irrigated pasture or cropland, parks and recreational areas, historical and archeological sites, and environmentally sensitive areas, if any, are depicted.

For each route, cross-reference each habitable structure (or group of habitable structures) and directly affected property identified on the maps or photographs with a list of corresponding landowner names and addresses and indicate which route segment affects each structure/group or property.

Attachment No. 8 is a table that cross-references each habitable structure and directly affected property identified in Figures 3-1A-D of Attachment No. 1; the cross-reference table includes corresponding landowner names and addresses and indicates which links and alternative routes affect each structure or property.

20.	Permits: 
List any and all permits and/or approvals required by other governmental agencies for the construction of the proposed project.  Indicate whether each permit has been obtained.

The following permits/approvals will be obtained after PUC approval of the CCN and prior to beginning construction, if necessary:

- Texas Department of Transportation (“TxDOT”) permit(s) for crossing a state-maintained roadway.

- A Storm Water Pollution Prevention Plan (“SWPPP”) will be prepared and a Notice of Intent will be submitted to the Texas Commission on Environmental Quality under the Texas Pollutant Discharge Elimination System (“TPDES”) program.

- A cultural resources survey plan will be developed with the Texas Historical Commission (“THC”) for the proposed project.

- Consultation with the U.S. Army Corps of Engineers will occur following the Commission’s approval of this Application to determine appropriate requirements under Section 404/Section 10 Permit criteria.

- Consultation with the U.S. Fish and Wildlife Service will occur following the Commission’s approval of this Application to determine appropriate requirements under the Endangered Species Act.

- Consultation with the Federal Aviation Administration (“FAA”) will occur following the Commission’s approval of this Application to determine appropriate requirements and notification under Federal Aviation Regulations (14 CFR Part 77).

21.	Habitable structures:

For each route list all single-family and multi-family dwellings and related structures, mobile homes, apartment buildings, commercial structures, industrial structures, business structures, churches, hospitals, nursing homes, schools, or other structures normally inhabited by humans or intended to be inhabited by humans on a daily or regular basis within 300 feet of the centerline if the proposed project will be constructed for operation at  230kV or less, or within 500 feet of the centerline if  the proposed project will be constructed for operation at greater than 230kV.  Provide a general description of each habitable structure and its distance from the centerline of the route.  In cities, towns or rural subdivisions, houses can be identified in groups.  Provide the number of habitable structures in each group and list the distance from the centerline of the route to the closest and the farthest habitable structure in the group.  Locate all listed habitable structures or groups of structures on the routing map.

A listing of all habitable structures located within 500 feet of each proposed link centerline used in the alternative routes filed in this CCN, along with a general description of each habitable structure and its distance from the centerline of the link and the associated alternative routes, is provided in the table in Attachment No. 9.

Figures 3-1A-D (Appendix H map pockets), located in Attachment No. 1, depict the locations of all known habitable structures directly affected by the links used in the proposed alternative routes.

22.	Electronic Installations:

For each route, list all commercial AM radio transmitters located within 10,000 feet of the center line of the route, and all FM radio transmitters, microwave relay stations, or other similar electronic installations located within 2,000 of the center line of the route.  Provide a general description of each installation and its distance from the center line of the route.  Locate all listed installations on a routing map.

There are no known AM radio transmitters located within 10,000 feet of the centerline of any of the alternative route links and no known FM radio transmitters located within 2,000 feet of the centerline of any of the alternative route links.

There are twelve other communication towers located within 2,000 feet of the centerline of the filed alternative routes. A listing of these communication towers located within 2,000 feet of each proposed link centerline used in the alternative routes filed in this CCN, along with a general description of each tower and its distance from the centerline of the link and the associated alternative routes is provided in the table in Attachment No. 10.

Please refer to Section 3.7.7, page 3-77, and Section 7.7.6, page 7-24, of the Environmental Assessment and Routing Study included as Attachment No. 1.

23.	Airstrips:

For each route, list all known private airstrips within 10,000 feet of the center line of the project.  List all airports registered with the Federal Aviation Administration (FAA) with at least one runway more than 3,200 feet in length that are located within 20,000 feet of the center line of any route.  For each such airport, indicate whether any transmission structures will exceed a 100:1 	horizontal slope (one foot in height for each 100 feet in distance) from the closest point of the closest runway.  List all listed airports registered with the FAA having no runway more than 3,200 feet in length that are located within 10,000 feet of the center line of any route.  For each such airport, indicate whether any transmission structures will exceed a 50:1 horizontal slope from the closest point of the closest runway.  List all heliports located within 5,000 feet of the center line of any route.  For each such heliport, indicate whether any transmission structures will exceed a 25:1 horizontal slope from the closest point of the closest landing and takeoff area of the heliport.  Provide a general description of each listed private airstrip, registered airport, and heliport; and state the distance of each from the center line of each route.  Locate and identify all listed airstrips, airports, and heliports on a routing map.

Halff’s review of federal and state aviation/airport maps and directories, aerial photo interpretation, and reconnaissance surveys identified: no private airstrips within 10,000 feet of the centerline of the proposed routes; four FAA-registered airports with a runway greater than 3,200 feet in length within 20,000 feet of the proposed routes; six FAA-registered airports without a runway greater than 3,200 feet in length within 10,000 feet of the proposed routes; and three heliports within 5,000 feet of the proposed routes.

A listing of the airstrips, airports and heliports located near the filed alternative routes, along with a general description of each facility and its distance from the centerline of the link and the associated alternative routes is provided in the table in Attachment No. 11.

Please refer to Section 3.7.6, pages 3-74 through 3-77, and Section 7.7.5, pages 7-21 through 7-24, of the Environmental Assessment included as Attachment No. 1.

24.	Irrigation Systems: 
For each route identify any pasture or cropland irrigated by traveling irrigation systems (rolling or pivot type) that will be traversed by the route.  Provide a description of the irrigated land and state how it will be affected by each route (number and type of structures etc.).  Locate any such irrigated pasture or cropland on a routing map.

Results of aerial photography interpretation and field reconnaissance surveys did not identify any pasture or cropland irrigated by traveling irrigation systems (rolling or pivot type) that will be traversed by any of the alternative routes of the Proposed Transmission Line Project.

Please refer to Tables 7-2 and 7-3 in Appendix E of the Environmental Assessment and Routing Study included as Attachment No. 1.

25.	Notice: 
Notice is to be provided in accordance with 16 TAC §22.52.

A.	Provide a copy of the written direct notice to owners of directly affected land.  Attach a list of the names and addresses of the owners of directly affected land receiving notice.

A copy of the written direct notice, with attached map, that will be provided to the owners of the directly-affected land is included as Attachment No. 12.  The names and addresses of the owners of the directly-affected land, to whom notice will be mailed by first-class mail, are included as Attachment No. 8.

B.	Provide a copy of the written notice to utilities that are located within five miles of the routes.

A copy of the written direct notice, with attached map, that will be provided to utilities that are located within five miles of the routes is included as Attachment No. 13.

C.	Provide a copy of the written notice to county and municipal authorities, and the Department of Defense Siting Clearinghouse. Notice to the DoD Siting Clearinghouse should be provided at the email address found at http://www.acq.osd.mil/dodsc/.

A representative copy of the written notice, with attached map, that will be provided to county authorities is included as Attachment No. 13.  The following county authorities will be provided the requisite notice on or before the filing date as required by Commission rules:

# Denton County, County Judge

# Denton County, County Commissioners – Precincts 1, 2, 3, and 4

# Denton County, County Administrator

# Denton County, Historical Commission

# Wise County, County Judge

# Wise County, County Commissioners – Precincts 1, 2, 3, and 4

# Wise County, Historical Commission

A representative copy of the written notice, with attached map, that will be provided to municipal authorities is included as Attachment No. 13.  The following municipal authorities will be provided the requisite notice on or before the filing date, as required by Commission rules:

- Town of Argyle: Mayor, Town Administrator, Assistant Town Secretary, Council Members, Community Development Director

- City of Aurora: Mayor, Mayor Pro Tem, Interim City Administrator, City Secretary, Council Members

- Town of Bartonville: Mayor, Mayor Pro Tem, Town Administrator, Town Secretary, Council Members

- Town of Corral City (formerly known as Draper): Mayor, Mayor Pro Tem, Aldermen

- City of Denton: Mayor, Mayor Pro Tem, City Manager, City Secretary, Economic Development Director, Council Members

- Town of DISH: Mayor, Commissioners

- Town of Double Oak: Mayor, Mayor Pro Tem, Deputy Mayor Pro Tem, Town Secretary, Council Members

- Town of Flower Mound: Mayor, Mayor Pro Tem, Deputy Mayor Pro Tem, Town Manager, Town Secretary, Economic Development Director, Council Members

- City of Fort Worth: Mayor, City Manager, Assistant City Managers, City Secretary, Development Services Director, Council Members

- City of Haslet: Mayor, Mayor Pro Tem, City Secretary, Council Members

- City of Justin: Mayor, Mayor Pro Tem, Interim City Manager, Assistant City Manager, City Secretary, Council Members

- City of Keller: Mayor, Mayor Pro Tem, City Manager, City Secretary, Economic Development Manager, Council Members

- City of New Fairview: Mayor, Mayor Pro Tem, City Administrator, City Operations Administrator, City Secretary, Council Members

- City of Newark: Mayor, Mayor Pro Tem, City Secretary, Council Members

- Town of Northlake: Mayor, Town Manager, Town Secretary, Council Members

- City of Rhome: Mayor, Mayor Pro Tem, City Administrator, City Secretary, Council Members

- City of Roanoke: Mayor, Mayor Pro Tem, City Manager, City Secretary, Council Members

- City of Southlake: Mayor, Mayor Pro Tem, Deputy Mayor Pro Tem, City Manager, Assistant City Manager, City Secretary, Council Members

- Town of Trophy Club: Mayor, Interim Town Manager, Town Secretary, Community Director, Council Members

- Town of Westlake: Mayor, Mayor Pro Tem, Town Manager, Town Secretary, Council Members

A representative copy of the written notice, with attached map, that will be provided to the Department of Defense Siting Clearinghouse by email at: osd.dod-siting-clearinghouse@mail.mil, and by first-class mail to the address below on the date this Application is filed, is included as Attachment No. 13.

DOD Siting Clearinghouse

3400 Defense Pentagon, Room 5C646

# Washington, DC 20301-3400

D.	Provide a copy of the notice that is to be published in newspapers of general circulation in the counties in which the facilities are to be constructed.  Attach a list of the newspapers that will publish the notice for this application.  After the notice is published, provide the publisher's affidavits and tear sheets.

Notice of this Application will be published in the Denton Record Chronicle, a newspaper of general circulation in Denton County, and in the Wise County Messenger, a newspaper of general circulation in Wise County.  A representative copy of the general public notice to be published is included as Attachment No. 14.

Proof of publication will be provided in the form of a publisher’s affidavit and tear sheet following publication of this notice.

For a CREZ application, in addition to the requirements of 16 TAC § 22.52 the applicant shall, not less than twenty-one (21) days before the filing of the application, submit to the Commission staff a “generic” copy of each type of alternative published and written notice for review.  Staff’s comments, if any, regarding the alternative notices will be provided to the applicant not later than seven days after receipt by Staff of the alternative notices,  Applicant may take into consideration any comments made by Commission staff before the notices are published or sent by mail.

Not applicable.

A copy of the application and all attachments will also be provided to the Texas Office of Public Utility Counsel (“OPUC”).  A representative copy of the written notice, with attached map, that will be provided to OPUC is included as Attachment No. 13.

26.	Parks and Recreation Areas:

For each route, list all parks and recreational areas owned by a governmental body or an organized group, club, or church and located within 1,000 feet of the center line of the route.  Provide a general description of each area and its distance from the center line.  Identify the owner of the park or recreational area (public agency, church, club, etc.).  List the sources used to identify the parks and recreational areas.  Locate the listed sites on a routing map.

A review of federal, state, and local websites and maps, as well as field reconnaissance surveys, identified several parks and recreational areas owned by a government body or an organized group, club, or church within 1,000 feet of the centerline of the alternative routes.  The table in Attachment No. 16 provides a general description of each area, its distance from the proposed route centerlines and the park or recreational area’s ownership.

Please refer to Section 3.7.2, pages 3-66 through 3-68, and Section 7.7.2, pages 7-17 through 7-19, of the Environmental Assessment and Routing Study, included as Attachment No. 1.

27.	Historical and Archeological Sites:

For each route, list all historical and archeological sites known to be within 1,000 feet of the center line of the route.  Include a description of each site and its distance from the center line.  List the sources (national, state or local commission or societies) used to identify the sites.  Locate all historical sites on a routing map.  For the protection of the sites, archeological sites need not be shown on maps.

Research and a records review were conducted of the Texas Historical Commission (“THC”) Historic Sites Atlas and the THC Archaeological Sites Atlas, to locate known cultural resources within 1,000 feet of the centerline of any route for the Proposed Transmission Line Project.  THC records indicated two Historic Texas Cemeteries and one historical marker are within 1,000 feet of the alternative route centerlines. Two archeological sites were identified within 1,000 feet of the alternative route centerlines.  The distances from these cultural resources to the closest route links and the corresponding routes are provided in the table in Attachment No. 17.

Please refer to Section 3.8, pages 3-77 through 3-92, and Section 7.8, pages 7-24 through 7-29, of the Environmental Assessment and Routing Study, included as Attachment No. 1.

28.	Coastal Management Program:

For each route, indicate whether the route is located, either in whole or in part, within the coastal management program boundary as defined in 31 T.A.C. §503.1.  If  any route is, either in whole or in part, within the coastal management program boundary, indicate whether any part of the route is seaward of the Coastal Facilities Designation Line as defined in 31 T.A.C. §19.2(a)(21).  Using the designations in 31 T.A.C. §501.3(b), identify the type(s) of Coastal Natural Resource Area(s) impacted by any part of the route and/or facilities.

The Proposed Transmission Line Project is not located, either in whole or in part, within the coastal management program boundary as defined in 31 TAC §503.1.

29.	Environmental Impact:

Provide copies of any and all environmental impact studies and/or assessments of the project.  If no formal study was conducted for this project, explain how the routing and construction of this project will impact the environment.  List the sources used to identify the existence or absence of sensitive environmental areas.  Locate any environmentally sensitive areas on a routing map.  In some instances, the location of the environmentally sensitive areas or the location of protected or endangered species should not be included on maps to ensure preservation of the areas or species.

The Environmental Assessment and Routing Study prepared by Halff is included as Attachment No. 1.

Within seven days after filing the application for the project, provide a copy of each environmental impact study and/or assessment to the Texas Parks and Wildlife Department (TPWD) for its review at the address below.  Include with this application a copy of the letter of transmittal with which the studies/assessments were or will be sent to the TPWD.

Wildlife Habitat Assessment Program

Wildlife Division

Texas Parks and Wildlife Department

4200 Smith School Road

Austin, Texas 78744

The applicant shall file an affidavit confirming that the letter of transmittal and studies/assessments were sent to TPWD.

A copy of the Environmental Assessment and Application will be provided to the Texas Parks and Wildlife Department for review within seven days following the filing of the Application for the Proposed Transmission Line Project.  Please refer to Attachment No. 18 for a copy of the transmittal letter with which the Environmental Assessment and Application will be sent to the TPWD.

30.	Affidavit

Attach a sworn affidavit from a qualified individual authorized by the applicant to verify and affirm that, to the best of their knowledge, all information provided, statements made, and matters set forth in this application and attachments are true and correct.

31.	List of Attachments to the CCN Application

Attachment No. 1:   	Environmental Assessment

Attachment No. 2:	Layout of the Proposed Ramhorn Hill Switch and Layout of the Proposed Dunham Switch

Attachment No. 3:	Cost Estimates

Attachment No. 4:	ERCOT’s Independent Review of Oncor Roanoke Area Upgrades Project dated July 19, 2022

Attachment No. 5:	Transmission Area Map showing ERCOT’s Recommended Roanoke Area Upgrades

Attachment No. 6:	Schematic of Transmission System in Proximate Area of Project

Attachment No. 7:   	Routing Memorandum of Brenda J. Perkins

Attachment No. 8: 	Listing of Directly Affected Land Owners for Notice

Attachment No. 9:	Habitable Structures within 500 Feet of the Filed Alternative Routes

Attachment No. 10:	Electronic Installations within 2,000 Feet of the Filed Alternative Routes

Attachment No. 11:	Aircraft Landing Facilities Near the Filed Alternative Routes

Attachment No. 12:	Copy of Notice to Directly Affected Land Owners

Attachment No. 13:	Copy of Notice to Utilities, Counties, Municipalities, OPUC, and Department of Defense Siting Clearinghouse

Attachment No. 14:	Copy of Newspaper/Public Notice

Attachment No. 15:	Copy of Courtesy Notice to Pipeline Owners/Operators

Attachment No. 16:	Park and Recreational Areas within 1,000 Feet of the Filed Alternative Routes

Attachment No. 17:	Cultural Resources within 1,000 Feet of the Filed Alternative Routes

Attachment No. 18:	Transmittal Letter to TPWD

Attachment No. 19:	Affidavit