## Slide 1
Jimmy Glotfelty
Commissioner
Public Utility Commission of Texas
Texas Advanced Nuclear Reactor Working Group
PUC Project #55421
Organizational Discussion
DRAFT

## Slide 2
Working Group Members - Sectors
Sector | 
Industrial | State Government
Electric System | Local Government
Higher Education | Supply Chain
Nuclear Knowledge | End Users – Chips – Data Centers
Construction | Financial
Nuclear Knowledge | Economic Development / Workforce
SMR Companies | Oil / Gas

## Slide 3: WG Structure
Working Group
Financial Incentives
ERCOT market changes
Siting
Brownfields
Gas, Coal to Nuclear
Regulatory
Workforce
Supply Chain
End Users
Eco Devo (CHIPS, Data Centers)
Oil and Gas
Chemical and Industrial Uses
R&D
Higher Ed
National labs
Community Involvement/ Safety /Security

## Slide 4
Preliminary Working Group Timeline
 | Sept / Oct | Nov / Dec | Jan / Feb | Mar / April | May / June | July / Aug | Sept / Oct | Nov / Dec
Name Task Force Members | X |  |  |  |  |  |  | 
First Meeting | X |  |  |  |  |  |  | 
Review Workplan | X |  |  |  |  |  |  | 
Develop Survey of Views | X |  |  |  |  |  |  | 
Outline Work Tasks | X | X |  |  |  |  |  | 
Public Meetings | X | X | X | X |  |  |  | 
File Meeting Summaries | X | X | X | X | X |  |  | 
Develop Draft Report |  |  |  |  | X | X |  | 
Finalize Recommendations |  |  |  |  |  | X | X | 
Public Meeting to Discuss Recs. |  |  |  |  |  |  | X | 
Present Report to Governor |  |  |  |  |  |  |  | X

## Slide 5: Preliminary Public Meeting Timeline
Meetings | October | November | December | January | February | March | April
SMR Company Presentations | X |  |  |  |  |  | 
Texas Supply Chain | X |  |  |  |  |  | 
Community Involvement |  | X |  |  |  |  | 
State Funding Ideas / Possibilities |  | X |  |  |  |  | 
University / R&D Role |  | X |  |  |  |  | 
High Technology use for Nuclear |  |  | X |  |  |  | 
Oil and Gas use for Nuclear |  |  | X |  |  |  | 
Industrial Uses for Nuclear |  |  |  | X |  |  | 
Discussion on Texas Sites |  |  |  | X |  |  | 
Environmental Discussion |  |  |  |  | X |  | 
State Law / ERCOT Changes |  |  |  |  | X | X | 
Meeting with House and Senate |  |  |  |  |  | X | 
Discuss Federal Incentives |  |  |  |  |  |  | X

## Slide 6: General Thoughts on Meetings
Initiative | To Do’s
All Meetings Broadcast | Texas Admin is set up
All Presentations filed in Docket 55421 | On Going
All Meetings in Austin at PUC | Reserve Hearing room
Name Tags / Tents Needed | Support staff to help
Public Comment at all meetings | Yes, they are conversational workshops
Are there formal Invites / Agendas | They will be filed and sent to email group

## Slide 7: PUC Staff Support for Task Force
PUC Team
  Jimmy Glotfelty
  VA Stephens – Project Management
  Ramya Ramaswamy – Market Analysis
  Rich Parsons - Communications
  Mike Hoke – Public Outreach
  Consultant

## Slide 8: Initial Major Questions to Answer
Is Texas willing to put forth financial resources to attract a SMR? Is HB 5 enough? What other resources?
How do we incent industry to invest in SMR technologies?
Should the Texas electricity market be modified to promote SMR’s and other dispatchable resources?
Will/could the Texas Power Program help attract SMR’s?
Can Texas permit a site and transfer it at a later date?
Should the state consider using state or other public lands (ports/universities) for a site?
What financial resources are needed to attract the nuclear supply chain?
Should Texas develop a plan for 20 SMR’s?
What must state agencies do to attract supply chain?
Should the state consider developing a new nuclear development agency? Precedent of Superconducting Super Collider.
How does Texas help bridge the valley between licensing and operation?
What can the Texas federal delegation do to help the state?
What are university roles? Can they build a new reactor?
What legislation is needed or modified for next session?