## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
1904810 | Hilltop-West Weatherford Rebuild | Parker | Rebuild 12.93 miles of single pole, double circuit from Hilltop Substation to West Weatherford Substation | 2022-09-19 | 2023-09-08 | 2023-05-24 | 9817000 | 12568116.69 |  |  | 100% | 138 | 138 | 12.93 | 1433 ACSS/TW | Single Pole Concrete or Steel | 60 | 12.93 | 0 | 0 | 25.101(c)(5)(B) | Affidavit to be filed upon request
1902510 | India-DWU Southside Rebuild | Dallas/ Ellis | Rebuild 10.11 miles of single pole, single circuit from India Substation to DWU Southside Substation | 2022-10-24 | 2023-09-21 | 2023-08-31 | 6950000 | 13798344.88 |  |  | 100% | 69 | 138 | 10.11 | 1433 ACSS/TW | Single Pole Concrete or Steel | 60 | 10.11 | 0 | 0 | 25.101(c)(5)(B) | Affidavit to be filed upon request
17016 | Windsor Switch Transmission | McLennan | Construction and removal of temporary shoo fly needed to perform work at Windsor Switch Station | 2022-09-19 | 2023-10-17 | 2023-09-29 | 550000 | 1078297.72 |  |  | 100% | 138 |  | 0.28 | 795 ACSR | Wood H-Frames | NA | NA | NA | NA | 25.83(a)(3) | Affidavit to be filed upon request
19014 | Downing Transmission | Comanche | Remove existing steel deadend and install new single pole deadend and HF1 tower at Downing Substation | 2023-04-24 | 2023-06-07 | 2023-06-01 | 600000 | 747738.5 |  |  | 100% | 138 | 138 | 0.04 | 1033 ACSR | Single Pole Concrete or Steel | 60 | 0.04 | NA | NA | 25.101(c)(5)(A) | Affidavit to be filed upon request
19054 | Bankhead P.O.I. | Parker | Construct P.O.I. in the Hudson Oaks to Railroad 138kV line | 2023-01-16 | 2023-05-19 |  | 1500000 | 1847603.57 |  |  | 100% | 138 | 138 | 0.15 | 795 ACSR | Single Pole Concrete or Steel | 60 | 0.15 | NA | NA | 25.101(c)(5)(A) | Affidavit to be filed upon request
1004120 | Gibbs Transmission | Walker | Construct 0.11 miles of single circuit 138kV transmission line to connect Gibbs and ETEC substations | 2023-11-13 | 2023-11-27 | 2024-04-08 | 374099.46 | 367741.46 |  |  | 100% | NA | 138 | 0.11 | 959 ACSS/TW | Single Pole Concrete or Steel | NA | NA | NA | NA | 25.101(c)(5)(A) | Affidavit to be filed upon request
19014 | Holder Line Mods | Brown | Rerouting two 138kV transmission lines into the Holder Substation, Rising Star-Holder and Holder - Brownwood. | 2024-01-02 | 2024-02-28 | 2024-02-28 | 431715 | 430422.15 |  |  | 100% | 138 | 138 | 0.21 | 959 ACSS/TW & 477 ACSR | Single Pole Concrete or Steel | 60 & 100 | NA | NA | NA | 25.101(c)(5)(B) | Affidavit to be filed upon request
21600 | Petteway-Kosse SW Mods | Robertson | Remove 2 existing H-frame tangents and install 2 new H-frame deadends on the Petteway to Kosse SW line . | 2023-09-25 | 2023-11-09 | 2023-11-07 | 750000 | 884276.19 |  |  | 100% | 138 | 138 | 0.1 | 795 ACSR | Single Pole Concrete or Steel | 60 | 0.1 | NA | NA | 25.101 (C)(5)(D) | Affidavit to be filed upon request
2160001 | Rector Rd to Aubrey Line Mods | Denton | Replace structures 1/4 thru 1/9 due to TxDOT IH35 ROW Expansion | 2023-12-01 |  |  | 1621923.5 |  |  |  | 0% | 138 | 138 | 0.75 | 795 ACSR | Single Pole Concrete or Steel | 60 | 0.75 | 0 | 0 | 25.101 (C)(5)(D) | Affidavit to be filed upon request
22022 | Judith Transmission Line | McLennan | Construct 0.71 miles of double circuit 138kV transmission line to loop the existing McGregor – Moody through the new Judith substation. | 2024-03-11 |  |  | 1250000 | 1568026.68 |  |  | 75% | NA | 138 | 0.71 | 795 ACSR | Single Pole Concrete or Steel | NA | NA | 70 | 0.71 | 25.101(c)(5)(A) | Affidavit to be filed upon request
23043 | Hideout P.O.I. | Wise | Construct P.O.I. in the Jack County to Wise County Switch Station 138kV transmission line | 2024-03-18 |  |  | 600000 | 565000 |  |  | 30% | 138 | 138 | 0.04 | 959 ACSS/TW | Single Pole Concrete or Steel | 70 | 0.04 | NA | NA | 25.101(c)(5)(A) | Affidavit to be filed upon request
22021 | Tomcat P.O.I. | Johnson | Construct P.O.I. in the Wildcat-Wildcat Tap 138kV transmission line | 2024-08-19 |  |  | 1000000 |  |  |  | 0% | 138 | 138 | 0.04 | 1033 ACSR | Single Pole Concrete or Steel | 70 | 0.04 | NA | NA | 25.101(c)(5)(A) | Affidavit to be filed upon request
22022 | Green Creek Line Mods | Erath | Construct a shoofly, wreck out a box structure and reterminate two lines into the new Green Creek Substation. | 2024-08-05 |  |  | 802755.28 | 788904.63 |  |  | 0% | 69 | 138 | 0.1 | 795 ACSR | Single Pole Concrete or Steel | 60 | 0.1 | NA | NA | 25.101(c)(5)(A) | Affidavit to be filed upon request
Note on H2: aboling: Please enter only a single integer, if possible.
Note on I2: aboling: Please enter only a single integer, if possible.
Note on M2: aboling: If applicable.
Note on N2: aboling: If applicable.