## MonthlyReportForm-AEPTX North
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
TA-2022008 T10558836 (A22008001) (A22008002) | OnyxTap-Ft. Phantom Pump 69-kV T-Line Relocation (TxDOT) | Jones | Relocate a section of the Onyx Tap to Ft. Phantom transmission line and switch structure. Install & remove structures & Upgrade the 69-kV line to 138-kV standards. | 2024-07-17 | 2024-09-06 |  |  | 3602266 |  |  | 0 | 69 |  | 0.99 | T2 477 ACSR "Hawk" | Steel Mono Pole | Centerline | 0.99 | 100 | 1.01 | 16 TAC 25.101 (c)(5)(F) | Landowner consent obtained. Final cost is with the CIAC.CIAC is $3,602,259 This project is 70.14% reimbursable.
TA-2022008 T10559194 (A22008004) | Laramie 69-kV Switch Station | Jones | Install a 138-kV two-way, SCADA controlled switch structure at the tap structure. | 2024-07-17 | 2024-09-04 |  |  | 1055681 |  |  | 0 | 69 |  |  | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.83(a)(3) | Landowner consent obtained