## MonthlyReportForm-SWEPCO
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
42941390 (P18215001) | Lydia 345-kV Station | Bowie | Convert the Lydia 345kV station to a ring bus configuration, eliminating the 3-terminal line by adding breakers. A new station will be built in the clear on newly purchased property; the existing station will be retired. | 2020-09-14 | 2022-05-11 | 2022-12-08 |  | 15843030 |  |  | 99 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Property Purchased
42952896 (A18106011) | N Marshall 69-kV Substation: Construct Box Bay | Marshall/Harrison | The 69-kV portion of the station will be replaced with a box bay. Breaker 7570 with be replaced with new 2000 A breaker as part of this rebuild. A DICM will be installed to house all of the new transmission relay equipment. | 2021-02-01 | 2022-03-15 | 2022-02-10 |  | 3940359 |  |  | 99 |  | 69 | [7 empty] | 16 TAC 25.83(a)(3) | Within AEP Property
42963433 (A18106017) | N Marshall - Marshall 69-kV Retermination | Marshall/Harrison | Terminate the existing N Marshall to Marshall 69-kV line into new Box Bay as part of the Jefferson station rebuild | 2021-02-01 | 2021-12-31 | 2021-12-30 |  | 514806 |  |  | 99 | 69 |  | 0.02 | 795 KCM ACSR "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP Property
42952898 (A18106002) (A18106004) | Woodlawn - N Marshall 69-kV Rebuild | Marshall/Harrison | Rebuild and reconductor the Woodlawn to N. Marshall 69-kV transmission line to 138-kV standards but will continue to operate at 69 kV. | 2021-02-01 | 2021-12-31 | 2021-12-30 |  | 8098078 |  |  | 99 | 69 |  | 7.55 | 795 KCM ACSR "Drake" | Steel Mono Pole | Centerline | 7.55 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing Existing Easement Landowners Noticed
42939973 (P18231001) (P18231002) | Carthage T 138-kV Box Bay | Panola | Install 3 new138-kV breakers in current box bay. Expand station site to accommodate DICM. Install line relaying and breakers controls in new control house. | 2021-04-14 | 2021-12-01 | 2021-12-30 |  | 3830879 | 4299483 | 12.23% | 100 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Property Purchased for Expansion
42907529 (A18093003) | IPC Domino - Red Springs REA 138-kV T-Line | Bowie,Cass | Rebuild and Reconductor the IPC Domino to Red Springs REA 138-kV transmission line. | 2021-08-01 | 2022-02-25 | 2022-02-25 |  | 16929647 |  |  | 99 | 138 |  | 8.29 | 1590 ACSR/AW 54/19 "Falcon" | Steel, Single Pole | 100 | 8.29 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowners noticed
42941398 (P18215002) | Lydia - Valiant 345-kV Line: Retermination | Bowie | Reterminate the Lydia - Valliant 345-kV transmission line into the newly reconstructed Lydia 345-kV Station. | 2021-09-27 | 2022-05-11 | 2022-12-08 |  | 994017 |  |  | 99 | 345 |  |  |  | Steel, Single Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
42941406 (P18215005) | Lydia - NW Texarkana 345-kV Line: Retermination | Bowie | Reterminate the Lydia - NW Texarkana 345-kV transmission line into the newly reconstructed Lydia 345-kV Station. | 2021-09-27 | 2022-05-11 | 2022-12-08 |  | 1263867 |  |  | 99 | 345 |  |  |  | Steel, Single Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
42941408 (P18215006) | Lydia - Welsh 345-kV Line: Retermination | Bowie | Reterminate the Lydia - Welsh 345-kV transmission line into the newly reconstructed Lydia 345-kV Station. | 2021-09-27 | 2022-05-11 | 2022-12-06 |  | 996635 |  |  | 99 | 345 |  |  |  | Steel, Single Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
42963930 (P19057001) (P19057002) | Morton to E Burges 138-kV Transmission Line | Van Zandt | Construct a new 2.57 mile 138-kV transmission line from a cut-in near the SWEPCO Morton 138-kV Substation to a cut-in near the WCEC E Burges 138-kV Substation. | 2022-08-01 | 2022-11-02 | 2023-10-27 | 4185088 | 4700779.67 |  |  | 99 |  | 138 | 2.57 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel Mono Pole |  |  | 100 | 2.57 | 50669 | PUCT Docket 50669 Approved on 05/07/2021
T10329431 (P20025001) (P20025003) | Murvaul 138-kV Box Bay | Panola | Construct a new 138-kV box bay with Scada controlled switches. | 2022-01-31 | 2022-09-23 | 2022-11-10 |  | 1548080 | 2539894 | 64.07% | 100 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Landowner consent obtained
T10356096 (P20025002) | Carthage T - Tenaha 138-kV T-Line | Panola | Construct a temporary tap prior to the permanent box bay installation. Re-terminate the existing Carthage T to Tenaha transmission line into new Murvaul Tap 138-kV Box Bay. | 2022-01-17 | 2022-11-30 | 2022-12-13 |  | 1348733 | 1181716 | -12.38% | 100 |  | 138 | 0.2 | 1272 KCM 54/19 ACSR | Steel Mono Pole |  |  | 100 | 0.2 | 16 TAC 25.101 (c)(5)(A) | Landowner consent obtained
42965029 (P18231006) | Carthage Connection 138/69-kV POD | Panola | Update relay settings and tuner at Carthage 69/138kV POD. | 2023-10-01 | 2023-11-30 | 2023-10-31 |  | 224032 | 325046 | 45.09% | 100 | 138 / 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42908317 (A15706581) | Childress Airport 69-kV Substation | Childress | Replace switches 6147 and 6153 with 2000 A switches. Upgrade upper and lower bus. | 2023-01-25 | 2023-03-08 | 2023-02-28 |  | 443841 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
43002631 (A16806635) | Clarendon - W. Childress 69-kV T-Line | Childress | Add Fiber Transitions at the substations along the Clarendon to NW Memphis to W Childress 69-kV transmission line. | 2022-01-10 | 2023-12-14 | 2024-02-28 |  | 755188 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3)
T10052253 (P18251001) (P18251002) (P18251015) | West Atlanta 138/69-kV Substation | Cass | Demo the existing West Atlanta station and rebuild it on an adjacent piece of property. Convert the 138-kV and 69-kV portions to a ring bus configuration with all of the necessary relaying. The 90MVA auto will be re-used at the new W. Atlanta station. | 2022-03-07 | 2022-12-01 | 2022-12-12 |  | 10344453 |  |  | 99 | 138 / 69 | [8 empty] | 16 TAC 25.83(a)(3) | Property purchased for expansion
T10052341 (P18251004) | West Atlanta - Linden 69-kV T-Line | Cass | Reterminate the West Atlanta to Linden 69-kV transmission line into the newly rebuilt W. Atlanta Substation. | 2022-03-07 | 2022-12-01 | 2023-02-08 |  | 882380 |  |  | 99 | 69 |  | 0.12 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP purchased property
T10052462 (P18251005) | West Atlanta - Atlanta 69-kV T-Line | Cass | Reterminate the West Atlanta to Atlanta 69-kV transmission line into the newly rebuilt W. Atlanta Substation. | 2022-03-07 | 2022-12-01 | 2023-02-08 |  | 374269 |  |  | 99 | 69 |  | 0.15 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within AEP purchased property
42962665 (A18105002) | Jefferson 138-kV Switch Station | Marion | Replace 138-kV Marshall line relaying. Replace 138-kV CB-3650 controls with SEL451S relay. Add 3 new CCVTs. | 2022-06-04 | 2022-11-17 |  |  | 263000 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10476409 (A20006004) | IPC Domino - West Atlanta 138-kV T-Line: Telecomm Fiber Transitions | Cass | Install telecomm fiber transitions from T-line into station at IPC Domino, IPC Tap, Cass Tap, and West Atlanta | 2022-08-15 | 2024-03-09 | 2024-03-14 |  | 255965 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10162138 (A20006003) (A20006013) | Cass Tap - West Atlanta 138-kV T-Line | Cass | Rebuild and Reconductor the Cass Tap to West Atlanta 138-kV transmission line. | 2022-08-15 | 2022-11-22 | 2022-12-14 |  | 3187425 |  |  | 99 | 138 |  | 1.81 | 795 KCM ACSR "Drake" | Steel, Single Pole | 100 | 1.81 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowners noticed
T10162127 (A20006001) (A20006011) | IPC Domino - IPC Tap Switch 138-kV T-Line | Cass | Rebuild and Reconductor the IPC Domino to IPC Tap Switch 138-kV transmission line. | 2022-09-15 | 2023-03-03 | 2023-03-02 |  | 7389905 |  |  | 99 | 138 |  | 2.67 | 795 KCM ACSR "Drake" | Steel, Single Pole | 100 | 2.67 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowners noticed
42966143 (P18215009) | NW Texarkana 345-kV Station: Carrier Tuner | Bowie | Remote end upgrades to support the newly upgraded Lydia 345-kV station. | 2022-09-20 | 2022-11-08 | 2022-12-08 |  | 438880 | 349533 | -20.36% | 100 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10130478 (A20006005) | IPC Domino Relay Upgrade | Cass | IPC Domino Substation: Replace line relays on line to West Atlanta and complete associated terminal upgrades. | 2022-11-01 | 2023-03-03 | 2023-03-02 |  | 912876 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42965027 (P18231005) | Tenaha 138-kV Substation | Tenaha/Shelby | Update settings and tuner | 2022-11-10 | 2022-11-29 | 2022-12-12 |  | 295543 | 420060 | 42.13% | 100 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10162129 (A20006002) (A20006012) | IPC Tap Switch - Cass Tap 138-kV T-Line | Cass | Rebuild and Reconductor the IPC Tap Switch to Cass Tap 138-kV transmission line. | 2022-12-01 | 2023-12-20 | 2023-12-18 |  | 14196277 |  |  | 99 | 138 |  | 14.11 | 795 KCM ACSR "Drake" | Steel, Single Pole | 100 | 14.11 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowners noticed
42907620 (A15706585) | Clarendon REC 69-kV Tap | Donley | Install phase-over-phase (POP) switch | 2023-03-12 | 2023-04-27 | 2023-05-02 |  | 1440112 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42907595 (A15706583) | Memphis LHEC 69-kV Tap | Hall | Install phase-over-phase (POP) switch | 2023-04-24 | 2023-06-08 | 2023-06-09 |  | 1438861 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42908315 (A15706580) | Carey 69-kV Substation | Childress | Install phase-over-phase (POP) switch | 2023-06-02 | 2023-07-18 | 2023-08-03 |  | 682491 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10171890 (A20063001) (A20063002) (A20063003) | Mineola - N. Mineola 69-kV T-Line: Rebuild | Mineola/Wood | Rebuild and reconductor the Mineola to N. Mineola 69-kV transmission line to 138-kV standards but will continue to operate at 69 kV. Reconductor-only a 0.80 mile segment of this transmission line on existing concrete structures. | 2023-02-27 | 2023-05-31 | 2023-05-17 |  | 5870000 |  |  | 99 | 69 |  | 2.98 | 556.5 ACSR 26/7 "Dove" | Steel, Single Pole | Centerline | 2.98 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowners noticed
T10130443 (A20007001) (A20007002) (A20007005) | Knox Lee - Rock Hill 138-kV Rebuild | Gregg, Rusk, Panola | Rebuild a 7.6-mile section of the Knox Lee to Rock Hill 138-kV transmission line and install OPGW. Replace conductor only on separate 3.7-mile section of the same transmission line. | 2023-04-15 | 2024-12-15 |  |  | 10689701 |  |  | 65 | 138 |  | 11.3 | 795 KCM ACSR "Drake" | Steel, Single Pole | Centerline | 11.3 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowners noticed
A18125001 (T10405233) | Scottsville 138-kV Switch Station Rebuild | Scottsville/Harrison | Rebuild the existing Scottsville 138-kV Switch Station approximately 200 feet to the east of the existing station. | 2023-04-06 | 2023-08-27 |  |  | 4803093 |  |  | 45 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
A18125004 (T10487847) | Pirkey - Scottsville 138-kV T-Line: Retermination | Scottsville/Harrison | Reterminate the Pirkey to Scottsville 138-kV transmission line into the rebuilt Scottsville 138-kV Switch Station. | 2023-04-06 | 2023-08-27 |  |  | 495598 |  |  | 10 | 138 |  | 0.02 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
A18125007 (T10296219) | Longwood - Scottsville 138-kV T-Line Retermination | Scottsville/Harrison | Reterminate the Longwood to Scottsville 138-kV transmission line into the rebuilt Scottsville 138-kV Switch Station. | 2023-04-06 | 2023-08-27 |  |  | 534946 |  |  | 10 | 138 |  | 0.02 | 1272 KCM 54/19 ACSR "PHEASANT" | Steel, Single Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
42635328 (A16926040) (A16926042) | Jefferson Switch - Marshall 138-kV T-Line | Marion, Marshall/Harrison | Rebuild and reconductor the existing Jefferson Switch to Marshall 138-kV transmission line. | 2023-04-21 | 2023-10-04 |  |  | 21651112 |  |  | 0 | 138 |  | 16.6 | 1590 ACSR/AW 54/19 "Falcon" | Steel Mono Pole | 16.6 | Centerline |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowners Noticed
42962670 (A18105003) | Marshall 138-kV Substation | Marshall/Harrison | Upgrade relays to Jefferson Switching Station. | 2023-04-21 | 2023-10-04 |  |  | 1727081 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42963946 (P18246005) (P18245007) | Atlanta - Bloomburg 69-kV T-Line | Cass | Install a permanent shoe-fly along the Atlanta to Bloomburg 69-kV transmission line to contruct the new Bloomburg 69-kV Substation. | 2023-08-07 | 2024-11-01 |  |  | 1201497 |  |  | 50 | 69 |  | 0.14 | 1590 ACSR/AW 54/19 "Falcon" | Steel Mono Pole |  |  | 100 | 0.14 | 16 TAC 25.101 (c)(5)(A) | Landowner consent obtained
T10150662 (A20007012) | Tatum Tap 138-kV Switch | Panola | Replace switches 10594 and 10655 with new 2000A switches. | 2024-02-29 | 2024-06-04 |  |  | 780510 |  |  | 85 | 138 | [8 empty] | 16 TAC 25.83(a)(3)
42907618 (A15706584) | Hedley 69-kV Substation | Childress | Replace existing switch with phase-over-phase (POP) switch | 2023-09-05 | 2023-09-20 | 2023-09-21 |  | 457918 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3)
T10417569 (P21721001) | Overton 138-kV Substation: Capacitor Replacement | Rusk | Replace capacitor bank and associated equipment including a new circuit breaker for the new cap bank | 2023-10-10 | 2023-11-30 | 2023-12-12 |  | 1106319 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10408928 (A20084021) | Perdue 138-kV Substation: Failed Relay | Upshur | Replace Line Relay to Harrison Replace Breaker Control Relays Replace CCVT’s & Line Tuner | 2023-09-25 | 2023-12-08 | 2023-11-21 |  | 595723 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10408932 (A20084023) | Harrison Road 138-kV Substation: Failed Relay | Gregg | Replace Line Relay to Perdue Replace Breaker Control Relay | 2024-01-08 | 2024-03-01 | 2024-03-08 |  | 372830 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10066111 (DP16S03C2) | Kilgore - Sabine 69-kV T-Line: Cut-In | Gregg | Rebuild and terminate the existing Kilgore to Sabine 69-kV T-Line into new Sabine Substation. | 2023-09-04 | 2024-11-18 |  |  | 1139331 |  |  | 0 | 69 |  | 0.26 | 795 KCM ACSR "Drake" | 2 Steel deadend, 2 steel Mono Pole | 100 |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
43006266 (DP16S03C3) | Clarksville - Sabine 69-kV T-Line: Cut-In | Gregg | Rebuild and terminate the existing Clarksville to Sabine 69-kV T-Line into new Sabine Substation. | 2023-09-04 | 2024-11-18 |  |  | 581902 |  |  | 0 | 69 |  | 0.1 | 795 KCM ACSR "Drake" | 1 Steel deadend structure | 100 |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
42908319 (A15706593) | W Childress 138/69-kV Substation | Childress | Upgrade Auto-Transformer, DICM expansion, new RTU, new CCVT and install surge arrester | 2023-09-25 | 2023-12-08 | 2023-12-18 |  | 2108233 |  |  | 99 | 138 / 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10447788 (P22015001) | Long Glade 138-kV Switch | Rusk | Install 3-Way phase-over-phase (POP) Long Glade Tap along the Knox Lee to NW Henderson 138-kV line with three motor operated and SCADA controlled switches. Long Glade 138 kV TFC Knox Lee Telecom Work. | 2023-10-23 | 2024-01-19 | 2024-01-26 |  | 1184997 |  |  | 90 | 138 |  |  | 795 KCM ACSR "Drake" | Steel Pole Mono |  |  |  |  | 16 TAC 25.83(a)(3) | Landowner consent obtained
T10503337 (A22033007) | North Mineola 69/138-kV Substation | Mineola/Wood | Replace failed 69-kV 23 MVAR Capacitor Bank (8290). | 2023-09-14 | 2023-10-27 | 2023-10-27 |  | 939628 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10503332 (A22033005) | North Mineola 69/138-kV Substation | Mineola/Wood | Replace failed 138-kV 23 MVAR Capacitor Bank (4390). | 2023-10-30 | 2023-12-15 | 2023-12-21 |  | 1010391 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10447803 (P22015003) | Knox Lee - NW Henderson 138-kV T-Line | Rusk | Replace existing dead-end structures both north and south of the new Long Glade POP Switch. | 2023-10-23 | 2024-01-19 | 2024-01-26 |  | 887057 |  |  | 90 | 138 |  |  | 795 KCM ACSR "Drake" | Steel Pole Mono |  |  |  |  | 16 TAC 25.83(a)(3) | Landowner consent obtained
T10561606 (A22084028) | LeBrock 345-kV Station: Relay Failure | Harrison | Replace the three existing DME (DME_LZ1T1) equipment on panel 301 with three GE-N60 relays | 2023-10-02 | 2023-03-30 |  |  | 379474 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10487847 (A18125004) | Pirkey - Scottsville 138-kV T-Line: Retermination | Harrison | Reterminate the Pirkey to Scottsville 138-kV transmission line into new Scottsville Station. | 2024-01-09 | 2024-03-31 |  |  | 495598 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
TS0274023 (A22084040) | Diana 345-kV Station: Transformer Replacement | Harrison | Replace the existing 345-kV failed transformer with a spare transformer stored on site. Remove and construct a new oil containment pit around the 345-kV transformer | 2023-10-30 | 2024-02-23 |  |  | 1275000 |  |  | 99 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
42907623 (A15706591) | Clarendon 69-kV Substation | Clarendon/Donley | Remove SW 2093 and SW 2488. Remove/Replace SW 4484, 4486, 2667. Replace Surge Arrestors and PT. Install new CCVT | 2023-12-04 | 2024-02-28 | 2024-02-28 |  | 1490675 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42995483 (A21216009) | Gates 69-kV Substation: SWEPCO RTU Reliability 2021 | Longview/Gregg | Replace obsolete RTU to provide more reliable communication & data collection/monitoring. | 2023-11-30 | 2023-12-28 |  |  | 374767 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42995482 (A21216007) | Eastex 138-kV Switch Station: SWEPCO RTU Reliability 2021 | Longview/Gregg | Replace obsolete RTU to provide more reliable communication & data collection/monitoring. | 2023-11-30 | 2023-12-11 | 2023-11-03 |  | 374891 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10463840 (A20084031) | NW Texarkana 138-kV Switching Station | Bowie | Replace all EM relays for this line with our current standard. DM 07.01 L90/SEL-411L/UPLCII. Replace relays associated with CB 10770 and 11840 (SBC-21 (551), NLR (79), and IJS-52D relays). | 2024-02-05 | 2024-03-15 | 2024-03-22 |  | 862987 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10290425 (A20087001) (A20087003) (A20087004) | Lake Pauline - West Childress (STR 183) 138-kV T-Line | Hardeman,Childress | Rebuild and reconductor 19.40 miles of the Lake Pauline to West Childress 138-kV transmission line. | 2024-04-15 | 2025-10-31 |  |  | 20965386.3435 |  |  | 15 | 138 |  | 19.4 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 19.4 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easemsnts Landowners Noticed
T10435502 (A20087002) (A20087003) (A20087004) | Lake Pauline (STR 183) - West Childress 138-kV T-Line | Childress | Rebuild and reconductor 15.70 miles of the Lake Pauline to West Childress 138-kV transmission line. | 2024-09-15 | 2025-10-31 |  |  | 16640597.6565 |  |  | 5 | 138 |  | 15.7 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 15.7 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easemsnts Landowners Noticed
42995482 (A21216007) | Eastex 138-kV Substation: SWEPCO RTU Reliability 2021 | Longview/Gregg | Replace obsolete RTU to provide more reliable communication & data collection/monitoring. | 2024-03-08 | 2024-03-16 |  |  | 374891 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42921976 (A20216001) | Liberty City 138-kV Substation: RTU Reliability | Gregg | Replace obsolete RTU to provide more reliable communication & data collection/monitoring. | 2024-03-08 | 2024-03-18 |  |  | 310605 |  |  | 80 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42921988 (A20216009) | Monroe Corners 69-kV Substation: RTU Reliability | Rusk | Replace obsolete RTU to provide more reliable communication & data collection/monitoring. | 2024-03-08 | 2024-03-18 |  |  | 462162 |  |  | 70 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42965012 (P18224001) | Jefferson 138-kV Switch Station | Marion | Install new breaker on Jefferson Switching – IPC Jefferson circuit. Replace breaker 8790 with 3000A breaker. Install new DICM. | 2024-02-05 | 2023-05-18 |  |  | 3629290 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
42965044 (P18224004) | IPC Jefferson 138-kV Substation | Marion | Upgrade relaying at IPC Jefferson remote end. | 2024-02-05 | 2023-05-18 |  |  | 298121 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10278598 (A20131005) | Beckville 69-kV Substation | Panola | Replace breaker 9010 with new 2000A breaker. Replace transmission EM/static relays. Replace RTU. Replace 600A switches with new 2000A switches and 350 KCM CU sub conductor on line terminal to Rock Hill. Remove bypass switches 9011 and 4181. | 2024-02-19 | 2024-11-26 |  |  | 1674715 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10386734 (P21299001) | TB Beard 69-kV POP Switch | Hall | Install a 69-kV phase-over-phase (POP) on structure 44 with three motor operated SCADA controlled 69-kV switches. | 2024-02-05 | 2024-04-04 |  |  | 1926477 |  |  | 99 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10386738 (P21299003) (P21299005) (P21299007) | Memphis - Estelline 69-kV T-Line | Hall | Terminate the Memphis to Estelline 69-kV transmission line into the new TB Beard 69-kV Phase-Over-Phase (POP) Switch. | 2024-02-05 | 2024-04-04 |  |  | 807775 |  |  | 99 | 69 |  | 0.01 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 0.01 |  |  | 16 TAC 25.101 (c)(5)(A) | Landowner Noticed
T10309898 (A20092004) | Bann 69-kV Substation | Texarkana/Bowie | Replace the north auto with a new 133 MVA auto. Relocate CB 9780 and associated CCVTs to south side of box bay. | 2024-04-01 | 2024-11-15 |  |  | 2404737 |  |  | 65 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10309912 (A20092006) | Kings Highway 69-kV Substation | Texarkana/Bowie | Replace 500 CU switch jumpers. | 2024-10-01 | 2024-11-01 |  |  | 279000 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10278596 (A20131004) | Rockville 69-kV Substation | Panola | Replace line relays. Replace 600 A switches with new 2000 A switches and 500 KCM CU sub conductor on line terminal to Beckville. Reset relays to not limit the line. | 2024-03-15 | 2024-11-26 |  |  | 529302 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10278570 (A20131001) (A20131002) (A20131003) | Beckville - Rock Hill 69-kV Rebuild | Panola | Rebuild and reconductor the Beckville to Rock Hill 69-kV transmission line to 138-kV standards. Will continue to operate at 69-kV. | 2024-03-15 | 2024-11-26 |  |  | 7504133 |  |  | 0 | 69 |  | 4.04 | 795 KCM ASCR "Drake" | Steel Mono Pole | Centerline | 4.04 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed.
T10177714 (A20065001) (A20065002) (A20065003) | Diana - Lone Star South 138-kV Rebuild | Morris, Camp, Upshur, Marion, Harrison | Rebuild and reconductor the Lone Star South to Diana 138-kV transmission line. | 2024-08-01 | 2025-03-27 |  |  | 20187392 |  |  | 0 | 138 |  | 12.6 | 1272 KCM ACSR "Pheasant" | Steel Mono Pole | Various | 12.6 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements. Landowners Noticed. Landowner Consent obtained as necessary.
T10519802 (A19039058) | Pirkey 138/345-kV Station (Pirkey Station Rehab) | Harrison | Replace/Remove Breakers/Relays/RTU. Add Health Monitoring. Install new fencing. | 2024-04-17 | 2025-06-12 |  |  | 12726069 |  |  | 15 | 138/345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10519802 (A19039058) | LeBrock 345-kV Station (Pirkey Station Rehab) | Harrison | Upgrade remote end relaying and RTU. Add DICM. | 2024-04-17 | 2024-12-31 |  |  | 2080007 |  |  | 15 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10519802 (A19039058) | Diana 345-kV Station (Pirkey Station Rehab) | Harrison | Upgrade remote end relaying. | 2024-04-17 | 2024-05-15 |  |  | 1142075 |  |  | 15 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10519802 (A19039058) | Knox Lee 138-kV Station (Pirkey Station Rehab) | Gregg | Upgrade remote end relaying and RTU. | 2025-05-16 | 2025-05-29 |  |  | 884994 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10519802 (A19039058) | Pirkey 138/345-kV Station (Pirkey Station Rehab) | Harrison | Add PQ monitoring on 345-kV and 138-kV bus. | 2025-06-06 | 2025-05-15 |  |  | 189085 |  |  | 0 | 138/345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
T10178042 (A20065004) | Diana 138-kV Substation: Remote End Work | Harrison | Replace/Remove 138kV breaker, RTU and Relays. | 2025-02-19 | 2025-03-27 |  |  | 1250604 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
TA-2020033 T10458244 (A20033125) | Jefferson 138-kV Switching Station: TS Equipment | Marion | Installing new DWDM Fiber Optic Equipment inside a concrete shelter to monitor communications throughout the AEP Telecommunications Network | 2024-07-29 | 2024-11-30 |  |  | 1241985 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station property
TA-2020033 T10458248 (A20033126) | Jefferson 138-kV Switching Station: TS Shelter | Marion | Installing a concrete shelter, fencing, generator, propane tank grounding wire, underground conduit and 200AMP distribution service to operate new DWDM fiber optic equipment | 2024-07-29 | 2024-11-30 |  |  | 1308524 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station property
TA-2020033 T10475806 (A20033127) | Jefferson 138-kV Switching Station: TS Fiber Cable Extension | Marion | Installing underground conduit and wire from the existing station to the new DWDM to allow for communications between the two facilities | 2024-07-29 | 2024-11-30 |  |  | 216188 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station property
TA-2020103 T10611765 (A20103148) | Petty 138-kV Switching Station: TS Shelter | Titus | Installing a concrete shelter, fencing, generator, propane tank grounding wire, underground conduit and 200AMP distribution service to operate new DWDM fiber optic equipment | 2024-07-22 | 10/31/20204 |  |  | 1086227 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station property
TA-2020103 T10611737 (A20103147) | Petty 138-kV Switching Station: TS Equipment | Titus | Installing new DWDM Fiber Optic Equipment inside a concrete shelter to monitor communications throughout the AEP Telecommunications Network | 2024-07-22 | 2024-10-31 |  |  | 1567121 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station property
TA-2020103 T10611765 (A20103153) | Petty 138-kV Switching Station: TS Fiber Cable Extension | Titus | Installing underground conduit and wire from the existing station to the new DWDM to allow for communications between the two facilities | 2024-07-22 | 10/31/20204 |  |  | 292388 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station property
TP-2022017 T10446230 (P22017001) | Tiller Tap 138-kV Switch Station | Panola | Install new Tiller Tap 138-kV Switching Station along the SWEPCO Rock Hill to Southwest Shreveport 138-kV transmission line with SCADA controlled switches on the lines to Rock Hill and Southwest Shreveport. | 2024-08-04 | 2025-01-30 |  |  | 2369996 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Landowner consent obtained
TP-2022017 T10446235 (P22017002) | Tiller Tap 138-kV Switch Station: Metering | Panola | . Install metering & 138-kV transformers on the new Tiller Tap 138-kV Switching Station. | 2024-08-04 | 2025-01-30 |  |  | 405337 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Landowner consent obtained
TP-2022017 T10446249 (P22017003) (P22017004) | Rock Hill - SW Shreveport 138-kV T-Line | Panola | Terminate the Rock Hill to SW Shreveport 138-kV transmission line into the new Tiller Tap 138-kV Switching Station. | 2024-08-04 | 2025-01-30 |  |  | 2132640 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.101 (c)(5)(A) | Landowner consent obtained
TA-2019445 T10310730 (A19445002) | Tenaska 345-kV Station | Rusk | Metering upgrade - Install new: Panel, Meter, and upgrade Comms | 2024-09-09 | 2024-09-20 |  |  | 251000 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Preperty
TA-2020103 T10610750 (A20103112) | Perdue 69/138-kV Station: Telecom: TS Equipment | Upshur | Installing new DWDM Fiber Optic Equipment inside a concrete shelter to monitor communications throughout the AEP Telecommunications Network | 2024-08-19 | 2024-11-30 |  |  | 1156928 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station property
TA-2020103 T10611469 (A20103114) | Perdue 69/138-kV Station: TS Shelter | Upshur | Installing a concrete shelter, fencing, generator, propane tank grounding wire, underground conduit and 200AMP distribution service to operate new DWDM fiber optic equipment | 2024-08-19 | 2024-11-30 |  |  | 1129805 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station property
TA-2020103 T10611480 (A20103115) | Perdue 69/138-kV Station: TS Fiber Cable Extension | Upshur | Installing underground conduit and wire from the existing station to the new DWDM to allow for communications between the two facilities | 2024-08-19 | 2024-11-30 |  |  | 334590 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station property