## MonthlyReportForm-AEPTX Central
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
T10713945 (A19045053) (A19045054) | Pt. Comfort - Carancahua 69-kV Rebuild | Jackson | Rebuild, reconductor and relocate a 1.00-mile segment of the existing Pt. Comfort to Carancahua 69-kV transmission line that were not included in prior rebuild work of this transmission line in prior years. Constructed to 138-kV standards but will continue to be operated at 69-kV | 2024-03-10 | 2024-04-10 |  |  | 3836799 |  |  | 0 | 69 |  | 1 | 795 KCM ACSS "Drake" | Steel Mono Pole | Centerline | 1 | 50 | 1 | 16 TAC 25.101 (c)(5)(E) | Landowner Consent Obtained.