## MonthlyReportForm-ETT
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
ETT-157a P18126001 P18126009 | McKenzie - Westside 138-kV: Rebuild | Corpus Christi/ Nueces | Rebuild and reconductor the McKenzie to West Side 138-kV transmission line from the Westside Switch Station to structure 5/9. | 2021-10-04 | 2022-12-31 |  |  | 19805943 |  |  | 98 | 138 |  | 10.72 | 795 KCM ACSS "Drake" | Steel Monopole | Various | 10.72 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
ETT-157 P18126010 | McKenzie - Westside 138-kV: Fiber Replacement | Corpus Christi/ Nueces | Replace the fiber on the McKenzie Rd. Substation to Westside Switch Station 138-kV transmission line. | 2021-10-04 | 2023-05-01 |  |  | 1763171 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3)
ETT-176 P21200002 P21200001 | Nebula 345-kV Station | Scurry | Construct a new three (3) breaker ring, 345-kV Station. Install three (3) 345-kV, 5000A, 63kA breakers. Install DICM, RTU, SSO Relays, and EPS Meter. Install telecom equipment and terminate fiber. ONCOR – To update relay settings at Dermott. Update relaying and protection at Figaro. | 2022-01-10 | 2022-11-27 | 2022-10-27 |  | 15903000 |  |  | 99 |  | 345 | [7 empty] | 16 TAC 25.83(a)(3) | Construction Right-of-Entry obtained
ETT-176 P21200003 P21200004 P21200005 | Dermott - Figaro 345-kV T-Line: Cut-In | Scurry | Terminate the existing Dermott to Figaro 345-kV transmission line into new Nebula 345-kV Station. | 2022-01-10 | 2022-11-27 | 2022-10-27 |  | 1559400 |  |  | 99 | 345 |  | 0.05 | 1590 ACSR Bundled "Lapwing" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property Construction Right-of-Entry obtained for station property
ETT-176 P21200006 P21200007 P21200008 | Nebula - Andromenda 345-kV T-Line | Scurry | Construct a 1.70 mile 345-kV transmission line from Nebula 345-kV Station to Andromeda Solar Point of Interconnect (POI). | 2022-01-10 | 2022-11-27 | 2023-04-29 |  | 3852500 |  |  | 99 |  | 345 | 1.7 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  | 150 | 1.7 | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
ETT-178 P21208002 P21208003 P21208004 | Bakersfield - Hydra BESS 345-kV T-Line | Pecos | Construct a 0.10 mile 345-kV transmission line from Bakersfield 345-kV Station to Hydra BESS Point of Interconnect (POI) | 2022-02-24 | 2023-10-16 |  |  | 1500000 |  |  | 95 |  | 345 | 0.1 | 2-795 KCM ACSS "Drake" | Steel Monopole |  |  | 150 | 0.1 | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
ETT-900 P17107021 | Vernon Plant 69-kV Tap | Vernon/Wilbarger | Replace Structure No. 48 and 49 for ETT along the AEP Texas Chillicothe to Vernon 69-kV transmission line. | 2022-02-28 | 2022-05-04 | 2022-10-28 |  | 461128 |  |  | 99 | 69 |  |  | 795 KCM ACSS "Drake" | Steel Monopole |  |  |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
ETT-901 A19057005 A19057006 A19057007 | Steamboat - Winters 69-kV T-Line | Taylor Winters/Runnels | Rebuild and reconductor the Steamboat to Winters 69-kV transmission line to 138-kV standards. Will continue to operate at 69 kV. | 2022-02-03 | 2022-06-02 | 2022-05-31 |  | 8606468 |  |  | 99 | 69 |  | 9.86 | 795 KCM ACSR "Drake" | Steel Mono Pole | Various | 9.86 |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners noticed
ETT-900 ET1406401 ET1406402 | Champlin - Weil Tract 138-kV T-Line | Nueces | Reterminate the Champlin to Weil Tract 138-kV capable transmission line into the Champlin 138-kV Substation. Continue to operate at 69 kV. | 2022-10-03 | 2022-11-01 | 2022-12-12 |  | 927749.09 |  |  | 99 | 69 |  | 0.05 | 795 KCM ACSS "Drake" | Steel Monopole | 50' | 0.04 | 50' | 0.05 | 16 TAC 25.101 (c)(5)(A) | Landowner consent obtained
ETT-900 P16067002 P16067010 | Champlin - Weil Tract 138-kV T-Line | Nueces | Rebuild and reconductor a 0.41 mile segment of the existing Champlin to Weil Tract 138-kV capable transmission line to double-circuit capability. Continue to operate at 69 kV. | 2022-10-03 | 2022-11-01 | 2022-11-22 |  | 1694838.6 |  |  | 99 | 69 |  | 0.41 | 795 KCM ACSS "Drake" | Steel Monopole | 50' | 0.41 | 50 | 0.41 | 16 TAC 25.101 (c)(5)(B) | Landowner consent obtained
ETT-177 P21242002 P21242001 P21242009 | Inertia Wind Interconnection: Pendulo 345-kV Substation | Haskell | Construct a new three (3) breaker ring, 345-kV Station. Install three (3) 345-kV, 5000 A, 63 kA breakers Install DICM, RTU, SSO Relays, and EPS Meter. Install telecom equipment and terminate fiber. Update relaying and protection at remote ends. Install EPS Metering at Generator Substation. | 2022-05-02 | 2022-11-18 | 2022-11-12 |  | 12500000 |  |  | 99 |  | 345 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
ETT-177 P21242003 P21242004 P21242005 | Inertia Wind Interconnection: ClearCrossing - Smoky Hill 345-kV T-Line Cut-In | Haskell | Terminate the existing Clear Crossing to Smoky Hill 345-kV transmission line into new Pendulo 345-kV Substation. | 2022-05-02 | 2022-11-18 | 2022-11-12 |  | 4500000 |  |  | 99 | 345 |  | 0.75 | 2x1590 ACSR Bundled "Lapwing" | Steel Mono Pole |  |  | 150 | 0.75 | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
ETT-177 P21242006 P21242007 P21242008 | Inertia Wind Interconnection: Pendulo - Inertia 345-kV Gen Tie | Haskell | Construct a Dead End 345kV structure from Pendulo 345-kV Substation to Intertia Point of Interconnect (POI). | 2022-05-02 | 2022-11-18 | 2022-11-12 |  | 750000 |  |  | 99 |  | 345 | 0.01 | 2x795 KCM ACSR "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
ETT-180 P20132001 P20132002 | Sunray Solar Interconnect: Dry Frio 138-kV Substation | Uvalde | Construct a new three (3) breaker ring, 138-kV Substation. Install three (3) 138-kV, 3000 A, 40 kA breakers Install DICM and EPS Metering for Sunray Terminal. Update relaying and protection at remote ends. | 2022-06-05 | 2023-03-30 | 2023-05-02 |  | 8500000 |  |  | 99 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
ETT-180 P20142004 P20142003 P20142005 | Sunray Solar Interconnect: Razorback-Uvalde 138-kV T-Line | Uvalde | Terminate the existing Razorback to Uvalde 138-kV transmission line into new Dry Frio 138-kV Substation. | 2022-12-05 | 2023-03-30 | 2023-05-02 |  | 1000000 |  |  | 99 | 138 |  | 0.01 | 795 KCM ACSR "Drake" | Steel Monopole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
ETT-180 P21242006 P21242007 P21242008 | Sunray Solar Interconnect: Dry Frio - Sun Ray 138-kV Gen Tie | Uvalde | Construct a 0.01 mile 138-kV transmission line from Dry Frio 138-kV Substation to Sunray Solar Point of Interconnect (POI). | 2022-12-05 | 2023-03-30 |  |  | 500000 |  |  | 95 |  | 138 | 0.01 | 795 KCM ACSR "Drake" | Steel Monopole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
ETT-178 P21208005 | Hydra BESS 345-kV Substation | Pecos | Add WLS metering at Hydra BESS 345-kV Substation. | 2023-03-06 | 2023-10-16 |  |  | 700000 |  |  | 0 |  | 345 | [7 empty] | 16 TAC 25.83(a)(3) | Within Customer's Station Property
ETT-192 P21136001 | Wolf Tank Storage Interconnection: Lobo 138-kV Switch Station | Webb | Install two (2) 138-kV, 40kA, 3000 A breakers. Install EPS metering for the Wolf Tank Storage terminal. | 2022-09-15 | 2022-12-04 |  |  | 5000000 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-192 P21136003 P21136004 | Wolf Tank Storage Interconnection: Lobo - Wolf Tank Storage 138-kV Gen-Tie | Webb | Construct a 138-kV Dead End structure and TFC from Lobo 138-kV Switch Station to Wolf Tank Storage Point of Interconnect (POI). | 2022-09-15 | 2022-12-04 |  |  | 787000 |  |  | 0 |  | 138 | 0.1 | 795 KCM ACSR "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
ETT-192 P21136005 | Wolf Tank Storage Interconnection: Wolf Tank Storage 138-kV Substation | Webb | Install WSL meter for Collector station at Wolf Tank Storage 138-kV Substation. | 2022-09-15 | 2022-12-04 |  |  | 225000 |  |  | 0 |  | 138 | [7 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-800 P21120001 | Illinois #4 138-kV Station | Crockett | Add two 138-kV, 15.4 MVAR Capacitor Banks and two 138-kV, 3000A Circuit Breakers @ Illinois #4 Station | 2023-02-03 | 2023-04-10 | 2023-10-20 |  | 2365638 |  |  | 99 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-188 P21706001 | Tiempo 345-kV Station | Zapata | Construct a new three (3) breaker ring, 345-kV Station. Install three (3) 345-kV, 5000A, 63kA breakers. Install DICM, RTU, and EPS Meter. Install telecom equipment and terminate fiber. | 2022-08-04 | 2023-05-10 |  |  | 15900000 |  |  | 90 |  | 345 | [7 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-188 P21706006 | Tiempo 345-kV : Cut - In | Zapata | Construct (2) Dead End's & terminate the Cenizo - Del Sol 345-kV circuit into the new Tiempo 345-kV station. | 2022-11-15 | 2023-05-10 |  |  | 2400000 |  |  | 90 | 345 |  | 0.01 | 1590 ACSR Bundled "Lapwing" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
ETT-188 P21706003 | Tiempo 345-kV: Re-configure Reloj Del Sol 345-kV T-Line | Zapata | Re-configure the Reloj Del Sol generation 345-kV transmission line into the new 345-kV Tiempo Station. | 2022-08-04 | 2023-05-10 |  |  | 1500000 |  |  | 90 | 345 |  | 0.01 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
ETT-800 A19031008 | Illinois #4 69-kV Substation | Crockett | Replace relays at Illinois #4 69-kV substation. | 2025-01-03 | 2025-05-31 |  |  | 552616 |  |  | 0 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Existing Station Property
ETT-200 P21610001 P21610002 | Salvare 345-kV Substation | Childress | Construct new Salvare 345-kV substation with three (3) 345 kV, 5000 A, 63 kA Breakers and disconnect switches designed as breaker and a half. Install PQ meter. Install Telecom equipment and terminate fiber. Update Relaying and Protection | 2022-08-04 | 2023-03-31 | 2023-03-08 |  | 15025000 |  |  | 99 |  | 345 | [7 empty] | 16 TAC 25.83(a)(3) | Property Purchased
ETT-200 P21610006 | Jim Treece - Tesla 345-kV T-Line | Childress | Terminate the Jim Treece to Tesla 345-kV transmission line into the new Salvare 345-kV Substation; double circuit capable | 2022-08-04 | 2023-03-31 | 2023-03-08 |  | 1800000 |  |  | 99 | 345 |  | 0.1 | 795 KCM ACSR "Drake" | Steel Deadend Structure |  |  | 100 | 0.1 | 16 TAC 25.101 (c)(5)(A) | Landowner consent obtained
ETT-200 P21610007 | Jim Treece - Tesla 345-kV T-Line: TFC | Childress | Install OPGW Fiber | 2022-08-04 | 2023-03-31 | 2023-03-08 |  | 400000 |  |  | 99 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
ETT-200 P21610008 | Tesla 345-kV Station: Remote End Work & TFC | Childress | Upgrade remote end relay panels at Tesla 345-kV Station | 2022-08-04 | 2023-03-31 | 2023-03-08 |  | 500000 |  |  | 99 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
ETT-200 P21610009 | Jim Treece 345-kV Station: Remote End Work & TFC | Childress | Upgrade remote end relay panels at Jim Treece 345-kV Station | 2022-08-04 | 2023-03-31 | 2023-03-08 |  | 500000 |  |  | 99 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within station property
ETT-196 P22009001 | Redonda Solar Interconnection: Tiempo 345-kV Station - Install Terminal | Zapata | Construct a new 345-kV terminal for Redonda Solar by installing a 345-kV, 4000A, 50kA breaker and disconnect switches. | 2022-09-04 | 2023-05-10 |  |  | 5500000 |  |  | 98 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-196 P22009003 P22009004 | Redonda Solar Interconnection: Tiempo - Redonda 345-kV Gen-Tie | Zapata | Construct a 345-kV Dead End structure and TFC from Tiempo 345-kV Station to Redonda Solar Point of Interconnect (POI). | 2022-09-04 | 2023-05-10 |  |  | 1500000 |  |  | 95 | 345 |  | 0.01 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
ETT-800 P21120002 | Ft. Lancaster-Hamilton 138-kV T-Line: TLE | Crockett | Replace Structure 145 along the Ft. Lancaster-Hamilton 138-kV transmission line, restring conductor from Structure 145-144, restring conductor to station A-Frame. | 2023-03-06 | 2023-03-17 | 2023-10-05 |  | 648847 |  |  | 99 | 138 |  | 0.01 | 795 KCM ACSS | Steel Mono Pole |  |  |  |  | 16 TAC 25.83(a)(3) | Within Station Property
ETT-183 P19271005 | Clear Crossing 345-kV Station: Install Terminal | Haskell | Expand 345-kV bus by installing one (1) rung. Install two (2) 345-kV breakers, 5000A, 63kV with pre-insertion resistors. Install Switches. | 2022-09-06 | 2022-12-20 |  |  | 5300000 |  |  | 95 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-183 P19271001 P19271002 | Clear Crossing - HODL Ranch II 345-kV T-Line | Haskell | Construct a 345-kV Dead End structure and TFC from Clear Crossing 345-kV Station to the HODL Ranch II Point of Interconnect (POI). | 2022-09-06 | 2022-12-20 |  |  | 3001000 |  |  | 80 |  | 345 | 0.7 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
ETT-184 P21703002 P21703003 | LRGV System Enhancement Project: Add 2nd Circuit to the Lobo to Fowlerton 345-kV transmission line. | Webb, LaSalle, McMullen | Install the second circuit along the Lobo to Fowlerton 345-kV transmission line and add TFC. | 2023-01-04 | 2023-11-01 |  |  | 56586303 |  |  | 95 | 345 |  | 68.8 | 2-954 ACSR Cardinal | Steel Mono Pole | 150 | 68.8 |  |  | 16 TAC 25.83(a)(3) | Project No. 52682 Order Adding Second Circuit
ETT-184 P21703005 P21703006 | LRGV System Enhancement Project: Add 2nd Circuit to the Cenizo to Lobo 345-kV transmission line. | Webb | Install the second circuit along the Cenizo to Lobo 345-kV transmission line and add TFC. | 2022-12-12 | 2023-11-01 | 2023-12-13 |  | 4956928 |  |  | 99 | 345 |  | 26.6 | 2-954 ACSR Cardinal | Steel Mono Pole | 150 | 26.6 |  |  | 16 TAC 25.83(a)(3) | Project No. 52682 Order Adding Second Circuit
ETT-162 P19067002 P19067003 P19067004 | Misae II Solar Interconnection: Tesla - Fagus 345-kV T-Line | Childress | Construct approximately three (3) miles of new 345-kV transmission line from Tesla 345-kV Station to Misae Solar Park II Fagus 345-kV POI. Install TFC. | 2022-10-03 | 2023-05-15 | 2023-04-13 | 7671910 | 9400000 |  |  | 99 |  | 345 | 2.82 | 954 KCM ACSR "Cardinal" | Steel Mono Pole |  |  | 150 | 2.82 | 50016 | PUC Docket 50016 Approved on 12/19/2019
ETT-162 P19067005 | Misae II Solar Interconnection: Tesla 345kV Substation Expansion | Childress | Tesla 345 kV Station - Add 2 new 5000 A, 63 kA, 345 kV breakers with pre-insertion resistors. Install all switches. Add EPS Metering and SSO and Line Relay to accommodate new interconnection. | 2022-10-03 | 2023-05-15 | 2023-04-06 | 6125807 | 8600000 |  |  | 99 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | PUC Docket 50016 Approved on 12/19/2019 Within Station Property
ETT-166 P16067004 P16067008 P16067015 | Valero East - Valero West 69-kV T-Line | Nueces | Rebuild and reconductor the existing Valero East to Valero West 69-kV transmission line with double-circuit capable structures and constructed to 138-kV standards. Continue to operate at 69 kV. | 2022-11-01 | 2023-01-23 | 2023-04-05 |  | 1313589 |  |  | 99 | 69 |  | 0.15 | 795 KCM ACSS "Drake" | Steel Mono Pole | 75 | 0.15 | 100 | 0.15 | 16 TAC 25.101 (c)(5)(B) | Landowner Consent Obtained
ETT-194 A22007004 | Kirchoff 345-kV Station: Polymer MOV Replacement | Fisher | Replace ceramic MOV bank with Polymer bank. | 2022-11-07 | 2022-11-11 |  |  | 3154014 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-194 A22007003 | Edison 345-kV Station: Polymer MOV Replacement | Kimble | Replace ceramic MOV bank with Polymer bank. | 2022-11-14 | 2022-11-18 |  |  | 3079174 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-194 A22007006 | Oerstead 345-kV Station: Polymer MOV Replacement | Sutton | Replace ceramic MOV bank with Polymer bank. | 2022-11-28 | 2022-11-30 |  |  | 1708300 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-194 A22007001 | Cenizo 345-kV Station: Polymer MOV Replacement | Webb | Replace ceramic MOV bank with Polymer bank. | 2022-12-05 | 2022-12-07 |  |  | 763000 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-187 P21704001 | Lobo 345-kV Station: Construct Two Terminals | Webb | Construct new 345-kV terminals at Lobo 345-kV Station for the Fowlerton and Cenizo second circuits by completing the existing unused 345-kV rung and installing three 345-kV circuit breakers. | 2023-01-15 | 2023-07-31 |  |  | 10601878 |  |  | 87 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-187 P21704002 | Cenizo 345-kV Station: Construct One Terminal | Webb | Construct one 345-kV terminal at Cenizo for the Lobo second circuit into Cenizo by installing one 345 kV circuit breaker. Reterminate Reloj Del Sol. | 2023-01-15 | 2023-07-31 | 2023-10-13 |  | 5156999 |  |  | 99 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-187 P21704003 | Del Sol 345-kV Station: Upgrade Line Settings | Hidalgo | Update protection systems as needed. Remove metering for Mig Howard. | 2023-01-15 | 2023-10-31 | 2023-11-16 |  | 534639 |  |  | 99 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-187 P21704004 | Pomelo 345-kV Station: Construct Two Terminals | Hidalgo | Construct two 345-kV terminals at Pomelo 345-kV Station for the Pronto line and the North Edinburg second circuit by installing one 345-kV circuit breaker. Update protection systems as needed. | 2023-01-15 | 2023-07-31 | 2023-12-07 |  | 5668867 |  |  | 99 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-194 A22007002 | Del Sol 345-kV Station: Polymer MOV Replacement | Starr | Replace ceramic MOV bank with Polymer bank. | 2022-12-07 | 2022-12-09 |  |  | 763000 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-194 A22007005 | Gauss 345-kV Station: Polymer MOV Replacement | Knox | Replace ceramic MOV bank with Polymer bank. | 2022-12-12 | 2022-12-16 |  |  | 2425790 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-202 A22062004 | Oerstead 345-kV Station: ETT SVC/Series Capacitor Control Replacement | Sutton | Replace GE Series Capacitor PLC | 2022-10-19 | 2023-10-31 |  |  | 687525 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-199 P22013001 | Guajillo Energy Storage Interconnection | Webb | Install metering at the generator's Corazon Solar 345-kV Substation in support of a 200MW energy storage facility | 2023-01-02 | 2024-03-31 |  |  | 578559 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-194 A22039001 | N. Edinburg 345-kV Station: Polymer MOV Replacement | Hidalgo | Replace ceramic MOV bank with Polymer bank. | 2022-12-19 | 2022-12-20 |  |  | 2428944 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-190 P21709002 | Pronto 345-kV Station: Construct New Station | Starr | Construct a new three (3) breaker ring, 345-kV Station. Install three (3) 345-kV, 5000A, 63kA breakers. Install DICM, RTU, and EPS Meter. Install telecom equipment and terminate fiber. | 2023-01-09 | 2023-11-15 |  |  | 16800000 |  |  | 90 |  | 345 | [7 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-190 P21709004 P21709005 | Pronto 345-kV Station: Del Sol to Pomelo Cut-In | Starr | Construct (2) Dead End's & terminate the Del Sol to Pomelo 345-kV transmission line into the new Pronto 345-kV Station. | 2023-01-09 | 2023-11-15 |  |  | 2200000 |  |  | 95 | 345 |  | 0.01 | 1590 ACSR Bundled "Lapwing" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
ETT-190 P21709007 P21709008 | Pronto 345-kV Station: Re-configure the Mig Howard Windfarm Line | Starr | Provide a Dead End POI for terminating the Mig Howard Generation 345-kV Tie Line into Pronto 345-kV Station. | 2023-01-09 | 2023-11-15 |  |  | 1500000 |  |  | 95 | 345 |  | 0.01 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
ETT-800 A22800002 | Laredo VFT 138-kV | Webb | Laredo VFT Collector rings/GE - Purchase insulators | 2023-03-01 | 2023-04-14 |  |  | 327436 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-800 P22079001 | Riley - Tesla 345-kV T-Line | Wilbarger, Hardeman, Childress | Repairing Galloping issues across the transmission line. | 2023-05-01 | 2023-10-31 |  |  | 289657 |  |  | 0 | 345 | [8 empty] | 16 TAC 25.83(a)(3)
ETT-185 P21702008 P21702009 P21702010 | LRGV System Enhancement Project: Add 2nd Circuit to the Rapido to Tiempo 345-kV transmission line. | Webb,Zapata | Install the second circuit along the Rapido to Tiempo 345-kV transmission line and add TFC. | 2023-04-17 | 2023-12-31 | 2023-11-11 |  | 47855873 |  |  | 99 | 345 |  | 40.5 | 2-954 ACSR Cardinal | Steel Mono Pole | 150 | 40.5 |  |  | 16 TAC 25.83(a)(3) | Project No. 52682 Order Adding Second Circuit
ETT-185 P21702005 P21702006 | LRGV System Enhancement Project: Add 2nd Circuit to the Pomelo to Pronto Line transmission line | Starr | Install the second circuit along the Pomelo to Pronto 345-kV transmission line and add TFC | 2023-08-07 | 2023-12-31 | 2023-11-16 |  | 13902491 |  |  | 99 | 345 |  | 11.48 | 2-954 ACSR Cardinal | Steel Mono Pole | 150 | 11.48 |  |  | 16 TAC 25.83(a)(3) | Project No. 52682 Order Adding Second Circuit
ETT-185 P21702002 P21702003 | LRGV System Enhancement Project: Add 2nd Circuit to the N. Edinburg to Pomelo transmission line | Starr, Hidalgo | Install the second circuit along the N. Edinburg to Pomelo 345-kV transmission line and add TFC | 2023-07-31 | 2023-12-31 | 2023-12-19 |  | 36572563 |  |  | 99 | 345 |  | 26.54 | 2-954 ACSR Cardinal | Steel Mono Pole | 150 | 26.54 |  |  | 16 TAC 25.83(a)(3) | Project No. 52682 Order Adding Second Circuit
ETT-197 P22016001 | Anemoi Storage Interconnection: Install New Terminal | Hidalgo | Construct a new 345 kV terminal for Anemoi. Install a 345 kV, 5000 A, 63 kA breaker and disconnect switches. Install a 345-kV, 3000A line MOAB on the Anemoi terminal. nstall jumpers to new line terminal. Install SSO relaying and EPS metering for the new Anemoi line. Terminate dual fiber. | 2023-08-15 | 2023-12-13 | 2024-02-13 |  | 5577432 |  |  | 99 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-197 P22016002 | Anemoi Storage Interconnection: Install WLS Metering | Hidalgo | Install Wholesale Storage Load (WSL) Metering with all associated equipment at customer’s Anemoi Substation. | 2023-08-15 | 2023-12-13 |  |  | 653104 |  |  | 95 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Customer's Station Property
ETT-197 P22016004 P22016005 | Anemoi Storage Interconnection: Pomelo - Anemoi 345-kV T-Line | Hidalgo | Construct a new 0.05 mile 345-kV transmission line between the ETT Pomelo Station and the customer's point of interconnect (POI) to Anemoi Substation. Install dual fiber. | 2023-08-15 | 2023-12-13 |  |  | 1891041 |  |  | 95 |  | 345 | 0.05 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
ETT-201 P19249002 P19249001 | Montgomery Ranch Interconnection: Penumbra 345-kV Station Build | Foard | Construct a new (3) breader ring, 345kV Station called Penumbra. Install three (3) 345kV, 5000 A, 63 kV Breackers with associated equipment, install SSO Relay and EPS meter, install telecom equipment and terminate fiber, and update relaying and protection at remote ends. | 2023-08-21 | 2024-03-29 |  |  | 18501193.69 |  |  | 43 |  | 345 | [7 empty] | 16 TAC 25.83(a)(3) | Construction Right-of-Entry obtained
ETT-201 P19249003 P19249004 P19249005 | Montgomery Ranch Interconnection: Avogadro-Edith Clarke 345-kV Cut-In | Foard | Terminate the existing Avogrado to Edith Clarke 345-kV transmission line into new Penumbra 345-kV Station. | 2023-08-21 | 2024-03-29 |  |  | 6622918.19 |  |  | 33 | 345 |  | 0.44 | 1590 ACSS Bundled "Falcon" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property Construction Right-of-Entry obtained for station property
ETT-201 P19249006 P19249007 | Montgomery Ranch Interconnection: Penumbra-Montgomery Ranch 345-kV POI | Foard | Construct a one span of 345-kV transmission line from Penumbra 345-kV Station to Montgomery Ranch Point of Interconnect (POI). | 2024-08-21 | 2024-03-29 |  |  | 2014326.62 |  |  | 40 |  | 345 | 0.1 | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Landowner Consent Obtained
ETT-189 P21707002 P21707001 | Rapido 345-kV Station: Construct New Station | Zapata | Construct a new three (3) breaker ring, 345-kV Station. Install three (3) 345-kV, 5000A, 63kA breakers. Install DICM, RTU, and EPS Meter. Install telecom equipment and terminate fiber. | 2023-07-15 | 2024-03-15 |  |  | 22500000 |  |  | 70 |  | 345 | [7 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-189 P21707004 P21707003 P21707005 | Rapido 345-kV Station: Del Sol to Tiempo Cut-In | Zapata | Construct (2) Dead End's & terminate the Del Sol to Tiempo 345-kV transmission line into the new Rapido 345-kV Station. | 2023-07-15 | 2024-03-15 |  |  | 1800000 |  |  | 50 | 345 |  | 0.01 | 2 X 954 KCM ACSR "Cardinal" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
ETT-189 P21707007 P21707006 P21707008 | Rapido 345-kV Station: Rapido to Cabezon 345-kV Line | Zapata | Reterminate Del Sol to Cabezon 345-kV transmission line into new Rapido 345-kV Station. | 2023-07-15 | 2024-03-15 |  |  | 2800000 |  |  | 30 |  | 345 | 0.3 | 2 X 954 KCM ACSR "Cardinal" | Steel Mono Pole |  |  | 150 | 0.3 | 16 TAC 25.101 (c)(5)(A) | Easement Obtained
ETT-186 P21701002 P21701003 | LRGV System Enhancement Project: Add 2nd Circuit to the N. Edinburg to Palmito transmission line | Hidalgo | Install the second circuit along the N. Edinburg to Palmito 345-kV transmission line and add TFC | 2023-09-15 | 2024-05-28 |  |  | 92623166 |  |  | 32 | 345 |  | 47.93 | 2-954 ACSR Cardinal | Steel Mono Pole | 150 | 47.93 |  |  | 16 TAC 25.83(a)(3) | Project No. 52682 Order Adding Second Circuit
ETT-211 DR21X05D3 | Devine 69-kV Substation | Medina | Install two 3000A, 40kA circuit switchers rated for 138-kV. Install CT/VT Metering structure to Devine - Medina Electric Tie. | 2023-09-05 | 2024-03-29 |  |  | 1549894 |  |  | 50 | 69 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-210 P20087002 P20087005 P20087001 | Champlin-Weil Tract 138-kV Line Rebuild | Nueces | Rebuild and reconductor a 0.85-mile section of the Champlin to Weil Tract 138-kV transmission line. | 2023-10-16 | 2023-12-15 |  |  | 2219161 |  |  | 75 | 138 |  | 0.88 | 795 KCM ACSS | Steel Mono Pole | 50 | 0.88 |  |  | 16 TAC 25.101 (c)(5)(B) | Utilizing existing easements Landowner Noticed
ETT-223 ETT-800 A22800016 | Magruder 138/68-kV Substation: Auto Replacement | Victoria/Victoria | Replace failed 138/69-kV Auto with an ETT capital spare. Make necessary repairs to replacement. Perform necessary P&C and station work to get auto operating. | 2024-02-20 | 2024-04-22 |  |  | 2199042 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-800 P21246002 | Hamilton Rd. 138-kV Substation | Del Rio/Val Verde | Upgrade Relays between Hamilton Rd and LCRA's Pinto Creek stations so they can communicate following the install of new CB's at Pinto Creek. | 2023-11-30 | 2023-12-31 |  |  | 266069 |  |  | 0 | 138 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-800 A22800006 | Ajo 345-kV Station | Kenedy | Replace 345-kV Reactor CB 555 at the Ajo 345-kV Station. | 2024-02-06 | 2024-03-25 |  |  | 966713 |  |  | 5 | 345 | [8 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-198 P22023001 | Outpost Solar Interconnection: Avanzada 345-kV Station Build | Webb | Construct a 345 kV, 4000 A, 3-breaker ring bus expandable to breaker-and-a-half, Install (3) 345 kV, 4000 A, 50 kA breakers, Install DICM, RTU, and EPS metering for the outpost solar Terminal, Update Remote end relay settings, terminate fiber, and add SSO relaying | 2024-02-01 | 2024-10-30 |  |  | 20500000 |  |  | 0 |  | 345 | [7 empty] | 16 TAC 25.83(a)(3) | Within Station Property
ETT-198 P22023003 P22023004 P22023005 | Outpost Solar Interconnection: Avanzada 345-kV Lobo to Fowlerton Cut-In | Webb | Construct (2) Dead End's & terminate the Lobo to Fowlerton 345-kV transmission line into the new Avanzada 345-kV Station. | 2024-02-01 | 2024-10-30 |  |  | 1000000 |  |  | 0 | 345 |  | 0.01 | 2 X 954 KCM ACSR "Cardinal" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
ETT-198 P22023006 P22023007 | Outpost Solar Interconnection: Avanzada 345-kV: Avanzada to Outpost Solar POI | Webb | Construct a one span of 345-kV transmission line from Avanzada 345-kV Station to Outpost Solar Point of Interconnect (POI). | 2024-02-01 | 2024-10-30 |  |  | 1200000 |  |  | 0 |  | 345 | 0.01 | 2 X 954 KCM ACSR "Cardinal" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(A) | Within Station Property
ETT - 206 P20838001 P20838002 P20838003 P20838004 | Del Sol - Frontera 345-kV T-Line | Hidalgo, Starr | Construct a new 345-kV transmission line from the AEP Texas Point of Interconnect to Del Sol 345-kV Station. | 2025-01-01 | 2026-05-31 |  | 62277740 |  |  |  | 0 |  | 345 | 18.1 | 3 x 954 KCM ACSR "Cardinal" | BOLD Lattice |  |  | 150 | 18.1 | 55001 | PUC Docket 55001 Approved 09/28/2023
ETT - 206 P20838005 | Del Sol 345-kV Station | Starr | Convert Station to breaker and a half. Add all necessary breakers. Terminate lines to frontera. Terminate fiber. Update relaying and protection. | 2024-06-01 | 2026-05-31 |  | 27393158 |  |  |  | 0 | 345 | [8 empty] | 55001 | PUC Docket 55001 Approved 09/28/2023
ETT - 900 2019 A20144005 | Laredo VFT North - Lobo CKT #2 138-kV T-Line | Laredo/Webb | Replace and move Structure 5/4 east down the centerline to remove from TxDOT’s right of way. | 2024-03-04 | 2024-04-19 |  |  | 1021747 |  |  | 0 | 138 |  |  | 1020 KCM AAAC "Drake" | Steel Mono Pole | Centerline |  |  |  | 16 TAC 25.101 (c)(5)(F) | Reimburseable Project - CIAC Acquired Landowners Noticed.