## 2023 CEHE Capital Variances
CEHE Capital Plan
| Year-to-Date |  |  | % |  | Variance Explanations
| Plan | Actual | Variance | Over/(Under) | Ref
[6 empty] | {a} | Increases spend to meet customer load demand.
Interconnections | 96.8881 | 96.8622 | -0.025817 | -0.02665%
Load Growth | 507.6609 | 742.8156 | 235.1547 | 31.66% | {a} | {b} | Increased spend due to storm/tornado/heat response
Public Improvements | 29.2597 | 32.5307 | 3.2711 | 10.06%
[6 empty] | {c} | Construction overhead was 21% over 2023 plan due to the capitalization of temporary poles not included in plan.
System Improvements | 934.8967 | 783.0611 | -151.8356 | -19.39%
Restoration | 67.9921 | 137.1264 | 69.1343 | 50.42% | {b}
[6 empty] | {d} | Utility Operations was 31% under 2023 plan primarily due to Facilities related projects below plan, including: Santa Fe construction deferred $3.1M Cypress furniture replacement deferred $1.1M Harrisburg roof replacement deferred $1.6M Mag park roof replacement cost less than planned $1.1M
Fleet | 25.3627 | 24.6162 | -0.74649 | -3.033%
Construction Overhead | 205.2079 | 258.7711 | 53.5631 | 20.7% | {c}
Utility Operations | 26.6049 | 20.2795 | -6.3254 | -31.19% | {d}
IT | 63.1104 | 48.0659 | -15.0444 | -31.3% | {e}
General Equipment | 96.0491 | 93.088 | -2.9611 | -3.181% |  | {e} | IT was 31% under 2023 plan due to the following: Change in allocation of EIP costs made up almost half of the $15M year-end variance. Less than planned costs associated with the following activities. These are the top contributors: Texas Set Fusion Resiliency Network Refresh BPC Planning & Forecasting
Back Up Control Center | 0 | 0.046388 | 0.046388 | 0%
Plan Top-Side | -85.0574 | 0 | 85.0574
Total TDU Capital | 1967.975 | 2237.2631 | 269.2881
AMS | 1.7303 | 2.0674 | 0.33702 | 16.3%
Advanced Digital Systems | 2.5 | 0.92041 | -1.5796 | -171.6% | {f}
[6 empty] | {f} | Advanced Digital Systems was 172% under plan primarily as a result of a shift in effort during Q4 2023 from CEHE to IE for the ADMS System consolidation project. In addition, infrastructure costs planned for 2023 were deferred until Q1 2024 due to a supply change delay.
Total Smart Grid Capital | 4.2303 | 2.9878 | -1.2426
Total CEHE Capital | 1972.2054 | 2240.2509 | 268.0455

## Sheet2
CEHE Capital Plan
|  | Year-to-Date |  |  | %
|  | Plan | Actual | Variance | Over/(Under)
Interconnections | HVO | 96.8881 | 96.8622 | -0.025817 | -0.02665%
Load Growth |  | 507.6609 | 742.8769 | 235.2159 | 31.66%
| HVO | 224.8387 | 328.1122 | 103.2736 | 31.48%
| DO | 282.8223 | 414.7646 | 131.9424 | 31.81%
Public Improvements |  | 29.2597 | 32.5307 | 3.2711 | 10.06%
| HVO | 2.1779 | 6.1357 | 3.9578 | 64.5%
| DO | 27.0818 | 26.395 | -0.68672 | -2.602%
System Improvements |  | 934.8967 | 783.0611 | -151.8356 | -19.39%
| HVO | 569.3682 | 399.1629 | -170.2053 | -42.64%
| DO | 365.5285 | 383.8982 | 18.3697 | 4.785%
Restoration |  | 67.9921 | 137.1264 | 69.1343 | 50.42%
| HVO | 2.4423 | 6.5145 | 4.0723 | 62.51%
| DO | 65.5498 | 130.6118 | 65.062 | 49.81%
Fleet | Fleet | 25.3627 | 24.6162 | -0.74649 | -3.033%
Construction Overhead |  | 205.2079 | 258.7711 | 53.5631 | 20.7%
| HVO | 73.0114 | 111.5373 | 38.5259 | 34.54%
| DO | 92.9503 | 101.5306 | 8.5804 | 8.451%
| TELECOM | 6.4606 | 6.458 | -0.0026102 | -0.04042%
| ADS | 3.1404 | 2.5041 | -0.63629 | -25.41%
| GTIS | 9.0748 | 7.435 | -1.6398 | -22.05%
| Fleet | 0 | 0.14107 | 0.14107 | 100%
| Other | 20.5705 | 29.165 | 8.5945 | 29.47%
Utility Operations |  | 26.6049 | 20.2795 | -6.3254 | -31.19%
| Facilities | 24.3562 | 17.3624 | -6.9938 | -40.28%
| GIS | 2.2487 | 2.9171 | 0.66838 | 22.91%
IT | TO | 63.1104 | 48.0659 | -15.0444 | -31.3%
General Equipment |  | 96.0491 | 93.088 | -2.9611 | -3.181%
| HVO | 4.152 | 6.4332 | 2.2812 | 35.46%
| DO | 30.0435 | 29.0908 | -0.95266 | -3.275%
| Fleet | 3.5559 | 2.5345 | -1.0214 | -40.3%
| TO | 3.2271 | 6.8738 | 3.6467 | 53.05%
| TELECOM | 39.1555 | 33.7296 | -5.4259 | -16.09%
| ADS | 3.0233 | 4.7382 | 1.7148 | 36.19%
| MKT | 3.8463 | 2.5087 | -1.3376 | -53.32%
| ENG | 3.6432 | 1.3743 | -2.2689 | -165.1%
| GTIS | 0 | 2.2725 | 2.2725 | 100%
| Other | 5.4022 | 3.5323 | -1.8699 | -52.94%
Back Up Control Center | ADS | 0 | 0.046388 | 0.046388 | 100%
AOC IT | TO | 0 | 0 | 0 | #DIV/0!
#DIV/0!
Plan Top-Side | Other | -85.0574 | 0 | 85.0574
Total TDU Capital |  | 1967.975 | 2237.278 | 269.303
AMS | ADS | 1.7303 | 2.0674 | 0.33702 | 16.3%
Advanced Digital Systems | ADS | 2.5 | 0.92041 | -1.5796 | -171.6%
Total Smart Grid Capital |  | 4.2303 | 2.9878 | -1.2426 | -41.59%
Total CEHE Capital Excluding Freeport |  | 1972.2054 | 2240.2658 | 268.0604 | 11.97%
Freeport Area Upgrades | Freeport | 0 | -0.061231 | -0.061231 | 100%
Total CEHE Capital |  | 1972.2054 | 2240.2045 | 267.9991 | 11.96%
|  | Year-to-Date |  |  | %
|  | Plan | Actual | Variance | Over/(Under)
| HVO | 972.8784 | 954.7581 | -18.1203 | -1.898%
| DO | 863.9761 | 1086.2912 | 222.3151 | 20.47%
| GTIS | 9.0748 | 9.7076 | 0.63276 | 6.518%
| GIS | 2.2487 | 2.9171 | 0.66838 | 22.91%
| Fleet | 28.9186 | 27.2918 | -1.6268 | -5.961%
| Utility Operations | 24.3562 | 17.3624 | -6.9938 | -40.28%
| TO | 122.3477 | 105.4038 | -16.9439 | -16.08%
| MKT | 3.8463 | 2.5087 | -1.3376 | -53.32%
| ENG | 3.6432 | 1.3743 | -2.2689 | -165.1%
| Other | 25.9727 | 32.6972 | 6.7245 | 20.57%
| Topside | -85.0574 | 0 | 85.0574
|  | 1972.2054 | 2240.3121 | 268.1068
| Freeport | 0 | -0.061231 | -0.061231 | 100%