## Schedule M-3.1_PUC07 001-075
| This file starts with Schedule M-3.1 in columns A through L, | [10 empty] | This file starts with Schedule M-3.1 in columns A through L,
| displays the corresponding PUC RFI set 07 question numbers | [10 empty] | displays the corresponding PUC RFI set 07 question numbers
| in columns O through Q, and adds responses to | [10 empty] | in columns O through Q, and adds responses to
| the RFIs for parts b etc starting in column S. | [10 empty] | the RFIs for parts b etc starting in column S.
-1 | -2 | -3 | -4 | -5 | -6 | -7 | -8 | -9 | -10 | -11 | -12 | -13
Projects Submitted to ERCOT RPG | WBS# | (a) Project Name (with CCN Docket No., if Any) | (b) Estimated Costs at the Time of ERCOT Review (if Any) | (c) Estimated Costs in First MCPR Entry* | (d) First MCPR Where Project Appeared | Final Updated Costs in MCPR Entry | MCPR Where Cost Updated | (e) Final Total Project Costs | (f) Last MCPR Where Project Appeared | (g) Percent difference between (c) and (e) [% diff btwn inital & final estimate] | Percent difference between Column G and (e) [% diff btwn actual and final estimate] | Variance Explanation | PUC RFI 7 |  | b. The contingency, if any, built into the initial project estimate. | c. Any impact the Covid-19 pandemic had on the project. | c./d. Any impact Winter Storm Uri had on the project. | e. Regarding the explanation for the variance, why would outages keep the contractors from working? | f. Regarding the explanation for the variance, please explain the easement issue. Was CNP expecting to have access to the easement and the landowner changed their mind for some reason? | c./d./e. Regarding the explanation for the variance, please detail how the project was expanded as a result of feedback from the construction team. | e. Regarding the explanation for the variance, please explain how the delays and permitting issues led to a cost increase of 63%. | c./d./e. Regarding the explanation for the variance, please provide any other solutions CenterPoint Houston considered when adjusting to these unexpected issues and why these solutions were selected. | d. Regarding the explanation for the variance, please explain why the Covid-19 Pandemic required the project to be delayed for a year. | c./e./f./g. Regarding the explanation for the variance, what was the cost of the mats and was that less than the cost of delaying the project due to weather? | e. Regarding the explanation for the variance, please explain why the scope of the project was increased. | d. Regarding the explanation for the variance, please describe the reliability considerations that required the increased labor costs. | e. Regarding the explanation for the variance, please further explain the reasons for the easement issues with Exxon and what the issues were that led to the lengthy negotiations. | f. Regarding the explanation for the variance, please explain the source of the unexpected outage constraints. | e. When did this project begin and end construction? | f. Regarding the explanation for the variance, what was the time period when these unexpected rains occurred? | d./f. Regarding the explanation for the variance, please provide the costs for the mats. | e. Regarding the explanation for the variance, please explain the need to repair the bypass. | c. Regarding the explanation for the variance, describe the issues with railroad access. What was the unrelated project? Why was this missed in the planning phase? | d. Regarding the explanation for the variance, please describe the circumstances of the shelter in place order | e. Regarding the explanation for the variance, please explain how the manufacturing delivery delays cause outage constraints. | d. Regarding the explanation for the variance, what was the total cost of the work the landowners required? Was the mistake in the RR permit the result of any paperwork CNP submitted? Were the DOW rules/Hoffman ROW access issues known at the time the estimate was made? | e. Regarding the explanation for the variance, how did the landowner cause delays in obtaining the railroad permit? What was the extent of that delay? | e. Regarding the explanation for the variance, why did the delays lead to increased equipment costs? What were the extent of those costs? | d. Regarding the explanation for the variance, why were more mats required than initially planned? | d. Regarding the explanation for the variance, what was the cost to do the necessary corrections to the raiser beams? | d. Regarding the explanation for the variance, what was the damage that required repair and replacement? | e. Regarding the explanation for the variance, why was the deadend material missing from one structure, and why were two deadend structures required to overcome this issue ? | e. Regarding the explanation for the variance, what were the extent of the pipeline company's requirements? | f. Regarding the explanation for the variance, what were the rest of the unexpected ROW issues? | e. Regarding the explanation for the variance, was the severe weather mentioned the same as the hurricane? What was the name of the hurricane? Were there any other ways the hurricane impacted this project? | e. Regarding the explanation for the variance, please explain the issues with caving and why they were unanticipated | d. Regarding the explanation for the variance, please elaborate on the issues with the trains and railways and why they impacted access to the project. | e. Regarding the explanation for the variance, was the temporary easement due to the bypass? | f. Regarding the explanation for the variance, what were the circumstances that required the project to be energized “on time?” | e. Regarding the explanation for the variance, was there a particular storm that was responsible for the flooding? | c. Regarding the explanation for the variance, was the severe weather a particular storm? | d. Regarding the explanation for the variance, please explain why the weights and class of the structures require an update to the cost. Was the weight greater than planned? | c. Regarding the explanation for the variance, please total the cost of the modifications requested by the pipeline company. | c. Regarding the explanation for the variance, please explain the reasons for the permit delays. | c. Regarding the explanation for the variance, what was the total cost of the corrections to the towers?
Freeport Area Master Plan | HLP/00/1115/TR/0005 | P1115 Bailey-Jones Creek: Docket# 48629 | $481,700,000-$695,200,000 (BJC) + $32,340,000 (BTG) | 497627696 | 2018-09-18 | 498255242 | 2021-01-01 | 550220832 | 2023-06-01 | 10.57% | 10.43% | Labor variance due to: (1) customers needing emergency outages, which lasted two days, prevented the contractor from working, and led to increased labor costs; (2) a landowner's refusing to release an easment to CNP, which required redesign of FAA lighting, use of additional matts, and new access road; and (3) high winds causing multiple installation and removal delays, resulting in increased labor and equipment rental costs. |  | 1 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | d. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | e. There were two instances where customer substations required emergency outages for maintenance that prevented the needed outage on 138kV Ln02_VL_CPR for contractors to safely work on the Freeport Area Master Plan construction. | f. CenterPoint’s original design called for an AC system for FAA lighting. DOW would not release an easement to build the distribution line for the FAA lighting. Due to this CenterPoint had to go with solar FAA lighting since that did not require the distribution line and easement. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/1115/TR/0005 | P1115.2 Jones Creek Loop |  |  | 2018-04-01 |  | 2018-06-01 |  | 2020-08-01
| HLP/00/1115/TR/0006 | P1115.64 Bailey Approach Spans |  |  | 2020-02-01 |  | 2020-05-01 |  | 2021-08-01
| HLP/00/1115/TR/0006 | P1115.65 COPPER-Velasco (Structure 19401) |  |  | 2020-02-01 |  | 2020-04-01 |  | 2021-09-01
| HLP/00/1115/TR/0007 | P1115.7 DOW345-Jones Creek |  |  | 2019-11-01 |  | 2020-03-01 |  | 2023-05-01
| HLP/00/1115/SB/0006 | PE210016 INSTALL (2) 345KV LINE POSITIONS |  |  | N/A |  | N/A |  | N/A
| HLP/00/1115/SB/0006 | PE210017 INSTALL (2) 345KV LINE POSITIONS |  |  | N/A |  | N/A |  | N/A
Southwyck - Algoa Corner Rebuild | HLP/00/1114/TR/0001 | P954.3 Southwyck Substation | 20080000 | 37339187.7912 | 2018-01-01 | 64275000 | 2018-01-01 | 49053008.17 | 2018-10-01 | 31.37% | -23.68% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect multiple fluctuations in estimates that could have a cumulative impact above 10% as well as to provide estimates for additional cost categories. Variance percentage of final total costs vs. final estimate filed in MCPR is -24%. |  | 2 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/1114/TR/0001 | P954.4 Southwyck-Algoa Corner (Southwyck-Structure #32235) |  |  | 2018-03-01 |  | 2018-05-01 |  | 2020-03-01
| HLP/00/1114/TR/0001 | P954.5 Southwyck-Algoa Corner (Structure #32236-Algoa Corner) |  |  | 2018-03-01 |  | 2018-05-01 |  | 2020-03-01
| HLP/00/1114/TR/0001 | P954.6 Southwyck-Algoa Corner (Structures #32235-32236) |  |  | 2018-04-01 |  | 2018-05-01 |  | 2020-03-01
| HLP/00/1114/TR/0001 | P954.7 Algoa Corner-Friendswood Corner Partial Rebuild and Partial Reconductor of 138 kV Ckt. 05B |  |  | 2018-12-01 |  | 2019-02-01 |  | 2020-05-01
Angleton - MONSAN Rebuild | HLP/00/1037/TR | P1037 Angleton-PETSON-MONSAN | 35300000 | 35333000 | 2018-04-01 | 32996000 | 2018-07-01 | 57519193.63 | 2021-05-01 | 62.79% | 74.32% | Labor costs were higher than the original estimate because of 13 unexpected rainout days which required multiple crew redployments. In addition, there were unanticpated delays in obtaining road permits from TxDOT. The County unexpectedly denied CenterPoint Houston's use of a county road, which required CenterPoint Houston to obtain a TxDOT permit and caused additional delays. As equipment had been rented for this project prior to the delays, each unexpected rainout day and the TxDot permit delay increased equipment rental costs. |  | 3 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | d. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | N/A | e. Delays increased the duration of equipment rental and crews allocated to the job, which increased costs. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Ft Bend - West Columbia Conversion | HLP/00/0997/TR/0001 | P997.1 Fort Bend-Rosenberg | 51700000 | 20682000 | 2019-07-01 | 22530000 | 2019-07-01 | 34938745 | 2021-06-01 | 68.93% | 55.08% |  |  | 4 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | d. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | N/A | N/A | e. The original scope called to replace the existing structures along the South Side of Old Needville – Fairchilds Road. During design, it was determined that Fort Bend County had a road widening project that would directly interfere with our current easement and force CenterPoint to relocate. CenterPoint made an agreement with Fort Bend County to relocate the line to the North Side of Old Needville – Fairchilds Road to prevent having to re do the work. Fort Bend County agreed that if they wanted to widen the road again before January 1, 2030, they would pay CenterPoint Houston to relocate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/0997/TR/0001 | P997.2 Rosenberg-Needville |  |  | 2018-11-01 |  | 2019-01-01 |  | 2023-09-01 |  |  | Labor costs and equipment rental costs were higher than estimated due to Fort Bend County’s unexpected decision to widen a road that the existing line paralleled, which required CenterPoint Houston to relocate a portion of the line from south side of the road to the north. This created a number of issues: • As the road widening decision was made after the rebuild had begun, approximately half of the newly installed wires needed to be removed and restrung. Increasing labor costs. • CenterPoint was forced to obtain new ROW on the north side of the road. As this was a rebuild, CenterPoint had not anticipated acquiring new ROW. • The newly affected landowners would not willingly sell the required ROW forcing CenterPoint Houston to use the Condemnation process, which is time consuming. Because the line could not be out of service for an extended period of time, CenterPoint Houston was required to build a temporary line on the south side of the road. Project costs were further increased when (1) Contractors discovered an unmarked underground pipeline, causing delays and requiring the relocation of three poles; (2) severe weather conditions that caused project delays and required the removal and reinstallation of mats twice; and (3) Updated load growth projections required the use of larger and more expensive conductor than initially anticipated. The conductor selected will also make future line rebuilds easier.
| HLP/00/0997/TR/0001 | P997.4 West Columbia Approach Span |  |  | 2018-11-01 |  | 2018-11-01 |  | 2021-05-01
| HLP/00/0997/TR/0001 | P997.5 Big Creek Loop |  |  | 2019-12-01 |  | 2019-12-01 |  | 2021-06-01
| HLP/00/0997/TR/0001 | P997.6 Needville Substation |  |  | 2020-04-01 |  | 2020-04-01 |  | 2020-12-01
Deepwater Auto | HLP/00/1408/TR/0002 | P1409.1 Deepwater Substation Auto Lead | 13220000 | 2187535 | N/A | 1375735 | N/A | 1420550.79 | N/A | -35.06% | 3.258%
| HLP/00/1408/TR/0002 | P1409.2 Install Fiber Deepwater-LydelL |  |  | N/A |  | N/A |  | N/A
| HLP/00/1408/TR/0002 | P1409.3 Reconfigure/Reenergize Deepwater Sub |  |  | N/A |  | N/A |  | N/A
Jordan Area Load Addition | HLP/00/0055/TR/0142 | P1028 PLACID Substation | 30972000 | 7684402.1923 | 2021-02-01 | 15276000 | 2021-04-01 | 16010646.74 | 2023-06-01 | 108.4% | 4.809% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect multiple fluctuations in estimates related to contract labor and transportation costs that could have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is 5% |  | 5 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | c. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | d. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/1415/TR/0002 | P1415 Jordan-BENDER-CONNER |  |  | 2020-08-01 |  | 2021-01-01 |  | 2022-09-01
| HLP/00/1416/TR/0002 | P1416 Jordan Loop |  |  | 2020-08-01 |  | 2021-01-01 |  | 2023-01-01
WAP to Westpark Tollway ckt 09 Rebuild | HLP/00/1261/TR | P1261 W.A. Parish-Hayes | 50770000 | 28883000 | 2019-11-01 | 28883000 | 2019-11-01 | 44219655.31 | 2021-11-01 | 53.1% | 53.1% | Variance was due to (1) 13 days delayed due to bad weather and flooding resulting in additional labor costs and mat rental costs. (2) Job was placed on hold for over a year due to pandemic constraints. This resulted in permits expiring and needing to be re-done. |  | 6 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | c. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | N/A | N/A | N/A | d. The primary reason for shut down was due to budget constraints which resulted from higher labor and material costs due to the pandemic. | e. Please see response to PUC 07-015 parts C and D for a daily cost comparison of mats vs. delaying. For this project it was more cost effective to get additional mats as opposed to delaying the project. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/1261/TR | P1261.1 W.A. Parish-Hayes (Structures 33016-33018) |  |  | 2020-02-01 |  | 2020-02-01 |  | 2021-10-01
| HLP/00/1261/TR | P1261.3 Hayes Approach Spans |  |  | 2020-10-01 |  | 2020-10-01 |  | 2021-10-01
Mt Belvieu Reliabiliy Upgrades | HLP/00/1425/TR/0001 | P1425 CHEVON-LNGSTN-EAGLE | 27280000 | 16334000 | 2021-02-01 | 34237000 | 2021-09-01 | 50321602.54 | 2023-12-01 | 208.1% | 46.98% |  |  | 7 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | N/A | N/A | c. Variance was caused by unplanned severe weather. Severe weather downed several trees and damaged completed work. This resulted in increased labor, material, and equipment costs. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/1425/TR/0001 | P1425.3 Jordan-WINFE-EAGLE-Mont Belvieu |  |  | 2021-10-01 |  | 2022-01-01 |  | 2023-12-01
| HLP/00/1425/TR/0001 | P1425.4 HOPSON-Cedar Bayou Plant |  |  | 2021-07-01 |  | 2022-03-01 |  | 2023-12-01 |  |  | (1) Multiple instances of severe weather required CenterPoint to re-energize the line in order to provide reliable transmission service to CenterPoint's Retail customers. The re-energizations themselves required significant labor, and the resulting delays further increased labor and equipment rental costs. (2) Severe weather downed several trees and damaged completed work. This resulting in increased labor, material, and equipment costs. (3) For reliability reasons, CenterPoint had to authorize the use of significant overtime so as to minimize the impact of the above delays so that power would be returned on schedule as requested.
| HLP/00/1425/TR/0001 | P1425.5 CHEV-Cedar Bayou Plant |  |  | 2021-07-01 |  | 2022-03-01 |  | 2023-12-01
Wallis - Peters ckt 65 Rebuild | HLP/00/1412/TR | P1399.1 GEBHRT-Wallis | 64781000 | 55059000 | 2020-12-01 | 63917000 | 2021-02-01 | 64573857.05 | 2023-07-01 | 17.28% | 1.028% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect multiple fluctuations in estimates related to an increase in contract engineering and consulting costs that could have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is 1%. |  | 8 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | d. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/1412/TR | P1399.2 GEBHRT-Sealy |  |  | 2020-04-01 |  | 2020-12-01 |  | 2023-05-01
| HLP/00/0922/TR/0012 | P1399.3 Sealy-Peters |  |  | 2021-08-01 |  | 2021-12-01 |  | 2023-09-01
Angleton - West Columbia ckt 04 RB/RC | HLP/00/0922/TR/0014 | P1235.1 Angleton-West Columbia | 38702000 | 41890745.7925 | 2021-07-01 | 75946000 | 2021-09-01 | 102210904.56 | 2023-12-01 | 144% | 34.58% | After the project was engineered and designed, a governmental entity announced it planned to build a lake over a portion of the planned route. CenterPoint was required to lengthen the route so as to go around the planned lake and to acquire an additional ROW (as a rebuild, the plan had initially been to use CenterPoint Houston’s existing ROW). This unexpected routing change resulted in increased labor, equipment and ROW expenses. Project costs were further increased by: (1) the need to design and install a 16.5 mile temporary bypass; (2) severe weather and flooding (up to five feet of water in portions of the Right of Way area); and (3) a need to accelerate the construction of the project requiring crews to work overtime and weekends, increasing labor costs. |  | 9 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | N/A | N/A | c. Government entity announcing the plan to build a lake within our existing ROW limited CenterPoint on alternative solutions outside of acquiring additional ROW. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/0922/TR/0014 | P1235.2 Angleton-West Columbia (Structures 34141-34145 and 34052-34053) |  |  | 2021-10-01 |  | 2021-12-01 |  | 2023-06-01
| HLP/00/0922/TR/0014 | P1235.3 Angleton-West Columbia (Structures 03971-03976) |  |  | 2021-08-01 |  | 2021-08-01 |  | 2023-06-01
Algoa Corner - LaMarque ckt 93 RB/RC | HLP/00/0922/TR/0016 | P1042.1 P.H. Robinson-Alta Loma | 34564000 | 69772000 | 2021-07-01 | 102644000 | 2022-03-01 | 104421719.78 | 2023-12-01 | 49.66% | 1.732% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect multiple fluctuations in estimates that have a cumulative impact above 10% as well as to provide estimates for additional cost categories. Variance percentage of final total costs vs. final estimate filed in MCPR is 2% |  | 10 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/0922/TR/0016 | P1042.2 La Marque-Hitchcock |  |  | 2021-07-01 |  | 2022-03-01 |  | 2023-12-01
| HLP/00/0922/TR/0016 | P1042.3 Alta Loma-Hitchcock |  |  | 2021-07-01 |  | 2021-09-01 |  | 2023-12-01
Flewellen - Peters ckt 25 RB/RC | HLP/00/1413/TR | P1413.1 Flewellen-Peters (Structures 34905-35126) | 76191000 | 135710000 | 2021-11-01 | 150824000 | 2022-01-01 | 111568666.49 | 2023-12-01 | -17.79% | -26.03%
| HLP/00/1413/TR | P1413.2 Flewellen-Peters (Structures 35331-35170) |  |  | 2021-11-01 |  | 2022-02-01 |  | 2023-10-01
THW - WO ckt 29 Conversion | HLP/00/0496/TR | P1391.1/P1392.2 T.H. Wharton-Little York-White Oak | 79900000 | 43127033.08 | 2021-09-01 | 83490000 | 2021-11-01 | 42419990.81 | 2023-12-01 | -1.639% | -49.19%
| HLP/00/0496/TR | P1391.3 T.H. Wharton Substation Conversion |  |  | 2022-11-01 |  | 2023-01-01 |  | 2023-12-01
| HLP/00/0496/TR | P1391.4 Little York Substation Conversion |  |  | 2022-11-01 |  | 2022-11-01 |  | 2023-12-01
| HLP/00/0496/TR | P1391.5 White Oak Substation Conversion |  |  | N/A |  | N/A |  | N/A
Greens Bayou - Clinton 138 kV Conversion | HLP/00/0914/TR/0005 | P1063.1 TEXWAL-Greens Bayou Plant | 88500000 | 43270454.1502 | 2021-12-01 | 67749000 | 2022-05-01 | 72263086.86 | 2024-02-01 | 67% | 6.663% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect multiple fluctuations in estimates related to contract labor and transportation costs that could have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is 7% |  | 11 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c.The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/0914/TR/0005 | P1063.2 TEXWAL-Wallisville |  |  | 2023-02-01 |  | 2023-02-01 |  | 2024-02-01
| HLP/00/0914/TR/0005 | P1063.3 Wallisville-Casten-Clinton |  |  | 2022-07-01 |  | 2022-11-01 |  | 2024-02-01
| HLP/00/0914/TR/0005 | P1063.4 GBY-TEXWAL-Wallisville-Casten-Clinton |  |  | N/A |  | N/A |  | N/A
STONE LAKE - NEW 35KV SUBSTATION | HLP/00/1306/TR | P1306.1 Stone Lake: Loop 138kV Ckt 66B Near Str #18668 (4/2022-12/2022) | 14552000 | 3933000 | 2022-02-01 | 7052000 | 2022-04-04 | 5315240.22 | 2023-11-01 | 35.14% | -24.63% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect multiple fluctuations in estimates that have a cumulative impact above 10% as well as to provide estimates for additional cost categories. Variance percentage of final total costs vs. final estimate filed in MCPR is -25% |  | 12 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/1481/TR/0001 | P1481.1 Hockley-Tomball |  |  | 2021-11-01 |  | 2022-01-04 |  | 2023-12-01
CUTLASS SOLAR INTERCONNECTION | HLP/00/1491/TR | P1491.1 Whaley Sub: Loop 345kV Ckt 72C Near Str #28367 | 15200000 | 9254299.62 | 2022-04-01 | 8286000 | 2022-08-01 | 8763731.4 | 2023-11-01 | -5.301% | 5.766%
| HLP/00/1491/TR | P1491.2 Rowland Sub: 345kV Generator Lead (Cutlass Solar) |  |  | 2022-06-01 |  | 2022-08-01 |  | 2023-11-01
FIGHTING JAYS INTERCONNECTION | HLP/00/1492/TR | P1492 Wolf Substation | 16800000 | 5791000 | 2021-08-02 | 5791000 | 2021-08-02 | 6071782.29 | 2023-12-01 | 4.849% | 4.849%
RED-TAILED HAWK INTERCONNECTION | HLP/00/1493/TR | P1493 Blue Substation | 18760000 | 2636000 | 2022-01-01 | 2814000 | 2022-03-15 | 4073764 | 2023-11-01 | 54.54% | 44.77% | Labor costs were higher than expected because: (1) the wholesale customer was not ready for CenterPoint's crews on multiple occasions, resulting in multiple mobilizations and demobilizations (2) unanticipated issues obtaining outage permissions from ERCOT, resulting in multiple mobilizations and demobilizations (3) Due to time lost from the first issue, reliability considerations required the crews to work overtime, increasing labor costs. |  | 13 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | N/A | N/A | c. Unforeseen delays due to customer not being ready to energize required crews to work overtime to maintain schedule. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HUNGERFORD-SBRANCH SOLAR INTERCONNECTION | HLP/00/1497/TR | P1497.1 Hungerford Substation | 9892000 | 767000 | 2021-08-01 | 906000 | 2021-10-01 | 947269.74 | 2023-11-01 | 23.5% | 4.555% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction. Variance percentage of final total costs vs. final estimate filed in MCPR is 5% |  | 14 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RIVERSIDE SUB INTERCONNECTION | HLP/00/1498/TR | P1498 Riverside Loop | 10298000 | 1774000 | 2021-10-01 | 4011000 | 2022-01-01 | 6321625.27 | 2023-09-01 | 256.3% | 57.61% | Labor and rental costs were higher than estimated due to: (1) outage constraints resulting in two mobilizations/demobizations; (2) inclement weather resulting in both rain delays and the need to lay additional mats over the entirety of the ROW |  | 15 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | N/A | N/A | d. The alternative solution was to delay the project until the ROW was cleared to travel along. This solution would cost more than paying for additional mats. | N/A | c. 4500 mats for the additional 21 days cost $142,000 or $6,761.90 per day. The daily cost to delay a 30-man crew is $64,000 per day. Based on this, it was more cost effective to obtain additional mats. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LONGBOW INTERCONNECTION | HLP/00/1501/TR | P1501.1 Danbury Substation | 15437000 | 2601000 | 2022-01-01 | 3391000 | 2022-03-10 | 5897887.73 | 2023-06-01 | 126.8% | 73.93% | Unexpected rainy weather caused delays and required the use of more mats were needed than initially estimated. The delays and additional mats increased labor and equipment costs. |  | 16 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | c. Please see response to PUC 07-015 parts C and D for a daily cost comparison of mats vs. delaying. For this project it was more cost effective to get additional mats as opposed to delaying the project. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BEACHWOOD GENERATOR INTERCONNECTION | HLP/00/1516/TR | P1516 Beachwood Sub: 138kV Generator Lead (Mark One) (2/2022-2/2022) | 3237000 | 1444396 | N/A | 1444396 | N/A | 947483.53 | N/A | -34.4% | -34.4%
GARTH - NEW 12KV SUBSTATION | HLP/00/1266/TR | P1241.1 Garth Substation | 27280000 | 3112348.857 | 2019-04-01 | 3182000 | 2019-06-01 | 3433331.38 | 2020-06-01 | 10.31% | 7.899% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect multiple fluctuations in estimates related to contract labor and transportation costs that could have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is 8% |  | 17 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | N/A | N/A | N/A | d. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/1266/TR | P1241.2 Crosby-Mont Belvieu |  |  | 2019-02-01 |  | 2019-02-01 |  | 2020-06-01
Lake Houston Sub | HLP/00/1250/TR | P1250 Lake Houston Substation |  | 1038000 | 2019-04-01 | 1478000 | 2019-07-01 | 1103817.87 | 2020-06-01 | 6.341% | -25.32%
WORTHAM - NEW 35KV SUBSTATION | HLP/00/1308/TR | P1308 Wortham Substation |  | 942000 | 2020-10-01 | 942000 | 2020-10-01 | 1127065.02 | 2022-03-01 | 19.65% | 19.65% | During construction, the job scope changed because work was added to the work order. The new work required adding a tangent pole between the 3-pole to the substation rack to role the project phases. To finish the project on schedule there was a temporary post insulator jumper configuration installed on the 3-pole. This was needed to allow time for a new tangent pole to be fabricated and installed. These changes resulted in increased labor and construction costs as well as renting additional equipment. |  | 18 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | d. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | e. Phasing issues caused the need for an additional permanent concrete pole to roll the phases to the correct orientation. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BURKE INTERCONNECTION | HLP/00/1389/TR | P1389 Burke Substation |  | 896000 | 2019-11-01 | 896000 | 2019-11-01 | 2024360.67 | 2020-09-01 | 125.9% | 125.9% | Unanticipated ERCOT outage constraints resulted in multiple mobilization and demobilizations, increasing labor costs. Due to time lost from the outage constraints, reliability considerations required the crews to work overtime, increasing labor costs. |  | 19 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | d. Outage constraints presented by ERCOT were unanticipated, CenterPoint had no other options outside of working crews overtime to maintain schedule. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
the RFIs for parts b etc starting in column S. -2: HLP/00/1389/TR; the RFIs for parts b etc starting in column S. -3: P1389.1 WAGYU_ Substation; the RFIs for parts b etc starting in column S. -6: 2019-11-01; the RFIs for parts b etc starting in column S. -8: 2019-11-01; the RFIs for parts b etc starting in column S. -10: 2020-08-01 |  |  |  | x | [9 empty] | x
BRAZORIA WEST SOLAR INTERCONNECTION | HLP/00/1454/TR | P1454 Eagle Nest Substation |  | 7704000 | 2021-04-01 | 7704000 | 2021-04-01 | 7963549.72 | 2023-05-01 | 3.369% | 3.369%
Baytown Area Upgrades | HLP/00/1216/TR/0001 | P1216.2 Restor SanJaciBayErosion @ Str #14727 |  | 6137476.0038 | 2019-06-01 | 7348000 | 2019-06-01 | 10794222.93 | 2022-09-01 | 75.87% | 46.9% | The initial estimate did not reflect that CenterPoint's existing easement crossing Exxon's property only permitted mantenance. To complete the project, CenterPoint had to obtain addditional rights from Exxon. It took nearly a year of negotiations to obtain access to perform soil boring and to install the requisite foundations, which resulted in increased labor costs from additional mobilization and demobilization. In order to avoid condemnation, CenterPoint had to revise design drawings, foundation locations, and test bore locations. After construction began, Exxon was slow to approve proposed drawings and took months before getting a response. This stall resulted in increased labor costs due to mats that remained in place for the duration of the project. Labor cost variance primarily due to additional mats cost. Unanticipated outage constraints resulted in in multiple mobilizations and demobilization, increasing labor costs. These delays also increased equipment rental costs. |  | 20 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | d. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | e. Existing structure was in Exxon property, CenterPoint had rights for maintenance only. It took multiple attempts and almost a year of back-and-forth negotiation with Exxon to grant access and get LONO to perform soil boring and to install foundation on agreed upon space. CenterPoint revised P&P drawings to meet Exxon’s requirements and revised foundation location and test bore locations per Exxon’s recommendation. Exxon was slow to approve our proposed drawings and took months before getting a response. These delays were not foreseeable. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/1216/TR/0001 | P1216.4 RC/Thermally Uprate 138kV Ckt87E TX-CB |  |  | 2019-10-01 |  | 2020-04-01 |  | 2023-01-12
the RFIs for parts b etc starting in column S. -2: HLP/00/1216/TR/0001; the RFIs for parts b etc starting in column S. -3: P1216.50 ThermUprate 138kV Ckt21F Diabox-Moment; the RFIs for parts b etc starting in column S. -8: N/A; the RFIs for parts b etc starting in column S. -10: 2019-12-31 | [14 empty] | x
Peyton Creek Wind Generator Interconnect | HLP/00/1262/TR | P1262 REFUGE Substation |  | 4426000 | 2019-03-01 | 4359000 | 2019-05-01 | 5599160.18 | 2020-04-01 | 26.51% | 28.45% | Unanticipated rainy weather required the use of mats to access the ROW, increasing labor and equipment costs. |  | 21 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | d. Please see response to PUC 07-015 parts C and D for a daily cost comparison of mats vs. delaying. For this project it was more cost effective to get additional mats as opposed to delaying the project. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Greens Bayou Reconfiguration | HLP/00/1338/TR | P1338.1 P1338 Relocate 138kV Ckt 94A/95C at GBY |  | 2851782.4 | N/A | 2851782.4 | N/A | 3265229.55 | N/A | 14.5% | 14.5% | Unanticipated rainy weather resulted in multiple mobilizations and demobilizations, increasing labor and equipment rental costs. |  | 22 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | d. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | e. October 2019 to December 2020. | f. The unexpected rains occurred in January of 2020. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/1338/TR | P1338.2 P1338 Greens Bayou 69kV Ckt 17A-Cons |  |  | N/A |  | N/A |  | N/A
Limburg Substation | HLP/00/1345/TR | P1350 Limburg Substation |  | 1157000 | 2019-12-01 | 1157000 | 2019-12-01 | 824688.91 | 2020-10-01 | -28.72% | -28.72%
Blodgett 138kV Loop Conversion | HLP/00/1335/TR | P1260.10 Blodgett Sub Loop 138kV Ckt 37C |  | 2291148.6737 | N/A | 2291148.6737 | N/A | 1666751.57 | N/A | -27.25% | -27.25%
DANISH FIELDS SOLAR INTERCONNECTION | HLP/00/1450/TR | P1450.1 Hillje Sub: Danish Fields Generator Lead |  | 4728323 | N/A | 4728323 | N/A | 3112391.6 | N/A | -34.18% | -34.18%
Ckt.05B Line Reposition | HLP/00/1518/TR/0002 | P1426.3 H.O. Clarke-Garrott |  | 18275712.703 | 2021-07-01 | 28993000 | 2021-09-01 | 28430464.2 | 2023-12-01 | 55.56% | -1.94% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect multiple fluctuations in estimates related to materials and contract labor and transportation costs that could have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is -2% |  | 23 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/1518/TR/0003 | P1426.4 H.O. Clarke Approach Spans (Structures 35970-35977) |  |  | 2022-04-01 |  | 2022-06-01 |  | 2023-12-01
Mykawa Substation | HLP/00/1424/TR/0001 | P1424.4 Mykawa Substation |  | 1605000 | 2021-10-01 | 3336000 | 2022-01-01 | 2448252.13 | 2023-09-01 | 52.54% | -26.61% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect differences in estimates related to contract labor and transportation costs that could have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is -27% |  | 24 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Generator - PES1 (@ HOC) | HLP/00/1426/TR/0001 | P1426.1 PES1 HOC: Generator Lead |  | 1471963.7813 | N/A | 924000 | N/A | 1274037.6 | N/A | -13.45% | 37.88%
| HLP/00/1426/TR/0001 | P1426.2 PES1 HOC: Relo Ckt05A & 26A App. Spans |  |  | 2020-07-01 |  | 2020-10-01 |  | 2023-12-01
Spillman Restoration | HLP/00/1414/TR | P1414.1 Cedar Bayou Plant Approach Span |  | 2148000 | 2021-04-01 | 2981000 | 2021-04-01 | 1974644.35 | 2023-06-01 | -8.071% | -33.76%
| HLP/00/1414/TR | P1414.2 Morgans Point Reconfiguration |  |  | 2021-01-01 |  | 2021-01-01 |  | 2023-05-01
WAP FAULT DUTY-BUS SPLIT | HLP/00/0130/TR/0036 | P1015 W.A. Parish Approach Spans |  | 987000 | 2018-09-01 | 987000 | 2018-09-01 | 1116323.74 | 2021-01-01 | 13.1% | 13.1% | While working on the project, 2 additional poles were noticed to need replacement due to strength issues. Variance was due to the increased labor and equipment cost associated with the replacement of the poles. |  | 25 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Marick Substation | HLP/00/0055/TR/0144 | P1030 MARICK Substation |  | 1280000 | 2020-07-01 | 1204000 | 2020-09-01 | 1032367 | 2021-10-01 | -19.35% | -14.26%
HOPSON SUBSTATION | HLP/00/0055/TR/0136 | P1017 HOPSON Substation |  | 987000 | 2024-06-19 | 987000 | 2024-06-19 | 1772174.13 | 2024-12-20 | 686474.13 | 80% | Variance primarily due to unforeseen severe weather which caused: (1) three days of delay; (2) the need for additional mats; (3) temporary work to repair bypass from weather decay |  | 26 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | d. Mats cost $61,420. | e. Severe weather caused the soil to decay causing a need to repair the temporary bypass. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CELWST SUBSTATION | HLP/00/0055/TR/0133 | P1009 CELWST Substation |  | 402000 | 2024-06-18 | 402000 | 2024-06-18 | 648512 | 2024-11-19 | 61% | 61% | Variance due to difficulty with the railroad access. Unrelated work was ongoing and crews had to wait three days for railroad to be cleared. Severe unsafe weather led to additional delays and crew mobilizations. |  | 27 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | CenterPoint Houston is currently drafting this response and will provide in a later update. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RIGBY SUBSTATION | HLP/00/0055/TR/0137 | P1345 RIGBY_ Substation |  | 894825 | 2024-02-19 | 929000 | 2024-02-19 | 1259136 | 2024-08-20 | 41% | 36% | Variance primarily due to flooding from Tropical Storm Imelda. Additional crew mobilizations and demobilizations as well as mats needed. |  | 28 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | CenterPoint Houston is currently drafting this response and will provide in a later update. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RUSSEL - NEW TRANSMISSION CUSTOMER | HLP/00/0055/TR/0119 | P1001 Service to New Braskem RUSSEL Substation |  | 761000 | 2024-03-18 | 761000 | 2024-03-20 | 1834778 | 2024-07-20 | 141% | 141% | Variance due to (1) increase in guard services after a shelter in place protocol enacted while on the jobsite. (2) Weather delays and mats needed to access the right of way. |  | 29 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | CenterPoint Houston is currently drafting this response and will provide in a later update. | N/A | N/A | CenterPoint Houston is currently drafting this response and will provide in a later update. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WATERHOLE SUBSTATION | HLP/00/1571/TR | P1571.1 Waterhole Substation |  | 4363978.4115 | 2022-07-01 | 3694000 | 2023-01-01 | 3668435.09 | 2024-01-01 | -15.94% | -0.6921%
GULFTIE GENERATOR INTERCONNECTION | HLP/00/1509/TR | P1509.1 New Gulf Approach Spans |  | 4352205.3059 | 2022-09-01 | 5945497.18 | 2023-05-01 | 5120780.96 | 2024-01-01 | 17.66% | -13.87% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, as well as to provide estimates for additional cost categories. Variance percentage of final total costs vs. final estimate filed in MCPR is -14% |  | 30 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/1577/TR | P1509.2 Gulftie Sub: Loop 138kV Ckt 60 |  |  | 2022-07-01 |  | 2023-03-01 |  | 2024-01-01
| HLP/00/1577/TR | P1509.3 Install 138kV Generator Lead: Gulftie-TXGLF
SNUG INTERCONNECT | HLP/00/1570/TR | P1570.1 Snug Sub: Loop Ckt 04 near Str #32567 (Cottonwood) |  | 5468000 | 2023-09-01 | 5468000 | 2023-09-01 | 5495248.24 | 2024-01-01 | 0.4983% | 0.4983%
| HLP/00/1570/TR | P1570.2 Upgrade Ckt 04B: Hudson-Monsan |  |  | 2022-10-01 |  | 2022-10-01 |  | 2024-01-01
| HLP/00/1570/TR | P1570.3 Upgrade Ckt 04A: Hudson-Mustang Bayou |  |  | 2022-10-01 |  | 2022-10-01 |  | 2024-01-01
ARCHER SUB | HLP/00/1567/TR | P1567.1 Archer Sub: Loop Ckt 26B-3 near Str #08857 |  | 6317992.5 | 2022-08-01 | 6505000 | 2022-10-01 | 6066828.47 | 2023-11-01 | -3.975% | -6.736%
| HLP/00/1567/TR | P1567.2 Archer Sub: 138kV Generator Lead to Brotman Sub
| HLP/00/1600/TR | P1567.3 Upgrade 138kV Ckt 26: Archer-Rosharon | 16478000 |  | 2022-08-01 |  | 2023-04-01 |  | 2023-12-01
RABBS INTERCONNECTION | HLP/00/1500/TR | P1500.1 RABBS Substation |  | 4521807.6827 | 2021-05-01 | 6125000 | 2021-10-01 | 3697654.83 | 2022-12-01 | -18.23% | -39.63%
ROUGHNECK STORAGE INTERCONNECTION | HLP/00/1485/TR | P1485 NORTCO Substation |  | 1377000 | 2021-02-01 | 1377000 | 2021-02-01 | 913779.77 | 2022-12-14 | -33.64% | -33.64%
SRB AREA 69 KV UPGRADES | HLP/00/1419/TR/0002 | P1419.1 SRB Area 69kV Upgrades |  | 150818.97 |  | 150818.97 |  | 91087.21 |  | -39.6% | -39.6%
COPPER TO JONES CREEK CKT02 | HLP/00/1337/TR/0001 | P1337.1 Install Conductor: Jones Creek-Str #31519 |  | 1920547.0496 | 2020-05-01 | 1920547.0496 | 2020-05-01 | 4331083.5 | 2023-06-01 | 125.5% | 125.5% | Work order was also charged to P1337.4. Charges to be accounted for in P1337.4 variance analysis |  | 31 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | d. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | e. Due to material not arriving on time, crews had to wait until material was delivered to complete construction. Previously scheduled outages had to be rescheduled. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/1337/TR/0001 | P1337.2 JCK Sub: Relocate Switchable Cap Bank Leads |  |  | N/A |  | N/A |  | N/A
| HLP/00/1337/TR/0001 | P1337.3 Velasco Sub: Relocate Ckt 59 Sub Lead |  |  | N/A |  | N/A |  | N/A
| HLP/00/1337/TR/0001 | P1337.4 Jones Creek Approach Spans |  |  | 2021-01-01 |  | 2021-01-01 |  | 2023-06-01 |  |  | Manufacturing delivery delays that caused outage constraints, resulting in multiple crew mobilizations and demoblilizations.
| HLP/00/1337/TR/0001 | P1337.5 Install Fiber: Copper-Str #31519 |  |  | N/A |  | N/A |  | N/A
NASH LOOP | HLP/00/1278/TR | P1278 Nash Loop |  | 6472000 | 2018-11-01 | 7546000 | 2019-02-01 | 8678623.08 | 2020-03-01 | 34.09% | 15.01% | Additional variance caused by unexpected rainy weather that required mat rentals. |  | 32 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | d. Please see response to PUC 07-015 parts C and D for a daily cost comparison of mats vs. delaying. For this project it was more cost effective to get additional mats as opposed to delaying the project. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BASF HOFMAN UPDGRADE CKT 2 | HLP/00/1246/TR | P1246 COPPER-BASF__-HOFMAN- Lake Jackson |  | 4281000 | 2018-07-01 | 4281000 | 2018-07-01 | 7133182.21 | 2020-04-01 | 66.62% | 66.62% | In order to avoid condemnation, CenterPoint had to agree to a landowner's demands related to matting, soil removal and disposal, greatly increasng the costs of the project. The landowner also caused unaticipated delays in obtaining a railroad crossing permit. These problems resulted in increased labor and equipment rental costs. |  | 33 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | CenterPoint Houston is currently drafting this response and will provide in a later update. | e. See comment to part "d" | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAMSEY SOLAR GENERATOR INTERCONNECTION | HLP/00/1480/TR/0001 | P1480.1 Hillje Sub: Relocate 345kV Ckt 72D Approach Span |  | 150807.24 |  | 150807.24 |  | 57741.54 |  | -61.71% | -61.71%
MYRTLE SOLAR INTERCONNECTION | HLP/00/1445/TR | P1445.1 MYRTLE Sub: Generator Lead |  | 319771 | N/A | 319771 | N/A | 279005.61 | N/A | -12.75% | -12.75%
OLD 300 SOLAR CENTER INTERCONNECTION | HLP/00/1453/TR | P1453 Cedar Creek Sub: Loop 345kV Ckt 72C-1 Near Str #28412 |  | 2444000 | 2020-12-01 | 4060000 | 2021-03-01 | 5019592 | 2022-12-01 | 105.4% | 23.64% | Tower manufacturer delivered tower late, causing CenterPoint to miss the planned outage window. The resulting outage constraints increased labor and equipment costs as they required mulitple mobilizations and demobilizations. |  | 34 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | d. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | CenterPoint Houston is currently drafting this response and will provide in a later update. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PARKES SUBSTATION | HLP/00/0055/TR/0134 | P1012 PARKES Substation |  | 2775000 | 2018-12-01 | 1416000 | 2019-02-01 | 1345879.9 | 2020-02-01 | -51.5% | -4.952%
Convert Alvin sub to 138 kV, double tap | HLP/00/0996/TR/0001 | P913.1 Alvin-Algoa Corner |  | 16139450.46 | 2021-02-01 | 36866000 | 2021-10-01 | 21220750.29 | 2023-12-01 | 31.48% | -42.44% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which included increased installation and material costs. Variance percentage of final total costs vs. final estimate filed in MCPR is -34% |  | 35 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | c. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | d.The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/0996/TR/0001 | P913.2 Alvin Sub: Convert to 138kV Ckt 26B |  |  | 2020-11-01 |  | 2021-01-01 |  | 2022-01-14
the RFIs for parts b etc starting in column S. -2: HLP/00/0996/TR/0001; the RFIs for parts b etc starting in column S. -3: P913.4 Karsten-Manvel-Alvin Conversion; the RFIs for parts b etc starting in column S. -6: 2023-03-01; the RFIs for parts b etc starting in column S. -8: 2023-03-01; the RFIs for parts b etc starting in column S. -10: 2023-12-01 |  |  |  |  | x
| HLP/00/0996/TR/0001 | P920.1 Manvel-Karsten (Manvel-Structure 28223, Structure 28217-Karsten) |  |  | 2021-02-01 |  | 2021-04-01 |  | 2023-12-01
| HLP/00/0996/TR | P920.2 Partial Rebuild of 345 kV Ckts. 18C and 99B |  |  | 2021-01-01 |  | 2021-04-01 |  | 2023-05-01
| HLP/00/0996/TR/0001 | P920.5 Partial Rebuild and Partial Reconductor of 69 kV Ckt. 53D |  |  | 2021-06-01 |  | 2021-06-01 |  | 2023-05-01
WALLER ADD XFMR AND FEEDER | HLP/00/1162/TR | P1162 Waller Substation |  | 297000 | 2018-06-01 | 297000 | 2018-06-01 | 316976.58 | 2021-10-01 | 6.726% | 6.726%
READING INSTALL 35KV TRFS AND FDRS | HLP/00/1226/TR | P1226 Reading Approach Spans |  | 477187.6957 | 2018-12-01 | 546762.6604 | 2019-04-01 | 358037 | 2019-09-01 | -24.97% | -34.52%
CONVERT HOC LOAD FROM 69 TO 138KV | HLP/00/1112/TR | P914.1 H.O. Clarke Conversion |  | 895000 | 2018-08-01 | 895000 | 2018-08-01 | 1740540 | 2019-10-01 | 94.47% | 94.47% | Severe weather and flooding required the use of more mats than originally anticipated. Extra labor and equipment costs were incurred because of the mud around the project, requiring additional mats and the mobilization and demobilization of equipment. |  | 36 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | c. Please see response to PUC 07-015 parts C and D for a daily cost comparison of mats vs. delaying. For this project it was more cost effective to get additional mats as opposed to delaying the project. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UPGRADE CKT 73 CLODINE | HLP/00/1125/TR | P1125 Clodine-Barker |  | 627000 | 2018-10-01 | 627000 | 2018-10-01 | 197693 | 2019-11-01 | -68.47% | -68.47%
IMPERIAL TAP UPGRADE | HLP/00/0927/TR/0002 | P987 Imperial Tap |  | 7518142.3099 | 2018-06-01 | 10825950.7238 | 2018-09-01 | 10407451 | 2019-12-01 | 38.43% | -3.866% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which included increased labor and transportation & engineering costs. Variance percentage of final total costs vs. final estimate filed in MCPR is -4% |  | 37 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RED BLUFF SUBSTATION | HLP/00/1152/TR | P1152 Red Bluff Substation |  | 3973902 | 2018-06-01 | 2748000 | 2018-09-01 | 4231775 | 2019-12-01 | 6.489% | 53.99%
GALV-WGALV REBUILD 138KV CKT 63A | HLP/00/0922/TR/0005 | P926 West Galveston-Galveston 26th Street |  | 6309472 | 2018-08-01 | 6309000 | 2018-08-01 | 5625886 | 2019-12-01 | -10.83% | -10.83%
GALVESTON CAUSEWAY REBUILD 138KV LINE | HLP/00/1080/TR | P930 Galveston Causeway Crossing |  | 10203073.1934 | 2017-12-01 | 11770000 | 2018-04-01 | 9130873 | 2020-01-01 | -10.51% | -22.42%
DALTON - NEW TRANSMISSION CUSTOMER | HLP/00/0055/TR/0132 | P1132 DALTON Substation |  | 2295190.1014 | 2018-01-01 | 2443000 | 2018-03-01 | 2470627.29 | 2020-01-01 | 7.644% | 1.131%
UPGRADE CKT 90 NB-GREENS TAP-Lockwood | HLP/00/1126/TR | P1126 North Belt-Greens Tap-Lockwood |  | 4655000 | 2018-06-01 | 10411000 | 2018-09-01 | 8227450 | 2020-01-01 | 76.74% | -20.97% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction. Variance percentage of final total costs vs. final estimate filed in MCPR is -3% |  | 38 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UPGRADE CKT 37 AND CKT 08 BUNKER AND TECO AREA | HLP/00/1119/TR | P1119.2 Grant-TECO__ |  | 6011000 | 2018-02-01 | 6011000 | 2018-02-01 | 5365019 | 2020-02-01 | -10.75% | -10.75%
| HLP/00/1119/TR | P1119.1 Knight-H.O. Clarke |  |  | 2017-11-01 |  | 2017-11-01 |  | 2019-12-01
LUBIZOL DP NEW TRANMISSION CUSTOMER | HLP/00/0055/TR/0121 | P991 PATRIK Substation |  | 1171546.2359 | 2017-11-01 | 1215000 | 2018-01-01 | 924543.0849 | 2020-03-01 | -21.08% | -23.91%
UPGRADE CKT 25 AND 73 CLODINE - OBRIEN | HLP/00/1118/TR | P1118 Clodine-Obrien |  | 3850000 | 2018-07-01 | 3850000 | 2018-07-01 | 10087962 | 2020-05-01 | 162% | 162% | Unforseen severe weather resulted in (1) 11 days of weather delays increasing labor and equipment rental costs and (2) the use of more mats than originally anticipated increasing labor and equipment rental costs. There was also damage to equipment. A rental track boom broke down and took 3 days to repair as mechanic was on a different job site. (3) Outages were delayed because of ongoing work at Memorial and Wood Creek substations that were scheduled for completion but were delayed. |  | 39 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | N/A | N/A | N/A | N/A | N/A | e. Other solution would be to fully delay the project until ROW is clear to work on without additional mats. This solution would drastically delay schedule and increase costs. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | d. Additional mats were required due to unforeseen weather. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KATY-FREEMAN-BETKA-HOCKLEY REBUILD CKT66 | HLP/00/1146/TR | P1146.1 Katy-Freeman (Freeman-Structure #06677) |  | 19140719.8754 | 2018-09-01 | 19131000 | 2018-09-01 | 20511756.93 | 2020-04-01 | 7.163% | 7.217%
| HLP/00/1146/TR | P1146 Freeman-Hockley |  |  | 2018-07-01 |  | 2018-07-01 |  | 2020-03-01
GERTIE TAP UPGRADE | HLP/00/0927/TR/0003 | P988 Gertie Tap |  | 5585000 | 2018-07-01 | 5585000 | 2018-07-01 | 6638815.98 | 2020-05-01 | 18.87% | 18.87% | The manufactuer delivered raiser beams that did not meet the required specifications. For reliability reasons, it was not perferrable to delay the project, so CenterPoint decided to adjust the improperly sized raiser beams rather than to wait for replacements. This unanticpated work increased labor costs. |  | 40 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | CenterPoint Houston is currently drafting this response and will provide in a later update. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PSARCO-METALSSW REBUILD CKT 94 | HLP/00/1149/TR | P956.1 Metals Switch-PSARCO (Structure #17586) |  | 2388000 | 2019-07-01 | 3053000 | 2019-10-01 | 4499386 | 2020-05-01 | 88.42% | 47.38% |  |  | 41 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | d. A damaged gate needed to be repaired/replaced before construction activities could begin. | CenterPoint Houston is currently drafting this response and will provide in a later update. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/1149/TR | P956 Metals Switch-PSARCO |  |  | 2018-10-01 |  | 2019-07-01 |  | 2020-05-01 |  |  | (1) Unanticpated severe weather resulted in four rainout days and required the use of more mats than originally anticipated, increasing labor and equipment costs. (2) A structure was found to be missing deadend material, all material necessary for 2 deadends was ordered to repair and replace damage.
NEW 345KV CKT SHELDON - DEEPWATER | HLP/00/1409/TR | P1408 Deepwater-Sheldon |  | 323000 | 2019-12-01 | 323000 | 2019-12-01 | 204222 | 2020-07-01 | -36.77% | -36.77%
S90 TOWER REPLACEMENTS | HLP/00/0054/TR/0025 | P25 Chambers-King (Structure #13238) |  | 126910680.0372 | 2019-09-01 | 128482000 | 2019-11-01 | 94251823.33 | 2020-08-01 | -25.73% | -26.64%
| HLP/00/0054/TR/0025 | P25.10 Cedar Bayou-Center (Structure 03021) |  |  | 2021-10-01 |  | 2022-03-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.11 Cedar Bayou-Center (Structure 03025) |  |  | 2021-10-01 |  | 2022-03-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.13 Cedar Bayou-KENNY_ (Structure 03016) |  |  | 2021-10-01 |  | 2022-03-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.14 Cedar Bayou-Center (Structure 03015) |  |  | 2021-10-01 |  | 2022-03-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.3/P25.30 South Texas-W.A. Parish (Structure 00703) |  |  | 2021-10-01 |  | 2022-03-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.33 Dow345-Oasis (Structure 00376) |  |  | 2021-05-01 |  | 2022-11-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.34 DOW345-Oasis (Structure 35705) |  |  | 2022-06-01 |  | 2023-04-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.35 DOW345-Oasis (Structure 35706) |  |  | 2022-06-01 |  | 2022-10-01 |  | 2023-11-01
| HLP/00/0054/TR/0025 | P25.36 Dow345-Oasis (Structure 24034) |  |  | 2021-05-01 |  | 2022-10-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.37 DOW345-Oasis (Structure 35707) |  |  | 2022-06-01 |  | 2022-10-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.38 DOW345-Oasis (Structure 35708) |  |  | 2022-06-01 |  | 2022-10-01 |  | 2023-11-01
| HLP/00/0054/TR/0025 | P25.39 O'Brien-W.A. Parish (Structure 01583) |  |  | 2021-05-01 |  | 2021-10-01 |  | 2023-09-01
| HLP/00/0054/TR/0025 | P25.4 Bellaire-W.A. Parish (Structure 00852) |  |  | 2021-04-01 |  | 2023-01-01 |  | 2023-09-01
| HLP/00/0054/TR/0025 | P25.40 O'Brien-W.A. Parish (Structure 01582) |  |  | 2021-05-01 |  | 2021-12-01 |  | 2023-06-01
| HLP/00/0054/TR/0025 | P25.41 T.H. Wharton-Zenith (Structure 18846) |  |  | 2021-05-01 |  | 2021-10-01 |  | 2023-06-01
| HLP/00/0054/TR/0025 | P25.42 T.H. Wharton-Zenith (Structure 18847) |  |  | 2021-05-01 |  | 2021-10-01 |  | 2023-06-01
| HLP/00/0054/TR/0025 | P25.43 Str 14226 S90 Tower Replacement |  |  | 2022-09-01 |  | 2022-09-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.5 Bellaire-Smithers (Structure 26056) |  |  | 2021-08-16 |  | 2021-08-16 |  | 2022-03-30
| HLP/00/0054/TR/0025 | P25.57 Addicks-T.H. Wharton (Structure 01240) |  |  | 2022-05-01 |  | 2022-10-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.58 Addicks-T.H. Wharton (Structure 01258) |  |  | 2022-05-01 |  | 2022-10-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.59 Str 01417 S90 Tower Replacement |  |  | 2022-08-01 |  | 2023-01-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.6 South Texas-W.A. Parish (Structure 19035) |  |  | 2021-05-01 |  | 2021-10-01 |  | 2022-12-01
| HLP/00/0054/TR/0025 | P25.60 Addicks-White Oak (Structure 01449) |  |  | 2021-05-01 |  | 2021-10-01 |  | 2022-12-01
| HLP/00/0054/TR/0025 | P25.61 Str 01418 S90 Tower Replacement |  |  | 2022-08-01 |  | 2022-08-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.62 Str 01400 S90 Tower Replacement |  |  | 2022-08-01 |  | 2023-06-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.63 Str 01438 S90 Tower Replacement |  |  | 2022-08-01 |  | 2022-08-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.64 Str 01431 S90 Tower Replacement |  |  | 2022-08-01 |  | 2022-08-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.65 Str 01430 S90 Tower Replacement |  |  | 2022-08-01 |  | 2022-08-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.66 Addicks-White Oak (Structure 01452) |  |  | 2021-05-01 |  | 2021-10-01 |  | 2023-05-01
| HLP/00/0054/TR/0025 | P25.67 Str 01437 S90 Tower Replacement |  |  | 2022-08-01 |  | 2022-08-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.68 Str 01402 S90 Tower Replacement |  |  | 2022-08-01 |  | 2022-08-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.69 Str 01407 S90 Tower Replacement |  |  | 2022-08-01 |  | 2022-08-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.7 South Texas-W.A. Parish (Structure 00646) |  |  | 2021-05-01 |  | 2022-12-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.70 Str 35721 S90 Tower Replacement |  |  | 2022-08-01 |  | 2021-08-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.71 Zenith-O'Brien (Structure 01585) |  |  | 2021-05-01 |  | 2022-06-01 |  | 2023-09-01
| HLP/00/0054/TR/0025 | P25.72 Zenith-O'Brien (Structure 01584) |  |  | 2021-05-01 |  | 2022-06-01 |  | 2023-09-01
| HLP/00/0054/TR/0025 | P25.75 Jordan-North Belt (Structure 02730) |  |  | 2021-09-01 |  | 2021-09-01 |  | 2023-11-01
| HLP/00/0054/TR/0025 | P25.76 Str 14225 S90 Tower Replacement |  |  | 2022-09-01 |  | 2022-09-01 |  | 2023-12-01
| HLP/00/0054/TR/0025 | P25.8 South Texas-W.A. Parish (Structure 00717) |  |  | 2021-10-01 |  | 2021-12-01 |  | 2023-06-01
| HLP/00/0054/TR/0025 | P25.9 South Texas-W.A. Parish (Structure 00651) |  |  | 2021-05-01 |  | 2022-03-01 |  | 2023-05-01
RITTENHAUS REBUILD CKT 95B TAP | HLP/00/1148/TR | P924.1 Rittenhouse Tap (Berry-North Belt) |  | 2858799 | 2019-07-01 | 5570000 | 2020-03-01 | 4435028 | 2020-10-01 | 55.14% | -20.38% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect multiple fluctuations in estimates that have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is -20% |  | 42 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RITTENHAUS TAP CKT 86 REBUILD | HLP/00/0922/TR/0003 | P924.2 Rittenhouse Tap (Aldine-Hardy) |  | 2285000 | 2019-07-01 | 3960000 | 2019-08-01 | 3872498.53 | 2020-10-01 | 69.47% | -2.21% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect multiple fluctuations in estimates that have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is 4% |  | 43 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRSM PREV MAINTENANCE PRGM-CAPITAL | HLP/00/0054/TR/0001 | P2019.3 Alvin-Webster Plant |  | 7989000 | 2019-11-01 | 8756000 | 2019-11-01 | 25119052.17 | 2021-03-01 | 214.4% | 186.9% | (1) Severe weather required the use of more mats than anticpated, unanticipated ROW clean up, the installation of a culvert, and unanticpated ROW maintenance. This increased labor and equipment rental costs. (2) unanticipated ROW issues casued delays which increased labor and equipment rental costs. For example, a pipeline company limited access to the ROW by imposing onerous restrictions and a farmer planted crops around a circuit, forcing crews to wait until after harvest to complete the work. |  | 44 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | d. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | N/A | N/A | N/A | N/A | g. Please see response to PUC 07-015 parts C and D for a daily cost comparison of mats vs. delaying. For this project it was more cost effective to get additional mats as opposed to delaying the project. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | e. TARGA required unforeseen work permits which resulted in delays. | f. Coordinating construction with farmers harvesting crops, the need to install culverts due to weather, replacing customer cattle gates, maintaining ROW due to high vegetation, safely removing bees from wooden poles, and angry landowners requiring police to guard crews. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/0054/TR/0001 | P2018 W.A. Parish-Jeanetta |  |  | 2018-06-01 |  | 2018-06-01 |  | 2019-11-01
| HLP/00/0054/TR/0001 | P2018.1 W.A. Parish-Britmoore |  |  | 2022-06-01 |  | 2022-06-01 |  | 2019-11-01
| HLP/00/0054/TR/0001 | P2018.2 Bellaire-Britmoore |  |  | 2018-07-01 |  | 2018-07-01 |  | 2020-02-01
| HLP/00/0054/TR/0001 | P2020 H.O. Clarke-W.A. Parish |  |  | 2019-11-01 |  | 2019-11-01 |  | 2020-11-01
| HLP/00/0054/TR/0001 | P2020.5 Routine maintenance of 69 kV Ckt. 43Z |  |  | 2020-06-01 |  | 2020-06-01 |  | 2022-09-01
| HLP/00/0054/TR/0001 | P2021 Routine maintenance of 69 kV Ckt. 46Z |  |  | 2021-06-01 |  | 2021-09-01 |  | 2022-09-01
| HLP/00/0054/TR/0001 | P2019.2 P.H. Robinson-La Marque |  |  | 2019-10-01 |  | 2019-10-01 |  | 2021-01-01
| HLP/00/0054/TR/0001 | P2019 W.A. Parish-West Columbia |  |  | 2019-02-01 |  | 2019-02-01 |  | 2020-05-01
| HLP/00/0054/TR/0001 | P2017.1 East Bernard-Peters |  |  | 2017-11-01 |  | 2017-11-01 |  | 2019-06-01
| HLP/00/0054/TR/0001 | P2017.2 Tomball-Hockley |  |  | 2017-11-01 |  | 2017-11-01 |  | 2019-06-01
| HLP/00/0054/TR/0001 | P2019.1 Flewellen-Peters |  |  | 2019-05-01 |  | 2019-07-01 |  | 2021-06-01
| HLP/00/0054/TR/0001 | P2022 Cedar Bayou-Kenny |  |  | 2022-04-01 |  | 2022-05-01 |  | 2023-06-01
BRAZOS RIVER STRUCTURE RELOCATIONS | HLP/00/1393/TR | P1393 Brazos River Crossing (Structures 01545-01548) |  | 9138000 | 2020-02-01 | 11028000 | 2020-04-01 | 13503840 | 2021-05-01 | 47.78% | 22.45% | (1) Severe weather resulted in 4 rainout days and required the use of more mats than anticipated, increasing labor and equipment rental costs. (2) CenterPoint had to accelerate portions of the project for reliability reasons as the curcuit needed to be re-energized because of a hurricane and unanticpated loading issues. These accelearations required the use of overtime, increasing labor costs (3) A crane failure occurred just prior to hurricane and caused further delay. |  | 45 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | d. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | e. Yes. Hurricane Hanna. Labor resources and the need to operate circuits that were supposed to be out for construction to work due to Hurricane. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PSARCO-CROSBY REBUILD CKT 08G | HLP/00/1150/TR | P1150.3 Crosby-PSARCO |  | 18904000 | 2019-05-01 | 16711000 | 2019-05-01 | 25946897.54 | 2021-07-01 | 37.26% | 55.27% | Severe weather caused (1) three rainout days, (2) the use of more mats than initially anticipated, (3) an unanticipated need for casing to keep drilled holes from caving, and (4) 30' sidewall trenches to cave in in 12' down, pausing work. These delays greatly increased labor costs and equipment rental costs. |  | 46 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | d. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | N/A | N/A | N/A | N/A | f. Please see response to PUC 07-015 parts C and D for a daily cost comparison of mats vs. delaying. For this project it was more cost effective to get additional mats as opposed to delaying the project. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | e. Caving was caused due to unexpected poor soil conditions while re drilling. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/1150/TR | P1150.4 Highland-Highlands Corner |  |  | 2019-04-01 |  | 2019-11-01 |  | 2021-05-01
| HLP/00/1150/TR | P1150 Highlands Tap |  |  | 2018-07-01 |  | 2019-01-02 |  | 2021-06-01
UPGRADE CKT31 DUNLAVY TO HEIGHTS | HLP/00/1117/TR | P1117 Dunlavy-Heights |  | 5224000 | 2019-08-01 | 5891000 | 2019-11-01 | 5486004 | 2021-07-01 | 5.015% | -6.875%
LINE CLEARANCE CORRECTIONS | HLP/00/1055/TR | P868 Angleton-STRATT |  | 8469908.3294 | 2016-04-01 | 11570000 | 2016-04-01 | 23218068.03 | 2016-04-01 | 174.1% | 100.7% | (1) After construction began, TxDOT began a road project and requested an alteration that required the use of a temporary pole. Additional labor was needed to install a bypass in order to install the temporary pole. This work also required additional mats for equipment to access the location of installation. (2) Labor costs increased between the time of the initial estimate and the start of the project. (3) Unanticipated severe weather resulted in rain outs, the use of more mats than originally anticipated, and the regrading of an access road, all of which increased labor and equipment rental costs. (4) For relaibility reasons, CenterPoint had to authorize the use of overtime so as to minimize the impact of the weather related delays. |  | 47 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | d. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | N/A | N/A | e. Other solution would be to fully delay the project until ROW is clear to work on without additional mats. This solution would drastically delay schedule and increase costs. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/1055/TR | P868.2 T.H. Wharton-Willow |  |  | 2020-07-01 |  | 2021-01-01 |  | 2021-07-01
| HLP/00/1055/TR | P868.4 Plaza-Telephone |  |  | 2021-07-01 |  | 2022-02-01 |  | 2022-12-01
| HLP/00/1055/TR | P868.5 South Lane City-Texas Gulf Cogen |  |  | 2021-07-02 |  | 2022-06-01 |  | 2023-11-01
| HLP/00/1055/TR | P868.6 T.H. Wharton-CAMRON (Structures 21509-21544) |  |  | 2022-04-01 |  | 2022-06-01 |  | 2023-10-01
| HLP/00/1055/TR | P868.7 Oates-Greens Bayou-Clinton (Structures 10401-10402) |  |  | 2022-07-01 |  | 2022-11-01 |  | 2023-12-01
| HLP/00/1055/TR | P868.8 53E H.O. Clarke to Karsten-Hframe Replacement & Int. Str. |  |  | 2022-08-01 |  | 2022-12-01 |  | 2023-12-01
| HLP/00/1055/TR | P868.9 Flewellen-Mason Road |  |  | 2022-10-01 |  | 2022-10-01 |  | 2023-12-01
| HLP/00/1055/TR | P868.10 Fannin-Grant (Structures 11486-11489) |  |  | 2023-03-01 |  | 2023-06-01 |  | 2023-12-01
MORGAN PT-ALKANE REBUILD 138KV CK96 | HLP/00/0922/TR/0006 | P857.2 Morgans Point-Sandy Point |  | 4502000 | 2018-12-01 | 4502000 | 2018-12-01 | 10854189.54 | 2021-09-01 | 141.1% | 141.1% | (1) As a result of the Winter Freeze in 2021, the project was delayed by 2 weeks and additional costs were incurred because workers had to temporarily energize the line in preparation for the storm. (2) A new railyard was added after the project was initially estimated. The railway was in operation continuously and the owner was not willing to shutdown the railyard so that crews could have access. As a result, crews had to work at night, increasing labor costs. There were about 13 train related delays. Special precautions were taken to transport mats and rentals over tracks, adding to expense. |  | 48 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | d. The railway customer refused to work with operations and required permission to work within the railyard. Operations was forced to work nights to meet the railways demands. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RESTORE CKT 18/27/60B COLORADO RIVER CROSSING | HLP/00/1400/TR | P1400.1 Partial Rebuild and Partial Reconductor of 345 kV Ckts. 18A and 27C |  | 7983757.0923 | 2020-03-01 | 9150000 | 2021-01-01 | 13717566.29 | 2023-05-01 | 71.82% | 49.92% | Outages needed to be shortened due to peak approaching which required temporary structures to be put in place and requiring alternate work shifts at premium labor costs to energize on time. Additional temporary easement for west side of river was required with contract reseeding when complete. |  | 49 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability.x | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | d. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | e. Yes, temporary easement was required for temporary work. | f. Project was placed on hold due to outage restrictions. To maintain schedule once outage was acquired, crews had to work overtime. | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/1400/TR | P1400.2 Colorado River Crossing (Structures 27117-27119) |  |  | 2020-08-01 |  | 2021-01-01 |  | 2021-09-01
CBY-AIRTEK CKT87 UPGRADES | HLP/00/1190/TR | P1190.4 Cedar Bayou-WALKER |  | 12077306.7287 | 2020-10-01 | 7452000 | 2021-03-01 | 9291907 | 2021-09-01 | -23.06% | 24.69%
| HLP/00/1190/TR | P1190.2 Ship Channel-ARITEK |  |  | 2017-12-01 |  | 2018-02-01 |  | 2019-12-01
MISSOURI CITY-ADD 3RD XFMR AND 2 FEEDERS | HLP/00/1288/TR | P1288 Missouri City Approach Span |  | 387000 | 2020-10-01 | 459000 | 2021-01-01 | 591088 | 2021-10-01 | 52.74% | 28.78% | Severe weather and flooding resulted in delays and required the use of more mats than initially estimated, increasing labor and equipment costs. |  | 50 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | d. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | f. $11,744 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | e. The storm/flooding variance explanation was incorrectly referenced for “Missouri City-Add 3rd XFMR and 2 Feeders” project. The variance was actually due to the initial MCPR estimate and the updated estimate 30 days prior to construction with further input from the construction team. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A
WEST GALVESTON ADD 3RD 50MVA XFMR | HLP/00/1444/TR | P1444 West Galveston Approach Span |  | 1413217.63 | 2020-10-01 | 2155000 | 2021-01-01 | 1465570 | 2021-11-01 | 3.704% | -31.99%
REBUILD CKT04 MUSTBY-HUD-MONS FOR CLEARANCE | HLP/00/1144/TR | P1349 Clear Creek Crossing |  | 28867774.7394 | 2019-07-01 | 35262000 | 2019-09-02 | 24797917.93 | 2021-12-01 | -14.1% | -29.68%
| HLP/00/1144/TR | P963.1 AMOCO_-MONSAN |  |  | 2016-06-01 |  | 2018-04-01 |  | 2019-04-01
| HLP/00/1144/TR | P963 AMOCO_-Algoa Corner |  |  | 2015-11-01 |  | 2015-11-01 |  | 2019-11-01
JONES CREEK NEW 12KV SUB | HLP/00/1344/TR | P1344 Jones Creek Tap |  | 2384000 | 2020-05-01 | 3266000 | 2021-02-01 | 3545457 | 2021-12-01 | 48.72% | 8.557% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect a difference in estimates related to materials that could have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is 9%. There was a cost increase in the materials that varied from initial estimates. |  | 51 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | d. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | d. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
San Bernard Sub for Danciger Solar | HLP/00/1482/TR/0001 | P1482 San Bernard Substation |  | 1381434.3279 | 2021-10-01 | 1749000 | 2022-03-01 | 1626542.82 | 2023-11-01 | 17.74% | -7.002% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect multiple fluctuations in estimates that have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is -7% |  | 52 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JONTE 138KV SWITCHING STATION | HLP/00/1483/TR | P1483.1 Jonte Sub: Loop 138kV Ckt 86E-2 & 90C-1 near Str 13895 |  | 4679323.6939 | 2022-11-01 | 4679000 | 2022-11-01 | 3673858 | 2024-01-01 | -21.49% | -21.48%
CKT 24 UPGRADES | HLP/00/1503/TR | P1503 Upgrade 138kV Ckt 24B Str 17240 - 17228 |  | 5599000 | 2021-12-01 | 6237000 | 2022-02-01 | 5857322.49 | 2023-11-01 | 4.614% | -6.088%
EXPLORER CORNER | HLP/00/1447/TR | P1002.1 EXPLOR Corner-Channelview | 10000000 | 6315000 | 2021-06-01 | 6315000 | 2021-06-01 | 16657183.77 | 2023-10-01 | 163.8% | 163.8% | Unforseen severe weather caused 2 days of delay, resulting in additional mobilizations and demobilizations of crews. Increasing labor expenses. For reliability reasons, the circuit needed to be energized by the end of the year, which required temporary structures. This increased labor, material, and equipment costs. It also required the use of more mats than anticpated, further increasing labor and equipment costs. The initial estimate was updated to account for final structure weights and class. |  | 53 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | c. The severe weather was not a named storm. | CenterPoint Houston is currently drafting this response and will provide in a later update. | N/A | N/A | N/A
BRAZOS RIVER RELOCATE STRUCTURES | HLP/00/0054/TR/0024 | P1018.1 Brazos River Crossing (Structures 17476-17481) |  | 8559000 | 2021-02-15 | 11740000 | 2021-04-01 | 14656414.62 | 2023-01-30 | 71.24% | 24.84% | Heavy rains caused a private road failure, affecting 1.25 miles along the river. CenterPoint had to repair the stretch of road to move its trucks through. Additional mats were required for repairs or reinforcement of structures which required additional guard services. After the intial cost estimate, CenterPoint determined that the project required bird diverters, required additional 7958ACSR conductor to splice the existing line, and changed the final structure weights. |  | 54 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | N/A | N/A | c. Other solution would be to fully delay the project until ROW is clear to work on without additional mats. This solution would drastically delay schedule and increase costs. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/0054/TR/0024 | P1018.2 Brazos River Crossing (Structures 18983-18988) |  |  | 2021-05-01 |  | 2021-08-01 |  | 2023-01-01
BEARLE NEW CUSTOMER SUBSTATION | HLP/00/0055/TR/0145 | P1031 BEARLE Substation | 1337000 | 818000 | 2021-09-01 | 2286000 | 2021-12-01 | 1580241.49 | 2023-02-01 | 93.18% | -30.87% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect a difference in estimates related to contract labor and transportation costs that could have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is -28% |  | 55 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FORT BEND CITY STRUCTURE RELOCATION | HLP/00/0922/TR/0013 | P1033 Brazos River Crossing (Structures 6449-6453) |  | 6321656.8265 | 2021-09-01 | 7738000 | 2021-12-01 | 6218125.52 | 2022-12-30 | -1.638% | -19.64%
Rebuild/Reconductor Gulfgate Sub Taps | HLP/00/0922/TR/0019 | P1044.1 Gulfgate Tap (North) (Structures 10942-14419) |  | 32867189.5581 | 2021-07-15 | 30054000 | 2021-09-01 | 25781901.56 | 2023-06-01 | -21.56% | -14.21%
| HLP/00/0922/TR/0019 | P1044.2 Gulfgate Tap (South) (Structures 14363-14419) |  |  | 2021-07-15 |  | 2022-01-01 |  | 2023-06-01
138kV Ckt 06F-2: Holmes to Str #11434 | HLP/00/0922/TR/0020 | P1045 Holmes-Plaza | 11379000 | 6125000 | 2021-08-01 | 11379000 | 2021-10-01 | 9342064.71 | 2022-12-30 | 52.52% | -17.9% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect a difference in estimates related to contract labor and transportation costs that could have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is -18% |  | 56 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
REBUILD/RECONDUCTOR LA PORTE SUB TAPS | HLP/00/0922/TR/0021 | P1046.1 Rebuild LaPorte-Sandy Point: Ckt 96F for Hardening |  | 6154000 | 2022-01-01 | 12349000 | 2024-01-01 | 11603381.63 | 2024-01-01 | 88.55% | -6.038% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect a difference in estimates related to materials costs, contract labor and transportation costs, and engineering costs that could have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is -6% |  | 57 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/0922/TR/0021 | P1046.2 La Porte-SYLVAN |  |  | 2021-05-01 |  | 2021-09-06 |  | 2022-12-30
| HLP/00/0922/TR/0021 | P1046.3 SYLVAN-Morgans Point (Structure 12302) |  |  | 2022-07-01 |  | 2022-09-01 |  | 2023-09-01
CKT 32A DUNLAVY-HYDE PARK | HLP/00/0914/TR/0010 | P1069.1 Dunlavy-Hyde Park | 1470000 | 3386000 | 2021-12-01 | 4815000 | 2022-03-17 | 6936045.24 | 2023-12-01 | 104.8% | 44.05% | (1) Severe weather caused multiple mobilizations and demobilizations of crews and required the use of additional mats, increasing labor and equipment rental costs (2) To improve work site efficiency, the wire boat was left on the job site over night, rather than transported to and from the laydown yard. This led to additional security costs. (3) Customer/property requested work to ended early on 2 separate days, resulting in delays that increased labor costs. |  | 58 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | N/A | N/A | c. Other solution would be to fully delay the project until ROW is clear to work on without additional mats. This solution would drastically delay schedule and increase costs. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COLLEGE SUB TAPS | HLP/00/0922/TR/0036 | P1072.1 RB/RC 138kV Ckt 94L-1: College Sub to Str #14333 |  | 13825000 | 2022-08-01 | 18811000 | 2022-08-01 | 16816509.51 | 2024-01-01 | 21.64% | -10.6% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect a difference in estimates related to labor and transportation costs that could have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is -11% |  | 59 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c.The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/0922/TR/0036 | P1072.2 College-College Corner (Structures 35933-35972) |  |  | 2022-05-01 |  | 2022-09-01 |  | 2023-12-01
FOUNDATION REPLACEMENTS - ASR | HLP/00/0801/TR | P875.2 North Belt-King-Jordan |  | 16690000 | 2019-04-01 | 20892000 | 2019-08-01 | 20483306.66 | 2020-07-01 | 22.73% | -1.956% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect multiple fluctuations in estimates that have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is 0%. |  | 60 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | c. CenterPoint Houston did not identify COVID-19 impacts specific to this project. However, as discussed in the direct testimony of Carla Kneipp, David Mercado, Eric Easton and other CenterPoint Houston witnesses, the Company’s operations were generally impacted by the COVID-19 pandemic. COVID-19 impacts that the Company experienced included reduced number and availability of qualified vendors, materials shortages, longer lead-times for equipment and increased material costs. These challenges complicated construction schedules and outage coordination. Additionally, the Company incurred various incremental costs across its operations, including personal protective equipment and cleaning/sanitizing supplies. | d. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | e. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/0801/TR | P875.3 Jeanetta-W.A. Parish |  |  | 2019-04-01 |  | 2019-10-01 |  | 2020-05-01
| HLP/00/0801/TR | P875.4 W.A. Parish-Westchase (Structure 22891) |  |  | 2021-04-01 |  | 2021-09-01 |  | 2022-12-01
| HLP/00/0801/TR | P875.5 Tomball-Singleton-Roans Prairie (Structure 35165) |  |  | 2021-10-01 |  | 2021-12-01 |  | 2023-06-01
| HLP/00/0801/TR | P875.6 Tomball-Singleton-Roans Prairie (Structures 35128-35129) |  |  | 2021-10-01 |  | 2021-12-01 |  | 2023-06-01
| HLP/00/0801/TR | P875.7 Tomball-Singleton-Roans Prairie (Structures 35130-35131) |  |  | 2021-10-01 |  | 2022-01-01 |  | 2023-06-01
Rebuild/Reconductor Lauder Sub Taps | HLP/00/0922/TR/0018 | P923.1 Lauder-North Belt (Structures 18145-32201 and 23301-25538) |  | 25061000 | 2021-11-01 | 48342000 | 2022-03-01 | 36396321.57 | 2023-12-01 | 45.23% | -24.71% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect a difference in labor cost estimates that have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is -25% |  | 61 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/0922/TR/0018 | P923.2 Lauder-Lauder Corner (Structures 25539-23392) |  |  | 2021-07-01 |  | 2021-09-06 |  | 2023-09-01
TNP TOPAZ & PHR-ATTWATER UPGRADES | HLP/00/1468/TR | P1468 P.H. Robinson - TNMP Freeway Park | 2300000 | 2438000 | 2021-02-01 | 7420000 | 2021-04-01 | 4518717 | 2022-12-01 | 85.35% | -39.1% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect a difference in estimates related to contract labor and transportation costs that could have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is -39% |  | 62 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | c. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | d. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BUILD NEW RADIAL FROM ZENITH - VILLAGE C | HLP/00/1472/TR | P1472.1 Zenith-Village Creek | 7730000 | 7210069.9594 | 2022-07-01 | 8144000 | 2022-10-01 | 6200169 | 2023-12-01 | -14.01% | -23.87%
CKT96 DEER PARK TO CA UPGRADE | HLP/00/1428/TR | P1428.1 Morgans Point-Cardiff | 4190000 | 6017000 | 2022-07-01 | 9563000 | 2023-01-01 | 15026197 | 2023-12-01 | 149.7% | 57.13% | Variance due to unanticipated work required by pipeline company: 1) the pipeline company requested additional offset; 2) routing modification resulted in two of the concrete poles no longer being needed and two Temporary poles to remain as permanent; (3) bypass had to be re-engineered, requiring four extra temporary poles, add guy wires, and pull extra wire off structures; 4) and Pipeline companies also requested double layer of mats. |  | 63 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | c. Unplanned modifications resulted in $1.1M in added material and labor charges. | N/A | N/A
FT BEND SOLAR INTERCONNECTION | HLP/00/1395/TR | P1395 Beasly Substation | 11057000 | 4720000 | 2021-05-01 | 4844000 | 2021-07-01 | 6361350.91 | 2023-11-01 | 34.77% | 31.32% | (1) It took longer to acquire a railroad crossing permit than anticpated for reasons beyond CenterPoint's control. This delay led resuled in additional mobilizations and demobilizations. (2) Additionally, the final approved Right of Way required additional mats than initially planned, which all culminated in increased costs. |  | 64 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | d. Operations needed to install mats from a different direction than originally estimated due to ROW constraints. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | c. There were no delays with permits, rather acquisition with drainage easement. | N/A
Jordan-CITIES-DALTON | HLP/00/1448/TR | P1448 Partial Rebuild and Partial Reconductor of 138 kV Ckt. 86I |  | 1809000 | 2020-08-01 | 5003000 | 2021-01-01 | 4799917.72 | 2022-12-01 | 165.3% | -4.059% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect a difference in estimates related to contract labor and transportation costs that could have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is -4% |  | 65 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | c. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | d.The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ENCO Substation | HLP/00/0055/TR/0143 | P1029.1 138 kV Service to ENCO__ Substation within one mile of Ckt. 91A; Partial Reuild of 69 kV Ckt. 53B; Partial Rebuild of 138 kV Ckts. 01B, 06K, 63D and 91A |  | 2167246.5453 | 2020-06-01 | 3346246.5453 | 2020-09-01 | 3326975.56 | 2022-10-01 | 53.51% | -0.5759% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect a difference in estimates related to contract labor and transportation costs and contract engineering and consulting costs that could have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is -1% |  | 66 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | c. CenterPoint Houston did not identify any winter storm Uri impacts specific to this project. However, Winter Storm Uri brought extreme record-breaking winter weather with strong winds, snow, ice, and bitterly cold temperatures to most of the region, including the Company’s service area. In light of this, the impacts from Winter Storm Uri may have impacted the Company’s construction timeline for this project. | N/A | N/A | d.The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/1452/TR/0001 | P1452.1 Upgrade 138kV Ckt 91A Cougar-Gulfgate Tap |  |  | N/A |  | N/A |  | N/A
DUAL PILOT RELAYING | HLP/00/0798/TR | P798.4 CROWN Jefferson (Structures 36614-36617) |  | 1379022.6888 | 2022-07-01 | 4809000 | 2022-10-01 | 3648679.48 | 2023-12-01 | 164.6% | -24.13% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, as well as to provide estimates for additional cost categories. Variance percentage of final total costs vs. final estimate filed in MCPR is -24% |  | 67 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BRAZOS RIVER CROSSING Relocate Str #05429 | HLP/00/0922/TR/0039 | P1078.1 Brazos River Crossing (Structures 35367-35370) |  | 4573000 | 2022-08-01 | 5956000 | 2022-10-01 | 8778580.34 | 2023-12-01 | 91.97% | 47.39% | (1) Material and labor costs significantly increased between the initial estimate and the beginning of construction. (2) The 995ACCS/C7 conductor that was originally estimated was not available, requiring the use of more expensive 973ACCS/C7 conductor. (3) Unanticipated outage scheduling issues resulted in 4 day delay, causing additional mobilization and de-mobilization of crews. This increased labor and equipment rental costs. (4) When crews arrived on site, it was discovered that static arms were bent beyond use. The project was delayed 5 weeks, through holidays, for replacement static arms and pole caps to be installed. |  | 68 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | N/A | N/A | c. There were no other solutions to the static arms being bent upon delivery except for delaying project until they could be replaced. Communicated with manufacturer to expedite order. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BOGGY SUBSTATION | HLP/00/0055/TR/0138 | P1347 BOGGY_ Substation |  | 4514000 | 2020-01-01 | 4761000 | 2020-03-01 | 3035540.22 | 2023-12-01 | -32.75% | -36.24%
DUNVALE TO JEANETTA CKT 05 UPGRADE | HLP/00/1558/TR/0001 | P1558.1 Jeanetta-Structure 26665 |  | 2895741.7335 | 2022-11-01 | 2856000 | 2022-11-01 | 2060406 | 2023-12-01 | -28.85% | -27.86%
BRITMOORE - ADD 3RD XFMR AND 2 FEEDERS | HLP/00/1286/TR | P1286 BRITMOORE SUB: ADD 3RD TRANSFORM |  | 203465 |  | 457196.155 |  | 143265 |  | -29.59% | -68.66%
CLEAR LAKE - ADD 3RD XFMR AND 2 F (Cum.) | HLP/00/1451/TR | P1451 CLEAR LAKE SUB: ADD 3RD XFRM |  | 305199.4878 |  | 305199.4878 |  | 101255.52 |  | -66.82% | -66.82%
ALMEDA-ADD 3RD XFMR AND 3 FEEDERS | HLP/00/1284/TR | P1025 Almeda: Add 3rd Transformer |  | 327686.2279 |  | 327686.2279 |  | 346715.43 |  | 5.807% | 5.807%
NORTHSIDE -ADD 3RD XFMR AND 2 FEEDERS | HLP/00/1252/TR | P1252 Northside Sub Install 3rd Transf |  | 461723 | N/A | 461723 | N/A | 224542 | N/A | -51.37% | -51.37%
SPRINGWOOD-INSTALL 2 XFRS AND 6 FEEDERS | HLP/00/1249/TR | P1249 Springwoods Sub: Install 2-100MVA |  | 370675.0658 | N/A | 370675.0658 | N/A | 152440.59 | N/A | -58.87% | -58.87%
Convert University 69kV Load to 138kV | HLP/00/1123/TR | P916 Line 91H 69kV Converstion at Univer |  | 316563.7478 |  | 316563.7478 |  | 341616.09 |  | 7.914% | 7.914%
DOW Load Increase | HLP/00/0095/TR/0104 | P1137.6 3rd VELASCO SUB CAP BANK (CKT59G |  | 115079 |  | 115079 |  | 102807 |  | -10.66% | -10.66%
RELOCATE STR 10659 | HLP/00/0922/TR/0035 | P1060 Greens Bayou Erosion: Relocate Str #10659 |  | 453000 | 2022-01-01 | 1994000 | 2022-03-01 | 704339.98 | 2023-01-01 | 55.48% | -64.68% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect a difference in estimates related to contract labor and transportation costs that could have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is -65% |  | 69 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TWINWOOD - NEW 35KV SUBSTATION | HLP/00/1417/TR | P1417.1 Twinwood Substation | 14370000 | 219107.392 | 2022-10-03 | 1258000 | 2022-10-03 | 424507.16 | 2024-01-01 | 93.74% | -66.26% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect a difference in estimates related to material costs, contract labor and transportation costs, and engineering and consulting costs that could have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is -66% |  | 70 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DUNLAVY TAP | HLP/00/0914/TR/0009 | P1068.2 Create 138kV Ckt 37A Tap Kirby - Dunlavy |  | 1212832.9321 | 2023-05-01 | 1215000 | 2023-05-01 | 1762005.86 | 2024-01-01 | 45.28% | 45.02% | Additional labor expenses were incurred when towers arrived incorrectly drilled from the manufacturer. Instead of delaying the project to wait on the manufacturer to replace the towers, labor crews made the necessary corrections on site. |  | 71 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | c. Added a week and a half of labor at $175k per additional week, for drilling holes in the poles. This comes out to $262.5K
| HLP/00/0914/TR/0009 | P1068.3 Create 138kV Ckt 09D Tap Heights - Dunlavy |  |  | FUTURE PROJECT
| HLP/00/0914/TR/0009 | P1068.4 Create 69kV HOC-Hyde Park |  |  | FUTURE PROJECT
69KV CKT 34A HEIGHTS-WHITE OAK | HLP/00/0914/TR/0012 | P1067.1 H.O. Clarke-Dunlavy | 17034000 | 12125000 | 2022-04-01 | 15618000 | 2022-11-01 | 14844074.15 | 2024-01-01 | 22.43% | -4.955% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect multiple fluctuations in estimates that have a cumulative impact above 10% as well as to provide accurate estimates for additional items as soon as they were possible to identify. Variance percentage of final total costs vs. final estimate filed in MCPR is -5% |  | 72 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/0914/TR/0012 | P1067.2 Create 69kV Ckt HOC - Dunlavy |  |  | 2022-09-01 |  | 2024-01-01 |  | 2024-01-01
| HLP/00/0914/TR/0012 | P1067.3 Raise 345kV Ckt 72B near Eureka Sub to Prep 138kV Heights Sub |  |  | FUTURE PROJECT
| HLP/00/0914/TR/0012 | P1067.4 Convert Heights Sub: Loop 138kV Ckt 09D |  |  | FUTURE PROJECT
138KV CKT 37C TECO-GARROTT | HLP/00/0922/TR/0032 | P1057 TECO-Blodgett |  | 15906000 | 2022-10-01 | 23423000 | 2023-01-01 | 24289077 | 2024-01-01 | 52.7% | 3.698% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect a difference in estimates related to costs of materials that could have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is 4% |  | 73 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CKT 24 DUNVALE - WESTCHASE | HLP/00/1553/TR | P1553.1 Upgrade 138kV Ckt 24B-1: Str #17304-17240 | 6160000 | 11207939.0485 | 2022-11-01 | 12095000 | 2023-01-01 | 12833899.66 | 2024-01-01 | 14.51% | 6.109% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which as in this case, may reflect fluctuations in cost which have a cumulartive impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is 6% |  | 74 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MOODY-STEWART CKT 63C-4 | HLP/00/0922/TR/0008 | P1016 STEWRT-Moody | 6568353 | 14971000 | 2021-08-01 | 34236000 | 2021-10-01 | 26585653.26 | 2024-01-01 | 77.58% | -22.35% | The MCPR filing process entails having as complete of an estimate, as available, to move forward with intial filing, but allowing flexibility for refinement within one month of construction starting. While working within PUC guidelines, project estimate was updated with construction team's input prior to 30 days before construction, which may reflect a difference in estimates related to cost of materials and contract labor and transportation costs that could have a cumulative impact above 10%. Variance percentage of final total costs vs. final estimate filed in MCPR is -22% |  | 75 | b. A contingency of 10% was added to construction material and labor to account for possible tariffs, labor increases, material increases, and other cost variability. | N/A | N/A | N/A | N/A | c. The feedback from construction did not require a change in scope. The feedback from construction after additional analysis and available information resulted in updated and more refined estimates of additional labor and/or materials (and associated costs) that weren’t in the original estimate. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| HLP/00/0922/TR/0008 | P1016.1 Stewart-Moody (Structures 34764-34786) |  |  | 2021-11-01 |  | 2022-01-03 |  | 2024-01-01