## Clemville Tap - El Campo
Region Name | OPCO Name | Line Object ID | Line Name | Structure Object ID | Inspection Type | Inspection Start Date | Inspection End Date | Work Order | Inspection Status | Structure Number | Structure Material | State | Inspection Area | Inspection Date | Inspector | Assessment | Condition Type | First Component | Second Component | Condition | Condition Category | Condition Status | Condition Notes | Inspection Notes
Corpus Christi | Texas Central Co. | 281326 | Clemville Tap - El Campo | 20006920 | Comprehensive Walking Inspection | 2020-01-01 | 2020-12-31 | TL0037793 | Closed | 22 | Wood | TX | TCC | 2020-11-19 22:33 | Michael D Hardin | Condition | Structure | Pole |  | Rot Heart | A3 | Reported | 11/11/2020 21:25:54 c355781 Michael Hardin Discover LOC NOTES: Conductor Height at LOC (ft): LOC Object Height (ft): Distance between Conductor and LOC Object (ft): Ambient Temp (F): Wind Speed (mph): Owner of Utility Undercrossing: LOC Comments: | 3/24/2020 4:16:09 PM Theresa Perez 2020 CGI

## Clemville Tap - Clemville
Region Name | OPCO Name | Line Object ID | Line Name | Structure Object ID | Inspection Type | Inspection Start Date | Inspection End Date | Work Order | Inspection Status | Structure Number | Structure Material | State | Inspection Area | Inspection Date | Inspector | Assessment | Condition Type | First Component | Second Component | Condition | Condition Category | Condition Status | Condition Notes | Inspection Notes
Corpus Christi | Texas Central Co. | 280638 | Clemville Tap - Clemville | 20036136 | Comprehensive Walking Inspection | 2020-01-01 | 2020-12-31 | TL0037792 | Closed | 2/16 | Wood | TX | TCC | 2020-10-22 16:40 | Jose L Cavazos | Condition | Structure | Pole |  | Rot Heart | A2 | Reported | 10/22/2020 16:39:56 ctsof37 Jose Cavazos Discover | 3/24/2020 4:14:18 PM Theresa Perez 2020 CGI

## CST Tap - Midfield STEC
Region Name | OPCO Name | Line Object ID | Line Name | Structure Object ID | Inspection Type | Inspection Start Date | Inspection End Date | Work Order | Inspection Status | Structure Number | Structure Material | State | Inspection Area | Inspection Date | Inspector | Assessment | Condition Type | First Component | Second Component | Condition | Condition Category | Condition Status | Condition Notes | Inspection Notes
Corpus Christi | Texas Central Co. | 280894 | CST Tap - STEC Midfield West | 19499432 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044876 | Active | 22 | Wood | TX | TCC | 2022-06-14 14:10 | Joel A Hilburn | Condition | Structure | Conductor Hdw | Clamp - Susp (Conductor) | Rust Heavy | A2 | Reported | 06/13/2022 19:40:15 s197085 Joel Hilburn Discover | 10/7/2021 1:21:49 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 280894 | CST Tap - STEC Midfield West | 19499432 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044876 | Active | 22 | Wood | TX | TCC | 2022-06-14 14:10 | Joel A Hilburn | Condition | Structure | Insulator | Insulator - Susp | Rust Heavy | A2 | Reported | 06/13/2022 19:40:15 s197085 Joel Hilburn Discover | 10/7/2021 1:21:49 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 280894 | CST Tap - STEC Midfield West | 19499528 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044876 | Active | 23 | Wood | TX | TCC | 2022-06-14 15:06 | Joel A Hilburn | Condition | Structure | Conductor Hdw | Clamp - Susp (Conductor) | Rust Heavy | A2 | Reported | 06/13/2022 19:40:20 s197085 Joel Hilburn Discover | 10/7/2021 1:21:49 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 280894 | CST Tap - STEC Midfield West | 19499528 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044876 | Active | 23 | Wood | TX | TCC | 2022-06-14 15:06 | Joel A Hilburn | Condition | Structure | Crossarm |  | Rot Heart | A2 | Reported | 06/13/2022 19:40:20 s197085 Joel Hilburn Discover | 10/7/2021 1:21:49 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 280894 | CST Tap - STEC Midfield West | 19499528 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044876 | Active | 23 | Wood | TX | TCC | 2022-06-14 15:06 | Joel A Hilburn | Condition | Structure | Insulator | Insulator - Susp | Rust Heavy | A2 | Reported | 06/13/2022 19:40:20 s197085 Joel Hilburn Discover | 10/7/2021 1:21:49 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 280894 | CST Tap - STEC Midfield West | 19500296 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044876 | Active | 28 or 2/10 | Wood | TX | TCC | 2022-10-13 09:35 | Joel A Hilburn | Skip | [7 empty] | 10/7/2021 1:21:49 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 280894 | CST Tap - STEC Midfield West | 19500408 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044876 | Active | 29 | Wood | TX | TCC | 2022-06-13 19:41 | Joel A Hilburn | No Condition | [7 empty] | 10/7/2021 1:21:49 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 280894 | CST Tap - STEC Midfield West | 19501080 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044876 | Active | 35 | Wood | TX | TCC | 2022-06-14 14:31 | Joel A Hilburn | Condition | Structure | Crossarm |  | Rot Heart | A3 | Reported | 06/13/2022 19:41:39 s197085 Joel Hilburn Discover | 10/7/2021 1:21:49 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 280894 | CST Tap - STEC Midfield West | 19501192 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044876 | Active | 36 | Wood | TX | TCC | 2022-06-14 15:10 | Joel A Hilburn | Condition | Structure | Conductor Hdw | Clamp - Susp (Conductor) | Rust Heavy | A2 | Reported | 06/13/2022 19:41:44 s197085 Joel Hilburn Discover | 10/7/2021 1:21:49 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 280894 | CST Tap - STEC Midfield West | 19501192 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044876 | Active | 36 | Wood | TX | TCC | 2022-06-14 15:10 | Joel A Hilburn | Condition | Structure | Crossarm |  | Rot Heart | A2 | Reported | 06/13/2022 19:41:44 s197085 Joel Hilburn Discover | 10/7/2021 1:21:49 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 280894 | CST Tap - STEC Midfield West | 19501192 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044876 | Active | 36 | Wood | TX | TCC | 2022-06-14 15:10 | Joel A Hilburn | Condition | Structure | Insulator | Insulator - Susp | Rust Heavy | A2 | Reported | 06/13/2022 19:41:44 s197085 Joel Hilburn Discover | 10/7/2021 1:21:49 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 280894 | CST Tap - STEC Midfield West | 19501336 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044876 | Active | 37 or 3/1 | Wood | TX | TCC | 2022-06-13 19:42 | Joel A Hilburn | No Condition | [7 empty] | 10/7/2021 1:21:49 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 280894 | CST Tap - STEC Midfield West | 19501448 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044876 | Active | 38 | Wood | TX | TCC | 2022-06-14 14:22 | Joel A Hilburn | Condition | Structure | Conductor Hdw | Clamp - Susp (Conductor) | Rust Heavy | A3 | Reported | 06/13/2022 19:41:49 s197085 Joel Hilburn Discover | 10/7/2021 1:21:49 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 280894 | CST Tap - STEC Midfield West | 19501448 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044876 | Active | 38 | Wood | TX | TCC | 2022-06-14 14:22 | Joel A Hilburn | Condition | Structure | Insulator | Insulator - Susp | Rust | A3 | Reported | 06/13/2022 19:41:49 s197085 Joel Hilburn Discover | 10/7/2021 1:21:49 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 280894 | CST Tap - STEC Midfield West | 19501592 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044876 | Active | 39 | Wood | TX | TCC | 2022-06-14 14:39 | Joel A Hilburn | Condition | Structure | Conductor Hdw | Clamp - Susp (Conductor) | Rust | A3 | Reported | 06/13/2022 19:41:52 s197085 Joel Hilburn Discover | 10/7/2021 1:21:49 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 280894 | CST Tap - STEC Midfield West | 19501592 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044876 | Active | 39 | Wood | TX | TCC | 2022-06-14 14:39 | Joel A Hilburn | Condition | Structure | Crossarm |  | Rot Heart | A2 | Reported | 06/13/2022 19:41:52 s197085 Joel Hilburn Discover | 10/7/2021 1:21:49 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 280894 | CST Tap - STEC Midfield West | 19501672 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044876 | Active | 40 | Wood | TX | TCC | 2022-06-13 19:42 | Joel A Hilburn | No Condition | [7 empty] | 10/7/2021 1:21:49 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 280894 | CST Tap - STEC Midfield West | 19507768 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044876 | Active | 69 | Wood | TX | TCC | 2022-10-13 09:35 | Joel A Hilburn | Skip | [7 empty] | 10/7/2021 1:21:49 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 280894 | CST Tap - STEC Midfield West | 19507896 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044876 | Active | 70 | Wood | TX | TCC | 2022-06-15 15:04 | Joel A Hilburn | Condition | Structure | Conductor Hdw | Clamp - Susp (Conductor) | Rust Heavy | A2 | Reported | 06/14/2022 18:01:38 s197085 Joel Hilburn Discover | 10/7/2021 1:21:49 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 280894 | CST Tap - STEC Midfield West | 19507896 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044876 | Active | 70 | Wood | TX | TCC | 2022-06-15 15:04 | Joel A Hilburn | Condition | Structure | Insulator | Insulator - Susp | Rust Heavy | A2 | Reported | 06/14/2022 18:01:38 s197085 Joel Hilburn Discover | 10/7/2021 1:21:49 PM Adam Pearson 2022 CWI

## Blessing - Coastal States Tap
Region Name | OPCO Name | Line Object ID | Line Name | Structure Object ID | Inspection Type | Inspection Start Date | Inspection End Date | Work Order | Inspection Status | Structure Number | Structure Material | State | Inspection Area | Inspection Date | Inspector | Assessment | Condition Type | First Component | Second Component | Condition | Condition Category | Condition Status | Condition Notes | Inspection Notes
Corpus Christi | Texas Central Co. | 280622 | Blessing - Coastal States Tap | 20045208 | Comprehensive Walking Inspection | 2020-01-01 | 2020-12-31 | TL0037790 | Closed | 18/16 | Wood | TX | TCC | 2022-01-25 11:25 | Javier Mejia | Condition | Structure | Conductor Hdw | Clamp - Susp (Conductor) | Rust | B | Reported | 10/29/2020 15:19:52 s275000 Javier Mejia Discover | 3/24/2020 3:42:11 PM Theresa Perez 2020 CGI
Corpus Christi | Texas Central Co. | 280622 | Blessing - Coastal States Tap | 20045208 | Comprehensive Walking Inspection | 2020-01-01 | 2020-12-31 | TL0037790 | Closed | 18/16 | Wood | TX | TCC | 2022-01-25 11:25 | Javier Mejia | Condition | Structure | Insulator | Insulator - Susp | Rust | A2 | Completed by AEP | 10/29/2020 15:19:52 s275000 Javier Mejia Discover 01/25/2022 10:25:24 S186532 Trent Kainer Update 12/05/2022 00:00:00 S186532 Trent Kainer Complete | 3/24/2020 3:42:11 PM Theresa Perez 2020 CGI
Corpus Christi | Texas Central Co. | 280622 | Blessing - Coastal States Tap | 20047912 | Comprehensive Walking Inspection | 2020-01-01 | 2020-12-31 | TL0037790 | Closed | 21/5 | Wood | TX | TCC | 2020-10-29 01:05 | Javier Mejia | No Condition | [7 empty] | 3/24/2020 3:42:11 PM Theresa Perez 2020 CGI

## El Campo - Ganado
Region Name | OPCO Name | Line Object ID | Line Name | Structure Object ID | Inspection Type | Inspection Start Date | Inspection End Date | Work Order | Inspection Status | Structure Number | Structure Material | State | Inspection Area | Inspection Date | Inspector | Assessment | Condition Type | First Component | Second Component | Condition | Condition Category | Condition Status | Condition Notes | Inspection Notes
Corpus Christi | Texas Central Co. | 281566 | Ganado - El Campo | 19716200 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044873 | Active | 37/2 |  | TX | TCC | 2022-06-13 13:00 | Joel A Hilburn | Condition | Structure | Crossarm |  | Rot Heart | A2 | Reported | 06/09/2022 22:10:12 s197085 Joel Hilburn Discover Conductor on arm. 38? arm? Road crossing. 2 distribution crossing | 10/7/2021 1:33:40 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 281566 | Ganado - El Campo | 19716200 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044873 | Active | 37/2 |  | TX | TCC | 2022-06-13 13:00 | Joel A Hilburn | Condition | Structure | Crossarm |  | Rot Heart | A2 | Reported | 06/09/2022 22:10:12 s197085 Joel Hilburn Discover Shield wire arm. 14?6?pole spacing. Static on pole. | 10/7/2021 1:33:40 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 281566 | Ganado - El Campo | 19723096 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044873 | Active | 40/5 |  | TX | TCC | 2022-06-13 13:12 | Joel A Hilburn | Condition | Structure | X-Brace |  | Cracked | A3 | Reported | 06/09/2022 22:11:57 s197085 Joel Hilburn Discover 1/2 x brace WPH | 10/7/2021 1:33:40 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 281566 | Ganado - El Campo | 19731736 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044873 | Active | 45/1 |  | TX | TCC | 2022-06-10 04:24 | Joel A Hilburn | Condition | Structure | X-Brace |  | Broken | A2 | Reported | 06/06/2022 19:58:41 s197085 Joel Hilburn Discover 1/2 x brace broken | 10/7/2021 1:33:40 PM Adam Pearson 2022 CWI
Corpus Christi | Texas Central Co. | 281566 | Ganado - El Campo | 19739592 | Comprehensive Walking Inspection | 2022-01-01 | 2022-12-31 | TL0044873 | Active | 51/2 |  | TX | TCC | [10 empty] | 10/7/2021 1:33:40 PM Adam Pearson 2022 CWI