## Line Crew Resource Tracker
Event: Hurricane Beryl
EVENT: | Hurricane |  | Date / Time: | 2024-07-05 | [11 empty] | Comments
Resources Requested
Resource Type Requested - Date / Time |  |  |  | Distribution Line | Line Crews |  |  |  | Destination | Latest Arrival |  |  |  |  | GENERAL COMMENTS
Distribution Line - 07/5/24 15:00 |  |  |  | 1028 | 257 |  |  |  | Robstown, TX
Distribution Line - 7/6/2024 16:00 |  |  |  | *164 | *41 |  |  |  | Robstown, TX | 2024-07-09 12:00 |  |  |  |  | Request canceled 7/7/24 8:00
Distribution Line -
Total Requested |  |  |  | 1028 | 257 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Resources Acquired
Source Company |  | Company, Contractor, IOU, Baseload | Departure Location | Distribution Line | Line Crews | Support Personnel | General Foreman | GF Cell Number | Destination | ETA | Visible in ARCOS | OPCO Contact Made?
SWEPCo - Chain Electric (Sunday) |  | Baseload | SWEPCo | 30 | 6 | 2 | Chris Jackson |  | Robstown, TX | 2024-07-07 14:00 | Yes
Chain Electric (Sunday) |  | Contractor | San Antonio, TX | 9 | 2 | 2 | Alefredo Delafuente |  | Robstown, TX | 2024-07-07 12:00 | Yes
Chain Electric (Sunday) |  | Contractor | Franklin, LA | 22 | 5 | 0 | Matt Miley |  | Robstown, TX | 2024-07-07 12:00 | Yes
Chain Electric (Sunday) |  | Contractor | Baton Rouge, LA | 9 | 2 | 2 | Doug Armstrong |  | Robstown, TX | 2024-07-07 12:00 | Yes
Chain Electric (Sunday) |  | Contractor | Lucedale, MS | 22 | 4 | 4 | Blake Jones |  | Robstown, TX | 2024-07-07 12:00 | Yes
Davis H Elliot (Monday) |  | Contractor | Bowling Green, KY | 20 | 4 | 1 | Lloyd Ellis |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Davis H Elliot (Monday) |  | Contractor | Dickson, TN | 16 | 4 | 1 | Kenneth Medley |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Davis H Elliot (Monday) |  | Contractor | Memphis, TN | 25 | 5 | 2 | Willie Sampley |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Davis H Elliot (Monday) |  | Contractor | Memphis, TN | 25 | 5 | 0 | Blake Reed |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Davis H Elliot (Monday) |  | Contractor | Nashville, TN | 10 | 5 | 1 | Bill Harrison |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Davis H Elliot (Monday) |  | Contractor | Chatanooga, TN | 10 | 3 | 1 | Brian McBroom |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Davis H Elliot (Monday) |  | Contractor | Evansville, IN | 20 | 5 | 2 | Brian Cox |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Davis H Elliot (Monday) |  | Contractor | McKee, KY | 25 | 5 | 1 | David Means |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Davis H Elliot (Monday) |  | Contractor | Somerset, KY | 25 | 5 | 1 | Devin Burton |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Davis H Elliot (Monday) |  | Contractor | Shelbyville, KY | 24 | 5 | 1 | Justin Martin |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Davis H Elliot (Monday) |  | Contractor | Tulsa, OK | 27 | 6 | 1 | Brandon Kester |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Linetec (Sunday) |  | Contractor | Johnson City, TX | 30 | 6 | 2 | Eric Clausen |  | Robstown, TX | 2024-07-07 12:00 | Yes
Linetec (Sunday) |  | Contractor | Alexandria, LA | 27 | 6 | 0 | Brandon Franks |  | Robstown, TX | 2024-07-07 12:00 | Yes
Linetec (Sunday) |  | Contractor | Sikeston, MO | 20 | 4 | 1 | James Cooper |  | Robstown, TX | 2024-07-07 12:00 | Yes
Linetec (Sunday) |  | Contractor | Douglasville, GA | 15 | 3 | 3 | Steven Taylor |  | Robstown, TX | 2024-07-07 12:00 | Yes
Linetec (Sunday) |  | Contractor | Douglasville, GA | 15 | 3 | 1 | Mark Pagett |  | Robstown, TX | 2024-07-07 12:00 | Yes
Riggs-Distler (Monday) |  | Contractor | Alexandria, LA | 10 | 2 | 2 | Dave Countess |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Riggs-Distler (Monday) |  | Contractor | Alexandria, LA | 15 | 3 | 1 | Jason O'Dell |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Northstar (Sunday) |  | Contractor | Princeton, TX | 5 | 1 | 0 | Dan Filkins |  | Robstown, TX | 2024-07-07 15:00 | Yes
Northstar (Sunday) |  | Contractor | Texarkana, TX | 5 | 1 | 0 | Greg Bradshaw |  | Robstown, TX | 2024-07-07 15:00 | Yes
3S (Monday) |  | Contractor | Midland, TX | 20 | 4 | 1 | Waylon Gore |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Axis Power (Monday) |  | Contractor | Weatherford, TX | 32 | 6 | 2 | Michael Graham |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Axis Power (Monday) |  | Contractor | Denham Springs, LA | 26 | 5 | 1 | Freddy Chavez |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
AMP Power (Monday) |  | Contractor | Sequin, TX | 38 | 8 | 1 | Jesus Cruz |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
AMP Power (Monday) |  | Contractor | Sequin, TX | 17 | 4 | 1 | Jonathan Lavy |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Grid Co (Monday) |  | Contractor | Huntsville, AL | 40 | 7 | 5 | Slade Guthrie |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Force Electrical (Sunday) |  | Contractor | OKC | 11 | 2 | 1 | Wes Heffner |  | Robstown, TX | 2024-07-07 12:00 | Yes
Tempest - MDR (Monday) |  | Contractor | Tylertown, MS | 16 | 3 | 1 | Brian Bramlett |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Tempest - MDR (Monday) |  | Contractor | Tylertown, MS | 11 | 2 | 1 | Allen Ball |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Tempest - MDR (Monday) |  | Contractor | Tylertown, MS | 30 | 5 | 1 | Allen White |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Tempest - MDR (Monday) |  | Contractor | Ozark, AR | 17 | 3 | 1 | Troy Bigham |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Tempest - MDR (Monday) |  | Contractor | Ozark, AR | 12 | 2 | 1 | Brandon Linville |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Tempest - MDR (Monday) |  | Contractor | Texarkana, AR | 17 | 3 | 1 | Jackie Peach |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Tempest - MDR (Monday) |  | Contractor | Texarkana, AR | 13 | 2 | 1 | James Wickizer |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Tempest - MDR (Monday) |  | Contractor | Wiggins, MS | 12 | 2 | 1 | Jeff Barber |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Tempest - MDR (Monday) |  | Contractor | Wiggins, MS | 12 | 2 | 1 | Chris Jones |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Tempest - MDR (Monday) |  | Contractor | Greenwood, MS | 18 | 3 | 1 | Danny Lewis |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Tempest - MDR (Monday) |  | Contractor | Greenwood, MS | 13 | 2 | 1 | Anthony Anderson |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Tempest - MDR (Monday) |  | Contractor | Lucedale, MS | 26 | 5 | 1 | Marco Jordan |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Tempest - MDR (Monday) |  | Contractor | Olive Branch, MS | 26 | 5 | 1 | Curtis Chisholm |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Tempest On-Site Mgt |  | Contractor | Covington, LA |  |  | 4 | Anthony Bramlett |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Bird Electric - Brave (Kerney Pipken 254-721-1579) |  | Contractor | Andrews, TX | 27 | 5 | 3 | Javier Peralta |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Bird Electric - Brexan (Kerney Pipken 254-721-1579) |  | Contractor | Mineola, TX | 29 | 5 | 1 | Bradly Martin |  | Robstown, TX | 2024-07-07 12:00 | Yes
Bird Electric - Power Standard (Kerney Pipken 254-721-1579) |  | Contractor | Krum, TX | 32 | 6 | 1 | Luis Aguilar |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Bird Electric - JAB (Kerney Pipken 254-721-1579) |  | Contractor | Big Springs, TX | 10 | 2 | 0 | Gerado Luquis |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Bird Electric - Dept 34 (Kerney Pipken 254-721-1579) |  | Contractor | Winnsboro. LA | 12 | 2 | 0 | Chrsitian Sykes |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Bird Electric - Dept 33 (Kerney Pipken 254-721-1579) |  | Contractor | Hattiesburg, MS | 11 | 2 | 0 | Stephen Ray |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Bird Electric (Tuesday) |  | Contractror |  | *160 | *40 |  |  |  | Robstown, TX | 2024-07-09 12:00 |  |  |  |  | Request canceled 7/7/24 8:00
Hugo Garcia Electric |  | Contractror | Laredo, TX | 4 | 1 | 1 | Fausto Zamarripa |  | Bay City, TX | 2024-07-09 20:00 | Yes |  |  |  | Vac Trailer
↑ WAVE 1 ABOVE ↑
Total Acquired |  |  |  | 993 | 198 | 67 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Excess/Gap |  |  |  | -35 | -59 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEGEND: Red background indicates all FTE's released. Bright Yellow background indicates RMAG notification required upon release.
Staging Sites

## Svc Team Resource Tracker
Event: Hurricane Beryl
EVENT: | Hurricane |  | Date / Time: | 2024-07-05 | [11 empty] | Comments
Resources Requested
Resource Type Requested - Date / Time |  |  |  | Distribution Line | Svc Teams |  |  |  | Destination | Latest Arrival |  |  |  |  | GENERAL COMMENTS
Service Line - 07/5/24 15:00 |  |  |  | 572 | 286 |  |  |  | Robstown, TX
Service Line - 7/6/2024 16:00 |  |  |  | *110 | *55 |  |  |  | Robstown, TX | [5 empty] | Request canceled 7/7/24 8:00
Service Line
Total Requested |  |  |  | 572 | 286 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Resources Acquired
Source Company |  | Company, Contractor, IOU, Baseload | Departure Location | Distribution Line | Svc Teams | Support Personnel | General Foreman | GF Cell Number | Destination | ETA | Visible in ARCOS | OPCO Contact Made?
PSO -Linetec |  | Baseload | Oklahoma | 44 | 22 | 1 | Steven Roberts |  | Robstown, TX | 2024-07-07 12:00 | Yes
PSO - Force Electrical |  | Baseload | Oklahoma | 30 | 15 | 3 | James Hill (PSO) |  | Robstown, TX | 2024-07-07 15:00 | Yes
PSO - SEC Svc Teams |  | Baseload | Oklahoma | 24 | 12 | 3 | Greg Mullins |  | Robstown, TX | 2024-07-07 15:00 | Yes
PSO Svc Teams |  | Company | Oklahoma | 18 | 9 | 9 | Victor Landin |  | Robstown, TX | 2024-07-07 12:00 | Yes
SWEPCo Svc Teams |  | Company | SWEPCo | 60 | 30 | 18 | Todd Nottingham |  | Robstown, TX | 2024-07-07 15:00 | Yes
PSO-DHE |  | Baseload | Oklahoma | 60 | 30 | 3 | Armando Gonzalez |  | Robstown, TX | 2024-07-07 15:00 | Yes
I&M |  | Company | Indiana | 40 | 20 | 14 | Jared Stork |  | Robstown, TX |  | Yes
AEP-Ohio |  | Company | Ohio | 114 | 57 | 10 | David Booth |  | Robstown, TX |  | Yes
I&M - ACC |  | Baseload | Indiana | 60 | 30 | 5 | Jonathan Spohr |  | Robstown, TX | 2024-07-07 19:00 | Yes
I&M - AMPP |  | Baseload | Indiana | 24 | 12 | 1 | Jose Sanchez |  | Robstown, TX | 2024-07-07 19:00 | Yes
↑ WAVE 1 ABOVE ↑
Total Acquired |  |  |  | 474 | 237 | 67 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Excess/Gap |  |  |  | -98 | -49 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEGEND: Red background indicates all FTE's released. Bright Yellow background indicates RMAG notification required upon release.
Staging Sites

## Damage Assessor Tracker
Event: Hurricane Beryl
EVENT: | Hurricane |  | Date / Time: | 2024-07-05 | [11 empty] | Comments
Resources Requested
Resource Type Requested - Date / Time |  |  |  | Assessors | Teams |  |  |  | Destination | Latest Arrival |  |  |  |  | GENERAL COMMENTS
Damage Assessors - 07/5/24 15:00 |  |  |  | 600 | 300
Damage Assessors
Damage Assessors
Total Requested |  |  |  | 600 | 300 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Resources Acquired
Source Company |  | Company, Contractor, IOU, Baseload | Departure Location | Assessors | Teams | Support Personnel | Team Lead | Team Lead Cell Number | Destination | ETA | Visible in ARCOS | OPCO Contact Made?
SWEPCo DA |  | Company | SWEPCo | 18 | 9 | 0 | Todd Nottingham |  | Robstown, TX | 2024-07-07 12:00 | Yes
TechServ (Sunday) (Rob Johnson 304-644-5213) |  | Contractor | Texas | 18 | 11 | 1 | JD Kinsey |  | Robstown, TX | 2024-07-07 12:00 | Yes
TechServ (Sunday) (Rob Johnson 304-644-5213) |  | Contractor | Texas | 20 | 10 | 0 | Hunter Thurston |  | Robstown, TX | 2024-07-07 12:00 | Yes
TechServ (Sunday) (Rob Johnson 304-644-5213) |  | Contractor | Texas | 24 | 12 | 0 | Jason Bandy |  | Robstown, TX | 2024-07-07 12:00 | Yes
TechServ (Sunday) (Rob Johnson 304-644-5213) |  | Contractor | Texas | 22 | 11 | 0 | Brian Avants |  | Robstown, TX | 2024-07-07 12:00 | Yes
TechServ (Sunday) (Rob Johnson 304-644-5213) |  | Contractor | Various | 18 | 9 | 0 | Leighton Piper |  | Robstown, TX | 2024-07-07 12:00 | Yes
TechServ (Sunday) (Rob Johnson 304-644-5213) |  | Contractor | Various | 10 | 5 | 0 | Tim Taylor |  | Robstown, TX | 2024-07-07 12:00 | Yes
TechServ (Sunday) (Rob Johnson 304-644-5213) |  | Contractor | Texas | 20 | 10 | 0 | Greg Petzold |  | Robstown, TX | 2024-07-07 12:00 | Yes
TechServ (Sunday) (Rob Johnson 304-644-5213) |  | Contractor | LA | 30 | 15 | 0 | Randy Henry |  | Robstown, TX | 2024-07-07 12:00 | Yes
TechServ (Sunday) (Rob Johnson 304-644-5213) |  | Contractor | Various | 20 | 10 | 0 | Keith Grooms |  | Robstown, TX | 2024-07-07 12:00 | Yes
TechServ (Sunday) (Rob Johnson 304-644-5213) |  | Contractor | Various | 20 | 10 | 0 | John McCormick |  | Robstown, TX | 2024-07-07 12:00 | Yes
TechServ (Sunday) (Rob Johnson 304-644-5213) |  | Contractor | Florida | 18 | 9 | 0 | Gerald McCormick |  | Robstown, TX | 2024-07-07 12:00 | Yes
TechServ (Sunday) (Rob Johnson 304-644-5213) |  | Contractor | Various | 20 | 10 | 0 | Damon Hancock |  | Robstown, TX | 2024-07-07 12:00 | Yes
TechServ (Sunday) (Rob Johnson 304-644-5213) |  | Contractor | Various | 16 | 8 | 0 | Bryant Collins |  | Robstown, TX | 2024-07-07 12:00 | Yes
TechServ (Sunday) (Rob Johnson 304-644-5213) |  | Contractor | Various | 24 | 12 | 0 | Nathan Morrison |  | Robstown, TX | 2024-07-07 12:00 | Yes
TechServ (Sunday) (Rob Johnson 304-644-5213) |  | Contractor | Various | 24 | 12 | 0 | Patrick Gomez |  | Robstown, TX | 2024-07-07 12:00 | Yes
Utility Power (Sunday) (Terry Sears 817-688-7897) |  | Contractor | Meridian, TX | 24 | 12 | 2 | Freddy Lovell |  | Robstown, TX | 2024-07-07 12:00 | Yes
Utility Power (Sunday) (Terry Sears 817-688-7897) |  | Contractor | Weatherford, TX | 24 | 12 | 0 | Wesley Wright |  | Robstown, TX | 2024-07-07 12:00 | Yes
Utility Power (Sunday) (Terry Sears 817-688-7897) |  | Contractor | Gladewater, TX | 22 | 11 | 0 | Anthony Cox |  | Robstown, TX | 2024-07-07 12:00 | Yes
DRG (Sunday) (Charles Harris 870-365-3536) |  | Contractor | Mountainville, AR | 14 | 7 | 2 | Keith Jessen |  | Robstown, TX | 2024-07-07 12:00 | Yes
DRG (Sunday) (Charles Harris 870-365-3536) |  | Contractor | Kirbyville, MO | 16 | 8 | 0 | John Bruns |  | Robstown, TX | 2024-07-07 12:00 | Yes
DRG (Sunday) (Charles Harris 870-365-3536) |  | Contractor | Jerseyville, IL | 10 | 5 | 0 | Joseph Steckel |  | Robstown, TX | 2024-07-07 12:00 | Yes
DRG (Sunday) (Charles Harris 870-365-3536) |  | Contractor | Potosi, MO | 20 | 10 | 0 | Anthony Lauglin |  | Robstown, TX | 2024-07-07 12:00 | Yes
DRG (Monday) (Charles Harris 870-365-3536) |  | Contractor | Salem, AL | 16 | 8 | 0 | Stephen Lewis |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
DRG (Monday) (Charles Harris 870-365-3536) |  | Contractor | Port St. Joe, FL | 22 | 11 | 0 | Walden Price |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
DRG (Monday) (Charles Harris 870-365-3536) |  | Contractor | Clarksville, TN | 8 | 4 | 0 | Randy Price |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
DRG (Monday) (Charles Harris 870-365-3536) |  | Contractor | Jefferson, LA | 4 | 2 | 0 | Clinton Dickens |  | Within 3 hrs of CC | 2024-07-08 07:00 | Yes
Storm Services (Steven Craig 228-380-5952) |  | Contractor | Pass Christian, MS | 8 | 4 | 2 | Merritt Randal Castello |  | Robstown, TX | 2024-07-07 12:00 | Yes
Storm Services (Steven Craig 228-380-5952) |  | Contractor | Moselle, MS | 22 | 11 | 0 | Ronald Ladner |  | Robstown, TX | 2024-07-07 12:00 | Yes
Storm Services (Steven Craig 228-380-5952) |  | Contractor | Mobile, AL | 16 | 8 | 0 | Ricky Lynn Russell |  | Robstown, TX | 2024-07-07 12:00 | Yes
Storm Services (Steven Craig 228-380-5952) |  | Contractor | Lucedale, MS | 12 | 6 | 0 | Jason Le Fallon |  | Robstown, TX | 2024-07-07 12:00 | Yes
Storm Services (Steven Craig 228-380-5952) |  | Contractor | Orange, TX | 20 | 10 | 0 | Nick Pervan |  | Robstown, TX | 2024-07-07 12:00 | Yes
Storm Services (Steven Craig 228-380-5952) |  | Contractor | Chatham, LA | 10 | 5 | 0 | Harold Pickering |  | Robstown, TX | 2024-07-07 12:00 | Yes
Storm Services (Steven Craig 228-380-5952) |  | Contractor | Pearl River, LA | 6 | 3 | 0 | Michael Creel |  | Robstown, TX | 2024-07-07 12:00 | Yes
Storm Services (Steven Craig 228-380-5952) |  | Contractor | Pace, FL | 8 | 4 | 0 | Stephen Howell |  | Robstown, TX | 2024-07-07 12:00 | Yes
PSO |  | Company | PSO | 2 | 1 | 0 | Bailey Magby |  | Robstown, TX | 2024-07-07 12:00 | Yes
↑ WAVE 1 ABOVE ↑
Total Acquired |  |  |  | 606 | 305 | 7 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Excess/Gap |  |  |  | 6 | 5 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEGEND: Red background indicates all FTE's released. Bright Yellow background indicates RMAG notification required upon release.
Staging Sites

## Drone Assessor Tracker
Event: Hurricane Beryl
EVENT: | Hurricane |  | Date / Time: | 2024-07-05 | [11 empty] | Comments
Resources Requested
Resource Type Requested - Date / Time |  |  |  | Drone Operators | Teams |  |  |  | Destination | Latest Arrival |  |  |  |  | GENERAL COMMENTS
Drone Assessors - 7/4/2024 11:00 |  |  |  | 20 | 10 |  |  |  | McAllen, TX | 2024-07-05 20:00
Drone Assessors - 07/5/24 15:00 |  |  |  | 10 | 5
Total Requested |  |  |  | 30 | 15 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Resources Acquired
Source Company |  | Company, Contractor, IOU, Baseload | Departure Location | Drone Operators | Teams | Support Personnel | Team Lead | Team Lead Cell Number | Destination | ETA | Visible in ARCOS | OPCO Contact Made? | Released to Mutual Assistance? | Release Date/Time | Comments
AEP-Telecom |  | Company | TX, LA, OL | 10 | 5 | 0 | Eric Elizondo |  | McAllen, TX | 2024-07-05 20:00 | Yes
Appalachian Power |  | Company | WV | 10 | 5 | 0 | Guy Rayl |  | McAllen, TX | 2024-07-05 20:00 | Yes
Acuren (Sunday) |  | Contractor | Texas | 10 | 5 | 0 | William Moreno |  | Robstown, TX | 2024-07-07 14:00 | Yes
↑ WAVE 1 ABOVE ↑
Total Acquired |  |  |  | 30 | 15 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Excess/Gap |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEGEND: Red background indicates all FTE's released. Bright Yellow background indicates RMAG notification required upon release.
Staging Sites

## Forestry Resource Tracker
Event: Hurricane Beryl
EVENT: | Hurricane |  | Date / Time: | 2024-07-05 | [11 empty] | Comments
Resources Requested
Resource Type Requested - Date / Time |  |  |  | Tree Trimmers | Tree Crews |  |  |  | Destination | Latest Arrival |  |  |  |  | GENERAL COMMENTS
Tree Trimmers - 07/5/24 15:00 |  |  |  | 390 | 130 |  |  |  | Robstown, TX
Tree Trimmers - 7/6/2024 16:00 |  |  |  | *250 | *111 |  |  |  | Robstown, TX | 2024-07-09 12:00 |  |  |  |  | Request canceled 7/7/24 8:00
Tree Trimmers
Total Requested |  |  |  | 390 | 130 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Resources Acquired
Source Company |  | Company, Contractor, IOU, Baseload | Departure Location | Tree Trimmers | Tree Crews | Support Personnel | General Foreman | GF Cell Number | Destination | ETA | Visible in ARCOS
Pannell Contracting (Sunday) |  | Contractor | Blanco, TX |  |  | 1 | Jorge Cuellar |  | Robstown, TX | 2024-07-07 12:00 | Yes
Pannell Contracting (Sunday) |  | Contractor | Blanco, TX | 13 | 5 | 1 | John Hernandez |  | Robstown, TX | 2024-07-07 12:00 | Yes
Pannell Contracting (Sunday) |  | Contractor | Blanco, TX | 12 | 5 | 1 | Guadalupe Hernandez |  | Robstown, TX | 2024-07-07 12:00 | Yes
Pannell Contracting (Sunday) |  | Contractor | Blanco, TX | 12 | 5 | 1 | Israel Lopez |  | Robstown, TX | 2024-07-07 12:00 | Yes
Lewis Tree (Sunday) |  | Contractor | Dallas, TX | 37 | 12 | 2 | Gabriel Estrada |  | Robstown, TX | 2024-07-07 12:00 | Yes
Asplundh - Region 636 (SWEPCo) |  | Baseload | Maumelle, AR | 7 | 3 | 1 | Jorge Hernandez |  | Robstown, TX | 2024-07-07 12:00 | Yes
Asplundh - Region 039 |  | Contractor | Clinton, MO | 13 | 7 | 2 | Dusten Hall |  | Robstown, TX | 2024-07-07 12:00 | Yes
Asplundh - Region 039 |  | Contractor | Union, MO | 8 | 4 | 1 | Joe Price |  | Robstown, TX | 2024-07-07 12:00 | Yes
Asplundh - Region 039 |  | Contractor | Gallatin, MO | 11 | 5 | 1 | Nicholas Greathouse |  | Robstown, TX | 2024-07-07 12:00 | Yes
Asplundh - Region 039 |  | Contractor | Union, MO | 9 | 4 | 1 | Samuel Hott |  | Robstown, TX | 2024-07-07 12:00 | Yes
Asplundh - Region 636 |  | Contractor | Fulton, TN | 8 | 4 | 1 | Kevin Livingston |  | Robstown, TX | 2024-07-07 15:00 | Yes
Asplundh - Region 636 |  | Contractor | Dickson, TN | 16 | 7 | 1 | Chris Wilson |  | Robstown, TX | 2024-07-07 15:00 | Yes
Asplundh - Region 070 (PSO) |  | Baseload | Oklahoma | 13 | 5 | 1 | Nathan Godeaux |  | Robstown, TX | 2024-07-07 15:00 | Yes
Asplundh - Region 070 (PSO) |  | Baseload | Oklahoma | 19 | 6 | 1 | POTTER, JACOB |  | Robstown, TX | 2024-07-07 15:00 | Yes
Asplundh - Region 070 (PSO) |  | Baseload | Oklahoma | 26 | 11 | 1 | KEVIN RIOS |  | Robstown, TX | 2024-07-07 15:00 | Yes
Asplundh - Region 070 (PSO) |  | Baseload | Oklahoma | 13 | 5 | 1 | Edgar Garcia |  | Robstown, TX | 2024-07-07 15:00 | Yes
Asplundh - Region 070 (PSO) |  | Baseload | Oklahoma |  |  | 1 | Vaughn Forell |  | Robstown, TX | 2024-07-07 15:00 | Yes
Asplundh - Region 068 |  | Contractor | Texarkana, TX | 32 | 11 | 3 | Raul Miranda |  | Robstown, TX | 2024-07-07 15:00 | Yes
Asplundh - Region 068 |  | Contractor | Texarkana, TX |  |  | 1 | Alberto Torres Jr |  | Robstown, TX | 2024-07-07 15:00 | Yes
Asplundh - Region 637 |  | Contractor | Texarkana, TX | 13 | 4 | 1 | Raul Miranda |  | Robstown, TX | 2024-07-07 15:00 | Yes
Asplundh - Region 066 |  | Contractor | Kansas City, KS | 11 | 5 | 1 | Chris Newport |  | Robstown, TX | 2024-07-08 12:00 | Yes
Asplundh - Region 037 |  | Baseload? | Corpus Christi, TX | 13 | 6 | 2 | EDWIN A PENA JR |  | Robstown, TX | 2024-07-07 08:00 | Yes
Asplundh - Region 037 |  | Baseload? | Harlingen, TX | 10 | 5 | 1 | Joel Rendon |  | Robstown, TX | 2024-07-07 08:00 | Yes
Asplundh - Region 037 |  | Baseload? | Corpus Christi, TX | 14 | 7 | 4 | Eduardo Alvarez |  | Robstown, TX | 2024-07-07 08:00 | Yes
Asplundh - Region 052 (Mark Johnson 256-223-6140) |  | Contractor | Montgomery, AL | 12 | 6 | 2 | Hurtis Cleckler |  | Within 3 hrs of CC | 2024-07-08 12:00 | Yes
Asplundh - Region 052 (Mark Johnson 256-223-6140) |  | Contractor | Huntsville, AL | 10 | 5 | 1 | Johnny Patterson |  | Within 3 hrs of CC | 2024-07-08 12:00 | Yes
Asplundh - Region 052 (Mark Johnson 256-223-6140) |  | Contractor | Cullman, AL | 11 | 5 | 2 | Randy Bruer |  | Within 3 hrs of CC | 2024-07-08 12:00 | Yes
Asplundh - Region 052 (Mark Johnson 256-223-6140) |  | Contractor | Rainsville, AL | 8 | 4 | 2 | Timothy Henderson |  | Within 3 hrs of CC | 2024-07-08 12:00 | Yes
Asplundh - Region 052 (Mark Johnson 256-223-6140) |  | Contractor | Graceville, FL | 13 | 6 | 2 | Taras Prytula |  | Within 3 hrs of CC | 2024-07-08 12:00 | Yes
↑ WAVE 1 ABOVE ↑
Total Acquired |  |  |  | 364 | 152 | 41 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Excess/Gap |  |  |  | -26 | 22 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEGEND: Red background indicates all FTE's released. Bright Yellow background indicates RMAG notification required upon release.
Staging Sites