## UPSHUR (hidden)
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 0 | 0
[24 empty] | 0 | 0 | 0 | Project Count
[24 empty] | Completed | Active | Total

## NEW3 (hidden)
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 0 | 0
[24 empty] | 0 | 0 | 0 | Project Count
[24 empty] | Completed | Active | Total

## NEW4 (hidden)
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 0 | 0
[24 empty] | 0 | 0 | 0 | Project Count
[24 empty] | Completed | Active | Total

## NEW (hidden)
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) |  | Last Month: | Current minus last month: | Cumulative Sum
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | 0 | 0 | 0
[23 empty] | Actual Cost of Projects Completed This Month (Will Not Appear on Next Month Report): | Estimated Cost of Projects Completed This Month: | Estimated Cost of Projects Remaining Active This Month: | Total Estimated Cost of Projects Appearing in This Report:
[23 empty] | 0 | 0 | 0 | 0
[24 empty] | 0 | 0 | 0 | Project Count
[24 empty] | Completed | Active | Total

## 04.15.2025
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (Total) | Final Estimated Project Cost (Total) | Final Actual Project Cost (Total) | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | INITIAL OR FINAL SELECTER | COMPLETED PROJECTS | ACTIVE PROJECTS | Estimated OR Actual Project Cost (SUBSTATION) | Last Month: | Current minus last month: | Cumulative Sum
LST2020001 | Reata Station to Roadrunner Crossing Wind 345 kV Transmission Line Project | Eastland | Construction of the new Reata 345 kV Station and new 2.3-mile 345 kV transmission line to the Roadrunner Crossing Wind, LLC collector station | 2022-02-01 |  | 2023-04-07 | Transmission Line Costs - $3,420,000; Station Costs - $21,560,000 | Transmission Line Costs - $6,340,000; Station Costs - $18,100,000 | 25842636 |  | 100% | 345 | 345 | 1 | Twin-bundled 795 kcmil "Drake" ACSR | Pre-stressed spun concrete poles | NA | NA | 100-150 | 1 | 50910; PURA sec. 37.052(c)(1)(B) | Project was rescheduled due to customer change in in-service date. Construction of the Reata Station commenced on Feb. 1, 2022. Construction of the Reata to Roadrunner transmission line will commence in Sept. 2022. Line length has been shortened from 2.3 miles to 1 mile with agreement of all directly affected landowners.
LST2021004 | Reata to Century Oak Wind 345 kV Transmission Line Project | Eastland and Callahan | Construction of new, 3.6-mile 345 kV single circuit transmission line from Reata Station to Century Oak Wind, LLC-owned collector station and interconnection facilities at Reata Station; project to interconnect Century Oak Wind, LLC | 2022-10-01 |  | 2023-09-14 | Transmission Line Costs - $5,081,000; Station Costs - $5,180,000 | Transmission Line Costs - $3,630,000; Station Costs - $13,370,000 |  |  | 100% | 345 | 345 | 3.6 | Twin-bundled 795 kcmil "Drake" ACSR | Pre-stressed spun concrete and steel poles | NA | NA | 100-150 | 3.6 | 52854 | CCN Notice of Approval issued 03/25/2022; construction start date for the transmission line adjusted to October 2022; percentage complete reflects construction progress of Reata Station
LST2022001 | Navarro to Lefty Data Center 345 kV Transmission Line Project | Navarro | Construction of new 345kV Navarro Station upgrades and new 0.1-mile 345 kV single circuit transmission line from Navarro Station to PPM Data, LLC-owned collector station | 2023-06-26 |  | 2023-11-02 |  | Transmission Line Costs - $2,010,000; Station Costs - $2,660,000 | 4633734 |  | 100% | 345 | 345 | 0.1 | Twin-bundled 1590 kcmil "Falcon" ACSR | Pre-stressed spun concrete and steel poles | NA | NA | 100-150 | 0.1 | 25.101(c)(2) 25.101(c)(5)(A)(I) 25.83(c) | Adding a breaker, CVT, and line exit at Navarro Station and 937 feet of new 345 kV transmission line to connect interconnection customer; all work will occur on Lone Star's or the customer's property
LST2023001 | Claytonville to Camp Springs 138 kV Transmission Line | Fisher and Scurry | Construction of new, 16.8-mile 138 kV transmission line from existing Claytonville Station to new Camp Springs Station | 2024-01-08 |  |  | Transmission Line Costs - $21,208,000 Station Costs - $2,512,000 | Transmission Line Costs - $21,208,000 Station Costs - $2,512,000 |  |  | 99% | 138 | 138 | 16.8 | Single 336.4 Linnet ACSR | Pre-stressed spun concrete and steel poles | NA | NA | 100-150 | 16.8 | 55326 | CCN Notice of Approval issued 11/28/2023
LST2024001 | Sam Switch to Ash Creek 345kV Transmission Line Project | Hill | Construction of new 345kV Sam Switch Station upgrades and new 0.1-mile 345 kV single circuit transmission line from Sam Switch Station to Ash Creek Solar LLC | 2024-04-01 | 2024-11-11 | 2024-11-11 |  | Transmission Line Costs - $900,000 Station Costs - $6,682,000 |  |  | 100% | 345 | 345 | 0.1 | Twin-bundled 1590 kcmil "Falcon" ACSR | Pre-stressed spun concrete and steel poles | NA | NA | 100-150 | 0.1 | 25.101(c)(2) 25.101(c)(5)(A) 25.83(c) 25.198 | Adding a breaker, CVT, and line exit at Sam Switch and 0.1 miles of new 345kV transmission line to connect interconnection customer. All work will occur on Lone Star’s property, the customer’s leased property, or county-owned right-of-way.
LST2024002 | Reata Station to Dorado Solar 345 kV Transmission Line Project | Eastland and Callahan | Construction of new, 3.3-mile 345 kV single circuit transmission line on double-circuit capable poles from Reata Station to Enbridge Solar (Eldorado), LLC-owned collector station and interconnection facilities at Reata Station; project to interconnect new approximately 401-MW solar generation facility | 2025-01-27 |  |  | Transmission Line Costs - $15,972,000 Station Costs - $16,345,000 | Transmission Line Costs - $15,972,000 Station Costs - $16,345,000 |  |  | 12% | 345 | 345 | 3.3 | Twin-bundled 1590 kcmil "Falcon" ACSR | Pre-stressed spun concrete and steel poles | NA | NA | 150-200 | 3.3 | 56599 | CCN Notice of Approval issued 8/22/2024
LST2024003 | Helix Switchyard to Hickerson Solar 345kV Station and Transmission Line Project | Bosque | Construction of the new Helix 345 kV Station, which will be cut-in to the existing 345 kV Kopperl to Navarro line and construction of new 0.2-mile 345 kV single circuit transmission line from Helix Station to BT Hickerson Solar (Hickerson), LLC-owned collector station; project to interconnect new 310-MW solar generation facility | 2024-09-23 |  |  |  | Transmission Line Costs - $11,920,000 Station Costs - $25,680,000 |  |  | 75% | 345 | 345 | 1.5 | Twin-bundled 1590 kcmil "Falcon" ACSR | Pre-stressed spun concrete and steel poles | NA | NA | 100-150 | 1.5 | 25.101(c)(2) 25.101(c)(5)(A) 25.83(c) 25.198 | Constructing new 345 kV breaker and a half open air switchyard (Helix), 0.57 miles of new 345 kV single circuit transmission line to enter and exit at Helix, and 0.68 miles of new 345 kV single circuit transmission line to shoefly/route around Helix; removing 0.54 miles of existing 345 kV double circuit transmission line; and constructing 0.2 miles of new 345 kV single circuit transmission line to connect interconnection customer. All work will occur on Lone Star's easements and the customer's owned or leased properties with agreement of all directly affected landowners.
LST2024004 | Bullock 345 kV Switchyard | Hill | Construction of the new Bullock 345 kV Station, which will be cut-in to the existing 345 kV Sam Switch to Navarro line | 2025-02-10 |  |  |  | Station Costs - $28,900,000 |  |  | 1% | 345 | 345 | 0.2 | Falcon 1590 ACSS/TW | Steel on Caisson Foundations | NA | NA | NA | NA | 25.101(c)(2) 25.101(c)(5)(A) 25.83(c) | Constructing new 345 kV breaker and a half open air switchyard (Bullock) and 0.20 miles of new 345 kV single circuit transmission line to enter and exit at Bullock; removing 0.18 miles of existing 345 kV single circuit transmission line. All work will occur on property that will be owned by Lone Star.
LST2025001 | Bullock Station to Aquilla Lake III Wind 345-kV Transmission Line | Hill | Construction of new single-circuit 345-kV transmission line that will begin at the new Bullock Station (Project LST2024004) and extend to the Aquilla Lake III Point of Interconnection with a total length of approximately 3.64 miles | 2025-09-01 |  |  | Transmission Line Costs - $15,163,692 |  |  |  | 0% | 345 | 345 | 3.64 | Twin-bundled 795 kcmil "Drake" ACSR | Pre-stressed spun concrete poles | NA | NA | 150 - 200 | 3.64 | 57836 | CCN Filed in Docket No. 57836 on April 11, 2025; Station Costs for this project are for the Bullock Station, reported separately as Project LST2024004.