## MonthlyReportForm
Utility Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
0PT40515 | Gainesville North Switch - Spring 138 kV Line : I-35 Relocation for TxDOT | City of Gainesville, Cooke County | Relocate structures 41/8, 41/9, 42/1, 42/2 and 42/3 adjacent to I-35 in Gainesville, TX. The relocated structures will utilize single circuit concrete or steel H-frames. | 2024-10-10 | 2024-11-11 | 2024-11-11 |  | 1481456 |  |  | 100 | 138 | na | 0.4 | 795 ACSR Drake | Concrete H-Frame, Steel H-Frame | 100 | 0.4 | na | na | 25.101(c)(5)(F)
0PT40577 0PT52804 | Stone Creek Switch - Gainesville Sub 69 kV Line : I-35 Relocation for TxDOT | City of Gainesville, Cooke County | Relocate structures 4/5, 4/6, 4/7 and 4/8 adjacent to I-35 in Gainesville, TX. | 2024-05-01 | 2024-05-21 | 2024-05-21 |  | 1409168 |  |  | 100 | 69 | na | 0.3 | 1/0 ACSR Raven | Concrete H-Frame, Steel H-Frame | 147 | 0.3 | na | na | 25.101(c)(5)(F)
0PT41810 (R984) | Allen Sw - Monticello Sw 345kV Line: Stouts Creek Cut In | City of Sulphur Springs, Hopkins County | Line work associated with connecting the 345 kV Stouts Creek Switch | 2025-03-31 | 2025-05-08 |  |  | 2079777 |  |  | 0 | 345 | na | 0.1 | 2-1926.9 ACSS/TW Cumberland | Steel Pole | 160 | 0.1 | na | na | 25.101(c)(5)(A)
0PT42378 | Handley-Liggett 138 kV: SE Connector Relocation For TxDOT | City of Fort Worth, Tarrant County | Relocation with new double circuit, steel monopole, tangent & dead end structures. | 2021-04-21 | 2022-03-02 | 2022-03-02 |  | 2474886 |  |  | 100 | 138 | na | 2 | 959.6 ACSS/TW Suwannee | Steel 2-Pole, Steel Pole | varies | 1.0021 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT42380 | Handley-Saginaw 138 kV: SE Connector Relocation For TxDOT | City of Fort Worth, Tarrant County | Relocation with new double circuit, steel monopole, tangent & dead end structures. | 2021-04-26 | 2021-11-19 | 2021-11-19 |  | 2560873 |  |  | 100 | 138 | na | 2 | 1926.9 ACSS/TW Cumberland | Steel Pole | varies | 0.99527 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT42381 | Handley-Richland Hills 69 kV: SE Connector Relocation For TxDOT | City of Fort Worth, Tarrant County | Relocation with new single circuit, steel monopole, tangent & dead end structures. | 2021-05-14 | 2021-11-03 | 2021-11-03 |  | 2236717 |  |  | 100 | 69 | na | 0.99 | 959.6 ACSS/TW Suwannee | Steel 2 - Pole. Steel 3 - Pole, Steel Pole | varies | 0.98902 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT40622 (M5222) | Forest Hill Switch - Handley Switch 69 kV Line : Line Conversion To 138 kV (Handley Switch-Duval Section) | City of Fort Worth, Tarrant County | Reterminate the Forest Hill Switch - Handley Switch 69 kV Line at its new terminal location at the Handley Switch Station and at the Duval Switch Station for the 138 kV line conversion. | 2022-10-13 | 2025-05-30 |  |  | 2993815 |  |  | 99* | 69 | 138 | 1.1 | 1233.6 ACSS/TW Yukon, 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 0.8 | 50 | 0.3 | 25.101(c)(5)(B) | Upgrade to 138 kV and extend alignment to Handley 138 kV Station.
0PT40627 (R8523) | Andrews County South Switch - Fullerton Switch 138 kV Line : POI for point of interconnection | Andrews County | Install one span of wire to connect the customer owned transmission line for point of interconnection (POI) | 2026-01-05 | 2026-07-15 | [5 empty] | 0 | 138 | na | 0.03 | 1590 ACSR Falcon | Steel Pole | na | na | 60 | 0.03 | 25.101(c)(5)(A)
0PT38463 0PT42532 (R9015) | Big Spring - Buzzard Draw 69 kV: Rebuild the line to operate at 138kV | Howard County | This project is to rebuild the 21 mile section of Big Spring to Buzzard Draw 69 kV Line. | 2021-06-01 | 2021-12-17 | 2021-12-17 |  | 25000000 |  |  | 100 | 69 | 138 | 21.3 | 959.6 ACSS/TW Suwannee | Concrete Pole, Steel H-Frame, Steel Pole | 50 | 21.3 | na | na | 25.101(c)(5)(B) | Temporary work
0PT44585 (R3023) | Blackwater Draw – Paleo Bess Solar 345 kV Line: Line Interconnection | Hale County | Install a new, single-circuit 345 kV transmission line from Blackwater Draw Switch station dead-end to a Point of Interconnection (“POI”) on a dead-end structure located near the Blackwater Draw Switch east property boundary. | 2022-02-10 | 2024-07-23 | 2024-07-23 |  | 976885 |  |  | 100 | na | 345 | 0.2 | 2-959.6 ACSS/TW Suwannee | Steel Pole | na | na | 150 | 0.2 | 25.101(c)(5)(A)
0PT43960 0PT46326 (R985) | Commerce Switch - Scatter Branch Sub 138 kV Line: Rebuild and convert 69 kV Line to 138 kV operation | City of Commerce, Hunt County | Rebuild a section from Commerce Switch to Scatter branch (Str 56/3) of the Commerce Switch - Royse Switch 69 kV Line and convert to 138 kV operation. | 2021-12-17 | 2022-05-09 | 2022-05-09 |  | 12433688 |  |  | 100 | 69 | 138 | 7.4 | 959.6 ACSS/TW Suwannee | Steel Pole | 70 | 7.4 | na | na | 25.101(c)(5)(B)
0PT40680 (M5222) | Forest Hill Switch - Handley Switch 69 kV Line: Convert Bryan Ave Tap to Forest Hill to 138 kV | City of Fort Worth, Tarrant County | Reterminate the Forest Hill Switch - Handley Switch 69 kV Line at its new terminal location at the Marrs Switch Station | 2025-04-15 | 2025-05-30 |  |  | 1148058.55 |  |  | 0 | 69 | 138 | 0.5 | 959.6 ACSS/TW Suwannee | Steel Pole | 100 | 0.5 | na | na | 25.101(c)(5)(C)
0PT45276 | Handley-Lancaster 138 kV: SE Connector Relocation for TxDOT | City of Fort Worth, Tarrant County | Relocation with new double circuit, steel monopole, tangent and angle structures on Handley-Lancaster 138 kV Line. | 2021-10-29 | 2021-11-19 | 2021-11-19 |  | 550521 |  |  | 100 | 138 | na | 0.18 | 795 ACSR Drake | Steel Pole | varies | 0.09 | na | na | 25.101(C)(5)(F) | Relocation is a request and 100% reimbursable by the Texas Department of Transportation.
0PT45371 | Handley-Duval 138 kV: SE Connector Relocation for TxDOT | City of Fort Worth, Tarrant County | Relocation with new double circuit, steel monopole, tangent structure on Handley-Duval 138 kV Line. | 2021-11-15 | 2021-11-19 | 2021-11-19 |  | 357832 |  |  | 100 | 138 | na | 0.18 | 959.6 ACSS/TW Suwannee | Steel Pole | varies | 0.18 | na | na | 25.101(C)(5)(F) | Relocation is a request and 100% reimbursable by the Texas Department of Transportation.
0PT42416 0PT44921 (M4292) | Payne Switch - Royse City 138 kV Line : Rebuild Audie Murphy POI to Royse Switch | City of Royse, Rockwall County | Rebuild the Audie Murphy POI to Royse Switch section of the Payne Switch - Royse City 138 kV line. | 2022-01-11 | 2022-12-16 | 2022-12-16 |  | 28941915 |  |  | 100 | 138 | na | 13.9 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 13.9 | na | na | 25.101(c)(5)(B)
0PT44253 0PT46213 (R3021) | Windmill Switch - AJ Swope Switch 345 kV Line : Wallaby Switch Cut In for point of interconnection (POI) | City of Hereford, Deaf Smith County | Cut in the Windmill Switch - AJ Swope Switch 345 kV Line to establish Wallaby Switch. | 2024-09-10 | 2025-01-01 | 2025-01-01 |  | 1872222.98 |  |  | 100 | 345 | na | 0.45 | 2-1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 175 | 0.4 | 410 | 0.05 | 25.101(c)(5)(A)
0PT37599 0PT39320 (M5155) | Handley - Sherry 138 kV Line: Rebuild Pantego Sub - Sherry Line Section (South Circuit) | City of Arlington, Tarrant County | Rebuild the Handley-Sherry 138kV Line: Pantego Sub to Sherry Sub | 2022-03-18 | 2022-12-28 | 2022-12-28 |  | 10533506 |  |  | 100 | 138 | na | 5.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 5.1 | na | na | 25.101(c)(5)(C)
0PT43019 (M4230) | Venus Switch - Cedar Hill Switch 345 kV Line: Reconductor Venus Switch - Britton Road | City of Venus, Ellis County | Reconductor the portion of the 345kV Venus Switch - Cedar Hill Switch circuit that goes from Britton Road station to structure 14/4 using a conductor rated for 3200 A or greater. | 2022-12-13 | 2022-12-29 | 2022-12-29 |  | 5674693 |  |  | 100 | 345 | na | 7.4 | 2-959.6 ACSS/TW Suwannee | Lattice Tower | 150 | 7.4 | na | na | 25.101(c)(5)(B)
0PT44572 (R6160) | Hillsboro Substation to Navarro Substation 138 kV Retermination/Shoo-Fly | City of Navarro, Navarro County | Line work associated with new 138kV Revolution Switch Station | 2025-05-15 | 2025-12-04 | [5 empty] | 0 | 138 | na | 0.15 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | na | na | 100 | 0.15 | 25.101(c)(5)(A)
0PT43740 | Nacogdoches-Chireno 138 kV: SH 21 @ Carizzo Creek Relocation for TxDOT | City of Lufkin, Angelina County | Replace existing wood pole H-frames with two (2) new single-circuit, concrete H-frame tangent structures (Str. 4/2 and 4/3). | 2022-05-26 | 2022-06-08 | 2022-06-08 |  | 591144 |  |  | 100 | 138 | na | 0.36 | 336.4 ACSR Linnett | Concrete H-Frame | 100 | 0.36 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT43246 | East Waco-West Waco, M&M Tap 138 kV: TxDOT Relocation for SH 6 @ Loop 340 | City of Waco, McLennan County | Relocation with new single circuit, steel monopole, tangent & swing angle structures. | 2022-04-04 | 2022-04-26 | 2022-04-26 |  | 1285252 |  |  | 100 | 138 | na | 0.33 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.33 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the Texas Department of Transportation and is 100% reimbursable by the Texas Department of Transportation.
0PT45707 0PT47747 (R8581) | Wink Switch - Wink Basin Sub 138 kV Line : 69 kV Conversion to 138 kV | City of Wink, Winkler County | Rebuild Wink Switch - Wink Basin 69 kV section on the Wink Switch - Keystone No 1 East 69 kV Line. | 2023-09-19 | 2023-12-06 | 2023-12-06 |  | 3853819 |  |  | 100 | 69 | 138 | 2.9 | 1926.9 ACSS/TW Cumberland | Steel 3-Pole, Steel Pole | 50 | 2.9 | na | na | 25.101(c)(5)(B)
0PT43897 0PT43896 0PT48828 (R8570) | Eskota Switch - Sweetwater No. 2 Sub 69 kV Line: Rebuild | City of Sweetwater, Nolan County | Rebuilding 12.2 miles of double circuit wood poles with new steel poles. Installing one circuit. | 2022-06-05 | 2023-05-01 | 2023-05-01 |  | 18576188 |  |  | 100 | 69 | na | 24.2 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 12.2 | na | na | 25.101(c)(5)(B)
0PT45995 (R2014) | Big Brown Switch - Richland Chambers Switch 345 kV Line : Raise Line for Pin Oak Switch 138 kV | City of Fairfield, Freestone County | Install one lattice tower to raise line for new Pin Oak Station. | 2022-04-18 | 2022-06-03 | 2022-06-03 |  | 871651 |  |  | 100 | 345 | na | 0.2 | 2-795 ACSR Drake | Steel Lattice Tower | 375 | 0.1 | na | na | 25.101(c)(5)(A)
0PT45724 0PT47700 (R8596) | Andrews North Sub - Mustang Sub 138 kV Line : Rebuild | Andrews County | Rebuild Andrews North Sub - Mustang Sub 138 kV Line. | 2022-06-17 | 2022-12-21 | 2022-12-21 |  | 22845646 |  |  | 100 | 138 | na | 12.9 | 2 - 1926.9 ACSS/TW Cumberland | Steel Pole, Wood 3 - Pole | varies | 12.9 | na | na | 25.101(c)(5)(B)
0PT42879 0PT47805 (R4015) | Bellevue Sub - Bowie Sub 69 kV Line: Rebuild Smith Creek Sub - Tower One Sub 138 kV Line | City of Bowie, Montague County | Rebuild the 10-mile Smith Creek - Tower One 138 kV Line Section of the Burnett - Bowie 69 kV Line using a conductor rated 1649 A or greater. New 138 kV double-circuit structures with one circuit in place will be installed. | 2022-06-20 | 2023-05-26 | 2023-05-26 |  | 11036755 |  |  | 100 | 69 | 138 | 10 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | 50 | 10 | na | na | 25.101(c)(5)(B)
0PT45364 0PT44946 | Wedgwood Switch - Pafford St Switch 138 kV Line : Line Retermination Into New Rosemont Switch | City of Fort Worth, Tarrant County | Reterminate the Wedgwood Switch – Pafford Street Switch 138 kV Line at its new terminal location at the Rosemont Switch. | 2022-11-04 | 2025-05-15 |  |  | 2591809 |  |  | 89 | 138 | na | 0.5 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 55 | 0.25 | 25.101(c)(5)(D)
0PT44759 (M4320) | Bardwell Switch - Italy Sub 69 kV Line : Rebuild | City of Forreston, Ellis County | Rebuild the Bardwell Lake Switch - Italy section of the Hillsboro - Waxahachie 69 kV Line. Bundle existing circuits of the Italy - Hillsboro section of the Hillsboro - Waxahachie 69 kV Line. | 2022-07-25 | 2022-12-31 | 2022-12-31 |  | 11790246 |  |  | 100 | 69 | 138 | 6.1 | 959.6 ACSS/TW Suwannee | Steel Pole | 80 | 6.1 | na | na | 25.101(c)(5)(B)
0PT45495 0PT43815 (M5172) | Handley Switch - Executive Parkway Switch 138 kV Line : Reconductor the Hurst Sub - International Airport Sub 138 kV Line | City of Fort Worth, Tarrant County | Reconductor the Handley Switch - Executive Parkway Switch 138 kV Line between the Hurst Substation - International Airport Substation. | 2022-09-12 | 2022-12-30 | 2022-12-30 |  | 6709213 |  |  | 100 | 138 | na | 11.2 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | 100 | 11.2 | na | na | 25.101(c)(5)(B)
0PT43962 (R985) | Scatter Branch Sub - Caddo Mills Explorer Tap 69 kV Line: Rebuild Scatter Branch - Caddo Mills Explorer Tap | City of Greenville, Hunt County | Rebuild from Scatter Branch Sub to Caddo Mills Explorer Tap of the Commerce Switch - Royse Switch 69 kV Line. | 2022-10-17 | 2023-05-31 | 2023-05-31 |  | 30785002 |  |  | 100 | 69 | na | 19.1 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 19.1 | na | na | 25.101(c)(5)(B)
0PT46946 (M5222) | Marrs Switching Station – Rolling Hills Substation 138 kV Line: Re-terminate the Marrs Switching Station – Rolling Hills Substation 138 kV Line at Marrs Switching Station | City of Fort Worth, Tarrant County | Re-terminate the Marrs Switching Station – Rolling Hills Substation 138 kV Line at a new terminal location in the Marrs Switching Station to accommodate the for the new Marrs Switching Station | 2025-04-11 | 2025-05-30 |  |  | 877203 |  |  | 0 | 138 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 0.2 | na | na | 25.101(c)(5)(B)
0PT44570 (R6160) | Corsicana Sub to Navarro Sub 138 kV Line: Re-terminate at Revolution Switch | City of Corsicana, Navarro County | Modify the Corsicana Substation CB 15015/15020 – Navarro Substation 138 kV transmission line. | 2025-10-01 | 2025-12-04 | [5 empty] | 0 | 138 | na | 0.15 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 100 | 0.15 | 25.101(c)(5)(B)
0PT44528 0PT44520 (R3022) | SL Ogallala - Tule Canyon 345 kV Line: Kress Switch Interconnection | City of Kress, Kress County | Cut-In the Ogallala - Tule Canyon 345 kV Line to establish the new Kress Switch. | 2022-10-13 | 2023-05-26 | 2023-05-26 |  | 1891641 |  |  | 100 | 345 | na | 0.1 | 2 -1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 160 | 0.1 | na | na | 25.101(c)(5)(A)
0PT43948 0PT46138 (M4236) | Royse Switch - Rowlett Sub 138 kV Line : Reconductor Fate Sub to Rockwall Sub | Royse City, Rockwall County | Reconductor the Fate Sub - Rockwall Sub section of the Royse Switch - Rowlett 138 kV Line. | 2022-09-30 | 2022-12-01 | 2022-12-01 |  | 13223812 |  |  | 100 | 138 | na | 3.85 | 2-959.6 ACSS/TW Suwannee | Steel H-Frame, Steel Pole | Varies | 3.85 | na | na | 25.101(c)(5)(B)
0PT46646 (R6183) | Hillsboro Switch - Navarro Switch 138 kV Line: Install Ash Creek Switch for Pitts Dudik Solar | City of Hubbard, Hill County | Cut in the Navarro - Hillsboro 138 kV Line to establish the new Ash Creek Switch Station. | 2023-03-29 | 2023-04-18 | 2023-04-18 |  | 1163236 |  |  | 100 | 138 | na | 0.31 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.25 | 195 | 0.06 | 25.101(c)(5)(A)
0PT41809 0PT47334 (R8607) | Glass Ranch Switch - Sale Ranch Switch 138 kV Line : Red Sand point of delivery (POD) | City of Midland, Martin County | Establish Red Sand Point of Delivery (POD) | 2022-09-26 | 2022-12-01 | 2022-12-01 |  | 2116406 |  |  | 100 | 138 | na | 0.81 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel H-Frame, Steel Pole | 100 | 0.5 | varies | 0.34 | 25.101(c)(5)(A)
0PT43721 (R6141) | Waco East Sub - Waco West Switch 138 kV Line : Reterminate at Peppervine Switch | City of Waco, McLennon County | Retermination into new Peppervine Switch | 2023-06-07 | 2023-12-18 | 2023-12-18 |  | 775379.88 |  |  | 100 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | 80 | 0.2 | na | na | 25.101(c)(5)(B)
0PT43691 0PT48058 (R6147) | Waco East Switch - Bellmead Sub 69kV Line: Conversion to 138 kV | City of Waco, McLennan County | Conversion to 138 kV as a part of rebuilding the Waco East Switch - Elm Mott Switch 69 kV line conversion to 138 kV operation | 2022-09-27 | 2023-05-26 | 2023-05-26 |  | 9173498 |  |  | 100 | 69 | 138 | 3.8 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 3.8 | na | na | 25.101(c)(5)(B)
0PT44965 (R8479) | Sargent Road Switch - Industrial Blvd Switch 138 kV Line : Rebuild | City of Dallas, Dallas County | Reconductor the Sargent Road Switch - Industrial Blvd Switch 138 kV Line. | 2025-09-17 | 2025-12-30 | [5 empty] | 0 | 69 | 138 | 1.6 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 0.3 | 70 | 0.5 | 25.101(c)(5)(C)
0PT48355 0PT49178 (R8530) | Moss Switch - Red Lakes Switch 138 kV Line : Rebuild | Odessa County | Rebuild the 14.0 mile Moss Switch - Red Lakes Switch 138 kV line. | 2023-02-20 | 2023-11-20 | 2023-11-20 |  | 21838771 |  |  | 100 | 138 | na | 14 | 1926.9 ACSS/TW Cumberland | Steel H-Frame, Steel Pole | 70 | 14 | na | na | 25.101(c)(5)(A)
0PT46925 (R8624) | Barber Lake Switch - Morgan Creek Switch 138 kV Line : Install Moser Canyon point of delivery (POD) | City of Colorado City, Mitchell County | Rebuild 0.4-miles of the Barber Lake Switch - Morgan Creek Switch 138kV Line East Circuit to establish the Moser Canyon point of delivery (POD) | 2023-10-03 | 2024-05-14 | 2024-05-14 |  | 2216404.28 |  |  | 100 | 138 | na | 0.39 | 1926.9 ACSS/TW Cumberland, 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel H-Frame, Steel Pole | na | na | 50 | 0.39 | 25.101(c)(5)(A)
0PT46759 0PT46760 (R8606) | SL South Midland Switch - Cottonfield 138 kV Line: Rebuild | City of Odessa, Odessa County | Rebuild the SL South Midland Switch - Cottonfield 138 kV Line. | 2023-01-27 | 2023-05-26 | 2023-05-26 |  | 4682906 |  |  | 100 | 138 | na | 2.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 1.1 | na | na | 25.101(c)(5)(B)
0PT46882 (R8479) | Yucca Drive Switch - Northern Natural Gas Sub 69 kV Line: Cut-in Courtney Creek Switch - Fort Stockton Switch 138 kV Line | City of Grand Falls, Ward County | Cut in the Yucca Drive Switching Station – Northern Natural Sub 69 kV Line to establish the new Courtney Creek 138 kV Switching Station | 2023-01-16 | 2023-05-30 | 2023-05-30 |  | 4178631 |  |  | 100 | 69 | 138 | 0.8 | 1926.9 ACSS/TW Cumberland | Steel 3-Pole, Steel H-Frame, Steel Pole, Wood Pole | 70 | 0.3 | 70 | 0.5 | 25.101(c)(5)(C)
0PT47460 (R4015) | Hopewell - Johnson SS (BEPC) 138 kV Line: Reterminate to establish Hopewell Switch | City of Bowie, Montague County | Reterminate the existing Montague - Johnson SS (BEPC) 69 kV Line at its new terminal location at the new Hopewell Switch. | 2022-10-11 | 2022-12-28 | 2022-12-28 |  | 297610 |  |  | 100 | 69 | 138 | 0.2 | 959.6 ACSS/TW Suwannee | Steel Pole | varies | 0.2 | na | na | 25.101(c)(5)(B) | This line is a shared ownership with Brazos and Brazos will reimburse Oncor for their portion of the cost.
0PT46610 0PT48345 (R6184) | Brown Switch - Killeen Switch 345 kV Line : Cut-in to establish Russell Gap Switch | Mills County | Cut - In to Brown - Killeen Switch 345 kV Line to Establish Russell Gap Switch | 2022-11-14 | 2022-12-22 | 2022-12-22 |  | 1999500 |  |  | 100 | 345 | na | 0.21 | 2 -1926.9 ACSS Cumberland | Steel Lattice Tower | 80 | 0.21 | na | na | 25.101(c)(5)(A)
0PT44731 (R788) | Comanche Peak Switch - Stephenville Switch 138 kV Line: Antler Hollow Associated Line Work (South Circuit) | City of Stephenville, Erath County | Line work associated with establishing Antler Hollow Substation | 2022-10-22 | 2022-12-19 | 2022-12-19 |  | 746949 |  |  | 100 | 138 | na | 0.2 | 959.6 ACSS/TW Suwannee | Steel Pole | 70 | 0.2 | na | na | 25.101(c)(5)(A)
0PT47719 | Allen Switch - Plano West Sub 138 kV Line : Structure Replacement | City of Richardson, Collin County | Project will be to replace Structure 1/1C which is located outside of Plano West Substation on the Allen Switch – Plano West 138 kV Line | 2023-04-06 | 2023-04-12 | 2023-04-12 |  | 357732 |  |  | 100 | 138 | na | 0.1 | 795 ACSR Drake | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT47462 (R4015) | Hopewell - Joy (BEPC) 138 kV Line: Reterminate to establish Hopewell Switch | City of Bowie, Montague County | Reterminate the existing Montague - Joy SS (BEPC) 69 kV Line at its new terminal location at the new Hopewell Switch. | 2022-10-11 | 2022-12-28 | 2022-12-28 |  | 407914 |  |  | 100 | 69 | 138 | 0.2 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0.2 | na | na | 25.101(c)(5)(B) | This line is a shared ownership with Brazos and Brazos will reimburse Oncor for their portion of the cost.
0PT44238 0PT46722 (R6215) | Taylor Switch - Hutto Switch 138 kV Line: Mallard Switch Cut-in | City of Taylor, Williamson County | Construct the cut-in line for the new Mallard Sw station. | 2022-12-09 | 2023-05-31 | 2023-05-31 |  | 9053879 |  |  | 100 | na | 138 | 1.63 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 140 | 1.63 | 25.101(c)(5)(A)
0PT46975 (R6215) | Mallard Switch - SAS FAB1 138kV Line: Construct New Double Circuit POD Line | City of Taylor, Williamson County | Construct the POD line from Mallard to SAS FAB1 | 2022-12-29 | 2023-05-30 | 2023-05-30 |  | 2664714 |  |  | 100 | na | 138 | 1.62 | 1926.9 ACSS/TW Cumberland | Steel 2 - Pole, Steel Pole | na | na | varies | 0.81 | 25.101(c)(5)(A)
0PT46074 0PT46072 (R8565) | SL East Stiles Sub - St. Lawrence Sub 138 kV Line: Rebuild | Glasscock and Reagan Counties | Rebuild 13.1 miles of East Stiles – St. Lawrence 138kV Line | 2023-02-24 | 2023-06-29 | 2023-06-29 |  | 15574364 |  |  | 100 | 138 | na | 13.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 90 | 13.1 | na | na | 25.101(c)(5)(B)
0PT46744 (M4126) | Centerville Switch - Centerville Road - Lake Hubbard Switch 138 kV Double-Circuit Line: Reconductor | City of Dallas, Dallas County | Reconductor the Centerville Switch to Lake Hubbard 138 kV Double Circuit line | 2023-01-27 | 2023-12-05 | 2023-12-05 |  | 7913000 |  |  | 100 | 138 | na | 13.6 | 959.6 ACSS/TW/E3X Suwannee | Steel Lattice Tower | Varies | 6.8 | na | na | 25.101(c)(5)(B)
0PT43949 0PT46562 (M4236) | Rowlett Sub - Oates Sub 138 kV Line : Rebuild | City of Rowlett & Garland, Dallas County | Rebuild the Rowlett Sub -Oates 138 kV Line. | 2023-08-28 | 2023-12-06 | 2023-12-06 |  | 20338645.84 |  |  | 100 | 138 | na | 5.7 | 959.6 ACSS/TW SUWANNEE | Steel Pole | Varies | 5.7 | na | na | 25.101(c)(5)(b)
0PT48509 0PT49817 0PT50835 (R4015) | Burnett Switch - Old Lake Switch 69 kV Line: Rebuild Fisher Road - Lanham Tap section to 138 kV | City of Wichita Falls, Wichita County | Rebuild Burnett - Lanham Tap section of the Burnett Switch - Old Lake Switch 69 kV Line to 138 kV. | 2023-01-28 | 2024-05-16 | 2024-05-16 |  | 15051629 |  |  | 100 | 69 | 138 | 10.4 | 959.6 ACSS/TW SUWANNEE | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 10.4 | na | na | 25.101(c)(5)(B)
0PT46826 | Trinidad Switch - Eustace Southeast Sub 138 kV Line : Replace Structure 61/8A | City of Trinidad, Henderson County | Replace structure 61/8A due to corrosion of structure leg. | 2025-01-16 | 2025-02-15 |  |  | 489490 |  |  | 99* | 138 | na | 0.01 | 1033.5 ACSR Curlew | Steel H-Frame | 160 | 0.01 | na | na | 25.101(c)(5)(B)
0PT46945 (M5222) | Handley Switch – Handley Sub 69 kV Strain Bus: Rebuild and Reconfigure as the Handley Switch - Rosedale Sub 138 kV Line | City of Fort Worth, Tarrant County | Re-terminate the Handley Switching Station – Handley Substation 69 kV Strain Bus at its new terminal location at the Handley Switching Station | 2022-10-13 | 2025-05-30 |  |  | 1602887 |  |  | 78 | 69 | 138 | 0.3 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel H-Frame, Steel Pole | 50 | 0.3 | na | na | 25.101(c)(5)(B)
0PT46644 0PT47903 (R8614) | Sale Ranch Switch - Natural Dam Switch 138 kV Line : Install Rock Lake point of delivery (POD) | City of Stanton, Martin County | Provide a 138 kV point of delivery (POD) on the Sale Ranch - Natural Dam 138 kV Line | 2024-08-12 | 2024-10-10 | 2024-10-10 |  | 3582498 |  |  | 100 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel 3-Pole, Steel H-Frame, Steel Pole | na | na | 70 | 0.4 | 25.101(c)(5)(A)
0PT47706 (M4330) | Haggerty Switch Station - MEMC Southwest Substation (North) 138 kV Line | City of Sherman, Grayson County | Reroute the North MEMC Southwest Tap 138kV single circuit line 0.6 miles into the new Haggerty 138 kV Switch Station. | 2023-03-07 | 2023-12-15 | 2023-12-15 |  | 1876123 |  |  | 100 | 138 | na | 0.6 | 2-959.6 ACSS/TW Suwannee | Steel Pole | na | na | 100 | 0.6 | 25.101(c)(5)(B)
0PT47674 (M4330) | Haggerty Switch Station: Sherman TI 138 kV Tie Line to XFMR #2 | City of Sherman, Grayson County | Build the new tie line between the new Haggerty 138 kV Switch Station and existing Sherman TI Substation (XFMR #2) | 2023-01-18 | 2023-04-14 | 2023-04-14 |  | 935544 |  |  | 100 | na | 138 | 0.1 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | varies | 0.1 | 25.101(c)(5)(B)
0PT47705 (M4330) | Valley-Anna 138 kV Line: Establish Haggerty 138 kV Switch | City of Sherman, Grayson County | Reroute the Valley/Anna 138kV double circuit line 0.3 miles into the new Haggerty 138 kV Switch Station | 2023-01-23 | 2023-05-24 | 2023-05-24 |  | 3333681 |  |  | 100 | 138 | na | 1.2 | 2-959.6 ACSS/TW Suwannee | Steel Pole | 80 | 0.3 | varies | 0.3 | 25.101(c)(5)(B)
0PT48310 (M4330) | Haggerty Switch Station: 138kV Line to TI SM1-1 | City of Sherman, Grayson County | Build the new line between the new Haggerty 138 kV Switch Station and new TI SM1-1 | 2023-05-09 | 2024-04-30 | 2024-04-30 |  | 2019065 |  |  | 100 | na | 138 | 1 | 2-959.6 ACSS/TW Suwannee | Steel Pole | na | na | varies | 1 | 25.101(c)(5)(B)
0PT48311 (M4330) | Haggerty Switch Station: 138 kV Line to TI SM1-2 | City of Sherman, Grayson County | Build the new line between the new Haggerty 138 kV Switch Station and new TI SM1-2 | 2023-05-10 | 2024-04-30 | 2024-04-30 |  | 2025804 |  |  | 100 | na | 138 | 1 | 2-959.6 ACSS/TW Suwannee | Steel Pole | na | na | varies | 1 | 25.101(c)(5)(B)
0PT47391 (R8619) | Wolf Switch - Moss Switch 345 kV Line : Cut-in Meteor Switch 345 kV | City of Odessa, Ector County | Cut in the Wolf Switch - Moss Switch 345 kV Line to establish the new Meteor Switch 345 kV | 2024-10-01 | 2024-12-30 | 2024-12-30 |  | 1598886 |  |  | 100 | 345 | na | 0.1 | 2-1926.9 ACSS/TW Cumberland | Steel Lattice Tower | na | na | 180 | 0.1 | 25.101(c)(5)(A)
0PT48967 (M5326) | Lavender Switch – SDC Wilmer (Focus) 138kV Line: Station Tie Lines Build | Dallas County | Built the two (2) new tie lines between Oncor's Lavender station and Stream's Focus station | 2023-03-15 | 2024-06-20 | 2024-06-20 |  | 784840 |  |  | 100 | na | 138 | 0.2 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | varies | 0.1 | 25.101(c)(5)(A)
0PT48536 0PT49159 (R8642) | SL Pronghorn - Salt Flat Road 138 kV Line: Rebuild | Midland County | Rebuild the Pronghorn-Salt Flat Road 138 kV line to 1926 ACSS/TW capable structures. | 2023-08-14 | 2023-12-08 | 2023-12-08 |  | 13100797 |  |  | 100 | 138 | na | 7.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | varies | 7.2 | na | na | 25.101(c)(5)(B)
0PT47279 (M4331) | Kemp Ranch Switch - Sardis Switch 138 kV Line : Cut-in Newton Branch Sub | City of Midlothian, Ellis County | Cut in the Kemp Ranch Switch - Sardis Switch 138 kV Line to establish the new Newton Branch Substation. | 2023-12-07 | 2024-02-16 | 2024-02-16 |  | 1420628.9 |  |  | 100 | 138 | na | 0.06 | 2-959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0.06 | na | na | 25.101(c)(5)(A)
0PT47545 | North Network Sub - Bryan Sub 138 kV Line | City of Dallas, Dallas County | Replace six 138 kV Underground Transmission Terminations at North Network-Bryan Sub 138kV. | 2024-10-08 | 2024-12-01 | 2024-12-01 |  | 998077 |  |  | 100 | 138 | na | na | 1500 AL HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT48531 (M3015) | Krum West Switch - Hummingbird Storage POI 345 kV Line: Install Line | Denton County | Build a 345 kV Point of Interconnection (POI) to KCE TX 10, LLC Hummingbird Storage from Krum West Switch | 2023-02-23 | 2024-05-30 | 2024-05-30 |  | 1132115 |  |  | 100 | na | 345 | 0.18 | 2-1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 160 | 0.18 | na | na | 25.101(c)(5)(A)
0PT48089 (M5359) | Hicks Switch - Roanoke Switch 138 kV Line : Install Elizabethtown point of interconnection (POI) | City of Fort Worth, Denton County | Cut in the Hicks Switch - Roanoke Switch 138 kV Line to establish the new Elizabethtown POI | 2023-03-06 | 2025-11-06 |  |  | 1665582 |  |  | 87 | 138 | na | 0.22 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 60 | 0.11 | 25.101(c)(5)(A)
0PT47753 (R6208) | Bell County East Switch - Chillingham POI 345 kV Line: Install Line for point of interconnection (POI) | Bell County | Establish a 345 kV point of interconnection (POI). | 2024-02-12 | 2024-08-02 | 2024-08-02 |  | 2842097 |  |  | 100 | na | 345 | 0.21 | 2-959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel Pole | na | na | 120 | 0.21 | 25.101(c)(5)(A)
0PT49060 | Sargent Road Switch - West Levee Sub 345 kV Line : Replace OPGW | City of Dallas, Dallas County | The existing OPGW between West Levee and Sargent Road is damaged and no spare fibers exist. This project is to replace the existing OPGW. | 2024-10-03 | 2024-12-05 | 2024-12-05 |  | 3171931.16 |  |  | 100 | 345 | na | 5.1 | 1590 ACSR Falcon | Steel Pole | Varies | 5.1 | na | na | 25.101(c)(3)
0PT49001 | Graham Plant Switch - Cook Field Road Switch 345 kV Line : Relocate structure 27/6 | Stephens County | Rebuild a section of the Graham Plant Switch - Cook Field Road Switch 345 kV Line | 2024-03-06 | 2024-06-01 | 2024-06-01 |  | 577215.86 |  |  | 100 | 345 | na | 1.4 | 2 - 795 ACSR Drake | Steel Lattice Tower | 120 | 0.7 | na | na | 25.101(c)(5)(B)
0PT48629 | Watermill Switch - Sargent Road Switch 345 kV Line : Replace OPGW | City of Dallas, Dallas County | Replace the OPGW on the Watermill Switch - Sargent Road Switch 345 kV Line. | 2024-04-05 | 2024-05-16 | 2024-05-16 |  | 3986568.15 |  |  | 100 | 345 | na | 12.6 | 1590 ACSR Falcon | Steel Pole | varies | 12.6 | na | na | 25.101(c)(5)(B)
0PT48983 | Krum Switch - Jacksboro Switch 345 kV Line : Increase Foundation Reveal Cap | City of Chico, Wise County | Increase foundation caps on structures for Krum Switch - Jacksboro Switch 345 kV Line. | 2024-08-07 | 2024-11-01 | 2024-11-01 |  | 459595 |  |  | 100 | 345 | na | 0.9 | 2-1590 ACSR Falcon | Steel Lattice Tower | 160 | 0.9 | na | na | 25.101(c)(5)(B)
0PT47718 | Jewett-Long Lake-Palestine South 138 kV Line: Relocate Structure 2/9 | City of Jewett, Leon County | Relocate structure on Jewett - Long Lake - Palestine South 138 kV Line | 2025-03-24 | 2025-12-01 |  |  | 2285325 |  |  | 56 | 138 | na | 0.1 | 795 ACSR Drake | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT46085 0PT48258 (R6138) | Pin Oak Switch - Fairfield West Switch 138 kV Line: Rebuild from Fairfield West to Fairfield Switch (BEPC) 138 kV | City of Fairfield, Freestone County | Rebuild the Pin Oak Switch – Fairfield West Switch 138 kV Line section from Fairfield West to Fairfield Switch (BEPC) using double circuit structures with one circuit in place. | 2023-02-09 | 2023-11-29 | 2023-11-29 |  | 9413391 |  |  | 100 | 138 | na | 4.8 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 4.8 | na | na | 25.101(c)(5)(B)
0PT48054 0PT48267 (R944) | Commerce Switch - Sulphur Springs Switch 138 kV Line: Reterminate at Cumby Tap | City of Cumby, Hopkins County | Reterminate the Commerce Switch - Sulphur Springs Switch 138 kV line at Cumby Tap. | 2023-11-10 | 2024-03-08 | 2024-03-08 |  | 996477.52 |  |  | 100 | 138 | na | 0.2 | 795 ACSR Drake | Steel 3- Pole | varies | 0.2 | na | na | 25.101(c)(5)(A)
0PT48971 | Stryker Creek Switch - Lufkin Switch 345 kV Line : Replace and relocate tower 23/2 | Nacogdoches County | Replacing Structure on Stryker Creek Switch - Lufkin Switch 345 kV Line. | 2024-03-25 | 2024-05-15 | 2024-05-15 |  | 2652703 |  |  | 100 | 345 | na | 0.5 | 2 - 795 ACSR Drake | Steel Lattice Tower | 150 | 0.5 | na | na | 25.101(c)(5)(B)
0PT48780 0PT47487 (R8027) | SL Ogallala Switch - Tule Canyon Switch 345 kV Line : Cut-in for Ozark Trail Switch | Swisher County | The work required to loop the Ogallala Switch - Tule Canyon Switch 345 kV line into Ozark Trail Switch. | 2024-03-26 | 2024-05-28 | 2024-05-28 |  | 1665988 |  |  | 100 | 345 | na | 0.1 | 2 -1926.9 ACSS/TW Cumberland | Steel Lattice Tower | na | na | 175 | 0.1 | 25.101(c)(5)(A)
0PT43468 (M4205) | Carrollton Northwest Switch - Carrollton East Switch 138 kV Line : Line Termination at Carrollton Northwest | City of Carrollton, Dallas County | Establish the Carrollton East Switch - Carrollton Northwest Switch 138 kV Double-Circuit Line and Carrollton Northwest Switch - Northlake Switch 138 kV Line by terminating the existing Carrollton East Switch - Northlake Switch 138 kV Line at Carrollton Northwest Switch. | 2023-09-18 | 2023-12-21 | 2023-12-21 |  | 2101040.58 |  |  | 100 | 138 | na | 1.8 | 959.6 ACSS/TW Suwannee | Steel Pole | varies | 0.9 | na | na | 25.101(c)(5)(A)
0PT47513 | Killeen Taft Sub - Killeen Switch 138 kV Line : Install OPGW | City of Killeen, Bell County | Installing OPGW from Killeen Taft Sub to Killeen Switch. Leave splice drop at Killeen Elms Road. | 2024-04-01 | 2024-06-03 | 2024-06-03 |  | 961314 |  |  | 100 | 138 | na | 12 | 1590 ACSR Falcon | Steel Pole | 100 | 6 | na | na | 25.101(c)(5)(B)
0PT02607 (R9022) | Graham - Morgan Creek 345 kV line (South): Reterminate at Mulberry Creek due to Station Rebuild | City of Abilene, Jones County | Line work associated with rebuilding Mulberry Creek 345 kV Switch Station | 2024-09-09 | 2025-05-15 |  |  | 6772651 |  |  | 99* | 345 | na | 1.2 | 2 -1926.9 ACSS/TW Cumberland | Steel Lattice Tower, Steel Pole | 120 | 0.4 | varies | 0.2 | 25.101(c)(5)(A)
0PT47795 (M5323) | Valley Switch - Paris Switch 345 kV Line : Cut-in for Pacific Switch | Lamar County | To provide service to the Customer’s generating facility, modifications to one circuit of the double circuit 345 kV transmission line will be necessary. The work required to loop the Valley Switch - Paris Switch 345 kV line into Pacific Switch. | 2023-10-26 | 2023-12-20 | 2023-12-20 |  | 2244840.8 |  |  | 100 | 345 | na | 0.6 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 250 | 0.4 | 300 | 0.1 | 25.101(c)(5)(A)
0PT42093 0PT42844 (R8591) | Blair Lake Substation-Courtney Creek Switch 69 kV Line: Conversion to 138 kV | Pecos County | Rebuild 13.8 miles of the Yucca Drive Switch – Northern Natural Substation 69 kV Line between Blair Lake Substation – the new Courtney Creek Switch and convert the circuit to 138 kV. | 2023-06-29 | 2023-12-14 | 2023-12-14 |  | 16108141 |  |  | 100 | 69 | 138 | 13.83 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 13.6 | 50 | 0.23 | 25.101(c)(5)(B)
0PT46932 0PT48703 (R8593) | NTUSU Brown Sub - Grady Sub 138 kV Line: Expanse Switch Cut In | Martin County | Loop in the Brown Sub - Grady Sub 138 kV line into the new Expanse 345/138 kV Switch | 2023-03-13 | 2023-12-01 | 2023-12-01 |  | 1774555 |  |  | 100 | 138 | na | 0.51 | 1926.9 ACSS/TW/E3X Cumberland | Steel Pole | 70 | 0.5 | 100 | 0.01 | 25.101(c)(5)(A)
0PT48643 (R8595) | McKenzie Draw - Lamesa Sub 138 kV Line: Lamesa Sub Cut - In | Dawson County | Line Work Associated with Retermination of Lamesa Sub | 2023-02-12 | 2024-03-09 | 2024-03-09 |  | 386236 |  |  | 100 | 138 | na | 0.01 | 959.6 ACSS/TW Suwannee | Steel A-Frame | 100 | 0.01 | na | na | 25.101(c)(5)(B)
0PT47106 0PT47929 (R8617) | SL Blue Acres Sub - Grey Well Draw Sub 138 kV Line : Rebuild | City of Midland, Midland County | Rebuild the 5.5 mile SL Blue Acres Sub - Grey Well Draw Sub 138 kV Line with double circuit capable structures. | 2023-04-27 | 2023-10-23 | 2023-10-23 |  | 12400488 |  |  | 100 | 138 | na | 5.5 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | 70 | 5.5 | na | na | 25.101(c)(5)(B)
0PT43540 (M5317) | Tyson Nick Solar: Establish a 138kV POI for customer's generator at Toco Switch | City of Paris, Lamar County | Establish 138 kV point of interconnection of the Tyson Nick Solar generating facility | 2025-03-22 | 2025-04-17 |  |  | 562867 |  |  | 64 | na | 138 | 0.1 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | varies | 0.1 | 25.101(c)(5)(A)
0PT48309 (M4330) | Haggerty Switch Station - MEMC Southwest Substation (South) 138 kV Line | City of Sherman, Grayson County | Reroute the South MEMC Southwest Tap 138 kV single circuit line 0.6 miles into the new Haggerty 138 kV Switch | 2023-06-27 | 2023-12-21 | 2023-12-21 |  | 1741500 |  |  | 100 | na | 138 | 0.6 | 2 - 959.6 ACSS/TW SUWANNEE | Steel Pole | na | na | 50 | 0.6 | 25.101(c)(5)(A)
0PT48845 (R8621) | Delaware River Switch - Delaware Ranch Sub 138 kV Line: Build | Culberson County | Build the tie line between the new Delaware River Switch and existing Delaware Ranch Sub. | 2024-03-07 | 2024-05-06 | 2024-05-06 |  | 543557 |  |  | 100 | na | 138 | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 0.1 | varies | 25.101(c)(5)(A)
0PT48223 (R6182) | Palestine South - Long Lake 138 kV line: Reterminate at Palestine South | City of Palestine, Anderson County | Reterminate the Palestine South - Long Lake 138 kV line at Palestine South. | 2023-03-23 | 2023-11-01 | 2023-11-01 |  | 1159099 |  |  | 100 | 138 | na | 0.2 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | varies | 0.2 | na | na | 25.101(c)(5)(A)
0PT47787 (R8621) | Horseshoe Spring Switch - Riverton Switch 138 kV Line : Cut-in for Delaware River Switch | Culberson County | Cut-in the Horseshoe Springs Switch - Riverton Switch 138 kV Line to establish the new Delaware River Switch | 2024-02-29 | 2024-05-06 | 2024-05-06 |  | 2230377 |  |  | 100 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 75 | 0.4 | 25.101(c)(5)(A)
0PT46888 (M4137) | Mesquite East Switch - Sunnyvale 138 kV Line: Rebuild | City of Mesquite, Dallas County | Rebuild the Mesquite East Switch - Sunnyvale 138 kV Line. | 2023-02-21 | 2023-12-01 | 2023-12-01 |  | 7179241 |  |  | 100 | 138 | na | 4.08 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | 2.04 | na | na | 25.101(c)(5)(b)
0PT47790 0PT48725 (R6182) | Palestine - Crockett 69 kV Line: Rebuild Palestine Switch - Elkhart Switch | City of Palestine, Anderson County | Rebuild the Palestine - Crockett 69 kV line from Palestine Switch - Elkhart Switch. | 2023-03-21 | 2025-09-15 |  |  | 16621693 |  |  | 9 | 69 | 138 | 10 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | varies | 10 | na | na | 25.101(c)(5)(B)
0PT41200 0PT51456 (R944) | Cumby Tap Switch - Cumby Sub 69 kV Line : Conversion to 138 kV | City of Cumby, Hopkins County | Reterminate the Cumby Tap Switch - Cumby Sub 69 kV line at Cumby Sub. | 2023-04-05 | 2024-03-08 | 2024-03-08 |  | 2367244 |  |  | 100 | 69 | 138 | 0.2 | 336.4 ACSR Linnett | Steel Pole | varies | 0.2 | na | na | 25.101(c)(5)(A)
0PT48098 0PT49115 (R6172) | McGregor Phillips Tap Switch - Waco West Switch 69 kV Line : Rebuild Structure 24/4B to McGregor Phillips Switch | City of McGregor, McLennan County | Rebuild McGregor Phillips Tap Switch - Waco West Switch 69 kV Line from Structure 24/4B to McGregor Phillips Switch. | 2023-05-02 | 2024-12-01 | 2024-12-01 |  | 3443330.22 |  |  | 100 | 69 | 138 | 2 | 1926.9 ACSS/TW/E3X Cumberland | Steel Pole, Wood Pole | 100 | 1 | na | na | 25.101(c)(5)(B)
0PT47983 (R8669) | Wink Switch - Aroya Switch 138 kV Line : Establish White Dune 138 kV point of delivery (POD) | City of Wink, Winkler County | Provide a 138 kV point-of-delivery (POD) on the Wink Switch - Aroya Switch 138 kV Line Section. | 2025-01-24 | 2025-05-15 |  |  | 2817908.42 |  |  | 99* | 138 | na | 0.23 | 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 0.2 | varies | 0.03 | 25.101(c)(5)(A)
0PT48973 | Martin Lake Switch - Stryker Creek Switch 345 kV Line : Replace and relocate Str. 41/1 | City of Tatum, Rusk County | Replacing Structure on Martin Lake Switch - Stryker Creek Switch 345 kV Line. | 2024-11-21 | 2024-12-11 | 2024-12-11 |  | 2103357.17 |  |  | 100 | 345 | na | 1 | 2-1590 ACSR Falcon | Steel Lattice Tower | 150 | 0.5 | na | na | 25.101(c)(5)(B)
0PT48376 (R6224) | Hutto Switch - Gilleland Creek Switch 138 kV Line : Cut-in to establish Double Creek Sub | City of Round Rock, Williamson County | Build new line section to cut in Double Creek 138 kV Sub. | 2023-04-27 | 2023-12-28 | 2023-12-28 |  | 2379553 |  |  | 100 | 138 | na | 0.6 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 95 | 0.3 | 25.101(c)(5)(A)
0PT48556 0PT48557 (R8597) | SL East Stiles – Rocky Road 138 kV Line: Rebuild | City of Stiles, Reagan Country | Rebuild the SL East Stiles – Rocky Road 138 kV Line. | 2023-06-15 | 2023-09-29 | 2023-09-29 |  | 13809085 |  |  | 100 | 138 | na | 7.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 58 | 7.1 | na | na | 25.101(c)(5)(B)
0PT48359 0PT49344 (R8530) | Penwell POD - Wolf Switch 138 kV Line : Rebuild | Ward County | Rebuild/Reconductor the 9.5 mile Moss Switch - Red Lakes Switch 138 kV Line. | 2024-05-04 | 2024-12-19 | 2024-12-19 |  | 17500394 |  |  | 100 | 138 | na | 9.53 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 9.53 | na | na | 25.101(c)(5)(B)
0PT47103 0PT47345 (R8618) | SL Buffalo Switch - Triangle Switch 138 kV Line : Rebuild | City of Stanton, Martin County | Rebuild the Buffalo Switch - Triangle Switch138 kV Line on double-circuit structures with one circuit in place from Buffalo - Triangle. | 2023-06-15 | 2023-10-04 | 2023-10-04 |  | 7913408 |  |  | 100 | 138 | na | 3.5 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | Varies | 3.5 | na | na | 25.101(c)(5)(B)
0PT47022 (R6136) | Trinidad - Mexia 138 kV Line: Retermination at Ranchland Switch | City of Fairfield, Freestone County | Reterminate the Fairfield West - Jewett 138 kV Line at its new terminal location at Ranchland Switch. | 2023-01-23 | 2023-05-26 | 2023-05-26 |  | 1139613.5 |  |  | 100 | 138 | na | 0.25 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.25 | na | na | 25.101(c)(5)(A)
0PT46851 0PT47714 0PT48213 (R6211) | Brushy Creek Switch - Mallard Switch 138 kV Line : 69 kV Line Rebuild from Brushy Creek to Str. 1/5 | City of Taylor, Williamson County | Rebuild the Taylor - Elgin 69 kV line from Brushy Creek - Structure 1/5 as the Brushy Creek - Mallard 138 kV Line | 2023-03-22 | 2023-12-13 | 2023-12-13 |  | 19985182.47 |  |  | 100 | 69 | 138 | 10.7 | 1926.9 ACSS/TW CUMBERLAND | Steel H-Frame, Steel Pole | Varies | 10.6 | 70 | 0.1 | 25.101(c)(5)(B)
0PT46785 0PT49067 (M4326) | Italy Sub - Hillsboro Switch 69 kV Line: Rebuild Milford Exxon Tap - Hillsboro Switch | City of Hillsboro, Hill County | Rebuild the Milford Exxon Tap - Hillsboro section of the Italy Sub - Hillsboro Switch 69 kV | 2023-06-08 | 2023-12-15 | 2023-12-15 |  | 23726345 |  |  | 100 | 69 | na | 14.4 | 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel Pole | Varies | 14.4 | na | na | 25.101(c)(5)(b)
0PT46136 0PT48269 (R6094) | Chandler West Switch to Murchison Switch 69 kV: Rebuild to 138 kV | City of Brownsboro, City of Chandler, Henderson County | Rebuild a 9.2 miles section of the Athens to Tyler Switch 69 kV line as a 138 kV double circuit line with only one circuit installed. | 2023-06-22 | 2023-11-08 | 2023-11-08 |  | 18559930.84 |  |  | 100 | 69 | 138 | 9.2 | 959.6 ACSS/TW Suwannee | Steel H-Frame, Steel Pole | Centerline | 9.2 | na | na | 25.101(c)(5)(B) | Line will be operating as 69kV initially when it's back in service, once other associated line/station projects are finalized it will be converted to 138kV
0PT45889 (R6173) | Holland Sub - Bartlett Tap 69kV Line: Rebuild from Holland Sub to Str. 62/5 | City of Holland, Bell County | Rebuild the Holland Sub - Str 62/5 section of the Taylor Switch - Holland 69 kV Line. | 2023-06-13 | 2023-11-01 | 2023-11-01 |  | 8791887.09 |  |  | 100 | 69 | na | 5.6 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 5.6 | na | na | 25.101(c)(5)(B)
0PT44429 0PT44430 (R8564) | SL Driver Switch - SkyWest Switch 138 kV Line : Rebuild | Midland County | Rebuild 11.9 miles from T37 - SkyWest Switch section of the Driver Switch - SkyWest Switch 138 kV Line. | 2023-08-03 | 2024-06-03 | 2024-06-03 |  | 18259397 |  |  | 100 | 138 | na | 11.9 | 1926.9 ACSS/TW Cumberland | Steel Pole | 90 | 11.9 | na | na | 25.101(c)(5)(B)
0PT43937 0PT56562 (R6146) | Waco West - Waco East Switch - Elm Mott 138 kV Line: Retermination at McLane Switch | City of Waco, Waco County | Reterminate the Waco West - Waco East Switch - Elm Mott 138 kV Line at its new terminal location at McLane Switch. | 2025-03-25 | 2025-05-15 |  |  | 3063036.41 |  |  | 6 | 138 | na | 1 | 1926.9 ACSS/TW Cumberland | Steel Pole | varies | 0.5 | na | na | 25.101(c)(5)(A)
0PT43936 (R6146) | Lake Creek Switch - Waco East Switch 138 kV Line : Retermination at McLane Switch. | City of Waco, Waco County | Reterminate the Lake Creek Switch - Waco East Switch 138 kV Line at its new terminal location at McLane Switch. | 2025-09-01 | 2025-12-15 | [5 empty] | 0 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | varies | 0.4 | na | na | 25.101(c)(5)(A)
0PT43935 (R6146) | Waco East Switch - Waco West Sub 138 kV Line : Retermination at McLane Switch. | City of Waco, Waco County | Reterminate the Waco East Switch - Waco West Sub 138 kV Line at its new terminal location at McLane Switch. | 2025-09-01 | 2025-12-15 | [5 empty] | 0 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | varies | 0.4 | na | na | 25.101(c)(5)(A)
0PT43747 | Collin-Renner 138 kV: Panther Creek Parkway Relocation for City of Frisco | City of Frisco, Collin County | Relocation with new double circuit, steel monopole, tangent structure. | 2023-04-18 | 2023-05-15 | 2023-05-15 |  | 516383 |  |  | 100 | 138 | na | 0.34 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.17 | na | na | 25.101(C)(5)(F) | Relocation is at the request of the City of Frisco and is 100% reimbursable by the City of Frisco.
0PT43159 0PT49345 (R8530) | Red Lakes Switch - Penwell POD 138 kV Line: Rebuild | Ward, Winkler and Ector Counties | Rebuild the 11.0 mile Red Lakes Switch - Penwell POD 138 kV line | 2023-10-15 | 2024-05-23 | 2024-05-23 |  | 18306531 |  |  | 100 | 138 | na | 11 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 11 | na | na | 25.101(c)(5)(B)
0PT42525 0PT49816 (R4015) | Burnett Switch - Old Lake Switch 69 kV Line : Rebuild Lanham Tap - Old Lake Section to 138 kV | City of Wichita Falls, Clay County | Rebuild Lanham Tap - Old Lake section of the Burnett Switch - Old Lake Switch 69 kV Line to 138 kV. | 2023-05-03 | 2024-06-11 | 2024-06-11 |  | 19604624 |  |  | 100 | 69 | 138 | 10.8 | 959.6 ACSS/TW Suwannee | Steel Pole | 100 | 10.8 | na | na | 25.101(c)(5)(B)
0PT42092 0PT49409 (R8591) | Royalty Substation – Blair Lake Substation 69 kV Line : Conversion to 138 kV | Ward and Pecos Counties | Rebuild the Royalty Substation – Blair Lake Substation section of the Yucca Drive Switch – Northern Natural 69 kV Line and convert the circuit to 138 kV. | 2024-01-30 | 2024-09-12 | 2024-09-12 |  | 13756725.8 |  |  | 100 | 69 | 138 | 11.84 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | 11.84 | na | na | 25.101(c)(5)(B)
0PT50224 0PT49040 (R6165) | Hutto - Taylor 138 kV Line: Cut In Teal Switch | City of Hutto, Williamson County | Construct the cut-in line for the new Teal Switch station. | 2023-09-15 | 2023-12-15 | 2023-12-15 |  | 6286166.72 |  |  | 100 | na | 138 | 0.7 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 140 | 0.7 | 25.101(c)(5)(A)
0PT48946 0PT49111 | SL Coyote – Luther 138 kV Line: Coyote Retermination | City of Big Spring, Howard County | Line work associated with reterminating the Coyote - Luther 138 kV Line at its new terminal location at Coyote Substation. | 2023-02-01 | 2023-12-08 | 2023-12-08 |  | 583278 |  |  | 100 | 138 | na | 0.01 | 795 ACSR Drake | Steel Pole | 0.01 | 40 | na | na | 25.101(c)(5)(A)
0PT47577 (M4327) | Watermill Switch - Desoto Switch 345 kV Line : Cut-In Loop Nine Switch | City of Red Oak, Ellis County | Cut-in Watermill - Desoto and Waltermill - Cedar Hill 345 kV lines to establish the new Loop Nine Switch. | 2023-11-08 | 2024-04-01 | 2024-04-01 |  | 12324127.93 |  |  | 100 | 345 | na | 1.2 | 2 - 1926.9 ACSS/TW Cumberland | Steel 2 - Pole, Steel Pole | na | na | varies | 0.3 | 25.101(c)(5)(A)
0PT47850 (M4335) | Pebble Creek Switch - Red Mesquite 138 kV Lines: Install 2 single circuit POD lines | City of Red Oak, Ellis County | Build a new Pebble Creek Switch - Red Mesquite Substation 138 kV Line. | 2023-09-12 | 2024-12-01 | 2024-12-01 |  | 3259301.28 |  |  | 100 | na | 138 | 1 | 959.6 ACSS/TW Suwannee | Steel 2 - Pole, Steel 3 - Pole, Steel Pole | na | na | varies | 0.5 | 25.101(c)(5)(A)
0PT47041 (M4327) | Pebble Creek Switch - Loop Nine Switch 138 kV Line: Construct Line | City of Red Oak, Ellis County | Build a new Pebble Creek Switch - New Loop 9 Station 138 kV Line. | 2024-01-11 | 2024-05-10 | 2024-05-10 |  | 9458796.14 |  |  | 100 | na | 138 | 3.6 | 2 - 959.6 ACSS/TW Suwannee | Steel 2-Pole | na | na | varies | 1.8 | 25.101(c)(5)(A)
0PT48553 0PT49641 0PT51256 (R8640) | SL South Midland – Pecan Grove 138 kV Line: Rebuild | City of Midland, Midland County | Rebuild the South Midland - Pecan Grove 138 kV line. | 2023-08-27 | 2024-06-06 | 2024-06-06 |  | 20949939 |  |  | 100 | 138 | na | 7.8 | 1926.9 ACSS/TW Cumberland, 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H-Frame, Steel Pole | 70 | 7.3 | 70 | 0.5 | 25.101(c)(5)(B)
0PT40890 0PT50173 0PT51209 (R9047) | Yucca Drive Switch - Moss Switch 138 kV Line: Rebuild Section from Moss Switch to Future Oxy POD | City of Odessa, Ector County | Rebuild the first 12.7 miles of the Yucca Drive Switch - Moss Switch 138 kV Line, starting at Moss Switch. | 2023-11-16 | 2024-06-05 | 2024-06-05 |  | 24119836 |  |  | 100 | 138 | na | 12.7 | 1926.9 ACSS/TW Cumberland | Steel 2-Pole, Steel 3 - Pole, Steel Pole | varies | 12.7 | na | na | 25.101(c)(5)(B)
0PT47500 0PT51397 (R6228) | Waco West Switch - Temple Elm Creek Switch 138 kV Line: Install McGuffey point of delivery (POD) | City of McGregor, McLennan County | Provide a 138 kV point of delivery (POD) | 2023-06-11 | 2024-05-01 | 2024-05-01 |  | 6163600 |  |  | 100 | 69 | 138 | 5 | 1926.9 ACSS/TW Cumberland | Steel 2-Pole, Steel 3-Pole, Steel H-Frame, Steel Pole | 100 | 1.8 | 70 | 0.7 | 25.101(c)(5)(A)
0PT45437 (R6190) | Temple Elm Creek Switch - Belton Switch 138 kV Line : Install Pepper Creek Switch | City of Temple, Bell County | Cut in Pepper Creek Switch on the Temple Elm Creek Switch - Belton Switch 138 kV DCKT Line. | 2024-08-13 | 2024-12-01 | 2024-12-01 |  | 4865246.36 |  |  | 100 | 138 | na | 2.6 | 1926.9 ACSS/TW Cumberland , 959.6 ACSS/TW Suwannee | Steel Pole | na | na | varies | 1.3 | 25.101(c)(5)(A)
0PT46209 (R1743) | Lake Creek Switch - Marlin Switch 69kV Line: Conversion to 138kV | City of Marlin, Falls County | Rebuild the 13.7-mile Lake Creek Switch - Marlin Switch 69 kV Line, using 138 kV double-circuit structures with one circuit in place. | 2025-05-15 | 2025-09-15 | [5 empty] | 0 | 69 | 138 | 13.7 | 959.6 ACSS/TW Suwannee | Steel 2- Pole, Steel Pole | varies | 13.7 | na | na | 25.101(c)(5)(B)
0PT48698 0PT48727 (M4330) | Stone Creek Sw - Anna Sw 138 kV Line: Cut In Haggerty Switch | City of Sherman, Grayson County | The project will cut in the Stone Creek - Anna Switch 138 kV line into the new Haggerty Switch. | 2023-05-07 | 2023-10-03 | 2023-10-03 |  | 9770654.45 |  |  | 100 | na | 138 | 4 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | na | na | 100 | 2 | 25.101(c)(5)(A)
0PT50159 (R6191) | Waco West Switch - Temple 69 kV Line: Cut-In to Establish Bronze Age 138 kV Switch | City of Troy, Bell County | Cut in the Waco West Switch - Temple 69 kV Line to the establish the new Bronze Age Switch. | 2024-03-25 | 2024-06-19 | 2024-06-19 |  | 959294.86 |  |  | 100 | 69 | 138 | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 40 | 0.2 | na | na | 25.101(c)(5)(A)
0PT50158 (R6191) | Waco West Switch - Temple 69 kV Line: Cut-In to Establish Eddy 138 kV Switch | City of Bruceville-Eddy, McLennan County | Cut in the Waco West Switch - Temple 69 kV Line to the establish the new Eddy Switch. | 2023-10-20 | 2023-12-01 | 2023-12-01 |  | 625763.33 |  |  | 100 | 69 | 138 | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 45 | 0.1 | na | na | 25.101(c)(5)(A)
0PT50157 (R6191) | Waco West Switch - Temple 69 kV Line: Cut-In to Establish Lorena 138 kV Switch | City of Lorena, McLennan County | Cut in the Waco West Switch - Temple 69 kV Line to the establish the new Lorena Switch. | 2024-01-31 | 2024-03-19 | 2024-03-19 |  | 1119200.8 |  |  | 100 | 69 | 138 | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 40 | 0.1 | na | na | 25.101(c)(5)(A)
0PT49982 0PT57150 (R6094) | Sam Switch - Tradinghouse Switch 345 kV Line : Cut-in to establish Tiger Creek Switch | City of Waco, Bell County | Cut in tiger Creek Switch on the Sam Switch - Tradinghouse Switch 345 Line. | 2024-09-15 | 2024-12-01 | 2024-12-01 |  | 3540081.65 |  |  | 100 | 345 | na | 0.25 | 2-1926.9 ACSS/TW Cumberland | Steel Lattice Tower, Steel Pole | na | na | varies | 0.25 | 25.101(c)(5)(A)
0PT49807 0PT51085 (R8626) | Falcon Seaboard - Midland East 345 kV Line: Replace Structures 61/2-61/5 | City of Midland, Midland County | Rebuild a section of the Falcon Seaboard - Midland East 345 kV line. | 2023-10-28 | 2024-03-01 | 2024-03-01 |  | 4633089 |  |  | 100 | 345 | na | 1.6 | 2-1926.9 ACSS/TW Cumberland | Steel 2-Pole, Steel 3-Pole, Steel Pole | 150 | 1 | 150 | 0.6 | 25.101(c)(5)(B)
0PT48554 0PT49571 0PT50862 (R8646) | SL Einstein – St. Lawrence 138 kV Line: Rebuild | Glasscock County | Rebuild the SL Einstein – St. Lawrence 138 kV Line | 2023-09-26 | 2024-03-18 | 2024-03-18 |  | 11264371 |  |  | 100 | 138 | na | 4.6 | 1926.9 ACSS/TW Cumberland | Steel Pole | 75 | 4.6 | na | na | 25.101(c)(5)(B)
0PT48544 0PT48742 0PT50861 (R8638) | Blue Acres- Yosemite 138 kV Line: Rebuild | City of Midland, Midland County | Rebuild of the Yosemite - Blue Acres 138 kV Line. | 2023-10-02 | 2024-02-09 | 2024-02-09 |  | 13566439 |  |  | 100 | 138 | na | 5.9 | 1926.9 ACSS/TW Cumberland | Steel 2-Pole, Steel Multi-pole, Steel Pole | varies | 5.9 | na | na | 25.101(c)(5)(B)
0PT48029 | Ferris Sub - Wilmer Sub 69 kV Line : Ferris Sub Cut In | City of Ferris, Ellis County | Reconfigure and reterminate the Ferris Sub - Wilmer Sub 69 kV Line at the two (2) new terminals at Ferris Sub. | 2023-08-01 | 2024-05-15 | 2024-05-15 |  | 1610298.35 |  |  | 100 | 69 | na | 0.2 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 0.2 | na | na | 25.101(c)(5)(A)
0PT47905 (R8616) | Buchanan Ranch Sub - Blue Acres Sub 138 kV Line : Rebuild | City of Midland, Midland County | Rebuild the Blue Acres - Buchanan Ranch 138 kV line. | 2023-09-11 | 2023-10-09 | 2023-10-09 |  | 1156815 |  |  | 100 | 138 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | varies | 0.2 | na | na | 25.101(c)(5)(B)
0PT47911 0PT47900 0PT50219 (R8626) | SL Triangle - Yosemite 138kV Line: Rebuild | Martin and Midland Counties | Rebuild the Triangle - Yosemite 138 kV line. | 2023-08-30 | 2024-08-01 | 2024-08-01 |  | 23686900 |  |  | 100 | 138 | na | 11.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 11.2 | na | na | 25.101(c)(5)(B)
0PT48846 (M4354) | Allen Switch - Anna Switch 138 kV Line : Install POI for RCEC at Bloomdale 138 kV Switch | City of McKinney, Collin County | Cut-in the Allen Switch - Anna Switch 138 kV Line to establish Bloomdale 138 kV Switch | 2024-03-12 | 2024-10-01 | 2024-10-01 |  | 2144469 |  |  | 100 | 138 | na | 0.13 | 2-1926.9 ACSS/TW Cumberland | Steel Pole | na | na | varies | 0.13 | 25.101(c)(5)(A)
0PT48802 0PT57077 (R6146) | Waco East Switch - Bellmead Sub 138 kV Line: Retermination at Waco East | City of Waco, McLennan County | Reterminate the Waco East Switch - Bellmead Sub 138 kV Line at its new terminal location at McLane Switch. | 2025-04-01 | 2025-05-15 |  |  | 1840401.26 |  |  | 0 | 138 | na | 0.3 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.3 | na | na | 25.101(c)(5)(A)
0PT45958 0PT49410 (R8591) | Structure 3/6 – Thorntonville Sub – Ward Switch 69 kV Conversion to 138 kV | Monahans, Ward and Reeves Counties | Rebuild the Yucca Drive Switch – Crane Substation 69 kV Line between Structure 3/4 – Thorntonville Substation – Ward Switch and convert the circuit to 138 kV. | 2024-08-26 | 2024-12-13 | 2024-12-13 |  | 13490729 |  |  | 100 | 69 | 138 | 10.53 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 10.53 | na | na | 25.101(c)(5)(B)
0PT40562 0PT49411 (R8591) | Yucca Drive Switch - Structure 3/6 - 69 kV Line Conversion to 138 kV | Monahans, Ward County | Rebuild Yucca Drive Switch – Structure 3/6 – Thorntonville Sub – Ward Switch – Royalty – Coyanosa – Blair Lake Sub – Wolfcamp Tap – Courtney Creek 69 kV line and convert the circuit to 138 kV. | 2024-11-01 | 2024-12-13 | 2024-12-13 |  | 4439451.35 |  |  | 100 | 69 | 138 | 2.32 | 1926.6 ACSS/TW Cumberland | Steel Pole | 50 | 2.32 | na | na | 25.101(c)(5)(B)
0PT47024 0PT53137 (R6191) | Waco West Switch - Temple 69 kV Line: Convert to 138 kV | City of Waco, McLennan County | Convert the 31.4 mile existing 69 kV Line to 138 kV operations. This conversion contains a rebuild of the Eddy - Troy line section. | 2024-02-06 | 2024-06-21 | 2024-06-21 |  | 17551335 |  |  | 100 | 69 | 138 | 6.7 | 1926.9 ACSS/TW Cumberland | Steel 3-Pole, Steel H-Frame, Steel Pole | 40 | 6.7 | na | na | 25.101(c)(5)(B)
0PT47665 (M4329) | Pebble Creek Switch - Compass's Station: Install PODs #3 & #4 | City of Red Oak, Ellis County | Build two additional points of delivery from Pebble Creek Switch-Compass Station 138kV | 2023-10-15 | 2023-11-01 | 2023-11-01 |  | 226505.98 |  |  | 100 | na | 138 | 0.08 | 959.6 ACSS/TW Suwannee | na | Station Property | 0.04 | na | na | 25.101(c)(5)(A)
0PT41466 (R1752) | Marlin Switch - Lott Sub 69 kV Line : Retermination | City of Marlin, Falls County | Line work associated to Reterminating Marlin Switch. | 2025-01-27 | 2025-05-15 |  |  | 453691.33 |  |  | 1 | 69 | na | 0.09 | 959.6 ACSS/TW SUWANNEE | Steel Pole | Centerline | 0.09 | na | na | 25.101(c)(5)(A)
0PT41465 (R1752) | Marlin Switch - Groesbeck Sub 69 kV Line : Retermination | City of Marlin, Falls County | Line work associated to Reterminating Marlin Switch. | 2025-01-06 | 2025-05-15 |  |  | 1359735.35 |  |  | 11 | 69 | na | 0.06 | 959.6 ACSS/TW SUWANNEE | Steel 3 - Pole | 50 | 0.06 | na | na | 25.101(c)(5)(A)
0PT41464 (R1752) | Lake Creek Switch - Marlin Switch 69 kV Line : Retermination | City of Marlin, Falls County | Line work associated to Reterminating Marlin Switch. | 2025-01-27 | 2025-05-15 |  |  | 958606.07 |  |  | 1 | 69 | na | 0.25 | 959.6 ACSS/TW SUWANNEE | Steel Pole | 50 | 0.25 | na | na | 25.101(c)(5)(A)
0PT44505 0PT51476 (M5283) | Everman Sw. - Cleburne Sw. 138 kV Line: Wilshire Sub Cut-In | City of Burleson, Johnson County | Line work associated to Cutting In Wilshire Substation. The work is occurring on the Everman Switch - Cleburne Switch 138 kV line. | 2023-08-25 | 2023-12-15 | 2023-12-15 |  | 1186297.17 |  |  | 100 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 0.4 | na | na | 25.101(c)(5)(A)
0PT48805 R8593 | Expanse Switch - Volta Switch 345 kV Line: Tie Lines | Martin County | Install two 345 POIs to connect Oncor's Expanse Switch to WETT's Volta Switch. | 2023-11-03 | 2024-06-07 | 2024-06-07 |  | 513300.15 |  |  | 100 | na | 345 | 0.26 | 2 - 1926.9 ACSS/TW Cumberland | na | na | na | 160 | 0.26 | 25.101(c)(5)(A)
0PT43963 (R985) | Burrow POI - Royse Switch 138 kV Line: Rebuild and convert 69 kV Line to 138 kV operation | City of Royse City, Hunt & Collin Counties | Rebuild the 69 kV Line using a conductor rated 1649 A or greater as a part of the Commerce - Royse 69 kV line conversion to 138 kV | 2023-06-26 | 2023-12-14 | 2023-12-14 |  | 11913848.83 |  |  | 100 | 69 | 138 | 5.2 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 5.2 | na | na | 25.101(c)(5)(B)
0PT45420 (M3223) | Royse Switch - Terrell Switch 138/69 kV Line: Re-terminate at Terrell Switch | City of Terrell, Kaufman County | Re-terminate the Royse Switch - Terrell Switch 138 kV and 69 kV Lines to the Terrell Switch Station. | 2023-09-18 | 2023-12-11 | 2023-12-11 |  | 2820213 |  |  | 100 | 69/138 | 138 | 0.25 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.25 | na | na | 25.101(c)(5)(A)
0PT45229 (M3223) | Terrell Switch - Kaufman Northwest - Seagoville Switch 138 kV Line: Retermination at Terrell Switch | City of Terrell, Kaufman County | Re-terminate the Terrell Switch - Kaufman Northwest - Seagoville Switch 138 kV Line to the Terrell Switch Station. | 2023-09-11 | 2023-10-01 | 2023-10-01 |  | 1864912.7 |  |  | 100 | 138 | na | 0.27 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 0.14 | 70 | 0.13 | 25.101(c)(5)(A)
0PT45228 (M3223) | Royse Switch - Blackland - Terrell Switch 138 kV Line: Re-termination at Terrell Switch | City of Terrell, Kaufman County | Re-terminate the Royse Switch - Blackland - Terrell Switch 138 kV Line to the Terrell Switch Station. | 2023-09-15 | 2023-12-11 | 2023-12-11 |  | 1173408.65 |  |  | 100 | 138 | na | 0.12 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.12 | na | na | 25.101(c)(5)(A)
0PT48019 0PT51558 (R8672) | Morgan Creek Switch - Barber Lake Switch 138 kV Line : Rebuild the East circuit | City of Colorado City, Mitchell County | Rebuild the East Circuit of the Morgan Creek Switch - Barber Lake Switch 138 kV Line. | 2023-10-18 | 2024-05-14 | 2024-05-14 |  | 9436571 |  |  | 100 | 138 | na | 4.83 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 4.83 | na | na | 25.101(c)(5)(B)
0PT48008 | Marrs Switch - Rolling Hills 138 kV Line: Rolling Hills Substation Cut In | City of Fort Worth, Tarrant County | Cut into the Marrs Switch - Rolling Hills 138 kV Line to establish the new Rolling Hills Substation. | 2023-12-01 | 2023-12-19 | 2023-12-19 |  | 340033 |  |  | 100 | 138 | na | 0.2 | 1926.9 ACSS/TW Cumberland, 795 ACSR Drake | Steel Lattice Tower | varies | 0.2 | na | na | 25.101(c)(5)(A)
0PT47962 0PT49372 (R6220) | Waco West Switch - Temple Elm Creek Switch 138 kV Line : Waco Sanger Avenue Sub Cut In | City of Waco, McLennan County | Cut in the Waco West Switch - Temple Elm Creek Switch 138 kV Line at the Waco Sanger Avenue Sub. | 2023-10-13 | 2024-03-06 | 2024-03-06 |  | 180666.19 |  |  | 100 | 138 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 150 | 0.2 | na | na | 25.101(c)(5)(A)
0PT47961 0PT49224 (R6220) | Waco North Sub - Waco West Sub 138 kV Line : Waco Sanger Avenue Sub Cut In | City of Waco, McLennan County | Terminate the idle Waco North Tap - Waco West Sub 138 kV Line on new steel monopole deadends to accommodate the new Waco Sanger Avenue Sub configuration | 2023-09-08 | 2024-03-06 | 2024-03-06 |  | 839736.37 |  |  | 100 | 138 | na | 0.12 | 1926.9 ACSS/TW Cumberland | Steel 2-Pole | 150 | 0.12 | na | na | 25.101(c)(5)(A)
0PT47958 0PT49225 (R6220) | Waco West - Waco East Switch - Elm Mott Switch 138 kV Line : Waco Sanger Cut In | City of Waco, McLennan County | Reterminate the Waco West - Waco East Switch - Elm Mott 138 kV Line at its new terminal location at Waco Sanger Avenue Sub. | 2023-09-18 | 2024-03-06 | 2024-03-06 |  | 988490.45 |  |  | 100 | 138 | na | 0.12 | 1926.9 ACSS/TW Cumberland | Steel 2- Pole | 150 | 0.12 | na | na | 25.101(c)(5)(A)
0PT47634 (M3205) | Greenbrier Switch - Royse Switch 138 kV Line: Blackstock Substation Cut-In | Collin County | Cut in the Greenbrier Switch - Royse Switch 138 kV Line to establish the new Blackstock Substation. | 2025-10-13 | 2025-12-15 | [5 empty] | 0 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT47417 | Preston North Sub - Meadow Creek Sub 138 kV Line : Pumping Plant Replacement | City of Dallas, Dallas County | Replacing the one existing UG Transmission HPFF Pressurization Plants at Preston North Sub with a new HPFF Pressurization Plant. | 2024-03-18 | 2024-06-13 | 2024-06-13 |  | 948838 |  |  | 100 | 138 | na | na | 1500 AL HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT46976 (M4336) | Payne – MEMC Southwest Tap 138 kV Line: Rebuild | City of Sherman, Grayson County | Rebuild the Payne-MEMC Southwest Tap 138 kV Line | 2023-09-18 | 2023-12-12 | 2023-12-12 |  | 6,474,360 |  |  | 100 | 138 | na | 3.28 | 2-959.6 ACSS/TW Suwannee | Steel Pole | 100 | 3.28 | na | na | 25.101(c)(5)(B)
0PT46563 (M4071) | Cedar Crest Switch - Wall Street Sub 138 kV Line: Reterminate at Cedar Crest Switch | City of Dallas, Dallas County | Line work associated with the conversion of the Cedar Crest-Wall Street Line from 69 kV to 138 kV operation. Reterminate line from Cedar Crest Sub to Cedar Crest Switch. | 2023-10-15 | 2023-11-20 | 2023-11-20 |  | 283643.65 |  |  | 100 | 69 | 138 | 0.2 | 959.6 ACSS/TW Suwannee | Steel Lattice Tower | 100 | 0.2 | na | na | 25.101(c)(5)(B)
0PT45938 0PT51211 | Bennett Road Switch - Bowie Switch 69 kV Line : CMPC Line Hardening (Str. 86/3 - 86/4) | City of Bowie, Montague County | Line work associated with the hardening of the Bennett Road Switch – Bowie Switch 69 kV Line. | 2023-08-11 | 2023-11-15 | 2023-11-15 |  | 698288 |  |  | 100 | 69 | na | 0.5 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 0.5 | na | na | 25.101(c)(5)(B)
0PT47928 0PT51113 | Mountain Creek Switch-West Dallas Sub-West Levee Switch 138kV Line: Structure Replacement | City of Dallas, Dallas County | Rebuild 0.7 miles of the Mountain Creek Switch - West Dallas Sub 138 kV Line and 0.93 miles of the Mountain Creek Switch - West Levee Switch 138 kV Line. | 2024-02-23 | 2024-12-20 | 2024-12-20 |  | 5393743 |  |  | 100 | 138 | na | 1.68 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | 1.68 | na | na | 25.101(c)(5)(B)
0PT44573 (R6160) | Revolution Switch – Generator 138 kV Transmission Line Addition | City of Navarro, Navarro County | Oncor to establish Revolution 138 kV Switch to provide a point-of-interconnection for a solar generator | 2025-10-16 | 2025-12-04 | [5 empty] | 0 | na | 138 | 0.07 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 50 | 0.07 | 25.101(c)(5)(A)
0PT49552 (M3228) | Royse Switch - Shamburger Switch 345 kV Line : Cut-in to establish Poetry Switch | Kaufman County | Cut in the Royse Switch - Shamburger Switch 345 kV Line to establish the new Poetry Switch. | 2024-02-14 | 2024-06-04 | 2024-06-04 |  | 3498479.93 |  |  | 100 | 345 | na | 0.9 | 2 -1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 230 | 0.8 | na | na | 25.101(c)(5)(A)
0PT49662 (HB4150) | Monticello Switch - Woodard Switch 345 kV Line : Clearance Improvement | City of Mount Vernon, Franklin County | Replace 11 structures on the Monticello Switch - Woodard Switch 345 kV to improve clearances | 2024-07-22 | 2024-11-01 | 2024-11-01 |  | 11367782 |  |  | 100 | 345 | na | 33 | 2- 795 ACSR Drake | Steel Lattice Tower | varies | 33 | na | na | 25.101(c)(5)(B)
0PT47963 (R6220) | Waco West Switch - McGregor Phillips Switch 69 kV Line : Waco Sanger Avenue Sub Cut In | City of Waco, McLennan County | Reroute the Waco West Switch - McGregor Phillips Switch 69 kV Line around the rebuilt Waco Sanger Avenue Sub | 2023-08-30 | 2024-03-06 | 2024-03-06 |  | 3498479.93 |  |  | 100 | 69 | na | 0.23 | 1926.9 ACSS/TW Cumberland | Steel Pole | 150 | 0.23 | na | na | 25.101(c)(5)(A)
0PT45417 (M3223) | Royse Switch - Terrell Switch 138/69 kV Line: Re-terminate at Royse Switch | City of Royse City, Rockwall County | Re-terminate the Royse Switch - Terrell Switch 138 kV and 69 kV Line to the Royse Switch Station. | 2023-09-11 | 2023-12-11 | 2023-12-11 |  | 2887344.92 |  |  | 100 | 69/138 | na | 0.36 | 1926.9 ACSS/TW Cumberland | Steel Pole | Station Property | 0.36 | na | na | 25.101(c)(5)(A)
0PT48909 0PT49546 (R6138) | Pin Oak Switch - Fairfield West Switch 138 kV Line: Rebuild Fairfield Switch (BEPC) - Big Brown Tap | City of Fairfield, Freestone County | Rebuild the 2.8 mile Pin Oak Switch – Fairfield West Switch 138 kV Line section from Fairfield Switch (BEPC) to Big Brown Tap using double circuit structures with one circuit in place. | 2023-11-14 | 2023-12-29 | 2023-12-29 |  | 4953213 |  |  | 100 | 138 | na | 2.8 | 1926.9 ACSS/TW Cumberland | Steel H-Frame, Steel Pole | 100 | 2.8 | na | na | 25.101(c)(5)(B) | This line is a shared ownership with Brazos and Brazos will reimburse Oncor for their portion of the cost.
0PT48044 (M5231) | Everman Switch - Burleson Switch 138 kV Line: Cut-in to Est Rendon Sub | City of Burleson, Tarrant County | Cut in the Everman Switch - Burleson Switch 138 kV line to establish the new Rendon Substation. | 2024-10-18 | 2024-12-31 | 2024-12-31 |  | 627721.25 |  |  | 100 | 138 | na | 0.18 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 0.18 | na | na | 25.101(c)(5)(A)
0PT48279 (M4326) | Italy Sub - Hillsboro Switch 69 kV Line: Rebuild Italy Sub - Milford Exxon Tap | City of Italy, Ellis County | Rebuild the Italy Sub - Milford Exxon Tap section of the Italy Sub - Hillsboro Switch 69 kV Line. | 2026-02-23 | 2026-05-15 | [5 empty] | 0 | 69 | na | 5 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 5 | na | na | 25.101(c)(5)(b)
0PT50482 (R6211) | Pintail Switch - Teal Switch 138 kV Line : Add Second Circuit from Taylor West to Teal | City of Hutto, Williamson County | Install a second circuit on the Pintail - Teal 138 kV line from Taylor West to Teal | 2023-09-18 | 2023-12-15 | 2023-12-15 |  | 3361493.52 |  |  | 100 | 138 | na | 2.67 | 1926.9 ACSS/TW Cumberland | Steel Pole | varies | 2.67 | na | na | 25.101(c)(5)(C)
0PT50250 0PT52154 (R6260) | Leon Switch - Dublin Sub 69 kV Line: Establish Ellison Springs 69 kV point of interconnection (POI) | City of Gorman, Comanche County | Establish a Point of Interconnect on the Leon Switch - Dublin Sub 69 kV line. | 2023-10-23 | 2023-12-15 | 2023-12-15 |  | 2561680.01 |  |  | 100 | 69 | na | 0.5 | 1926.9 ACSS/TW Cumberland, 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H –Frame Switch, Steel Pole | varies | 0.3 | varies | 0.2 | 25.101(c)(5)(A)
0PT48097 0PT49201 (R6172) | McGregor Phillips Tap Switch - Waco West Switch 69 kV Line : Rebuild Structure 15/2 to Harris Creek Sub | City of McGregor, McLennan County | Rebuild from structure 15/2 to Harris Creek Sub on double circuit monopoles with one circuit installed. | 2023-09-04 | 2023-12-22 | 2023-12-22 |  | 12561670 |  |  | 100 | 69 | 138 | 8 | 1926.9 ACSS/TW Cumberland | Steel 2-Pole, Steel 3-Pole, Steel Pole | varies | 8 | na | na | 25.101(c)(5)(B)
0PT50897 (R8672) | Morgan Creek Switch - Sun Switch 138 kV Line : Structure Replacement | City of Colorado City, Mitchell County | Replace and restring structure to accommodate Morgan Creek - Barber Lake 138 kV Line. | 2023-10-17 | 2023-12-01 | 2023-12-01 |  | 481791.77 |  |  | 100 | 138 | na | 0.15 | 636 ACSR Grosbeak | Steel 3-Pole | 100 | 0.15 | na | na | 25.101(c)(5)(B)
0PT50414 (R8703) | Upton Sub - Goodnight Sub 138 kV Line : Establish 138 kV Point of Interconnect for point of interconnection (POI) | City of Midkiff,Upton County | Establish 138 kV point of interconnection (POI) | 2023-11-09 | 2023-12-19 | 2023-12-19 |  | 949357.32 |  |  | 100 | 138 | na | 0.04 | 1926.9 ACSS/TW Cumberland | Steel Pole | Station Property | 0.04 | na | na | 25.101(c)(5)(A)
0PT49480 0PT54476 | Graham Plant Switch - Breckenridge-Leon Switch 138 kV Line : Substation reconfiguration | City of Graham, Young County | Retermination of the Graham Plant Switch - Breckenridge-Leon Switch 138 kV Line to establish the higher voltage of South bend Sub. | 2024-11-05 | 2024-12-10 | 2024-12-10 |  | 697097 |  |  | 100 | 138 | na | 0.1 | 636 ACSR Grosbeak | Wood H-Frame | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT49258 0P48066 (R3028) | SL Alibates Switch - Tule Canyon Switch 345 kV Line: Establish Midpoint Switch for point of interconnection (POI) | Armstrong County | Cut in the Alibates Switch - Tule Canyon Switch 345 kV Line to establish the new Midpoint Switch. | 2023-09-19 | 2023-11-14 | 2023-11-14 |  | 1564121 |  |  | 100 | 345 | na | 0.1 | 2-1926.9 ACSS/TW Cumberland | Steel Lattice Towers | na | na | 300 | 0.1 | 25.101(c)(5)(A)
0PT50337 (M3205) | Royse Switch - Nevada 138 kV Line: Blackstock Substation Cut-In | Collin County | Cut in the Royse Switch - Nevada 138 kV Line to establish the new Blackstock Substation. | 2024-11-19 | 2025-12-15 |  |  | 865778.52 |  |  | 1 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT48041 (M4322) | Ennis West Switch - Sterrett Switch 138 kV Line: Cut In Templeton Substation | City of Waxahachie, Ellis County | Cut-in the Templeton Substation into the Ennis West Switch - Sterrett Switch 138 kV Line | 2023-12-03 | 2023-12-21 | 2023-12-21 |  | 1275505 |  |  | 100 | 138 | na | 0.39 | 2-959.6 ACSS/TW Suwannee | Steel Pole, Wood H-Frame | 80 | 0.39 | na | na | 25.101(c)(5)(A)
0PT49251 (R3029) | AJ Swope Switch - Carol Wind POI 345 kV Line : Install Line for point of interconnection (POI) | Potter County | Establish 345 kV point of interconnection (POI) | 2024-10-21 | 2025-12-04 |  |  | 1941246 |  |  | 99* | na | 345 | 0.2 | 2-1926.9 ACSS/TW Cumberland | Steel Pole | Station Property | 0.2 | na | na | 25.101(c)(5)(A)
0PT49236 (M4338) | Stone Creek Switch - Whitesboro Jordan Sub 138 kV Line : Cut-in Southmayd Switch | Grayson County | Cut in the Stone Creek Switch - Whitesboro Jordan Sub 138 kV Line to establish the new Southmayd Switch. | 2025-11-01 | 2027-05-13 | [5 empty] | 0 | 138 | na | 0.04 | 2-959.6 ACSS/TW Suwannee | Steel Pole | na | na | 100 | 0.02 | 25.101(c)(5)(A)
0PT48645 R8634 | Odessa EHV Switch - Spraberry Switch 138 kV Line : Establish Tesoro Switch | Midland County | Cut into the Odessa EHV Switch - Spraberry Switch 138 kV Line to establish the new Tesoro Switch. | 2023-10-24 | 2023-12-14 | 2023-12-14 |  | 2298381.93 |  |  | 100 | 138 | na | 0.7 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | 50 | 0.6 | 200 | 0.1 | 25.101(c)(5)(A)
0PT47633 (R6178) | Hutto Switch - Gilleland Creek Switch 138 kV line: Cut-In to Establish Star Ranch Sub | City of Hutto, Williamson County | Cut-in the Hutto Switch - Gilleland Creek 138 kV line to establish the new Starr Ranch Sub. | 2023-11-01 | 2023-12-13 | 2023-12-13 |  | 2592531.45 |  |  | 100 | 138 | na | 0.6 | 1926.9 ACSS/TW Cumberland | Steel Pole | 40 | 0.3 | na | na | 25.101(c)(5)(A)
0PT46152 0PT52027 0PT51317 (R8630) | McDonald Road Switch - Spraberry Switch 138 kV Line : Install Oncor Wrage Ranch POD | City of Garden City, Glasscock County | Establish a 138 kV point of delivery (POD) | 2024-09-19 | 2025-07-01 |  |  | 4158265.18 |  |  | 99* | 138 | na | 1.5 | 1926.9 ACSS/TW Cumberland | Steel 3-pole, Steel Pole, Steel H-Frame, Steel Pole | 50 | 0.2 | varies | 1.3 | 25.101(c)(5)(A)
0PT47794 (R6219) | Taylor Switch - Sandow Switch 138 kV Line : Cut-in for Rookie Switch | Milam County | Cut in the Taylor Switch - Sandow Switch 138 Line to establish the new Rookie Switch. | 2024-03-11 | 2024-05-08 | 2024-05-08 |  | 2231271 |  |  | 100 | 138 | na | 0.5 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 100 | 0.25 | 25.101(c)(5)(A)
0PT48667 0PT49223 (M4137) | Mesquite E Station - Mesquite N Station 138 kV Line: Rebuild Mesquite Town East Station -Mesquite North Station - Mesquite North Tap | City of Mesquite, Dallas County | Rebuild the Mesquite Town East Station - Mesquite North Station - Mesquite North Tap 138 kV Line. | 2025-03-11 | 2025-05-15 |  |  | 7980271.14 |  |  | 34 | 138 | na | 4.5 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 2.25 | na | na | 25.101(c)(5)(B)
0PT46380 (M4212) | Cedar Crest Switch - Dealey Street - West Levee Switch 138 kV Line: Reconductor | City of Dallas, Dallas County | Reconductor the T27 - Dealey Street - West Levee Switch section of the Cedar Crest Switch - Dealey Street - West Levee Switch 138 kV line. | 2025-01-15 | 2025-05-15 |  |  | 5682497.06 |  |  | 47 | 138 | na | 2.4 | 1590 ACSR Falcon | Steel Pole | 80 | 2.4 | na | na | 25.101(c)(5)(A)
0PT49765 R8634 | Consavvy Switch - Quail Switch 345 kV Line : Establish Tesoro Switch | Midland County | Cut into the Consavvy Switch - Quail Switch 345 kV Line to establish the new Tesoro Switch. | 2023-12-06 | 2023-12-27 | 2023-12-27 |  | 2605656.42 |  |  | 100 | 345 | na | 0.3 | 2-1926.9 ACSS/TW Cumberland | Steel Pole | 120 | 0.3 | na | na | 25.101(c)(5)(A)
0PT48648 R8634 | Midessa South Switch - Odessa EHV Switch 345 kV Line : Establish Tesoro Switch | Midland County | Cut into the Midessa South Switch - Odessa EHV Switch 345 kV Line to establish the new Tesoro Switch. | 2023-09-20 | 2024-02-05 | 2024-02-05 |  | 3167643.39 |  |  | 100 | 345 | na | 0.3 | 2-1926.9 ACSS/TW Cumberland | Steel Pole | 120 | 0.3 | na | na | 25.101(c)(5)(A)
0PT48664 (M4137) | Mesquite E Station - Mesquite N Station 138 kV Line: Rebuild Sunnyvale Station to Mesquite Town East Station | City of Mesquite, Dallas County | Rebuild the Sunnyvale - Mesquite Town East Station 138 kV Line. | 2023-07-14 | 2023-12-12 | 2023-12-12 |  | 10338011 |  |  | 100 | 138 | na | 6.3 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 3.15 | na | na | 25.101(c)(5)(B)
0PT50371 (R8581) | Wink Switch Autotransformer #1 - Wink Switch 69 kV Line: Re-termination | City of Kermit, Winkler County | Re-terminate the Wink Switch Autotransformer #1 - Wink Switch 69 kV Line on the Structure 1/2 - Wink Switch section. | 2023-06-07 | 2023-08-30 | 2023-08-30 |  | 396687.22 |  |  | 100 | 69 | na | 0.2 | 959.6 ACSS/TW Suwannee | Wood 3 - Pole, Wood H-Frame | 80 | 0.2 | na | na | 25.101(c)(5)(A)
0PT49517 (R8674) | Driver Sub - DJ Hutt 138 kV: Station Tie Line Build | Midland County | Establish 138 kV point of interconnection (POI) | 2023-11-10 | 2023-12-20 | 2023-12-20 |  | 703577.38 |  |  | 100 | na | 138 | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | varies | 0.1 | na | na | 25.101(c)(5)(A)
0PT45019 (M4071) | Cedar Crest Switch - Sargent RD Sub 138 kV Line : Reterminate at Cedar Crest SW | City of Dallas, Dallas County | Reterminate the Cedar Crest SW – Sargent Road Sub 138 kV Line from its existing bay to its new bay. | 2023-09-07 | 2023-09-22 | 2023-09-22 |  | 571160.71 |  |  | 100 | 138 | na | 0.2 | 959.6 ACSS/TW Suwannee | Steel Pole | 100 | 0.2 | na | na | 25.101(c)(5)(B)
0PT45959 0PT49227 (R8591) | Ward Switch - Royalty Sub 69 kV Line : Conversion to 138 kV | City of Grandfalls, Ward County | Rebuild the Ward Switch – Royalty Substation section of the Yucca Drive Switch – Crane Substation 69 kV Line. | 2024-05-14 | 2024-12-13 | 2024-12-13 |  | 7114968 |  |  | 100 | 69 | 138 | 5.06 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 5.06 | na | na | 25.101(c)(5)(B)
0PT48043 (R6226) | Cut-In to Establish South Hewitt Sub | City of Waco, McLennan County | Cut in the Waco West - Temple 69 kV Line at the newly established Castleman Sub | 2023-11-06 | 2023-12-14 | 2023-12-14 |  | 1393782.1 |  |  | 100 | 69 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 40 | 0.2 | na | na | 25.101(c)(5)(A)
0PT46488 | Lufkin Switch - Redland Switch 138 kV Line: Kolb Lake POD | City of Lufkin, Angelina County | Provide a 138 kV point of delivery to Kolb Lake POD | 2024-11-05 | 2025-03-31 |  |  | 2490831.68 |  |  | 99* | 138 | na | 0.22 | 959.6 ACSS/TW Suwannee | Steel 3-pole, Steel Pole, Steel H-Frame, | 100 | 0.1 | varies | 0.12 | 25.101(c)(5)(A)
0PT49588 | Calmont Switch - Benbrook Switch 138 kV Line: Add OPGW | City of Fort Worth, Tarrant County | Install OPGW from Calmont Switch to Benbrook Switch. | 2023-10-30 | 2023-12-21 | 2023-12-21 |  | 1721324.86 |  |  | 100 | 138 | na | 4.7 | 1233.6 ACSS/TW Yukon | Steel Lattice Tower | Varies | 4.7 | na | na | 25.101(c)(5)(A)
0PT47806 (R6218) | Bell County East Switch - TNP One (TNMP) Switch 345 kV Line : Cut-in to establish Gibson Switch | City of Cameron, Milam County | Cut into the Bell County East - TNP One (TNMP) 345 kV Line to establish the new Gibson Switch. | 2023-09-29 | 2023-12-09 | 2023-12-09 |  | 1707517.11 |  |  | 100 | 345 | na | 0.2 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 160 | 0.1 | varies | 0.1 | 25.101(c)(5)(A)
0PT47807 (R6188) | Bell County East Switch - TNP One (TNMP) Switch 345 kV Line : Cut-in to establish Little Pond Switch | City of Burlington, Milam County | Cut into the Bell County East - TNP One (TNMP) 345 kV Line to establish the new Little Pond Switch. | 2023-09-22 | 2023-12-09 | 2023-12-09 |  | 2074518.49 |  |  | 100 | 345 | na | 0.2 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 160 | 0.1 | varies | 0.1 | 25.101(c)(5)(A)
0PT48986 (R8659) | Midland East Switch - Midessa South Switch 138 kV Line : Cut-In Sloan Switch for Point of Interconnection | Midland County | Cut in the Midland East Switch - Midessa South Switch 138 kV Line to establish Sloan Switch | 2025-04-01 | 2025-05-08 |  |  | 2158169 |  |  | 0 | 138 | na | 0.08 | 1926.9 ACSS/TW Cumberland | Steel Pole | Station Property | 0.08 | na | na | 25.101(c)(5)(A)
0PT48994 (R8659) | Sloan Switch - Holzer Sub 138 kV Line : Install Point of Interconnection | Midland County | Establish a 138 kV Point of Interconnection from Sloan Switch to customer. | 2025-09-01 | 2025-12-04 | [5 empty] | 0 | na | 138 | 0.14 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 70 | 0.14 | 25.101(c)(5)(A)
0PT46786 0PT54267 (R4015) | Old Lake Switch - Bellevue Sub 69 kV Line: Rebuild to Old Lake Switch - Smith Creek Sub | City of Henrietta, Clay County | Rebuild the Old Lake Switch - Bellevue Sub. Bellevue Sub will be rebuilt as Smith Creek Sub. | 2024-06-06 | 2024-11-14 | 2024-11-14 |  | 13824822 |  |  | 100 | 69 | 138 | 10.8 | 959.6 ACSS/TW SUWANNEE | Steel Pole | 50 | 10.8 | na | na | 25.101(c)(5)(B)
0PT46977 (M4330) | Payne - Valley 138 kV Line: Add OPGW | Grayson County | Add OPGW to the Payne (16/10) to Valley 138 kV line. | 2023-10-16 | 2024-05-13 | 2024-05-13 |  | 2895486 |  |  | 100 | 138 | na | 19.19 | 1590 ACSR FALCON | Steel Pole | varies | 19.19 | na | na | 25.101(c)(5)(B)
0PT47658 0PT51210 (M4328) | Pebble Creek Switch - Desoto Switch 138 kV Line : Rebuild | City of Desoto, Ellis County | Rebuild the Red Oak to Desoto Switch 138 kV line. | 2024-04-03 | 2024-06-05 | 2024-06-05 |  | 7074033 |  |  | 100 | 138 | na | 3 | 2 - 959.6 ACSS/TW SUWANNEE | Steel 3 - Pole, Steel Pole | 100 | 3 | na | na | 25.101(c)(5)(B)
0PT48559 0PT51390 0PT50404 0PT51921 (R8637) | SL Driver – Hadacol Corner 138 kV Line: Rebuild | Glasscock County | Rebuild the Driver – Hadacol Corner 138 kV line. | 2024-02-13 | 2024-08-30 | 2024-08-30 |  | 8367555 |  |  | 100 | 138 | na | 3.2 | 1926.9 ACSS/TW Cumberland | Steel 3- Pole, Steel H-Frame Switch, Steel Pole | 90 | 3.2 | na | na | 25.101(c)(5)(B)
0PT48561 0PT52901 (R8303) | Big Spring West Switch – Stanton East Switch 138 kV Line: Rebuild | Howard County | Rebuild the Onemile Switch (Big Spring West) – Stanton East Switch 138 kV Line. | 2024-02-07 | 2024-12-15 | 2024-12-15 |  | 32043703 |  |  | 100 | 138 | na | 16.5 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 70 | 16.5 | na | na | 25.101(c)(5)(B)
0PT48562 0PT49583 0PT53319 (R8635) | SL Tall City – Pecan Grove 138 kV Line: Rebuild | Midland County | Rebuild SL Tall City – Pecan Grove 138 kV Line. | 2024-03-21 | 2024-06-01 | 2024-06-01 |  | 15694795 |  |  | 100 | 138 | na | 7.5 | 1926.9 ACSS/TW CUMBERLAND | Steel 3- Pole, Steel pole | 70 | 7.45 | 70 | 0.05 | 25.101(c)(5)(B)
0PT48567 0PT43110 0PT52074 (R8636) | SL Luther – Vealmoor 138 kV Line: Rebuild | Borden and Lamar County | Rebuild the SL Luther - Vealmoor 138 kV Line | 2024-01-24 | 2024-06-12 | 2024-06-12 |  | 18076053 |  |  | 100 | 138 | na | 10 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | Varies | 10 | na | na | 25.101(c)(5)(B)
0PT48570 0PT51255 (R8360) | McDonald Road Sub - Morgan Creek Switch 138 kV Line: Rebuild Navigation Sub to Morgan Creek Switch | City of Colorado City, Mitchell County | Rebuild the Navigation Sub - Morgan Creek Switch 138 kV section on the McDonald Road Switch - Morgan Creek Switch 138 kV line. | 2024-06-27 | 2024-11-16 | 2024-11-16 |  | 27897986 |  |  | 100 | 138 | na | 20.3 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 20.3 | na | na | 25.101(c)(5)(B)
0PT48571 0PT51254 (R8360) | McDonald Road Switch - Morgan Creek Switch 138 kV Line: Rebuild McDonald Road to Navigation Sub | City of Big Spring, Howard County | Rebuild the McDonald Road Switch - Navigation Sub 138 kV section on the McDonald Road Switch - Morgan Creek Switch 138 kV line. | 2024-01-24 | 2024-05-15 | 2024-05-15 |  | 11292287 |  |  | 100 | 138 | na | 7.7 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 7.7 | na | na | 25.101(c)(5)(B)
0PT48572 0PT52382 (R8645) | Spraberry Switch – Polecat Creek Switch 138 kV Line: Rebuild Spraberry Switch to Quartz Sand Switch | City of Odessa, Midland County | Rebuild the line from Spraberry Switch to the newly established Quartz Sand Switch. | 2023-11-21 | 2024-08-06 | 2024-08-06 |  | 22619614 |  |  | 100 | 138 | na | 16.1 | 1926.9 ACSS/TW CUMBERLAND, 636 ACSR GROSBEAK | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 16.1 | na | na | 25.101(c)(5)(B)
0PT49378 | Wichita Falls South Switch - Alvord Sub 138 kV Line : Replace Lake Arrowhead Tap | City of Wichita Falls, Wichita County | Replace POD switch structure on Wichita Falls South Switch - Alvord Sub 138 kV Line | 2024-01-11 | 2024-02-14 | 2024-02-14 |  | 1963447 |  |  | 100 | 138 | na | 0.22 | 636 ACSR GROSBEAK | Steel H –Frame Switch, Steel Multi-pole | 50 | 0.22 | na | na | 25.101(c)(5)(B)
0PT49596 0PT51519 (R8475) | Lamesa Switch - McKenzie Draw Switch 138 kV Line : Rebuild from Jim Payne POI - Lamesa Switch | City of Lamesa, Dawson County | Rebuild the Lamesa Switch - Jim Payne POI 138 kV Line. | 2024-01-19 | 2024-05-15 | 2024-05-15 |  | 14022070 |  |  | 100 | 138 | na | 7.82 | 1926.9 ACSS/TW CUMBERLAND | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 7.82 | na | na | 25.101(c)(5)(B)
0PT45633 0PT56700 (R6246) | Graham Plant Switch - Breckenridge - Leon Switch 138 kV Line: Cut-in to establish Ghost Town Switch | City of Breckenridge, Stephens County | Cut in the Graham Plant Switch - Breckenridge - Leon Switch 138 kV line to establish the new Ghost Town Switch. | 2024-05-07 | 2024-10-30 | 2024-10-30 |  | 1522952 |  |  | 100 | 138 | na | 0.3 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 60 | 0.1 | 120 | 0.1 | 25.101(c)(5)(A)
0PT50441 (R8679) | Lamesa Switch - POI 138 kV Line: Install Line | City of Lamesa, Dawson County | Establish 138 kV point of interconnection (POI) | 2024-03-04 | 2024-05-28 | 2024-05-28 |  | 580644 |  |  | 100 | na | 138 | 0.1 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | na | na | 100 | 0.1 | 25.101(c)(5)(A)
0PT50440 (R6253) | Temple Pecan Creek Switch - POI 138 kV Line: Install Line | City of Temple, Bell County | Establish 138 kV point of interconnection (POI) | 2025-02-18 | 2025-05-08 |  |  | 1100566.36 |  |  | 99* | na | 138 | 0.1 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | na | na | 100 | 0.1 | 25.101(c)(5)(A)
0PT50335 (R6256) | Jewett Switch - St. Johns Switch 345 kV Line: Cut-in to establish Bale Switch | Falls County | Cut in the Jewett Switch - St. Johns Switch 345 kV line to establish the new Bale Switch. | 2024-04-05 | 2024-05-17 | 2024-05-17 |  | 2464149 |  |  | 100 | 345 | na | 0.1 | 2 -1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 225 | 0.1 | na | na | 25.101(c)(5)(A)
0PT50370 (R6257) | Lufkin Switch - Crockett Switch 138 kV Line: Cut-in to establish Rowan Creek Switch | City of Lufkin, Angelina County | Cut in the Lufkin Switch - Crockett Switch 138 kV line to establish the Rowan Creek Switch. | 2024-09-10 | 2025-01-24 | 2025-01-24 |  | 1469773 |  |  | 100 | 138 | na | 0.1 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT48020 0PT52793 (R8623) | Morgan Creek Switch - Barber Lake Switch 138 kV Line: Rebuild the West circuit | City of Colorado City, Mitchell County | Rebuild the West circuit of Morgan Creek Switch - Barber Lake Switch 138 kV Line. | 2024-01-18 | 2024-05-02 | 2024-05-02 |  | 8654396 |  |  | 100 | 138 | na | 4.75 | 1926.9 ACSS/TW Cumberland | Steel 2 - Pole, Steel 3 - Pole, Steel Pole | Varies | 4.75 | na | na | 25.101(c)(5)(B)
0PT47551 (R8709) | Paint Creek Switch - China Grove Switch 138 kV Line: Install Raven POI | City of Sylvester, Fisher County | Establish the Raven POI | 2024-02-05 | 2024-06-27 | 2024-06-27 |  | 2736025 |  |  | 100 | 138 | na | 0.55 | 1926.9 ACSS/TW CUMBERLAND, 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel H –Frame Switch, Steel Pole | 50 | 0.4 | 100 | 0.15 | 25.101(c)(5)(A)
0PT50272 (M4356) | Tri Corner Switch - Anole BESS 345 kV Line : Establish 345 kV POI | City of Combine, Dallas County | Cut in the Tri Corner Switch – Anole BESS 345 kV line | 2024-03-14 | 2025-03-28 | 2025-03-28 |  | 2287745 |  |  | 100 | na | 345 | 0.13 | 2-1926.9 ACSS/TW Cumberland | Steel Lattice Tower | na | na | varies | 0.13 | 25.101(c)(5)(A)
0PT48505 0PT52751 0PT52755 0PT53138 (R8528) | Odessa EHV Switch - Edwards Tap 138 kV Line: Rebuild | City of Odessa, Ector County | Rebuild the Odessa EHV Switch to Edwards Tap 138kV Line | 2024-04-30 | 2024-12-14 | 2024-12-14 |  | 38327027 |  |  | 100 | 138 | na | 16.2 | 1926.9 ACSS/TW CUMBERLAND, 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 16.1 | varies | 0.1 | 25.101(c)(5)(B)
0PT48038 (M3504) | Wise County Switch - Jack County Switch 138 kV Line: Cut - In to Establish Runaway Bay Substation | City of Runaway Bay, Wise County | Cut into the Brazos Electric-owned line to establish Oncor Electric-owned Runaway Bay Substation. | 2024-05-08 | 2024-11-06 | 2024-11-06 |  | 300663 |  |  | 100 | na | 138 | 0.06 | 1926.9 ACSS/TW CUMBERLAND | na | 0.06 | Station Property | na | na | 25.101(c)(5)(A)
0PT51953 | Sandow Switch - Taylor Sub 138 kV Line : Thorndale North Sub Re-termination | City of Thorndale, Milam County | Re-terminate existing Sandow Switch - Taylor 138 kV Line at its new location inside Thorndale North Sub. | 2023-11-29 | 2023-12-15 | 2023-12-15 |  | 452731.74 |  |  | 100 | 138 | na | 0.1 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT47755 (R6214) | Temple Switch - Minerva Switch 69 kV Line : Cut-in to establish McFall Switch | City of Cameron, Milam County | Cut into the Temple Switch - Minerva Switch 69 kV Line to establish the new McFall Switch | 2024-03-27 | 2024-06-01 | 2024-06-01 |  | 1605399 |  |  | 100 | 69 | na | 0.1 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | varies | 0.1 | 25.101(c)(5)(A)
0PT48361 (M4001) | Venus Switch - Liggett Switch 345 kV Line : Cut-in Endeavor Switch | City of Midlothian, Ellis County | Cut in the Venus - Liggett 345 kV Line to establish the new Desert Willow Switching Station. | 2024-04-22 | 2024-12-11 | 2024-12-11 |  | 3114703 |  |  | 100 | 345 | na | 0.2 | 2 -1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | 160 | 0.2 | na | na | 25.101(c)(5)(A)
0PT49484 0PT53277 | Hutto Switch - Round Rock Sub 138 kV Line : Relocation for Old Settlers Blvd | City of Round Rock, Williamson County | Relocate structure 13/4 to 13/11 due to city expansion of roadway. | 2024-04-03 | 2024-07-01 | 2024-07-01 |  | 1985880 |  |  | 100 | 138 | na | 0.9 | 1590 ACSR Falcon | Steel Pole | 100 | 0.9 | na | na | 25.101(c)(5)(F)
0PT50059 (R8667) | Vincent Sub - Wildhorse POD 138 kV Line : Rebuild | Howard County | Rebuild the Vincent Sub - Wildhorse POD 138 kV Line. | 2024-01-29 | 2024-04-30 | 2024-04-30 |  | 7732021 |  |  | 100 | 138 | na | 4.13 | 1926.9 ACSS/TW Cumberland | Steel Pole | 75 | 4.13 | na | na | 25.101(c)(5)(B)
0PT50347 (R8678) | Yucca Drive Switch - Moss Switch 138 kV Line : Cut-in to establish Raceway Switch | City of Odessa, Ector County | Cut into the Yucca Drive Switch - Moss Switch 138 kV Line to establish the new Raceway Switch. | 2024-04-04 | 2024-06-01 | 2024-06-01 |  | 1232895 |  |  | 100 | 138 | na | 0.19 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 75 | 0.19 | 25.101(c)(5)(A)
0PT50418 (M3500) | Bennett Road Switch - Krum Tap Switch 138 kV Line: Cut-In Denton Creek Switch | City of Decatur, Wise County | Cut in the new Denton Creek Switch. | 2024-04-22 | 2024-05-15 | 2024-05-15 |  | 1557404 |  |  | 100 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | Centerline | 0.1 | na | na | 25.101(c)(5)(A)
0PT50909 (R985) | Commerce Sub - Commerce Switch 138 kV Line : Re-termination at Commerce Switch | City of Commerce, Hunt County | Re-terminate the Commerce Substation - Commerce Switch 138 kV line at Commerce Switch. | 2024-03-28 | 2024-05-15 | 2024-05-15 |  | 928794 |  |  | 100 | 138 | na | 0.15 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0.15 | na | na | 25.101(c)(5)(B)
0PT51088 0PT50513 0PT53094 (M5281) | Roanoke Switch - Euless /Deen Switch 138 kV Line: Retermination at Keller Wall Price (East) | City of Keller, Tarrant County | Reterminate both circuits from Euless and Deen into the East side of Keller Wall Price | 2024-01-18 | 2024-06-06 | 2024-06-06 |  | 10238228 |  |  | 100 | 138 | na | 0.2 | 1926.9 ACSS/TW/E3X Cumberland | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(B)
0PT51143 (R8691) | Tall City Sub - Glass Ranch Sub 138 kV Line : Cut-In to Establish Lazy Ranch Sub | City of Stanton, Martin County | Cut into City Sub - Glass Ranch Sub 138 kV Line to establish Mustang Spring Sub. | 2024-04-22 | 2024-05-10 | 2024-05-10 |  | 1675862.42 |  |  | 100 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 0.1 | na | na | 25.101(c)(5)(A)
0PT48142 (R6252) | Sam Switch - Fort Smith Switch 345 kV Line : Cut-in to establish Files Valley Switch | City of Itasca, Hill County | Cut into the Sam Switch - Fort Smith Switch 345 kV Line to establish the new Files Valley Switch | 2024-04-16 | 2024-06-01 | 2024-06-01 |  | 2826239 |  |  | 100 | 345 | na | 0.16 | 2-1926.9 ACSS/TW Cumberland | Steel Lattice Tower, Steel Pole | na | na | varies | 0.16 | 25.101(c)(5)(A)
0PT50766 (R8697) | Midkiff Switch - Shaw POD 138 kV line: Shaw POD | Midland County | Establish Shaw POD on Midkiff Switch - Spraberry 138 kV Line. | 2024-03-13 | 2024-05-22 | 2024-05-22 |  | 3072883 |  |  | 100 | 138 | na | 0.83 | 1926.9 ACSS/TW Cumberland & 959.6 ACSS/TW Suwannee | Steel 3-Pole, Steel H-Frame, Steel Pole | 50 | 0.23 | varies | 0.22 | 25.101(c)(5)(A)
0PT46342 | Timberview Switch - Cedar Hill Switch 138 kV Line : OPGW Only | City of Arlington, Tarrant County | Install OPGW on the Timberview Switch - Cedar Hill Switch 138 kV Line. | 2024-09-12 | 2024-12-09 | 2024-12-09 |  | 2837871 |  |  | 100 | 345 | na | 10.9 | 795 ASCR Drake | Steel Lattice Tower | 220 | 10.9 | na | na | 25.101(c)(5)(A)
0PT48049 0PT48236 (R6094) | Athens Switch - Murchison Sub 69 kV: Rebuild to 138 kV | Henderson County | Rebuild a section of the Athens to - Tyler Switch 69 kV line as a 138 kV double circuit line with one circuit installed. | 2024-03-29 | 2024-05-30 | 2024-05-30 |  | 11693852 |  |  | 100 | 69 | 138 | 5.40 | 959.6 ACSS/TW SUWANNEE | Steel H-Frame, Steel Pole | Varies | 5.40 | na | na | 25.101(c)(5)(B)
0PT48568 0PT51660 (R8641) | Midkiff Switch – Pemkiff 138 kV Line: Rebuild | Upton County | Rebuild the line from Midkiff Switch – Pemkiff with double circuit steel poles with one circuit installed. | 2024-03-12 | 2024-06-21 | 2024-06-21 |  | 1754563 |  |  | 100 | 138 | na | 0.31 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 150 | 0.31 | na | na | 25.101(c)(5)(B)
0PT49445 0PT50541 (R8671) | SL Expanse Switch - Brown Switch 138 kV Line : Install Merrick Tap | Martin County | Provide a 138 kV POD on the SL Expanse Switch - Brown Switch 138 kV Line. | 2024-02-05 | 2024-05-06 | 2024-05-06 |  | 2573674 |  |  | 100 | 138 | na | 0.23 | 1926.9 ACSS/TW CUMBERLAND | Steel H-Frame, Steel Pole | na | na | 70 | 0.23 | 25.101(c)(5)(A)
0PT49594 (R8635) | Tall City - Glass Ranch 138 kV Line: Rebuild | City of Odessa, Midland County | Reconductor from Tall City - Glass Ranch 138 kV line. | 2024-03-24 | 2024-06-01 | 2024-06-01 |  | 2421974 |  |  | 100 | na | 138 | 4.05 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 70 | 4.05 | na | na | 25.101(c)(5)(B)
0PT50901 0PT52842 (R8699) | Buffalo Sub - Sale Ranch Sub 138 kV Line : Establish POD for customer | City of Stanton, Martin County | Establish Wishbone POD on the Buffalo - Sale Ranch 138 kV Line. | 2024-04-11 | 2024-10-01 | 2024-10-01 |  | 1978800 |  |  | 100 | 138 | na | 0.15 | 1926.9 ACSS/TW CUMBERLAND, 959.6 ACSS/TW SUWANNEE | Steel Pole | na | na | 70 | 0.15 | 25.101(c)(5)(A)
0PT51154 0PT49792 (R8670) | Quartz Sand Switch - Dewey Lake Sub 138 kV Line: Build New Line | City of Stanton, Glasscock County | This project will construct the Quartz Sand Switch - Dewey Lake Sub 138 kV Line. | 2024-05-30 | 2024-06-24 | 2024-06-24 |  | 555031 |  |  | 100 | 138 | na | 0.10 | 959.6 ACSS/TW SUWANNEE | Steel Pole | Station Property | 0.10 | na | na | 25.101(c)(5)(A)
0PT51155 (R8670) | Spraberry Sub - Polecat Creek Sub 138 kV Line: Cut in to establish Quartz Sand Switch | City of Stanton, Glasscock County | The Spraberry Sub - Polecat Creek Sub 138 kV line will cut-in Quartz Sand Switch. | 2024-04-17 | 2024-10-17 | 2024-10-17 |  | 1278699 |  |  | 100 | 138 | na | 0.20 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 50 | 0.20 | na | na | 25.101(c)(5)(A)
0PT51454 (R8677) | Horseshoe Springs Switch - Riverton Switch 138 kV Line: Cut in to Establish Roadrunner Capacitor Bank | City of Orla, Reeves County | Retermination of wire into Roadrunner Cap Bank from existing structure 5/5. | 2024-05-05 | 2024-05-09 | 2024-05-09 |  | 356988 |  |  | 100 | 138 | na | 0.80 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 70 | 0.80 | na | na | 25.101(c)(5)(A)
0PT49950 (R8671) | Merrick Tap - Merrick POD 138 kV Line : Install POI Line to Customer | Martin County | Build a 2.45 mile 138 kV line from Merrick POD to customer. | 2024-02-13 | 2024-05-06 | 2024-05-06 |  | 2858455 |  |  | 100 | na | 138 | 2.45 | 959.6 ACSS/TW SUWANNEE | Steel Pole | na | na | 70 | 2.45 | 25.101(c)(5)(A)
0PT51967 (M4368) | Colin Switch - Stone Creek Switch 138 kV Line: Install 138kV POI for Rayburn's Celina Sub | City of Celina, Collin County | Line modifications to the Collin Switch - Stone Creek Switch 138 kV transmission line to establish POI for Rayburns Celina Sub. | 2024-03-06 | 2024-12-16 | 2024-12-16 |  | 2186115 |  |  | 100 | 138 | na | .27 | 1926.9 ACSS/TW CUMBERLAND, 795 ACSR DRAKE | Steel Pole, Wood Pole | 100 | .27 | na | na | 25.101(c)(5)(A) | Percentage was reduced from 99% to 50% due to increased Scope of work.
0PT52164 (M4370) | Anna Switch - Sherman South Sub 138 kV Line: Establish POI for REC Waldrip | City of Anna, Collin County | Line modifications to the Anna Switch - Sherman South 138 kV transmission line near Str. 18/1 to establish POI for Rayburns Waldrip Sub. | 2023-11-27 | 2025-10-30 |  |  | 2751009 |  |  | 1 | 138 | na | .5 | 2 - 959.6 ACSS/TW Suwannee, 795 ACSR Drake | Steel Pole, Wood 3 Pole | varies | .07 | .43 | varies | 25.101(c)(5)(A)
0PT47346 | Waco West - Waco East - Elm Mott 138kV Line: Cut-In to est Circle Point Sub (formerly Cameron Park Sub) | City of Waco, McLennan County | Cut in the Waco West – Elm Mott 138 kV Line to establish the new Circle Point Substation. | 2024-08-15 | 2024-12-02 | 2024-12-02 |  | 1612601.8 |  |  | 100 | 138 | na | 0.11 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | .25 | varies | 0.11 | 25.101(c)(5)(A)
0PT47631 (R6177) | Watermill Switch - Cedar Crest Switch 138 kV Line: Floyd Branch Substation Cut-In | City of Dallas, Dallas County | Cut in the Watermill Switch - Cedar Crest Switch 138 kV Line to establish the new Floyd Branch substation. | 2024-03-26 | 2024-12-13 | 2024-12-13 |  | 1188645 |  |  | 100 | 138 | na | 0.12 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | 0.12 | na | na | 25.101(c)(5)(A)
0PT48042 (M4051) | Seagoville Switch - Mesquite East 138 KV Line: New Vanguard Sub Cut In | City of Mesquite, Dallas County | Cut in the Seagoville Switch - Mesquite East 138 KV Line to establish the new Vanguard Sub. | 2024-07-18 | 2024-12-20 | 2024-12-20 |  | 8921442 |  |  | 100 | na | 138 | 1.9 | 1926.9 ACSS/TW CUMBERLAND | Steel 2 - Pole, Steel Pole | na | na | varies | .95 | 25.101(c)(5)(A)
0PT48045 (R4601) | Collin Switch – Stone Creek 138 kV Line: New Dorchester Sub Line Cut In | City of Dorchester, Grayson County | Cut in the Collin Switch – Stone Creek 138 kV Line to establish the new Dorchester Substation. | 2024-09-20 | 2025-05-15 |  |  | 1160615.83 |  |  | 99* | 138 | na | 0.08 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | Varies | .08 | na | na | 25.101(c)(5)(A)
0PT48731 0PT53957 | Wedgwood Switch - Marrs Switch 138 kV Line : Relocate tower 11/2 at intersection of Altamesa & McCart for City of Ft Worth | City of Fort Worth, Tarrant County | Relocate tower 11/2 at the intersection of Altamesa and McCart in the city Fort Worth. | 2024-09-06 | 2024-11-01 | 2024-11-01 |  | 457026 |  |  | 100 | 138 | na | 0.40 | 959.6 ACSS/TW SUWANNEE | Steel Pole | 75 | 0.20 | na | 75 | 25.101(c)(5)(D)
0PT49533 (M4225) | Watermill Switch - Cedar Hill Switch 138 kV Line: Floyd Branch Substation Cut-In | City of Dallas, Dallas County | Cut in the Watermill Switch - Cedar Hill Switch 138 kV Line to establish the new Floyd Branch substation. | 2024-03-28 | 2024-12-13 | 2024-12-13 |  | 692012 |  |  | 100 | 138 | na | 0.12 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | 0.12 | na | na | 25.101(c)(5)(A)
0PT50006 0PT50935 (M4347) | DFW B East – Shorthorn POD 138 kV: Re-conductor Underground Circuits | City of Irving, Dallas County | Reconductor DFW B East- QTS 138 kV line and terminate at a new termination station | 2024-03-20 | 2025-12-31 |  |  | 71848059 |  |  | 54 | 138 | na | 1.20 | 4000 CU XLPE | na | Centerline | 06 | na | na | 25.101(c)(5)(A)
0PT50174 (R9047) | Yucca Switch - Moss Switch 138 kV Line : Rebuild 13.7 Mile Section From Future Oxy POD to Shin Oak POD | City of Odessa, Ector | Rebuild the second 13.7 miles of the Yucca Drive Switch - Moss Switch 138 kV Line, starting at the new Oxy POD and ending at Shin Oak POD. | 2024-05-08 | 2024-12-01 | 2024-12-01 |  | 25073599 |  |  | 100 | 138 | na | 13.70 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | Varies | 13.70 | na | na | 25.101(c)(5)(B)
0PT50348 (R8658) | Culberson Switch - Sand Lake Switch 138 kV Line : Cut in to Lean Clay Switch | City of Pecos, Reeves County | Establish new Lean Clay Switch by cutting in the Culberson Switch - Sand Lake Switch 138 kV Double Circuit Line. | 2024-12-13 | 2025-02-20 | 2025-02-20 |  | 2661550.94 |  |  | 100 | 138 | na | .8 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 70 | 02 | 70 | .2 | 25.101(c)(5)(A)
0PT50361 (R8658) | Culberson Switch - Sand Lake Switch 138 kV Line : Line Reroute for Lean Clay Switch (TNMP) | City of Pecos, Reeves County | Establish a tie line between Oncor's new Lean Clay Switch and TNMP's Cottonwood station. | 2024-12-13 | 2025-02-21 | 2025-02-21 |  | 540504.19 |  |  | 100 | na | 138 | .1 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | na | na | 70 | .1 | 25.101(c)(5)(A)
0PT50436 0PT48560 0PT52903 (R8303) | Big Spring Switch - Natural Dam Sub 138 kV Line: Reconfigure & Rebuild | City of Big Spring, Howard County | Rebuild a section of the Big Spring Switch - Big Spring West 138 kV line and reterm the line circuits to the Steer Sub and Onemile Switch (New Big Spring West). | 2024-04-02 | 2024-12-16 | 2024-12-16 |  | 7400613 |  |  | 100 | 138 | na | 2.10 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | Varies | 1.5 | 70 | .3 | 25.101(c)(5)(B)
0PT52205 (HB4150) | Watermill Switch - Seagoville Switch 138 kV Line: Clearance Improvement | City of Seagoville, Dallas County | Replace 4 - Wood H-frames along the Watermill Switch - Seagoville Switch 138 kV Line to improve clearances. | 2023-11-14 | 2023-12-20 | 2023-12-20 |  | 366703 |  |  | 100 | 138 | na | 0.4 | 795 ACSR Drake | Wood H-Frame | 100 | 0.4 | na | na | 25.101(c)(5)(B)
0PT50439 (M3069) | Valley South Switch - Platinum Storage POI 345 kV Line : Install Line for customer | City of Savoy, Fannin County | Install a new single circuit 345 kV line from Valley South Switch to customer. | 2024-09-27 | 2025-04-15 |  |  | 2759956 |  |  | 99* | na | 345 | 0.22 | 2 - 1926.9 ACSS/TW CUMBERLAND | Steel Pole | na | na | 100 | 0.22 | 25.101(c)(5)(A)
0PT50447 (M4347) | Hackberry Switch - DFW B-East Tap 138 kV Line : Rebuild | City of Irving, Dallas County | Rebuild the double-circuit Hackberry - DFW B East 138 kV Line. | 2024-02-12 | 2024-06-28 | 2024-06-28 |  | 7267793 |  |  | 100 | 138 | na | 4.00 | 2 - 959.6 ACSS/TW SUWANNEE | Steel 2 - Pole, Steel Pole | Varies | 2.00 | na | na | 25.101(c)(5)(B)
0PT50548 | East Network Sub - Medill Terminal Sub 138 kV Line : Pumping Plant Replacement | City of Dallas, Dallas County | Replace the existing three (3) Pressurization Plants at East Network Substation with a new Pressurization Plant. | 2024-05-08 | 2024-06-28 | 2024-06-28 |  | 1477354 |  |  | 100 | 138 | na | na | 1250 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT50638 (M3505) | Seymour Sub - Munday Switch 69 kV Line : Cut In for Bomarton Sub Skid | City of Seymour, Baylor County | Cut in the Seymour Sub - Monday Switch 69 kV line into the Bomarton Sub to accommodate the expansion. | 2024-03-06 | 2024-07-02 | 2024-07-02 |  | 1717608 |  |  | 100 | 69 | na | 0.13 | 4/0 ACSR PENGUIN, 959.6 ACSS/TW SUWANNEE | Steel Pole | 40 | 0.13 | na | na | 25.101(c)(5)(A)
0PT51156 (M5339) | Vineyard Switch - Roanoke Switch 138 kV Line : Reterminate into Roanoke West Sub | City of Roanoke, Denton County | Reterminate the Vineyard Switch - Roanoke Switch 138 kV Line into Roanoke West Sub for the substation expansion that will include a new transformer. | 2024-04-04 | 2024-05-09 | 2024-05-09 |  | 1521370 |  |  | 100 | 138 | na | 0.30 | 1926.9 ACSS/TW CUMBERLAND | Steel 2 - Pole, Steel Pole | 100 | 0.15 | na | na | 25.101(c)(5)(A)
0PT51225 (M4358) | Cedar Crest Switch - Watermill Switch Station 138 kV Line: Ten Miles Sub Cut In | City of Lancaster, Dallas County | Line work to establish the newly establish Ten Mile Sub | 2024-04-08 | 2024-10-15 | 2024-10-15 |  | 1657454 |  |  | 100 | 138 | na | 0.20 | 2 - 959.6 ACSS/TW SUWANNEE | Steel Pole | 200 | 0.20 | na | na | 25.101(c)(5)(A)
0PT51437 (R8692) | SL Grey Well Draw Switch - Blue Acres Sub 138 kV Line: Reterminate Line at SL Grey Well Draw | City of Midland, Midland County | Reterminate the SL Grey Well Draw Switch - Blue Acres Sub 138 kV Line to the SL Grey Well Draw Switch Station. | 2024-09-24 | 2024-12-22 | 2024-12-22 |  | 1067852.29 |  |  | 100 | 138 | na | 0.20 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | Station Property | 0.1 | varies | 0.1 | 25.101(c)(5)(A)
0PT51483 (M3224) | Allen Sw - Anna Sw 138 kV Line: Cut In to Establish Ridgeview | City of Allen, Collin County | Cut in the Allen - Anna 138 kV line into the new Ridgeview Substation. | 2024-04-05 | 2024-12-01 | 2024-12-01 |  | 4998391 |  |  | 100 | 138 | na | 0.34 | 2 - 1233.6 ACSS/TW YUKON | Steel 2 - Pole | Station Property | 0.17 | na | na | 25.101(c)(5)(A)
0PT51538 0PT51566 (R8708) | SL Pemkiff Switch - Ringo Switch - Stiles Sub 138 kV Line : Re-terminate Ringo Switch | Reagan County | Reterminate the Pemkiff - Ringo 138kV line at Ringo Switch. | 2024-05-24 | 2024-07-26 | 2024-07-26 |  | 804564 |  |  | 100 | 138 | na | .1 | 959.6 ACSS/TW SUWANNEE | Concrete Pole | 50 | .1 | na | na | 25.101(c)(5)(A)
0PT51581 0PT54723 (R8692) | Grey Well Draw Switch - Azalea Sub - Yosemite Sub 138 kV Line: Add Second Circuit | City of Midland, Midland County | Install a new 138 kV second circuit between Grey Well Draw Switch and Yosemite Tap. | 2024-04-15 | 2024-12-22 | 2024-12-22 |  | 9706367 |  |  | 100 | 138 | na | 11.50 | 1926.9 ACSS/TW CUMBERLAND | Steel 2 - Pole, Steel 3 - Pole, Steel Pole | Varies | 11.5 | na | na | 25.101(c)(5)(A)
0PT51710 | Weatherford Sub - Oran Switch 138 kV Line : Relocation of H-frames for landowner | City of Weatherford, Parker County | Relocation of structures 38/5,38/6, & 38/7 due to landowner request. | 2024-04-08 | 2024-05-16 | 2024-05-16 |  | 311691 |  |  | 100 | 138 | na | 0.70 | 636 ACSR GROSBEAK | Wood H-Frame | 50 | 0.70 | na | na | 25.101(c)(5)(D)
0PT51728 0PT51888 (R8591) | Courtney Creek Switch - Athey Switch 138 kV Line: Build Tie Line | Ward County | Build a 138 kV Point of Interconnection (POI) between the Courtney Creek Switch and Athey Switch. | 2024-12-10 | 2024-12-27 | 2024-12-27 |  | 1064616.1 |  |  | 100 | 138 | na | 0.10 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 50 | 0.10 | na | na | 25.101(c)(5)(A)
0PT51846 (M4359) | Shankle Switch - Ennis West Switch 138 kV Line : Reterminate Ennis South Sub | City of Ennis, Ellis County | Line work associated with the Ennis South Substation rebuild | 2025-01-13 | 2025-04-12 |  |  | 1468796.29 |  |  | 99* | 138 | na | 0.10 | 795 ACSR DRAKE | Steel Pole | Varies | 0.10 | na | na | 25.101(c)(5)(A)
0PT52141 (R8708) | Ringo Switch - Hartring Sub 138 kV Line : Tie line to Est Hartring Sub | City of Midkiff, Reagan County | Establish a new Tie Line from the existing Ringo Sub to the new Hartring Sub. | 2024-06-19 | 2024-07-26 | 2024-07-26 |  | 502014 |  |  | 100 | 138 | na | 0.32 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | Station Property | 0.16 | na | na | 25.101(c)(5)(A)
0PT52206 (M4358) | Cedar Hill Switch - Watermill Switch 138 kV Line : Ten Mile Sub Cut In | City of Lancaster, Dallas County | Line work to establish the newly establish Ten Mile Sub | 2024-04-11 | 2024-10-15 | 2024-10-15 |  | 1279087 |  |  | 100 | na | 138 | 0.20 | 2 - 959.6 ACSS/TW SUWANNEE | Steel Pole | 200 | 0.20 | na | na | 25.101(c)(5)(A)
0PT43547 | Venus Switch - Navarro Switch 345 kV Line : Erosion Control | City of Waxahachie, Ellis County | Replace tower 60/1 on the Venus Switch - Navarro Switch 345 kV Line. | 2024-08-06 | 2024-12-02 | 2024-12-02 |  | 801019.02 |  |  | 100 | 345 | na | 1.40 | 795 ACSR DRAKE | Steel Lattice Tower | 150 | 0.70 | na | na | 25.101(c)(5)(B)
0PT49555 (M5137) | Calmont Switch - White Settlement Switch 69 kV Line : Rebuild | City of Fort Worth, Tarrant County | Rebuild of Calmont Switch-White Settlement Switch 69 kV line. | 2024-10-18 | 2025-05-15 |  |  | 1147083.2 |  |  | 9 | 69 | na | 0.20 | 959.6 ACSS/TW SUWANNEE | Steel Pole | 80 | 0.20 | na | na | 25.101(c)(5)(B)
0PT49600 0PT49597 (R8599) | Rocky Road - Stiles 138 kV Line: Rebuild | Reagan County | Rebuild the 6.6-mile Rocky Road - Stiles 138 kV Line. | 2024-05-11 | 2025-02-14 | 2025-02-14 |  | 11661939 |  |  | 100 | 138 | na | 6.60 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | Varies | 6.60 | na | na | 25.101(c)(5)(B)
0PT49605 0PT53351 (R8499) | McKenzie Draw Switch - Lamesa Switch 138 kV Line : Rebuild from Paul Davis Tap - Jim Payne POI | Dawson County | Rebuild the 11.8-mile Jim Payne POI - Paul Davis Tap 138 kV Line. | 2024-06-20 | 2024-12-02 | 2024-12-02 |  | 22312950 |  |  | 100 | 138 | na | 11.80 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 50 | 11.80 | na | na | 25.101(c)(5)(B)
0PT49813 0PT53093 (R6173) | Holland Sub - Granger Sub 69 kV Line : Rebuild from Str. 62/6 - Str. 67/14 | City of Bartlett, Williamson County | Rebuild the Str 62/6 - Str 67/14 section of the Taylor Switch - Holland 69 kV Line. | 2024-06-03 | 2024-12-01 | 2024-12-01 |  | 16319801 |  |  | 100 | 69 | na | 5.38 | 959.6 ACSS/TW SUWANNEE | Steel 3 – Pole Switch, Steel Pole | Varies | 5.38 | na | na | 25.101(c)(5)(B)
0PT50062 (R8667) | Wildhorse POD - Getty Vealmoor Tap 138 kV Line : Rebuild | City of Big Spring, Howard County | Rebuild the 6.8-mile Wildhorse POD - Getty Vealmoor Tap 138 kV Line. | 2024-06-25 | 2024-12-20 | 2024-12-20 |  | 12675279 |  |  | 100 | 138 | na | 6.80 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 75 | 6.80 | na | na | 25.101(c)(5)(B)
0PT51090 (R8692) | Grey Well Draw Switch - Yosemite Sub 138kV Line: Cut In Azalea Sub for Targa | City of Midland, Midland County | Build a 2.5 mile Greenfield line to cut-in the new Azalea Sub for Targa. | 2024-07-09 | 2024-12-22 | 2024-12-22 |  | 9548929 |  |  | 100 | na | 138 | 5.00 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | na | na | 70 | 2.50 | 25.101(c)(5)(A)
0PT51478 | Sherry Switch – Timberview Switch 345 kV Line: Install OPGW from Century Sub to 10/7 | City of Arlington, Tarrant County | Install 5.6 miles of OGPW from structure 10/7 to Century Sub to establish a fiber link between Cedar Hill Switch and Sherry Switch.. | 2024-11-04 | 2024-12-09 | 2024-12-09 |  | 1282290.17 |  |  | 100 | 345 | na | 5.6 | 795 ACSR DRAKE | Steel Lattice Tower | 170 | 5.6 | na | na | 25.101(c)(5)(A)
0PT51480 | Sherry Switch – Timberview Switch 345 kV Line: Install OPGW from Century Sub to Sherry SW | City of Arlington, Tarrant County | Install 5.6 miles of OGPW from Century Sub to Sherry Switch to establish a fiber link between Cedar Hill Switch and Sherry Switch. | 2024-09-26 | 2024-12-09 | 2024-12-09 |  | 1561889.86 |  |  | 100 | 345 | na | 5.60 | 795 ACSR DRAKE | Steel Lattice Tower | 80 | 5.60 | na | na | 25.101(c)(5)(A)
0PT51582 0PT54529 0PT54977 (R8692) | Yosemite Sub - Buffalo Switch 138kV Line: Add second circuit | Martin and Midland County | Install a new 138 kV second circuit between Yosemite Sub and Buffalo Switch. | 2024-09-25 | 2024-12-22 | 2024-12-22 |  | 17266919 |  |  | 100 | 138 | na | 14.40 | 1926.9 ACSS/TW CUMBERLAND | Steel 2 - Pole, Steel 3 - Pole, Steel Pole | Varies | 14.4 | na | na | 25.101(c)(5)(A)
0PT51583 0PT53438 (R8692) | SL Buffalo Switch - Triangle Sub 138kV Line: Reterminate line at Buffalo Switch | City of Stanton, Martin County | Reterminate the SL Buffalo Switch - Triangle Sub 138 kV Line to the Buffalo Switch Station. | 2024-11-13 | 2024-12-22 | 2024-12-22 |  | 1726425 |  |  | 100 | 138 | na | 0.25 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | na | na | 50 | 0.25 | 25.101(c)(5)(A)
0PT51820 0PT51642 (R8603) | SL Driver - SkyWest 138 kV Line : Reterm to New Terminal at Driver | City of Odessa, Midland County | Line work to reterminate the existing SL Driver - SkyWest 138kV line into a new terminal location at Driver. | 2024-09-09 | 2024-11-19 | 2024-11-19 |  | 998546.76 |  |  | 100 | 138 | na | 0.15 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 70 | 0.15 | na | na | 25.101(c)(5)(A)
0PT52359 (R6094) | Trinidad Switch - Palestine Sub 69 kV Line : POI | City of Athens, Anderson County | Establish a 3-switch POI structure on the Trinidad Switch - Palestine Switch 69 kV Line. | 2025-12-01 | 2025-12-31 | [5 empty] | 0 | 69 | na | .20 | 4/0 ACSR PENGUIN | Steel 3 - Pole, Steel H –Frame Switch | Varies | .20 | na | na | 25.101(c)(5)(A)
0PT53120 (R6165) | Teal Sw - LCRA Limmer Sw 345 kV Tie Line | City of Hutto, Williamson County | Construct the tie line between Oncor's Teal Switch Station and LCRA's Limmer Switch Station. | 2024-04-15 | 2025-05-30 |  |  | 2607178 |  |  | 99* | na | 345 | 0.15 | 2 - 795 ACSR DRAKE | Steel 3 - Pole, Steel Pole | Varies | 0.15 | na | na | 25.101(c)(5)(A)
0PT48573 0PT52296 (R8645) | Spraberry Switch – Polecat Creek Switch 138 kV Line: Rebuild Quartz Sand Switch to Polecat Creek Switch | Glasscock County | Rebuild the 16 mile line from the newly established Quartz Sands to Polecat Creek Switch. | 2024-07-23 | 2024-12-26 | 2024-12-26 |  | 21169215 |  |  | 100 | 138 | na | 16.00 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 50 | 16.00 | na | na | 25.101(c)(5)(B)
0PT53370 (R6191) | Waco West Switch - Temple 69 kV Line: Reterminate at Peppervine Switch | City of Waco, McLennan County | Reterminate the Waco West - Temple 69 kV Line at its new terminal location at Peppervine Switch. | 2024-07-05 | 2025-11-30 |  |  | 2048965 |  |  | 60 | 69 | 138 | 0.30 | 1926.9 ACSS/TW CUMBERLAND | Steel 3 - Pole | 75 | 0.30 | na | na | 25.101(c)(5)(A)
0PT53371 (R6191) | Waco West Switch - Temple 69 kV Line: Replace Switch Str 12/13 at (BEPC) Lorena Sub to 138 kV | City of Lorena, McLennan County | Replace Switch Structure 12/13 on the Waco West Switch- Temple 69 kV Line. | 2025-01-13 | 2025-02-24 | 2025-02-24 |  | 1492074.75 |  |  | 100 | 69 | na | 0.01 | 795 ACSR DRAKE | Steel Pole Switch | 50 | 0.01 | na | na | 25.101(c)(5)(A)
0PT53436 (R8787) | Morgan Creek Switch - Tonkawa Switch 345 kV Line : Upgrade Between 154/5 and Morgan Creek Switch | City of Colorado City, Mitchell County | Install shunts required on a section of line on Morgan Creek Switch - Tonkawa Switch 345 kV Line to increase maximum operating temperature. | 2024-03-23 | 2024-05-01 | 2024-05-01 |  | 822873 |  |  | 100 | 345 | na | 0.29 | 2 - 795 ACSR DRAKE | Steel Lattice Tower | Station Property | 0.29 | na | na | 25.101(c)(5)(A)
0PT53698 | Cleburne Switch - Blum Switch 138 kV Line : Replace 14 poles, 10 cross arms, 30 insulators assemblies, and 10 X braces | Johnson County and Hill County | Replace Various Poles, Cross Arms, Insulators and X Braces on Cleburne Switch - Blum Switch 138 kV Line. | 2024-03-01 | 2025-02-10 | 2025-02-10 |  | 210886 |  |  | 100 | 138 | na | 13.44 | 795 ACSR Drake | Wood H-Frame | 100 | 13.44 | na | na | 25.101(c)(5)(B)
0PT46370 0PT49103 (R6172) | McGregor Phillips Tap Switch - Waco West Switch 69 kV Line : Voltage Conversion to 138 kV | City of McGregor, McLennan County | Rebuild the McGregor Phillips Tap Switch - Waco West Switch 69 kV Line | 2024-09-24 | 2025-12-15 |  |  | 14551380.5 |  |  | 84 | 69 | 138 | 4.60 | 1926.9 ACSS/TW CUMBERLAND, 795 ACSR DRAKE | Steel 2 - Pole, Steel Pole | Varies | 4.6 | na | na | 25.101(c)(5)(B)
0PT46671 0PT48591 (M5137) | Calmont Switch - Lockeed Sub 69 kV Line : Refurbish | City of White Settlement, Tarrant County | Rebuild the 3.5 mile Calmont Switch - Lockheed Sub 69 kV Line. | 2024-06-18 | 2024-12-28 | 2024-12-28 |  | 6410336 |  |  | 100 | 69 | na | 2.90 | 959.6 ACSS/TW SUWANNEE | Steel Pole | Varies | 2.90 | na | na | 25.101(c)(5)(B)
0PT48569 0PT49442 (R8639) | SL Grady to Expanse Switch 138 kV Line: Rebuild | City of Lenorah, Martin County | Rebuild a section of the Brown to Grady 138 kV Line | 2024-09-16 | 2025-03-07 | 2025-03-07 |  | 14400877 |  |  | 100 | 138 | na | 7.30 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | Varies | 7.30 | na | na | 25.101(c)(5)(B)
0PT49534 0PT55112 (R8603) | Spraberry Switch - McDonald Road Sub 138kV Line and Spraberry Switch - Garden City 69 kV Line : Cut-in to Mudstone Switch and Convert 69 kV to 138 kV | Midland County | Terminate the Spraberry Switch - McDonald Road Sub 138 kV Line and Spraberry Switch - Garden City 69 kV line into the new Mudstone Switch. | 2024-07-22 | 2024-12-14 | 2024-12-14 |  | 2529330 |  |  | 100 | 69 | 138 | 0.40 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 50 | 0.40 | na | na | 25.101(c)(5)(B)
0PT50501 (R8717) | Horseshoe Springs Switch - Riverton Switch 138 kV Line: Angel POD | City of Orla, Reeves County | Establish a point of delivery on the Horseshoe Springs Switch - Riverton Switch 138 kV line. | 2024-09-05 | 2025-01-29 | 2025-01-29 |  | 4997929.5 |  |  | 100 | na | 138 | 0.50 | 1926.9 ACSS/TW CUMBERLAND, 959.6 ACSS/TW SUWANNEE | Steel 3 - Pole, Steel H-Frame, Steel Pole | na | na | varies | .3 | 25.101(c)(5)(A)
0PT50804 | Krum West Switch - Riley Switch 345 kV Line : Replace OPGW | City of Burkburnett, Wichita County | Replace OPGW from str. 26/5 to 43/1 due to failed OPGW fiber | 2023-09-25 | 2023-12-05 | 2023-12-05 |  | 2047066 |  |  | 100 | 345 | na | 16.4 | 1926.9 ACSR/TW CUMBERLAND | Steel Pole | 150 | 16.4 | na | na | 25.101(c)(3)
0PT51111 (M4340) | Sherman South - MEMC Southwest - Valley Switch 138 kV Line: Howe Sub Cut In | City of Sherman, Grayson County | Cut in to the Howe Sub | 2024-10-30 | 2024-12-27 | 2024-12-27 |  | 1925159 |  |  | 100 | 138 | na | 0.50 | 2 - 959.6 ACSS/TW SUWANNEE | Steel Pole | 100 | 0.50 | na | na | 25.101(c)(5)(A)
0PT51886 | McDonald Road Switch - Spraberry Switch 138 kV Line : Replace failed OPGW | Glasscock County | Replace failed OPGW spans between structure 16/9 and 21/5. | 2023-09-01 | 2023-12-01 | 2023-12-01 |  | 977145 |  |  | 100 | 138 | na | 4.6 | 959.6 ACSS/TW SUWANNEE | Concrete Pole | 50 | 4.6 | na | na | 25.101(c)(3)
0PT52042 | Big Brown - Jewett 345 kV Line: Storm Damage | Freestone County | Restore 66 structures along the Big Brown - Jewett 345 kV Line due to storm event, approximately 13 miles. | 2023-06-22 | 2023-08-11 | 2023-08-11 |  | 34510413 |  |  | 100 | 345 | na | 24.80 | 2 - 795 ACSR DRAKE, 2 - 959.6 ACSS/TW SUWANNEE | Steel Lattice Tower | 170 | 24.80 | na | na | 25.101(c)(3)
0PT52269 (M3031) | Watermill Switch - Cedar Crest Switch 138 kV Line : Retermination to new Watermill Switch | City of Lancaster, Dallas County | Reterminate the Watermill Switch - Cedar Crest Switch 138 kV line to the new Watermill Switch. | 2024-09-17 | 2024-12-16 | 2024-12-16 |  | 877179.11 |  |  | 100 | 138 | na | 0.06 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | Station Property | 0.06 | na | na | 25.101(c)(5)(A)
0PT52270 (M3031) | Watermill Switch - Cedar Hill 138 kV Line : Retermination to new Watermill Switch | City of Lancaster, Dallas County | Reterminate the Watermill Switch - Cedar Hill Switch 138 kV line to the new Watermill Switch. | 2024-09-16 | 2024-12-16 | 2024-12-16 |  | 2292510.18 |  |  | 100 | 138 | na | 0.18 | 1926.9 ACSS/TW CUMBERLAND | Steel H-Frame, Steel Pole | Station Property | 0.18 | na | na | 25.101(c)(5)(A)
0PT52271 (R8698) | Quarry Field Switch - Riverton Switch 138 kV Line : Establish Border Tap | Loving County | Establish Border Tap on the Quarry Field Switch - Riverton Switch 138 kV Line | 2025-02-07 | 2025-06-30 |  |  | 4922846.66 |  |  | 99* | 138 | na | .40 | 1926.9 ACSS/TW CUMBERLAND | Steel 3 - Pole, Steel A-Frame, Steel H –Frame Switch, Steel Pole | 70 | 0.20 | na | na | 25.101(c)(5)(A)
0PT52342 0PT56505 | Eskota Switch - Flintkote North Tap 69 kV Line : IH-20 Sweetwater Relocation for TxDOT | City of Sweetwater, Nolan County | Relocate the Eskota Switch - Flintkote North Tap 69 kV Line at the request of TxDOT | 2025-06-16 | 2025-12-15 | [5 empty] | 0 | 69 | na | .84 | 1/0 ACSR RAVEN | Wood Pole | na | na | 70 | .84 | 25.101(c)(5)(F)
0PT52529 (R6249) | Whitney Switch - Stephenville Switch 138 kV Line : Cut-in to Establish new Walnut Springs 138 kV Switch | City of Walnut Springs, Bosque County | Cut-in to establish the new Walnut Springs 138 kV Switch | 2024-11-14 | 2024-12-18 | 2024-12-18 |  | 2177095.48 |  |  | 100 | 138 | na | 0.22 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | na | na | varies | 0.22 | 25.101(c)(5)(A)
0PT52670 (R8698) | Atchison POD - customer substation 138 kV Line | Loving County | Establish the Atchison POD to customer substation on the Border Tap – Atchison POD 138 kV Line. | 2025-03-24 | 2025-06-30 |  |  | 1251334.43 |  |  | 27 | na | 138 | 0.30 | 959.6 ACSS/TW SUWANNEE | Steel 3 - Pole, Steel Pole | na | na | 70 | 0.30 | 25.101(c)(5)(A)
0PT52721 (R6094) | Athens Sub - Tyler Switch 69 kV Line : Brownsboro Sub Retermination | City of Brownsboro, Henderson County | Retermination for the rebuild of Brownsboro Substation. | 2024-09-09 | 2024-12-02 | 2024-12-02 |  | 904831 |  |  | 100 | 69 | 138 | 0.20 | 959.6 ACSS/TW SUWANNEE | Steel Pole | Centerline | na | na | na | 25.101(c)(5)(B)
0PT52873 0PT53525 (M4002) | Montfort Switch - Shankle Switch 138 kV Line: Rebuild Montfort - Ennis Pump Tap | City of Ennis, Navarro County | Rebuild the Telico Tap - Ennis Pump Tap section of the Montfort Switch - Shankle Switch 138 kV Line | 2024-10-03 | 2024-12-20 | 2024-12-20 |  | 8171027.97 |  |  | 100 | 138 | na | 4.50 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | na | na | na | 25.101(c)(5)(B)
0PT53372 (R6191) | Waco West Switch - Temple 69 kV Line: Reterminate at Temple Elm Creek Switch | City of Temple, Bell County | Reterminate the Waco West Switch - Temple 69 kV Line to establish the new Temple Elm Creek Switch. | 2024-03-27 | 2024-12-26 | 2024-12-26 |  | 2639656 |  |  | 100 | na | 138 | 0.71 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | Varies | 0.71 | na | na | 25.101(c)(5)(A)
0PT53373 (R6191) | Temple Elm Creek Switch - Temple Pecan Creek Switch 138 kV Line: Rebuild Str 6/4 to 6/5 RR Xing Span | City of Temple, Bell County | Rebuild Temple Pecan Creek - to Temple Elm Creek 138 kV railroad crossing span | 2024-03-29 | 2024-12-26 | 2024-12-26 |  | 835538 |  |  | 100 | 138 | na | 0.09 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 50 | 0.09 | na | na | 25.101(c)(5)(B)
0PT53776 | Sandow Switch - Austrop Sub 345 kV Line : Install Bird Guards on Multiple Structures | Lee County, Milam County, Williamson County | Install Bird Guards and Insulators on Various Structures | 2024-01-10 | 2025-11-14 |  |  | 308789.85 |  |  | 80 | 345 | na | 75.34 | 795 ACSR Drake | Steel Lattice Tower | Varies | 75.34 | na | na | 25.101(c)(5)(B)
0PT46399 (M5281) | Roanoke Switch - Hicks Switch 345 kV Line : Cut-In to establish Exchange Switch | City of Fort Worth, Tarrant County | Loop in the double circuit Roanoke - Hicks 345 kV line into the new Exchange Switch 138 kV 345 kV Switch station. | 2024-09-09 | 2024-12-18 | 2024-12-18 |  | 4409075.38 |  |  | 100 | 345 | na | 4.00 | 2 - 1926.9 ACSS/TW CUMBERLAND | Steel 3 - Pole, Steel Pole | 160 | 2.00 | na | na | 25.101(c)(5)(B)
0PT48021 | Fisher Road Switch - Riley Switch 345 kV Line : Aviation Light DC/AC Conversion | City of Wichita Falls, Wichita County | Converting the six (6) FAA lights on the Fisher Road - Riley 345 kV Line from a DC source to an AC source | 2025-10-01 | 2025-12-15 | [5 empty] | 0 | 345 | na | na | 795 ACSR Drake | Steel Lattice Tower | na | na | na | na | 25.101(c)(5)(F)
0PT48047 (R6222) | Stryker Creek Switch - Lufkin Switch 138kV line: Cut-In to Establish Lufkin Central Angelina Substation | City of Lufkin, Angelina County | Cut-in line to establish the Lufkin Central Angelina Substation. | 2024-09-04 | 2025-02-03 | 2025-02-03 |  | 2811753.28 |  |  | 100 | 138 | na | 0.30 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | 0.30 | na | na | 25.101(c)(5)(B)
0PT48114 | Temple Elm Creek Switch - Belton Switch 138 kV Line : Loop 363 Relocation for TxDOT | City of Temple, Bell County | Raise and relocate the Temple Elm Creek - Belton 138 kV Line at the request of TxDOT | 2025-10-20 | 2025-12-12 | [5 empty] | 0 | 138 | na | 0.40 | 1926.9 ACSS/TW CUMBERLAND | Steel 2 - Pole, Steel Pole | 100 | 0.20 | na | na | 25.101(c)(5)(F)
0PT49404 0PT52433 (R8603) | Mudstone - Peck Sub 69 kV Line : Rebuild and convert to 138 kV | City of Midland, Midland County | Establish Mudstone Switch and rebuild from Mudstone Switch to Peck Sub and convert to 138 kV. | 2024-07-23 | 2024-12-14 | 2024-12-14 |  | 7579628.62 |  |  | 100 | 69 | 138 | 4.00 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 50 | 4.00 | na | na | 25.101(c)(5)(B)
0PT49531 (R8603) | Spraberry Switch - Polecat Creek Switch 138 kV Line : Reterminate at Spraberry Switch | City of Midland, Midland County | Reterminate the Spraberry Switch - Polecat Creek Switch 138 kV Line to supplement the conversion of the Spraberry - Mudstone - Desert Wind 138 kV Double Circuit Line. | 2024-11-12 | 2024-12-16 | 2024-12-16 |  | 347600.64 |  |  | 100 | 138 | na | 0.10 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 50 | 0.10 | na | na | 25.101(c)(5)(B)
0PT50184 (M3031) | Watermill Switch - Parkdale Switch 138 kV Line : Retermination to new Watermill Switch | City of Lancaster, Dallas County | Reterminate the Watermill Switch - Parkdale Switch 138 kV Line to the new Watermill Switch. | 2024-09-11 | 2024-12-16 | 2024-12-16 |  | 1977466.66 |  |  | 100 | 138 | na | 0.26 | 2 - 959.6 ACSS/TW SUWANNEE | Steel Pole | Station Property | 0.26 | na | na | 25.101(c)(5)(A)
0PT50185 (M3031) | Watermill Switch - Seagoville Switch 138 kV Line : Retermination to new Watermill Switch | City of Lancaster, Dallas County | Reterminate the Watermill Switch - Seagoville Switch 138 kV Line to the new Watermill Switch. | 2024-09-10 | 2024-12-16 | 2024-12-16 |  | 1400851.71 |  |  | 100 | 138 | na | 0.24 | 2 - 959.6 ACSS/TW SUWANNEE | Steel Pole | Station Property | 0.24 | na | na | 25.101(c)(5)(A)
0PT50402 (R8502) | Arco Crane Tap - Crane Arco POD 138 kV Line : Cut-In to Establish Foundry Sw | City of Crane, Crane County | Build a Point of Interconnect (POI) to AEP's Heron switch station. | 2024-10-15 | 2024-12-20 | 2024-12-20 |  | 3274709.12 |  |  | 100 | 138 | na | 1.07 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | 0.45 | varies | 0.36 | 25.101(c)(5)(A)
0PT50426 | Greenville Avenue Switch - Matilda Sub 138 kV Line : Replace underground Terminations | City of Dallas, Dallas County | Replace twelve 138 kV Underground Transmission Terminations along the Greenville Avenue Switch - Matilda Sub 138 kV Line. | 2024-10-17 | 2024-12-01 | 2024-12-01 |  | 1650306 |  |  | 100 | 138 | na | na | 600 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT50591 (R8675) | Catclaw Switch - Midkiff Switch138 kV Line: Tie Line between Stations | City of Midkiff, Upton County | Build a 138 kV tie line between Catclaw Switch and Midkiff Switch. | 2024-11-14 | 2024-12-23 | 2024-12-23 |  | 999308 |  |  | 100 | na | 138 | 0.18 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | na | na | 100 | 0.18 | 25.101(c)(5)(C)
0PT50599 (R8675) | Catclaw Switch - Peck/McDonald Road 138 kV Line: Cut-In | City of Midkiff, Upton County | Terminate the Catclaw Switch - Peck Switch/McDonald Rd 138 kV Lines into Catclaw Switch | 2024-11-19 | 2024-12-23 | 2024-12-23 |  | 4426137 |  |  | 100 | 138 | na | 0.76 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | Varies | 0.38 | na | na | 25.101(c)(5)(A)
0PT50612 (R3024) | Ranger Camp Switch - Eskota Switch 138 kV Line : Single Circuit Rebuild | City of Colorado City, Mitchell County | Construct a new line between the Ranger Camp Switch and the existing Eskota Switch Station | 2024-07-19 | 2025-04-01 |  |  | 1378270.26 |  |  | 99* | 138 | na | 0.15 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | 0.15 | na | na | 25.101(c)(5)(B)
0PT50613 (R3024) | Ranger Camp Switch - Barber Lake Switch 138 kV Line : Line Reroute from existing Morgan Creek to New Morgan Creek North | City of Colorado City, Mitchell County | Line Reroute from existing Morgan Creek Switch to new Morgan Creek North Ranger Camp Switch | 2024-07-19 | 2025-04-01 |  |  | 1042153.51 |  |  | 99* | 138 | na | 0.15 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | 0.15 | na | na | 25.101(c)(5)(B)
0PT50614 (R3024) | Ranger Camp Switch - Barber Lake Switch 138 kV Line : Reroute existing line to new Morgan Creek North Switch | City of Colorado City, Mitchell County | Line Reroute from existing Morgan Creek Switch to new Morgan Creek North Ranger Camp Switch. | 2024-07-22 | 2025-04-30 |  |  | 952022.49 |  |  | 51 | 138 | na | 0.20 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | 0.20 | na | na | 25.101(c)(5)(B)
0PT50615 (R3024) | Ranger Camp Switch - Sun Switch 138 kV Line : Reroute existing line to new Ranger Camp Switch | City of Colorado City, Mitchell County | Line Reroute from existing Morgan Creek Switch to new Morgan Creek North Ranger Camp Switch | 2024-07-22 | 2025-04-30 |  |  | 1435477 |  |  | 99* | 138 | na | 0.15 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | 0.15 | na | na | 25.101(c)(5)(B)
0PT50616 (R3024) | Ranger Camp Switch - Cosden Switch 138 kV Line : Reroute existing line to the new Ranger Camp Switch | City of Colorado City, Mitchell County | Line Reroute from existing Morgan Creek Switch to new Morgan Creek North Ranger Camp Switch | 2024-07-26 | 2025-04-30 |  |  | 1275454.16 |  |  | 45 | 138 | na | 0.20 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | 0.20 | na | na | 25.101(c)(5)(B)
0PT50639 (R6173) | Temple Switch - Taylor Switch 69 kV Line : Station Cut in for Cathey Creek Sub | City of Holland, Bell County | Cut in the Temple Switch - Taylor Switch 69 kV Line to loop the circuit through the Cathey Creek Sub. | 2024-05-07 | 2024-11-01 | 2024-11-01 |  | 517785 |  |  | 100 | 69 | na | 0.07 | 959.6 ACSS/TW SUWANNEE | Steel Pole | Centerline | 0.07 | na | na | 25.101(c)(5)(A)
0PT50714 0PT52243 (R8675) | Pemkiff -Canal Rd 138 kV Line: Terminate into Catclaw | City of Midkiff, Upton County | Terminate the Pemkiff - Canal Rd 138 kV Line into Catclaw Switch. | 2024-10-07 | 2024-12-23 | 2024-12-23 |  | 3282613 |  |  | 100 | 138 | na | .48 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | Varies | .22 | 100 | 0.26 | 25.101(c)(5)(A)
0PT50718 (R8675) | Pemkiff- Ringo 138 kV Line: Terminate into Catclaw | City of Midkiff, Upton County | Terminate the Pemkiff - Ringo 138 kV Line into Catclaw Switch. | 2024-10-23 | 2024-12-23 | 2024-12-23 |  | 2629188 |  |  | 100 | 138 | na | .55 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | Varies | 0.3 | varies | 0.25 | 25.101(c)(5)(A)
0PT51027 0PT53885 (R8303) | Big Spring West Switch - Air Park Switch 138 kV Line: Reterminate at Onemile Switch | City of Big Spring, Howard County | Reterm the Big Spring West Switch - Air Park Switch 138 kV line into its new terminal position at Onemile Switch | 2024-10-01 | 2024-12-16 | 2024-12-16 |  | 763091.67 |  |  | 100 | 138 | na | 0.50 | 1926.9 ACSR/TW CUMBERLAND | Steel Pole | Varies | 0.50 | na | na | 25.101(c)(5)(B)
0PT51141 (M3229) | Krum Tap Switch - Spring (BEPC) 138 kV Line : Establish Grain Belt Sub Substation | City of Krum, Denton County | Cut-in the Krum Tap Switch - Spring (BEPC) 138 kV Line to establish Grain Brain Belt Sub | 2024-11-20 | 2024-12-20 | 2024-12-20 |  | 2287057 |  |  | 100 | 138 | na | 0.30 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | 0.3 | na | na | 25.101(c)(5)(A)
0PT51243 (R3024) | Morgan Creek Switch - Colorado City 69 kV Line: Reterminate into new Ranger Camp Switch | City of Colorado City, Mitchell County | Reterminate the Colorado City - Morgan Creek 69 kV line into the new Ranger Camp Switch | 2024-07-29 | 2025-04-30 |  |  | 715186.4 |  |  | 51 | 69 | na | 0.57 | 959.6 ACSS/TW SUWANNEE | Steel 3 - Pole | 100 | 0.57 | na | na | 25.101(c)(5)(B)
0PT51244 (R3024) | Morgan Creek Switch - Big Spring Switch 69 kV Line: Reterminate into new Ranger Camp Switch | City of Colorado City, Mitchell County | Reterminate the Big Spring Switch - Morgan Creek 69 kV line into the new Ranger Camp Switch | 2024-07-24 | 2025-04-30 |  |  | 874379.89 |  |  | 45 | 69 | na | 0.20 | 959.6 ACSS/TW SUWANNEE | Steel 3 - Pole | 100 | 0.20 | na | na | 25.101(c)(5)(B)
0PT51599 (M5341) | Base Camp Switch - Deen Switch 138 kV Line : Rosen Heights Cut In | City of Fort Worth, Tarrant County | Cut in the Base Camp Switch - Deen Switch 138 kV Line to establish the new Rosen Heights Substation. | 2024-10-14 | 2025-05-15 |  |  | 1460392.9 |  |  | 99* | 138 | na | 0.10 | 959.6 ACSS/TW SUWANNEE | Steel Pole | 100 | 0.10 | na | na | 25.101(c)(5)(A)
0PT51769 (R8667) | Big Spring Switch - China Grove Switch 138 kV Line: Tributary Switch Cut In | City of Coahoma, Howard County | Cut in the Big Spring Switch - China Grove Switch 138 kV line to establish Tributary Switch | 2024-07-10 | 2024-12-20 | 2024-12-20 |  | 1707428 |  |  | 100 | 138 | na | 0.60 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 50 | 0.60 | na | na | 25.101(c)(5)(B)
0PT51788 (R6277) | Sandow Switch - Austrop Switch 345 kV Line : Line work to establish Beulah Switch | Milam County | Cut-in the Sandow Switch - Austrop Switch 345 kV Line to establish Beulah Switch. | 2024-10-25 | 2024-12-24 | 2024-12-24 |  | 2863348.35 |  |  | 100 | 345 | na | .2 | 1926.9 ACSR/TW CUMBERLAND, 1926.9 ACSS/TW CUMBERLAND | Steel Lattice Tower | na | na | 0.2 | 160 | 25.101(c)(5)(A)
0PT51806 (R8702) | Wink - Quarry Field Sw 138 kV Line: Line Work to Establish Blue Mountain Switch | City of Wink, Winkler County | Cut-in the Wink - Quarry Field 138 kV line to establish Blue Mountain Switch | 2024-10-04 | 2024-12-19 | 2024-12-19 |  | 2170788.01 |  |  | 100 | 138 | na | 0.44 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | na | na | 93 | 0.22 | 25.101(c)(5)(A)
0PT51832 | Cheyenne Sub - Magwalt POD 138 kV Line : Retermination into Cheyenne Sub | Winkler County | Temporary bypass needed during replacement of the damaged transformer. The Cheyenne Sub - Magwalt POD 138 kV line will also be re-terminated into a new substation deadend. | 2023-07-10 | 2024-01-29 | 2024-01-29 |  | 607595 |  |  | 100 | 138 | na | 0.3 | 795 ACSR DRAKE | Wood 3 - Pole | 50 | 0.3 | na | na | 25.101(c)(3)
0PT51853 (R8673) | Quartz Sand - Hog Mountain 138 kV Line: Install POI Line to Customer | Glasscock County | Build Hog Mountain Point of Delivery (POD) and line to customer on the new Quartz Sand Switch - Hog Mountain 138 kV Line. | 2025-02-25 | 2025-09-30 |  |  | 1108974 |  |  | 47 | na | 138 | 0.10 | 959.6 ACSS/TW SUWANNEE | Steel 3 - Pole, Steel H –Frame Switch | na | na | 70 | 0.10 | 25.101(c)(5)(A)
0PT51868 (R8705) | Midland East - Falcon Seaboard 345 kV Line: Cut In Rockhound Switch | City of Midland, Midland County | Cut-in the Midland East - Falcon Seaboard 345 kV Line to establish Rockhound Switch. | 2024-07-25 | 2024-12-22 | 2024-12-22 |  | 5033925.58 |  |  | 100 | 345 | na | 2.00 | 2 - 1926.9 ACSS/TW CUMBERLAND, 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 145 | 0.70 | na | 0.90 | 25.101(c)(5)(A)
0PT51869 (R8705) | Buffalo - Yosemite 138 kV Line: Cut in Rockhound Switch | City of Midland, Midland County | Cut-in the Buffalo - Yosemite 138 kV Line to establish the Rockhound Switch. | 2024-09-25 | 2024-12-22 | 2024-12-22 |  | 1102099.77 |  |  | 100 | 138 | na | 0.50 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | Station Property | .50 | na | na | 25.101(c)(5)(A)
0PT51870 (R8705) | Buffalo - Azalea 138 kV Line: Cut In Rockhound Switch | City of Midland, Midland County | Cut-in the Buffalo - Azalea 138 kV Line to establish the Rockhound Switch. | 2024-10-28 | 2024-12-22 | 2024-12-22 |  | 1084625.98 |  |  | 100 | 138 | na | 0.50 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | Station Property | .50 | na | na | 25.101(c)(5)(A)
0PT51872 (R2017) | Killeen Switch - Killeen Clark Road POI 138 kV Line : Establish Founders Trail Substation | City of Killeen, Bell County | Cut-in the Killeen Switch - Killeen Clark Road POI 138 kV Line to establish the Founders Trail Substation. | 2024-11-14 | 2024-12-20 | 2024-12-20 |  | 1623415.48 |  |  | 100 | 138 | na | 0.40 | 1590 ACSR Falcon | Steel Pole | 100 | 0.40 | na | na | 25.101(c)(5)(A)
0PT51927 (R6286) | Bell County East Switch - Little Pond Switch 345 kV Line : Line work to establish Gindale Switch 345 kV Switch | Bell County | Cut in the Bell County East Switch - TNP One Switch 345 kV Line to establish the new Gindale Switch. | 2024-10-07 | 2024-12-18 | 2024-12-18 |  | 6012310.41 |  |  | 100 | 345 | na | 0.30 | 2 - 1926.9 ACSS/TW CUMBERLAND | Steel 3 - Pole, Steel Lattice Tower, Steel Pole | 230 | 0.30 | na | na | 25.101(c)(5)(A)
0PT52050 (R6282) | Belfalls Switch - Lake Creek Switch 345 kV Line : Line work to establish Steakley 345 kV Dam Switch | Falls County | Cut-in the Belfalls Switch - Lake Creek Switch 345 kV line to establish the new Steakley Dam Switch. | 2024-10-03 | 2024-12-01 | 2024-12-01 |  | 3211361.02 |  |  | 100 | 345 | na | 0.14 | 2 - 1926.9 ACSS/TW CUMBERLAND | Steel Lattice Tower | na | na | 615 | 0.14 | 25.101(c)(5)(A)
0PT52127 | Plano West Switch - Richardson East Sub 138 kV Line : Replace structure 4/1 | City of Richardson, Collin County | Replace structure 4/1 due to erosion around the tower foundation. | 2024-10-18 | 2024-11-04 | 2024-11-04 |  | 1416322.82 |  |  | 100 | 138 | na | 0.40 | 795 ACSR DRAKE | Steel Pole | Varies | 0.40 | na | na | 25.101(c)(5)(B)
0PT52325 (M3031) | Watermill Switch - Sargent Road Switch 345 kV Line : Retermination to new Watermill Switch | City of Lancaster, Dallas County | Reterminate the Watermill Switch - Sargent Road Switch 345 kV line to the new Watermill Switch. | 2024-09-26 | 2024-12-27 | 2024-12-27 |  | 2701894 |  |  | 100 | 345 | na | 0.12 | 2 - 1926.9 ACSS/TW CUMBERLAND | Steel Pole | Varies | 0.12 | na | na | 25.101(c)(5)(A)
0PT52336 (R6266) | Belton Switch - Killeen Switch 138 kV Line : Cut In to Establish Button Sub | City of Temple, Bell County | Cut-in Belton Switch - Killeen Switch 138 kV Line to establish the Button Sub. | 2025-02-07 | 2025-03-26 | 2025-03-26 |  | 1228059.03 |  |  | 100 | 138 | na | 0.14 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | 0.14 | na | na | 25.101(c)(5)(A)
0PT53045 | Amelia Sub - Maple Sub 138 kV Line : Fluid Tagging | City of Dallas, Dallas County | Fluid injection on Amelia Sub - Maple Sub 138 kV underground line to improve restoration times. | 2025-09-15 | 2025-12-31 | [5 empty] | 0 | 138 | na | na | 600 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT53058 (R8705) | Midland East – Falcon Seaboard 345 kV Line: Cut In Second Circuit to Rockhound Switch | City of Midland, Midland County | Cut in the second circuit of Midland East - Falcon Seaboard 345 kV Line into the Rockhound Switch | 2024-10-26 | 2028-12-15 |  |  | 1186498.42 |  |  | 99* | na | 345 | 0.10 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 150 | 0.10 | na | na | 25.101(c)(5)(A)
0PT53160 0PT49487 (M5281) | Roanoke Switch - Hicks Switch 345 kV Line (South): Cut-in to Establish Exchange Switch | City of Fort Worth, Tarrant County | Loop in the south circuit of the Roanoke - Hicks 345 kV line into the new Exchange Switch 138 kV 345kV Switch | 2024-09-25 | 2024-12-26 | 2024-12-26 |  | 4619826.85 |  |  | 100 | 345 | na | 0.40 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | 160 | 0.40 | na | na | 25.101(c)(5)(B)
0PT53188 (R8702) | Blue Mountain Switch - Bull Moose POD 138 kV Line : Install POI Line to Customer | City of Wink, Winkler County | Install the 138 kV POD line from Blue Mountain Switch to Bull Moose POD | 2024-09-20 | 2025-01-22 | 2025-01-22 |  | 1910057.54 |  |  | 100 | na | 138 | 0.86 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | 70 | 0.86 | 25.101(c)(5)(A)
0PT53714 | Benbrook Switch - Wedgwood Switch 138 kV Line : Restoration | City of Fort Worth, Tarrant County | Replace structure 1/4 on the Benbrook Switch - Wedgwood Switch 138 kV Line due to damage. | 2023-12-15 | 2023-12-18 | 2023-12-18 |  | 764223 |  |  | 100 | 138 | na | 0.80 | 1233.6 ACSS/TW YUKON | Steel Pole | 0.4 | 70 | na | na | 25.101(c)(3)
0PT53762 0PT53763 (R8692) | SL Buffalo Switch - Sale Ranch Switch 138 kV Line : Reterminate line at Buffalo Switch | City of Stanton, Martin County | Reterminate the Buffalo Switch - Sale Ranch Switch 138 kV Line to the Buffalo Switch Station. | 2024-10-11 | 2025-01-16 | 2025-01-16 |  | 1789139 |  |  | 100 | 138 | na | 0.35 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | Varies | na | 70 | 0.35 | 25.101(c)(5)(A)
0PT41097 (R3050) | Ozark Trail Switch - Nazareth Solar POI 345 kV Line: Install Line for point of interconnection (POI) | Swisher County | Establish Point of Interconnection for an Ozark Trail Switch - Nazareth Solar 345 kV Line | 2024-09-25 | 2026-05-14 |  |  | 918864.36 |  |  | 99* | na | 345 | 0.10 | 2 - 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 160 | 0.10 | 25.101(c)(5)(A)
0PT44614 0PT54874 (M5177) | DFW D West - Euless 138 kV: Cut-In to DFW Mid Cities Sub | City of Euless, Tarrant County | Cut-in the DFW D West - Euless 138 kV line to establish the new DFW Mid-Cities Sub. | 2024-10-08 | 2024-12-16 | 2024-12-16 |  | 2263392 |  |  | 100 | 138 | na | .08 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | 100 | .08 | na | na | 25.101(c)(5)(B)
0PT46225 0PT50783 (R6164) | Brownwood Sub - Firerock POI 69 kV Line : Convert 69 kV to 138 kV | City of Brownwood, Brown County | Reconductor the Firerock POI - Brownwood Sub 69 kV Line and convert this line to 138 kV operation. | 2026-01-05 | 2026-12-15 | [5 empty] | 0 | 69 | 138 | 19.04 | 795 ACSR Drake, 959.6 ACSS/TW Suwannee | Steel Pole | Centerline | 15.50 | na | na | 25.101(c)(5)(B)
0PT47502 | Hillsboro – Whitney 138 kV Line: Erosion Control at Structure 1/1 | City of Hillsboro, Hill County | Replace structure on Hillsboro - Whitney 138 kV Line. | 2025-04-01 | 2025-05-31 |  |  | 1764914 |  |  | 0 | 138 | na | 0.04 | 1926.9 ACSR/TW Cumberland | Steel Pole | 100 | 0.04 | na | na | 25.101(c)(5)(B)
0PT49455 (R8603) | Spraberry Switch - Peck Tap 138 kV Line : Reterminate at Spraberry Switch and Voltage Conversion | City of Midland, Midland County | Reterminate at Spraberry Switch and convert the voltage from 69 kV to 138 kV. | 2024-12-06 | 2024-12-14 | 2024-12-14 |  | 387837 |  |  | 100 | 69/138 | na | .2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | .2 | na | na | 25.101(c)(5)(B)
0PT50122 (R6173) | Temple Switch - Taylor Switch 69 kV Line : Rebuild from Str. 67/14 to Str. 74/13 | City of Granger, Williamson County | Rebuild section of the Temple Switch - Taylor Switch 69 kV Line. | 2024-09-19 | 2024-12-22 | 2024-12-22 |  | 18843818.77 |  |  | 100 | 69 | na | 6.91 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 6.91 | na | na | 25.101(c)(5)(B)
0PT50181 (M3031) | Watermill Switch - Cedar Hill Switch 138 kV Line: Retermination to New Watermill Switch | City of Lancaster, Dallas County | Reterminate the Watermill Switch - Cedar Hill Switch 138 kV line to the new Watermill Switch. | 2024-09-26 | 2024-12-16 | 2024-12-16 |  | 785899 |  |  | 100 | 138 | na | 0.05 | 1926.9 ACSS/TW Cumberland | Steel Pole | Station Property | 0.05 | na | na | 25.101(c)(5)(A)
0PT50919 0PT52005 | Haltom Sub - Richland Hills Sub 138 kV Line : Replace structure 9/9 and 10/1 | City of Haltom City, Tarrant County | Replacing Structures 9/9 and 10/1 on the Deen Switch - Handley Switch 138 kV line. | 2023-11-15 | 2023-12-19 | 2023-12-19 |  | 773015 |  |  | 100 | 138 | na | 0.40 | 1233.6 ACSS/TW YUKON | Steel Pole | 75 | 0.20 | na | na | 25.101(c)(5)(B)
0PT51131 (R6264) | Hillsboro Switch - Alvarado Switch 69 kV Line: Cut-in New Itasca Sub | City of Itasca, Hill County | Line work to rebuild and connect the Itasca 69 kV substation to the Hillsboro Switch - Alvarado Switch 69 kV line. | 2024-10-15 | 2025-02-07 | 2025-02-07 |  | 869926.42 |  |  | 100 | 69 | na | 0.10 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | .10 | na | na | 25.101(c)(5)(A)
0PT51185 (M4360) | Ennis West Switch - Sterrett Sub 138 kV Line : Reterminate into Waxahachie North Sub | City of Waxahachie, Ellis County | Reterminate the Ennis West Switch - Sterrett Sub 138 kV Line to establish Transformer #3 | 2024-11-22 | 2025-09-15 |  |  | 1188423 |  |  | 72 | 138 | na | 0.20 | 2 - 959.6 ACSS/TW Suwannee | Steel 2 - Pole, Steel Pole | 100 | 0.10 | na | na | 25.101(c)(5)(A)
0PT51216 | Deen Switch - Euless Switch 138 kV Line : Replace structures 5/3 & 5/4 | North Richland Hills City, Tarrant County | Replacing structures 5/3 and 5/4 on the Deen Switch - Euless Switch 138 kV Line. | 2024-12-09 | 2024-12-18 | 2024-12-18 |  | 1209901.87 |  |  | 100 | 138 | na | 1.00 | 2 - 795 ACSR DRAKE | Steel Pole | 75 | 0.50 | na | na | 25.101(c)(5)(B)
0PT51484 (R8658) | Lean Clay Switch - Cottonwood (TNMP) 138 kV Tie Line | City of Pecos, Reeves County | Establish a tie line between Oncor's new Lean Clay Switch and TNMP's Cottonwood station. | 2024-12-13 | 2025-02-21 | 2025-02-21 |  | 544029.41 |  |  | 100 | 138 | na | 0.10 | 1926.9 ACSS/TW Cumberland | Steel Pole | varies | 0.10 | na | na | 25.101(c)(5)(A)
0PT51821 (R4015) | Fisher Road Switch - Riley 345 kV Line: Add Structure 1/1A | City of Wichita Falls, Wichita County | Add structure 1/1A on the Fisher Road Switch - Riley 345 kV Line. | 2023-11-28 | 2023-12-18 | 2023-12-18 |  | 562618 |  |  | 100 | 345 | na | 0.10 | 795 ACSR Drake | Steel 3 - Pole | 150 | 0.10 | na | na | 25.101(c)(5)(A)
0PT52025 0PT52261 | Liggett Switch - Norwood Switch 345 kV Line : Relocate structure 2/1 & 2/2 due to erosion issues | City of Grand Prairie, Dallas County | Replace structure 2/1 & 2/2 due to significant erosion of the creek near the structures. | 2024-10-07 | 2025-02-01 | 2025-02-01 |  | 3720964 |  |  | 100 | 345 | na | 1 | 2 - 1590 ACSR Falcon, 795 ACSR Drake | Steel Lattice Tower | varies | 1.00 | na | na | 25.101(c)(5)(B)
0PT52722 (R6094) | Athens Sub - Tyler Switch 69 kV Line : Echols Sub Retermination | City of Murchison, Henderson County | Retermination for the new Echols Sub on Athens Sub - Tyler Switch 69 kV Line | 2024-09-06 | 2024-12-16 | 2024-12-16 |  | 1288174 |  |  | 100 | 69 | 138 | 0.24 | 959.6 ACSS/TW Suwannee | Steel Pole | Centerline | 0.24 | na | na | 25.101(c)(5)(B)
0PT52920 | Carrollton Northwest Sub - Irving Norwood Sub 138 kV Line : Replace wood pole | City of Dallas, Dallas County | Replace structure on Carrollton Northwest Sub - Irving Norwood Sub 138 kV Line. | 2024-12-05 | 2024-12-20 | 2024-12-20 |  | 705838.18 |  |  | 100 | 138 | na | 0.10 | 336.4 ACSR MERLIN | Steel Pole, Wood Pole | 75 | 0.10 | na | na | 25.101(c)(5)(B)
0PT53884 (M5341) | Base Camp Switch - Deen Switch 138 kV Line: Rosen Heights Cut In | City of Fort Worth, Tarrant County | Cut in the Base Camp Switch - Deen Switch 138 kV Line to establish the new Rosen Heights Substation. | 2025-01-01 | 2025-05-15 |  |  | 484106.72 |  |  | 99* | 138 | na | 0.10 | 959.6 ACSS/TW Suwannee | Steel Pole | 100 | 0.10 | na | na | 25.101(c)(5)(A)
0PT54272 0PT57164 | Prairie Creek Switch - Oates Sub 138 kV Line : Replace Structure 2N8ET778 | City of Dallas, Dallas County | Replace structure on Prairie Creek Switch - Oates Sub 138 kV Line. | 2025-04-21 | 2025-05-15 |  |  | 891026.35 |  |  | 0 | 138 | na | 0.30 | 927.2 ACAR | Steel Pole | 40 | 0.30 | na | na | 25.101(c)(5)(B)
0PT46943 0PT56255 (R3024) | Morgan Creek Switch - Longshore Switch 345 kV Line : Terminate into new 345 kV Station | City of Colorado City, Mitchell County | Cut in the Morgan Creek Switch - Longshore Switch 345 kV Line to establish the Cattleman Switch. | 2025-02-03 | 2025-10-30 |  |  | 6347310.67 |  |  | 48 | 345 | na | 0.36 | 2 - 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 0.18 | na | na | 25.101(c)(5)(A)
0PT46955 (R3024) | Morgan Creek Switch - McDonald Road Switch 138 kV Line: Cut-in the new Cattleman Switch | City of Colorado City, Mitchell County | Cut in the Morgan Creek Switch - McDonald Road Switch 138 kV Line to establish the Cattleman Switch. | 2025-02-27 | 2025-10-30 |  |  | 3667852.2 |  |  | 47 | 138 | na | 1.46 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | 50 | 0.6 | 70 | 0.86 | 25.101(c)(5)(A)
0PT48037 (M3123) | Hicks Switch - Roanoke Switch 138 kV Line: Cut-In to Paloma Sub | City of Fort Worth, Tarrant County | Cut into the Hicks Switch - Roanoke Switch 138 kV Line to establish the Paloma substation. | 2025-04-22 | 2025-06-30 |  |  | 1,859,998.11 |  |  | 0 | 138 | na | 0.50 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | na | na | 70 | .25 | 25.101(c)(5)(A)
0PT49342 0PT53973 (R3025) | Ranger Camp Switch - Prong Moss Switch 345 kV Line : Rebuild | Howard County and Mitchell County | Rebuild the 27.8 miles of the Ranger Camp Switch - Prong Moss Switch 345 kV section on the Falcon Seaboard Switch - Morgan Creek Switch 345 kV Line. | 2024-10-07 | 2027-06-01 |  |  | 127693024.59 |  |  | 33 | 345 | na | 27.80 | 2 - 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | 150 | 27.80 | na | na | 25.101(c)(5)(B)
0PT49598 (M5002) | Eagle Mountain Switch - Deen Switch 138 kV Line: Boat Club Substation Cut In | City of Fort Worth, Tarrant County | Cut-in the Eagle Mountain Switch - Deen Switch 138 kV Line to establish the new Boat Club Substation. | 2024-10-15 | 2025-03-01 |  |  | 3885572 |  |  | 99* | 138 | na | 0.30 | 2 - 959.6 ACSS/TW Suwannee | Steel 2 - Pole, Steel Pole | 225 | 0.14 | 80 | 0.01 | 25.101(c)(5)(A)
0PT49858 (M4355) | Kemp Ranch Switch - Customer Sub 138 kV Line : Install POD for customer | City of Midlothian, Ellis County | Extend the Kemp Ranch Switch to customer | 2024-12-05 | 2025-05-09 |  |  | 578635 |  |  | 99* | 138 | na | 0.10 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | Varies | 0.10 | 25.101(c)(5)(A)
0PT49859 (M4355) | Kemp Ranch Switch - Customer Sub 138 kV Line : Install POD for customer | City of Midlothian, Ellis County | Extend the Kemp Ranch Switch to customer | 2024-12-04 | 2025-05-09 |  |  | 714093 |  |  | 99* | 138 | na | 0.20 | 959.6 ACSS/TW Suwannee | Steel Pole | na | na | Varies | 0.20 | 25.101(c)(5)(A)
0PT50431 (R6259) | Teal Switch - Skybox Sub 138 kV Line: Install 2 POD Lines | City of Hutto, Williamson County | Install two single circuit 138 kV lines from Teal Switch to Skybox. | 2024-10-09 | 2025-02-05 | 2025-02-05 |  | 3307660.99 |  |  | 100 | na | 138 | 0.70 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | na | na | 70 | 0.70 | 25.101(c)(5)(A)
0PT50450 (M4347 ) | Liggett - Hackberry 138 kV line DFW C-East - DFW D-East 1: Line Rebuild | City of Irving, Dallas County | Rebuild DFW C East- DFW D East 1 138 kV Line | 2024-09-20 | 2025-12-15 |  |  | 14565339.21 |  |  | 71 | 138 | na | 6.40 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 3.20 | varies | na | 25.101(c)(5)(B)
0PT50583 (R8675) | Catclaw Switch - Tumbleweed 138 kV Tie-In | City of Midkiff, Upton County | Build a 138 kV tie line between Catclaw Switch and Tumbleweed Statcom | 2025-01-11 | 2025-05-06 |  |  | 1124327.05 |  |  | 99* | na | 138 | 0.18 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 100 | 0.18 | 25.101(c)(5)(C)
0PT51152 (R8690) | Sale Ranch Sub - Natural Dam Sub 138 kV Line: Cut-in to establish Calf Tank Sub | City of Big Spring, Howard County | Cut-in the Sale Ranch Sub - Natural Dam Sub 138 kV Line to establish the new Calf Tank Sub. | 2024-11-04 | 2024-12-16 | 2024-12-16 |  | 1197928.74 |  |  | 100 | 138 | na | 0.20 | 959.6 ACSS/TW Suwannee | Steel Pole | 100 | 0.20 | na | na | 25.101(c)(5)(A)
0PT51221 0PT53099 (R8528) | Sandhills Tap - Edwards Tap 138 kV Line : Rebuild | City of Odessa, Ector County | Rebuild the Sandhills Tap to Edwards Tap 138 kV Line | 2024-11-07 | 2025-05-15 |  |  | 22443102.57 |  |  | 57 | 138 | na | 11.60 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 11.60 | na | na | 25.101(c)(5)(B)
0PT51584 (M3076) | Haggerty Switch - Valley Switch 138 kV Line: Cut-in to establish Progress Park Switch | City of Sherman, Grayson County | Cut in the Haggerty Switch - Valley Switch 138 kV line to establish the new Progress Park Switch. | 2024-10-15 | 2024-12-18 | 2024-12-18 |  | 3174902 |  |  | 100 | 138 | na | 0.50 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | na | na | 75 | 0.25 | 25.101(c)(5)(A)
0PT52013 | Round Rock Sub - Wells Branch Sub 138 kV Line : Foundation Remediation | City of Round Rock, Williamson County | Restore damaged and eroded foundations on the Round Rock Sub - Wells Branch Sub 138 kV Line | 2025-04-15 | 2025-05-31 |  |  | 341338 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.101(c)(5)(B)
0PT52343 | Stanton East Switch - Spraberry Switch 69 kV Line : IH-20 Midland Relocation for TxDOT | City of Midland, Midland County | Rebuild a section of the Stanton East Switch - Spraberry Switch 69 kV line. | 2025-03-20 | 2025-05-09 |  |  | 1529661.17 |  |  | 64 | 69 | na | 0.27 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 0.27 | na | na | 25.101(c)(5)(F)
0PT53065 (R6190) | Temple Elm Creek Switch - Belton Switch 138 kV Line : POD | City of Temple, Bell County | Install a Point of Delivery (POD) to customer at Pepper Creek Switch. | 2024-08-16 | 2024-11-18 | 2024-11-18 |  | 2583328.2 |  |  | 100 | na | 138 | 0.92 | 959.6 ACSS/TW Suwannee | Steel 2 - Pole, Steel Pole | na | na | 200 | 0.46 | 25.101(c)(5)(A)
0PT53066 (R6190) | Temple Elm Creek Switch - Belton Switch 138 kV Line : POD | City of Temple, Bell County | Install a Point of Delivery (POD) to customer on Pepper Creek Switch. | 2024-08-20 | 2025-01-31 |  |  | 1270683.94 |  |  | 99* | na | 138 | 0.40 | 959.6 ACSS/TW Suwannee | Steel 2 - Pole | na | na | 200 | 0.20 | 25.101(c)(5)(A)
0PT50093 (R1754) | Weatherford Switch - Oran 138 kV Line: Cut-in Grindstone Switch | City of Graford, Palo Pinto County | Cut-in the new Grindstone Switch on the Weatherford Switch - Oran 138 kV Line. | 2024-09-16 | 2024-10-01 | 2024-10-01 |  | 541329.49 |  |  | 100 | 69 | na | 0.20 | 4/0 ACSR Penguin | Wood 3 - Pole, Wood H-Frame | Varies | 0.20 | na | na | 25.101(c)(5)(B)
0PT50204 | Riverton Switch - Black River Sub 138 kV Line : Structure to Ground Resistance Testing | Culberson County | Install additional grounding components consisting of point grounds, counterpoises, and ground vaults on Riverton Switch - Black River Sub 138 kV Line. | 2025-05-05 | 2025-06-30 | [5 empty] | 0 | 138 | na | na | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | na | na | 25.101(c)(5)(B)
0PT50206 | Black River Sub - Culberson Switch 138 kV Line : Structure to Ground Resistance Testing | Culberson County | Install additional grounding components consisting of point grounds, counterpoises, and ground vaults on Black River Sub - Culberson Switch 138 kV Line. | 2025-05-05 | 2025-06-30 | [5 empty] | 0 | 138 | na | na | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | na | na | 25.101(c)(5)(B)
0PT50207 | Screwbean Tap - Screwbean Sub 138 kV Line : Structure to Ground Resistance Testing | Culberson County | Install additional grounding components consisting of point grounds, counterpoises, and ground vaults on Screwbean Tap - Screwbean Sub 138 kV Line. | 2025-05-05 | 2025-06-30 | [5 empty] | 0 | 138 | na | na | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | na | na | 25.101(c)(5)(B)
0PT50981 (R6273) | Peppervine Switch - Temple Elm Creek Switch 138 kV Line : Cut-in to Establish Central Park Switch | City of Waco, McLennan County | Cut into the Peppervine Switch - Temple Elm Creek Switch 138 kV Line to establish Central Park Switch. | 2024-08-15 | 2024-12-18 | 2024-12-18 |  | 4094060.84 |  |  | 100 | 69 | 138 | 1.29 | 1926.9 ACSS/TW Cumberland, 959.6 ACSS/TW Suwannee | Steel Pole | na | na | Varies | 0.69 | 25.101(c)(5)(A)
0PT51298 (R6263) | Pepper Creek Switch - Eberhardt Substation 138 kV Line: Establish Eberhardt Substation | City of Temple, Bell County | Construct new Pepper Creek - Eberhardt Substation 138 kV Line. | 2024-09-17 | 2024-12-23 | 2024-12-23 |  | 792923.22 |  |  | 100 | na | 138 | 0.13 | 1926.9 ACSS/TW Cumberland | Steel Pole | Station Property | 0.13 | na | na | 25.101(c)(5)(A)
0PT53475 (R6273) | Waco M/M Mars Tap 2 Switch - Waco M/M Mars Switch 138 kV Line : Replacement of Structures 3/7 and 1/1 | City of Waco, McLennan County | Remove and replace structures 3/7 and 1/1 on Waco M/M Mars Tap 2 Switch - Waco M/M Mars Switch 138 kV Line. | 2024-09-05 | 2024-12-02 | 2024-12-02 |  | 1146667.21 |  |  | 100 | 138 | na | 0.07 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 0.07 | na | na | 25.101(c)(5)(B)
0PT53979 | Morgan Creek Switch - Bitter Creek Switch 345 kV Line : tower replacement | City of Roscoe, Nolan County | Replace damaged tower on Graham Switch - Morgan Creek Switch 345 kV Line | 2024-01-25 | 2024-04-01 | 2024-04-01 |  | 713759 |  |  | 100 | 345 | na | na | 2 - 795 ACSR Drake | Steel Lattice Tower | 120 | na | na | na | 25.101(c)(3)
0PT54286 | Liggett Switch - Irving Norwood 138 kV Line: Emergency Restoration | City of Irving, Dallas County | Replace damaged tower on Liggett Switch - Irving Norwood 138 kV Line | 2024-02-11 | 2024-03-05 | 2024-03-05 |  | 700718 |  |  | 100 | 138 | na | 0.40 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 0.20 | na | na | 25.101(c)(3)
0PT54610 | Stone Creek Switch - Valley 138 kV Switch 138 kV Line : Replace structure 2/2 | City of Savoy, Fannin County | Replacing Structure 2/2 on the Stone Creek Switch - Valley 138 kV Switch 138 kV Line | 2025-04-01 | 2025-05-31 | [5 empty] | 34 | 138 | na | 2.22 | 1590 ACSR Falcon | Steel Lattice Tower | 100 | 2.22 | na | na | 25.101(c)(5)(B)
0PT54809 | Hillsboro - Corsicana - Frost 69 kV Line: Emergency Storm Restoration | City of Frost, Navarro County | Replace damaged structures due to a storm on the Hillsboro - Corsicana - Frost 69 kV Line. | 2024-04-09 | 2024-04-10 | 2024-04-10 |  | 414595 |  |  | 100 | 69 | na | 0.50 | 3/0 ACSR Pigeon | Wood Pole | 50 | 0.50 | na | na | 25.101(c)(3)
0PT55039 | Lake Creek Switch - Peppervine Switch 138 kV Line : Structure 1/4 Hardware Upgrade | City of Riesel, McLennan County | Upgrading hardware on structure 1/4 on the Lake Creek Switch - Peppervine Switch 138 kV Line. | 2024-11-25 | 2024-11-25 | 2024-11-25 |  | 290906.2 |  |  | 100 | 138 | na | 0.1 | 2 - 636 ACSR Grosbeak | Wood 3 - Pole | 0.1 | 100 | na | na | 25.101(c)(5)(B)
0PT39399 (R8738) | Horseshoe Springs Switch - Riverton Switch 138 kV Line : BPX Vail POD | City of Orla, Reeves County | Build a Point of Delivery to BPX Energy's Vail Substation on the Horseshoe Springs Switch - Riverton Switch 138 kV Line, approximately .3 miles. | 2025-03-07 | 2025-05-16 |  |  | 3270199.02 |  |  | 14 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel H-Frame, Steel Pole | 70 | 0.1 | 70 | 0.30 | 25.101(c)(5)(A)
0PT40875 (R8527) | Wolf - Odessa EHV 138 kV Line: Rebuild 44/7 to 41/1 | City of Odessa, Ector County | Rebuild Odessa EHV Switch - Monahans - Wolf Switch 138 kV Line with double circuit capable steel poles with one circuit installed. | 2025-03-18 | 2025-07-15 |  |  | 8430287.89 |  |  | 17 | 138 | na | 4.00 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | 75 | 4.00 | na | na | 25.101(c)(5)(B)
0PT45589 (R6160) | Corsicana Sub to Navarro Sub 138kV Line: Re-terminate at Revolution Switch | City of Navarro, Navarro County | To establish Revolution Switch it will be necessary to reterminate the Corsicana Substation – Navarro Substation 138 kV transmission line. | 2025-10-01 | 2025-12-04 | [5 empty] | 0 | 138 | na | 0.10 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT45590 (R6160) | Trinidad Switch – Navarro Sub 138kV Line: Re-termination at Revolution Switch | City of Navarro, Navarro County | To establish Revolution Switch it will be necessary to reterminate the Trinidad Switch – Navarro Sub 138kV transmission line. | 2025-10-01 | 2025-12-04 | [5 empty] | 0 | 138 | na | 0.10 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.10 | na | na | 25.101(c)(5)(A)
0PT45591 (R6160) | Revolution Switch – Navarro Sub 138 kV Line: Establish Revolution Switch | City of Navarro, Navarro County | To establish Revolution Switch it will be necessary to build the Revolution Switch – Navarro Sub 138 kV transmission line. | 2025-10-01 | 2025-12-04 | [5 empty] | 0 | na | 138 | 0.10 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 0.1 | na | na | 25.101(c)(5)(A)
0PT46343 | Duval Sub – Hemphill Sub 69/138 kV Line: Install OPGW from Duval Sub to Hemphill Sub | City of Fort Worth, Tarrant County | Install 7.7 miles of OPGW from Duval Sub to Hemphill Sub | 2025-04-07 | 2025-05-31 |  |  | 2993661.66 |  |  | 0 | 138 | na | 7.70 | 795 ACSR DRAKE | Steel Pole | Varies | 7.70 | na | na | 25.101(c)(5)(A)
0PT47998 0PT50997 (M4212) | Cedar Crest Switch - Dealey Street - West Levee Switch 138kV Line: Rebuild Structure T-27 to Cedar Crest Switch | City of Dallas, Dallas County | Rebuild a section of the Cedar Crest Switch - Dealey Street - West Levee Switch 138kV line. | 2025-09-16 | 2025-12-15 | [5 empty] | 0 | 138 | na | 2.30 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 2.30 | na | na | 25.101(c)(5)(B)
0PT47999 0PT49119 (R6172) | McGregor Phillips Switch - McGregor Phillips Tap Switch 138kV Line: Rebuild | City of McGregor, McLennan County | Rebuild from McGregor Phillips Switch to the new Launch Pad Switch | 2026-02-12 | 2026-04-30 | [5 empty] | 0 | 138 | na | 5.10 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 5.10 | na | na | 25.101(c)(5)(B)
0PT49795 (R6232) | Bell County Switch - TNP One Switch (TNMP) 345 kV Line: Customer POI | City of Rosebud, Milam County | Build a 345 kV Point of Interconnection (POI) for Customer to Gristmill Switch. | 2025-06-02 | 2026-04-16 | [5 empty] | 0 | 345 | na | 0.50 | 2 - 1926.9 ACSR/TW Cumberland | Steel Lattice Tower | 160 | 0.50 | na | na | 25.101(c)(5)(A)
0PT49855 (R6242) | Jewett Switch-Lake Creek Switch: Retermination to Phifer Creek Switch | City of Groesbeck, Limestone County | Re-termininating the existing Jewett Switch-Lake Creek Switch 138 kV Line into Phifer Creek Switch. | 2026-01-01 | 2026-04-23 | [5 empty] | 0 | 138 | na | 0.55 | 1926.9 ACSR/TW Cumberland, 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.48 | Varies | 0.07 | 25.101(c)(5)(A)
0PT49983 (R6255) | Minerva Switch - (BEPC) Robertson Switch 138 kV Line : Cut-in to establish Cannon Switch | City of Milano, Milam County | Cut into the Minerva Switch - (BEPS) Robertson Switch 138 kV Line to establish Cannon Switch. | 2025-09-01 | 2025-11-13 | [5 empty] | 0 | 138 | na | 0.63 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | Varies | 0.63 | 25.101(c)(5)(A)
0PT49984 (M3501) | Cedar Elm Switch 345 kV: Establish 345 kV Point of Interconnection | City of Valley View, Cooke County | Establish 345 kV point of interconnection out of Cedar Elm Switch. | 2025-03-27 | 2025-05-08 |  |  | 1724754 |  |  | 34 | na | 345 | 0.10 | 2 - 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 100 | 0.10 | 25.101(c)(5)(A)
0PT50007 (R6321) | Limestone Switch - Watermill Switch 345 kV Line : Cut-In Glasgow Switch | City of Barry, Navarro County | Cut-in Glasgow Switch on the Limestone - Watermill 345 kV Line. | 2026-09-01 | 2026-12-03 | [5 empty] | 0 | na | 345 | 0.52 | 1926.9 ACSS/TW Cumberland | Steel Lattice Tower, Steel Pole | na | na | 160 | 0.52 | 25.101(c)(5)(A)
0PT50027 | Carrollton Northwest Switch - Renner Switch 345 kV Line : Clearance Improvement | City of Hebron, Denton County | Replace 2 Structures located along the Carrollton Northwest - Renner 345 kV Line, | 2025-10-24 | 2025-12-31 | [5 empty] | 0 | 345 | na | na | 2 - 1590 ACSR Falcon | Steel Lattice Tower | 150 | na | na | na | 25.101(c)(5)(B)
0PT50046 | Navarro Switch - Big Brown Switch 345 kV Line : Clearance Improvement | Freestone County | Replace two (2) steel towers with two (2) taller steel towers along the Navarro Switch - Big Brown 345 kV Line to improve clearances. | 2025-08-01 | 2026-12-31 | [5 empty] | 0 | 345 | na | 2.88 | 2 - 795 ACSR Drake | Steel Lattice Tower | 165 | 1.44 | na | na | 25.101(c)(5)(B)
0PT50088 0PT54983 (R1754) | Weatherford - Oran - Barton 138kV Line: Re-terminate to establish Grindstone Switch and Juniper Sub | Palo Pinto County | Re-terminate the Weatherford - Oran - Barton 138 kV Line to establish Grindstone switch and Juniper Sub. | 2025-02-18 | 2025-05-15 |  |  | 2127329.57 |  |  | 49 | 138 | na | 0.25 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | 50 | 0.25 | na | na | 25.101(c)(5)(A)
0PT50104 (R1754) | Mineral Wells - Oran 138kV Line: Reterminate Grindstone Switch | Palo Pinto County | Reterminate the Mineral Wells - Oran 138 kV line at Grindstone Switch. | 2025-03-03 | 2025-05-15 |  |  | 1085054.68 |  |  | 34 | 138 | na | 0.33 | 1926.9 ACSS/TW Cumberland | Steel Pole, Wood H-Frame | 100 | na | 70 | 0.33 | 25.101(c)(5)(A)
0PT50123 0PT55680 (R6173) | Temple Switch - Taylor Switch 69 kV Line : Rebuild from Str. 74/13 to Taylor Switch | City of Taylor, Williamson County | Rebuild section of the Temple Switch - Taylor Switch 69 kV Line. | 2025-05-15 | 2025-08-15 | [5 empty] | 0 | 69 | na | 5.91 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 5.91 | na | na | 25.101(c)(5)(B)
0PT50166 (R1754) | Grindstone Switch - Oran Switch 138kV Line: Establish West tie line | Palo Pinto County | Construct a 0.1 mile transmission line between Oran Switch and Grindstone Switch 138 kV Line. | 2025-02-16 | 2025-05-15 |  |  | 763419.02 |  |  | 34 | na | 138 | 0.10 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole | Varies | 0.10 | na | na | 25.101(c)(5)(A)
0PT50175 (R9047) | Yucca Switch - Moss Switch 138 kV Line : Rebuild 9.4 Mile Section From Shin Oak POD to Yucca Switch | City of Monahans, Ward County | Rebuild 9.4 miles of the Yucca - Moss 138 kV Line starting at the existing Shin Oak POD and ending at Yucca Drive Switch. | 2024-10-27 | 2025-04-28 |  |  | 20812818.29 |  |  | 52 | 138 | na | 9.40 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | Varies | 9.40 | na | na | 25.101(c)(5)(B)
0PT50176 | Yucca Drive Switch - Turnbaugh Corner Switch 138 kV Line : Rebuild 0.7 Mile Section | City of Monahans, Ward County | Rebuild 0.7 miles of the Yucca - Turnbaugh Corner 138 kV Line starting at structure 2/1 and ending at structure 1/4H. | 2025-03-24 | 2025-04-28 |  |  | 2486555 |  |  | 1 | 138 | na | 0.70 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 0.70 | na | na | 25.101(c)(5)(B)
0PT51021 (R6323) | Martin Lake Switch - Elkton Switch 345 kV Line : Cut-in Dorsett Switch | City of Henderson, Rusk County | Cut-in Dorsett Switch for Dry Creek Solar | 2025-04-07 | 2025-05-08 |  |  | 2960935 |  |  | 0 | na | 345 | 0.20 | 1926.9 ACSR/TW Cumberland | Steel Lattice Tower | na | na | 160 | 0.20 | 25.101(c)(5)(A)
0PT51242 (R9022) | Mulberry Creek 345 kV Tie Lines | City of Abilene, Jones County | Install two 345 kV tie lines | 2025-04-14 | 2025-05-15 |  |  | 462918 |  |  | 0 | na | 345 | 0.12 | 2 - 1926.9 ACSS/TW Cumberland | na | na | na | Varies | 0.06 | 25.101(c)(5)(A)
0PT51302 (R8632) | Quartz Sand Switch - Prairieland Switch 138 kV Line: Install 2nd Circuit | City of Greenwood, Glasscock County | Extend the 138 kV Line from Hog Mountain POD to terminate at Prairieland Switch. Install the second circuit on the existing Quartz Sand Switch - Hog Mountain POD 138 kV Line. | 2024-11-21 | 2025-09-30 |  |  | 11393189 |  |  | 50 | 138 | na | 8.98 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 6.94 | 70 | 1.02 | 25.101(c)(5)(C)
0PT51304 0PT55478 (R8632) | Longshore Switch - Consavvy Switch 345kV Line: Cut In to Establish Prairieland Switch | City of Greenwood, Glasscock County | Cut in the Longshore Switch - Consavvy Switch 345 kV Line to establish the new Prairieland Switch. | 2025-05-07 | 2025-09-30 | [5 empty] | 0 | 345 | na | 0.75 | 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 120 | 0.42 | 220 | 0.33 | 25.101(c)(5)(A)
0PT51305 (R8632) | Morgan Creek Switch - Consavvy Switch 345kV Line: Cut In to Establish Prairieland Switch | City of Greenwood, Glasscock County | Cut in the Morgan Creek Switch - Consavvy Switch 345 kV Line to establish the new Prairieland Switch. | 2025-05-01 | 2025-09-30 | [5 empty] | 0 | 345 | na | 0.75 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 120 | 0.4 | 220 | 0.35 | 25.101(c)(5)(A)
0PT51348 (R3032) | Cottonwood Switch - White River Switch 345 kV Line :Cut-in Wrangler Switch | City of Afton, Dickens County | Cut-in Wrangler Switch | 2025-03-29 | 2025-05-08 |  |  | 3227762 |  |  | 26 | na | 345 | 0.20 | 1926.9 ACSS/TW Cumberland | Steel Lattice Tower, Steel Pole | na | na | 160 | 0.20 | 25.101(c)(5)(A)
0PT51431 0PT55071 (M4015) | Watermill Switch - Cedar Hill Switch 138 kV Line : Line work to establish Skybox Lancaster | City of Lancaster, Dallas County | Cut in to the Watermill Switch - Cedar Hill Switch 138 kV Line to establish Bradberry Switch. | 2025-03-20 | 2025-05-15 |  |  | 4726951.09 |  |  | 30 | 138 | na | 1.68 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | 70 | 0.84 | 25.101(c)(5)(A)
0PT51436 (R3030) | Blackwater Draw - Ogallala Switch 345 kV Line: Cut In to Establish Kangaroo Switch | City of Hart, Castro County | Line work to establish Kangaroo Switch for Hart Wind 2 POI on the Ogallala Switch to Black Water Draw Switch 345 kV Line. Kangaroo Switch will be located approximately 10 miles south of Ogallala Switch and 3 miles east of Hart, TX off of County Road 145. | 2025-02-25 | 2025-05-14 |  |  | 2154044.4 |  |  | 34 | 345 | na | 0.25 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | 175 | 0.25 | na | na | 25.101(c)(5)(A)
0PT51477 | Hemphill Sub - Adams Terminal Sub 138 kV Line : Install OPGW from Hemphill Sub to Adams Terminal | City of Fort Worth, Tarrant County | Install 0.5 miles of OPGW from Hemphill Substation to Adams Terminal to establish a fiber link between Duval Sub and Adams Terminal. | 2025-04-28 | 2025-05-15 |  |  | 1509744.59 |  |  | 0 | 138 | na | na | 795 ACSR Drake | Steel Pole | 40 | 0.5 | na | na | 25.101(c)(5)(A)
0PT51482 (M4378) | Elkton - Tri Corner 345 kV Line: Erika Solar Cut-In | City of Kaufman, Kaufman County | Line modification to connect Haley Switch to the Elkton - Tri Corner 345kV Line as a part of Interconnecting the new Erika Solar, to the ERCOT 345 kV transmission system. | 2026-04-01 | 2026-05-07 | [5 empty] | 0 | 345 | na | 0.18 | 2 - 1926.9 ACSS/TW Cumberland, 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 170 | na | 170 | 0.12 | 25.101(c)(5)(A)
0PT51510 (R8732) | Quarry Field Switch - Riverton Switch 138 kV Line : Establish Sullivan Tap for customer | Loving County | Build a Point of Delivery (POD) to customer on the Quarry Field Switch - Riverton Switch 138 kV Line | 2025-04-07 | 2025-05-15 |  |  | 2844818.25 |  |  | 0 | 138 | na | 0.28 | 1926.9 ACSS/TW Cumberland | Steel H-Frame, Steel Pole | na | na | 70 | 0.28 | 25.101(c)(5)(A)
0PT51551 (R6261) | Bell County East Switch - Little Pond Switch 345 kV Line : Line work to establish Yarrelton Switch | City of Rogers, Bell County | Cut into the Bell County East - Little Pond Switch 345 kV Line to establish Yarrelton Switch | 2025-09-15 | 2025-11-13 | [5 empty] | 0 | 345 | na | 2.20 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | na | na | Varies | 1.10 | 25.101(c)(5)(A)
0PT51703 (R6320) | Jewett Switch - Bale Switch 345 kV Line: Cut-In to Establish Stranger Switch | City of Thornton, Limestone County | Cut-In to Establish Stranger Switch | 2025-04-07 | 2025-05-15 |  |  | 3029827 |  |  | 0 | na | 345 | 0.42 | 1926.9 ACSR/TW Cumberland | Steel Lattice Tower | na | na | 160 | 0.42 | 25.101(c)(5)(A)
0PT51709 (R6317) | Bell County East Switch - Sandow Switch 345 kV Line: Badger Switch Cut-In | City of Buckholts, Milam County | Cut in the Bell County East Switch - Sandow Switch 345 kV Line to establish the new Badger Switch. | 2025-09-08 | 2025-11-20 | [5 empty] | 0 | 345 | na | 2.59 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 125 | 0.45 | 160 | 1.07 | 25.101(c)(5)(A)
0PT51787 (R8739) | Wolf Switch - Odessa EHV Switch 138 kV Line: Establish Calcite POD for GCC Odessa | City of Odessa, Ector County | Establish a 138 kV point-of-delivery on the Wolf Switch - General Tire Switch 138 kV line. This POD will have a 0.35 mile radial line serving the customer. | 2025-01-21 | 2025-05-09 |  |  | 3982518.26 |  |  | 84 | 138 | na | 0.65 | 336.4 ACSR Linnett, 959.6 ACSS/TW Suwannee | Concrete Pole, Steel 3 - Pole, Steel H-Frame, Steel Pole | 50 | 0.30 | 70 | 0.35 | 25.101(c)(5)(A)
0PT52238 (M4361) | Loop Nine Switch - Compass Phase 2 138 kV Line: Install 2 radial POD lines | City of Red Oak, Ellis County | Establish the new 1.1-mile Loop Nine Switch - Compass Data Centers 138 kV Line | 2025-03-11 | 2025-05-15 |  |  | 3953003.61 |  |  | 66 | 138 | na | 2.20 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | 120 | 1.1 | 180 | 2.20 | 25.101(c)(5)(A)
0PT52299 (R8794) | Midland County Northwest Switch - Midland East Switch 138 kV Line : Establish Oncor POD for Customer | City of Midland, Midland County | Build a Point of Delivery (POD) to Customer POD on the Midland East - Midland County Northwest 138 kV line. | 2025-03-26 | 2025-05-15 |  |  | 1583634.71 |  |  | 14 | 138 | na | 0.02 | 959.6 ACSS/TW Suwannee | Steel Pole | 75 | 0.02 | na | na | 25.101(c)(5)(A)
0PT52322 (M3031) | Watermill - Elrod Switch/Watermill - Big Onion Switch 345kV Line: Retermination to New Watermill Switch | City of Lancaster, Dallas County | Reterminate the Watermill Switch - Elrod Switch 345kV line and the Watermill Switch - Big Onion Switch 345kV line to the new Watermill Switch. | 2025-03-19 | 2025-05-15 |  |  | 2485942.1 |  |  | 34 | 345 | na | 0.24 | 2 - 1926.9 ACSS/TW Cumberland | Steel Pole | Station Property | 0.12 | na | na | 25.101(c)(5)(A)
0PT52323 (M3031) | Cedar Hill Switch - Watermill Switch/ Watermill Switch - Desoto Switch 345kV Line: Retermination to New Watermill Switch | City of Lancaster, Dallas County | Reterminate the Cedar Hill Switch - Watermill Switch 345kV line and the Watermill Switch - Desoto Switch 345kV line to the new Watermill Switch. | 2025-03-11 | 2025-05-15 |  |  | 2570967.11 |  |  | 33 | 345 | na | 0.26 | 2 - 1926.9 ACSS/TW Cumberland | Steel Pole | Station Property | 0.13 | na | na | 25.101(c)(5)(A)
0PT52324 (M3031) | Watermill Switch - West Levee Sub 345 kV Line : Retermination to New Watermill Switch | City of Lancaster, Dallas County | Reterminate the Watermill Switch - West Levee Sub 345kV line to the new Watermill Switch. | 2025-03-13 | 2025-05-15 |  |  | 1671733.17 |  |  | 34 | 345 | na | 0.11 | 2 - 1926.9 ACSS/TW Cumberland | Steel Pole | Station Property | 0.11 | na | na | 25.101(c)(5)(A)
0PT52328 (M3031) | Watermill - Tricorner Sub 345kV Line: Retermination to the New Watermill Switch | City of Lancaster, Dallas County | Reterminate the Watermill Switch - Tricorner Sub 345kV line to the new Watermill Switch. | 2024-09-27 | 2025-05-15 |  |  | 4176005 |  |  | 91 | 345 | na | 0.18 | 2 - 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 0.09 | na | na | 25.101(c)(5)(A)
0PT52725 (R6234) | Temple Elm Creek Switch - Temple Pecan Switch 138 kV Line : High - Temp Upgrade | City of Temple, Bell County | Line work required to increase the 5 mile double circuit line maximum operating temperature. | 2025-02-24 | 2025-05-15 |  |  | 2209591.35 |  |  | 72 | 138 | na | na | 1590 ACSR Falcon | Steel Pole | 70 | na | na | na | 25.101(c)(5)(B)
0PT52864 (R8723) | Benedum (LCRA) - Centralia 138 kV Line: Cut In Upland Substation | City of Rankin, Upton County | Double tap the Benedum (LCRA) - Centralia 138 kV Line with 2 switch structures to establish the Upland Substation. | 2025-03-29 | 2025-05-15 |  |  | 4650601 |  |  | 6 | 138 | na | 0.80 | 1926.9 ACSR/TW Cumberland | Steel 3 - Pole, Steel H-Frame, Steel Pole | 70 | 0.4 | na | na | 25.101(c)(5)(A)
0PT52915 (R6295) | Temple Switch - Bell County Switch 138 kV Line : Line Cut-ins to Establish Fryer's Creek Switch | City of Temple, Bell Country | Cut-In the Temple Switch - Bell Country Switch 138kV Line to establish Fryer's Creek Switch. | 2025-02-28 | 2025-05-01 |  |  | 2599342.94 |  |  | 34 | 138 | na | 0.9 | 959.6 ACSS/TW Suwannee | Steel Pole | 250 | 0.5 | 70 | 0.40 | 25.101(c)(5)(A)
0PT53037 (M4402) | Richardson East Switch - Richardson Spring Creek Sub 138 kV Line : Upgrade Line | City of Richardson, Dallas County | High Temperature Upgrade | 2025-02-26 | 2025-05-31 |  |  | 1813755.22 |  |  | 99* | 138 | na | 0.1 | 795 ACSR Drake | Steel Lattice Tower | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT53091 (R8732) | Sullivan Tap - Taray POD 138 kV Line : Install POI Line to Customer | Loving County | Build a 1.45 mile 138 kV line from Sullivan Tap to customer. | 2025-03-18 | 2025-05-15 |  |  | 3083696.36 |  |  | 23 | na | 138 | 1.45 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | na | na | 70 | 1.45 | 25.101(c)(5)(A)
0PT53323 (R6318) | Cleburne Switch - Hillsboro Switch 138 kV Line : Cut-In to Establish Red Hill Switch | City of Blum, Hill County | Cut in the Cleburne Switch - Hillsboro Switch 138 kV Line 138 kV Line to establish the new Red Hill Switching Station. | 2025-04-07 | 2025-05-08 |  |  | 1369876 |  |  | 0 | 138 | na | 0.2 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.1 | 550 | 0.1 | 25.101(c)(5)(A)
0PT53390 (R6327) | Stephenville Switch – Comanche Switch 138 kV Line : Establish Full House Switch | Erath County | Cut in the Stephenville Switch – Comanche Switch 138 kV Line to establish the new Full House Switch. | 2025-03-03 | 2025-05-08 |  |  | 2024349.73 |  |  | 34 | 138 | na | 0.10 | 1926.9 ACSS/TW Cumberland | Steel Pole, Wood H-Frame | na | na | Varies | 0.1 | 25.101(c)(5)(A)
0PT53403 (M4002) | Montfort Switch - Shankle Switch 138 kV Line : Rebuild Montfort Switch - Telico Tap | City of Ennis, Navarro County | Rebuild the 8.7 mile Montfort Switch - Telico Tap section of the Montfort Switch - Shankle Switch 138 kV Line | 2025-02-03 | 2025-05-15 |  |  | 11969441.93 |  |  | 43 | 138 | na | 8.70 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | na | na | na | 25.101(c)(5)(B)
0PT53422 (R6203) | Hutto Switch - Roundrock Switch 138 kV Line : High-Temp Upgrade | City of Round Rock, Williamson County | Upgrading hardware on northern circuit of 8.9 mile double circuit line between Round Rock and Hutto to increase maximum operating temperature. | 2025-04-01 | 2025-12-15 |  |  | 4178387.93 |  |  | 17 | 138 | na | 8.9 | 1590 ACSR Falcon | Steel Pole | 100 | 8.9 | na | na | 25.101(c)(5)(A)
0PT53461 (R8740) | SL Rocky Road - Stiles 138kV Line: Cut-In Overland Substation (fka Stiles Ranch Substation) | City of Big Lake, Reagan County | Cut-in Rocky Road - Stiles 138kV line to establish the new Overland Substation (fka Stiles Ranch Substation). | 2025-03-31 | 2025-06-30 |  |  | 2439171 |  |  | 1 | 138 | na | 0.10 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 0.10 | na | na | 25.101(c)(5)(A)
0PT53465 0PT55935 (R8798) | SL Carterville - Eiland 138kV Line: Cut-In Carterville Ranch Sub | City of Big Spring, Glasscock County | Cut-in the Carterville - Eiland 138 kV Line to establish the new Carterville Ranch Sub | 2025-02-12 | 2025-05-15 |  |  | 3518487 |  |  | 3 | 138 | na | 0.40 | 1926.9 ACSS/TW Cumberland | Steel Pole | 90 | 0.40 | na | na | 25.101(c)(5)(A)
0PT53524 0PT57313 (R6267) | Creslenn Ranch Switch - Palestine 69kV Line: Establish Holly Springs Sub | City of Montalba, Anderson County | Cut-in the Creslenn Ranch Switch to Palestine 69 kV Line to establish the new Holly Springs Substation. | 2025-02-11 | 2025-05-15 |  |  | 1424088.42 |  |  | 34 | 69 | na | 0.20 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole | Varies | 0.2 | na | na | 25.101(c)(5)(A)
0PT53526 (M4710) | Handley Switch - Hemphill 138kV Line: Reterminate Ayers Sub | Fort Worth, Tarrant | Re-terminate Handley Switch – Hemphill 138kV Line to the rebuilt Ayers Substation. | 2025-04-04 | 2025-10-30 |  |  | 1429876 |  |  | 0 | 138 | na | 0.20 | 1926.9 ACSS/TW Cumberland | Steel Pole | 40 | 0.1 | na | na | 25.101(c)(5)(A)
0PT53561 (R6330) | Trinidad Switch – Corsicana Switch 138 kV Line: Cut-in to Establish the Olympus Switch | City of Kerens, Navarro County | The work required to loop the Trinidad Switch - Corsicana Switch 138kV Line into Olympus Switch. | 2025-03-24 | 2025-05-08 |  |  | 1572379 |  |  | 45 | 138 | na | 0.40 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 0.2 | 70 | 0.2 | 25.101(c)(5)(A)
0PT53571 (M4710) | Crossroads Switch - Paris Switch 138kV Line: Establish Mallory Creek Sub | Lamar County | Cut in the Commerce Switch - Paris Switch138 kV Line to establish the new Mallory Creek Substation. | 2025-02-26 | 2025-12-31 |  |  | 1135729.41 |  |  | 38 | 138 | na | 0.20 | 1033.5 ACSR Curlew | Steel Pole | Centerline | 0.20 | na | na | 25.101(c)(5)(A)
0PT53629 0PT56663 (R8733) | Quarry Field - Kyle Ranch 138 kV Line: Add 2nd Circuit | QUARRY FIELD, Loving County | Install a new 11.3 mile 138 kV second conductor on existing double-circuit structures from Quarry Field - Kyle Ranch. | 2025-01-24 | 2025-05-15 |  |  | 16858554.01 |  |  | 51 | na | 138 | 11.30 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 11.30 | na | na | 25.101(c)(5)(C)
0PT53633 (R6293) | Venus Switch - Sam Switch 345 kV Line: Rebuild Venus Switch - Fort Smith Switch Section | Hill and Ellis County | Rebuild the Venus Switch - Fort Smith Switch 345 kV section on the Venus Switch - Sam Switch 345 kV Double-Circuit Line. | 2024-12-09 | 2025-12-15 |  |  | 61951994.63 |  |  | 18 | 345 | na | 35.20 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 170 | 17.60 | na | na | 25.101(c)(5)(B)
0PT53654 0PT55509 (M3220) | Liggett Switch - DFW Southwest Sub 138 kV Line: Estelle Sub Cut In | City of Dallas, Dallas County | Cut-in line to establish Estelle Substation. | 2025-10-01 | 2026-05-15 | [5 empty] | 0 | 138 | na | 0.40 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0.40 | na | na | 25.101(c)(5)(A)
0PT53667 | Border Switch - Atchison POD - Porterville Sub 138 kV Line : Cut-In to Establish Porterville Substation | City of Mentone, Loving County | Cut in the Border Switch - Atchison POD - Porterville Sub 138 kV Line to establish Porterville Sub | 2025-06-09 | 2025-06-30 |  |  | 251825.23 |  |  | 0 | na | 138 | 0.20 | 1926.9 ACSS/TW Cumberland | na | Station Property | 0.10 | Varies | 70 | 25.101(c)(5)(A)
0PT53829 (R6330) | Trinidad Switch – Montfort Switch 138 kV Line: Cut-in to Establish the Olympus Switch | City of Kerens, Navarro County | The work required to loop the Trinidad Switch - Montfort Switch 138kV Line into Olympus Switch. | 2025-03-31 | 2025-05-08 |  |  | 4071788 |  |  | 6 | 138 | na | 1.3 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.2 | 70 | 1.1 | 25.101(c)(5)(A)
0PT53858 0PT53778 (R3031) | SL Wallaby Switch - Windmill Switch 345 kV Line: Cut-In to Establish Mule Deer Switch | City of Hereford, Deaf Smith County | Cut in the Wallaby Switch - Windmill Switch 345 kV Line to establish the new Mule Deer Switch. | 2025-09-15 | 2025-12-04 | [5 empty] | 0 | 345 | na | 0.10 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower, Steel Pole | na | na | 570 | 0.10 | 25.101(c)(5)(A)
0PT53886 (R1754) | Grindstone Switch - Black Spring BESS 138 kV POI Line: Install Line for Customer | Palo Pinto County | Build one (1) new 138 kV single circuit tie line between the Grindstone Switch and the Customer POI structure. | 2025-02-25 | 2025-05-08 |  |  | 1480092.36 |  |  | 45 | na | 138 | 0.25 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | na | na | 25.101(c)(5)(A)
0PT53923 (M3302) | Toco Switch - Paris Switch 138 kV Line : Cut-in to establish Flying Tiger Switch | City of Paris, Lamar County | Loop the Toco Switch to Paris Switch 138 kV line into Flying Tiger Switch | 2025-03-23 | 2025-05-08 |  |  | 2119072.92 |  |  | 34 | 138 | na | 0.30 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 0.3 | na | na | 25.101(c)(5)(A)
0PT53924 (M3125) | Cash Switch - Sandy Ranch Switch 345 kV Line : Establish Sandy Ranch Switch | City of Sulphur Springs, Hopkins County | Cut-in the Cash Switch - Sandy Ranch Switch 345 kV Line to Sandy Ranch | 2025-03-13 | 2025-05-08 |  |  | 3402249.65 |  |  | 34 | 345 | na | 0.30 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 170 | 0.3 | na | na | 25.101(c)(5)(A)
0PT53991 | Hutto Switch - Round Rock Sub 138 kV Line : rosion and Foundation Restoration | City of Round Rock, Williamson County | Restore damaged and eroded foundations on the Hutto Switch - Round Rock Sub 138 kV Line | 2025-10-15 | 2025-12-31 | [5 empty] | 0 | 138 | na | 10.54 | 1590 ACSR Falcon | Steel 3 - Pole | 100 | 5.27 | na | na | 25.101(c)(5)(B)
0PT53992 | Killeen Switch - Killeen Fort Hood Sub 138 kV Line : Erosion and Foundation Restoration | City of Killeen, Bell County | Restore damaged and eroded foundations on the Killeen Switch - Killeen Fort Hood Sub 138 kV Line | 2024-12-02 | 2025-05-31 |  |  | 451854 |  |  | 70 | 138 | na | 2.94 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole | 40 | 2.94 | na | na | 25.101(c)(5)(B)
0PT53993 | Temple Switch - Temple Elm Creek Switch 138 kV Line : Erosion and Foundation Restoration | City of Temple, Bell County | Restore damaged and eroded foundations on the Temple Switch - Temple Elm Creek Switch 138 kV Line | 2025-10-15 | 2025-12-31 | [5 empty] | 0 | 138 | na | 7.98 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole | Varies | 3.99 | na | na | 25.101(c)(5)(B)
0PT54155 | Cedar Hill Switch - Soap Creek Switch 138 kV Line : Install OPGW | City of Midlothian, Ellis County | Install OPGW on the Cedar Hill Switch - Soap Creek Switch 138 kV Line | 2025-03-03 | 2025-05-30 |  |  | 791,146.39 |  |  | 99* | 138 | na | 11 | 959.6 ACSS/TW Suwannee | Steel Lattice Tower | 100 | 5.5 | na | na | 25.101(c)(5)(A)
0PT54161 (M3230) | Liggett Switch - Euless Sub 138 kV Line : Estelle Sub Cut In | City of Dallas, Dallas County | This project will be to cut the Liggett Switch - Euless Sub 138 kV Line into the new Estelle Substation. | 2025-10-01 | 2026-05-15 | [5 empty] | 0 | 138 | na | 0.40 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0.40 | na | na | 25.101(c)(5)(A)
0PT54563 (M5301) | Kirkland Park Switch - Northaven Switch 138 kV Line : Retermination at Edgemere Sub | City of Dallas, Dallas County | Retermination of the Kirkland Park Switch - Northaven Switch 138kV Line at Orr Branch Sub (fka Edgemere Terminal) | 2025-03-19 | 2025-05-15 |  |  | 1395682.79 |  |  | 34 | 138 | na | 0.20 | 2 - 959.6 ACSS/TW Suwannee | Steel 2 - Pole | Varies | 0.10 | na | na | 25.101(c)(5)(A)
0PT54645 | Hilltop Switch - Weatherford West Switch 69 kV Line : Replace deficiencies on structures 25/4, 25/1, 25/2, 25/6, 25/7, 25/8, 25/9, 25/10, 26/1(LineMitigation24) | Parker County | Replace structures on Hilltop Switch - Weatherford West Switch 69 kV Line. | 2024-03-28 | 2024-06-06 | 2024-06-06 |  | 576196.7 |  |  | 100 | 69 | na | 4.57 | 4/0 ACSR Penguin | Wood H-Frame | Varies | 4.57 | na | na | 25.101(c)(3)
0PT54787 0PT57904 (R8808) | Canal Road Sub - Hadacol Corner Sub 138 kV Line : Cut-In to Establish North Canal Road Substation | City of Midkiff, Upton County | Cut-in the Canal Road Sub - Hadacol Corner Sub 138 kV Line to establish North Canal Road Sub. | 2025-04-14 | 2025-05-15 | [5 empty] | 0 | 138 | na | 0.20 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 0.2 | Varies | 0.20 | 25.101(c)(5)(A)
0PT55060 (R6295) | Temple Sub - Taylor Sub 69 kV Line : Upgrade to 138kV Connection to Fryer's Creek Switch and add 2nd Circuit | City of Temple, Bell County | Line work to cut-in Fryer's Creek Switch, upgrade existing line to 138kV, and add second circuit to re-terminate Temple Sw-Minverva 69kV line from Temple Sw to Fryer's Creek Switch. | 2025-02-12 | 2025-05-01 |  |  | 2676779.46 |  |  | 99 | 69 | na | 1.20 | 959.6 ACSS/TW Suwannee | Steel Pole | 70 | 1.20 | na | na | 25.101(c)(5)(A)
0PT55061 0PT55971 (R6295) | Bob Pogue Sub - Seaton Sub 69 kV Line : Add 2nd Circuit | City of Temple, Bell County | Line work to add second circuit to re-terminate Temple Sw - Minerva 69kV line from Temple Sw to Fryer's Creek Switch. | 2025-02-15 | 2025-05-01 |  |  | 4226043.15 |  |  | 34 | 69 | na | 3.80 | 959.6 ACSS/TW Suwannee | Steel Pole | 70 | 3.80 | na | na | 25.101(c)(5)(A) | The Final Estimated Cost was revised to correct a numerical discrepancy reported last month.
0PT55062 (R6295) | Temple Switch - Minerva Sub 69 kV Line : Retermination from Temple Sw to Fryer's Creek Switch | City of Temple, Bell County | Line work to re-terminate from Temple Sw to Fryer's Creek. Associated with add second circuit projects 55060 and 55061. | 2025-03-21 | 2025-05-01 |  |  | 734960.48 |  |  | 34 | 69 | na | 0.10 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole | 70 | 0.10 | na | na | 25.101(c)(5)(A)
0PT55083 (R8733) | Riverton Switch - Quarry Field Switch 138kV Line: Retermination | City of Mentone, Loving County | Reterminate the Riverton - Quarry Field 138kV line into Quarry Field. | 2025-02-22 | 2025-05-15 |  |  | 2797211.5 |  |  | 26 | 138 | na | 0.60 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 0.30 | na | na | 25.101(c)(5)(B)
0PT50119 0PT55506 (R6245) | Killeen Fort Hood Switch - Killeen Fort Hood Sub 138 kV Line : Line Rebuild | City of Killeen, Bell County | Rebuild a section of Killeen Fort Hood Switch - Killeen Fort Hood Sub 138 kV Line. | 2026-03-02 | 2026-05-15 | [5 empty] | 0 | 138 | na | 2.20 | 959.6 ACSS/TW Suwannee | Steel Pole | 100 | 2.20 | na | na | 25.101(c)(5)(B)
0PT51148 | Graham Plant - Breckenridge Switch - Leon Switch 138 kV Line : Aging Infrastructure | City of Graham, Young County | Replace aging infrastructure on the Graham Plant - Breckenridge Switch - Leon Switch 138 kV Line. | 2025-11-15 | 2026-05-15 | [5 empty] | 0 | 138 | na | 84.00 | 636 ACSR Grosbeak | Wood H-Frame | Varies | 84 | na | na | 25.101(c)(5)(B)
0PT51470 (M3509) | Graham Switch - Parker Switch 345 kV Line: Cut-in to establish Long Hollow Switch | City of Jacksboro, Jack County | Cut into the Graham Plant Switch - Parker Switch 345 kV Line to establish Long Hollow Switch. | 2025-03-24 | 2025-05-08 |  |  | 4116062.56 |  |  | 14 | 345 | na | 0.50 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower, Steel Pole | 100 | 0.5 | na | na | 25.101(c)(5)(A)
0PT52250 0PT54505 (M4081) | Seagoville Switch – Wilmer Switch 138 kV Line: Rebuild | City of Wilmer, Dallas County | Rebuild the Seagoville Switch - Wilmer Switch 138 kV Line. | 2025-02-24 | 2025-12-15 |  |  | 38193649.18 |  |  | 39 | 138 | na | 11.16 | 2 - 959.6 ACSS/TW Suwannee | Steel H-Frame, Steel Pole | Varies | 11.16 | na | na | 25.101(c)(5)(B)
0PT52546 (M4008) | Royse Switch - Guevara Storage 345 kV Line: Establish POI | City of Royse, Rockwall County | Establish POI Line to connect Royse Switch to Guevara Storage. | 2025-02-26 | 2025-05-08 |  |  | 1929583.66 |  |  | 99* | na | 345 | 0.28 | 2 - 1926.9 ACSS/TW Cumberland | Steel 3 - Pole | na | na | 160 | 0.28 | 25.101(c)(5)(A)
0PT52874 (R6148) | Brushy Creek Switch - LCRA Elgin 138 kV: Tie Line | City of Elgin, Williamson County | Relocate the existing 138 kV tie line between Brushy Creek Switch and LCRA's Elgin Switch to its new bay position inside Elgin Switch. | 2025-03-13 | 2025-05-15 |  |  | 1624946 |  |  | 60 | 138 | na | 0.10 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 0.10 | na | na | 25.101(c)(5)(D)
0PT53487 (R8704) | Wellbore Switch - Barr Ranch Switch 138 kV Line: Add 2nd Circuit from 6/4R to Barr Ranch | Midland County | Add second circuit to the Salt Flat Road Switch - Barr Ranch Switch 138 kV Line. | 2025-04-01 | 2025-12-15 |  |  | 8410163.53 |  |  | 0 | 138 | na | 8.90 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 8.90 | na | na | 25.101(c)(5)(A)
0PT53513 0PT54478 (R8731) | Salt Flat Road Sub - Barr Ranch Switch 138 kV Line : Establish Red Corn Tap | City of Midland, Midland County | Line work to establish POD to connect Pheasant Station to Salt Flat Road Sub - Barr Ranch Switch 138 kV line. | 2025-04-15 | 2026-05-15 |  |  | 2527615 |  |  | 0 | 138 | na | 0 | 1926.9 ACSS/TW CUMBERLAND | Steel 3 – Pole Switch, Steel Pole | 70 | na | na | na | 25.101(c)(5)(A)
0PT53737 (M4372) | Wilmer - Ferris 69 kV Line: Conversion to 138 kV | City of Lancaster, Dallas County | Convert the 4 mile section between Ferris and Wilmer to 138 kV operation. | 2025-09-15 | 2025-12-31 | [5 empty] | 0 | 69 | 138 | 2.30 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 2.30 | na | na | 25.101(c)(5)(A)
0PT53940 | Watermill Switch - Cedar Crest Switch 138 kV Line : Replace structure T/418 and 8S3ET465 | City of Lancaster, Dallas County | Replace and relocate double-circuit lattice tower T/418 and 8S3ET465 on the Hillsboro - Whitney 138 kV. | 2025-03-25 | 2025-05-31 |  |  | 3347090 |  |  | 17 | 138 | na | 0.44 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | 100 | 0.22 | na | na | 25.101(c)(5)(B)
0PT53942 | Benbrook Switch - Mistletoe Heights Switch 138 kV Line : Replace Tower 1/4 | City of Fort Worth, Tarrant County | Replace Tower 1/4 with 2 monopoles due to torn up tower leg. | 2024-02-05 | 2024-04-10 | 2024-04-10 |  | 601207.25 |  |  | 100 | 138 | na | 0.60 | 1926.9 ACSS/TW Cumberland | Steel 2 - Pole | 230 | 0.30 | na | na | 25.101(c)(5)(B)
0PT53966 (M4340) | Sherman South - MEMC SW - Valley Switch 138 kV Line: Re-establish line after Sherman South Sub Retirement | City Of Sherman, Grayson County | Line work associated with retiring the existing Sherman South Sub | 2025-05-01 | 2025-06-01 | [5 empty] | 0 | 138 | na | 0.10 | 795 ACSR Drake | Steel Lattice Tower | 100 | 0.10 | na | na | 25.101(c)(5)(B)
0PT54097 (M4081) | Watermill Switch - Wilmer Switch 138 kV Line: Rebuild | City of Lancaster, Dallas County | Rebuild the Watermill Switch - Wilmer Switch 138 kV line. | 2025-09-16 | 2025-12-15 | [5 empty] | 0 | 138 | na | 4.37 | 2 - 959.6 ACSS/TW Suwannee | Steel H-Frame, Steel Pole | Varies | 3.40 | Varies | .97 | 25.101(c)(5)(B)
0PT54213 (M4009) | Liggett Switch - Irving Norwood Sub 138 kV Line : Cut-in to establish Wildwood Sub | City of Irving, Dallas County | Line work associated with the establishment of Wildwood Substation. | 2025-05-01 | 2025-12-15 | [5 empty] | 0 | 138 | na | 0.90 | 959.6 ACSS/TW Suwannee | Steel Pole | Station Property | 0.90 | na | na | 25.101(c)(5)(A)
0PT54502 0PT55985 (R8704) | Pegasus Tap - Barr Ranch Switch 138 kV Line : Add 2nd 138 kV Circuit | City of Odessa, Midland County | Add new 138 kV circuit to the existing Barr Ranch - Quickriver - Pegasus South Tap - Pleasant Farms Tap138 kV line. | 2025-03-29 | 2025-12-15 |  |  | 17163492.02 |  |  | 0 | 138 | na | 18.96 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | 50 | 18.46 | Varies | 0.50 | 25.101(c)(5)(C)
0PT55153 | Waco Atco - Cotton Belt Tap 138 kV line: Storm Restoration | City of Waco, McLennan County | Replace structures impacted on the Waco Atco - Cotton Belt Tap 138 kV Line due to storm damage. | 2024-05-17 | 2024-05-23 | 2024-05-23 |  | 894596.09 |  |  | 100 | 138 | na | 0.3 | 795 ACSR Drake | Wood H-Frame | 100 | 0.3 | na | na | 25.101(c)(3)
0PT55223 | Marlin - South Marlin Tap - Lott 69 kV Line: Storm Damage (TSP24017) | City of Marlin, Falls County | Replace wood structures on the Marlin - South Marlin Tap - Lott 69 kV Line | 2024-05-22 | 2024-06-21 | 2024-06-21 |  | 359653.12 |  |  | 100 | 69 | na | 0.45 | 4/0 ACSR Penguin | Wood Pole | 35 | 0.45 | na | na | 25.101(c)(5)(B)
0PT55256 | Krum Tap - Spring 138 kV Line: Emergency Storm Restoration | City of Valley View, Cooke County | Replace Structures on the Krum Tap - Spring 138 kV Line due to storm damage. | 2024-05-26 | 2024-06-01 | 2024-06-01 |  | 1215196.8 |  |  | 100 | 138 | na | 1.30 | 795 ACSR Drake | Wood H-Frame | 100 | 1.30 | na | na | 25.101(c)(3)
0PT55276 | Overton - Troup 69 kV Line: Storm Restoration | City of Overton, Rusk County | Replace structures on Overton - Troup 69 kV Line due to storm damage | 2024-05-28 | 2024-06-01 | 2024-06-01 |  | 247617.79 |  |  | 100 | 69 | na | 0.10 | 4/0 ACSR Penguin | Wood Pole | Centerline | 0.10 | na | na | 25.101(c)(3)
0PT55279 | Canton Sub - Canton Switch 138 kV Line : Storm Restoration (TSP24019) | City of Canton, Van Zandt County | Three Structures are damaged due to the weather event. Structures 6/3, 6/4, 6/5, 8/6, 8/7 are affected. | 2024-05-29 | 2024-06-01 | 2024-06-01 |  | 166577.95 |  |  | 100 | 138 | na | 0.8 | 336.4 ACSR Linnett | Wood H-Frame | 100 | 0.8 | na | na | 25.101(c)(3)
0PT55449 (R8694) | SL Driver - Canal Road 138 kV Line: Cut in to Establish Savanna Sub | City of Canton, Reagan County | Replace the existing 5 pole wood deadend structure at 8/5 with a 3 pole deadend steel structure. | 2024-12-05 | 2024-12-23 | 2024-12-23 |  | 292463.69 |  |  | 100 | 138 | na | 0.12 | 1926.9 ACSS/TW Cumberland | Steel Pole | Station Property | 0.12 | na | na | 25.101(c)(5)(A)
0PT55671 | Eustace Southeast Sub - Canton Switch 138 kV Line : Replace Structure 8/5 | City of Canton, Van Zandt County | Replace structure 8/5 on Eustace Southeast Sub - Canton Switch 138 kV Line. | 2025-04-15 | 2025-05-15 |  |  | 996369 |  |  | 0 | 138 | na | 0.20 | 336.4 ACSR Linnett | Steel 3 - Pole | Varies | 0.2 | na | na | 25.101(c)(5)(A)
0PT49465 | Benbrook Switch - Parker Switch 345 kV Line : Insulator Replacement | City of Fort Worth, Tarrant County | Replace insulators on the Benbrook Switch - Parker Switch 345 kV line. | 2025-03-11 | 2025-05-15 |  |  | 1728082 |  |  | 99* | 345 | na | 5.00 | 2 - 795 ACSR DRAKE | Steel Lattice Tower | 300 | 5.00 | na | na | 25.101(c)(5)(B)
0PT49556 0PT49195 (M3006) | Chico West Tap Switch - Oran Switch 69 kV Line: Rebuild Jacksboro Amoco - Jacksboro Substation to 138 kV | City of Jacksboro, Jack County | Rebuild the Jacksboro Amoco - Jacksboro Substation section of the Chico West Tap Switch - Oran Switch 69 kV single circuit line. | 2025-03-01 | 2025-09-15 |  |  | 12472306 |  |  | 1 | 69 | 138 | 7.11 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 7.11 | na | na | 25.101(c)(5)(B)
0PT51781 | Cedar Hill Switch - Liggett Switch 138 kV Line : Relocation | City of Grand Prairie, Tarrant County | Relocate the Cedar Hill Switch - Liggett Switch 138 kV Line to establish Tyre Park Sub | 2025-03-31 | 2026-05-15 |  |  | 1764453 |  |  | 23 | 138 | na | 0.30 | 795 ACSR Drake | Steel Pole | Varies | 0.30 | na | na | 25.101(c)(5)(A)
0PT53459 0PT57984 (R8334) | McKenzie Draw Switch - Midland County Northwest Switch: Cut-In Aqueduct Substation | Midland County | Cut into the McKenzie Draw Switch-Midland County Northwest Switch 138 kV line to establish the new Aqueduct Substation | 2025-04-02 | 2025-05-15 |  |  | 2246819 |  |  | 0 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel Pole | 75 | 0.1 | 100 | 0.3 | 25.101(c)(5)(A)
0PT53902 (M4369) | Watermill Switch - Parkdale Switch 138 kV Line: Cut In Wilmer Switch | City of Wilmer, Dallas County | Cut-in the Watermill Switch - Parkdale Switch 138 kV Line to establish Wilmer Switch. | 2025-10-13 | 2025-12-01 | [5 empty] | 0 | 138 | na | 0.41 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0.31 | Varies | 0.10 | 25.101(c)(5)(A)
0PT53941 | Lake Hubbard Switch - Prairie Creek Switch 138 kV Line : Relocate structure T438 and install erosion control | City of Garland, Dallas County | Replace structure T438 with monopole. | 2025-04-16 | 2025-06-02 |  |  | 1499983 |  |  | 0 | 138 | na | 0.54 | 1431 ACSR Plover | Steel Pole | Varies | 0.27 | na | na | 25.101(c)(5)(B)
0PT54217 0PT54728 | Bonham Switch - Toco Switch 69 kV Line : Replace Strs | City of Toco, Lamar County | Rebuild structures on the Bonham Switch - Toco Switch 69 kV line. | 2025-05-01 | 2025-05-31 | [5 empty] | 0 | 69 | na | 0.30 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 0.30 | na | na | 25.101(c)(5)(B)
0PT54935 0PT55259 | Corsicana Sub - Navarro Switch 138 kV Line : Relocation for Union Pacific's Bridge 619.57 | City of Corsicana, Navarro County | Relocation with new single circuit steel monopole structures. | 2025-03-20 | 2025-05-15 |  |  | 1417275 |  |  | 1 | 138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 0.1 | na | na | 25.101(c)(5)(B)
0PT56014 | Collin Switch - Stone Creek Switch 138 kV Line : Replace Structure 4/10 | City of Sherman, Grayson County | Replace and relocate double-circuit steel pole 4/10 on the Collin Switch - Stone Creek Switch 138 kV. | 2025-04-14 | 2025-05-01 |  |  | 2748869 |  |  | 0 | 138 | na | 0.01 | 1926.9 ACSR/TW Cumberland | Steel Pole | 100 | 0.01 | na | na | 25.101(c)(5)(B)
11T62379 0PT50703 | Randol Mill Substation - Hemphill Substation 138 kV Line: Section Rebuild | City of Fort Worth, Tarrant County | Rebuild a section of the Randol Mill Substation - Hemphill Substation 138 kV Line. | 2025-12-15 | 2026-01-31 | [5 empty] | 0 | 138 | na | 0.40 | 795 ACSR Drake | Steel Pole | 0.4 | 0.4 | na | na | 25.101(c)(5)(B)
0PT40873 0PT52794 (R8528) | Wolf Switch - Sandhills Tap 138 kV Line: Rebuild | City of Monahans, Ward County, Winkler County and Ector County | Rebuild the Wolf Switch-Sandhills Tap 138 kV Line | 2025-05-01 | 2025-12-31 | [5 empty] | 0 | 138 | na | 14.20 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | 50 | 14.20 | na | na | 25.101(c)(5)(B)
0PT46608 | Roanoke Switch - Lewisville Switch 345 kV Line : Dunham Cut-In | City of Roanoke, Denton County | Cut-in the Roanoke Switch - Lewisville Switch 345 kV Line and Krum West Switch - Lewisville Switch 345 kV Line to establish the new Dunham Switch. | 2025-01-24 | 2025-12-31 |  |  | 22912597.82 |  |  | 54 | 345 | na | 5.06 | 2 - 1926.9 ACSS/TW Cumberland | Steel 2 - Pole, Steel Lattice Tower, Steel Pole | 160 | 0.25 | 100 | 2.28 | 25.101(c)(5)(A)
0PT51183 | North Lake Switch - Carrollton East Switch 138 kV Line : Replace Structure 14N7WT238F | City of Carrollton, Dallas County | Replace wood pole structure. | 2025-04-07 | 2025-05-15 |  |  | 518917 |  |  | 0 | 138 | na | 0.10 | 336.4 ACSR Linnett | Steel Pole | Varies | 0.10 | na | na | 25.101(c)(5)(B)
0PT51429 0PT55232 (R6283) | Hillsboro Switch - Navarro Switch 138 kV Line : Reterminate Hubbard Sub | City of Hubbard, Hill County | This project is for the re-termination of Hubbard substation (re-build station with 1 transformer). | 2025-04-20 | 2025-06-01 |  |  | 3841810.72 |  |  | 0 | 138 | na | 0.40 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.40 | na | na | 25.101(c)(5)(A)
0PT52888 | Arco (DME) - Blagg Sub - Krugerville Sub 138 kV Line: SkyWrap Installation | City of Krugerville, Denton County | Install SkyWrap fiber optic cable on the existing shieldwire on the Arco - Krugerville 138 kV Line. | 2025-09-01 | 2025-12-15 | [5 empty] | 0 | 138 | na | 11.60 | 1926.9 ACSS/TW CUMBERLAND | Concrete H-Frame | Varies | 5.80 | na | na | 25.101(c)(5)(B)
0PT52889 | Frisco Sub (Brazos) - Collin Sub 138 kV Line: SkyWrap Installation | City of Frisco, Collin County | Install SkyWrap fiber optic cable on the existing shieldwire on the Frisco - Collin 138 kV Line. | 2025-09-01 | 2025-12-15 | [5 empty] | 0 | 138 | na | 4.00 | 1926.9 ACSS/TW CUMBERLAND | Steel Pole | 100 | 2 | na | na | 25.101(c)(5)(B)
0PT53124 (M5178) | DFW A East Sub - DFW Northeast Sub 138 kV Line : Construct New UG XLPE Line | City of Dallas, Dallas County | Construct a 138 kV UG XLPE circuit of two cables per phase between DFW A East Sub - DFW Northeast Sub to establish the new DFW Northeast Substation. | 2025-04-01 | 2026-06-30 |  |  | 35549013 |  |  | 0 | na | 138 | 1.00 | 6000 CU XLPE | na | 25 | 1.00 | na | na | 25.101(c)(5)(A)
0PT53530 0PT56156 | Seymour Sub - Munday Sub 69 kV Line : CMPC Line Hardening (Str. 39/24 - 39/25) | City of Seymour, Baylor County | Replace structure 39/24 & 39/25 with steel poles. | 2025-07-15 | 2025-12-31 | [5 empty] | 0 | 69 | na | 0.50 | 1/0 ACSR Raven | Steel Pole | 50 | 0.50 | na | na | 25.101(c)(5)(B)
0PT53632 0PT54494 0PT56681 (R8681) | SL Estacado - Tredway 138 kV Line: Rebuild | City of Ackerly, Martin County | Rebuild the 16.1-mile SL Estacado (Brown) - Tredway (Vealmoor) 138 kV line section | 2025-04-01 | 2025-12-31 |  |  | 46470363 |  |  | 0 | 138 | na | 32.20 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 16.10 | na | na | 25.101(c)(5)(B)
0PT54481 0PT54482 0PT56621 0PT55548 (R8713) | SL Pemkiff - Stiles 138 kV Line: Retermination at Ringo | Reagan County | Re-terminate the existing circuits to Pemkiff and Stiles connected at Ringo to their new terminal locations in the reconfigured Ringo Switch. | 2025-09-01 | 2025-11-15 | [5 empty] | 0 | 138 | na | 0.15 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | na | Varies | 0.15 | 25.101(c)(5)(A)
0PT54573 (R6077) | Stryker Creek Switch - Lufkin Switch 345 kV Line : Rebuild for Lufkin to Redland 345 kV Line | City of Lufkin, Angelina County | Rebuild the existing Lattice Tower structures that parallel the new Lufkin Switch to Redland Switch 345 kV Line to steel poles. | 2025-02-25 | 2025-12-15 |  |  | 4382942.02 |  |  | 34 | 345 | na | 2.00 | 2 - 1926.9 ACSS/TW Cumberland, 2/0 ACSR Quail | Steel Pole | 170 | 1.00 | 200 | 1.00 | 25.101(c)(5)(B) | The project will be moved to the CCN section and will not be included in this section in next month's report.
0PT54725 0PT54006 (R8681) | SL Vealmoor Sub - Luther Sub 138 kV Line : Tredway Retermination | City of Ackerly, Martin County | Reterminate the Vealmoor to Luther 138 kV Line into Tredway. | 2025-10-06 | 2025-12-15 | [5 empty] | 0 | na | 138 | 0.50 | 1926.9 ACSS/TW Cumberland | Steel Pole | na | na | Varies | 0.5 | 25.101(c)(5)(A)
0PT55347 (M5148) | Ramhorn Hill Switch - Dunham Switch 138 kV Line: Install New Circuit | City of Roanoke, Denton County | Install the 138 kV circuit from Ramhorn Hill to Dunham. | 2025-03-04 | 2026-12-14 |  |  | 14696428.08 |  |  | 11 | 138 | na | 20.6 | 1926.9 ACSS/TW/E3X Cumberland | Steel 3 - Pole, Steel H-Frame | 100 | 20.6 | na | na | 25.101(c)(5)(C)
0PT55947 (R6203) | Round Rock Sub - Structure 19/4 Tap 138 kV Line: Rebuild | City of Round Rock, Williamson County | Rebuild the 0.42 mile section between Round Rock Switch to Round Rock Tap (Structure 19/4) to be double circuit with 1926 ACSS/TW conductor and OPGW. | 2025-03-20 | 2025-05-15 |  |  | 1667608.17 |  |  | 27 | 138 | na | 0.84 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.42 | na | na | 25.101(c)(5)(B)
0PT46135 (R6094) | Elkton - Forest Grove 138 kV Line: Reterminate at Foggle Switch | City of Athens, Henderson County | Reterminate the Elkton - Forest Grove Switch at new Foggle Switch and install OPGW between Forest Grove Switch and Foggle Switch. | 2025-03-12 | 2025-09-15 |  |  | 4913065.7 |  |  | 6 | 138 | na | 0.11 | 959.6 ACSS/TW Suwannee | Steel Pole | Centerline | 0.01 | 100 | 0.10 | 25.101(c)(5)(A)
0PT47026 0PT54956 (R6203) | Salado Switch - Round Rock South Tap 138 kV Line: Rebuild Round Rock South Tap to Structure 25/8 | City of Round Rock, Williamson County | Rebuild the 11.6 mile section between Round Rock Switch to Structure 25/8 to be double circuit with 1926 ACSS/TW conductor and OPGW. | 2025-03-07 | 2025-12-15 |  |  | 24920880.56 |  |  | 29 | 138 | na | 11.60 | 1926.9 ACSS/TW/E3X Cumberland | Steel Pole | Varies | 11.60 | na | na | 25.101(c)(5)(A)
0PT52723 (R6235) | Temple Switch - Temple Pecan Creek Switch 138 kV Line : Install 2nd Circuit | City of Temple, Bell County | Install a second circuit on the 4.4 mile existing Temple Switch - Temple Pecan Creek 138 kV Line. | 2025-02-24 | 2026-05-15 |  |  | 7254195.3 |  |  | 81 | 138 | na | 4.40 | 1926.9 ACSS/TW Cumberland | Steel Pole | 225 | 4.40 | na | na | 25.101(c)(5)(C)
0PT52871 (R6243) | Sandow Switch - Taylor 138 kV Line: Establish Walleye Creek Switch | City of Thorndale, Milam County | Cut-in the Sandow Sw - Taylor 138 kV Line to Establish Walleye Creek Switch | 2025-04-01 | 2025-12-15 |  |  | 6793200 |  |  | 0 | 138 | na | 2.4 | 2 - 959.6 ACSS/TW Suwannee, 1926.9 ACSS/TW Cumberland | Steel 2 - Pole, Steel Pole | 100 | 1.49 | 70 | 0.90 | 25.101(c)(5)(A)
0PT53485 (R8704) | Wellbore Switch - Barr Ranch Switch 138 kV Line: Add 2nd circuit from 6/4R to Johnson Draw POD | City of Midland, Midland County | Adding a second circuit to the Salt Flat Road Switch - Barr Ranch Switch 138 kV Line. | 2025-06-02 | 2025-12-15 | [5 empty] | 0 | 138 | na | 2.85 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 2.85 | na | na | 25.101(c)(5)(C)
0PT54717 (R8681) | SL Tredway Switch - Vealmoor Sub 138 kV Line : 138 kV Tie Line | City of Ackerly, Martin County | Build the new tie line between Tredway Switch to Vealmoor Sub. | 2025-10-06 | 2025-12-15 | [5 empty] | 0 | na | 138 | 0.50 | 1926.9 ACSS/TW Cumberland | Steel 2 - Pole, Steel Pole | 100 | .50 | na | na | 25.101(c)(5)(A)
0PT54964 (R6276) | Lake Creek Switch - Temple Pecan Creek/Tradinghouse 345kV Line: Cut in to establish Possum Trot Switch | McLennan County | Cut-in to establish Possum Trot Switch | 2026-01-05 | 2026-05-15 | [5 empty] | 0 | 345 | na | 2.00 | 2 - 795 ACSR Drake | Steel Lattice Tower | 100 | 1 | na | na | 25.101(c)(5)(A)
0PT54966 | Possum Trot Switch - Lake Hall Switch 345 kV Line : Reterm | City of Riesel, McLennan County | Retermination of the existing Lake Creek Switch – Lake Hall Switch 345 kV line into the new Possum Trot Switch. | 2025-04-15 | 2026-05-15 |  |  | 2826954 |  |  | 0 | 345 | na | 0.35 | 2 - 1926.9 ACSR/TW Cumberland | Steel Lattice Tower, Steel Pole | 100 | 0.35 | na | na | 25.101(c)(5)(A)
0PT55139 | Kleberg Tap - Kleberg Sub 138 kV Line : Replace and relocate Str. 107 | City of Dallas, Dallas County | Replace and relocate structure on Kleberg Tap - Kleberg Sub 138 kV Line | 2025-03-31 | 2025-06-30 |  |  | 859993 |  |  | 0 | 138 | na | 0.50 | 336.4 ACSR Linnett | Steel Pole | 50 | 0.50 | na | na | 25.101(c)(5)(A)
0PT56158 (R6203) | Hutto Switch - Round Rock Westinghouse Tap 138 kV Line : High-Temp Upgrade South Circuit | City of Round Rock, Williamson County | Upgrading hardware on southern circuit of 8.5 mile double circuit line between Round Rock and Hutto to increase maximum operating temperature. | 2025-04-01 | 2025-12-15 |  |  | 373057.06 |  |  | 17 | 138 | na | 8.50 | 1590 ACSR Falcon | Steel Pole | 100 | 8.50 | na | na | 25.101(c)(5)(A)
0PT44282 0PT48647 (M5261) | Eagle Mountain Switch - Base Camp Switch 138 kV Line No 1 | City of Eagle Mountain, Tarrant County | Line connection No 1 between Eagle Mountain Switch - Base Camp Switch. This project covers the temporary connection between the West bus of Eagle Mountain Switch to the South bus of Base Camp Switch. | 2025-04-24 | 12/15/2025 |  |  | 1741619 |  |  | 0 | na | 138 | 0.29 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | na | na | Varies | 0.29 | 25.101(c)(5)(A)
0PT44288 (M5261) | Eagle Mountain Switch - Calmont Switch 138 kV Line : Base Camp Switch Retermination (South) | City of Eagle Mountain, Tarrant County | Retermination of south circuit of Eagle Mountain Switch - Calmont Switch 138 kV Line at Base Camp Switch | 2025-04-28 | 12/15/2025 |  |  | 1201829 |  |  | 0 | 138 | na | 0.14 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | na | na | Varies | 0.14 | 25.101(c)(5)(A)
0PT44289 (M5261) | Eagle Mountain Switch - Hicks Switch 138 kV Line : Re-termination at Base Camp Switch (South) | City of Eagle Mountain, Tarrant County | Retermination of Eagle Mountain Switch - Hicks Switch 138 kV Line at Base Camp Switch | 2025-04-24 | 12/15/2025 |  |  | 1093745 |  |  | 0 | 138 | na | 0.14 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | na | na | Varies | 0.14 | 25.101(c)(5)(A)
0PT44290 (M5261) | Eagle Mountain Switch - Weatherford Switch 138 kV Line : Base Camp Switch Retermination | City of Eagle Mountain, Tarrant County | Retermination of Eagle Mountain Switch - Weatherford Switch 138 kV Line at Base Camp Switch | 2025-04-24 | 12/15/2025 |  |  | 1233097 |  |  | 0 | 138 | na | 0.13 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | na | na | Varies | 0.13 | 25.101(c)(5)(A)
0PT44293 (M5261) | Eagle Mountain Switch - Base Camp Switch 138 kV Line No 2 | City of Eagle Mountain, Tarrant County | Line connection No 2 between Eagle Mountain Switch - Base Camp Switch. This project covers the temporary connection between the East bus of Eagle Mountain Switch to the North bus of Base Camp Switch. | 2025-04-24 | 12/15/2025 |  |  | 1750861 |  |  | 0 | na | 138 | 0.26 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | na | na | Varies | 0.26 | 25.101(c)(5)(A)
0PT45154 (M5261) | Eagle Mountain Switch - Calmont Switch 138 kV Line : Base Camp Switch Retermination (North) | City of Eagle Mountain, Tarrant County | Retermination of north circuit of Eagle Mountain Switch - Calmont Switch 138 kV Line at Base Camp Switch | 2025-04-28 | 12/15/2025 |  |  | 1218972 |  |  | 0 | 138 | na | 0.14 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | na | na | Varies | 0.14 | 25.101(c)(5)(A)
0PT46689 0PT48103 (R6186) | Temple Switch - Minerva Switch 69 kV Line: Rebuild | City of Temple, Bell County | Rebuilding the Temple Switch to Str. 11/8 section of the 33.6 mile Temple Switch – Minerva Switch Line 69 kV. | 2025-05-15 | 2025-09-19 | [5 empty] | 0 | 69 | na | 10.00 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | Varies | 10.00 | na | na | 25.101(c)(5)(B)
0PT46953 (R3024) | Ranger Camp Switch - Range Rider Switch 138 kV Line | Colorado City, Mitchell County | Construct a new double circuit tie line between Ranger Camp and Range Rider. | 2025-05-12 | 12/15/2025 | [5 empty] | 0 | 138 | na | 1.85 | 1926.9 ACSR/TW Cumberland, 1926.9 ACSS/TW Cumberland | Steel Pole | 1.25 | 0.65 | na | na | 25.101(c)(5)(B)
0PT53630 (R8733) | Kyle Field - Riverton 138 kV Line: Add 2nd Circuit | Riverton, Reeves and Loving County | Install a new 19.4 mile 138 kV second conductor on existing double-circuit structures from Riverton - Kyle Ranch. | 2025-05-12 | 12/15/2025 | [5 empty] | 0 | na | 138 | 19.40 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 19.40 | na | na | 25.101(c)(5)(C)
0PT54154 (R6361) | Richland Chambers Switch - Calpine POI 345-kV Line: Establish POI | City of Fairfield, Freestone County | Establish POI Line to connect Richland Chambers Switch to Calpine Freestone Peaker 1 & 2. | 2025-04-04 | 10/30/2025 |  |  | 2880016 |  |  | 0 | na | 345 | 0.20 | 2 - 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | na | na | Varies | 0.20 | 25.101(c)(5)(A)
0PT54223 (R8661) | Rockhound - Ranger Camp 345kV Line: Establish Prong Moss Switch | City of Big Spring, Howard County | Cut the single circuit Rockhound Switch - Ranger Camp Switch 345kV Line into Prong Moss Switch. | 2025-07-15 | 12/15/2025 | [5 empty] | 0 | 345 | na | 0.95 | 2 - 1926.9 ACSS/TW Cumberland, 795 ACSR Drake | Steel 3 - Pole, Steel Pole | 150 | 0.20 | 150 | 0.75 | 25.101(c)(5)(A)
0PT55202 | Rivercrest Switch Bkr 2930 AND Swt 2932 - Hawk Hollow Switch BKkr 20920 and Bkr 20925 138kV : Replace (19) Poles, (16) Cross Arms & Insulators (Patrol Back Log) (BL24) | Lamar County and Red River County | Replacing Poles, Arms and Insulators on Rivercrest Switch - Hawk Hollow Switch 138 kV Line. | 2024-08-01 | 10/23/2024 | 10/23/2024 |  | 322095.16 |  |  | 100 | 138 | na | 11.78 | 636 ACSR Grosbeak | Wood H-Frame | 100 | 11.78 | na | na | 25.101(c)(3)
0PT55222 | Temple Switch - Bell County East Switch 345 kV Line | City of Temple, Bell County | Replace damaged lattice towers with new 8000 series lattice towers due to a storm. | 2024-05-22 | 2024-07-01 | 2024-07-01 |  | 29815649.96 |  |  | 100 | 345 | na | na | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 125 | 5.9 | na | na | 25.101(c)(3)
0PT55226 | Sandow Switch - Temple Switch 138 kV Line : Emergency Storm Restoration | City of Temple, Bell County | Replace damaged conductor and damaged davit arms on the Sandow Switch - Temple Switch 138 kV Line due to storm damage | 2024-05-23 | 11/11/2024 | 11/11/2024 |  | 960110.15 |  |  | 100 | 138 | na | 0.10 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0.10 | na | na | 25.101(c)(3)
0PT55236 | Temple Switch - Marak Switch 69 kV Line : Storm Restoration | City of Stringtown, Bell County | Replace Structures on the Temple Switch - Minerva Switch 69 kV Line due to storm damage. | 2024-05-23 | 2024-05-29 | 2024-05-29 |  | 2166226.86 |  |  | 100 | 69 | na | 2.00 | 4/0 ACSR Penguin | Wood H-Frame | 50 | 2.00 | na | na | 25.101(c)(3)
0PT55246 | Hilltop Switch - Weatherford West Switch 69 kV Line : Replace Deficiencies on multiple structures (#BL24) | Palo Pinto County, Parker County, Tarrant County | Replacing Poles, Arms and Insulators on Hilltop Switch - Weatherford West Switch 69 kV Line. | 2024-07-30 | 10/29/2024 | 10/29/2024 |  | 307472.73 |  |  | 100 | 69 | na | 6.08 | 4/0 ACSR Penguin | Wood H-Frame | Varies | 6.08 | na | na | 25.101(c)(3)
0PT55263 | Tri Corner - Elkton 345kV Line: Storm Restoration | Kaufman County | Replace structures on Tri Corner - Elkton 345kV Line due to storm damage | 2024-06-03 | 2024-07-01 | 2024-07-01 |  | 2581920.37 |  |  | 100 | 345 | na | 1.00 | 795 ACSR Drake | Steel Lattice Tower | 170 | 0.50 | na | na | 25.101(c)(3)
0PT55367 | Stryker Creek Switch - Tyler Grande Sub 138 kV Line : Storm Restoration | City of Jacksonville, Cherokee County | Replace 4 insulators impacted on the Stryker Creek Switch - Tyler Grande Sub 138 kV Line due to storm damage | 2024-06-04 | 2024-06-05 | 2024-06-05 |  | 302602 |  |  | 100 | 138 | na | 0.40 | 1233.6 ACSS/TW Yukon | Concrete Pole | 100 | 0.40 | na | na | 25.101(c)(3)
0PT55423 | Tyler Grande Switch - Overton Sub 138 kV Line : Replaces Poles, Arms and Insulators (BL24) | Smith County | Replacing Poles, Arms and Insulators on Tyler Grande Switch - Overton Sub 138 kV Line. | 2024-08-01 | 10/20/2024 | 10/20/2024 |  | 408253 |  |  | 100 | 138 | na | 16.23 | 4/0 ACSR Penguin | Wood H-Frame | Varies | 16.23 | na | na | 25.101(c)(3)
0PT55646 (R6361) | Richland Chambers Switch - Trinidad Switch 345-kV Line: Retermination at Richland Chambers Switch | City of Fairfield, Freestone County | Re-terminate the east circuit of the Richland Chambers Switch to Trinidad Switch 345 kV Line to accommodate the establishment of a new 345 kV line between Richland Chambers Switch and Calpine. | 2025-04-04 | 10/30/2025 |  |  | 7277190 |  |  | 0 | 345 | na | 0.60 | 2 - 1926.9 ACSR/TW Cumberland, 2 - 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | 170 | 0.30 | Varies | 0.30 | 25.101(c)(5)(A)
0PT44286 (M5261) | Eagle Mountain Switch - Hicks Switch 138 kV Line : Re-termination at Base Camp Switch (North) | City of Eagle Mountain, Tarrant County | Retermination of Eagle Mountain Switch - Hicks Switch 138 kV Line at Base Camp Switch | 2025-04-28 | 2025-12-15 |  |  | 1134208 |  |  | 0 | 138 | na | 0.16 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | 50 | .16 | na | na | 25.101(c)(5)(A)
0PT44287 (M5261) | Eagle Mountain Switch - Deen Switch 138 kV Line : Base Camp Switch Retermination | City of Eagle Mountain, Tarrant County | Retermination of Eagle Mountain Switch - Deen Switch 138 kV Line at Base Camp Switch | 2025-04-28 | 2025-12-15 |  |  | 1874417 |  |  | 0 | 138 | na | 0.30 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | 100 | .15 | na | na | 25.101(c)(5)(A)
0PT53430 (R6307) | Redland Switch - Huntington Switch 138 kV Line : Cut-in Rocky Springs Road Substation | City of Lufkin, Angelina County | Cut in the Rocky Springs 138 kV Substation to the Redland Switch - Huntington 138 kV Line. | 2025-09-15 | 2025-12-15 | [5 empty] | 0 | 138 | na | 0.35 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.35 | na | na | 25.101(c)(5)(A)
0PT53628 0PT56528 0PT56529 0PT55774 (R8704) | Crane - Odessa North 69 kV Line: Rebuild to 138 kV from Apple Sub to Reiter Switch | City of Odessa, Ector County | Rebuild the Crane - Odessa North 69 kV line from Apple to Reiter and convert to 138 kV. | 2025-05-05 | 2025-12-15 | [5 empty] | 0 | 69 | 138 | 13.5 | 1926.9 ACSR/TW Cumberland, 1926.9 ACSS/TW Cumberland | Steel 3 – Pole Switch, Steel Pole | 50 | 13.29 | 50 | .21 | 25.101(c)(5)(B)
0PT54292 0PT56243 (M3508) | Old Lake Switch - Ringgold Magnolia 69 kV Line Rebuild | City of Ringgold, Clay County and Montague County | Rebuild the Old Lake Switch - Ringgold Magnolia 69 kV Line to 138 kV standards. | 2025-06-02 | 2025-12-15 | [5 empty] | 0 | 69 | na | 13.00 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | Centerline | 13.00 | na | na | 25.101(c)(5)(B)
0PT45153 (M5261) | Eagle Mountain Switch - Bennett Road Switch 138 kV Line : Base Camp Switch Retermination | City of Eagle Mountain, Tarrant County | Retermination of Eagle Mountain Switch - Bennett Road Switch 138 kV Line at Base Camp Switch | 2025-04-28 | 2025-12-15 |  |  | 1326553 |  |  | 0 | 138 | na | 0.17 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | 50 | .17 | na | na | 25.101(c)(5)(A)
0PT54439 | Krum West Switch - Riley Switch 345 kV Line : Replace Failed OPGW from Str. 141/3 to Krum West Switch | City of Krum, County of Wise | Replace OPGW from str. 141/3 to Krum West Switch due to failed OPGW fiber | 2024-09-25 | 2024-12-27 | 2024-12-27 |  | 3115889.92 |  |  | 100 | 345 | na | 23.00 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 150 | 23.00 | na | na | 25.101(c)(3)
0PT55789 | Deen Switch - Roanoke Switch 138 kV Line : Foundation remediation | City of North Richland Hills, Tarrant County | Restore damaged and eroded foundations 1/2, 1/3, 1/5, 1/7, and 1/9 on the Deen Switch - Roanoke Switch 138 kV Line. | 2025-04-15 | 2025-05-31 | [5 empty] | 0 | 138 | na | 3.58 | 336.4 ACSR Merlin | Steel Pole | 1.79 | 65 | na | na | 25.101(c)(5)(B) | The project has been determined to no longer meet the reporting requirements, and it will be removed from next month's report.
0PT46947 (R8721) | Range Rider Switch - Morgan Creek Gen Switch 138 kV Line | Colorado City, Mitchell County | Reconfigure the existing line from the new Range Rider Sw to Morgan Creek Gen Sw | 2025-09-01 | 2025-12-15 | [5 empty] | 0 | 138 | na | 0.40 | 1926.9 ACSR/TW Cumberland | Steel Pole | 100 | Station Property | na | na | 25.101(c)(5)(B)
0PT55416 | Shamburger Switch - Black Fork Switch 138 kV Line : Replace poles, crossarms and insulators | Smith County | Replacing poles, crossarms and insulators on the Shamburger Switch - Black Fork Switch 138 kV line. | 2024-07-11 | 2024-11-13 | 2024-11-13 |  | 593317.67 |  |  | 100 | 138 | na | 17.02 | 795 ACSR Drake | Wood H-Frame, Wood Pole | 100 | 17.02 | na | na | 25.101(c)(3)
0PT55277 | Handley 138 Switch - Everman Switch 138 kV Line : Replace multiple structures | City of Fort Worth, Kennedale and Arlington, Tarrant County | Replace multiple structures on Handley 138 Switch - Everman Switch 138 kV Line. | 2024-07-30 | 2024-11-11 | 2024-11-11 |  | 325207.81 |  |  | 100 | 138 | na | 7.15 | 336.4 ACSR Linnett | Wood H-Frame, Wood Multi-pole | Varies | 7.15 | na | na | 25.101(c)(3)
0PT55467 | Tyler Switch - Canton Switch 138 kV Line : Replacing poles and insulators | Van Zandt County | Replacing poles and insulators on the Tyler Switch - Canton Switch 138 kV line. | 2024-07-16 | 2024-11-20 | 2024-11-20 |  | 321287.36 |  |  | 100 | 138 | na | 30.08 | 636 ACSR Grosbeak | Wood H-Frame | 100 | 30.08 | na | na | 25.101(c)(3)
0PT54210 | Jewett-Riesel 138kV Line: Replacing poles, crossarm and insulators | Limestone County, Leon County | Replacing Poles, Cross Arm, and Insulators on Jewett-Riesel 138 kV Line. | 2024-07-12 | 2024-11-22 | 2024-11-22 |  | 488691.97 |  |  | 100 | 138 | na | 23.67 | 795 ACSR Drake | Wood H-Frame | Varies | 23.67 | na | na | 25.101(c)(3)
0PT54016 | Stryker Creek Switch - Elkton Switch 138 kV Line : Replace Poles, Arms, and Insulators (BL24) | Cherokee County, Smith County | Replace Poles, Arms, and Insulators on Stryker Creek Switch - Elkton Switch 138 kV Line. | 2024-07-02 | 2024-11-20 | 2024-11-20 |  | 253787.85 |  |  | 100 | 138 | na | 14.54 | 336.4 ACSR Linnett | Wood H-Frame | 100 | 14.54 | na | na | 25.101(c)(3)
0PT56863 | Kemp Ranch Switch - Sardis Switch 138 kV Line : Replace insulators on structures | Ellis County | Replace Insulators on structures on the Kemp Ranch Switch - Sardis Switch 138 kV line. | 2025-07-01 | 2025-12-01 | [5 empty] | 0 | 138 | na | 5.68 | 959.6 ACSS/TW Suwannee | Steel H-Frame | Varies | 3.12 | na | na | 25.101(c)(5)(B)
0PT46400 (M5148) | Hicks Switch - Willow Creek Switch 345 kV Line : Cut-In to Est Dunham Switch | City of Rhome, Wise County | Cut-in the Hicks Switch – Willow Creek Switch 345 kV Line to establish the new Ramhorn Hill Switch. | 2025-07-07 | 12/15/2025 | [5 empty] | 0 | 345 | na | 2.00 | 2 - 1926.9 ACSS/TW Cumberland | Steel 2 - Pole, Steel Pole | 100 | na | 100 | 1.00 | 25.101(c)(5)(A)
0PT46401 (M5148) | Eagle Mountain Switch - Bennett Road Switch 138 kV Line : Cut-In to Est Dunham Switch | City of Rhome, Wise County | Cut-in the Eagle Mountain Switch – Bennett Road Switch 138 kV Line to establish the new Ramhorn Hill Switch. | 2025-07-07 | 12/15/2025 | [5 empty] | 0 | 138 | na | 0.40 | 1926.9 ACSS/TW/E3X Cumberland | Steel 3 - Pole, Steel H-Frame, Steel Pole | 100 | na | 70 | 0.40 | 25.101(c)(5)(A)
0PT46603 (M3006) | Oran Sub - Chico West Tap Switch 69 kV Line : Voltage Conversion to 138kV | City of Jacksboro, Jack County | Rebuild a section of the Oran Sub - Chico West Tap Switch 69 kV line. | 2025-07-16 | 2025-10-01 | [5 empty] | 0 | 69 | 138 | 4.28 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | Varies | 4.28 | na | na | 25.101(c)(5)(B)
0PT46889 (M4137) | Oates (GP&L) - Mesquite North 138 kV Line: Rebuild | City of Garland, Dallas County | Upgrade a section of the Oates (GP&L) - Mesquite North Tap 138 kV Line. | 2025-08-18 | 12/15/2025 | [5 empty] | 0 | 138 | na | 2.68 | 1926.9 ACSR/TW Cumberland | Steel Pole | Centerline | 2.68 | na | na | 25.101(c)(5)(B)
0PT48005 0PT49196 (M3006) | Chico West Tap Switch - Oran Switch 69-kV Line: Rebuild Jacksboro Tap - Jacksboro Sinclair to 138kV | City of Jacksboro, Jack County | Rebuild the Jacksboro Tap - Jacksboro Sinclair section of the Chico West Tap Switch - Oran Switch 69-kV single circuit line to 138 kV with conductor rated for 1,649 Amps or greater. | 2025-07-16 | 10/01/2025 | [5 empty] | 0 | 69 | 138 | 2.67 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | 100 | 2.67 | na | na | 25.101(c)(5)(B)
0PT50475 | Krum West Switch - Riley Switch 345 kV Line : Foundation remediation | City of Ringgold, Clay County | Restore damaged and eroded foundations on the Krum West Switch - Riley Switch 345 kV Line. | 2025-06-01 | 12/31/2025 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.101(c)(5)(B)
0PT51481 (R6251) | Cleburne Switch - Hillsboro Sub 138 kV Line : Cut-in to Establish Woodbury Switch | Hill County | Establish Woodbury switch by cutting in the Cleburne Switch - Hillsboro Sub 138 kV line. | 2025-08-04 | 12/04/2025 | [5 empty] | 0 | 138 | na | 0.25 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole, Wood H-Frame | Varies | na | na | na | 25.101(c)(5)(A)
0PT52872 0PT57509 (R6243) | Sandow - Austrop (LCRA) 345 kV Line: Establish Walleye Creek Switch | City of Thorndale, Milam County | Establish the new Walleye Creek Switch on the Sandow Sw - Austrop (LCRA) 345 kV Line. | 2025-08-25 | 12/15/2025 | [5 empty] | 0 | 345 | na | 4.03 | 2 - 1926.9 ACSS/TW Cumberland | Steel Pole | 170 | 1.28 | Varies | 1.76 | 25.101(c)(5)(A)
0PT53486 0PT56626 (R8704) | Salt Flat Sub - Reiter Switch 138 kV Line : New circuit Installation | City of Midland, Midland County | Add a second circuit to a section of the Salt Flat Road Sub - Barr Ranch - Reiter 138 kV Line. | 2025-08-15 | 12/15/2025 | [5 empty] | 0 | 138 | na | 3.10 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 3.10 | na | na | 25.101(c)(5)(C)
0PT53539 (R8730) | Benge Tap - Roundup POD 138 kV Line : Install POI Line to Customer | City of Midland, Midland County | Establish 2.8 mile 138 kV line from Benge Tap - Roundup POD. | 2025-08-01 | 12/15/2025 | [5 empty] | 0 | na | 138 | 2.80 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | na | na | 70 | 2.80 | 25.101(c)(5)(A)
0PT53631 (R8681) | Grady - Brown 138 kV Line: Rebuild Expanse to Brown | City of Stanton, Martin County | Rebuild of Expanse - Brown 138 kV line into a double circuit 138kV line from Expanse to Estacado. Reterminate Grady-Expanse 138kV line into new Expanse bay. | 2025-08-04 | 2026-05-15 | [5 empty] | 0 | 138 | na | 28.60 | 1926.9 ACSR/TW Cumberland | Steel Multi-pole, Steel Pole | Varies | na | na | na | 25.101(c)(5)(B)
0PT54224 0PT54403 (R8661) | SL Bulldog - Elbow 138 kV Line: Relocate at Prong Moss Switch | City of Big Spring, Howard County | Relocate the Bulldog - Elbow 138 kV line to accommodate the two 345kV Cut Ins into Prong Moss. The relocation will also accommodate the future cut-in of this line to Prong Moss Switch. | 2025-07-15 | 12/15/2025 | [5 empty] | 0 | 138 | na | 0.4 | 1926.9 ACSS/TW Cumberland | Steel 2 - Pole, Steel Pole | 90 | .37 | 90 | .03 | 25.101(c)(5)(A)
0PT54877 | Argyle - Krum Tap Switch 138 kV Line: Rebuild Argyle to 1/9 | City of Argyle, Denton County | Rebuild a section of the Argyle - Krum Tap Switch 138 kV Line from Argyle to structure 1/9 to meet required clearances. | 2025-08-04 | 12/31/2025 | [5 empty] | 0 | 138 | na | 1.00 | 1926.9 ACSS/TW Cumberland | Steel 2 - Pole, Steel Pole | 70 | 1.00 | na | na | 25.101(c)(5)(B)
0PT55489 (R8832) | Delaware River Switch - Riverton Switch 138 kV Line: Brushy Canyon POD | City of Orla, Reeves County | Install the 138 kV Brushy Canyon POD. | 2025-08-18 | 12/15/2025 | [5 empty] | 0 | 138 | na | 0.46 | 1926.9 ACSS/TW Cumberland, 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel H-Frame, Steel Pole | na | 0.23 | na | 0.23 | 25.101(c)(5)(A)
0PT55595 | Parkdale Switch - Haskell Avenue Switch 138 kV Line : Erosion mitigation | City of Dallas, Dallas County | Restore damaged and eroded foundation on Parkdale Switch - Haskell Avenue Switch 138 kV Line | 2025-06-16 | 2025-06-27 | [5 empty] | 0 | 138 | na | 1.65 | na | Steel Lattice Tower | Varies | 1.65 | na | na | 25.101(c)(5)(B)
0PT56180 | Big Spring Switch - Chalk Sub 69 kV Line : Reconfiguration of Big Spring Gulf Sub Connection | Howard County | Reconfigure Big Spring Switch - Chalk Sub 69 kV Line by removing connection to Big Spring Gulf Sub as the station is being demolished. | 2025-06-02 | 2025-12-31 | [5 empty] | 0 | 69 | na | 0.10 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.10 | na | na | 25.101(c)(5)(C)
0PT57432 | South Marlin Tap - Lott 69 Switch 69 kV Line : Replace Poles and Insulators | Falls County and Ellis County | Replacing poles and insulators on the South Marlin Tap - Lott 69 Switch 69 kV line. | 2025-09-01 | 2025-11-17 | [5 empty] | 0 | 69 | na | 10.95 | 4/0 ACSR Penguin | Wood Pole | Varies | 10.95 | na | na | 25.101(c)(5)(B)
0PT53697 | Stryker Creek Switch - Palestine South Sub 138 kV Line : Replacing deficient poles, crossarms, and insulator strings (2024) (BL24) | Cherokee County | Replacing poles, crossarms and insulator strings on the Stryker Creek Switch - Palestine South Sub 138 kV Line. | 2024-08-21 | 12/03/2024 | 12/03/2024 |  | 335290.72 |  |  | 100 | 138 | na | 25.01 | 795 ACSR Drake | Wood H-Frame | 100 | 25.01 | na | na | 25.101(c)(3)
0PT53865 | Jewett Switch - Wortham Gulf Pump 69 kV Line: Replace Poles, Crossarms, and Insulators ENERGIZED - CONTRACTOR (2024)(BL24) | Navarro County and Freestone County and Leon County | Replacing poles, crossarms and insulators on the Jewett Switch - Wortham Gulf Pump 69 kV Line. | 2024-06-18 | 12/19/2024 | 12/19/2024 |  | 419117.33 |  |  | 100 | 69 | na | 37.19 | 4/0 ACSR Penguin | Wood H-Frame | Varies | 37.19 | na | na | 25.101(c)(3)
0PT53999 | Athens Switch - Jacksonville Switch 69 kV Line : Replace Poles and Arms (BL24) | Henderson County and Anderson County and Cherokee County | Replacing poles and crossarms on the Athens Switch - Jacksonville Switch 69 kV line. | 2024-08-26 | 12/17/2024 | 12/17/2024 |  | 482666.03 |  |  | 100 | 69 | na | 43.82 | 4/0 ACSR Penguin | Wood H-Frame | Varies | 43.82 | na | na | 25.101(c)(3)
0PT54218 | Valley Switch - Commerce Switch 138 kV line : pole and crossarm replacement | Fannin County and Hunt County | Replacing poles and crossarms on the Valley Switch - Commerce Switch 138 kV line. | 2024-06-01 | 12/06/2024 | 12/06/2024 |  | 252736 |  |  | 100 | 138 | na | 26.19 | 795 ACSR Drake | Wood H-Frame | 100 | 26.19 | na | na | 25.101(c)(3)
0PT54714 | Breckenridge to Leon Switch 69 kV line : Replacing poles, crossarms and insulators | Stephens County, Eastland County | Replace structures on Breckenridge to Leon Switch 69 kV Line. | 2024-05-08 | 12/27/2024 | 12/27/2024 |  | 214646.92 |  |  | 100 | 69 | na | 7.02 | 2/0 CU | Wood Pole | Varies | 7.02 | na | na | 25.101(c)(3)
0PT55175 | Martin Springs - Sulphur Springs Switch 138 kV line : Replacing poles and crossarms | Red River County, Hopkins County, Franklin County | Replacing poles and crossarms on the Martin Springs - Sulphur Springs Switch 138 kV line. | 2024-08-01 | 12/10/2024 | 12/10/2024 |  | 370122 |  |  | 100 | 138 | na | 30.58 | 636 ACSR Grosbeak | Wood H-Frame | Varies | 30.58 | na | na | 25.101(c)(3)
0PT55214 | Hillsboro Switch - Alvarado Sub 69 kV line : Replacing poles, crossarms and insulators | Hill County and Ellis County | Replacing poles, crossarms and insulators on the Hillsboro Switch - Alvarado Sub 69 kV line. | 2024-06-10 | 12/31/2024 | 12/31/2024 |  | 234955.94 |  |  | 100 | 69 | na | 6.81 | 4/0 ACSR Penguin | Wood H-Frame | 100 | 6.81 | na | na | 25.101(c)(3)
0PT55233 | Argyle Switch - Highlands TNP Sub 138 kV line : Replace structure 15/4 | Denton County | Replacing structure 15/4 on the Argyle Switch - Highlands TNP Sub 138 kV line. | 2024-05-23 | 12/18/2024 | 12/18/2024 |  | 239084 |  |  | 100 | 138 | na | 7.37 | 336 ASCR Linnett | Wood H-Frame | 100 | 7.37 | na | na | 25.101(c)(3)
0PT55248 | Weatherford Switch - Springtown Sub 138 kV line : Replace poles, crossarms and insulators | Springtown, Parker County | Replace poles, crossarms and insulators on the Weatherford Switch - Springtown Sub 138 kV Line. | 2024-07-30 | 12/16/2024 | 12/16/2024 |  | 299708 |  |  | 100 | 138 | na | 5.61 | 336.4 ACSR/TW | Wood H-Frame | 100 | 5.61 | na | na | 25.101(c)(3)
0PT55252 | Gainesville-Whitesboro Jordan 138KV: Replace poles, crossarms and insulators | Cooke County and Grayson County | Replacing poles, crossarms and insulators on the Gainesville-Whitesboro Jordan 138 kV line. | 2024-06-10 | 12/20/2024 | 12/20/2024 |  | 238347.69 |  |  | 100 | 138 | na | 15.70 | 1233.6 ACSS/TW Yukon, 636 ACSR Grosbeak | Concrete Pole | 100 | 15.70 | na | na | 25.101(c)(3)
0PT55268 | Odessa EHV-Monahans-Wolf 138kV Line: Replace poles and crossarms | Ward County and Ector County | Replacing poles and crossarms on the Odessa EHV- Monahans - Wolf 138 kV line. | 2024-05-30 | 12/18/2024 | 12/18/2024 |  | 404434.95 |  |  | 100 | 138 | na | 39.06 | 795 ACSR Drake | Wood H-Frame | 75 | 39.06 | na | na | 25.101(c)(5)(B)
0PT55285 | Wolf Switch - General Tire Switch 138 kV Line: Replace poles, crossarms and insulators | Ward County, Winkler County, Ector County | Replacing poles, crossarms and insulators on the Wolf Switch - General Tire Switch 138 kV Line. | 2024-05-30 | 12/11/2024 | 12/11/2024 |  | 314132.29 |  |  | 100 | 138 | na | 36.91 | 636 ACSR Grosbeak | Wood H-Frame | 50 | 36.91 | na | na | 25.101(c)(3)
0PT55288 | Yucca Drive Switch - Turnbaugh Corner Switch 138kV Line: Replace poles, crossarms and insulators. | Ward County, Winkler County, Ector County | Replacing poles, crossarms and insulators on the Yucca Drive Switch - Turnbaugh Corner Switch 138 kV line. | 2024-05-30 | 12/18/2024 | 12/18/2024 |  | 571756.27 |  |  | 100 | 138 | na | 26.83 | 636 ACSR Grosbeak | Wood H-Frame, Wood Multi-pole | Varies | 26.83 | na | na | 25.101(c)(3)
0PT55462 | Huntington Sub - Etoile/Zavalla Pump 138kV Idle Line: Replace crossarms and poles | Angelina County | Replacing poles and crossarms on the Huntington Sub - Etoile/Zavalla Pump 138 kV line. | 2024-06-24 | 12/04/2024 | 12/04/2024 |  | 246446.86 |  |  | 100 | 138 | na | 18.14 | 336.4 ASCR Merlin | Wood H-Frame | 100 | 18.14 | na | na | 25.101(c)(3)
0PT55498 | Deleon Magnolia Tap - Olive Spring POD 69 kV Line: Replacing poles, crossarms, and insulators | Comanche County | Replacing poles, crossarms, and insulators on the Deleon Magnolia Tap - Olive Spring POD 69 kV line. | 2024-09-06 | 12/26/2024 | 12/26/2024 |  | 272418.56 |  |  | 100 | 69 | na | 3.31 | 2/0 CU | Wood Pole | 50 | 3.31 | na | na | 25.101(c)(3)
0PT55551 | Hutto Switch - Round Rock Northeast 138 kV line: Replacing poles, crossarms and insulators | Williamson County, Travis County | Replacing poles, crossarms and insulators on the Hutto Switch - Round Rock Northeast 138 kV line. | 2024-09-27 | 12/11/2024 | 12/11/2024 |  | 368078.52 |  |  | 100 | 138 | na | 5.16 | 795 ACSS Drake | Wood H-Frame | Varies | 5.16 | na | na | 25.101(c)(3)
0PT55553 | Jewett Switch - Palestine South Switch 138 kV Line : Replace poles, crossarms and insulators | Leon County and Anderson County and Cherokee County | Replacing poles, crossarms and insulators on the Jewett Switch - Palestine South Switch 138 kV line. | 2024-06-28 | 12/19/2024 | 12/19/2024 |  | 496847 |  |  | 100 | 138 | na | 40.58 | 795 ACSR Drake | Wood H-Frame | 100 | 40.58 | na | na | 25.101(c)(3)
0PT55567 | Salado Switch - Killeen Switch 345 kV Line : Install bird guards | Bell County | Installing bird guards on structures on the Salado Switch - Killeen Switch 345 kV line. | 2024-09-10 | 12/27/2024 | 12/27/2024 |  | 222481.19 |  |  | 100 | 345 | na | 30.52 | 795 ACSR Drake | Steel Lattice Tower | 170 | 15.26 | na | na | 25.101(c)(3)
0PT55569 | Leon Switch to Dublin 69kV Line: Replace poles. insulators and crossarms. | Comanche County and Eastland County | Replacing poles, insulators and crossarms on the Leon Switch to Dublin 69 kV line. | 2024-10-09 | 12/27/2024 | 12/27/2024 |  | 1405599.94 |  |  | 100 | 69 | na | 31.70 | 2/0 CU | Wood Pole | Varies | 31.70 | na | na | 25.101(c)(3)
0PT55570 | Temple Switch - Minerva Switch 69 kV Line : Replace poles, crossarms and insulators | Bell County and Milam County | Replacing poles, crossarms and insulators on the Temple Switch - Minerva Switch 69 kV line. | 2024-09-30 | 12/27/2024 | 12/27/2024 |  | 672604.74 |  |  | 100 | 69 | na | 32.98 | 4/0 ACSR Penguin | Wood H-Frame | Varies | 32.98 | na | na | 25.101(c)(3)
0PT55609 | Peppervine Switch - Temple Elm Creek Switch 138 kV Line : Replace poles, insulators and crossarms | Bell County and McLennan County | Replacing poles, insulators and crossarms on the Peppervine Switch - Temple Elm Creek Switch 138 kV line. | 2024-10-08 | 12/27/2024 | 12/27/2024 |  | 638728.23 |  |  | 100 | 138 | na | 17.64 | 795 ACSR Drake | Wood H-Frame | 70 | 17.64 | na | na | 25.101(c)(3)
0PT55642 | Bell County Switch - Gabriel Sub 138 kV Line : Replace poles and crossarms | Bell County and Williamson County | Replacing poles and crossarms on the Bell County Switch - Gabriel Sub 138 kV line. | 2024-08-26 | 12/18/2024 | 12/18/2024 |  | 299888.67 |  |  | 100 | 138 | na | 14.39 | 1926.9 ACSS/TW/E3X Cumberland | Wood H-Frame | Varies | 14.39 | na | na | 25.101(c)(3)
0PT56921 | Killeen Switch - Killeen Fort Hood Sub 138 kV Line : Replace poles, insulators and crossarms | City of Killeen, Bell County | Replacing poles, insulators and crossarms on the Killeen Switch - Killeen Fort Hood Sub 138 kV line. | 2024-12-04 | 12/09/2024 | 12/09/2024 |  | 714832 |  |  | 100 | 138 | na | 8.42 | 795 ACSR Drake | Wood H-Frame | Varies | 8.42 | na | na | 25.101(c)(3)
0PT56976 | Valley Switch - Stone Creek Switch 138 kV Line : Relocate STR 2/7, 2/8, and 2/9 | City of Sherman, Grayson County | Relocation of structures 2/7, 2/8, and 2/9 on the Valley Switch - Stone Creek Switch 138 kV Line | 2025-04-01 | 2025-05-15 | [5 empty] | 0 | 138 | na | 0.30 | 795 ACSR Drake | Wood H-Frame | 100 | 0.30 | na | na | 25.101(c)(5)(D) | The project has been determined to no longer meet the reporting requirements, and it will be removed from next month's report.
0PT55357 | Scurry - Lake Thomas 69kV line: Replace poles and crossarms | Scurry County | Replacing poles and crossarms on the Scurry - Lake Thomas 69 kV line. | 2024-07-22 | 2024-12-17 | 2024-12-17 |  | 206928.03 |  |  | 100 | 69 | na | 8.03 | 4/0 ACSR "Penguin" | Wood H Frame | 50 | 8.03 | na | na | 25.101(c)(3)
0PT50363 (M4353) | Carrollton Northwest - Cypress Waters Switch 138 kV Line: Double Circuit Line Cut-in | City of Dallas, Dallas County | Line Cut-in from Existing Carrollton Northwest - Northlake Switch 138 kV Line to the new Cypress Waters Switch | 2025-09-02 | 2026-05-15 | [5 empty] | 0 | 138 | na | .8 | 2 -959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0.40 | na | na | 25.101(c)(5)(A)
0PT48826 0PT54500 (M3001) | Graham Switch - Graham 69 kV Line: Rebuild | City of Graham, Young County | Rebuild the 2.6-miles of the Graham Switch - Graham 69 kV Line. | 2025-09-01 | 12/15/2025 | [5 empty] | 0 | 69 | na | 2.60 | 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel Pole | 50 | 2.60 | na | na | 25.101(c)(5)(B)
0PT50363 (M4353) | Carrollton Northwest - Cypress Waters Switch 138 kV Line: Double Circuit Line Cut-in | City of Dallas, Dallas County | Line Cut-in from Existing Carrollton Northwest - Northlake Switch 138 kV Line to the new Cypress Waters Switch | 2025-09-05 | 12/15/2025 | [5 empty] | 0 | 138 | na | 0.80 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0.40 | na | na | 25.101(c)(5)(A)
0PT50364 (M4353) | Cypress Waters Switch - Carrollton East Switch 138kV Line: Double Circuit Line Cut-in | City of Dallas, Dallas County | Line Cut-in from Existing Northlake Switch - Carrollton East Switch 138kV Line to the new Cypress Waters Switch | 2025-08-25 | 12/15/2025 | [5 empty] | 0 | 138 | na | 0.40 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0.20 | na | na | 25.101(c)(5)(A)
0PT50365 (M4353) | Cypress Waters Switch - Hackberry 138kV Line: Double Circuit Line Cut-in | City of Dallas, Dallas County | Line Cut-in from Existing Northlake Switch - Hackberry 138kV Line to the new Cypress Waters Switch | 2025-08-08 | 12/15/2025 | [5 empty] | 0 | 138 | na | 0.20 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0.20 | na | na | 25.101(c)(5)(A)
0PT50366 (M4353) | Cypress Waters Switch - Vineyard Switch 138kV Line: Double Circuit Line Cut-in | City of Dallas, Dallas County | Line Cut-in from Existing Hackberry - Vineyard Switch 138kV Line to the new Cypress Waters Switch | 2025-07-21 | 12/15/2025 | [5 empty] | 0 | 138 | na | 0.60 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0.60 | na | na | 25.101(c)(5)(A)
0PT50367 (M4353) | Cypress Waters Switch - Morrison Lane Switch 138kV Line: Double Circuit Line Cut-in | City of Dallas, Dallas County | Line Cut-in from Existing Northlake Switch - Morrison Lane Switch 138kV Line to the new Cypress Waters Switch | 2025-08-27 | 12/15/2025 | [5 empty] | 0 | 138 | na | 0.40 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0.20 | na | na | 25.101(c)(5)(A)
0PT51229 0PT56199 (R6326) | Hudson Sub: Line Work to Establish Sub | City of Lufkin, Angelina County | Line work associated with establishing Hudson Substation. This work is occurring on the Lufkin Switch - Lufkin South 138kV line. | 10/27/2025 | 12/15/2025 | [5 empty] | 0 | 138 | na | 0.40 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole, Wood H-Frame | 100 | 0.40 | na | na | 25.101(c)(5)(A)
0PT51241 | Oran Switch - RW Miller - Mineral Wells Sub 138 kV Line : Refurbishment | City of Mineral Wells, Palo Pinto County | Replacing wooden h-frames on the Oran Switch - RW Miller - Mineral Wells Sub 138 kV Line to improve clearances. | 2025-09-15 | 12/31/2025 | [5 empty] | 0 | 138 | na | 25.10 | 336.4 ACSR Linnett | Wood H-Frame | Varies | 25.10 | na | na | 25.101(c)(5)(E)
0PT51297 (M5340) | Handley Switch - Sherry Switch 138 kV Line : Arlington Sub Cut In | City of Arlington, Tarrant County | Cut in the South Circuit for the Handley Switch - Sherry Switch 138 kV Line to establish the new Arlington sub. | 2025-09-08 | 2026-05-15 | [5 empty] | 0 | 138 | na | 0.10 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 0.10 | na | na | 25.101(c)(5)(A)
0PT51375 (M4353) | Cypress Waters Switch - Elm Fork Tap 138kV Line: Single Circuit Line Cut-in | City of Dallas, Dallas County | Line Cut-in from Existing Northlake Switch - Elm Fork Tap 138kV Line to the new Cypress Waters Switch | 2025-08-29 | 12/15/2025 | [6 empty] | 138 | na | 0.40 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 0.20 | na | na | 25.101(c)(5)(A)
0PT51415 (M5340) | Handley Switch - Sherry Switch 138 kV Line : Arlington Sub Cut In (North) | City of Arlington, Tarrant County | Cut in the North Circuit for the Handley Switch - Sherry Switch 138 kV Line to establish the new Arlington sub. | 2025-09-08 | 05/15/2026 | [5 empty] | 0 | 138 | na | 0.10 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 0.10 | na | na | 25.101(c)(5)(A)
0PT52713 (R6094) | Elkton - Forest Grove Switch 138kV: Reterminate at Foggle Switch | City of Athens, Henderson County | Terminate the Elkton-Forest Grove 138kV Line into Foggle Switch | 2025-09-15 | 12/15/2025 | [6 empty] | 138 | na | 1.30 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | 1.20 | na | 0.10 | 25.101(c)(5)(A)
0PT52714 (R6094) | Athens - Tyler Switch 69kV: Rebuild Str 29/2 to Athens Sub to 138kV | City of Athens, Henderson County | Rebuild a segment of the Tyler Switch to Athens 69 kV Line to 138 kV operation. | 2025-09-15 | 12/15/2025 | [6 empty] | 69 | 138 | 1.20 | 959.6 ACSS/TW Suwannee | Steel Pole | Varies | na | na | na | 25.101(c)(5)(B)
0PT52868 0PT54978 (R3025) | Falcon Seaboard Loop 345 kV Line: Establish Prong Moss Switch | City of Big Spring, Howard County | Reterminate the 2 circuits going north to Falcon Seaboard Switch from structure 30/2 into the new Prong Moss Switch. | 2025-07-21 | 12/15/2025 | [6 empty] | 345 | na | 1.1 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower, Steel Pole | 150 | .1 | 150 | 0.45 | 25.101(c)(5)(A)
0PT52869 (R6243) | Brushy Creek Sw - Sandow Sw 138 kV Line: Establish Walleye Creek Switch | City of Thorndale, Milam County | Establish the new Walleye Creek Switch on the Brushy Creek Sw - Sandow Sw 138 kV Line. | 2025-09-01 | 12/15/2025 | [6 empty] | 138 | na | 2.57 | 2 - 959.6 ACSS/TW Suwannee, 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | 100 | 2.31 | 70 | 0.26 | 25.101(c)(5)(A)
0PT53059 0PT53695 (M4002) | Montfort Switch - Shankle Switch 138 kV Line: Rebuild Ennis Pump Tap - Shankle | City of Ennis, Navarro County | Rebuild the 4.2-mile Ennis Pump Tap - Shankle Switch section of the Montfort Switch - Shankle Switch 138 kV Line with double circuit capable steel poles. | 2025-09-16 | 12/15/2025 | [6 empty] | 138 | na | 4.20 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 4.20 | na | na | 25.101(c)(5)(B)
0PT53431 (R6063) | Palestine South Switch - Blackburn Switch 138 kV Line : Cut-in Palestine North Substation | City of Palestine, Anderson County | Connect the Palestine North 138 kV Substation at structure 1/1 on the the Palestine South - Blackburn Switch 138 kV Line. | 2025-09-15 | 12/15/2025 | [6 empty] | 138 | na | 0.20 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 0.20 | na | na | 25.101(c)(5)(A)
0PT53433 (R6325) | Waco North Switch - Waco Northwest Switch - Waco Northeast Switch: Reterminate Waco North Substation | City of Waco, McLennan County | Work entails the retermination of the Peppervine Switch - Waco East - Elm Mott 138 kV Line into its new location at the newly rebuilt Waco North Substation. | 2025-09-15 | 12/15/2025 | [6 empty] | 138 | na | 0.10 | 1926.9 ACSS/TW Cumberland | Steel Pole | Station Property | 0.10 | na | na | 25.101(c)(5)(A)
0PT53446 0PT55097 (M3510) | Line Work Associated with Establishing Possum Kingdom Sub (fka Ivan Sub) | City of Breckenridge, Stephens County | Cut in the Graham Plant Switch - Breckenridge Tap 138 kV Line into the new Possum Kingdom Substation. | 2025-09-01 | 12/31/2025 | [6 empty] | 138 | na | 0.10 | 1926.9 ACSS/TW Cumberland | Steel Pole | 50 | 0.10 | na | na | 25.101(c)(5)(A)
0PT53448 (R8890) | Graham Plant Switch - Tonkawa Switch 345 kV Line: Cut-in to Establish Dusty Road Switch | City of Stamford, Haskell County | Cut in the Graham Plant Switch - Tonkawa Switch 345 kV Line to establish the new Dusty Road Switch. | 10/20/2025 | 12/04/2025 | [6 empty] | 345 | na | 0.10 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 150 | 0.10 | na | na | 25.101(c)(5)(A)
0PT53494 (R8730) | Salt Flat Road Sub - Barr Ranch Switch 138 kV Double-Circuit Line : Establish Benge Tap | City of Midland, Midland County | Establish Benge Tap on the Salt Flat Road Sub - Barr Ranch Switch 138 kV Double-Circuit Line | 2025-09-16 | 12/15/2025 | [6 empty] | 138 | na | 0.45 | 1926.9 ACSS/TW Cumberland, 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel H-Frame, Steel Pole | 70 | 0.22 | Varies | 0.21 | 25.101(c)(5)(A)
0PT53622 (R6311) | Tyler Switch - Canton Switch 138 kV Line : Cut-In to Establish Rhine Lake Substation | Van Zandt County | Cut-in the Tyler Switch - Canton Switch 138 kV Line to establish the new Rhine Lake Substation | 2025-09-15 | 12/15/2025 | [6 empty] | 138 | na | 0.70 | 1926.9 ACSR/TW Cumberland | Steel Pole | 100 | na | na | na | 25.101(c)(5)(A)
0PT53623 (R6312) | Shamburger Switch - Black Fork Switch 138 kV Line : Reterminate Lindale Substation | City of Lindale, Smith County | Cut into Shamburger Switch - Black Fork Switch 138 kV Line to reterminate Lindale Substation | 2025-09-15 | 12/15/2025 | [6 empty] | 138 | na | 0.30 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | .30 | na | na | 25.101(c)(5)(B)
0PT53653 (R6269) | Leon Switch - Flat Creek 138kV Line: Establish Tudor Substation | The City of Desdemona, Eastland County | Cut-in to establish Tudor Sub | 2025-09-15 | 12/15/2025 | [6 empty] | 138 | na | 0.60 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | na | na | na | 25.101(c)(5)(A)
0PT53656 (R6313) | Eustace Southeast Switch - Canton Switch 138 kV Line : Cut-In Mabank 138kV Substation | City of Mabank, Henderson County | Cut-In to re-terminate Mabank Sub. Replace two structures and add two structures. | 2025-09-15 | 12/15/2025 | [6 empty] | 138 | na | 0.40 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.40 | na | na | 25.101(c)(5)(A)
0PT53658 (R6297) | Sandow Switch - Temple Switch 138 kV Line : Cut-In Shallion Sub | Bell County | Cut into the Sandow Switch - Temple Switch 138 kV Line to establish Shallion Sub. | 2025-09-15 | 12/15/2025 | [6 empty] | 138 | na | 1.20 | 1926.9 ACSS/TW Cumberland | Steel 3 - Pole, Steel Pole | Station Property | 1.00 | 75 | 0.20 | 25.101(c)(5)(A)
0PT53663 (M3239) | Stone Creek Switch - Payne Sub 138 kV Line : Reterminate Payne Sub | City of Sherman, Grayson County | Reterminate the Stone Creek Switch - Payne Sub at Payne Sub. | 2025-09-15 | 12/15/2025 | [6 empty] | 138 | na | 0.10 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 0.10 | na | na | 25.101(c)(5)(A)
0PT53666 (R6300) | Temple Switch - Belton Switch 138 kV Line : Reterminate Belton Substation | City of Belton, Bell County | Cut in Temple Switch - Belton Switch 138 kV Line to establish Harden Sub. | 2025-10-06 | 12/15/2025 | [6 empty] | 138 | na | 0.10 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 0.10 | na | na | 25.101(c)(5)(A)
0PT53736 (M4371) | Watermill - Lavender - Wilmer 138 kV Line: Rebuild | City of Lancaster, Dallas County | Rebuild the Watermill - Lavender - Wilmer 138 kV line. | 2025-09-16 | 12/31/2025 | [6 empty] | 138 | na | 4.18 | 2 - 959.6 ACSS/TW Suwannee | Steel H-Frame, Steel Pole | Varies | 3.85 | na | na | 25.101(c)(5)(B)
0PT53896 0PT53893 0PT56542 (R6197) | Temple - Temple Switch 69-kV Line: Reconfiguration to Temple – Minerva 69-kV Line | City of Temple, Bell County | Reconfiguration of the Temple - Temple Switch 69 kV Line into the Temple - McFall Switch 69 kV Line. | 2025-05-05 | 12/15/2025 | [5 empty] | 0 | 69 | na | 0.5 | 795 ACSR Drake | Wood Multi-pole | Varies | 0.5 | na | na | 25.101(c)(5)(A)
0PT53967 (R6063) | Palestine Switch - Creslenn Ranch Switch 138 kV Line : Cut-in Palestine North Substation | City of Palestine, Anderson County | Connect the Palestine North 138 kV Substation at structure 33/8 on the Creslenn Ranch - Palestine 69 kV Line. | 2025-09-15 | 12/15/2025 | [6 empty] | 69 | na | 0.20 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 0.20 | na | na | 25.101(c)(5)(A)
0PT53985 (R8629) | Odessa EHV SW – Monahans – Wolf SW: Cut-In to New Reiter Substation | Odessa, Midland | Cut-In Existing 138kV Odessa EHV SW – Monahans – Wolf SW – Single Circuit line into New Reiter Switch. | 2025-09-29 | 12/15/2025 | [6 empty] | 138 | na | 1.01 | 1926.9 ACSS/TW Cumberland | Steel Pole, Wood 2 - Pole | Varies | na | na | 1.01 | 25.101(c)(5)(A)
0PT54041 | Kemp Rach - Venus Switch - Cleburn Switch 138 kV Line | City of Cleburne, Glen Rose County | Cut-in the Kemp Ranch - Venus Switch - Cleburne Switch 138kV Line to establish the new Keene Substation | 2025-09-15 | 12/15/2025 | [6 empty] | 138 | na | 0.50 | 795 ACSR Drake | Steel Pole | 100 | 0.50 | na | na | 25.101(c)(5)(A)
0PT54043 (R6304) | Killeen Switch - Killeen Fort Hood 138 kV Line: Reterminate Killeen Substation | City of Killeen, Bell County | Re-termination for the rebuild of Killeen Substation. | 2025-04-29 | 12/15/2025 |  |  | 1315953 |  |  |  | 138 | na | 0.30 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.30 | na | na | 25.101(c)(5)(A)
0PT54045 | Richland Springs- Terry- San Saba Switch: Richland Springs Retermination | San Saba County | Reterminate existing Richland Springs- Terry- San Saba Switch Line at its new location inside Richland Springs Sub | 2025-09-15 | 12/15/2025 | [6 empty] | 69 | na | 0.10 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | na | na | na | 25.101(c)(5)(A)
0PT54206 (M3301) | Krum West Switch/Cedar Elm Switch - Anna Switch 345 kV Line: Cut In Gunter Switch | City of Gunter, Grayson County | Re-termination of Krum West Switch/Cedar Elm Switch - Anna Switch 345 kV Line at Gunter Switch | 2025-10-27 | 12/31/2025 | [6 empty] | 345 | na | 1.00 | 2 - 1926.9 ACSR/TW Cumberland | Steel Lattice Tower | 160 | 0.50 | na | na | 25.101(c)(5)(A)
0PT54221 (R6293) | Venus Switch - Sam Switch 345 kV Line : Rebuild Fort Smith Switch - Files Valley Switch Section | Hill County | Rebuild the Fort Smith Switch - Files Valley Switch 345kV section on the Venus Switch - Sam Switch 345kV Double-Circuit Line. | 2025-05-26 | 12/15/2025 | [6 empty] | 345 | na | 6.60 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 170 | 3.30 | na | na | 25.101(c)(5)(B)
0PT54333 (R8704) | SL Pronghorn Sub - Salt Flat Switch138 kV Line: Salt Flat Switch Retermination | City of Midland, Midland County | Reterminate the Pronghorn Sub - Salt Flat Sub 138 kV Line into its new deadend location at the newly built Wellbore Switch. | 2025-10-13 | 12/15/2025 | [6 empty] | na | na | 0.10 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 0.10 | na | na | 25.101(c)(5)(C)
0PT54335 (R8704) | SL Salt Flat Road - Skywest Sub 138 kV Line: Salt Flat Road Switch Retermination | City of Midland, Midland County | Reterminate the Skywest - Salt Flat Sub 138 kV Line into its new deadend location at the newly built Wellbore Switch. | 2025-09-29 | 12/15/2025 | [6 empty] | na | na | 0.40 | 1926.9 ACSS/TW Cumberland | Steel Pole | 70 | 0.4 | na | na | 25.101(c)(5)(C)
0PT54426 | Plano West Switch - Renner Switch 138 kV Line : Install OPGW | City of Plano and Richardson | Install OPGW from structure S2 at Plano West to structure S3 at Renner Switch to have fiber path. | 2025-10-31 | 12/31/2025 | [6 empty] | 138 | na | 16.40 | 1033.5 ACSR Curlew | Steel Lattice Tower | Varies | 8.20 | na | na | 25.101(c)(5)(A)
0PT54501 | Bryan Sub - East Network Sub 138 kV Line : Replace U.G. Terminations | City of Dallas, Dallas County | Replace (6) six 138 kV Underground Transmission Terminations along the Bryan Sub - East Network Sub 138 kV Line. | 2025-09-15 | 12/31/2025 | [5 empty] | 0 | 138 | na | na | 1500 AL HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT54540 (m4010) | Anna Switch - Haggerty Switch 138 kV Line: Establish Squirrel Creek POI | City of Dallas, Grayson County | Provide a 138 kV point-of-interconnection (POI) for Rayburn Country Electric Cooperative LLC. on the Anna Switch - Haggerty Switch 138 kV Line. | 2025-09-02 | 12/15/2025 | [6 empty] | 138 | na | 0.40 | 2 - 959.6 ACSS/TW Suwannee, 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel H –Frame Switch, Steel Pole | 100 | 0.30 | 100 | 0.10 | 25.101(c)(5)(A)
0PT54592 (R8836) | Yucca Drive Switch - Turnbaugh Corner Switch 138 kV Line: POD | Odessa, Ector County | Establish Coalbed POD on the Yucca Drive Switch - Turnbaugh Corner Switch 138 kV Line. | 2025-08-01 | 12/15/2025 | [5 empty] | 0 | 138 | na | 0.27 | 1926.9 ACSS/TW Cumberland, 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel H-Frame, Steel Pole | 75 | 0.23 | Varies | 0.04 | 25.101(c)(5)(A)
0PT54620 | East Network Sub - Medill Sub 138 kV Line : Termination Replacement | City of Dallas, Dallas County | Replace 138 kV Underground Transmission Terminations at East Network Sub - Medill Sub. | 2025-09-15 | 12/15/2025 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.101(c)(5)(B)
0PT54623 | Railside Switch - Andrew County South Switch 138 kV Line : Foundation Remediation on 13 structures | Winkler County | Remediate 13 foundations on Railside Switch - Andrew County South Switch 138 kV Line. | 2025-04-28 | 06/13/2025 |  |  | 428444 |  |  | 0 | 138 | na | 18 | 1926.9 ACSR/TW Cumberland | Steel Pole | 50 | 18 | na | na | 25.101(c)(5)(B)
0PT54774 (R8629) | Odessa EHV SW - Olefin SW/Moss SW 138kV Line: Cut-In to New Reiter Switch | Odessa, Midland | Cut-In 138kV Odessa EHV SW - Moss SW line to New Reiter Substation | 2025-09-15 | 12/15/2025 | [6 empty] | 138 | na | 0.30 | 1926.9 ACSR/TW Cumberland | Steel Pole | Varies | na | na | na | 25.101(c)(5)(A)
0PT54836 | North Network Sub - Slocum Street Sub 138 kV Line : Pumping Plant Replacement | City of Dallas, Dallas County | Replace the existing Pressurization Plant at North Network Substation with a new Pressurization Plant. | 2025-10-15 | 12/15/2025 | [6 empty] | 138 | na | na | 3250 AL HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT54888 | Valley Switch - Stone Creek Switch 138 kV Line - Replace Str. 5/9 | City of Denison, Grayson County | Replace structure 5/9 on Valley Switch - Stone Creek Switch 138 kV Line. | 2025-10-31 | 12/31/2025 | [5 empty] | 0 | 138 | na | 0.50 | 336.4 ACSR Linnett | Steel Pole | 50 | 0.50 | na | na | 25.101(c)(5)(B)
0PT54967 | Navarro Mills Sub - Navarro Mills POI 69 kV Line : Re-build | City of Purdon, Navarro County | Re-build Navarro Mills Sub - Navarro Mills POI 69kV Line to re-connect Brazos line | 2025-09-15 | 09/26/2025 | [6 empty] | 69 | na | 0.10 | 4/0 ACSR Penguin | Steel 3 - Pole | 100 | na | 100 | 0.10 | 25.101(c)(5)(D)
0PT55046 | Watermill Switch - Cedar Hill Switch 345 kV Line: Structure 355 Corrosion Mitigation | City of Dallas, Dallas County | Replace Structure 355 on the Watermill Switch-Cedar Hill Switch 345kV double circuit line. | 2025-09-15 | 12/31/2025 | [6 empty] | 345 | na | na | 2 - 795 ACSR Drake, 2 - 959.6 ACSS/TW Suwannee | Steel Lattice Tower | 250 | na | na | na | 25.101(c)(5)(B)
0PT55063 (R6172) | McGregor Phillips Tap Switch - Waco West Switch 69 kV Line: Re-term at Peppervine Switch | City of McGregor, McLennan County | Retermination of McGregor Phillips Switch - Waco West Switch 69 kV Line at Peppervine Switch | 2025-10-15 | 12/15/2025 | [6 empty] | 69 | 138 | 0.50 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | na | na | na | 25.101(c)(5)(A)
0PT55482 (R6094) | Foggle Switch - Athens Sub 138 kV Line: Construct Tie Line | City of Athens, Henderson County | Build Tie Line to establish the Foggle Switch - Athens Sub 138 kV Line. | 2025-09-01 | 09/30/2025 | [6 empty] | na | 138 | 0.10 | 959.6 ACSS/TW Suwannee | na | Station Property | na | na | 0.10 | 25.101(c)(5)(C)
0PT55558 (M3239) | Valley Switch – Payne Sub 138 kV Line: Reterminate at Payne Sub | City of Sherman, Grayson County | Reterminate the Valley Switch - Payne Sub at Payne Sub. | 2025-10-27 | 12/15/2025 | [6 empty] | 138 | na | 0.20 | 1926.9 ACSS/TW Cumberland | Steel Pole | Varies | 0.20 | na | na | 25.101(c)(5)(A)
0PT55670 (M4426) | Watermill Switch - Cedar Hill Switch 138 kV Line : Reterminate Desoto Pleasant Run Sub | City of Desoto, Dallas County | Reterminate Watermill Switch - Cedar Hill Switch 138 kV to the newly rebuilt Desoto Pleasant Run Sub | 2025-09-01 | 12/15/2025 | [5 empty] | 0 | 138 | na | 0.30 | 2 - 959.6 ACSS/TW Suwannee | Steel Pole | 70 | 0.3 | na | na | 25.101(c)(5)(A)
0PT55686 | Cedar Crest Switch - Sargent Road Switch 138 kV Line: Replace structure 5S9ET964A | City of Dallas, Dallas County | Replace and relocate wood guyed structure 5S9ET964A on the Cedar Crest Switch - Sargent Road Switch 138 kV Line with a steel monopole. | 2025-10-06 | 12/31/2025 | [5 empty] | 0 | 138 | na | 0.2 | 336.4 ACSR Linnett | Steel Pole | na | na | 0.2 | 50 | 25.101(c)(5)(B)
0PT46757 | Sherry Switch - Fish Creek Switch 138 kV Line : Cut-in for Tyre Park Sub | City of Grand Prairie, Tarrant County | Cut into the Sherry Switch - Fish Creek Switch 138 kV Line to establish Tyre Park Sub | 2025-09-02 | 2026-05-15 | [5 empty] | 0 | 138 | na | 0.4 | 1926.9 ACSS/TW CUMBERLAND, 795 ACSR DRAKE | Steel Pole | 50 | 0.4 | na | na | 25.101(c)(5)(A)
0PT57277 | East Network Sub - Medill Terminal Sub 138 kV Line : Conduit System, Additions | City of Dallas, Dallas County | This project is to inject fluid tracer from PFT Tech on the East Network Sub - Medill Terminal 138 kV Line to reduce future emergency restoration times. | 2025-09-15 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | 1250 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT57278 | Polk Street Sub - Polk Terminal Sub 138 kV Line : Conduit System, Additions | City of Dallas, Dallas County | This project is to inject fluid tracer from PFT Tech on the Polk Street Sub - Polk Terminal Sub 138 kV Line to reduce future emergency restoration times. | 2025-09-15 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | 600 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT57280 | Polk Street Sub - Davis Street Sub 138 kV Line : Conduit System, Additions | City of Dallas, Dallas County | This project is to inject fluid tracer from PFT Tech on the Polk Street Sub - Polk Terminal Sub 138 kV Line to reduce future emergency restoration times. | 2025-09-15 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | 600 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT57281 | West Levee Switch - Topeka Terminal Sub 345 kV Line : Conduit System, Additions | City of Dallas, Dallas County | This project is to inject fluid tracer from PFT Tech on the West Levee Switch - Topeka Terminal Sub 345 kV Line to reduce future emergency restoration times. | 2025-09-15 | 2025-12-15 | [5 empty] | 0 | 345 | na | na | 3500 CU HPFF | na | na | na | na | na | 25.101(c)(5)(B)
0PT57518 | Calmont Sub - Hilltop Switch 69 kV Line : Relocate Structure 15/8 | Fort Worth, Tarrant County | Relocation of structure 15/7 and 15/8 on Calmont Sub - Hilltop Switch 69 kV Line. | 2025-05-01 | 2025-06-30 | [5 empty] | 0 | 69 | na | na | 4/0 ACSR Penguin | Wood H-Frame | na | na | na | na | 25.101(c)(5)(D)
0PT56519 | Stryker Creek Switch - Elkton Sub 138 kV Line : Relocation | City of Jacksonville, Cherokee County | Relocation with new double circuit, steel monopole, tangent and dead end structure on Stryker Creek Switch - Elkton Sub 138 kV Line | 2025-10-01 | 2025-12-15 | [5 empty] | 0 | 138 | na | 0.60 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | na | 100 | 0.60 | 25.101(c)(5)(D)
0PT56561 | Tri Corner Switch - Forney Switch 345 kV Line : Relocate Structure 24/4 | City of Dallas, Dallas County | Relocate structure 24/4 away from eroding creek bed. | 10/15/2025 | 12/31/2025 | [5 empty] | 0 | 345 | na | 1.00 | 795 ACSR Drake | Steel Lattice Tower | 250 | 0.50 | na | na | 25.101(c)(5)(B)
0PT56744 (M5013) | Burleson Switch - Cleburne Switch 138 kV Line: Install Cattle Creek POI | City of Burleson, Johnson County | Cut in Brazos Mountain Valley Sub on the Burleson Switch - Cleburne Switch 138 kV Line. | 2025-08-04 | 10/25/2025 | [5 empty] | 0 | 138 | na | 0.30 | 1926.9 ACSS/TW Cumberland, 959.6 ACSS/TW Suwannee | Steel 3 - Pole, Steel H-Frame, Steel Pole | Varies | 0.10 | Varies | na | 25.101(c)(5)(A)
0PT55245 | Bonham SW - Toco SW 69KV line: Replacing poles, crossarms and insulators | Fannin County and Lamar County | Replacing poles, crossarms and insulators on the Bonham SW - Toco SW 69 kV line. | 2024-06-10 | 2025-01-02 | 2025-01-02 |  | 522811.32 |  |  | 100 | 69 | na | 30.02 | 336.4 ASCR Linnett | Wood H Frame | Varies | 30.02 | na | na | 25.101(c)(3)
0PT50636 0PT56179 0PT56625 (M3233) | Stone Creek Switch - Valley Switch 138 kV Line : Station Cut in for Bells Sub Skid | City of Bells, Grayson County | Cut in the Stone Creek Switch - Valley Switch 138 kV Line into the Bells Sub to accommodate the expansion. | 2025-09-15 | 2025-12-15 | [5 empty] | 0 | 69/138 | na | 0.1 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.1 | na | na | 25.101(c)(5)(A)
0PT53657 0PT56732 | Rivercrest - Sulfur Springs - Monticello Switch 138 kV Line: Cut-In Jennings Lake Substation | City of Sulpher Springs, Hopkins County | Cut-In the Rivercrest - Sulfur Spring - Monticello Switch 138 kV Line at Jennings Lake Substation (fka Martin Springs Sub). | 2025-10-22 | 2025-12-15 | [5 empty] | 0 | 138 | na | 0.5 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.5 | na | na | 25.101(c)(5)(A)
0PT55504 (R8829) | Eskota Switch - Morgan Creek Switch 138 kV Line : Cut-In to Establish Stripe Substation | City of Roscoe, Nolan County | Cut in Eskota Switch - Morgan Creek Switch 138 kV line to cut-in Stripe Sub | 2025-10-27 | 2025-12-15 | [5 empty] | 0 | 138 | na | 0.40 | 1926.9 ACSS/TW Cumberland | Steel Pole | 75 | 0.4 | na | na | 25.101(c)(5)(A)
0PT54299 | China Grove Switch - Paint Switch 138 kV Line : Clearance Improvement | Mitchell County, Scurry County, Fisher County, Jones County, Haskell County, | Replace five (5) single circuit wood h-frames on the China Grove Switch - Paint Switch 138 kV Line to improve clearances. | 2025-09-15 | 2025-12-31 | [5 empty] | 0 | 138 | na | 1.00 | 636 ACSR Grosbeak | Wood H-Frame | 50 | 1.00 | na | na | 25.101(c)(5)(B)
0PT49601 | Jacksboro Switch - Burwick Switch 345 kV Line : Insulator Replacement | City of Jacksboro, Jack County | Replace polymer insulators on the Jacksboro Switch - Burwick Switch 345 kV line. | 2025-10-20 | 2025-12-15 | [5 empty] | 0 | 345 | na | 18 | 2 - 1590 ACSR FALCON | Steel Lattice Tower | 160 | 18 | na | na | 25.101(c)(5)(B)
0PT54205 | Stone Creek Switch - Collin Switch 138 kV Line: Cut In Gunter Switch | City of Gunter, Grayson County | Re-termination of Stone Creek Switch - Collin Switch 138 kV Line at Gunter Switch | 2025-10-27 | 2025-12-31 | [5 empty] | 0 | 138 | na | 0.3 | 1926.9 ACSS/TW Cumberland | Steel Pole | 100 | 0.3 | na | na | 25.101(c)(5)(A)
0PT56034 | Tonkawa Switch - Scurry County South Switch 345kV Line: Re-terminate at Tonkawa | City of Hermleigh, Scurry County | Re-terminate both circuits of the Tonkawa Switch to Scurry County South Switch 345kV line at the new terminals at Tonkawa Switch. | 2025-09-01 | 2025-12-15 | [5 empty] | 0 | 345 | na | 0.3 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 160 | 0.15 | na | na | 25.101(c)(5)(B)
0PT53483 | Dublin Switch - Brownwood Switch 69 kV Line: Establish Ireland 138kV Substation | City of Dublin, Erath County | Terminate line at Str 1/7, to establish Ireland 138 kV Substation | 2025-09-15 | 2025-12-31 | [5 empty] | 0 | 138 | na | 0.1 | #1 CU | Wood Pole | Varies | 0.1 | na | na | 25.101(c)(5)(A)
0PT56037 | Tonkawa Switch - Morgan Creek Switch 345kV Line: Re-terminate at Tonkawa | City of Hermleigh, Scurry County | Re-terminate the Tonkawa Switch to Morgan Creek Switch 345kV line into the new terminals within Tonkawa Switch. | 2025-09-15 | 2025-12-15 | [5 empty] | 0 | 345 | na | 0.10 | 2 - 1926.9 ACSS/TW Cumberland | Steel Lattice Tower | na | na | Varies | 0.10 | 25.101(c)(5)(B)
0PT53707 | Rivercrest Switch - Rivercrest Switch 138 kV Line : Clearance Improvement | Franklin County, Hopkins County | Replace three (3) single circuit wood h-frames on the Rivercrest Switch - Rivercrest Switch 138 kV Line to improve clearances. | 2025-10-31 | 2025-12-31 | [5 empty] | 0 | 138 | na | 1.5 | 636 ACSR Grosbeak | Wood H-Frame | 100 | 1.5 | na | na | 25.101(c)(5)(B)
0PT52024 | Yucca Drive Switch - Monahans Switch 138 kV Line : Clearance improvement | City of Monahans, Ward County | Replace structures on the Yucca Drive Switch - Monahans Switch 138 kV Line. | 2025-09-15 | 2025-12-31 | [5 empty] | 0 | 138 | na | 2.00 | 4/0 ACSR Penguin | Wood H-Frame | 50 | 2.00 | na | na | 25.101(c)(5)(B)
0PT48818 | Graham Switch - Paint Creek 138kV Line: Rebuild Brazos River Crossing | City of Graham, Young County | Rebuild structures 8/11 to 9/6 of the Graham Switch to Paint Creek 138kV line to harden the existing Brazos River crossing | 2025-10-14 | 2025-12-01 | [5 empty] | 0 | 138 | na | 0.60 | 959.6 ACSS/TW Suwannee | Steel Pole | 50 | 0.60 | na | na | 25.101(c)(5)(B)
0PT57189 | Knob Creek Switch - Salado Switch 345 kV Line : Line Damage | City of Belton, Bell County | Replace Steel lattice tower on the Knob Creek Switch - Salado Switch 345 kV Line due to damage | 2024-12-30 | 2025-02-01 | 2025-02-01 |  |  |  |  | 100 | 345 | na | na | 2 - 959.6 ACSS/TW Suwannee | Steel Lattice Tower | 250 | na | na | na | 25.101(c)(5)(B)
0PT54309 | Eskota Switch - Sweetwater Creek POI 69 kV Line : Clearance Improvement | City of Sweetwater, Nolan County | Replace structures on Eskota Switch - Sweetwater Creek POI 69 kV Line. | 2030-09-15 | 12/31/2025 | [5 empty] | 0 | 69 | na | na | 4/0 ACSR Penguin | Wood H-Frame, Wood Pole | 50 | 18.6 | na | na | 25.101(c)(5)(B)
0PT56115 | Leon Sw to Ranger Gulf 69kV Line: Replace poles, crossarms and insulators | Eastland County | Replacing poles, crossarms and insulators on the Leon SW to Ranger Gulf 69kV line. | 2024-12-16 | 2025-03-05 | 2025-03-05 |  | 280035.3 |  |  | 100 | 69 | na | 12.05 | 4/0 ASCR Penguin | Wood H Frame | Varies | 12.05 | na | na | 25.101(c)(3)
0PT55970 | Leon Switch to Breckenridge 69kV Line: Replace crossarms, poles, and insulators | Eastland County, Stephens County | Replacing poles, crossarms and insulators on the Leon Switch to Breckenridge 69 kV line. | 2024-12-01 | 2025-03-03 | 2025-03-03 |  | 488688.15 |  |  | 100 | 69 | na | 12.01 | #2 CU | Single Wood Pole | Varies | 12.01 | na | na | 25.101(c)(3)
0PT56609 | Comanche Sw to Mercers Gap to Brownwood Sw 138kV Line: Replace crossarms and insulators | Brown County, Comanche County | Replacing crossarms and insulators on the Comanche Sw to Mercers Gap to Brownwood Sw 138kV Line. | 2024-11-29 | 2025-03-03 | 2025-03-03 |  | 259424.38 |  |  | 100 | 138 | na | 26.7 | 795 ASCR Drake | Wood H Frame | 100 | 26.7 | na | na | 25.101(c)(3)
0PT56610 | Stephenville SW to Comanche SW 138kV Line: Replace poles, crossarms, and insulators | Brown County, Comanche County | Stephenville Sw to Comanche Sw 138kV Line: Replace poles, crossarms, and insulators on the Stephenville SW to Comanche SW 138kV Line. | 2024-11-15 | 2025-03-03 | 2025-03-03 |  | 248020.16 |  |  | 100 | 138 | na | 35.79 | 636 ACSR Grosbeak | Wood H Frame | 100 | 35.79 | na | na | 25.101(c)(3)
0PT58279 | Athens Switch - Jacksonville Switch 69 kV Line : Replace Poles and Arms, Insulators | Henderson County | Replacing poles, crossarms and insulators on the Athens Switch - Jacksonville Switch 69 kV line. | 2025-06-01 | 2025-08-31 | [5 empty] | 0 | 69 | na | 22.81 | 4/0 ASCR Penguin | Wood H Frame | Varies | 22.81 | na | na | 25.101(c)(5)(B)
0PT58075 | Shamburger Switch - Black Fork Switch 138 KV Line : Replace Pole and crossarms | Smith County | Replacing pole and crossarms on the Shamburger Switch - Black Fork Switch 138 KV line. | 2025-06-01 | 2025-09-30 | [5 empty] | 0 | 138 | na | 1.01 | 336 ASCR Linnett | Wood H Frame | Varies | 1.01 | na | na | 25.101(c)(5)(B)
Line Clearance Review Program (LCRP)
Projects Relating to HB 4150 (HB 4150) | TBD | TBD | TBD | TBD | TBD |  |  | TBD |  |  | 0 |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
0PT52198 (HB4150) | Graham Plant Switch - Cook Field Road Switch 345 kV Line: Clearance Improvement | Young and Shackelford Counties | Replace structures to improve clearance. | 2023-11-20 | 2023-12-27 | 2023-12-27 |  | 1418880.13 |  |  | 100 | 345 | na | 1 | 2 - 795 ACSR Drake | Steel Lattice Tower | 120 | 0.5 | na | na | 25.101(c)(5)(B)
0PT49760 (HB4150) | Big Brown Switch - Jewett Switch 345 kV Line : Clearance Improvement | City of Jewett, Leon County | Replace double circuit steel lattice structures on the Big Brown - Jewett 345 kV line with eight taller 345 kV double circuit steel lattice towers to improve clearances. | 2025-05-01 | 2025-05-15 | [5 empty] | 0 | 345 | na | 7.30 | 2 - 795 ACSR DRAKE | Steel Lattice Tower | 170 | 3.65 | na | na | 25.101(c)(5)(B)
0PT51237 | Oran Switch - RW Miller - Mineral Wells Sub 138 kV Line : Clearance Improvement | Palo Pinto County | Replacing wooden h-frames on the Oran Switch - RW Miller - Mineral Wells Sub 138 kV Line to improve clearances. | 2024-10-03 | 2024-12-11 | 2024-12-11 |  | 623457.23 |  |  | 100 | 138 | na | na | 336.4 ACSR Linnett | Wood H-Frame | na | na | na | na | 25.101(c)(5)(B)
0PT52594 | Rose Hill Switch - Kaufmann Northwest Switch 138 kV Line : Clearance Improvement | City of Forney, Kaufman County | Rebuilding the Terrell Switch - Rose Hill Switch 138 kV Line. | 2024-10-24 | 2024-11-08 | 2024-11-08 |  | 568769 |  |  | 100 | 138 | na | 0.40 | 795 ACSR Drake | Concrete H-Frame, Wood H-Frame | 100 | 0.40 | na | na | 25.101(c)(5)(B)
0PT50521 | Forest Grove Switch - Trinidad Switch 345 kV Line : Clearance Improvement | City of Athens, Henderson County | Replace structures on Forest Grove Switch - Trinidad Switch to improve line clearance. | 2025-04-09 | 2025-05-15 |  |  | 7052638 |  |  | 0 | 345 | na | .28 | 2 -1926.9 ACSS/TW Cumberland | Steel Lattice Tower | 160 | .28 | na | na | 25.101(c)(5)(B)
0PT50698 | Forest Grove Switch - Trinidad Switch 345 kV Line : Clearance Improvement | City of Athens, Henderson County | Replace structures to improve clearance. | 2025-08-15 | 2025-12-31 | [5 empty] | 0 | 345 | na | 0.28 | 2 - 1926.9 ACSR/TW Cumberland | Steel Lattice Tower | 160 | 0.28 | na | na | 25.101(c)(5)(B)
0PT50030 | Carrollton Northwest Switch - Collin Switch 345 kV Line : Clearance Improvement | City of Frisco, Collin County | Replace one (1) single circuit lattice tower with one (1) taller double circuit lattice tower on the Carrollton Northwest Switch - Collin Switch 345 kV Line. | 2025-10-17 | 2025-12-31 | [5 empty] | 0 | 345 | na | 0.2 | 795 ACSR Drake | Steel Lattice Tower | 170 | na | na | na | 25.101(c)(5)(B)
0PT50686 | Martin Lake Switch - Shamburger Switch 345 kV Line : Clearance Improvement | City of Tyler, Rusk County | Improve vertical clearance on the Martin Lake Switch - Shamburger Switch 345 kV Line. | 2025-10-01 | 2025-12-31 | [5 empty] | 0 | 345 | na | 3.00 | 2 - 1590 ACSR Falcon | Steel Lattice Tower | Varies | 3.00 | na | na | 25.101(c)(5)(B)
0PT51844 | Trinidad Switch - Eustace Southeast Switch 138 kV Line : Clearance Improvement | City of Malakoff, Henderson County | Replace four single circuit wooden H-Frames with four taller single circuit wooden H-Frames on the Trinidad Switch - Eustace Southeast Switch 138 kV Line improving clearances. | 2025-09-22 | 12/31/2025 | [6 empty] | 138 | na | 0.20 | 1033.5 ACSR Curlew | Wood H-Frame | 160 | 0.20 | na | na | 25.101(c)(5)(A)
STATION
0PT40876 0PT39914 | Triangle Sub : Install one Transformer on #2 | City of Stanton, Martin County | Install a second transformer and remove transformers #1 and #2 at Stanton Substation. Complete installation of fiber for line protection, modify 138 kV bus protection to provide redundancy. | 2022-01-31 | 2022-12-01 | 2022-12-01 |  | 3625120 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40615 (R8523) | Nelson Switch : Establish a 138 kV point of interconnection (POI) | City of Odessa, Ector County | Establish a 138 kV point of interconnection (POI) by installing one 138 kV, 3200 A circuit breaker in existing ring-bus. | 2020-09-18 | 2026-05-14 |  |  | 1240255 |  |  | 99 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41627 (R984) | Stouts Creek Switch : Establish Station for (POI) | Hopkins County | Establish station by installing three 345 kV, 3200 A circuit breakers in a 3-breaker ring bus arrangement for a (POI). Station will connect to the Allen Switch- Monticello Switch 345 kV line. | 2024-10-10 | 2025-05-08 |  |  | 9106188.51 |  |  | 88 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42794 0PT47090 | Plano Shiloh Road Sub : Install a third transformer at Plano Shiloh Rd and three breakers | City of Plano, Collin County | Install a third transformer at Plano Shiloh Rd and three breakers | 2021-03-30 | 2021-06-30 | 2021-06-30 |  | 6182250 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41447 (M5317) | Toco Switch: Add a single line terminal to establish POI | City of Toco, Lamar County | Add a single line terminal to the existing ring-bus for the POI. | 2025-02-22 | 2025-04-17 |  |  | 1434922.73 |  |  | 74 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41016 (M5222) | Duval Sub: Remove 69 kV station and establish 138-12.5 kV station | City of Fort Worth, Tarrant County | 69 kV station and establish 138-12.5 kV station | 2022-07-15 | 2022-12-21 | 2022-12-21 |  | 8309347 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41017 0PT41805 | Stuart (formerly Bryan Avenue) Substation: Convert Station from 69 kV to 138 kV operation by rebuilding a new substation to replace the existing station | City of Fort Worth, Tarrant County | Rebuild a new substation to replace the four existing transformers and switchgear feeder breakers with two transformers and eight new switchgear type feeder breakers. | 2021-04-12 | 2025-04-30 |  |  | 8238720 |  |  | 72 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | Station grading began prior to reporting on the MCPR. All construction work has ceased and will resume 45 days from the reporting date on June 28.
0PT41229 0PT39325 | Bell Mountain (formerly Hudson Oaks) Substation : Establish substation with one transformer and two feeder breakers | City of Hudson Oaks, Parker County | Establish substation with one transformer and two feeder breakers | 2022-10-17 | 2023-12-04 | 2023-12-04 |  | 6859188 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41015 (M5222) | Handley Switch: Remove 69 kV station, and add 138 kV terminal by using the existing autotransformer position | City of Fort Worth, Tarrant County | Remove all existing 69 kV equipment from the station and add 138 kV terminal by using the existing autotransformer position. | 2022-10-22 | 2025-05-15 |  |  | 2131413 |  |  | 79 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41741 (R3021) | Wallaby Switch : Install three 3200 A ,345 kV circuit breakers in a ring bus configuration | City of Dawn, Deaf Smith County | Establish switching station by installing three 3200 A, 345 kV circuit breakers in a ring bus configuration. | 2024-05-06 | 2024-12-20 | 2024-12-20 |  | 6839311.35 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44632 0PT45249 (R6152) | Will White POI : Establish 138 kV point-of-interconnection | City of Tool, Henderson County | Establish a 138 kV point -of-interconnection including the installation of three 138 kV 2000 A motor operated sectionalizing switches. | 2022-02-09 | 2023-06-27 | 2023-06-27 |  | 811168 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43642 (R3023) | Blackwater Draw Switch : Add rung with two 345 kV breakers | City of Abernathy, Hale County | Install two 3200 A, 345 kV circuit breakers as part of installing a 345 kV point-of-interconnection. | 2022-01-03 | 2024-06-28 | 2024-06-28 |  | 3838169 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44887 0PT50208 0PT39254 | Waco M&M Mars Sub : Install transformer #3 with 2 feeder breakers | City of Waco, McLennan County | Install transformer #3 with two feeder breakers | 2022-04-29 | 2024-06-01 | 2024-06-01 |  | 6227656 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45122 | Calmont Sub : Add transformer #8 with 3 feeders and rework 138 bus, and remove transformer #2 and #3 along with switchgear | City of Fort Worth, Tarrant County | Add transformer #8 with 3 feeders and rework 138 bus, and remove transformer #2 and #3 along with LV switchgear | 2022-06-24 | 2022-12-31 | 2022-12-31 |  | 5218758 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42132 (R3022) | Kress Switch : Establish station and install three 345 kV, 3200 A circuit breakers in a ring bus configuration | Swisher County | Establish station and install three 345 kV, 3200 A circuit breakers in a ring bus configuration | 2022-08-14 | 2023-05-31 | 2023-05-31 |  | 7986575 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42269 (R6160) | Revolution Switch: Rebuild 138 kV station in a 10-breaker 138 kV breaker-and-a-half arrangement | City of Navarro, Navarro County | Rebuild existing Navarro 138 kV station in a 10-breaker 138 kV breaker-and-a-half arrangement. | 2025-05-05 | 2025-12-04 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45227 (R6160) | Navarro Sub : Reconfigure 138 kV bus & relocate line terminals to Revolution Switch | City of Navarro, Navarro County | Reconfigure 138 kV bus & relocate line terminals to Revolution Switch. | 2025-10-01 | 2025-12-04 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44337 0PT46862 | Frow Sub: Establish substation with one transformer and two feeder breakers | City of Waco, McLennan County | Establish station with one transformer and two feeders | 2023-06-01 | 2024-06-27 | 2024-06-27 |  | 2992104 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45737 0PT46724 (R8604) | Crater Rock Switch : Establish three breaker ring POI station | Culberson County | Establish three breaker ring POI station. | 2022-08-07 | 2023-12-14 | 2023-12-14 |  | 6077188 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46414 0PT50443 | Rosedale Sub : Establish substation with two transformers | City of Fort Worth, Tarrant County | Establish substation with two transformers and six feeder breakers | 2022-12-29 | 2024-12-09 | 2024-12-09 |  | 6478207 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46725 (M5222) | Handley Switch : Remove transformers #1 and #2 with the removal of the associated switchgear | City of Fort Worth, Tarrant County | Remove transformers #1 and #2 with the removal of the associated switchgear. | 2024-10-16 | 2025-04-15 |  |  | 2105456 |  |  | 99* | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46093 | Graford Sub : Rebuild existing substation to rural substation skid | City of Graford, Palo Pinto County | Rebuild existing substation to rural substation skid | 2023-03-20 | 2024-06-03 | 2024-06-03 |  | 2989585 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46716 | Moorehead Sub : Install two transformers with two feeder breakers | City of Garland, Dallas County | Install two transformers with two feeder breakers | 2022-05-09 | 2022-12-20 | 2022-12-20 |  | 5136068 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44267 (R6140) | Rockdale Sub : Install transformer #2 with two feeders | City of Rockdale, Milam County | Install a second transformer with two feeders and add FID to the existing substation. | 2022-07-27 | 2022-12-29 | 2022-12-29 |  | 2743160 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44313 0PT44748 (R4022) | Short Grass Sub: Establish new substation | City of Archer, Archer County | Establish a new substation to replace the existing Archer City Sub. | 2022-08-01 | 2022-12-22 | 2022-12-22 |  | 3647282 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46333 0PT47029 (M3010) | Rose Hill Switch : Rebuild Rose Hill Sub Tap to 3-breaker ring | City of Kaufman, Kaufman County | Rebuild the existing 138 kV Rose Hill Tap into a three position 138 kV ring bus configuration. | 2022-07-05 | 2022-12-22 | 2022-12-22 |  | 4855264 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46875 0PT47739 (R8611) | Yantis Ranch POD : Establish 138 kV point of delivery | City of Wink, Winkler County | Establish 138 kV point of delivery. | 2022-11-14 | 2023-06-28 | 2023-06-28 |  | 1911568 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44304 (R6141) | Peppervine Switch: 138 kV Station Rebuild | City of Waco, McLennan County | Rebuild the 138 kV Switch with ten 3200 A or greater, 138 kV circuit breakers in a breaker-and-a-half arrangement. | 2022-08-12 | 2023-11-28 | 2023-11-28 |  | 11566138 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46695 0PT47758 0PT47760 (R6215) | Mallard Switch : Establish breaker-and-a-half station | City of Hutto, Williamson County | Establish Breaker-and-a-half Station for SAS. | 2022-08-19 | 2023-05-03 | 2023-05-03 |  | 16173528 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43163 0PT44823 (R4015) | Smith Creek (Formerly Bellevue Sub): Rebuild 69 kV station with a rural design | City of Bellevue, Clay County | Rebuild 69 kV station with a rural design | 2022-08-08 | 2022-12-20 | 2022-12-20 |  | 2200977 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41807 (R8619) | Meteor Switch: Establish 345 kV ring bus station for point of interconnection (POI). | City of Odessa, Ector County | Establish a 3-breaker, 345 kV, 5000 A ring bus station for point of interconnection (POI). | 2024-05-07 | 2024-12-27 | 2024-12-27 |  | 10,779,415.40 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45683 (M5324) | Bird Dog Switch: Establish a 345 kV for point of interconnection (POI) | City of Denton, Denton County | Establish a 345 kV, 3-breaker ring bus switchyard for point of interconnection (POI). | 2023-02-24 | 2023-05-15 | 2023-05-15 |  | 7865658 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46327 0PT49964 (R6190) | Pepper Creek Switch : Establish for point of delivery POD | City of Temple, Bell County | Establish with thirteen 138 kV circuit breakers to provide three point of delivery's to adjacent customer station. | 2024-03-14 | 2024-12-12 | 2024-12-12 |  | 15402937.36 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46153 (R8027) | Ozark Trail Switch : Establish 3-breaker ring bus station for point of interconnection (POI) | City of Tulia, Swisher County | Establish 3-breaker ring bus station for point of interconnection (POI) | 2023-12-12 | 2024-05-17 | 2024-05-17 |  | 8175933.92 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48528 0PT51672 (R6256) | Bale Switch POI : Establish 345 kV station for a point of interconnection (POI) | Falls County | Establish 345 kV station for a point of interconnection (POI). | 2023-12-14 | 2024-05-15 | 2024-05-15 |  | 10701854.75 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41699 (R1752) | Marlin Switch : Rebuild station by installing three 2000 A or greater 69 kV circuit breakers | City of Marlin, Falls County | Rebuild station by installing three 2000 A or greater 69 kV circuit breakers. | 2025-04-01 | 2025-05-15 |  |  | 5698445.58 |  |  | 2 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44139 0PT51654 (M5323) | Pacific Switch : Establish 3-breaker ring bus for POI | City of Brookston, Lamar County | Establish 345 kV, 3 breaker ring bus for point of interconnection. | 2023-06-28 | 2024-02-05 | 2024-02-05 |  | 6924290.09 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46606 (R8621) | Delaware River Switch : Establish 3-breaker ring bus for point of interconnection (POI) | Culberson County | Establish 138 kV, 3-breaker ring bus for point of interconnection (POI). | 2023-08-30 | 2024-05-07 | 2024-05-07 |  | 8155593 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45165 (M3015) | Krum West Switch : Establish a 345 kV point of interconnection (POI) | City of Krum, Denton County | Modify to provide one 345 kV point of interconnection. | 2023-03-11 | 2024-06-01 | 2024-06-01 |  | 2035427 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47709 (M5326) | Lavender Switch : Establish a new 138 kV, 4 breaker ring bus station for point of interconnection (POI). | City of Wilmer, Dallas County | Establish the 138 kV switch in a 4-breaker-ring bus arrangement by installing four 138 kV, 3200 A circuit breakers to provide two 138 kV points of delivery (PODs). | 2023-01-27 | 2023-06-01 | 2023-06-01 |  | 6480932 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46199 | Stephen F. Austin Sub : Relocate substation demarcation | City of Nacogdoches, Nacogdoches County | Relocate substation demarcation | 2026-01-01 | 2026-10-01 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48180 (M5329 ) | Elizabethtown : Establish 138 kV point of interconnection (POI). | City of Roanoke, Denton County | Establish 138 kV point of interconnection (POI). | 2025-09-01 | 2025-11-06 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46909 (R8614) | Rock Lake POD: Establish 138 kV point of delivery | City of Stanton, Martin County | Establish a 138 kV for point of interconnection (POI) | 2024-03-09 | 2024-11-20 | 2024-11-20 |  | 1125908.8 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46340 (R6219) | Rookie Switch : Establish 138 kV station for point of interconnection | City of Thorndale, Milam County | Establish new station by installing three 138 kV, 3200 A circuit breakers in a 3-breaker ring bus arrangement. | 2024-01-29 | 2024-06-01 | 2024-06-01 |  | 6446199.16 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46171 (R6207)) | Riesel Switch : Establish 138 kV point of interconnection | City of Riesel, Falls County | Establish new station by installing three 138 kV, 3200 A circuit breakers in a 3-breaker ring bus arrangement. | 2022-11-11 | 2023-05-11 | 2023-05-11 |  | 4998964 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45041 0PT49586 (R6210) | Hog Creek Switch: Establish 345 kV point of interconnection | City of Cameron, Milam County | Establish a 345 kV point of interconnection (POI) | 2023-01-07 | 2023-05-12 | 2023-05-12 |  | 8486799 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45535 0PT48288 (R6213) | Belfalls Switch - Establish a 345 kV point of interconnection | City of Troy, Bell County | Establish a 345 kV, 3-breaker ring bus switchyard for point of interconnection (POI). | 2023-04-12 | 2023-11-01 | 2023-11-01 |  | 7911903 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48011 (M4352) | Greenville Ave Sub : Rebuild station to install new 138 kV bus and two transformers #3 & #4 | City of Dallas, Dallas County | Rebuild station to install new 138 kV bus and two transformers #3 & #4. | 2023-03-03 | 2023-12-27 | 2023-12-27 |  | 8850144 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43530 | Eiland Switch : Relay protection upgrade | City of Big Spring, Howard County | Relay protection upgrade | 2025-08-25 | 2025-10-31 |  |  | 336780 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46509 | Elm Mott Switch : Upgrade relaying for capacitor bank #1 | City of Elm Mott, McLennan County | Upgrade relaying for capacitor bank #1 | 2023-01-16 | 2024-11-27 | 2024-11-27 |  | 341627 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47310 | Rhome Sub: Replace 138 kV transformer | City of Rhome, Wise County | Replace 138 kV transformer and 138 kV motor operated switches | 2023-02-15 | 2023-05-26 | 2023-05-26 |  | 3342223 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46242 0PT44820 | Dry Fork Sub : Establish substation with two transformers and three feeder breakers | City of Wichita Falls, Wichita County | Establish substation with two transformers and three feeder breakers | 2023-08-17 | 2024-06-11 | 2024-06-11 |  | 7438715 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47886 (M4335) | Pebble Creek Switch : Install two 138 kV line terminals for point of delivery (POD) | City of Red Oak, Ellis County | Provide two 138 kV point of delivery (POD) line terminals by installing four 138 kV circuit breakers. | 2023-06-02 | 2025-04-01 |  |  | 4404845.61 |  |  | 99* | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47579 0PT47812 0PT47816 (M4327) | Loop Nine Switch : Establish two 345 kV autos. | City of Red Oak, Ellis County | Establish switch with a 345 kV six breaker ring bus with two autotransformers, and six 138 kV breakers in a breaker-and-a-half configuration. | 2023-08-21 | 2024-05-15 | 2024-05-15 |  | 38570962 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47363 0PT46957 | Plano Sub: Rebuild station | City of Plano, Collin County | Rebuild transformers and eight new switchgear type feeder breakers. | 2023-07-10 | 2024-01-05 | 2024-01-05 |  | 10581061 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47761 (M4327) | Pebble Creek Switch: Install breakers on rung to establish line terminals | City of Red Oak, Ellis County | Install two 138 kV breakers on rungs 5 and 6 to establish the line terminals | 2023-03-13 | 2024-05-10 | 2024-05-10 |  | 4461165 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47526 | Juniper Sub : Rebuild existing substation with rural substation skid | City of Graford, Palo Pinto County | Rebuild existing substation with rural substation skid | 2024-10-16 | 2025-04-30 |  |  | 3939069.66 |  |  | 91 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46493 | Anna Switch: Upgrade relaying on auto #2 | City of Anna, Collin County | Upgrade 345 kV auto #2 protection to provide redundancy for three phase faults. Install one 345 kV circuit breaker on auto #2 | 2023-09-16 | 2023-12-27 | 2023-12-27 |  | 1953723 |  |  | 100 | 138 | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46514 | Temple Switch : Upgrade relaying on capacitor bank #1 | City of Temple, Bell County | Upgrade relaying on capacitor bank #1 | 2024-04-01 | 2024-05-15 | 2024-05-15 |  | 609664.58 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46510 | Garland Bobtown Road Sub : Upgrade relaying on capacitor bank #1 | City of Garland, Dallas County | Upgrade relaying on capacitor bank #1 | 2024-04-01 | 2024-06-26 | 2024-06-26 |  | 453474 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46092 0PT47752 (R4021) | Bowman Switch : Replace existing autotransformer #1 | City of Wichita Falls, Wichita County | Replace existing auto on transformer #1 | 2023-09-15 | 2023-12-27 | 2023-12-27 |  | 8095355.11 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47086 (M3011) | Southlake Sub: Install 138 kV capacitor bank | City of Southlake, Tarrant County | Install capacitors on the 138 kV bus. | 2022-11-30 | 2023-05-26 | 2023-05-26 |  | 4439746 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48724 | Bear Creek Sub : Replace station #3 and #4 relaying with suburban IV | City of North Richland Hills, Tarrant County | Upgrade relaying on station #3 and #4. Replace station #3 and station #4 breakers and disconnect switches. | 2023-12-18 | 2024-06-03 | 2024-06-03 |  | 2587936.16 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47745 0PT49243 (R8618) | Buffalo Sub: Upgrade 138 kV circuit breaker | City of Stanton, Martin County | Upgrade 138 kV circuit breaker. Modify 138 kV bus protection to provide redundancy. | 2023-05-01 | 2024-06-28 | 2024-06-28 |  | 560304 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47525 0PT51292 | South Bend Sub : Rebuild station with Delta-Star skid mount | City of Graham, Young County | Rebuild existing substation utilizing a skid mounted substation. | 2024-02-09 | 2024-12-16 | 2024-12-16 |  | 4597592 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44227 0PT48161 | DFW Mid Cities Sub : Establish station with two transformers and four feeder breakers | City of Euless, Tarrant County | Establish station with two transformers and four feeder breakers | 2024-08-12 | 2025-05-15 |  |  | 14501213.58 |  |  | 99* | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47225 (M4331) | Newton Branch Sub: Establish station with one transformer and two feeder breakers | City of Midlothian, Ellis County | Establish station with one transformer and two feeder breakers | 2023-09-18 | 2024-09-10 | 2024-09-10 |  | 5567773.71 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47205 (M4137) | Mesquite North Sub : Upgrade Terminal to 3200A | City of Mesquite, Dallas County | Upgrade the line terminals to 3200 A at Mesquite North Sub. | 2025-09-15 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47199 (M4137) | Thornton East Sub : Add Line Switches and FID | City of Dallas, Dallas County | Add line switches and FID | 2025-09-15 | 2025-12-15 |  |  | 1549511.47 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46296 0PT48273 0PT47588 (R8564) | SkyWest : Upgrade 138 kV driver line terminal to be rated at 3200 A | City of Midland, Midland County | Remove wave trap and upgrade line communication to fiber. | 2023-10-19 | 2023-12-01 | 2023-12-01 |  | 616609 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46295 0PT48759 (R8564) | Driver : Upgrade 138 kV SkyWest line terminal to meet or exceed 3200 A | Midland County | Remove wave trap and upgrade line communication to fiber. | 2023-11-06 | 2024-06-01 | 2024-06-01 |  | 906192.32 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46003 (R8595) | Lamesa Switch : Rebuild/convert existing substation to 138 kV with two transformers | City of Lamesa, Dawson County | Disconnect the existing substation and rebuild to operate at 138 kV. | 2023-02-01 | 2024-03-27 | 2024-03-27 |  | 7588290 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46511 | Centerville Switch : Upgrade relaying on capacitor bank #1 | City of Buffalo, Leon County | Upgrade relaying on capacitor bank #1 | 2024-01-25 | 2024-06-28 | 2024-06-28 |  | 918404.1 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47350 0PT47102 (R8649) | Vincent Sub : Establish substation with one transformer | City of Big Spring, Howard County | Establish station with one transformer and two feeder breakers | 2023-01-31 | 2023-12-15 | 2023-12-15 |  | 5650762 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47322 0PT51464 | Ennis Southeast Sub : Install transformer #2 with two feeders | City of Ennis, Ellis County | Install transformer #2 with two feeder breakers. | 2023-01-20 | 2023-05-29 | 2023-05-29 |  | 1884960 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44231 0PT47655 0PT48829 (R6224) | Double Creek Sub : Establish substation with two transformers and four feeder breakers | City of Round Rock, Williamson County | Establish substation with two transformers and four feeder breakers | 2023-08-30 | 2023-12-27 | 2023-12-27 |  | 12237395 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44259 0PT44210 (M5310) | Padera Sub: Establish substation with two transformers and four feeder breakers | City of Midlothian, Ellis County | Establish two transformers and four feeder breakers | 2022-12-23 | 2023-11-01 | 2023-11-01 |  | 7665758 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47201 (M4137) | Sunnyvale Sub : Upgrade terminals to 3200A | City of Sunnyvale, Dallas County | The upgrade will replace all 138 kV switches, bus, and terminal equipment to meet 3200A. | 2023-10-20 | 2024-12-06 | 2024-12-06 |  | 443757 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47124 (R8659) | Sloan Switch : Establish 138 kV 3-breaker ring-bus point of interconnection (POI) for station | City of Midland, Midland County | Establish 138 kV 3-breaker ring-bus point of interconnection (POI) for station | 2024-11-15 | 2025-05-08 |  |  | 12398630.63 |  |  | 58 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47828 (R8624) | Moser Canyon POD: Establish 138 kV point of delivery (POD) for station | City of Colorado City, Mitchell County | Establish 138 kV point of delivery (POD) for station | 2023-09-20 | 2025-04-30 |  |  | 1156883 |  |  | 99* | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47207 (M4137) | Mesquite East Switch : Upgrade one circuit breaker terminal to 3200A and add two new terminals | City of Mesquite, Dallas County | Upgrade one circuit breaker terminal to 3200A and add two new terminals | 2023-01-27 | 2023-12-06 | 2023-12-06 |  | 2876107 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44255 0PT44779 (M5283) | Wilshire Sub : Establish substation with one transformer and two feeder breakers | Johnson County | Establish substation with one transformer and two feeder breakers | 2023-06-10 | 2024-02-23 | 2024-02-23 |  | 7816660 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT40856 (R3029) | AJ Swope Switch : Establish 345 kV terminal | Potter County | Establish 345 kV terminal. | 2023-12-21 | 2025-12-04 |  |  | 2783358 |  |  | 99* | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49046 (R8669) | White Dune POD : Establish 138 kV point of delivery (POD) | City of Wink, Winkler County | Establish 138 kV point of delivery (POD) | 2025-03-25 | 2025-06-06 |  |  | 6318892.4 |  |  | 7 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48618 | Blue Mound Sub : Install SODG on one feeder breaker | City of Fort Worth, Tarrant County | Install a distribution and transmission transfer trip protection scheme. | 2023-01-22 | 2025-01-10 | 2025-01-10 |  | 373613 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48124 (R6141) | Waco West Switch: Remove 138 kV yard & reconfigure auto connection | City of Waco, McLennon County | Remove all equipment in the 138 kV yard and reconfigure autotransformer #2 | 2023-09-30 | 2023-12-15 | 2023-12-15 |  | 1930107 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41044 | Royalty Sub: Convert station to 138 kV operation | City of Grandfalls, Ward County | Replace existing transformer and associated 69 kV equipment with 138 kV rated equipment. | 2024-02-13 | 2024-12-02 | 2024-12-02 |  | 4063623.16 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48200 (R6223) | Tiger Creek Switch : Establish 3-breaker ring -bus arrangement point of interconnection (POI) | City of McLennan, McLennan County | Establish 3-breaker ring-bus arrangement point of interconnection (POI) | 2024-05-22 | 2024-11-14 | 2024-11-14 |  | 11358438.37 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47778 | Westmoreland North Sub: Install transformer #2 and one feeder breaker | City of Dallas, Dallas County | Install transformer #2 and one feeder breaker | 2023-06-08 | 2024-12-12 | 2024-12-12 |  | 4471785 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46303 (R944) | Cumby Sub: Convert station to 138 kV operation | City of Cumby, Hopkins County | Convert station to 138 kV operation | 2023-05-29 | 2023-12-15 | 2023-12-15 |  | 3453066.64 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41021 (M5222) | Marrs Switch: Terminate 138 kV Duval Switch Line | City of Forest Hill, Tarrant County | Terminate the new 138 kV Duval Switch Line | 2025-04-11 | 2025-05-15 |  |  | 269523 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48541 0PT46372 0PT47882 0PT48590 (R8634) | Tesoro Switch: Establish station as a 10-breaker 345 kV breaker-and-a-half bus arrangement | City of Odessa, Midland County | Establish station as a 10-breaker 345 kV breaker-and-a-half bus arrangement | 2023-03-21 | 2024-06-01 | 2024-06-01 |  | 51315612 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49951 (R6172) | Bewley Sub : Rebuild 138 kV substation | City of McGregor, McLennan County | Rebuild 138 kV substation. | 2023-03-27 | 2023-09-01 | 2023-09-01 |  | 5112873 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48783 | Paris Switch : Replace three 345 kV circuit breaker | City of Paris, Lamar County | Replace three 345 kV circuit breaker | 2024-03-01 | 2024-06-01 | 2024-06-01 |  | 2657976 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47255 0PT47105 | Starr Ranch Sub (Norman Crossing): Establish station | City of Hutto, Williamson County | Establish substation with one transformer and two feeder breakers. | 2023-09-12 | 2023-12-13 | 2023-12-13 |  | 12035583.3 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47143 (R6191) | Eddy Sub: Rebuild substation with two transformers | City of Bruceville-Eddy, Falls County | Rebuild substation with two transformers . | 2023-05-04 | 2023-12-11 | 2023-12-11 |  | 7674888.26 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
16T64009 0PT47317 | Mary Avenue Sub : Establish with one transformer and four feeder breakers | City of Waco, McLennan County | Establish with one transformer and four feeder breakers | 2023-03-20 | 2025-06-30 |  |  | 6881328 |  |  | 99* | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49960 | Odessa EHV 138 kV: Replace seven oil pumps on Auto #2 | City of Odessa, Ector County | Replace various oil pumps on Auto #2. | 2025-04-01 | 2025-11-07 |  |  | 242336 |  |  | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47323 | Forest Hill Sub: Install bank #3 with one transformer and three feeder breakers | City of Fort Worth, Tarrant County | Install bank #3 with one transformer and three feeder breakers. | 2023-08-01 | 2024-01-22 | 2024-01-22 |  | 5634503 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47931 (R8633) | Bull Head POD: Establish 138 kV point of delivery (POD) | Odessa County | Establish 138 kV point of delivery (POD) | 2023-09-15 | 2024-05-31 | 2024-05-31 |  | 1284511.28 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47671 (M3228) | Poetry Switch - Establish 345 kV, 3200 A Switch for point of interconnection (POI) | City of Terrell, Kaufman County | Establish 345 kV, 3200 A switch for point of interconnection (POI) | 2023-08-08 | 2024-06-01 | 2024-06-01 |  | 8918238 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47407 | Rendon Sub: Establish station | City of Mansfield, Tarrant County | Establish station with two transformers and four feeder breakers. | 2024-06-20 | 2024-12-31 | 2024-12-31 |  | 9005526.81 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47542 | Shafter Lake Sub : Establish stations #3 & #4 each with one transformer one feeder breaker | Odessa County | Establish stations #3 & #4 each with one transformer one feeder breaker | 2023-05-20 | 2024-06-14 | 2024-06-14 |  | 6718470.06 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47136 0PT45862 0PT51132 0PT52905 0PT52906 0PT47111 (R6165) | Teal Switch: Establish a new switching station | City of Hutto, Williamson County | Establish a new switching station with fifteen 138 kV breakers, two 345 kV breakers, two autotransformers, and four reactors. | 2023-07-24 | 2025-05-15 |  |  | 37104354.76 |  |  | 99 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47355 0PT46906 | Circle Point Sub: Establish station with one transformer and two feeder breakers | City of Waco, McLennan County | Establish station with one transformer and two feeder breakers | 2024-03-15 | 2024-12-10 | 2024-12-10 |  | 9314574.12 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49260 (M3013) | Valley South: Install two 345 kV reactors | Fannin County | Install two 345 kV reactors, two 3200 A circuit breakers and two 3200 A sectionalizing switches. | 2023-07-05 | 2023-12-29 | 2023-12-29 |  | 11479356 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48779 (R8674) | SL Driver Sub : Addition of 138 kV line terminal | Midland County | Addition of 138 kV line terminal | 2023-09-19 | 2023-12-19 | 2023-12-19 |  | 1766020 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48182 (R8623) | Morgan Creek Switch : Upgrade terminal to 3200 A as part of establishing a 138 kV point of delivery (POD). | City of Colorado City, Mitchell County | Upgrade terminal to 3200 A as part of establishing a 138 kV point of delivery (POD). | 2024-04-01 | 2024-05-15 | 2024-05-15 |  | 467843.65 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47932 (R6228) | McGuffey POD : Establish 138 kV point of delivery (POD) | City of McGregor, McLennan County | Establish 138 kV point of delivery (POD) | 2023-05-22 | 2024-05-02 | 2024-05-02 |  | 1132098 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47775 | Hutto Switch : Replace electromechanical relays for auto #1 | City of Hutto, Williamson County | Replace electromechanical relays for auto #1. | 2023-09-13 | 2023-12-20 | 2023-12-20 |  | 2294627.9 |  |  | 100 | 345 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47531 | Waco Sanger Avenue Sub: Install transformer #2 | City of Waco, McLennan County | Install one transformer #2 and three feeder breakers. Replace existing control center with one pre-wired control center. | 2023-07-01 | 2024-06-03 | 2024-06-03 |  | 4454481 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47518 | Western Hills Sub: Install feeder on station #3 and upgrade relaying | City of Fort Worth, Tarrant County | Install feeder on station #3 and upgrade relaying. | 2023-09-16 | 2024-12-02 | 2024-12-02 |  | 6000000 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47439 | Ferris Sub: Rebuild station | City of Ferris, Ellis County | Rebuild station for a 4 transformer or 3 transformers & capacitor bank ultimate. | 2023-07-07 | 2024-06-28 | 2024-06-28 |  | 7696775.17 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47404 0PT46924 0PT54617 | Blackstock Sub: Establish substation with two transformer and three feeder breakers | Collin County | Establish substation with two transformer and three feeder breakers | 2025-06-01 | 2025-12-15 |  |  | 9675383.63 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT43108 0PT44821 (R4015) | Old Lake Switch: Establish station with an autotransformer and a 3-breaker 69 kV ring bus | City of Henrietta, Clay County | Establish station with a 100 MVA autotransformer and a 3-breaker 69 kV ring bus. | 2023-07-17 | 2024-06-10 | 2024-06-10 |  | 8224356 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45155 (R3028) | Midpoint Switch : Establish 3 breaker ring arrangement point of interconnection (POI) | Armstrong County | Establish 3 breaker ring arrangement point of interconnection (POI) | 2023-05-12 | 2023-11-15 | 2023-11-15 |  | 8256917.48 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44863 0PT54846 (R6246) | Ghost Town Switch: Establish 138 kV point of interconnection (POI) | City of Caddo, Stephens County | Establish 138 kV point of interconnection (POI) | 2024-04-08 | 2024-10-04 | 2024-10-04 |  | 5546376.54 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT02608 0PT44837 (R9022) | Mulberry Creek Switch: Rebuild the existing station | City of Abilene, Taylor County | Rebuild the existing 345 kV switching station as a 4-breaker ring bus. | 2024-11-15 | 2025-05-15 |  |  | 10963080.21 |  |  | 75 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42592 (R985) | Royse Switch: Remove 69 kV yard and establish 138 kV terminal to Commerce Switch | City of Royse City, Rockwall County | Remove 69 kV yard and establish 138 kV terminal to Commerce Switch | 2023-10-26 | 2023-12-21 | 2023-12-21 |  | 799329.21 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44209 0PT44619 (M5261) | Base Camp Switch : 138 kV station rebuild | City of Saginaw, Tarrant County | Rebuild the existing 138 kV Eagle Mountain switching station. | 2023-05-08 | 2025-12-15 |  |  | 25331071.08 |  |  | 50 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44256 0PT44755 | Charca Sub : Establish with one transformer and one feeder breaker and relay upgrade | Johnson County | Establish with one transformer and one feeder breaker and relay upgrade | 2023-08-01 | 2024-02-13 | 2024-02-13 |  | 6441930.3 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46203 (R6214) | McFall Switch : Establish 69 kV station for point of interconnection (POI) | City of Cameron, Milam County | Establish 69 kV station for point of interconnection (POI) | 2024-01-10 | 2024-05-10 | 2024-05-10 |  | 5182447.92 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46302 0PT55515 (R944) | Cumby Tap Switch: Remove auto #1 & 69 kV equipment and reconfigure as 138 kV ring bus | City of Cumby, Hopkins County | Remove autotransformer #1, 69 kV equipment and reconfigure station as a 138 kV ring bus and install deadend. | 2023-06-09 | 2024-03-11 | 2024-03-11 |  | 7014280.55 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46621 | DFW Southwest Sub : Reconfigure high side bus with breakers and FIDs | City of Dallas, Dallas County | Reconfigure high side bus with breakers and FIDs | 2023-06-26 | 2024-01-16 | 2024-01-16 |  | 4028834 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47402 | Robinson Northwest Sub: Install bank #2 and two feeder breakers | City of Waco, McLennan County | Install bank #2 and two feeder breakers | 2024-06-18 | 2024-12-31 | 2024-12-31 |  | 3162926.75 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48458 | Snyder Switch : Replace one 138 kV circuit breaker | City of Snyder, Scurry County | Replace one 138 kV circuit breaker. | 2024-09-18 | 2024-12-07 | 2024-12-07 |  | 524956.11 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48716 | Edwards Sub : Rebuild station with replacing bank #1 & installing new bank #2 for point of interconnection (POI) | City of Odessa, Crane County | Rebuild station with replacing bank #1 & installing new bank #2 with one transformer for point of interconnection (POI) | 2023-06-09 | 2024-03-01 | 2024-03-01 |  | 7746476.38 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49102 0PT48466 (M4354) | Bloomdale Switch : Establish four breaker ring bus | City of McKinney, Collin County | Establish three breaker 138 kV ring bus (ultimate four breaker) for point of interconnection (POI). | 2023-12-18 | 2024-09-26 | 2024-09-26 |  | 26114264 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47930 0PT51317 (R8624) | Wrage Ranch : Establish 138 kV Point of Delivery (POD) | Glasscock County | Establish 138 kV point of delivery (POD) | 2024-10-25 | 2025-07-01 |  |  | 1182727.27 |  |  | 99* | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50100 | Judkins Sub : Install feeder for Distributed Energy Storage Resource (DESR) | City of Odessa, Ector County | Install new feeder for Distributed Energy Storage Resource, including a transmission overvoltage protection scheme with three 138 kV CCVTs. | 2023-09-16 | 2024-03-19 | 2024-03-19 |  | 522194.67 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46378 (M4212) | Dealey Street Sub : Upgrade line terminal to 3200A | City of Dallas, Dallas County | Upgrade main through line terminals to 3200A. | 2023-09-26 | 2023-12-18 | 2023-12-18 |  | 1584343 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50253 0PT50769 (R8626) | Roughneck Tap: 138 kV line terminal upgrade | City of Stanton, Martin County | Upgrade all associated terminal equipment to meet or exceed 3200A. | 2024-03-19 | 2024-04-09 | 2024-04-09 |  | 459939.13 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49759 (R6208) | Bell County East Switch : Establish 345 kV point of interconnection (POI) | City of Temple, Bell County | Establish 345 kV point of interconnection (POI) | 2024-02-05 | 2024-06-01 | 2024-06-01 |  | 1641833.71 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49854 | Killeen Clear Creek Sub : Upgrade relaying to suburban IV | City of Killeen, Bell County | Upgrade relaying to suburban IV and replace feeder breakers. | 2023-10-19 | 2024-06-04 | 2024-06-04 |  | 2926358.35 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47359 | Pantego Sub: Replace two transformers | City of Arlington, Tarrant County | Replace two transformers and control center with a pre-wired control center. | 2024-09-06 | 2025-05-15 |  |  | 7122947.03 |  |  | 53 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47356 0PT46922 | Runaway Bay Sub: Establish substation with one transformer | Wise County | Establish substation with one transformer and two feeder breakers. | 2023-10-04 | 2024-07-16 | 2024-07-16 |  | 5865337 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48013 | Lemmon Ave Sub : Install transformers #3 and #4 | City of Dallas, Dallas County | Establish stations #3 and #4 with two transformers and eight new switchgear type feeder breakers. | 2023-09-02 | 2024-12-12 | 2024-12-12 |  | 8648622 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49790 0PT47302 (R6191) | Bronze Age Sub : Establish substation with one transformer | City of Troy, Bell County | Establish substation with one transformer and two feeder breakers. | 2023-11-13 | 2024-05-16 | 2024-05-16 |  | 6280985 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48718 | Barr Ranch Sub: Install bank #3 with one transformer and two feeder breakers | City of Midland, Midland County | Install bank #3 with one transformer and two feeder breakers for point of interconnection (POI). | 2023-08-18 | 2023-12-19 | 2023-12-19 |  | 4934341 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47204 | Mesquite Town East Sub : Upgrade terminal to 3200A | City of Mesquite, Dallas County | Upgrade the 138 kV line terminal and associated equipment to meet or exceed 3200 A. | 2024-02-27 | 2024-05-01 | 2024-05-01 |  | 907830.91 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44272 (M3223) | Royse Switch: Establish new 138 kV line terminal and disconnect existing Terrell 69 kV line | City of Royse, Rockwall County | Establish new 138 kV line terminal and disconnect existing Terrell 69 kV line | 2023-09-25 | 2023-12-21 | 2023-12-21 |  | 1269094.91 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42598 (R985) | Commerce Switch : Add 138 kV terminal addition for 138 kV Royse line conversion | City of Commerce, Hunt County | Add line terminal by installing a new 138 kV single-breaker terminal position. | 2023-08-06 | 2023-12-29 | 2023-12-29 |  | 1488433.79 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50813 | Crandall Sub: Install transformer #2 with one transformer and two feeder breakers | City of Crandall, Kaufman County | Install transformer #2 with one transformer and two feeder breakers. | 2024-01-12 | 2024-05-20 | 2024-05-20 |  | 3783842.75 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50268 (R6146) | McLane Switch : Rebuild station into a six breaker ring bus | City of Waco, McLennan County | Rebuild station into a six breaker ring bus | 2024-05-04 | 2025-05-15 |  |  | 10363590.22 |  |  | 93 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47647 | Taylor West Sub : Install bank #2 with one transformer and two feeder breakers | Williamson County | Install bank #2 with one transformer and two feeder breakers. | 2023-08-13 | 2023-12-01 | 2023-12-01 |  | 3088708.21 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47405 0PT46905 | Castleman Sub: Establish substation with one transformer and two feeder breakers | City of Hewitt, McLennan County | Establish substation with one transformer and two feeder breakers. | 2023-08-03 | 2024-01-11 | 2024-01-11 |  | 6220625 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48014 | Matilda Sub : Install transformer #3, #4, and associated switchgear | City of Dallas, Dallas County | Establish stations #3 and #4 with two transformers and eight switchgear feeder breakers. | 2023-06-07 | 2024-06-21 | 2024-06-21 |  | 8573178 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47361 0PT47104 (M4332) | Templeton Sub: Establish substation with one transformer | City of Waxahachie, Ellis County | Establish substation with one transformer and two feeder breakers | 2023-07-18 | 2023-12-28 | 2023-12-28 |  | 6068762 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44334 (R6147) | Elm Mott Switch: Add a line terminal | City of Elm Mott, McLennan County | Add a line terminal to convert 69 kV Waco East Switch line to 138 kV | 2023-10-01 | 2024-06-11 | 2024-06-11 |  | 1150308 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46385 | Industrial Blvd Switch : Replace three overdutied breakers | City of Dallas, Dallas County | Replace 138 kV overdutied circuit breakers | 2023-10-22 | 2023-12-18 | 2023-12-18 |  | 1511565.61 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48773 (R8606) | South Midland Switch : Reconfigure the 138 kV high side | City of Midland, Midland County | Reconfigure the 138 kV high side | 2024-01-22 | 2024-02-05 | 2024-02-05 |  | 679897 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46506 | Cedar Hill Switch : Upgrade relaying on auto #2 | City of Cedar Hill, Dallas County | Upgrade 345 kV auto #2 protection to provide redundancy for three phase faults. | 2024-01-21 | 2024-06-17 | 2024-06-17 |  | 1628115.95 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50076 | Maverick Draw Sub : Install bank #2 with one transformer and two feeder breakers | City of Salt Flat, Culberson County | Install bank #2 with one transformer and two feeder breakers | 2024-01-25 | 2024-06-13 | 2024-06-13 |  | 3015513.2 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49660 0PT48928 (R8670) | Quartz Sand Switch: Establish 138 kV station | City of Stanton, Glasscock County | Establish as a 5-breaker 138 kV breaker-and-a-half bus arrangement. | 2024-01-26 | 2024-06-22 | 2024-06-22 |  | 9228939.54 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49486 (R8678) | Raceway Switch : Establish 138 kV, 3 breaker ring bus station for point of interconnection (POI) | City of Odessa, Ector County | Establish 138 kV, 3 breaker ring bus station for point of interconnection (POI). | 2024-01-16 | 2024-06-05 | 2024-06-05 |  | 6002291.05 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47093 (M3063) | Bear Pen Switch: Establish 345 kV station for point of interconnection (POI) | City of Mt Vernon, Franklin County | Establish 345 kV station for point of interconnection (POI) | 2026-06-05 | 2027-12-09 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49018 0PT51675 (R6231) | Dos Rios Switch: Establish 138 kV station for point of interconnection (POI) | Milam County | Establish 138 kV station for point of interconnection (POI). | 2028-11-01 | 2029-05-10 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49981 (M3500) | Denton Creek Switch: Establish 138 kV station for point of interconnection (POI) | City of Decatur, Wise County | Establish 138 kV station for point of interconnection (POI). | 2023-11-03 | 2024-05-15 | 2024-05-15 |  | 6036824 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49664 0PT51698 (M4001) | Endeavor Switch : Establish 345 kV station for a point of interconnection (POI) | City of Midlothian, Ellis County | Establish 345 kV station for a point of interconnection (POI) | 2024-01-29 | 2024-12-02 | 2024-12-02 |  | 11325067.55 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47779 (R6255) | Cannon Switch : Establish 138 kV station for a point of interconnection | City of Milano, Milam County | Establish 138 kV station for point of interconnection (POI) | 2025-05-05 | 2025-11-13 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46105 (R6094) | Tyler Switch : Upgrade one circuit breaker terminal to 2000A | City of Tyler, Smith County | Upgrade jumpers on one circuit breaker terminal to be rated 2000A. | 2026-06-05 | 2026-09-15 | [5 empty] | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45620 (M3232) | Nautilus Switch : Establish 345 kV station for a point of interconnection (POI) | City of Glen Rose, Somervell County | Establish 345 kV station for point of interconnection (POI). | 2025-12-15 | 2027-05-13 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47268 (M4356) | Tri Corner Switch : Add a breaker and a half rung to existing station for new point of interconnection (POI) | City of Seagoville, Dallas County | A breaker-and-a-half rung will be added to the existing station for point of interconnection (POI). | 2023-12-04 | 2025-03-27 |  |  | 4553646.26 |  |  | 99* | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50292 | Moss Switch 345/138 kV: Replace (6) Oil Pumps on Auto #1 | Ector County | Replace oil pumps on Auto #1 at Moss Switch 345/138 kV | 2024-03-12 | 2024-12-18 | 2024-12-18 |  | 479840 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49492 | Anna Switch : Replace existing SSVTs | City of Anna, Collin County | Replace existing SSVTs and upgrade grounding grid | 2024-02-12 | 2024-05-13 | 2024-05-13 |  | 1681386 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50485 (M4356) | Carrollton Northwest : Replace one overdutied 138 kV circuit breaker | City of Carrollton, Dallas County | Replace one overdutied 138 kV circuit breaker | 2024-01-18 | 2024-03-01 | 2024-03-01 |  | 622143.12 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48106 0PT53764 (R6252) | Files Valley Switch: Establish 345 kV ring bus station for a point of interconnection (POI) | City of Itasca, Hill County | Establish a 345 kV ring bus station for a point of interconnection (POI). | 2023-10-24 | 2024-05-14 | 2024-05-14 |  | 9187622.53 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46515 (R8530) | Moss Switch: 138 kV circuit breaker line terminal upgrade | City of Odessa, Ector County | Upgrade the 138 kV circuit breaker line terminal to 3200 A. | 2024-03-06 | 2024-06-01 | 2024-06-01 |  | 413295 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50806 | Roanoke West Sub: Install transformer #3 | City of Roanoke, Denton County | Install transformer #3, two 25 kV feeder breakers, one 25 kV bus tie breaker, 25 kV feeder ties, and new control center. | 2023-11-20 | 2024-06-19 | 2024-06-19 |  | 6276612.67 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47403 0PT47108 | Vanguard Sub: Establish station with two transformers and five circuit breakers | City of Mesquite, Dallas County | Establish substation with two transformers and five circuit breakers. | 2023-10-16 | 2024-12-20 | 2024-12-20 |  | 10372355.48 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50805 | Kaufman South Sub: Upgrade transformer #1 and install transformer #2 | City of Kaufman, Kaufman County | Replace existing transformer #1, remove associated voltage regulators, and install transformer #2 with one feeder breaker. | 2024-02-01 | 2024-07-08 | 2024-07-08 |  | 5307743.44 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47524 0PT49508 (R4026) | Bowman Switch : Replace auto transformer #2 | City of Wichita Falls, Wichita County | Replace existing auto transformer #2 | 2024-01-18 | 2024-05-28 | 2024-05-28 |  | 7893819.97 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49746 0PT48318 0PT54643 | Steer Sub : Establish station with two transformers | City of Big Spring, Howard County | Establish station with two transformers and four feeder breakers. | 2024-01-26 | 2024-08-30 | 2024-08-30 |  | 8326843.3 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50079 | China Lake Sub : Install bank #2 with one transformer and install two feeder breakers | City of Monahans, Ward County | Install bank #2 with one transformer and install two feeder breakers. | 2024-01-31 | 2024-10-30 | 2024-10-30 |  | 3200826.04 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47660 (M4328) | Red Oak Sub : Upgrade existing terminal and associated equipment to meet or exceed 3200 A | City of Red Oak, Ellis County | Upgrade existing terminal and associated equipment to meet or exceed 3200 A. | 2024-04-06 | 2024-05-31 | 2024-05-31 |  | 473635.54 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47440 0PT47099 | Dorchester Sub: Establish station with one transformer and two feeder breakers | Grayson County | Establish station with one transformer and two feeder breakers. | 2024-06-01 | 2025-05-15 |  |  | 8436097.96 |  |  | 99* | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49446 (R8671) | Merrick POD : Establish 138 kV point of delivery (POD) | City of Stanton, Martin County | Establish 138 kV point of delivery (POD) | 2024-01-26 | 2024-05-01 | 2024-05-01 |  | 1100120.75 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50900 0PT54556 (R8699) | Wishbone POD : Establish 138 kV point of delivery (POD) | City of Stanton, Martin County | Establish 138 kV point of delivery (POD) | 2024-03-15 | 2024-11-15 | 2024-11-15 |  | 2354178.17 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50818 | Shifting Sands Sub : Install bank #2 with one transformer and two feeder breakers | Winkler County | Install bank #2 with one transformer and install two feeder breakers. | 2024-02-05 | 2024-06-04 | 2024-06-04 |  | 3717076.94 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50850 | Britton Road Sub : Install station #4 with one 345 kV transformer and one feeder breaker; install one feeder breaker on #3 | City of Mansfield, Tarrant County | Britton Road Sub : Install station #4 with one 345 kV transformer and one feeder breaker; install one feeder breaker on #3 | 2023-12-10 | 2024-12-27 | 2024-12-27 |  | 5645752 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49104 (R8679) | Lamesa Switch : Add 138 kV rung and line terminal addition | Dawson County | Add 138 kV rung and line terminal, two-breaker rung in breaker and a half arrangement with minimum terminal and equipment rating of 3200 A | 2024-03-01 | 2024-05-21 | 2024-05-21 |  | 2206288.95 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48489 0PT46856 | Floyd Branch Sub: Establish station with one transformer and three feeder breakers | City of Dallas, Dallas County | Establish station with one transformer and three feeder breakers | 2024-03-14 | 2024-12-13 | 2024-12-13 |  | 10049090.88 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51492 | Hartring Sub : Establish substation with one transformer and install two feeder breakers | City of Big Lake, Reagan County | Establish substation with one transformer and install two feeder breakers. | 2024-04-01 | 2025-04-30 |  |  | 9006261.24 |  |  | 99* | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | The project will be moved to the CCN section and will not be included in this section in next month's report.
0PT48778 (M4352) | Greenville Ave Sub : Install two transformers | City of Dallas, Dallas County | Install two transformers | 2024-01-02 | 2024-12-12 | 2024-12-12 |  | 6483491.94 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49834 (R8360) | McDonald Road Switch: Upgrade 138 kV line terminal | City of Ross, Glasscock County | Upgrade 138 kV circuit breaker line terminal and associated equipment to meet or exceed 3200 A. | 2024-03-04 | 2025-01-15 | 2025-01-15 |  | 800181.44 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50080 | Frankel City Sub : Upgrade bank#1 and install bank #2 with one transformer | City of Andrews, Andrews County | Upgrade bank #1 with one transformer and install one feeder breaker and install bank #2 with one transformer and four feeder breakers. | 2024-01-18 | 2024-08-12 | 2024-08-12 |  | 5237672.45 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50817 0PT51504 | Lazy Ranch Sub : Establish station with two 138 kV transformers | City of Stanton, Martin County | Establish station with two transformers, four feeder breakers, one bus tie breaker, and five sectionalizing switches. | 2023-11-18 | 2024-12-19 | 2024-12-19 |  | 8793582.66 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44297 (R6146) | Waco East Substation: Rebuild substation with two transformers | City of Waco, McLennan County | Rebuild substation with two transformers and retire switching station | 2025-05-16 | 2025-12-15 |  |  | 14648666 |  |  | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50194 0PT49507 (R6239) | Temple Pecan Creek Switch: Install auto #2 and two 345 kV line terminals | City of Temple, Bell County | Install auto #2, two 345 kV line terminals, and one 138 kV line terminal. | 2023-12-04 | 2024-12-16 | 2024-12-16 |  | 15041966.87 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48090 (R8621) | Chimney Well POD : Remove equipment for replacement by new Delaware River Switch point of Delivery (POD) | Culberson County | Remove existing line connections and associated equipment for point of delivery (POD). | 2024-04-23 | 2024-05-20 | 2024-05-20 |  | 291043 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46113 (R8591) | Yucca Drive Switch: 138 kV line terminal addition | City of Monahans, Ward County | Disconnect two line terminals and remove one autotransformer to add one line terminal. | 2024-09-05 | 2024-12-11 | 2024-12-11 |  | 1025973.82 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46516 (R8530) | Ector Harper Sub: 138 kV line terminal upgrade | Odessa County | Upgrade the 138 kV line terminal to 3200 A. | 2024-02-09 | 2024-06-01 | 2024-06-01 |  | 408478 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46654 0PT50465 | Tyre Park Sub : Establish new substation | City of Grand Prairie, Dallas County | Establish station with two transformers, two fault interrupting devices and five motor operated sectionalizing switches. | 2025-05-19 | 2026-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48697 (R8528) | Odessa EHV Switch: Upgrade circuit breaker line terminal | City of Odessa, Ector County | Upgrade circuit breaker line terminal and associated equipment to meet or exceed 3200 A. | 2024-11-27 | 2025-03-17 | 2025-03-17 |  | 1517538.91 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49025 (R6173) | Cathey Creek Sub: Install transformer #1 and two feeder breakers | City of Holland, Bell County | Install station with one transformer and two feeder breakers. | 2024-01-15 | 2024-05-09 | 2024-05-09 |  | 5312637 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52135 | Round Rock Southeast Sub : Install bank #4 with a one transformer and two feeder breakers | City of Round Rock, Williamson County | Install bank #4 with one transformer and two feeder breakers | 2024-04-03 | 2024-08-21 | 2024-08-21 |  | 4616659.05 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50077 | Alcatraz Sub : Install bank #3 with one transformer and install two feeder breakers | City of Mentone, Loving County | Install bank #3 with one transformer and install two feeder breakers. | 2024-01-11 | 2024-06-11 | 2024-06-11 |  | 4686632.15 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45580 (R6246) | Breckenridge Substation: Transfer trip addition and line terminal upgrade | City of Breckenridge, Stephens County | Addition of one transfer trip panel and associated wiring for the remote-end addition and associated line trap/tuner/CCVT will also need to be replaced. | 2024-03-06 | 2024-10-04 | 2024-10-04 |  | 359022.13 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50810 | Mariensfield Sub: Install bank #2 with one transformer and two feeder breakers | City of Midland, Martin County | Install bank #2 with one transformer and install two feeder breakers. | 2024-01-26 | 2024-06-01 | 2024-06-01 |  | 3102180.57 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50811 | Kyle Ranch Sub: Install bank #3 and two feeder breakers | City of Mentone, Loving County | Install bank #3 with one transformer and install two feeder breakers. | 2024-01-17 | 2024-12-01 | 2024-12-01 |  | 3184741.5 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50975 0PT49550 | Ten Mile Sub: Establish station with two transformers | City of Lancaster, Dallas County | Establish station with two transformers and four feeder breakers. | 2024-03-20 | 2024-12-01 | 2024-12-01 |  | 10464275.35 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50815 | Willow Wells Sub: Install bank #3 with one transformer and two feeder breakers | Winkler County | Install bank #3 with one transformer and install two feeder breakers. | 2024-01-21 | 2024-06-20 | 2024-06-20 |  | 4570551.78 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50838 (M4347) | DFW B East: 138 kV line terminal upgrades | City of Irving, Dallas County | Upgrade 138 kV line terminal and associated equipment to meet or exceed 3200 A. | 2024-08-21 | 2025-12-15 |  |  | 2046730.07 |  |  | 44 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51845 0PT51679 (R8692) | Azalea Sub : Establish Substation with three 47 MVA, 138-25 kV transformers and four feeder breakers | City of Midland, Midland County | Establish substation with three 47 MVA, 138-25 kV transformers and four feeder breakers. | 2024-06-27 | 2024-12-23 | 2024-12-23 |  | 15381947.99 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50966 | Ivy League Sub: Install bank #2 with one transformer and two feeder breakers | Collin County | Install bank #2 with one transformer and install two feeder breakers. | 2024-03-13 | 2024-06-28 | 2024-06-28 |  | 2908741.91 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51117 | Ennis South Sub: Rebuild station with two transformers and with eight feeder breakers | City of Ennis, Ellis County | Rebuild station with two transformers and with eight feeder breakers. | 2024-07-01 | 2025-04-12 |  |  | 8787341.92 |  |  | 99* | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51217 0PT48501 | Ridgeview Sub: Establish station with three transformers and six feeder breakers | City of Allen, Collin County | Establish station with three transformers, six feeder breakers, two bus tie breakers, three feeder ties, and nine sectionalizing switches. | 2024-03-06 | 2024-12-12 | 2024-12-12 |  | 16396730.23 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51523 0PT50035 (R8677) | Roadrunner POD: Install 138 kV capacitor bank | Ector County | Install one capacitor bank, including one circuit breaker, three circuit switchers, and three motor-operated air switches. | 2024-02-28 | 2024-06-27 | 2024-06-27 |  | 3536983.25 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51524 (R8693) | East Stiles Sub: Install 138 kV capacitor bank | City of Big Lake, Reagan County | Install one capacitor bank, including one circuit breaker, three circuit switchers, and one motor-operated air switch. | 2024-02-20 | 2024-07-24 | 2024-07-24 |  | 2154873.6 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51540 | Tex Harvey Sub : Install bank #2 with one transformer and two feeder breakers | Midland County | Install bank #2 with one transformer and two feeder breakers. | 2024-03-06 | 2024-06-28 | 2024-06-28 |  | 2951240.79 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51623 (R8700) | Centralia Sub: Install 138 kV capacitor Bank #2 | Odessa County | Install one capacitor bank, including one circuit breaker, three circuit switchers, and one motor-operated air switch. | 2024-02-09 | 2024-06-05 | 2024-06-05 |  | 3090037.78 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51635 | Century Sub: Install feeder for Distributed Energy Storage Resource (DESR) | City of Arlington, Tarrant County | Install new feeder for Distributed Energy Storage Resource, including a transmission overvoltage protection scheme. | 2024-03-22 | 2025-05-08 |  |  | 596064 |  |  | 93 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42599 (R985) | Commerce Sub: Remove 69 kV yard | City of Commerce, Hunt County | Remove 69 kV yard which includes one autotransformer, one circuit breaker, and all associated equipment and structures. | 2024-04-04 | 2024-05-15 | 2024-05-15 |  | 1086869.4 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47140 (R6191) | Peppervine Switch: Install one 138 kV line terminal | City of Waco, McLennan County | Install one 138 kV breaker to an existing rung as part of converting the existing line associated. | 2024-05-04 | 2024-07-19 | 2024-07-19 |  | 1653350.44 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47354 0PT52384 (R6236) | Thorndale North Sub: Install 138 kV capacitor bank | City of Thorndale, Milam County | Install 138 kV capacitor bank. | 2024-02-17 | 2024-06-03 | 2024-06-03 |  | 2901985.88 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49745 (R8303) | Stanton East Switch: 138 kV circuit breaker line terminal modifications | City of Stanton, Martin County | Modify two 138 kV circuit breaker line terminals. | 2024-11-20 | 2024-12-15 | 2024-12-15 |  | 751654.5 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49833 (R8360) | Morgan Creek Switch: Upgrade one circuit breaker line terminal | City of Colorado City, Mitchell County | Upgrade one line terminal and associated equipment. | 2024-03-04 | 2024-05-14 | 2024-05-14 |  | 660366.6 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50261 0PT50001 (R6241) | Carroll Springs Sub: 138 kV capacitor bank replacement | City of Palestine, Anderson County | Replace the existing single stage 69 kV capacitor bank. | 2024-03-07 | 2024-06-05 | 2024-06-05 |  | 2478415.31 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50571 (R6277) | Beulah Switch : Establish 345 kV station for a point of interconnection (POI) | Milam County | Establish 345 kV station for point of interconnection (POI). | 2024-07-18 | 2024-12-22 | 2024-12-22 |  | 10510829.63 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50765 (R8697) | Shaw POD : Establish 138 kV point of delivery (POD) | City of Midland, Midland County | Establish 138 kV point of delivery (POD). | 2024-02-27 | 2024-05-21 | 2024-05-21 |  | 1153081.18 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50809 | Cottonfield Sub: Install transformer #2 | City of Midland, Midland County | Install transformer #2 with two feeder breakers and one motor-operated sectionalizing switch. | 2024-02-06 | 2024-06-21 | 2024-06-21 |  | 2868222.04 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50816 | Knott Sub: Install Transformer #2 | City of Big Springs, Howard County | Install transformer #2 with two feeder breakers. | 2024-01-23 | 2024-06-26 | 2024-06-26 |  | 3319771.26 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50970 | Taylor Sub: Replace transformer #1 & transformer #2 | City of Taylor, Williamson County | Replace transformer #1 and transformer #2 with one transformer and install one feeder breaker on bank #1. | 2024-01-25 | 2024-10-01 | 2024-10-01 |  | 7492171.61 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49481 0PT50584 | Boat Club Sub: Establish substation with two transformers and three feeder breakers | City of Fort Worth, Tarrant County | Establish substation with two transformers and three feeder breakers | 2024-09-23 | 2025-05-15 |  |  | 10404875.82 |  |  | 99* | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51045 (R6187) | Tin Roof POD : Establish carrier blocking terminal for point of delivery (POD) | Bell County | Establish carrier blocking terminal for point of delivery (POD). | 2024-03-13 | 2024-12-01 | 2024-12-01 |  | 475319.7 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51142 (R8697) | Desert Wind Sub : Add 55.2 MVAR reactive compensation | City of Garden City, Glasscock County | Add 55.2 MVAR three stage capacitor bank for point of delivery (POD). | 2024-02-08 | 2024-06-30 | 2024-06-30 |  | 2943265.39 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51598 0PT50908 | Rosen Heights Sub : Rebuild station with three transformers | City of Fort Worth, Tarrant County | Rebuild with three transformers and ten feeder breakers. | 2024-06-05 | 2025-07-18 |  |  | 14679351.3 |  |  | 63 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51826 | Mesquite East Switch : Replace overduited 138 kV circuit breaker | City of Mesquite, Dallas County | Replace overdutied 138 kV circuit breaker. | 2024-05-02 | 2025-02-21 |  |  | 888747.24 |  |  | 99* | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51836 | Hutto Switch : Replace overdutied 138 kV circuit breaker | City of Hutto, Williamson County | Replace overdutied 138 kV circuit breaker. | 2024-02-16 | 2024-05-10 | 2024-05-10 |  | 365009.55 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47662 | Desoto Switch : Terminal upgrades | City of Red Oak, Ellis County | Modify relaying for Loop Nine Switch. | 2023-10-29 | 2024-04-09 | 2024-04-09 |  | 301610.47 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41321 0PT54410 (R6257) | Rowan Creek Switch : Establish 138 kV ring bus station for a point of interconnection (POI) | Angelina County | Establish 138 kV ring bus station for a point of interconnection (POI). | 2024-07-17 | 2024-11-15 | 2024-11-15 |  | 6578329.42 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46111 0PT48726 (R6094) | Brownsboro Sub : Rebuild substation with two transformers and three feeder breakers | City of Brownsboro, Henderson County | Rebuild station with two transformers, three feeder breakers and one feeder tie breaker. | 2024-06-03 | 2024-11-18 | 2024-11-18 |  | 7076270.08 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47141 (R6191) | Temple Elm Creek Switch: Establish new rung with two 138 kV breakers | City of Temple, Bell County | Install one 138 kV breaker as part of a new breaker-and-a-half rung. | 2024-02-15 | 2024-06-28 | 2024-06-28 |  | 1292171.74 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47657 (M4328) | Desoto Switch : Upgrade existing terminal | City of Dallas, Dallas County | Upgrade existing terminal and associated equipment to meet or exceed 3200 A. | 2024-04-03 | 2024-06-05 | 2024-06-05 |  | 455606.82 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47764 0PT49509 0PT49520 0PT48860 (R3024) | Ranger Camp Switch: Establish 345 kV station | City of Colorado City, Mitchell County | Establish new station as an 18-breaker 345 kV breaker-and-a-half bus arrangement with two autotransformers. | 2023-12-18 | 2025-04-01 |  |  | 73905086.77 |  |  | 99* | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49829 0PT50008 (R8658) | Lean Clay Switch: Establish 138 kV station | City of Pecos, Reeves County | Establish as a 10-breaker, 138 kV breaker-and-a-half bus arrangement with 3200 A terminals. | 2024-07-29 | 2025-02-20 |  |  | 12817097.11 |  |  | 99* | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50279 (M4367) | Shorthorn POD: Establish underground termination station for two point of delivery (POD) | City of Irving, Dallas County | Establish underground termination station with two points of delivery (POD). | 2024-05-01 | 2025-04-25 |  |  | 933157.1 |  |  | 74 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51182 0PT48331 0PT53673 (R8680) | Catclaw Switch: Establish 138 kV station | City of Midkiff,Upton County | Establish station as a 10-breaker 138 kV breaker-and-a-half bus arrangement. | 2024-03-09 | 2024-12-23 | 2024-12-23 |  | 22401326.63 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3) | This project is related to project 0PT49415 Tumbleweed
0PT51662 0PT50332 (R8694) | Savanna Sub: Establish station with one 138 kV capacitor bank | City of Big Lake, Reagan County | Establish station with one 138 kV capacitor bank | 2024-06-30 | 2025-02-01 | 2025-02-01 |  | 6281898.46 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51772 | Kirkland Park Switch : Replace one overdutied circuit breaker | City of Dallas, Dallas County | Replace one overdutied circuit breaker | 2024-05-01 | 2024-12-01 | 2024-12-01 |  | 825696.88 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51902 | Gainesville Sub : Replace one circuit breaker | City of Gainesville, Cooke County | Replace one circuit breaker. | 2024-04-05 | 2024-06-01 | 2024-06-01 |  | 257152.14 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52145 (R6277) | Sandow Switch : Transfer trip replacement, line terminal upgrade for addition, point of interconnection (POI) | Milam County | Transfer trip replacement, line terminal upgrade for addition, point of interconnection (POI) | 2024-10-15 | 2024-12-22 | 2024-12-22 |  | 723845.96 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52274 0PT52275 | SL Ringo Sub : Add deadends for Harting Sub | City of Big Lake, Reagan County | Add deadends for Harting Sub | 2024-06-26 | 2025-12-01 |  |  | 1533350.83 |  |  | 50* | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52427 (R8709) | Raven POI : Establish 138 kV point of interconnection (POI) | City of McCaulley, Fisher County | Establish 138 kV point of interconnection (POI). | 2024-02-25 | 2024-06-01 | 2024-06-01 |  | 1196631.64 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46090 0PT44803 (R8502) | Foundry Switch : Establish four breaker 138 kV ring bus for point of interconnection (POI) | City of Crane, Crane County | Establish four breaker 138 kV ring bus for point of interconnection (POI) | 2024-08-17 | 2024-12-20 | 2024-12-20 |  | 6592900.37 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48784 | Allen Switch : Replace three 138 kV circuit breakers | City of Plano, Collin County | Replace three 138 kV circuit breakers | 2024-03-26 | 2024-04-26 | 2024-04-26 |  | 1004529.42 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48976 0PT55073 (R6286) | Gindale Switch : Establish 345 kV station for a point of interconnection (POI) | City of Temple, Bell County | Establish 345 kV station for a point of interconnection (POI) | 2024-07-05 | 2024-12-18 | 2024-12-18 |  | 12821750.43 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48995 (M3069) | Valley South Switching Station : Establish 345 kV station for point of interconnection (POI) | City of Savoy, Fannin County | Establish station for point of interconnection (POI) | 2024-06-26 | 2025-04-15 |  |  | 4235203.61 |  |  | 99* | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49261 0PT48332 (R8603) | Mudstone (Peck Tap) Switch: Establish 138 kV switching station | City of Midland, Midland County | Establish 138 kV switching station | 2024-04-25 | 2024-12-14 | 2024-12-14 |  | 10623184.54 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46114 (R8591) | Thorntonville Sub: Convert station to 138 kV operation | City of Monahans, Ward County | Convert station operation from 69 kV to 138 kV. | 2024-09-16 | 2024-11-26 | 2024-11-26 |  | 495864.08 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49527 (R8603) | Spraberry Switch: 138 kV line terminal addition | City of Midland, Midland County | Install one 138 kV circuit breaker in a ring bus arrangement. | 2024-10-02 | 2024-12-14 | 2024-12-14 |  | 1465419.46 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49631 0PT53972 (R6282) | Steakley Dam Switch: Establish 345 kV ring bus station for point of interconnection (POI) | Falls County | Establish 345 kV ring bus station for point of interconnection (POI) | 2024-05-13 | 2024-11-14 | 2024-11-14 |  | 11781980.77 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49742 (R8303) | Onemile Switch: Establish 138 kV station | City of Big Spring, Howard County | Establish 138 kV station and Install three circuit breakers in a ring bus configuration. | 2024-06-25 | 2024-11-18 | 2024-11-18 |  | 6898882.99 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50163 (R6251) | Woodbury Switch : Establish 138 kV station for point of interconnection (POI) | Hill County | Establish 138 kV station for point of interconnection (POI) | 2025-05-16 | 2025-12-04 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50390 (R3050) | Ozark Trail Switch : Install 345 kV terminal for point of interconnection (POI) | City of Tulia, Swisher County | Install 345 kV terminal for point of interconnection (POI) | 2024-09-20 | 2026-05-14 |  |  | 2087138.41 |  |  | 99* | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50632 (M3031) | Watermill Switch : Rebuild 138 kV yard | City of Dallas, Dallas County | Rebuild 138 kV yard | 2024-06-19 | 2024-12-16 | 2024-12-16 |  | 25111624.53 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50814 | Calf Tank Sub: Establish station with two transformers and three feeder breakers | City of Big Spring, Howard County | Establish station with two transformers and three feeder breakers | 2024-06-20 | 2024-12-18 | 2024-12-18 |  | 8642703.74 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50967 0PT50045 | Howe Sub : Establish station with two transformers and six feeder breakers | City of Sherman, Grayson County | Establish station with two transformers and six feeder breakers | 2024-07-16 | 2024-12-30 | 2024-12-30 |  | 10973846.62 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51585 (M3076) | Progress Park Switch : Establish 138 kV, 4 breaker ring bus station for point of delivery (POD) | City of Sherman, Grayson County | Establish 138 kV, 4 breaker ring bus station for point of delivery (POD) | 2024-07-18 | 2024-12-17 | 2024-12-17 |  | 8156410.6 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51681 | Owl Hills Sub : Install bank #4 with a 138 kV transformer and two feeder breakers | City of Orla, Culberson County | Install bank #4 with a 138 kV transformer and two feeder breakers | 2024-06-26 | 2024-12-20 | 2024-12-20 |  | 3512732.57 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51685 0PT49512 0PT49513 0PT51619 (R8705) | Rockhound Switch (formerly Rough Switch) : Establish 345/138 kV station | City of Midland, Midland County | Establish station as a 8-breaker 345 kV breaker-and-a-half bus arrangement | 2024-04-01 | 2025-02-14 | 2025-02-14 |  | 59513275.35 |  |  | 100 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51770 (R8702) | Blue Mountain Switch: Establish 138 kV station for point of delivery | City of Wink, Winkler County | Establish 138 kV station for point of delivery | 2024-06-17 | 2024-12-23 | 2024-12-23 |  | 9999763.31 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51777 (R8692) | Grey Well Draw Switch : 138 kV terminal addition, one circuit breaker, three air switches and associated equipment | City of Midland, Midland County | 138 kV terminal addition, one circuit breaker, three air switches and associated equipment | 2024-09-12 | 2024-12-16 | 2024-12-16 |  | 1458858.35 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46680 (R6172) | Waco Atco Cement POD: Establish 138 kV point of delivery (POD) | City of Waco, McLennan County | Establish a 138 kV point of delivery (POD) and construct the POD with three motor operated sectionalizing switches. | 2025-08-08 | 2025-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52163 0PT55355 (M3095) | Winding Oaks Switch: Establish 138 kV station for point of interconnection (POI) | City of Anna, Collin County | Establish 138 kV station for point of interconnection (POI) | 2025-04-05 | 2025-10-30 |  |  | 6141623.08 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52527 (R6249) | Walnut Springs Switch: Establish station to provide 138 kV point of interconnection (POI) | City of Walnut Springs, Bosque County | Establish station to provide 138 kV point of interconnection (POI). | 2024-07-01 | 2024-12-20 | 2024-12-20 |  | 6625692.56 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49576 (R6253) | Temple Pecan Creek Switch: Install one 138 kV circuit breaker in a breaker-and-a-half arrangement for point of interconnection (POI) | City of Temple, Bell County | Install one 138 kV circuit breaker in a breaker-and-a-half arrangement for point of interconnection (POI) | 2025-02-05 | 2025-05-08 |  |  | 1676751.84 |  |  | 99* | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51970 | Midessa South Switch 345kV: Replace Gaskets on Auto Transformer #1 | Midland County | Regasket Auto 1 at Midessa South Switch 345 kV. | 2025-05-01 | 2025-06-30 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48690 | Wolf Switch: Upgrade two 138 kV circuit breaker line terminal | City of Monahans, Ward County | Upgrade two 138 kV circuit breaker line terminal and associated equipment to meet or exceed 3200 A. | 2024-10-11 | 2024-12-15 | 2024-12-15 |  | 313936.86 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51966 0PT52114 0PT55255 (M4368) | Outer Loop Switch: Establish 138 kV point of interconnection (POI) | City of Celina, Collin County | Establish three breaker 138 kV ring bus for point of Interconnection (POI) | 2024-08-21 | 2024-12-11 | 2024-12-11 |  | 7680208.8 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50968 0PT49606 | Sayers Sub: Establish station with one transformer and two feeder breakers | City of Elgin, Temple County | Establish station with one transformer, two 12.5 kV feeder breakers, one bus tie breaker, and three 138 kV sectionalizing switches. | 2024-07-19 | 2025-06-30 |  |  | 9606404.63 |  |  | 99* | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51778 (R8692) | SL Buffalo Switch : 138 kV terminal addition | City of Stanton, Martin County | Establish new 138 kV terminal to Grey Well Draw Switch | 2024-10-09 | 2024-12-23 | 2024-12-23 |  | 1252764.49 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47349 0PT47424 | Paloma Sub: Establish station with one transformer and two feeder breakers, and one bus tie breaker | City of Fort Worth, Tarrant County | Establish station with one transformer and two feeder breakers, and one bus tie breaker. | 2024-12-16 | 2025-06-30 |  |  | 12003868.83 |  |  | 1 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50976 0PT51031 | Itasca Sub: Rebuild station with one transformer | City of Itasca, Hill County | Rebuild existing station as rural Distran design with one transformer and two feeder breakers. | 2024-08-26 | 2025-02-07 | 2025-02-07 |  | 6056706.42 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51098 | Alliance Sub: Rebuild station with four transformers | City of Fort Worth, Tarrant County | Rebuild station by replacing the two transformers with four transformers. Install associated feeder breakers, bus ties and feeder ties, and nine sectionalizing switches. | 2024-05-26 | 2024-12-31 | 2024-12-31 |  | 12863642.68 |  |  | 100 | 345 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51544 | Lipan Substation : Replace bank #1 and install bank #2 with one transformer and one feeder breaker | City of Lipan, Palo Pinto County | Rebuild station with replacing bank #1 & installing new bank #2 transformers with two feeder breakers on bank #1 and one feeder breaker on bank #2. | 2024-09-09 | 2024-12-11 | 2024-12-11 |  | 1618843.37 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52129 | Jarrell East Sub: Replace two transformers and three feeder breakers | City of Jarrell, Williamson County | Replace two transformers, three feeder breakers with lower voltage feeder breakers, and one bus tie breaker and install one new feeder breaker. | 2024-06-10 | 2024-12-01 | 2024-12-01 |  | 4573892.65 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46683 (R6172) | McGregor Phillips Sub: Rebuild 138 kV station | City of McGregor, McLennan County | Remove the existing autotransformer equipment and structures. Establish a new 138 kV distribution station with two transformers. | 2025-11-15 | 2025-12-15 | [5 empty] | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47583 (M3505) | Bomarton Sub : Rebuild existing substation with a Delta Star rural substation skid | City of Seymour, Baylor County | Rebuild by installing one dual winding transformer and install three sectionalizing switches. | 2024-04-02 | 2024-07-02 | 2024-07-02 |  | 4759559.91 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47765 (R3024) | Morgan Creek Switch: Reconfigure station for Ranger Camp Switch | City of Colorado City, Mitchell County | Modify station configuration as part of relocating lines to Ranger Camp Switch. | 2024-10-30 | 2025-05-15 |  |  | 1230713.93 |  |  | 99* | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53109 | Olefin Switch : Install high side revenue metering | City of Odessa, Ector County | Install high side revenue metering and removal of six (6) single-phase 138 kV switches for point of interconnection (POI). | 2024-09-23 | 2025-01-29 | 2025-01-29 |  | 396763.93 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47856 | Lake Texoma Sub : Replace transformer #1 and install transformer #2 | City of Denison, Grayson County | Replace transformer #1 and install transformer #2 | 2023-10-02 | 2027-01-17 |  |  | 5113741 |  |  | 50 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47142 (R6191) | Rosenthal Sub: Establish one transformer with two feeder breakers and one tie breaker | City of Lorena, McLennan County | Establish one transformer with two feeder breakers and one tie breaker. | 2023-06-01 | 2024-06-28 | 2024-06-28 |  | 5451267.38 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45579 | Leon Switch: Transfer trip addition, line terminal upgrade, for the addition of point of interconnection (POI) | City of Eastland, Eastland County | Transfer trip addition, line terminal upgrade for the addition of point of interconnection (POI). | 2024-03-28 | 2024-10-11 | 2024-10-11 |  | 469520 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50819 | Fairfield West Sub: Install transformer #2 with two feeder breakers and one bus tie breaker | City of Fairfield, Freestone County | Install transformer #2 with two feeder breakers and one bus tie breaker and install a new control center and rebuild station #1 low-side arrangement. | 2024-08-01 | 2024-12-13 | 2024-12-13 |  | 4623458.24 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50821 | Trailwood Sub: Install transformer #3 with two feeder breakers | City of Grand Prairie, Dallas County | Install transformer #3 with two feeder breakers, one bus tie breaker, one feeder ties, one sectionalizing switch, and new control center. | 2024-08-21 | 2025-03-31 |  |  | 8450538.58 |  |  | 99* | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50972 | Buchanan Ranch Sub: Replace existing transformer #1 | City of Midland, Midland County | Replace existing transformer #1 and two 25 kV under ground feeder breakers. | 2024-03-09 | 2024-07-23 | 2024-07-23 |  | 3034799 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50973 0PT50549 | Grain Belt Sub : Establish station with one transformer | City of Denton, Denton County | Establish station with one transformer, two feeder breakers, one bus tie breaker, and three sectionalizing switches. | 2024-08-09 | 2024-12-20 | 2024-12-20 |  | 11631211.08 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51119 0PT50038 | Waxahachie North Sub: Install transformer #3 | City of Waxahachie, Ellis County | Expand station yard, install three sectionalizing switches and modify high-side bus work for loop in, loop out configuration. Install transformer #4 with one feeder breaker, one bus tie breaker, one feeder ties, and new control center. | 2024-09-30 | 2025-09-15 |  |  | 12328377.83 |  |  | 37 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51545 | Boundary Sub : Establish substation with two transformers and four feeder breakers | City of Coahoma, Howard County | Establish substation with two transformers and four feeder breakers. | 2024-06-10 | 2025-02-01 | 2025-02-01 |  | 9,533,666.66 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51693 0PT51129 | Button Sub: Establish station with two transformers and three feeder breakers | City of Nolanville, Bell County | Establish station with two transformers, three feeder breakers, and three sectionalizing switches. | 2024-09-23 | 2025-03-31 |  |  | 8946156.92 |  |  | 96 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51901 | Plano West Sub : Replace one 138 kV circuit breaker | City of Plano, Collin County | Replace one 138 kV circuit breaker | 2024-04-01 | 2024-11-04 | 2024-11-04 |  | 300153.45 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51928 | Allen Switch Sub : Replace one 138 kV circuit breaker | City of Plano, Collin County | Replace one 138 kV circuit breaker | 2024-10-21 | 2024-12-18 | 2024-12-18 |  | 489800.98 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46381 (R8596) | Andrews North Sub : Upgrade two circuit breakers to 3200A terminal | Andrews County | Upgrade two circuit breakers to 3200A terminal | 2024-02-27 | 2024-06-01 | 2024-06-01 |  | 493862.36 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50196 0PT49359 (R8667) | Tributary Switch: Establish 138 kV station | City of Coahoma, Howard County | Establish tributary Switch as a 4-breaker 138 kV ring bus arrangement with 3200 A terminals | 2024-06-20 | 2024-12-20 | 2024-12-20 |  | 11504530.45 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50808 | Round Rock Switch: Replace transformer #4 | City of Round Rock, Williamson County | Replace existing transformer #4 and include adjusting the conduit and bus work. | 2024-08-11 | 2024-11-01 | 2024-11-01 |  | 2045864.34 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50971 (R6273) | Chireno Sub: Rebuild station with one transformer and two feeder breakers | City of Chireno, Nacogdoches County | Rebuild existing station as rural skid design with one transformer and two feeder breakers. | 2024-08-09 | 2024-12-20 | 2024-12-20 |  | 5349809.18 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50979 | Central Park Switch : Establish 4 breaker ring bus arrangement for point of interconnection (POI) | City of Waco, McLennan County | Establish three 138 kV circuit breakers in a 4 breaker ring bus arrangement for point of interconnection (POI). | 2024-06-26 | 2024-12-19 | 2024-12-19 |  | 7283442.68 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51419 (R8303) | Beals Creek Sub: Install 138 kV capacitor bank | City of Big Springs, Howard County | Install MVAR capacitor bank, including one 138 kV circuit breaker, three 138 kV circuit switchers, and one motor-operated air switch. | 2024-08-16 | 2024-12-17 | 2024-12-17 |  | 3114927.22 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51494 | Belt Line Sub : Replace circuit switchers #121 and #122 | City of Dallas, Dallas County | Replace 138 kV Circuit Switchers #121 & #122 and retrofit Transformer #1 & #2 protective relay panels. | 2024-10-09 | 2024-12-10 | 2024-12-10 |  | 619916.04 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51851 0PT50918 | Hubbard Sub: Rebuild station with two transformers and two feeder breakers | City of Hubbard, Hill County | Establish station with transformers, two feeder breakers, one bus tie breaker, and four 138 kV sectionalizing switches. | 2025-01-13 | 2025-05-15 |  |  | 6966731.97 |  |  | 66 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51974 | Comanche Peak 345 kV Switch : Replace six 345 kV CCVTs | City of Glen Rose, Somervell County | Replace six bus CCVTs for both buses and replace two indoor bus junction boxes. | 2024-09-16 | 2024-11-22 | 2024-11-22 |  | 293263.2 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53882 | Rocky Creek Sub : Replace Regasket on Auto# 1- R.Martinez | Tarrant County | Regasket Auto #1 at Rocky Creek Sub | 2024-09-30 | 2024-12-17 | 2024-12-17 |  | 454496 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46112 0PT48324 (R6094) | Echols Sub: Rebuild station to 138 kV operation rural design | City of Murchison, Henderson County | Rebuild the substation to replace the one existing transformer and feeder breaker using rural design as a part of converting the line to 138 kV operation. | 2024-05-08 | 2024-12-11 | 2024-12-11 |  | 5256713.59 |  |  | 100 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49386 (R8603) | Desert Wind Sub: Add three stage capacitor bank for substation expansion | City of Garden City, Glasscock County | Add three stage capacitor bank for substation expansion includes installing three additional 138 kV, one MVAR capacitor banks, one 138 kV and one 3200 A circuit breaker. | 2024-09-29 | 2024-12-04 | 2024-12-04 |  | 3008130.4 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49568 (M5324) | Everman Switch : 138 kV breaker replacement | City of Fort Worth, Tarrant County | Replace one over-duty 138 kV, one circuit breaker as part of the work required for the interconnection project. | 2024-10-21 | 2024-11-04 | 2024-11-04 |  | 578572.1 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50500 | Angel POD : Establish 138 kV point of delivery (POD) | City of Angeles, Reeves County | Establish three 138kV motor operators, one 138 kV circuit switcher, three manually operated 138 kV air switches and one transclosure for point of delivery (POD). | 2024-10-14 | 2025-02-01 | 2025-02-01 |  | 2607657.68 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47441 | Lufkin Central Angelina Sub: Rebuild station | Angelina County | Replace transformer #1 with one transformer and two feeder breakers. Transformer #2 will be re-used on site with replacement of two existing feeders. | 2024-06-05 | 2025-02-03 | 2025-02-03 |  | 7554704.82 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47777 | Stagecoach Sub: Install transformer #2 and two feeder breakers | City of Killeen, Bell County | Install bank #2 with one transformer and two under ground feeder breakers. | 2024-08-26 | 2024-11-04 | 2024-11-04 |  | 3244911.52 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49750 (R6232) | Gristmill Switch : Establish 345 kV station for point of interconnection (POI) | Milam County | Establish switching station by installing three 345 kV, 3200A circuit breakers in a ring bus arrangement to provide a single point of interconnection (POI). | 2025-12-31 | 2026-04-16 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50195 0PT49516 0PT50180 (M4012) | Watermill Switch: Rebuild 345 kV yard | City of Lancaster, Dallas County | Rebuild the Watermill Switch 345 kV yard as a 6-breaker, 6 rung breaker-and-a-half station with 5000 A terminals. | 2024-08-23 | 2025-05-15 |  |  | 48039312.95 |  |  | 91 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50807 | Eberhardt Sub : Establish station with one transformer | City of Temple, Bell County | Establish station with one transformer, four feeder breakers, one bus tie breaker, and four 138 kV sectionalizing switches. | 2024-06-19 | 2024-12-30 | 2024-12-30 |  | 6957085.81 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50812 17T80063 | Founders Trail Sub: Establish station with two transformers | City of Killeen, Bell County | Establish station with two transformers and three feeder breakers. | 2024-08-26 | 2024-12-27 | 2024-12-27 |  | 10780754.85 |  |  | 100 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51037 0PT56520 (R6261) | Yarrelton Switch : Establish 345 kV switching station for point of interconnection (POI) | City of Rogers, Milam County | Establish a POI switching station by installing three 345 kV, 5000A circuit breakers in a ring bus arrangement. | 2025-01-10 | 2025-11-13 |  |  | 12121090.31 |  |  | 25 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51179 | Waxahachie O.C.F. Sub : Replace one 69 kV circuit breaker | City of Waxahachie, Ellis County | Replace one 69 kV circuit breaker. | 2024-09-18 | 2024-12-17 | 2024-12-17 |  | 319263.13 |  |  | 100 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51830 0PT55751 (R3030) | Kangaroo Switch : Establish 345 kV point of interconnection (POI) | Castro County | Establish 3 breaker ring-bus station for a point of interconnection (POI). | 2024-10-11 | 2025-05-15 |  |  | 11856304.18 |  |  | 63 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51904 0PT55757 (M3302) | Flying Tiger Switch : Establish 138 kV station for point of interconnection (POI) | City of Paris, Lamar County | Establish 138 kV station and install three 138 kV, 3200 A circuit breakers for point of interconnection (POI). | 2024-11-21 | 2025-05-08 |  |  | 6831131.34 |  |  | 98 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52079 | Webb Sub : Replace two 345 kV circuit breakers | City of Arlington, Tarrant County | Replace two 345 kV circuit breakers with Odessa EHV Switch spare breakers. | 2024-09-17 | 2024-12-21 | 2024-12-21 |  | 1009836.24 |  |  | 100 | 345 | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52098 | Denison North Sub : Upgrade transformer #1 and #2 relaying and convert cell communication | City of Denison, Grayson County | Install communication pole for cell conversion. Replace transformer #1 and #2 electromechanical relays with microprocessor relays. | 2024-07-24 | 2024-11-25 | 2024-11-25 |  | 537637.6 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52130 (M4378) | Healy Switch: Establish 345 kV station for point of interconnection (POI) | Kauffman County | Establish switching station by installing three 345 kV, 5000 A circuit breakers in a ring bus arrangement to provide a single point of interconnection (POI). | 2025-10-01 | 2026-05-07 |  |  | 13851564.78 |  |  | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52431 (M3125) | Sandy Ranch Switch : Establish 345 kV Station for point of interconnection (POI) | Sulphur Springs, Hopkins | Establish 345 kV station for point of interconnection (POI) | 2024-11-07 | 2025-05-08 |  |  | 12455405.17 |  |  | 58 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52969 0PT49783 0PT52447 0PT48326 0PT53006 (R8632) | Prairieland Switch: Establish 345/138 kV station | City of Stanton, Glasscock County | Establish 345 kV yard as a 6-breaker 345 kV breaker-and-a-half bus arrangement, establish 138 kV yard as a 6-breaker 138 kV breaker-and-a-half bus arrangement, and install two autotransformers | 2024-11-09 | 2025-09-30 |  |  | 50561496.17 |  |  | 19 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53560 | Liggett Switch : Install fiber optic cable | City of Irving, Dallas County | Install fiber optic cable for ODC enterprise communication path. | 2024-07-11 | 2024-09-19 | 2024-09-19 |  | 350435.75 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49415 (R8675) | Tumbleweed STATCOM: Establish FACTS Device | Upton County | Install a 138 kV +250/-250 MVAR dynamic reactive device on the West Texas Stanton Loop near Midkiff Switch. | 2024-08-01 | 2025-05-09 |  |  | 44,956,812 |  |  | 55 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49616 (R8499) | McKenzie Draw Switch: 138 kV circuit breaker line terminal modifications | Martin County | Modify four 138 kV circuit breakers line terminals | 2024-12-07 | 2024-12-19 | 2024-12-19 |  | 299696.15 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51999 (R3024) | Eskota Switch: Modify relaying for Ranger Camp Switch | Nolan County | Modify relaying as part of establishing Ranger Camp Switch. | 2025-01-28 | 2025-04-01 | 2025-04-01 |  | 334837.94 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52970 (R8632) | Quartz Sand: 138 kV line terminal addition | City of Stanton, Glasscock County | Install one 3200 A, 138 kV circuit breaker and associated equipment for new terminal to Prairieland Switch. | 2025-03-17 | 2025-09-30 |  |  | 1039619.74 |  |  | 59 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48059 | Kolb Lake POD : Establish 138 kV point of delivery (POD) | City of Lufkin, Angelina County | Establish 138 kV POD | 2024-09-24 | 2025-04-11 |  |  | 1391597.9 |  |  | 99* | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT38757 | Lake Creek Switch: 138 kV line terminal addition and demolish yard | City of Riesel, McLennan County | 138 kV line terminal addition and demolish yard | 2025-06-16 | 2025-09-15 | [5 empty] | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT45109 (R3031) | Mule Deer Switch : Establish 345 kV 3-breaker ring bus point of interconnection (POI) | City of Hereford, Deaf Smith County | Establish 345 kV 3-breaker ring bus (POI) | 2024-11-07 | 2025-12-04 |  |  | 10851810.33 |  |  | 59 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47448 0PT46907 | Holly Spring Sub: Establish 345 kV station | City of Palestine, Anderson County | Establish substation with one transformer and two feeder breakers | 2025-01-29 | 2025-05-15 |  |  | 6333491.14 |  |  | 69 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49402 (R6321) | Mosher Switch: Establish 345 kV 3-breaker ring bus point of interconnection (POI) | City of Ennis, Ellis County | Establish 345 kV 3-breaker ring bus (POI) | 2026-06-01 | 2026-12-03 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49749 (R6258) | Fewell Solar POI: Establish 138 kV 3-breaker ring bus point of interconnection (POI) | Limestone County | Establish 138 kV 3-breaker ring bus (POI) | 2026-06-01 | 2026-12-03 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49802 (R6242) | Phifer Creek Switch: Establish 138 kV 2-breaker ring bus point of interconnection (POI) | City of Groesbeck, Limestone County | Establish 138 kV 2-breaker ring bus (POI) | 2025-10-01 | 2026-04-23 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50044 (R6242) | Mexia Main Station: Upgrade line terminal, carrier equipment, control center extension and bus work to 3200A | City of Mexia, Limestone County | Upgrade line terminal, carrier equipment, control center extension and bus work to 3200A | 2025-05-15 | 2025-12-04 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50060 | Comanche Peak Switch : Replace DFR for 138 kV station | City of Glen Rose, Somervell County | Replace DFR for 138 kV station at Comanche peak | 2024-01-02 | 2024-11-25 | 2024-11-25 |  | 314571.95 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50822 | Orr Branch Sub: Establish 138 kV station with two transformers | City of Dallas, Dallas | Establish 138 kV station with two transformers and switchgear building | 2025-01-14 | 2025-05-15 |  |  | 12875475.8 |  |  | 94 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51250 (R6317) | Badger Switch : Establish 345 kV 3-breaker ring bus point of interconnection (POI) | City of Rogers, Milam County | Establish 345 kV 3-breaker ring bus (POI) | 2025-05-12 | 2025-11-20 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51275 (R6320) | Stranger Switch : Establish 345 kV 3-breaker ring bus point of interconnection (POI) | City of Thornton, Limestone County | Establish 345 kV 3-breaker ring bus (POI) | 2024-10-24 | 2025-05-15 |  |  | 11214376.16 |  |  | 64 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51690 0PT49514 0PT52190 0PT47062 0PT55138 (R8647) | Cattleman Switch: Establish 345/138 kV station | City of Colorado City, Mitchell County | Establish new switch with 14- circuit breaker, 345 kV circuit breakers and two autotransformers | 2024-07-26 | 2025-10-30 |  |  | 70654900 |  |  | 80 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51785 0PT51077 | Upland Sub: Establish substation with one 138 kV transformer and two feeder breakers | City of Midkiff, Upton County | Establish station #1 with one 138 kV transformer and two feeder breakers | 2025-02-21 | 2025-05-15 |  |  | 7794301.05 |  |  | 20 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53528 | Wildwood Sub : Establish substation with one 138 kV transformer and four feeder breakers | City of Irving, Dallas County | Establish substation with one 138 kV transformer and four feeder breakers | 2025-04-04 | 2025-12-15 |  |  | 7405394.75 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53576 0PT53123 | Overland Sub: Establish substation with one 138 kV transformer and two feeder breakers | Reagan County | Establish substation with one 138 kV transformer and two feeder breakers | 2025-01-24 | 2025-06-30 |  |  | 7375608.3 |  |  | 67 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53577 | Savanna Sub: Establish substation with two 138 kV transformer and four feeder breakers | City of Big Lake, Reagan County | Establish substation with two 138 kV transformer and four feeder breakers | 2025-01-14 | 2025-05-15 |  |  | 7919882.78 |  |  | 82 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53578 | Starr Ranch Sub: Install bank #2 with one 138 kV transformer and two feeder breakers | City of Hutto, Williamson County | Install bank #2 with one 138 kV transformer and two feeder breakers | 2025-03-06 | 2025-05-15 |  |  | 2962640.38 |  |  | 32 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53705 (R6258) | Groesbeck Substation: Upgrade 138 kV line terminal bus section | City of Groesbeck, Limestone County | Upgrade 138 kV line terminal bus section | 2026-03-01 | 2026-04-23 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54157 (M3095) | Anna Switch: 138 kV circuit breaker line terminal modifications for point of interconnection (POI) | City of Anna, Collin County | 138 kV circuit breaker line terminal modifications (POI) | 2025-09-10 | 2025-10-30 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54166 | Tyler South Sub: Rebuild Station with two 138 kV transformers and seven feeder breakers | City of Tyler, Smith County | Rebuild Station with two 138 kV transformers and seven feeder breakers | 2025-03-03 | 2025-12-05 |  |  | 7427511.25 |  |  | 22 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54280 | Plano Shiloh Sub : Install bank #4 with one 138 kV transformer and two feeder breakers | City of Plano, Collin County | Install bank #4 with one 138 kV transformer and two feeder breakers | 2024-08-05 | 2024-10-15 | 2024-10-15 |  | 987902.67 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46622 | DFW Southeast Sub : Reconfigure high side bus with breakers and FIDs | City of Irving, Dallas County | Add 138 kV breakers for Euless & Liggett lines and two 138 kV breakers to the tie bus connecting these lines | 2024-10-18 | 2025-05-15 |  |  | 4789383.86 |  |  | 92 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47449 0PT46908 | Mallory Creek Sub: Establish station with one 138 kV transformer and two feeder breakers | City of Paris, Lamar County | Establish substation with one 138 kV transformer and two feeder breakers | 2025-01-16 | 2025-12-31 |  |  | 5391892.58 |  |  | 46 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47776 | Sandow Switch : Upgrade 345/138 kV auto #1 and auto #2 protection panels | Milam County | Upgrade 345/138 kV auto #1 and auto #2 protection panels | 2025-12-01 | 2025-12-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48135 (M3501) | Cedar Elm Switch: Install 345 kV line terminal upgrade point of interconnection (POI) | City of Era, Cooke County | Install 345 kV line terminal in a 4- breaker ring bus arrangement POI | 2024-12-04 | 2025-05-08 |  |  | 5473205.46 |  |  | 82 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48475 (M3006) | Jacksboro Sub: Rebuild 138 kV station with two transformers and four feeder breakers | City of Jacksboro, Jack County | Rebuild 138 kV station with two transformers and four feeder breakers | 2025-03-10 | 2025-07-30 |  |  | 11677504.96 |  |  | 1 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48804 (M4008) | Royse Switch : Establish 345 kV line terminal point of interconnection (POI) | City of Royse City, Rockwall County | Establish 345 kV line terminal POI | 2025-02-06 | 2025-05-08 |  |  | 2985283.39 |  |  | 75 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50378 0PT55082 (M3509) | Long Hollow Switch: Establish 345 kV 6-breaker ring bus point of interconnection (POI) | Jacksboro, Jack County | Establish 345 kV 6-breaker ring bus POI | 2024-10-04 | 2025-06-30 |  |  | 17609261.45 |  |  | 18 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50587 0PT54899 (R6327) | Full House Switch : Establish 138 kV 3-breaker ring bus point of interconnection (POI) | City of Dublin, Erath County | Establish 138 kV 3-breaker ring bus POI | 2024-10-16 | 2025-05-08 |  |  | 6068775.56 |  |  | 65 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50839 (M4347) | DFW C East: 138 kV line terminal upgrades | City of Irving, Dallas County | Upgrade 138 kV circuit breaker line terminals | 2025-01-24 | 2025-12-15 |  |  | 946516.14 |  |  | 16 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51423 (R1754) | Grindstone Switch: Add 138 kV terminal to provide point of interconnection (POI) | City of Oran, Palo Pinto County | Add 138 kV terminal to provide point of interconnection POI | 2025-01-15 | 2025-05-08 |  |  | 2205197.96 |  |  | 86 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51439 (M4015) | Bardberry Switch: Establish 138 kV 4-breaker ring bus point of interconnection (POI) | City of Lancaster, Dallas County | Establish 138 kV 4-breaker ring bus POI | 2024-12-16 | 2025-05-15 |  |  | 6967065.51 |  |  | 38 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51665 (R8732) | Sullivan Tap : Establish 138 kV point of delivery (POD) | City of Mentone, Loving County | Establish 138 kV point of delivery POD | 2025-02-20 | 2025-05-15 |  |  | 2474542.7 |  |  | 10 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52054 (R8738) | Rainwater POD : Establish 138 kV point of Delivery (POD) | Reeves County | Provide a 138 kV point-of-delivery (POD) | 2025-04-21 | 2025-06-20 |  |  | 2774278.42 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52186 (R6230) | Jewett Switch : Upgrade 345 kV line terminal upgrade for the addition of Stranger Switch | City of Jewett, Palestine County | Upgrade 345 kV line terminal upgrade for the addition of Stranger Switch | 2025-04-07 | 2025-05-15 |  |  | 556715.82 |  |  | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52200 (R3032) | Wrangler Switch : Establish 345 kV 3-breaker ring bus point of interconnection (POI) | City of Dickens, Dickens County | Establish 345 kV 3-breaker ring bus POI | 2024-11-12 | 2025-05-08 |  |  | 12116722.79 |  |  | 68 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52395 (R8794) | Hogan POD : Establish 138 kV point of Delivery (POD) | Midland County | Establish 138 kV point of Delivery (POD) | 2025-02-28 | 2025-05-15 |  |  | 3727826.56 |  |  | 12 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52750 0PT53119 0PT53117 0PT53444 (R6243) | Walleye Creek Switch: Establish 345/138 kV station | Milam County | Establish 345/138 kV station | 2025-03-03 | 2025-12-15 |  |  | 62657085.64 |  |  | 1 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52902 0PT52445 (R6295) | Fryers Creek Switch: Establish 138/69 kV station | Temple, Bell | Establish 138/69 kV station | 2024-09-19 | 2025-05-15 |  |  | 23003319.43 |  |  | 75 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53035 (R6258) | Ranchland Switch : Transfer trip addition and line terminal upgrade | City of Fairfield, Freestone County | Transfer trip addition and line terminal upgrade for addition of Frost Creek Switch | 2025-11-03 | 2026-04-23 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53417 | Double Creek Sub : Install bank #3 with one transformer and two feeder breakers | City of Round Rock, Williamson County | Install bank #3 with one transformer and two feeder breakers | 2025-02-24 | 2025-05-15 |  |  | 4795725.73 |  |  | 36 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53501 (R8739) | Calcite POD : Establish 138 kV point of delivery (POD) | Ector County | Establish 138 kV point of delivery POD | 2025-04-07 | 2025-05-15 |  |  | 2725431.3 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53581 0PT42301 0PT57226 | Aqueduct Sub: Establish 138 kV station with one transformer and two feeder breakers | Midland County | Establish 138 kV station with one transformer and two feeder breakers | 2025-01-14 | 2025-06-30 |  |  | 8182061.97 |  |  | 27 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53583 | Hillger Sub (fka: Carterville Ranch Sub): Establish 138 kV station with one transformer and two feeder breakers | City of Big Springs, Howard County | Establish 138 kV station with one transformer and two feeder breakers | 2025-01-24 | 2025-05-15 |  |  | 7109141.29 |  |  | 46 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53585 | Fate Sub: Install one 138 kV transformer and two feeder breakers | City of Rockwall, Rockwall County | Install one 138 kV transformer #2 and two 25 kV feeder breakers. | 2025-02-05 | 2025-05-15 |  |  | 3261483.26 |  |  | 99* | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53589 | Ayers Sub: Install 138 kV transformer and three feeder breakers | City of Fort Worth, Tarrant County | Install 138 kV transformer and three feeder breakers | 2025-04-21 | 2025-10-30 |  |  | 10756415 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53643 0PT53713 0PT54230 | Porterville Sub (fka Haley Ranch Sub): Establish 138 kV station with two transformers and four feeder breakers | City of Odessa, Ector County | Establish 138 kV station with two transformers and four feeder breakers | 2025-03-31 | 2025-06-30 |  |  | 10080778.97 |  |  | 2 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53644 | Devitt Sub: Establish 138 kV station with one transformer and two feeder breakers | City of Fort Worth, Tarrant County | Establish 138 kV station with one transformer and two feeder breakers | 2025-08-04 | 2025-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53646 | Loy Lake Sub: Install one 138 kV transformer and two feeder breakers | City of Denison, Grayson County | Install one 138 kV transformer #2 and two feeder breakers | 2025-02-05 | 2025-05-15 |  |  | 3489376.63 |  |  | 99* | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53648 | Desert Wind Sub: Install one 138 kV transformer and two feeder breakers | City of Garden City, Glasscock County | Install one 138 kV transformer #2 and two feeder breakers | 2025-02-28 | 2025-05-15 |  |  | 3386162.58 |  |  | 80 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54334 | Centerville I-45 Sub: Replace 138 kV capacitor switchers | City of Buffalo, Leon County | Replace two 138 kV switches with capacitor switchers | 2025-01-14 | 2025-05-31 |  |  | 476328.13 |  |  | 68 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54622 | Waterway Sub : Establish two 138 kV transformers and two feeder breakers | Odessa County | Establish two 138 kV transformers and two feeder breakers | 2025-02-19 | 2025-05-15 |  |  | 11492156.41 |  |  | 27 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48516 0PT47301 (R1754) | Grindstone Switch : Rebuild as a 138 kV switching station | City of Oran, Palo Pinto County | Rebuild as a new 138 kV switching station. | 2024-10-15 | 2025-04-01 |  |  | 12439612.26 |  |  | 90 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53852 | Crisp Sub: 138 kV circuit breaker line terminal upgrade | City of Ennis, Ellis County | Upgrade five 138 kV circuit breakers line terminals | 2025-08-01 | 2025-12-15 | [5 empty] | 0 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51118 0PT48160 | Arlington Sub: Rebuild station with four transformers | City of Arlington, Tarrant County | Rebuild existing station as switchgear with four 138 kV transformers | 2025-05-01 | 2026-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53949 (R8704) | Barr Ranch Switch: Install 138 kV circuit breaker line terminal | City of Midland, Midland County | Install 138 kV circuit breaker line terminal | 2025-03-24 | 2025-12-01 |  |  | 1533799.98 |  |  | 32 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51281 (R6318) | Red Hill Switch : Establish 138 kV 3-breaker ring bus point of interconnection (POI) | Hill County | Establish 138 kV 3-breaker ring bus point of interconnection | 2024-10-04 | 2025-05-08 |  |  | 6902492.58 |  |  | 91 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53674 | Lonesome Draw Sub : Install bank #4 with one transformer and two feeder breakers | City of Midkiff, Upton County | Install bank #4 with one transformer and two feeder breakers | 2024-11-05 | 2025-05-15 |  |  | 2884761.3 |  |  | 99* | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52435 (M3125) | Sulphur Springs Switch : Modifications on bus work for the addition of Sandy Ranch Switch | City of Sulphur Springs, Hopkins County | Modifications on bus work for the addition of Sandy Ranch Switch | 2025-03-20 | 2025-05-08 |  |  | 1181002.42 |  |  | 29 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48717 (M4353) | Cypress Waters Switch: Establish 138 kV station | City of Dallas, Dallas County | Rebuild as a new 138 kV switching station. | 2025-02-26 | 2025-12-15 |  |  | 30237077.27 |  |  | 2 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49112 0PT51811 (M3006) | Brummett Sub : Establish with 138 kV dual winding skid mounted transformer and one feeder breaker | City of Jacksboro, Jack County | Establish with 138 kV dual winding skid mounted transformer and one feeder breaker | 2025-06-02 | 2025-09-30 | [5 empty] | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53850 0PT53420 (M4002) | Montfort Switch: Rebuild as a 138 kV switching station | City of Chatfield, Navarro County | Rebuild as a new 138 kV switching station. | 2025-12-01 | 2026-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53642 | Estelle Sub: Establish 138 kV station with one transformer and three feeder breakers | City of Irving, Dallas County | Establish 138 kV station with one transformer and three feeder breakers | 2025-10-01 | 2026-05-15 | [5 empty] | 0 | na | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52991 (R6295) | Temple Sub: Modify station for connection to Fyers Creek Switch | City of Temple, Bell County | Modify station for connection to Fyers Creek Switch | 2025-09-15 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53693 (M4361) | Loop Nine Switch : Install two 138 kV line terminals for two point of deliveries (POD) | City of Lancaster, Dallas County | Install two 138 kV line terminals for two point of deliveries | 2025-02-24 | 2025-05-15 |  |  | 2353687.22 |  |  | 40 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48321 0PT46921 | Rhine Lake Sub : Establish 138 kV station with one transformer and four feeder breakers | City of Van, Van Zandt County | Establish 138 kV station with one transformer and four feeder breakers | 2025-05-05 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54898 (R8812) | Tex Harvey Sub : Upgrade the existing 138 kV capacitor bank | City of Odessa, Midland County | Upgrade the existing 138 kV capacitor bank | 2024-08-28 | 2024-10-18 | 2024-10-18 |  | 671822.91 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53584 | Round Rock Westinghouse Sub: Install 138 kV transformer and two feeder breakers | City of Round Rock, Williamson County | Install 138 kV transformer and two feeder breakers | 2025-03-06 | 2025-12-15 |  |  | 5070762.29 |  |  | 21 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48692 (R8528) | Judkins Sub: 138 kV circuit breaker line terminal upgrade | City of Odessa, Ector County | 138 kV circuit breaker line terminal upgrade | 2025-03-19 | 2025-05-15 |  |  | 498784.5 |  |  | 93 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53090 (M4404) | Richardson East Sub : Replace wave trap on one circuit breaker | City of Richardson, Dallas County | Replace wave trap on one circuit breaker | 2025-04-01 | 2025-04-15 |  |  | 544552.4 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53928 0PT53125 (R8681) | Tredway Switch: Establish 138 kV 9-breaker ring bus switching station | City of Big Springs, Howard County | Establish 138 kV 9-breaker ring bus switching station | 2025-02-06 | 2025-12-15 |  |  | 15067477.55 |  |  | 10 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53791 (R8721) | Morgan Creek Switch: 138 kV station partial demolition and modify relaying for Cattleman Switch | City of Colorado City, Mitchell County | Partial 138 kV station demolition and modify relaying for Cattleman Switch | 2025-04-01 | 2025-05-15 |  |  | 1334821.77 |  |  | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47453 (R6164) | Brownwood Sub: 138 kV circuit breaker line terminal upgrade | City of Brownwood, Brown County | 138 kV circuit breaker line terminal upgrade and remove one autotransformer | 2026-08-31 | 2026-12-20 | [5 empty] | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50823 0PT50256 0PT54430 | Carmelite Substation: Establish station with two transformers and four feeder breakers | City of Stanton, Martin County | Establish station with two transformers and four feeder breakers | 2024-10-26 | 2025-05-15 |  |  | 11144471.85 |  |  | 30 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52357 (R6330) | Olympus Switch : Establish 138 kV 5-breaker ring bus point of interconnection (POI) | City of Kerens, Navarro County | Establish 138 kV 5-breaker ring bus point of interconnection (POI) | 2024-10-05 | 2025-05-08 |  |  | 10255721.89 |  |  | 89 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50699 (R6323) | Dorsett Switch : Establish 345 kV switching station point of interconnection (POI) | City of Henderson, Rusk County | Establish 345 kV switching station point of interconnection | 2025-01-21 | 2025-05-08 |  |  | 11801088.26 |  |  | 53 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50840 (M4347) | DFW D East 1: 138 kV circuit breaker line terminal upgrade | City of Irving, Dallas County | 138 kV circuit breaker line terminal upgrade | 2025-01-14 | 2025-12-15 |  |  | 962876.15 |  |  | 24 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50841 (M4347) | Irving Sub: 138 kV circuit breaker line terminal upgrade | City of Irving, Dallas County | 138 kV circuit breaker line terminal upgrade | 2025-10-13 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51140 (M4357) | DFW D East 2: 138 kV circuit breaker line terminal upgrade | City of Irving, Dallas County | 138 kV circuit breaker line terminal upgrade | 2025-01-17 | 2025-12-15 |  |  | 946516.14 |  |  | 28 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55211 (R6249) | Walnut Springs: Modify station for Eulogy Switch line terminal 138 kV point of interconnection (POI) | City of Walnut Springs, Bosque County | Modify station for Eulogy Switch line terminal 138 kV point of interconnection | 2025-01-02 | 2025-05-14 |  |  | 1142417.66 |  |  | 99* | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54937 (R8733) | Quarry Field Switch: Install two 138 kV line terminals for Riverton Switch | City of Mentone, Loving County | Install two 138 kV line terminals for Riverton Switch | 2025-03-27 | 2025-05-15 |  |  | 1559880.66 |  |  | 23 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52584 (D20231) | Averitt (fka Reiter Switch) : Establish FACTS device | City of Odessa, Ector County | Install a 345kV +350/-350 MVAR Synchronous Condenser device at Reiter Switching Station. | 2025-06-02 | 2027-01-14 |  |  | 176775778.69 |  |  | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52585 0PT52597 0PT54534 (D20231) | Hermleigh (fka Tonkowa Switch) : Establish FACTS device | City of Roscoe, Nolan County | Install two 345kV +175/-175 MVAR Synchronous Condenser devices at Reiter Switching Station. | 2025-04-01 | 2027-01-14 |  |  | 180965544.05 |  |  | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54590 | Leon Switch: 138 kV Bus Panel Upgrade | City of Eastland, Eastland County | Bus Panel Upgrade at 138 kV Leon Switch | 2025-06-15 | 2025-11-14 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47443 | Ireland Sub: Establish substation with two transformers and four feeder breakers | City of Dublin, Erath County | Establish substation with two transformers and four feeder breakers | 2025-07-01 | 2025-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49469 | Beto Sub : Extend 138 kV bus for point of interconnection (POI) | City of Palestine, Anderson County | Extend 138 kV bus for point of interconnection | 2027-04-05 | 2027-05-14 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49653 (R9047) | Yucca Drive Switch: 138 kV circuit breaker line terminal modifications | City of Monahans, County of Ward | Modify two 138 kV circuit breakers line terminals | 2025-04-14 | 2025-04-28 |  |  | 600648.42 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50125 | Bridgeport Sub : Relay upgrade on one feeder breaker for DA | City of Bridgeport, Wise County | Relay upgrade on one feeder breaker for DA | 2024-12-02 | 2025-05-31 |  |  | 796529.36 |  |  | 99* | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52204 0PT44174 (R6276) | Possum Trot Switch: Establish 345 kV breaker-and-a-half station | City of Riesel, McLennan County | Establish 345 kV breaker-and-a-half station | 2025-06-16 | 2025-12-15 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53439 0PT48503 0PT53482 0PT53619 (R8629) | Reiter Switch: Establish 138 kV station with two autotransformers | City of Odessa, Ector County | Establish 138 kV station with two autotransformers | 2025-01-07 | 2025-12-01 |  |  | 47467679.22 |  |  | 2 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53594 | Palestine North Sub: Establish station with one transformer and two feeder breakers | City of Palestine, Anderson County | Establish station with one transformer and two feeder breakers | 2025-07-14 | 2025-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53636 | Waco North Sub: Rebuild station with two transformers and six feeder breakers | City of Waco, McLennan County | Rebuild station with two transformers and six feeder breakers | 2025-06-01 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53687 (R8731) | Redcorn TAP : Establish 138 kV point of delivery (POD) | City of Midland, Midland County | Establish 138 kV point of delivery POD | 2025-04-03 | 2026-05-15 |  |  | 1762309.52 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54858 0PT53613 0PT51263 (M3301) | Gunter Switch : Establish switchyard with one autotransformer | City of Gunter, Gunter County | Establish switchyard with one autotransformer | 2025-02-14 | 2025-12-15 |  |  | 53938691.89 |  |  | 5 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55772 | Lake Creek Switch : Regasket Auto #1 | McLennan County | Re-gasket Auto # 1 at Lake Creek Switch | 2025-04-01 | 2025-12-01 |  |  | 341950 |  |  | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55726 | Lindley Ranch POD 138 kV: Switch Replacement | City of Mentone, Loving County | Lindley Ranch POD 138 kV: Switch replacement at Lindley Ranch POD 138 kV. | 2025-09-01 | 2025-12-15 |  |  | 215838 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47444 0PT46930 | Seven Acres Sub: Establish station with one 138 kV transformer and two feeder breakers | City of Jewett, Leon County | Establish station with one 138 kV transformer and two feeder breakers | 2025-05-26 | 2025-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48383 (R6203) | Hutto Switch : 138 kV circuit breaker line terminal upgrade | City of Hutto, Williamson County | Upgrade two 138 kV circuit breakers line terminals | 2026-03-03 | 2026-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51605 (M5261) | Eagle Mountain Switch : Upgrade line terminals to Base Camp Switch | City of Fort Worth, Tarrant County | Upgrade two 138 kV line terminals to Base Camp Switch | 2025-04-14 | 2025-10-15 |  |  | 758788.36 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52746 0PT48911 (R6094) | Foggle Switch : Establish 138 kV ring bus | City of Athens, Henderson County | Establish 138 kV ring bus and install four circuit breakers | 2025-06-17 | 2025-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52993 (R6295) | Taylor Switch: Modify relaying for Boggy Creek Switch | City of Taylor, Williamson County | Modify relaying as part of establishing Boggy Creek Switch. | 2025-07-15 | 2025-08-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53493 (R8730) | Benge Tap: Establish 138 KV point of delivery (POD) | City of Midkiff, Midland County | Establish POD on the Salt Flat Road Switch to Barr Ranch Switch 138 kV line | 2025-09-15 | 2025-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53593 0PT53378 | Little Brown Sub: Establish 138 kV station with two transformers and six feeder breakers | City of Big Springs, Howard County | Establish 138 kV station with two transformers and six feeder breakers | 2025-07-01 | 2025-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53599 0PT50579 | Hudson Sub: Rebuild station with two 138 kV transformers and seven feeder breakers | City of Lufkin, Angelina County | Rebuild station with two 138 kV transformers and seven feeder breakers | 2025-06-02 | 2025-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53677 0PT53615 0PT53616 0PT49544 (M4369) | Wilmer Switch: Rebuild as a 345/138 kV switching station | City of Lancaster, Dallas County | Rebuild as a 345/138 kV switching station | 2025-03-17 | 2026-03-02 | [5 empty] | 2 | 138 | 345 | na | na | na | na | na | na | na | 25.83(a)(3) | The project will be moved to the CCN section and will not be included in this section in next month's report.
0PT53793 (R8721) | Range Rider Switch: Establish 138 kV switching station | Colorado City, Mitchell County | Establish 138 kV switching station | 2025-05-19 | 2025-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53947 (R8704) | Wellbore Switch: Establish 138 kV switching station | City of Midland, Midland County | Establish 138 kV switching station | 2025-06-02 | 2025-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54149 (R6361) | Richland Chambers Switch : Establish a 345 kV point of interconnection POI | City of Fairfield, Young County | Establish a 345 kV point of interconnection | 2025-03-13 | 2025-10-30 |  |  | 6723446.78 |  |  | 20 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54447 (M4128) | Southerland Sub: 138 kV line terminal upgrade | City of Dallas, Dallas County | 138 kV circuit breaker line terminal upgrade | 2025-09-18 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54786 | Nokomis Sub: Establish station with two 138 kV transformers and four feeder breakers | City of Lancaster, Dallas County | Establish station with two 138 kV transformers and four feeder breakers | 2025-07-21 | 2025-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55363 | Temple Elm Creek Switch: Replace nine overdutied breakers | City of Temple, Bell County | Replace nine overdutied breakers | 2025-09-15 | 2025-12-31 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51996 | Falcon Seaboard Switch: Modify relaying for Ranger Camp Switch | City of Big Springs, Howard County | Modify relaying as part of establishing Ranger Camp Switch. | 2025-02-03 | 2025-02-19 | 2025-02-19 |  | 351520.38 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT44116 0PT54960 (R8809) | Dusty Road Switch: Establish 345 kV 3-breaker ring bus point-of-interconnection (POI) | City of Haskell, Haskell County | Establish 345 kV 3-breaker ring bus POI | 2025-07-28 | 2025-12-04 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49109 0PT49371 (M3006) | Peanut Sub: Rebuild 69 kV sub with single skid | City of Jacksboro, Jack County | Rebuild 69 kV sub with single skid | 2025-06-02 | 2025-12-15 | [5 empty] | 0 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49146 0PT49485 | Hobson Lake Sub: Rebuild Station with two transformers and four feeder breakers | City of Cameron, Milam County | Rebuild Station with two transformers and four feeder breakers | 2025-05-05 | 2025-12-15 | [5 empty] | 0 | 69 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50225 (M3233) | Bells Sub : Rebuild existing substation to rural substation skid | City of Bells, Grayson County | Bells Sub : Rebuild existing substation to rural substation skid | 2025-06-16 | 2025-12-15 | [5 empty] | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52350 (M5148) | Hicks Switch: Modify relaying for Ramhorn Hill Switch | City of Fort Worth, Tarrant County | Modify relaying for Ramhorn Hill Switch | 2025-07-18 | 2025-12-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53685 (M4372) | Ferris Sub: Convert station to 138 kV operation and install one autotransformer | City of Ferris, Ellis County | Convert station to 138 kV operation and install one autotransformer | 2025-06-16 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54019 | Meadowpark Sub: Install transformer #2 and feeder for Distributed Energy Storage Resource (DESR) | City of North Richland Hills, Tarrant County | Install transformer #2 and new feeder for Distributed Energy Storage Resource | 2025-06-02 | 2025-11-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54271 0PT54262 | Killeen Sub: Rebuild station with two transformers and seven feeder breakers | City of Killeen, Bell County | Rebuild station with two transformers and seven feeder breakers | 2025-06-01 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54445 (M4128) | Industrial Boulevard Switch: Upgrade three 138 kV circuit breakers and line terminals | City of Dallas, Dallas County | Industrial Boulevard Switch: Upgrade three 138 kV circuit breakers and line terminals | 2025-09-30 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54755 (R8681) | SL Brown Sub: Reconfigure station | City of Ackerly, Martin County | Reconfigure substation as a line tapped capacitor bank. | 2025-11-03 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55381 | Dollarhide Sub: Install two transformers and four feeder breakers | City of Kermit, Winkler County | Install two transformers and four feeder breakers | 2025-07-01 | 2025-12-01 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55834 | Britton Road Sub : Replace one 345 kV circuit breaker | City of Mansfield, Tarrant County | Replace one 345 kV circuit breaker | 2025-09-05 | 2025-12-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55839 | Odessa EHV Switch : Replace four 345 kV circuit breakers | City of Odessa, Odessa County | Replace four 345 kV circuit breakers | 2025-09-01 | 2025-12-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55840 | Paris Switch : Replace one 345 kV circuit breaker | City of Paris, Lamar County | Replace one 345 kV circuit breaker | 2026-02-03 | 2026-05-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55843 | Valley Switch : Replace one 345 kV circuit breaker | City of Savoy, Fannin County | Replace one 345 kV circuit breaker | 2025-11-01 | 2025-12-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52818 0PT53618 (R6197) | Temple Switch: Rebuild 345/138 kV yard with two autotransformers | City of Temple, Bell County | Rebuild 345/138 kV yard | 2025-01-24 | 2026-05-15 |  |  | 80395727.13 |  |  | 5 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55844 | SL Ringo Sub : Ring bus expansion | City of Big Lake, Reagan County | Ring bus expansion | 2025-05-15 | 2025-11-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | The project will be moved to the CCN section and will not be included in this section in next month's report.
0PT51899 | Twin Star Sub : Replace 138 kV two circuit breakers | City of Plano, Collin County | Replace 138 kV two circuit breakers | 2025-04-01 | 2025-05-31 |  |  | 557373.36 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52000 (R3024) | Sun Switch: Modify relaying for Ranger Camp Switch | City of Snyder, Scurry County | Modify relaying for Ranger Camp Switch | 2025-03-25 | 2025-04-04 |  |  | 272240.05 |  |  | 99* | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55823 | Lake Creek Switch : Regasket Auto #2 | City of Waco, McLennan County | Regasket Auto Transformer #2 | 2025-05-01 | 2025-12-31 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT47438 (R6203) | Midnight Sub: Install second deadend for 138 kV double tap configuration | City of Georgetown, Williamson County | Install second deadend for 138 kV double tap configuration | 2025-09-15 | 2025-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48519 (R1754) | Oran Switch: Partially demo 138 kV and 69 kV yards | City of Oran, Palo Pinto County | Partially demo 138 kV and 69 kV yards | 2025-03-26 | 2025-05-15 |  |  | 1599711.39 |  |  | 3 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50227 | Hext Sub: Rebuild existing substation to rural substation skid | City of Hext, Menard County | Rebuild existing substation to rural substation skid | 2025-03-12 | 2025-06-15 |  |  | 2418551.72 |  |  | 1 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50228 | Nipak Sub: Rebuild existing substation to rural substation skid | City of Kerens, Navarro County | Rebuild existing station as rural skid design with one 138 kV transformer and two feeder breakers | 2025-09-01 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51689 0PT53614 0PT53617 0PT48587 0PT51631 (R8661) | Prong Moss Switch: Establish 345 kV switching station | City of Big Spring, Howard County | Establish a new switching station with a 345 kV breaker | 2025-03-28 | 2025-12-15 |  |  | 41532330.36 |  |  | 4 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51815 | Cheyenne Sub: Replace failed transformer #1 | City of Kermit, Winkler County | Replace failed 138 kV transformer #1. | 2023-09-29 | 2024-01-30 | 01/30/2024 |  | 4303146.31 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(d)
0PT52524 | Murdock Sub : Replace failed transformer #2 | City of Dallas, Dallas County | Replace failed 138 kV transformer #2. | 2023-09-01 | 2024-05-01 | 05/01/2024 |  | 2974143.9 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(d)
0PT52677 (M4081) | Seagoville Switch: 138 kV line terminal upgrade | City of Seagoville, Dallas County | Upgrade 138 kV line terminal | 2025-03-31 | 2025-12-15 |  |  | 485266.99 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52679 (M4081) | Seagoville Sub: 138 kV line terminal upgrade | City of Seagoville, Dallas County | Upgrade 138 kV line terminal | 2025-03-31 | 2025-12-15 |  |  | 746342.02 |  |  | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52806 | Benbrook Switch: Replace failed auto transformer #2 | City of Forth Worth, Tarrant County | Replace failed auto transformer #2 | 2024-01-19 | 2024-02-01 | 2024-02-01 |  | 2805946.54 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(d)
0PT53582 | Salado South Sub: Install one 138 kV transformer and three feeder breakers | City of Salado, Bell County | Install one 138 kV transformer and three feeder breakers | 2025-05-26 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53638 0PT53460 | New Mabank Sub: Establish station with two 138 kV transformers and four feeder breakers | Mabank City, Henderson County | Establish station with two 138 kV transformers and four feeder breakers | 2025-05-15 | 2025-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53641 0PT49640 | Tudor Sub: Establish station with one 138 kV transformer and two feeder breakers | City of Desdemona, Eastland County | Establish station with one 138 kV transformer and two feeder breakers | 2025-07-15 | 2025-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53649 | Ector Harper Sub: Install one 138 kV transformer and two feeder breakers | City of Odessa, Ector County | Install one 138 kV transformer and two feeder breakers | 2025-05-19 | 2025-09-01 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54385 | Powell Sub : Install one feeder on settlement only distribution generator (SODG) | City of Kerens, Navarro County | Install one feeder on settlement only distribution generator (SODG) | 2025-02-02 | 2025-04-15 |  |  | 345297.83 |  |  | 99* | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55503 0PT53407 | Stripe Sub : Establish station with one 138 kV transformer and two feeder breakers | City of Roscoe, Nolan County | Establish station with one 138 kV transformer and two feeder breakers | 2025-06-02 | 2025-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55250 | Jewett Switch : Re-gasket 345/138 kV Auto #3 | Leon County | Re-gasket 345/138 kV Auto #3 at Jewett Switch | 2025-04-01 | 2025-06-13 |  |  | 382031.38 |  |  | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT56126 (R8855) | Lindley Ranch POD: Install FID on each point of delivery | City of Mentone, Loving County | Install two switches and two FIDs on each POD | 2025-09-15 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT56416 | Fish Creek Switch: Replace 138 kV circuit breaker | City of Grand Priarie, Dallas County | Replace 138 kV circuit breaker | 2025-03-25 | 2025-06-15 |  |  | 384372.94 |  |  | 1 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT56420 | Canton Switch: Replace two 138 kV circuit breakers | City of Grand Saline, Van Zandt County | Replace two 138 kV circuit breakers | 2025-09-15 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT56422 | Plano Arco Sub: Replace 138 kV on two circuit breakers | City of Plano, Collin County | Replace 138 kV on two circuit breakers | 2025-04-28 | 2025-06-15 |  |  | 599815.71 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT41446 (R8832) | Brushy Canyon POD: Establish 138 kV Point of Delivery BP L48 | City of Angeles, Reeves County | Establish 138 kV POD | 2025-10-10 | 2025-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46387 (M4213) | East Levee Switch: Upgrade Industrial Blvd Switch Equipment to 3200 A | City of Dallas, Dallas County | Upgrade all line terminal and associated equipment to 3200 A. | 2026-01-05 | 2026-05-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51449 | Minerva Switch : Modifications for the cut-in of Cannon Switch | City Rockdale, Milam County | Minerva Substation : Modifications for the cut-in of Cannon Switch | 2025-08-15 | 2025-11-13 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51607 | Matilda Sub : Replace two transformers, and associated low voltage switchgear | City of Dallas, Dallas County | Replace two transformers, and associated low voltage switchgear | 2025-04-02 | 2025-12-01 |  |  | 12328083.91 |  |  |  | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51812 | Stone Creek Switch : Install SEL-ICON multiplexer | City of Sherman, Grayson County | Install SEL-ICON multiplexer | 2025-04-15 | 2025-05-31 |  |  | 276460.54 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51813 | Valley 138 kV Switch : Install SEL-ICON multiplexer | City of Savoy, Fannin County | Valley 138 kV Switch : Install SEL-ICON multiplexer | 2025-04-15 | 2025-05-31 |  |  | 437822.27 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51814 | Haggerty Switch : Establish SEL-ICON ring node | City of Sherman, Grayson County | Establish SEL-ICON ring node | 2025-04-15 | 2025-05-31 |  |  | 286583.57 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52348 (M5146) | Roanoke Switch: Modify Relaying for Dunham Switch | City of Roanoke, Denton County | Modify relaying for Dunham Switch. | 2025-09-15 | 2025-12-15 | [6 empty] | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53134 (R6276) | Rattlesnake Road Switch: Modify relaying for Possum Trot Switch (formerly Lake Creek Switch) | City of Riesel, McLennan County | Modify relaying for Possum Trot Switch (formerly Lake Creek Switch) | 2025-11-04 | 2025-12-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53159 (M5261) | Parker Switch: Modify relaying for Base Camp Switch | City of Weatherford, Parker County | Modify relaying for Base Camp Switch | 2025-06-30 | 2026-05-15 | [6 empty] | 138 | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53580 | Stallion Sub: Establish station with one 138 kV transformer & two feeder breakers | City of Temple, Bell County | Establish station with one 138 kV transformer & two feeder breakers | 2025-07-15 | 2025-12-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53591 | Newton Branch Sub: Install one 138 kV transformer and two feeder breakers | City of Midlothian, Ellis County | Install one 138 kV transformer and two feeder breakers | 2025-08-18 | 2025-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53600 0PT53511 | Jennings Lake Sub: Establish station with two 138 kV transformers and four feeder breakers | City of Sulphur Springs, Hopkins County | Establish station with two 138 kV transformers and four feeder breake | 2025-05-12 | 2025-12-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53637 0PT53517 | Lindale Sub: Rebuild station with two transformers and six feeder breakers | City of Lindale, Smith County | Rebuild station with two transformers and six feeder breakers | 2025-05-01 | 2025-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53639 0PT53770 | Mine Creek Sub: Establish station with one 138 kV transformer and two feeder breakers | City of Athens, Henderson County | Establish station with one 138 kV transformer and two feeder breakers | 2025-07-07 | 2026-12-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54324 | Keene Sub: Rebuild station with two 138 kV transformers and three feeder breakers | City of Cleburne, Johnson County | Rebuild station with two 138 kV transformers and three feeder breakers | 2025-07-28 | 2025-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54533 0PT53868 | Hardin Sub: Establish station with two 138 kV transformers and eight feeder breakers. | City of Belton, Bell County | Establish station with two 138 kV transformers and eight feeder breakers. | 2025-06-09 | 2025-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54961 (R6293) | Venus Switch: Upgrade two 345 kV circuit breakers and line terminals | City of Venus, Ellis County | Upgrade two 345 kV circuit breakers and line terminals | 2025-08-22 | 2026-05-15 | [6 empty] | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55081 (M4081) | Southside Filtration East Tap : Upgrade terminal | City of Wilmer, Dallas County | Upgrade terminal by installing three new 138 kV switches | 2025-08-29 | 2025-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55095 (R8799) | Blue Mountain Switch : Install 138 kV three stage capacitor banks | City of Wink, Winkler County | Install 138 kV three stage capacitor banks | 2025-08-04 | 2025-12-15 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55334 | Mesquite East Switch : Replace two 138 kV overdutied circuit breakers. | City of Mesquite, Dallas County | Replace two 138 kV overdutied circuit breakers. | 2025-08-14 | 2025-12-31 | [6 empty] | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55555 | Coalbed POD: Establish 138 kV Point of Delivery | City of Odessa, Ector County | Establish 138 kV POD | 2025-09-15 | 2025-12-15 | [6 empty] | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55678 | Desoto Pleasant Run Sub: Rebuild station with three transformers and feeder breakers | City of Desoto, Dallas County | Rebuild station with three transformers and feeder breakers | 2025-04-14 | 2025-12-30 |  |  | 15059040.77 |  |  |  | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT42529 0PT54519 (R8560) | Coody Crossing Switch: Establish 345 kV switching station point of interconnection | City of Graham, Throckmorton County | Establish 345 kV switching station POI | 2025-08-18 | 2026-05-14 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50868 | Lawther Drive Sub : Replace two 138 kV switches | City of Dallas, Dallas County | Replace two 138 kV switches | 2024-04-03 | 2024-06-03 | 2024-06-03 |  | 315235.3 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(d)
0PT51789 0PT51764 (R5343) | Cade Branch POD : Establish 138 kV point of delivery | City of Fort Worth, Tarrant County | Establish 138 kV point of delivery | 2025-06-02 | 2025-12-30 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53136 (R6276) | Tradinghouse Switch: Modify relaying for Lake Creek Switch | City of Waco, McLennan County | Modify relaying for Lake Creek Switch | 2025-08-13 | 2025-12-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53647 | Diboll Sub: Replace transformers #1 and #2 | City of Lufkin, Angelina County | Replace transformers #1 and #2 | 2025-07-14 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53650 | Reindeer Sub: Install one 138 kV transformer and two feeder breakers | City of Lancaster, Dallas County | Install one 138 kV transformer and two feeder breakers | 2025-08-04 | 2025-12-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54036 | Sandow Switch : Modifications to establish Walleye Creek Switch | City of Thorndale, Milam County | Modifications to establish Walleye Creek Switch | 2025-08-04 | 2025-12-15 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54543 (M3310) | Plano West Sub: Establish bus #3 and #4 to provide two 138 kV points of delivery | City of Richardson, Collin County | Establish bus #3 and #4 to provide two 138 kV points of delivery | 2025-06-30 | 2025-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54600 0PT54237 (M4010) | Squirrel Creek POI: Establish 138 kV point of interconnection | City of Howe, Grayson County | Establish 138 kV point of interconnection | 2025-07-07 | 2025-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT57053 | Knapp Sub: Install DESR on one feeder breaker | City of Snyder, Scurry County | Install Distributed Energy Storage Resource (DESR) on one feeder breaker | 2025-03-19 | 2025-04-15 |  |  | 516181.58 |  |  | 99* | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54689 | Killeen Switch :Upgrade MDAR and PVD relays with SEL microprocessor relay panels. | City of Killeen, Bell County | Upgrade MDAR and PVD relays with SEL microprocessor relay panels. | 2025-06-01 | 2025-12-31 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54700 | Henderson Ranch Switch : Upgrade PVD bus diff relays to SEL microprocessor relaying. | City of Bridgeport, Jack County | Upgrade PVD bus diff relays to SEL microprocessor relaying. | 2025-09-15 | 2025-12-31 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54791 0PT53802 (M5009) | Hillwood Switch: Establish two 138 kV points of delivery | City of Fort Worth, Tarrant County | Establish two 138 kV points of delivery | 2025-08-04 | 2025-12-01 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55329 | South Oak Cliff Sub : Replace failed transformer #1 | City of Dallas, Dallas County | Replace failed transformer #1 | 2024-06-10 | 2024-10-01 | 2024-10-01 |  | 1439106.9 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(d)
0PT57162 | Progress Park Switch : Install ICON Multiplexer | City of Sherman, Grayson County | Install SEL-ICON ring node | 2025-04-23 | 2025-05-31 |  |  | 292043.91 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55685 | Twin Oak Switch : Replace line terminator insulators | City of Franklin, Robertson County | Replace line terminator insulators | 2025-04-21 | 2025-06-30 |  |  | 1084498.19 |  |  | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46495 (M4213) | West Network Sub: Replace station deadend structures | City of Dallas, Dallas County | Replace station deadend structures | 2025-08-15 | 2026-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52893 (R6375) | Baines Creek Switch: Establish 138 kV station point of interconnection | City of Mexia, Limestone County | Establish 138 kV station for POI | 2025-09-19 | 2026-04-23 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53474 (R6372) | Quaid Switch: Establish 138 kV station point of interconnection | Milam County | Establish 138 kV station for POI | 2025-09-15 | 2026-05-07 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53586 0PT53187 | Little Sale Ranch Sub: Establish station with one 138 kV transformer and two feeder breakers | City of Stanton, Martin County | Establish station with one 138 kV transformer and two feeder breakers | 2025-06-16 | 05/15/2026 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54572 (R6369) | Bynum Switch: Establish 345 kV station point of interconnection | City of Bynum, Hill County | Establish 138 kV station for POI | 2025-09-12 | 2026-05-07 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54780 (R6276) | Lake Creek Switch: Modify station for new Possum Trot Switch 345 kV lines | City of Riesel, McLennan County | Modify station for new Possum Trot Switch 345 kV lines | 2026-01-07 | 2026-05-01 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54963 | Files Valley Switch: 345 kV line terminal upgrade | City of Itasca, Ellis County | 345 kV line terminal upgrade | 2025-09-23 | 5/15/2026 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55368 | Odessa Switch: Replace overdutied breakers | City of Odessa, Odessa County | Replace overdutied breakers | 2025-09-15 | 2025-12-01 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55727 (R6330) | Montfort Switch: Modify relaying for new Olympus Switch line terminal | City of Chatfield, Navarro County | Modify relaying for new Olympus Switch line terminal | 2025-04-07 | 2025-05-08 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3) | The project has been determined to no longer meet the reporting requirements, and it will be removed from next month's report.
0PT55944 | Upland Sub: Install bank #3 and #4 with two transformers and two feeder breakers | City of Midkiff, Upton County | Install bank #3 and #4 with two transformers and two feeder breakers | 2025-09-15 | 2025-12-01 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT55974 | Charles Hall Substation: Establish station with two 138 kV transformers and four 25 kV feeders | City of Rockdale, Milam County | Establish station with two 138 kV transformers and four 25 kV feeders | 2025-06-02 | 2025-12-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT57025 | Millers Ferry Road Sub: Install one feeder on settlement only distribution generator (SODG) | City of Wilmer, Dallas County | Install one feeder on settlement only distribution generator (SODG) | 2025-09-15 | 2025-11-17 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT57026 | Ten Mile Sub: Install one feeder on settlement only distribution generator (SODG) | City of Lancaster, Dallas County | Install one feeder on settlement only distribution generator (SODG) | 2025-10-15 | 2025-11-17 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50016 (R3309) | Cloud POD : Establish a 138 kV point of delivery | City of Plano, Collin County | Establish a 138 kV POD | 2025-09-15 | 12/31/2025 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53592 0PT51214 0PT54569 | Rocky Springs Sub: Establish station with one 138 kV transformer and two 15 kV feeder breakers | City of Lufkin, Angelina County | Establish station with one 138 kV transformer and two 15 kV feeder breakers, one 15 kV bus tie breaker, and three 138 kV sectionalizing switches. | 2025-07-01 | 12/15/2025 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54165 0PT54236 | Richland Springs: Rebuild station with two transformers and three feeder breakers | City of Richland Springs, San Saba County | Rebuild station with two transformers and three feeder breakers | 2025-08-11 | 12/15/2025 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT56893 | China Grove Switch: Install one feeder on settlement only distribution generator (SODG) | City of Colorado City, Mitchell County | Install one feeder on settlement only distribution generator (SODG) | 2025-04-25 | 11/14/2025 |  |  | 486145 |  |  | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT56832 | Mexia Main: Substation upgrades | City Of Mexia, Limestone County | Substation upgrades | 2025-07-09 | 10/31/2025 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53684 (M4371) | Lavender Switch: Upgrade two 138 kV circuit breaker line terminal | City of Wilmer, Dallas County | Upgrade two 138 kV circuit breaker line terminal | 2025-09-16 | 12/15/2025 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53925 | Sulphur Springs Switch : Replace three reactors at breaker R1 due to failure and age | City of Sulphur Springs, Hopkins County | Replace three reactors at breaker R1 due to failure and age | 04/01/2024 | 10/01/2024 | 10/01/2024 |  | 869798.2 |  |  | 100 | 345 | na | na | na | na | na | na | na | na | 25.83(d)
0PT54788 | Blackland Switch : Replace one failed cap bank live tank breaker with a circuit switcher (FID) | City of Royse, Rockwall County | Replace one failed cap bank live tank breaker with a circuit switcher (FID) | 2024-07-31 | 12/02/2024 | 12/02/2024 |  | 346965 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(d)
0PT55377 | Fossil Creek Sub : Replace failed transformer | City of Forth Worth, Tarrant County | Replace failed transformer | 06/10/2024 | 12/01/2024 | 12/01/2024 |  | 2364407 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(d)
0PT55820 | Burleson Sub : Replace existing ground grid | City of Burleson, Tarrant County | Replace existing ground grid | 2024-08-26 | 12/13/2024 | 12/13/2024 |  | 720142 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(d)
0PT56707 | Mistletoe Heights Sub : Relace one failed transformer | City of Fort Worth, Tarrant County | Relace one failed transformer | 10/25/2024 | 12/18/2024 | 12/18/2024 |  | 1172376 |  |  | 100 | 138 | na | na | na | na | na | na | na | na | 25.83(d)
0PT57388 | Sandow Switch : Regasket Autotransformer #1 | Milam County | Re-gasketing Auto Transformer #1 at Sandow Switch. | 2025-10-01 | 2025-11-28 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT56546 | Jacksonville West Sub : Replace failed oil containment and install secondary containment | City of Jacksonville, Cherokee County | Replace failed oil containment and install secondary containment | 2024-10-29 | 2025-12-28 | 2025-12-28 |  | 573829.02 |  |  | 100 | na | na | na | na | na | na | na | na | na | 25.83(d)
0PT46108 (R6094) | Athens Switch : Upgrade circuit breaker to terminal to 2000 A | City of Athens, Henderson County | Upgrade circuit breaker to terminal to 2000 A | 2025-09-26 | 01/30/2026 | [5 empty] | 0 | 69 | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT50112 0PT47669 (M3002) | Possum Kingdom: Establish new distribution substation | City of Breckenridge, Stephens County | Establish new distribution substation utilizing a skid mounted substation | 2025-09-01 | 11/15/2025 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51898 | Richardson East Sub : Replace 138 kV circuit breaker | City of Richardson, Dallas County | Replace 138 kV circuit breaker | 2025-09-15 | 12/15/2025 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53601 | Moss Switch: Replace one transformer with 138 kV and install one feeder breaker | City of Odessa, Ector County | Replace one transformer with 138 kV and install one feeder breaker | 2025-08-01 | 12/15/2025 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53645 | Mason Sub: Replace transformer #3 | City of Pecos, Reeves County | Replace transformer #3 | 2025-09-15 | 12/15/2025 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53678 (M4369) | Watermill Switch: Install two 345 kV line terminals | City of Lancaster, Dallas County | Install two 345 kV line terminals | 10/01/2025 | 12/15/2025 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53948 0PT56961 (R8704) | Salt Flat Road Sub: Reconfigure station for connection to Wellbore Switch | City of Midland, Midland County | Reconfigure station for connection to Wellbore Switch | 2025-09-01 | 12/01/2025 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54162 | Decordova Dam Sub: Replace transformers #1 and #2 | City of Granbury, Hood County | Replace transformers #1 and #2 | 2025-09-15 | 12/15/2025 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54389 (M3040) | Token POD : Establish 138 kV point of delivery (POD) | City of Plano, Collin County | Establish 138 kV (POD) | 09/15/2025 | 12/31/2025 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54936 (R8733) | Riverton Switch: Install one 138 kV line terminal | City of Orla, Reeves County | Install one 138 kV line terminal | 2025-09-16 | 12/15/2025 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT57158 | Harry Hines Substation- Install bank #2 with one 138 kV transformer and three feeder breakers | City of Dallas, Dallas County | Install bank #2 with one 138 kV transformer and three feeder breakers | 2025-08-15 | 05/15/2026 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT58221 | Herman Sub: Rebuild station with two 138 kV transformers and six feeder breakers | City of Sherman, Grayson County | Establish station with two 138 kV transformers and six feeder breakers | 2025-07-21 | 12/15/2025 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT56824 (M5013) | Cattle Creek POI: Establish 138 kV point of interconnection (POI) | City of Burleson, Johnson County | Establish 138 kV (POI) | 2025-06-30 | 12/15/2025 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT46679 (R6172) | Peppervine Switch: Install 138 kV Line Terminal | City of Waco, McLennan County | Install one 138 kV line terminal to Launch Pad Switch. | 2025-11-14 | 12/15/2025 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT57772 (M5343) | Iron Horse Tap: Establish 138 kV tap | City of Fort Woth, Tarrant County | Establish 138 kV tap | 08/25/2025 | 11/15/2025 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT57332 | Navarro Communication Hut: Add UFLS for Melton Branch point of delivery (POD) | City of Navarro, Navarro County | Add UFLS for Melton Branch (POD) | 2025-05-01 | 05/15/2025 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT48062 (R6094) | Forest Grove Switch : Install 138 kV relaying to Foggle Switch | City of Athens, Henderson County | Install 138 kV relaying to Foggle Switch | 2025-08-15 | 12/15/2025 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT51019 (R6371) | Notus Switch: Establish 345 kV 3-breaker ring-bus point of interconnection (POI) | City of Navarro, Navarro County | Establish 345 kV 3- breaker ring-bus POI | 2025-11-03 | 2026-05-07 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT52747 (R6094) | Elkton Switch : Modify relaying for Foggle Switch | City of Tyler, Smith County | Modify relaying for Foggle Switch | 2025-08-01 | 09/15/2025 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53064 (R6364) | Pathfinder Switch : Establish 3 breaker ring bus station for point of interconnection (POI) | City of Teague, Freestone County | Establish 3-breaker ring bus station for (POI) | 2025-10-15 | 2026-04-09 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53598 0PT53067 0PT56557 | Geller Sub: Establish station with one transformer | City of Dallas, Dallas County | Establish station with one transformer and two feeder breakers | 2025-11-03 | 2026-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT53944 (M3241) | Ironwood Switch: Establish station to provide two 345 kV points of delivery (POD) | City of Midlothian, Ellis County | Establish station to provide two 345 kV (POD) | 2025-11-17 | 2026-05-15 | [5 empty] | 0 | na | 345 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54163 0PT53509 | Fink Sub: Replace two transformers and install one feeder breaker | City of Pottsboro, Grayson County | Replace two transformers and install one feeder breaker | 2025-08-18 | 12/15/2025 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54164 0PT53382 | Hanby Substation: Rebuild station with three transformers and twelve feeder breakers | City of Mesquite, Dallas County | Rebuild station with three transformers and twelve feeder breakers | 2025-11-28 | 2026-05-15 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
(M4353) | Carrollton Northwest Switch: Modify relaying for Cypress Waters Switch | City of Dallas, Dallas County | Modify relaying for Cypress Waters Switch | 2025-06-20 | 12/15/2025 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT54892 | Hackberry Switch: Modify relaying for Cypress Waters Switch | City of Irving, Dallas County | Modify Relaying for Cypress Waters Switch | 2025-08-15 | 12/15/2025 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT57401 | Eberhardt Sub: Install one feeder on settlement only distribution generator (SODG) | City of Temple, Bell County | Install one feeder on settlement only distribution generator (SODG) | 2025-09-18 | 11/17/2025 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT57541 | Renner Switch : Replace six 138 kV circuit breakers | City of Plano, Collin County | Replace six 138 kV circuit breakers | 2025-09-16 | 12/15/2025 | [5 empty] | 0 | 345 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT57604 | Bryant Irvin Sub : Replace 138 kV circuit breaker | City of Fort Worth, Tarrant County | Replace 138 kV circuit breaker | 2025-09-15 | 12/15/2025 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT57605 | Currie Sub : Replace 138 kV circuit breaker | City of Fort Worth, Tarrant County | Replace 138 kV circuit breaker | 2025-10-06 | 12/15/2025 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT57606 | Mansfield Sub : Replace 138 kV circuit breaker | City of Mansfield, Tarrant County | Replace 138 kV circuit breaker | 2025-09-15 | 12/15/2025 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
0PT49141 (M5178) | DFW Northeast Sub: Establish Station | City of Dallas, Dallas County | Establish station with five 138 kV circuit breakers, two transformers and four feeder breakers. | 2025-07-25 | 2026-05-15 | [5 empty] | 0 | na | 138 | na | na | na | na | na | na | na | 25.83(a)(3)
0PT57608 | Monahans Sub : Replace 138 kV circuit breaker | City of Monahans, Ward County | Replace 138 kV circuit breaker | 2025-09-15 | 12/15/2025 | [5 empty] | 0 | 138 | na | na | na | na | na | na | na | na | 25.83(a)(3)
CCN APPLICATIONS - APPROVED
0PT44880 0PT45654 0PT49192 0PT46013 0PT46133 0PT43859 0PT50737 (M4172) | Old Country Switch 345 kV Tap Line | Ellis County | Construct the new single-circuit 345 kV line connecting the proposed Old Country Switch to Oystercatcher Solar's proposed substation. | 2026-01-05 | 2026-05-07 |  | 10,392,000 (t-line) 7,825,000 (station) |  |  |  | 0 | na | 345 | 4.2 | 1926.9 ACSS/TW Cumberland | Lattice Steel Towers | na | na | 160 | 4.2 | 52455 | Application Filed 8/26/2021. Application approved on 6/30/22 and final order issued on 7/14/22.
0PT45017 0PT42342 0PT42455 0PT42146 0PT50566 (M4238) | Ivy League 138 kV Line | Collin County | Construct the new single-circuit 138 kV line connecting the proposed Ivy League Substation to TNMP's existing Longneck Substation. | 2023-07-23 | 2024-04-11 | 2024-04-11 | 9,196,000 (t-line) 4,325,000 (station) | 7,481,835 (stations) 17,162,573 (Line) |  |  | 100 | na | 138 | 2.8 | 1926.9 kcmil ACSS/TW | Steel or Concrete Poles | na | na | 70 | 2.8 | 53053 | Application Filed 1/18/2022. Final Order issued on 12/15/2022.
0PT49039 0PT40468 0PT52385 0PT41070 0PT41164 0PT49515 (R6075) | Nacogdoches Southeast Switch - Redland Switch 345 kV Line | Nacogdoches and Angelina Counties | Construct the new 345 kV line in the vacant circuit position on the existing Nacogdoches Southeast Switch - Redland Switch 138 kV transmission line. | 2024-05-09 | 2024-12-26 | 2024-12-26 | 21,502,000 (t-line) 17,123,000 (station) | 22,178,546 (t-line) 34,837,850 (station) |  |  | 100 | na | 345 | 13.4 | 959.6 kcmil ACSS/TW | Lattice Steel Towers or Steel Poles | 170 | 13.4 | na | na | 54524 | Application Filed 1/12/2023. Received Notice of Approval 4/5/23
0PT49133 0PT51087 0PT51249 0PT53025 0PT51092 0PT51093 0PT51094 0PT51096 (M5281) | Keller Wall Price - Keller Magnolia 138 kV Transmission Line and Keller Wall Price - Roanoke 138 kV Rebuild | Tarrant County | Construct the new 138 kV transmission line connecting the proposed Keller Wall Price Switch to the existing Keller Magnolia Tap; rebuild the existing 138 kV line from the Keller Wall Price Substation to the existing Keller Magnolia Tap. | 2024-01-01 | 2024-05-20 | 2024-05-20 | 5,658,000 (t-line) 6,360,000(stations) | 575,837 (Line) 11,646,557 (Station) |  |  | 100 | 138 | 138 | 1.2 | 1926.9 ACSS/TW Cumberland | Steel Poles | 100 | 0.3 | na | na | 54733 | Application Filed 3/23/2023. Received a Revised Notice of Approval on 6/22/23.
0PT49421 0PT46128 0PT54337 0PT47652 (R8620) | North McCamey - Sand Lake 345 kV Line | Crane, Crockett, Pecos, Reeves, Upton, and Ward Counties | Construct the new double circuit 345 kV line connecting Oncor's existing Sand Lake Station to LCRA's existing North McCamey Station. | 2025-04-07 | 2026-07-31 |  | 159,264,500 (t-line) 5,534,000 (station) | 167,325,234 (Line) |  |  | 0 | na | 345 | 176.06 | 1926.9 ACSS/TW Cumberland | Lattice Steel Towers | na | na | 160 | 88.03 | 55121 | Application Filed 6/22/2023. Received Notice of Approval on 12/1/23.
0PT50023 0PT41140 0PT41166 0PT53968 0PT54573 (R6077) | Lufkin Switch - Redland Switch 345 kV Line | Angelina County | Construct the new single circuit 345 kV line connecting the existing Lufkin Switch to the existing Redland Switch on double circuit capable structures to accommodate a future 345 kV circuit. | 2025-02-24 | 2025-12-15 |  | 29,250,000 (t-line) 8,252,000 (station) | 38,884,618 (Line) |  |  | 2 | na | 345 | 7.92 | 1926.9 ACSS/TW Cumberland | Lattice Steel Towers or Steel Poles | na | na | varies | 7.92 | 55172 | Application Filed 7/13/2023. Received Notice of Approval on 12/1/23.
0PT49056 0PT43840 0PT52346 0PT53116 0PT53611 0PT52349 0PT53612 0PT44942 0PT44943 0PT54211 (M5148) | Ramhorn Hill - Dunham 345 kV Transmission Line | Denton and Wise Counties | Construct the new double circuit 345 kV transmission line connecting the proposed Ramhorn Hill Switch to the proposed Dunham Switch on triple circuit capable structures to accommodate a future 138 kV circuit. | 2024-11-01 | 2025-12-15 |  | 176,939,000 (t-line) 74,858,000 (station) | 264,699,472 (Line) 112,533,751 (station) |  |  | 6 | na | 345 | 41.7 | 1926.9 ACSS/TW Cumberland | Steel Poles | na | na | 100 | 20.84 | 55067 | Application Filed 6/8/2023. Final Order issued on 2/1/2024. Final Order on Rehearing issued on 5/6/2024.
0PT49068 0PT51089 0PT53097 0PT54710 0PT49510 0PT51097 0PT47814 0PT44941 (100%) (M5281) | Exchange Switch - Keller Magnolia Substation 138 kV Transmission Line | Tarrant County | Construct the new double circuit 138 kV transmission line between the proposed Exchange Switch, the existing Alliance Substation and the existing Keller Magnolia Substation. | 2024-03-19 | 2025-12-15 |  | 16,309,000 (t-line) 49,693,000(stations) | 18,003,657 (Line) 51,540,903 (Station) |  |  | 67 | na | 138 | 5.3 | 1926.9 ACSS/TW Cumberland | Steel Poles | na | na | 70 | 2.65 | 55574 | Application Filed 10/5/2023. Approved in the 5/2/24 PUC Open Meeting. Final Order issued on 6/5/2024. The Final Estimated Project Cost has been corrected to reflect what was filed in the CCN application.
0PT49135 0PT52792 0PT52354 0PT52355 0PT52010 0PT44941(0%) 0PT54629 (M5144) | Exchange Switch - Roanoke Switch 138/345 kV Transmission Line Rebuild | Tarrant and Denton Counties | Rebuild the existing double circuit 345 kV transmission line between the proposed Exchange Switch and the existing Roanoke Switch and add a new 138 kV circuit. | 2026-01-01 | 2026-05-26 |  | 34,364,000 (t-line) 1,100,000(stations) |  |  |  | 0 | 345 | 138 | 7.0 (345 kV) 3.5 (138 kV) | 1926.9 ACSS/TW Cumberland (345 kV) 959.6 ACSS/TW (138 kV) | Steel Poles | 160 | 3.5 | na | na | 55575 | Application Filed 10/5/2023. Final Order issued on 5/2/2024.
0PT52729 0PT54477 0PT49407 0PT49352 0PT49528 (R8603) | Peck - Driver 138 kV Line | Midland County | Construct the new single-circuit 138 kV line connecting the existing Peck Substation to the existing Driver Substation. | 2024-08-07 | 2024-12-16 | 2024-12-16 | 13,760,000 (t-line) 1,721,000(stations) | 14,972,164. (Line) 2,072,022 (Station) |  |  | 100 | na | 138 | 5.5 | 1926.9 ACSS/TW Cumberland | Steel Poles | na | na | 70 | 5.5 | 56220 | Application Filed 2/29/2024. Notice of approval on 5/28/2024.
0PT52165 0PT53477 0PT51299 0PT51460 (R8791) | Quartz Sand Sw - Hog Mountain POD 138 kV Transmission Line | Glasscock County | Construct a new single-circuit 138 kV transmission line connecting Quartz Sand Switch to the proposed Hog Mountain POD (XTO) on double-circuit capable structures | 2024-11-21 | 2025-09-30 |  | 18,063,000 (t-line) 960,000 (station) | 14,713,227 (t-line) 1,341,326 (Station) |  |  | 41 | na | 138 | 7.1 | 1926.9 ACSS/TW Cumberland | Steel Poles | na | na | 70 | 7.1 | 56396 | Application Filed 3/27/2024. Notice of approval on 6/14/2024
0PT52237 0PT53899 0PT51438 0PT51461 (R8698) (R8726) | Border Tap - Atchison POD 138 kV Transmission Line | Loving County | Construct a new single-circuit 138 kV transmission line connecting the proposed Border Tap to the proposed Atchison POD on double-circuit capable structures | 2025-02-03 | 2025-06-30 |  | 15,606,000 (t-line) 1,841,000 (station) | 17,788,151 (Line) 2,787,827 (Station) |  |  | 8 | na | 138 | 8 | 1926.9 ACSS/TW Cumberland | Steel Poles | na | na | 70 | 8 | 56523 | Application Filed 4/25/2024. Notice of approval on 7/8/2024.
0PT53566 0PT46948 (R3024) | Ranger Camp Switch 345 kV Transmission Tap Line | Mitchell County | Construct a new double-circuit 345 kV tap line and reterminate the existing Morgan Creek - Falcon Seaboard 345 kV transmission line into Ranger Camp Switch | 2024-08-20 | 2025-02-10 |  | 21,819,000 (t-line) | 14,398,849 (t-line) |  |  | 99* | na | 345 | 2.8 | 2 - 1926.9 ACSS/TW Cumberland | Steel Poles | na | na | 100 | 1.4 | 56597 | Application Filed 5/21/2024. Notice of Approval on 8/9/2024.
0PT54566 0PT46127 0PT53440 (R8629) | Reiter Switch - Tesoro Switch 345 kV Transmission Line | Ector and Midland Counties | Construct the new double-circuit 345 kV transmission line connecting Reiter Switch to Tesoro Switch | 2026-06-15 | 2026-12-31 |  | 18,115,000 (t-line) 5,425,000 (station) |  |  |  | 0 | na | 345 | 8.8 | 2 - 1926.9 ACSS/TW | Lattice Steel Towers | na | na | 160 | 4.4 | 56799 | Application Filed 7/25/2024. Final Order received on 11/14/24.
CCN APPLICATIONS - PENDING
0PT54649 0PT54492 0PT52728 0PT51492 0PT55844 (R8713) | Hartring Substation - Upland Substation 138 kV Transmission Line | Reagan and Upton Counties | Construct a new double-circuit138 kV transmission line between Oncor’s existing Hartring Substation in Reagan County and Oncor’s Upland Substation in Upton County, Texas | 2025-06-01 | 2025-11-30 |  | 21,861,000 (t-line) 3,301,000 (station) |  |  |  | 0 | na | 138 | 17.6 | 1926.9 ACSS/TW | Steel Monopoles | na | na | 70 | 8.8 | 57263 | Application Filed 11/14/2024.
0PT56974 0PT54862 0PT55832 0PT55827 (R6404) | Redland Switch – Longleaf POI 345 kV Transmission Line | Angelina County | The Proposed Transmission Line Project is a new 345 kV transmission line to be built on single-circuit monopole structures between Oncor’s existing Redland Switch and the proposed Longleaf POI, both in Angelina County, Texas. | 2025-09-18 | 2027-12-02 |  | $14,875,000 (line) $6,934,000 (station) |  |  |  | 0 | na | 345 | 1.63 | 959 ACSS/TW | Steel Monopoles | na | na | 130 | 1.63 | 57553 | Application Filed 1/30/2025. Added initial station cost as reported in CCN application.
0PT54632 0PT50572 0PT53077 0PT55819 (R8648) | Ranger Camp Switch - Cattleman Switch 345 kV Transmission Line | Mitchell County | Construct a new double-circuit 345 kV transmission line between Oncor's Ranger Camp Switch and Cattleman Switch in Mitchell County, Texas | 2025-06-16 | 2025-12-31 |  | 28,086,000 (t-line) 4,323,000 (station) |  |  |  | 0 | na | 345 | 8.4 | 2 - 1926.9 ACSS/TW Cumberland | Steel Poles | na | na | 100 | 4.2 | 57519 | Application Filed 2/6/2025.
0PT54658 0PT54735 (R8793) | Riverton Switch - Sand Lake Switch 138 kV Transmission Line | Reeves, Ward Counties | Construct a new double-circuit capable 138 kV transmission line between Oncor's existing Riverton Switch in Reeves County and Oncor's existing Sand Lake Switch in Ward County. | 2026-01-16 | 2026-12-15 |  | 70,855,000 (t-line) |  |  |  | 0 | na | 138 | 40 | 1926.9 ACSS/TW Cumberland | Steel Poles | 220 | 40 | na | na | 57633 | Application Filed on 2/13/2025.
0PT54652 0PT56307 0PT54338 0PT51575 0PT56942 0PT52172 (R6345) | Glaze Lake Switch 138 kV Loop Transmission Line | Leon County | Construct a new double-circuit 138 kV loop transmission line between Oncor’s existing Jewett Switch - Crockett Switch Line and the Proposed Glaze Lake Switch and Construct a single-circuit 138 kV transmission line from Proposed Glaze Lake Switch to the proposed Leon Solar POI on double-circuit capable structures | 2025-09-15 | 2026-04-16 |  | 32,168,000 (t-line) 7,732,000 (station) |  |  |  | 0 | na | 138 | 20 | 1926.9 ACSS/TW Cumberland | Steel Poles | na | na | 70 | 10 | 57723 | Application Filed on 2/27/2025.
0PT54686 0PT51759 0PT52381 0PT55136 (R6332) | Wofford POI - Berryville POD 138 kV Transmission Line | Anderson County | Construct a new single-circuit 138 kV transmission line to be built on double-circuit capable structures between Oncor's proposed Wofford POI and Oncor's proposed Berryville POD in Anderson County, TX. | 2027-06-01 | 2027-11-05 |  | 8,278,000 (t-line) 1,251,892 (station) |  |  |  | 0 | na | 138 | 2.12 | 1926.9 ACSS/TW Cumberland | Steel Poles | na | na | 100 | 2.12 | 57698 | Application Filed on 2/20/2025.
0PT56247 0PT57952 0PT54527 0PT58245 0PT56564 0PT56565 (PB_L5_D) | Drill Hole Switch - El Capitan Switch 345 kV Transmission Line | Culberson County | Construct a new double-circuit 345 kV transmission line between the existing Drill Hole Switch and the planned El Capitan Switch and Construct a new double-circuit 138 kV tie-line station asset to connect the Drill Hole 138 kV and 345 kV switchyards in Culberson County, TX | 2026-12-01 | 2027-12-31 |  | 97,468,000 (t-line) 110,493,000 (station) |  |  |  | 0 | na | 345 | 42.4 | 2 - 1926.9 ACSS/TW | Lattice Towers | na | na | 160 | 21.2 | 57828 | Application Filed on 3/20/2025.
0PT56246 0PT56566 0PT57941 0PT58374 0PT58375 0PT53838 (PB_L5_D) | Border Switch - Quarry Field Switch 345 kV Transmission Line | Loving County | Construct a new double-circuit 345 kV transmission line between the planned Border Switch and the existing Quarry Field Switch. | 2026-12-01 | 2028-12-31 |  | 36,109,000 (t-line) 50,385,000 (station) |  |  |  | 0 | na | 345 | 20.4 | 2 - 1926.9 ACSS/TW | Lattice Towers | na | na | 160 | 10.2 | 57837 | Application Filed on 3/27/2025.
0PT54656 0PT56556 0PT52986 0PT53678 0PT53677 0PT49544 0PT55560 0PT53615 0PT53616 0PT54033 0PT54032 (M4369) | Watermill Switch - Wilmer Switch 345 kV Transmission Line | Dallas County | Rebuild an existing double-circuit 345 kV transmission line and construct a new double-circuit 345 kV transmission line between Oncor’s existing Watermill Switch and Oncor’s proposed Wilmer Switch in Dallas County, Texas. | 2025-07-31 | 2026-06-30 |  | 63,300,000 (t-line) 91,834,000 (stations) |  |  |  | 0 | 345 | 345 | 8.8 | 2 - 1926.9 ACSS/TW Cumberland | Steel Poles | 250 to 310 | 3 | 180 | 1.4 | 57918 | Application Filed on 4/7/2025.

## EntryInstructions
General Instructions for Entering Information
1. Please use "na" whenever appropriate to reduce ambiguity, except in the "Costs," "Percent Complete," and "Percent Variance" columns. 2. Any new or revised entry must be entered using a red font and highlighted in yellow. In the month following the red font entry, change the previous month's red entries back to black and make any new entries for the new month in red. This aids PUCT staff in quickly identifying any changes from the previous month's report. 3. On the final monthly report on an existing line in which one of the attributes as listed in the attribute spreadsheets below has changed, enter that data in a bolded green font.
Utility's Project Number | Enter the Utility's Project Number. No duplicate numbers are allowed in this column.
Project Name | Enter the name of the project. If possible, use the same name as was reported to ERCOT in any reports.
Location (City/County) | Enter the names of the counties where the project is located. Also enter the names of cities, if appropriate. Please delineate all county and city names with commas only. (e.g., Liberty, Chambers, Anahuac, etc.)
Description | Describe the project in enough detail to allow the Commission to ensure that the work does not require a CCN, if the utility does not intend to apply for a CCN. Include any significant or relevant detail not being reported in other columns. Do not include Point of Delivery and add periods to all sentences.
Estimated (or Actual) Start Date | Enter the estimated project starting date. When construction begins, please replace the estimated date with the actual date of the start of construction
Finish Date (Construction Complete) | Enter the date (mm/dd/yy) when the construction related to the project has been completed.
Date Energized (If Applicable) | Enter the date (mm/dd/yy) the project was energized or restored to service (if applicable).
Initial Estimated Project Cost | CCN Projects Only: Enter the estimated cost from the CCN application. When reporting both T-Line and Substation Costs, enter them separately in the same cell. (e.g., "$3,946,000 T-Line; $1,768,000 Substation") This number shall not be changed in future months unless the Application is amended. Please DO NOT use links to other sheets within the workbook. Non-CCN Projects Only: No entry is needed; Enter the estimated cost in the
Final Estimated Project Cost | CCN Projects: Enter the latest available estimated cost for the month that construction starts. This number shall not be changed after construction begins. and a cost variance explanation is not required unless requested by PUC Staff For Non-CCN Projects: Enter the initial estimated cost. Estimate revisions are not necessary
Final Actual Project Cost | Enter the actual, final project cost after the project has been energized and all costs have been recorded. Omit the project from all following reports.
% Variance | The cells contain a formula for calculating the percent variance of the final actual cost with respect to the final estimated cost. This is essentially a calculation of the percent of the cost over-run or under-run. Please do not change these cells.
Percent Complete | State the construction progress of the project as a percent. Please use only an integer and do not write"%." Do not report the percent of money spent.
Existing Voltage | Enter the nominal system existing voltage, if any. In the event of a voltage upgrade, this will be the "before" voltage. If the project is for a new line, enter "na." For projects involving multiple voltages, please delineate the voltages by a comma, (e.g., "69,138"). Please do not write "volts."
Upgraded or New Voltage | Enter the nominal system voltage after upgrading or if new line construction is involved. Please use the same practices described in the "Existing Voltage" column. Please do not write "volts."
Circuit Length (Miles) | Enter the total circuit length. Example: For a new double-circuit line using 10 miles of new ROW, the circuit length would be 20 miles. Please enter only a number, if possible. Please do not write "miles."
Conductor Type & Size & Bundling | Describe the conductor characteristics, including whether double or single circuit or mixed. Lengthy explanations shall be made in the Project Description column. (Format should be Quantity - Conductor Size and Type). Do not include quotations for supplier given code words or the word bundled.
Structure Type(s) | Describe structure types and materials used.
Existing ROW Width (Feet) | Enter width of existing ROW. The entry type is unrestricted. If the project is only for new line and no old ROW exists, enter "na." Entries such as "60,80,100" or "60 - 100" or "centerline" are permissible. Make detailed explanations, if needed, elsewhere. Please do not write "feet."
Existing ROW Length (Miles) | Enter length of existing ROW. The entry type is unrestricted. If the project is only for new line and no old ROW exists, enter "na." Make detailed explanations, if needed, elsewhere. Please do not write "miles."
New ROW Width (Feet) | Enter width of new ROW. The entry type is unrestricted. Entries such as "60,80,100" or "60 - 100" or "centerline" or "railroad" or "street" are permissible. Make detailed explanations, if needed, elsewhere. Please do not write "feet."
New ROW Length (Miles) | Enter new (additional) ROW length, in miles. Please do not write "miles."
Rule Section or PUC Control Number | Enter the PUC Substantive Rule 25.101 section(s) which are applicable. For multiple section applicability, please delineate by commas, e.g., "25.101(c)(5)(A), 25.101(c)(5)(B)" for a project incorporating a line extension (A) and a voltage upgrade on the existing line which is being extended (B). If the project involves a CCN Application, enter ONLY the .5-digit control number. Please do not write "docket," "CCN" or other text, except when needed in citing Rule 25.101. Should the project include work done under both CCN and 25.101(c)(5), follow the same practices and delineate with commas.
Comments | Enter information not included elsewhere, including reimbursed costs. A cost variance explanation is no longer required for non-CCN projects. However, utilities will be required to submit a Cost Analysis only for CCN Projects. See Note below.

## 17T80077
Project No. 17T80077, 0PT38181, 0PT38182, 0PT38179, 0PT38178, 0PT38426, 19T63008, 0PT38517, 0PT38518 - Odessa EHV - Riverton and Moss - Riverton 345 kV Line - Transmission Line Project
| Estimated cost included in CCN Application (Route 1180) | Estimated cost once a route is approved and CCN granted (Route 1180) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 21540000 | 29205738 | Costs not yet available
Engineering and Design (Utility) | 5322000 | 0 | Costs not yet available
Engineering and Design (Contract) | 2269000 | 2877377 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 74495000 | 76498142 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 96103000 | 103610002 | Costs not yet available
Estimated Total Cost | 199729000 | 212191259 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 36379783 | Costs not yet available
Estimated Project Total | 199729000 | 248571042 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | N/A
Engineering and Design (Utility) | 245000 | 166800 | Costs not yet available
Engineering and Design (Contract) | 922857 | 908706 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 15969607 | 9781320 | Costs not yet available
Construction of Facilities (Utility) | 2270494 | 479109 | Costs not yet available
Construction of Facilities (Contract) | 4424042 | 5436125 | Costs not yet available
Estimated Total Cost | 23832000 | 0 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 2068010 | Costs not yet available
Estimated Project Total | 23832000 | 18840070 | Costs not yet available
Reported on Monthly Construction Report | 223561000 | 267411112 | Costs not yet available
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT37182
Project No. 0PT37182, 0PT40453, OPT38505, 0PT38427- Sand Lake - Solstice 345 kV Line - Transmission Line Project
*THIS IS A JOINT PROJECT WITH AEP TEXAS - ALL COSTS SHOWN IN TABLE BELOW ARE ONCOR'S PORTION OF THE PROJECT
| Estimated cost included in CCN Application (Route 320) | Estimated cost once a route is approved and CCN granted (Modified Route 320) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 4561500 | 10739693 | Costs not yet available
Engineering and Design (Utility) | 1058500 | 694256 | Costs not yet available
Engineering and Design (Contract) | 1348000 | 1105909 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 16793500 | 13285278 | Costs not yet available
Construction of Facilities (Utility) | 500 | 0 | Costs not yet available
Construction of Facilities (Contract) | 25348000 | 38847631 | Costs not yet available
Estimated Total Cost | 49110000 | 64672767 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 4250011 | Costs not yet available
Estimated Project Total | 49110000 | 68922778 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | N/A
Engineering and Design (Utility) | 0 | 0 | Costs not yet available
Engineering and Design (Contract) | 400000 | 444635 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 13200000 | 17005560 | Costs not yet available
Construction of Facilities (Utility) | 1210000 | 1065160 | Costs not yet available
Construction of Facilities (Contract) | 2026000 | 4008366 | Costs not yet available
Estimated Total Cost | 16836000 | 22523721 | Costs not yet available
Other (all costs not included in the above categories) | 764000 | 0 | Costs not yet available
Estimated Project Total | 17600000 | 22523721 | Costs not yet available
Reported on Monthly Construction Report | 66710000 | 91446499 | Costs not yet available
139510
0PT39030 SB |  | City of Tyler, Bell County

## 0PT39531
Project No. 0PT39531 - Bearkat (WETT) - Longshore 345 kV Line Transmission Line Project
*THIS IS A JOINT PROJECT WITH WETT - ALL COSTS SHOWN IN TABLE BELOW ARE ONCOR'S PORTION OF THE PROJECT
| Estimated cost included in CCN Application (Route 102) | Estimated cost once a route is approved and CCN granted (Route 69) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 3125500 | 4344273.75 | Costs not yet available
Engineering and Design (Utility) | 771500 | 807985.51 | Costs not yet available
Engineering and Design (Contract) | 1170000 | 2952589 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 8803500 | 11251734.71 | Costs not yet available
Construction of Facilities (Utility) | 0 | 31875 | Costs not yet available
Construction of Facilities (Contract) | 15469000 | 15596226.81 | Costs not yet available
Estimated Total Cost | 29339500 | 34984684.78 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 29339500 | 34984684.78 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | N/A
Engineering and Design (Utility) | 0 | 0 | Costs not yet available
Engineering and Design (Contract) | 150000 | 150000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 810000 | 810000 | Costs not yet available
Construction of Facilities (Utility) | 60000 | 60000 | Costs not yet available
Construction of Facilities (Contract) | 390000 | 390000 | Costs not yet available
Estimated Total Cost | 1410000 | 1410000 | Costs not yet available
Other (all costs not included in the above categories) | 290000 | 275394.44 | Costs not yet available
Estimated Project Total | 1700000 | 1685394.44 | Costs not yet available
Reported on Monthly Construction Report | 31039500 | 34984684.78 | Costs not yet available

## 0PT44880
Project No. 0PT44880 - Old Country Switch 345 kV Tap Line - Transmission Line Project
| Estimated cost included in CCN Application - Route 54 | Estimated cost included in CCN Application of PUC Approved Route 152 | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1765000 | 2315000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 153000 | 199000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 1470000 | 1499000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 1842000 | 2336000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 5162000 | 6389000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 10392000 | 12738000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | Costs not yet available | Costs not yet available
Estimated Project Total | 10392000 | 12738000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 393000 | 393000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 584000 | 584000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 370000 | 370000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 3491000 | 3491000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 351000 | 351000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 2636000 | 2636000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 7825000 | 7825000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | Costs not yet available | Costs not yet available
Estimated Project Total | 7825000 | 7825000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 18217000 | 20563000 | Costs not yet available | Costs not yet available

## 0PT45017
Project No. 0PT45017, 0PT42342, 0PT42455, 0PT42146 - Ivy League Substation 138 kV Line - Transmission Line Project
| Estimated cost included in CCN Application - Route 4626 | Estimated cost included in CCN Application of PUC Approved Route 4626 | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 2096000 | 2096000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 135000 | 135000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 1536000 | 1536000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 1978000 | 1978000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 3451000 | 3451000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 9196000 | 9196000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 9196000 | 9196000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 100000 | 100000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 339000 | 339000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 42000 | 42000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 2151000 | 2151000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 78000 | 78000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 1615000 | 1615000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 4325000 | 4325000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 4325000 | 4325000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 13521000 | 13521000 | Costs not yet available | Costs not yet available

## 0PT49039
Project No. 0PT49039, 0PT40468, 0PT41164, 0PT41070 - Nacogdoches SE Switch - Redland Switch 345 kV Line - Transmission Line Project
| Estimated cost included in CCN | Estimated cost once the route is approved and CCN granted (Single Route) | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 201000 | 423000 | Costs not yet available
Engineering and Design (Utility) | 25000 | 181000 | Costs not yet available
Engineering and Design (Contract) | 1576000 | 546340 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 5354000 | 4989996 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 14346000 | 16038210 | Costs not yet available
Estimated Total Cost | 21502000 | 22178546 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 21502000 | 22178546 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | Costs not yet available
Engineering and Design (Utility) | 0 | 1228905 | Costs not yet available
Engineering and Design (Contract) | 994000 | 1080286 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 8123000 | 17553026 | Costs not yet available
Construction of Facilities (Utility) | 587000 | 0 | Costs not yet available
Construction of Facilities (Contract) | 7419000 | 14975633 | Costs not yet available
Estimated Total Cost | 17123000 | 34837850 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 17123000 | 34837850 | Costs not yet available
Reported on Monthly Construction Report | 38625000 | 57016396 | Costs not yet available

## 0PT49133
Project No. 0PT49133 - Keller Wall Price – Keller Magnolia 138 kV Transmission Line Project (“KWP-KM”) and Keller Wall Price – Roanoke 138 kV Rebuild Project (“KWP-R”)
| Estimated cost included in CCN Application |  | Estimated cost once the route is approved and CCN granted |  | Estimated cost once the route is approved and CCN granted |  | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: |  | Initial Estimated Project Costs: |  | Final Estimated Project Costs: |  | Final Actual Project Costs:
| KWP- KM | KWP - R | KWP- KM | KWP - R | KWP- KM | KWP - R | KWP- KM | KWP - R
Right-of-Way and Land Acquisition | 17000 | 0 | 17000 | 0 |  |  | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 30000 | 30000 | 30000 | 30000 |  |  | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 1079000 | 229000 | 1079000 | 229000 |  |  | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 880000 | 647000 | 880000 | 647000 |  |  | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | 0 | 0 |  |  | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 1376000 | 1370000 | 1376000 | 1370000 |  |  | Costs not yet available | Costs not yet available
Estimated Total Cost | 3382000 | 2276000 | 3382000 | 2276000 |  |  | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | 0 | 0 |  |  | Costs not yet available | Costs not yet available
Estimated Project Total | 5658000 |  | 5658000 |  |  |  | Costs not yet available
| Substation Facilities |  | Substation Facilities |  | Substation Facilities |  | Substation Facilities
Right-of-Way and Land Acquisition | 0 |  | 0 |  |  |  | Costs not yet available
Engineering and Design (Utility) | 0 |  | 0 |  |  |  | Costs not yet available
Engineering and Design (Contract) | 275000 |  | 275000 |  |  |  | Costs not yet available
Procurement of Material & Equipment (including Stores) | 3290000 |  | 3290000 |  |  |  | Costs not yet available
Construction of Facilities (Utility) | 250000 |  | 250000 |  |  |  | Costs not yet available
Construction of Facilities (Contract) | 2545000 |  | 2545000 |  |  |  | Costs not yet available
Estimated Total Cost | 6360000 |  | 6360000 |  |  |  | Costs not yet available
Other (all costs not included in the above categories) | 0 |  | 0 |  |  |  | Costs not yet available
Estimated Project Total | 6360000 |  | 6360000 |  |  |  | Costs not yet available
Reported on Monthly Construction Report | 12018000 |  | 12018000 |  |  |  | Costs not yet available

## 0PT49056
Project No. 0PT49056 - Ramhorn Hill Switch - Dunham Switch 345 kV Transmission Line Project
| Estimated cost included in CCN Application - Route 179 | Estimated cost of PUC Approved Route 179C with M1 & M5 Modifications (Approved 1/18/24) | Estimated cost of PUC Approved Route 179C with C4, C6, E6, G1, M1 and M5 Modifications (Approved 5/2/24) | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 56996000 | 56296000 | 56738000 | 57364828 | Costs not yet available
Engineering and Design (Utility) | 309000 | 319000 | 322000 | 50000 | Costs not yet available
Engineering and Design (Contract) | 6099000 | 5947000 | 5976000 | 7067114 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 60597000 | 60230000 | 59875000 | 67775026 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 51207000 | 54224000 | 54028000 | 132442504 | Costs not yet available
Estimated Total Cost | 175208000 | 177016000 | 176939000 | 264699472 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | 0 | 0 | Costs not yet available
Estimated Project Total | 175208000 | 177016000 | 176939000 | 264699472 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 25458000 | 25458000 | 25458000 | 25838081.58 | Costs not yet available
Engineering and Design (Utility) | 0 | 0 | 0 | 1320800 | Costs not yet available
Engineering and Design (Contract) | 1000000 | 1000000 | 1000000 | 1673800 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 23140000 | 23140000 | 23140000 | 43045846 | Costs not yet available
Construction of Facilities (Utility) | 500000 | 500000 | 500000 | 0 | Costs not yet available
Construction of Facilities (Contract) | 24760000 | 24760000 | 24760000 | 40655223 | Costs not yet available
Estimated Total Cost | 74858000 | 74858000 | 74858000 | 112533750.58 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | 0 | 0 | Costs not yet available
Estimated Project Total | 74858000 | 74858000 | 74858000 | 112533750.58 | Costs not yet available
Reported on Monthly Construction Report | 250066000 | 251874000 | 251797000 | 377233222.58 | Costs not yet available

## 0PT49421
Project No. 0PT49421 - North McCamey (LCRA) - Sand Lake (Oncor) 345 kV Transmission Line Project
| Estimated cost included in CCN Application - Route 65 | Estimated cost included in CCN Application of PUC Approved Route 65 | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs*: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 8524500 | 8524500 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 167500 | 167500 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 6288000 | 6288000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 58462000 | 58462000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 85822500 | 85822500 | Costs not yet available | Costs not yet available
Estimated Total Cost | 159264500 | 159264500 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 159264500 | 159264500 | Costs not yet available | Costs not yet available
| Substation Facilities** | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 0 | 0 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 200000 | 200000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 3320000 | 3320000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 200000 | 200000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 1814000 | 1814000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 5534000 | 5534000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 5534000 | 5534000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 164798500 | 164798500 | Costs not yet available | Costs not yet available
*This is a joint project with LCRA. The transmission line costs shown here are the filed transmission line costs for Route 65 divided by 2.
** Oncor substation costs that were filed with the CCN application. Does not include LCRA substation costs.

## 0PT50023
Project No. 0PT50023 - Lufkin Switch - Redland Switch 345 kV Transmission Line Project
| Estimated cost included in CCN Application - Route 6 | Estimated cost included in CCN Application of PUC Approved Route 3 | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 3699000 | 3456000 | 5905611 | Costs not yet available
Engineering and Design (Utility) | 609000 | 660000 | 50000 | Costs not yet available
Engineering and Design (Contract) | 2092000 | 2141000 | 1320424 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 6398000 | 6622000 | 8332644 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 16452000 | 17387000 | 18892998 | Costs not yet available
Estimated Total Cost | 29250000 | 30266000 | 34501677 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | 0 | Costs not yet available
Estimated Project Total | 29250000 | 30266000 | 34501677 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 0 | 0 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 472000 | 472000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 3671000 | 3671000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 371000 | 371000 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 3738000 | 3738000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 8252000 | 8252000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 8252000 | 8252000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 37502000 | 38518000 | Costs not yet available | Costs not yet available

## 0PT49068
Project No. 0PT49068 - Exchange Switch - Keller Magnolia Sub 138 kV Transmission Line Project
| Estimated cost included in CCN Application - Route 339 | Estimated cost included in CCN Application of PUC Approved Route 339 | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 2435000 | 2435000 | 2435000 | Costs not yet available
Engineering and Design (Utility) | 115000 | 115000 | 91000 | Costs not yet available
Engineering and Design (Contract) | 2015000 | 2015000 | 2136233 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4752000 | 4752000 | 4688726 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 6992000 | 6992000 | 8652698 | Costs not yet available
Estimated Total Cost | 16309000 | 16309000 | 18003657 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | 0 | Costs not yet available
Estimated Project Total | 16309000 | 16309000 | 18003657 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
| Includes Exchange Sw & Keller Magnolia Sub | Includes Exchange Sw & Keller Magnolia Sub | Includes Exchange Sw & Keller Magnolia Sub | Includes Exchange Sw & Keller Magnolia Sub
Right-of-Way and Land Acquisition | 7080000 | 7080000 | 7142317 | Costs not yet available
Engineering and Design (Utility) | 0 | 0 | 1390000 | Costs not yet available
Engineering and Design (Contract) | 853000 | 853000 | 1211000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 23305000 | 23305000 | 26486262.78 | Costs not yet available
Construction of Facilities (Utility) | 1700000 | 1700000 | 0 | Costs not yet available
Construction of Facilities (Contract) | 16755000 | 16755000 | 15311323 | Costs not yet available
Estimated Total Cost | 49693000 | 49693000 | 51540902.78 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | 0 | Costs not yet available
Estimated Project Total | 49693000 | 49693000 | 51540902.78 | Costs not yet available
Reported on Monthly Construction Report | 66002000 | 66002000 | 69544559.78 | Costs not yet available

## 0PT49135
Project No. 0PT49135 - Exchange Switch - Roanoke Switch 138/345 kV Transmission Line Rebuild Project
| Estimated cost included in CCN | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 684000 | 684000 | Costs not yet available
Engineering and Design (Utility) | 92000 | 92000 | Costs not yet available
Engineering and Design (Contract) | 1772000 | 1772000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 12315000 | 12315000 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 19501000 | 19501000 | Costs not yet available
Estimated Total Cost | 34364000 | 34364000 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 34364000 | 34364000 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | Costs not yet available
Engineering and Design (Utility) | 50000 | 50000 | Costs not yet available
Engineering and Design (Contract) | 150000 | 150000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 435000 | 435000 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 465000 | 465000 | Costs not yet available
Estimated Total Cost | 1100000 | 1100000 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available
Estimated Project Total | 1100000 | 1100000 | Costs not yet available
Reported on Monthly Construction Report | 35464000 | 35464000 | Costs not yet available

## 0PT52729
Project No. 0PT52729, 0PT54477, 0PT49407 - Peck Substation - Driver Substation 138 kV Transmission Line Project
| Estimated cost included in CCN Application | Estimated cost included in CCN Application of PUC Approved Route | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 810000 | 810000 | 521640 | Costs not yet available
Engineering and Design (Utility) | 60000 | 60000 | 78500 | Costs not yet available
Engineering and Design (Contract) | 1760000 | 1760000 | 1387000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4460000 | 4460000 | 4704641 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 6670000 | 6670000 | 8280383 | Costs not yet available
Estimated Total Cost | 13760000 | 13760000 | 14972164 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | 0 | Costs not yet available
Estimated Project Total | 13760000 | 13760000 | 14972164 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | 0 | Costs not yet available
Engineering and Design (Utility) | 146000 | 146000 | 159400 | Costs not yet available
Engineering and Design (Contract) | 210000 | 210000 | 295000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 672000 | 672000 | 697566.71 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 693000 | 693000 | 920055.53 | Costs not yet available
Estimated Total Cost | 1721000 | 1721000 | 2072022 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | 0 | Costs not yet available
Estimated Project Total | 1721000 | 1721000 | 2072022 | Costs not yet available
Reported on Monthly Construction Report | 15481000 | 15481000 | 17044186 | Costs not yet available

## 0PT52165
Project No. 0PT52165 - Quartz Sand Sw - Hog Mountain POD 138 kV Transmission Line Project
| Estimated cost included in CCN Application | Estimated cost included in CCN Application of PUC Approved Route | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1087000 | 1087000 | 435766 | Costs not yet available
Engineering and Design (Utility) | 73000 | 73000 | 15000 | Costs not yet available
Engineering and Design (Contract) | 1730000 | 1730000 | 1761310 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 5910000 | 5910000 | 5316638 | Costs not yet available
Construction of Facilities (Utility) | $ - | $ - | 0 | Costs not yet available
Construction of Facilities (Contract) | 9263000 | 9263000 | 7184513 | Costs not yet available
Estimated Total Cost | 18063000 | 18063000 | 14713227 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | 0 | Costs not yet available
Estimated Project Total | 18063000 | 18063000 | 14713227 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
| Includes Hog Mountain POD | Includes Hog Mountain POD | Includes Hog Mountain POD | Includes Hog Mountain POD
Right-of-Way and Land Acquisition | 0 | 0 | 10000 | Costs not yet available
Engineering and Design (Utility) | 86000 | 86000 | 86000 | Costs not yet available
Engineering and Design (Contract) | 124000 | 124000 | 124000 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 349000 | 349000 | 393103.75 | Costs not yet available
Construction of Facilities (Utility) | $ - | $ - | 0 | Costs not yet available
Construction of Facilities (Contract) | 401000 | 401000 | 728221.99 | Costs not yet available
Estimated Total Cost | 960000 | 960000 | 1341325.74 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | 0 | Costs not yet available
Estimated Project Total | 960000 | 960000 | 1341325.74 | Costs not yet available
Reported on Monthly Construction Report | 19023000 | 19023000 | 16054552.74 | Costs not yet available

## 0PT52237
Project No. 0PT52237 - Border Tap - Atchison POD 138 kV Transmission Line Project
| Estimated cost included in CCN | Estimated cost included in CCN Application of PUC Approved Route Single Route | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 968000 | 968000 | 694831 | Costs not yet available
Engineering and Design (Utility) | 35000 | 35000 | 100000 | Costs not yet available
Engineering and Design (Contract) | 1552000 | 1552000 | 1683426 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 5653000 | 5653000 | 5359575 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 7398000 | 7398000 | 9950319 | Costs not yet available
Estimated Total Cost | 15606000 | 15606000 | 17788151 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | 0 | Costs not yet available
Estimated Project Total | 15606000 | 15606000 | 17788151 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 20000 | 20000 | 20000 | Costs not yet available
Engineering and Design (Utility) | 32000 | 32000 | 26200 | Costs not yet available
Engineering and Design (Contract) | 166000 | 166000 | 225600 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 650000 | 650000 | 679586.16 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 973000 | 973000 | 1836440.73 | Costs not yet available
Estimated Total Cost | 1841000 | 1841000 | 2787826.89 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | 0 | Costs not yet available
Estimated Project Total | 1841000 | 1841000 | 20575977.89 | Costs not yet available
Reported on Monthly Construction Report | 17447000 | 17447000 | Costs not yet available | Costs not yet available

## 0PT53566
Project No. 0PT53566 - Ranger Camp Switch 345 kV Transmission Tap Line Project
| Estimated cost included in CCN Application (Single Route) | Estimated cost included in CCN Application of PUC Approved Route (Single Route) | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 150000 | 150000 | 250000 | Costs not yet available
Engineering and Design (Utility) | 14000 | 14000 | 42210 | Costs not yet available
Engineering and Design (Contract) | 1112000 | 1112000 | 1536937 | Costs not yet available
Procurement of Material & Equipment (including Stores) | 5245000 | 5245000 | 4734935 | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | 0 | Costs not yet available
Construction of Facilities (Contract) | 15298000 | 15298000 | 7834767 | Costs not yet available
Estimated Total Cost | 21819000 | 21819000 | 14398849 | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | 0 | Costs not yet available
Estimated Project Total | 21819000 | 21819000 | 14398849 | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | 0 | 0
Engineering and Design (Utility) | 0 | 0 | 0 | 0
Engineering and Design (Contract) | 0 | 0 | 0 | 0
Procurement of Material & Equipment (including Stores) | 0 | 0 | 0 | 0
Construction of Facilities (Utility) | 0 | 0 | 0 | 0
Construction of Facilities (Contract) | 0 | 0 | 0 | 0
Estimated Total Cost | 0 | 0 | 0 | 0
Other (all costs not included in the above categories) | 0 | 0 | 0 | 0
Estimated Project Total | 0 | 0 | 0 | 0
Reported on Monthly Construction Report | 21819000 | 21819000 | 14398849 | 0

## 0PT54566
Project No. 0PT54566 - Reiter Switch - Tesoro Switch 345 kV Transmission Line Project
| Estimated cost included in CCN Application - Route 10 | Estimated cost included in CCN Application of PUC Approved Route - Route 10 | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1444000 | 1444000 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 0 | 0 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 1287000 | 1287000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 5286000 | 5286000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 10098000 | 10098000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 18115000 | 18115000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 18115000 | 18115000 | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | 0 | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 156000 | 156000 | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 190000 | 190000 | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 3094000 | 3094000 | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | 0 | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 1985000 | 1985000 | Costs not yet available | Costs not yet available
Estimated Total Cost | 5425000 | 5425000 | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | 0 | Costs not yet available | Costs not yet available
Estimated Project Total | 5425000 | 5425000 | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 23540000 | 23540000 | Costs not yet available | Costs not yet available

## 0PT54649
Project No. 0PT54649 - Hartring Substation - Upland Substation 138 kV Transmission Line Project
| Estimated cost included in CCN Application | Estimated cost included in CCN Application of PUC Approved Route | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 647000 | Cost not yet available | Cost not yet available | Costs not yet available
Engineering and Design (Utility) | 314000 | Cost not yet available | Cost not yet available | Costs not yet available
Engineering and Design (Contract) | 1204000 | Cost not yet available | Cost not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 7642000 | Cost not yet available | Cost not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Cost not yet available | Cost not yet available | Costs not yet available
Construction of Facilities (Contract) | 12054000 | Cost not yet available | Cost not yet available | Costs not yet available
Estimated Total Cost | 21861000 | Cost not yet available | Cost not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Cost not yet available | Cost not yet available | Costs not yet available
Estimated Project Total | 21861000 | Cost not yet available | Cost not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
| Includes Modification Costs for Hartring Substation, Upland Substation, and Ringo Switch | Includes Modification Costs for Hartring Substation, Upland Substation, and Ringo Switch | Includes Modification Costs for Hartring Substation, Upland Substation, and Ringo Switch | Includes Modification Costs for Hartring Substation, Upland Substation, and Ringo Switch
Right-of-Way and Land Acquisition | 0 | Cost not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 88000 | Cost not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 324000 | Cost not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 1344000 | Cost not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 20000 | Cost not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 1525000 | Cost not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 3301000 | Cost not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Cost not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 3301000 | Cost not yet available | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 25162000 | Costs not yet available | Costs not yet available | Costs not yet available

## 0PT56974
Project No. 0PT56974 - Redland Switch – Longleaf POI 345 kV Transmission Line Project
| Estimated cost included in CCN Application - Route 3 | Estimated cost included in CCN Application of PUC Approved Route | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 452000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 123000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 451000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 4876000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 8973000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 14875000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 14875000 | Costs not yet available | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 25000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 400000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 2540000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 122000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 3847000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 6934000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 6934000 | Costs not yet available | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 21809000 | Costs not yet available | Costs not yet available | Costs not yet available

## 0PT56432
Project No. 0PT54632 - Ranger Camp Switch - Cattleman Switch 345 kV Transmission Line Project
| Estimated cost included in CCN Application (Single Route) | Estimated cost included in CCN Application of PUC Approved Route | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 75000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 30000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 1350000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 12863000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 13768000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 28086000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 28086000 | Costs not yet available | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 246000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 165000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 2499000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 1413000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 4323000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 4323000 | Costs not yet available | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 32409000 | Costs not yet available | Costs not yet available | Costs not yet available

## 0PT54658
Project No. 0PT54658 - Riverton Switch - Sand Lake Switch 138 kV Transmission Line Project
| Estimated cost included in CCN Application (Single Route) | Estimated cost included in CCN Application of PUC Approved Route | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 1463000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 3438000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 27767000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 38187000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 70855000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 70855000 | Costs not yet available | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition |  | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) |  | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) |  | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) |  | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) |  | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) |  | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 70855000 | Costs not yet available | Costs not yet available | Costs not yet available

## 0PT54652
Project No. 0PT54652 - Glaze Lake Switch 138 kV Loop Transmission Line Project
| Estimated cost included in CCN Application (Single Route) | Estimated cost included in CCN Application of PUC Approved Route | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1494000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 450000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 6934000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 23290000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 32168000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 32168000 | Costs not yet available | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 6000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 480000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 2641000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 4605000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 7732000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 7732000 | Costs not yet available | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 39900000 | Costs not yet available | Costs not yet available | Costs not yet available

## 0PT54686
Project No. 0PT54686 - Wofford POI - Berryville POD 138 kV Transmission Line Project
| Estimated cost included in CCN Application - Route 43 | Estimated cost included in CCN Application of PUC Approved Route | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 1800000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 77000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 522000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 2167000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 3712000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 8278000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 8278000 | Costs not yet available | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 5000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 22000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 459403 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 65700 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 699789 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 1251892 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 1251892 | Costs not yet available | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 9529892 | Costs not yet available | Costs not yet available | Costs not yet available

## 0PT56247
Project No. 0PT56247 - Drill Hole Switch - El Capitan Switch 345 kV Transmission Line Project
| Estimated cost included in CCN Application - Route 36 | Estimated cost included in CCN Application of PUC Approved Route | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 2454000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 751000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 1733000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 39083000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 53447000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 97468000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 97468000 | Costs not yet available | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 8247000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 3581000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 1890000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 62687000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 34088000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 110493000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 110493000 | Costs not yet available | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 207961000 | Costs not yet available | Costs not yet available | Costs not yet available

## 0PT56246
Project No. 0PT56246 - Border Switch - Quarry Field Switch 345 kV Transmission Line Project
| Estimated cost included in CCN Application - Route 13 | Estimated cost included in CCN Application of PUC Approved Route | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 3274000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 1724000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 10135000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 20976000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 36109000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 36109000 | Costs not yet available | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 1849000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 900000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 31147000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 16489000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 50385000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 50385000 | Costs not yet available | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 86494000 | Costs not yet available | Costs not yet available | Costs not yet available

## 0PT54656
Project No. 0PT54656 - Watermill - Wilmer 345 kV Transmission Line Project
| Estimated cost included in CCN Application (Single Route) | Estimated cost included in CCN Application of PUC Approved Route | Estimated cost once the route is approved and CCN granted | Approximately 6 months after construction is complete
| Initial Estimated Project Costs: | Initial Estimated Project Costs: | Final Estimated Project Costs: | Final Actual Project Costs:
Right-of-Way and Land Acquisition | 2260000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 80000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 2920000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 25620000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 32420000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 63300000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 63300000 | Costs not yet available | Costs not yet available | Costs not yet available
| Substation Facilities | Substation Facilities | Substation Facilities | Substation Facilities
Right-of-Way and Land Acquisition | 11013000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Utility) | 101000 | Costs not yet available | Costs not yet available | Costs not yet available
Engineering and Design (Contract) | 1095000 | Costs not yet available | Costs not yet available | Costs not yet available
Procurement of Material & Equipment (including Stores) | 42325000 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Utility) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Construction of Facilities (Contract) | 37300000 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Total Cost | 91834000 | Costs not yet available | Costs not yet available | Costs not yet available
Other (all costs not included in the above categories) | 0 | Costs not yet available | Costs not yet available | Costs not yet available
Estimated Project Total | 91834000 | Costs not yet available | Costs not yet available | Costs not yet available
Reported on Monthly Construction Report | 155134000 | Costs not yet available | Costs not yet available | Costs not yet available