## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
19014 | Holder Line Mods | Brown | Rerouting two 138kV transmission lines into the Holder Substation, Rising Star-Holder and Holder - Brownwood. | 2024-01-02 | 2024-02-28 | 2024-02-28 | 431715 | 538028 |  |  | 100 | 138 | 138 | 0.21 | 959 ACSS/TW & 477 ACSR | Single Pole Concrete or Steel | 60 & 100 | NA | NA | NA | 25.101(c)(5)(B) | Affidavit to be filed upon request
2160001 | Rector Rd to Aubrey Line Mods | Denton | Replace structures 1/4 thru 1/9 due to TxDOT IH35 ROW Expansion | 2024-11-04 |  |  | 1621923.5 | 1665116 |  |  | 60 | 138 | 138 | 0.75 | 795 ACSR | Single Pole Concrete or Steel | 60 | 0.75 | 0 | 0 | 25.101 (C)(5)(D) | Affidavit to be filed upon request
22022 | Judith Transmission Line | McLennan | Construct 0.71 miles of double circuit 138kV transmission line to loop the existing McGregor – Moody through the new Judith substation. | 2024-03-11 | 2024-06-15 | 2024-05-30 | 1250000 | 1960033 |  |  | 100 | NA | 138 | 0.71 | 795 ACSR | Single Pole Concrete or Steel | NA | NA | 70 | 0.71 | 25.101(c)(5)(A) | Affidavit to be filed upon request
22021 | Tomcat P.O.I. | Johnson | Construct P.O.I. in the Wildcat-Wildcat Tap 138kV transmission line | 2024-09-23 | 2024-12-18 | 2024-12-31 | 1000000 | 1302133 |  |  | 100 | 138 | 138 | 0.04 | 1033 ACSR | Single Pole Concrete or Steel | 70 | 0.04 | NA | NA | 25.101(c)(5)(A) | Affidavit to be filed upon request
21030 | Bartlett Sw-Bartlett Rebuild | Bell | Rebuild 2.67 miles of single pole, double circuit capable from Bartlett Switch to Bartlett Substation | 2024-09-16 | 2025-01-31 | 2025-01-08 | 2754818.04 | 2867977 |  |  | 100 | 69 | 138 | 2.67 | 959 ACSS | Single Pole Concrete or Steel | 60 | 2.7 | NA | NA | 25.101(c)(5)(B) | Affidavit to be filed upon request
22020 | Keith SW-GCS | Grimes | Construct 0.15 miles of single circuit 138kV transmission line to tie Grimes County Solar into the Keith-Iola 138kV line through Keith Switch Station. | 2024-08-19 | 2024-09-20 | 2025-02-24 | 420177.54 | 508715 |  |  | 100 | NA | 138 | 0.15 | 959 ACSS | Single Pole Concrete or Steel | NA | NA | NA | NA | 25.101(c)(5)(A) | Affidavit to be filed upon request
22012 | Myra-Spring | Cooke | Rebuild 13.8 miles of single pole, double circuit capable 138kV transmission line from Myra to Spring Substation | 2024-09-16 |  |  | 14094799 | 16669723 |  |  | 80 | 138 | 138 | 13.8 | 959 ACSS | Single Pole Concrete or Steel | 100 | 13.8 | NA | NA | 25.101(c)(5)(B) | Affidavit to be filed upon request
19033 | Picard Line Mods | Parker | Remove existing structure and install 2 monopoles to connect new Picard Sw to the Aledo-Annetta 138 kV transmission line | 2024-12-09 | 2025-01-24 |  | 721907 | 833050 |  |  | 100 | 138 | 138 | 0.07 | 959 ACSS | Single Pole Concrete or Steel | 70 | 0.07 | NA | NA | 25.101(c)(5)(A) | Affidavit to be filed upon request
22021 | Tomcat Line Mods | Johnson | Construction and removal of temporary shoo fly needed to perform work at Tomcat P.O.I. | 2024-08-26 | 2025-01-22 | NA | 338917.04 | 933648 |  |  | 100 | 138 | 138 | 0.21 | 1033 ACSR | Single Pole Wood | 70 | 0.21 | NA | NA | 25.83(a)(3) | Affidavit to be filed upon request
21031 | Woodbine Tap | Cooke | Installation of one 138kV Steel Monopole Deadeand structure to connect into Woodbine Substation | 2025-09-15 |  |  | 265760 | 399223 |  |  | 0 | 138 | 138 | 0.06 | 795 ACSR | Single Pole Concrete or Steel | 60 | 0.06 | NA | NA | 25.101(c)(5)(A) | Affidavit to be filed upon request
1903310 | Picard Switch | Parker | Establish 138kv Switch with 2 tap points | 2024-09-30 | 2024-12-12 |  | 1455981 | 1782233 |  |  | 100 | NA | 138 | NA | NA | NA | NA | NA | NA | NA | 25.83(a)(3) | Affidavit to be filed upon request
23550 | Rector Rd to Aubrey Repairs | Denton | Remove 2 tangent structures and replace with 2 deadends. | 2025-02-10 | 2025-04-15 | 2025-03-24 | 800000 | 842917 |  |  | 100 | 138 | 138 | 0.15 | 795 ACSR | Single Pole Concrete or Steel | 60 | 0.15 | NA | NA | 25.101(c)(5)(A) | Affidavit to be filed upon request
22600 | Red River Line Mods | Cooke | Replace 3 existing H-frame wood structures and install 2 deadends and one tangent due to TxDOT IH35 ROW Expansion | 2025-02-10 |  | 2025-04-17 | 1100000 | 1094700 |  |  | 99 | 138 | 138 | 0.49 | 477 ACSR | Single Pole Concrete or Steel | 70 | 0.49 | NA | NA | 25.101 (C)(5)(D) | Affidavit to be filed upon request
24550 | Sanger North-Spring Repair | Denton/Cooke | Replace 6 structures and restringing 4.5 miles of conductor and HS shield wire | 2025-01-27 | 2025-03-24 | 2025-03-20 | 1500000 | 1206983 |  |  | 100 | 138 | 138 | 4.5 | 1033 ACSR | Single Concrete Pole | 60 | 4.5 | NA | NA | 25.101(c)(5)(B) | Affidavit to be filed upon request
1901011 | Spock Switch | Hood | Establish 138kv Switch with 2 tap points | 2025-01-06 |  |  | 1750000 |  |  |  | 0 | NA | 138 | NA | NA | Single Pole Concrete or Steel | NA | NA | NA | NA | 25.83(a)(3) | Affidavit to be filed upon request
17002 | Early Line Mods | Brown | Installation of two wood, 3-pole structures and two wood H-frame structures to connect the Holder-Brownwood SS 138kV line to new Early Substation | 2025-09-15 |  |  | 355000 | 501028 |  |  | 0 | 138 | 138 | 0.12 | 477 ACSR | Single Pole and H-frame Wood | NA | NA | 100 | 0.12 | 25.101(c)(5)(A) | Affidavit to be filed upon request
2103117 | Gainesville Line Mods | Cooke | Construct and remove a shoofly and reroute the Gainesville-Sinclair and Gainesville-Red River 138kV transmission lines using 12 wood poles, allowing circuits to exit from the new bays at the expanded Gainesville Substation. | 2026-09-14 |  |  | 437500 |  |  |  | 0 | 138 | 138 | 0.26 | 4/0 ACSR & 477 ACSR | Single Pole Wood | NA | NA | NA | NA | 25.101(c)(5)(B) | Affidavit to be filed upon request
22031 | Navarro Mills Reroute | Navarro | Rebuild 1.2 miles of the Navarro Mills SW-Navarro Milles 69kV transmission line. Of that, .8 miles is rerouted out of standing water on USACE land to and adjacent property. | 2025-07-14 |  |  | 1600000 |  |  |  | 0 | 69 | 69 | 1.2 | 959 ACSS | Single Pole Concrete or Steel | 60 | 1.2 | 60 | 2 | 25.101(c)(5)(A) | Affidavit to be filed upon request
06035 | Beecham Gap Transmission Line and Substation | Coryell & Lampasas | Construct approximately 13.34 miles of 138 kV double circuit capable transmission line with single-pole structures, along with a new approximate six-acre substation sited northwest of of Copperas Cove. | 2026-09-01 |  |  | 21,877,818 T-Line/ 6,915,000 Substation |  |  |  | 0 | NA | 138 | 13.34 | 1433 ACSS | Single Steel Pole | NA | NA | 70-100 | 13.34 | 57529
22013 | Hasse-Gustine Rebuild | Comanche | Rebuild 13.3 miles of single pole, double circuit capable 138kV transmission line from Hasse to Gustine Substation | 2025-09-15 |  |  | 14500000 |  |  |  | 0 | 138 | 138 | 13.3 | 959 ACSS | Single Pole Concrete or Steel | 60 | 13.3 | NA | NA | 25.101(c)(5)(B) | Affidavit to be filed upon request
24550 | Midway-Perry Repairs | Falls | Remove and replace structures 1/5,1/8 and 1/9 | 2025-09-15 | [6 empty] | 0 | 138 | 138 | 0.52 | 959 ACSS | Single Pole Steel & H-frames |  | 0.52 | NA | NA | 25.101(c)(5)(B) | Affidavit to be filed upon request
Note on H2: aboling: Please enter only a single integer, if possible.
Note on I2: aboling: Please enter only a single integer, if possible.
Note on M2: aboling: If applicable.
Note on N2: aboling: If applicable.