## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
10-10-023 | Yellow Wolf Substation | Leon | New solar interconnection substation | 2024-03-01 |  |  | N/A | 26500000 |  |  | 90% | 345 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
30-008-00 | Gray to Ghost Town Transmission Line | Gray | New solar and wind generation interconnection | 2025-10-01 |  |  | Gray; $6,365,000; T-LINE: $54,076,000; Ghost Town: $26,941,000 |  |  |  | 9% | 345 | N/A | 28 | 1590 Falcon ACSS - 2 conductor bundle | Monopole | N/A | N/A | 175 | 14 | 56402 | Gray substation expansion, new substation Ghost Town, and new transmission line
10-031-00 | Amarillo Operation Center Remodel | Amarillo | Remodel of CTT Op Center | 2024-10-01 |  |  | N/A | 900000 |  |  | 90% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Note on H1: aboling: Please enter only a single integer, if possible.
Note on I1: aboling: Please enter only a single integer, if possible.
Note on M1: aboling: If applicable.
Note on N1: aboling: If applicable.