## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
GV01-24 | Weiderstein Substation | Guadalupe | Replace existing 20 MVA T1 with new 40 MVA PWT, plus upgrade station equipment | 2024-02-05 | 2024-06-30 |  | 2.7M |  | 3.13M |  | 100% | 138 |  | 0 | 0 | Steel/Pipe Bus | 0 | 0 | 0 | 0 |  | Complete
GV02-24 | Nash Creek Substation | Guadalupe | Replace existing 69kV station with 138 kV substation, and replace existing PWT with 20 MVA from inventory | 2024-03-01 | 2025-04-20 |  | 3.7M |  |  |  | 90% | 69 | 138 | 0 | 0 | Steel/Pipe Bus | 0 | 0 | 0 | 0 |  | Construction in progress