## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
N/A | URECC Hallsville to Gum Springs 138kV Transmission Line | Harrison | New 138 kV Transmission Line from URECC Existing Hallsville Substation to new URECC Gum Springs Substation | January 2021 | April 2021 |  | $4,960,000 (Substation); $5,522,438- $6,753,460 (Transmission) |  |  |  | 0 | N/A | 138 | 4.80 - 5.90 | 959.6 kcmil ACSS/TW - "Suwanee/TW" | Single pole, 85-115 ft, steel/concrete/ductile iron | N/A | N/A | 100 | 4.80 - 5.90 | 49603 | CCN Amendment Application filed on 7/15/19; Stipulation and Settlement Agreement Filed on 07/22/22; Pre-Hearing Conference scheduled for 08/17/22; Final Order issued on 10/6/22; ROW procurement in progress