## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost (For CCN Projects Only) | Final Estimated Project Cost | Final Actual Project Cost | % Variance | Percent Complete | Existing Voltage | Upgraded or New Voltage | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments | Final Costs Due Date | 2009-04-01
1006 | T416 (Dripping Springs to Rutherford) Relocation | Hays | Relocate seven structures as requested and reimbursed by landowner. | 2019-09-01 |  |  |  | 1844000 |  |  | 0% | 138 | 138 | 0.47 | 795 ACSR | Steel Single Pole | 100 | 0.35 | 100 | 0.47 | 25.101(c)(5)(D) | Actual construction start date has been delayed.
1000-001-0001 | Paleface to Marshall Ford (T323) | Travis | Overhaul and reconductor single circuit and triple circuit sections between Paleface and Marshall Ford substations. | 2023-09-18 |  |  |  | 12000000 |  |  | 80% | 138 | 138 | 15.2 | 959.6 ACSS Suwannee, 1 cond per phase | Steel Monopoles | 100 | 15.2 | n/a | n/a | 25.101(c)(5)(B)
400-001-0004 | Yarrington Substation | Hays | New 138 kV load-serving substation | 2024-01-08 |  | 2025-01-28 |  | 12606000 |  |  | 99% | 138 | 138 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 25.83 | Minor sitework (asphalt and grass) still ongoing to complete construction
400-001-0003 | Florence Substation | Williamson | New 138 kV load-serving substation | 2024-02-05 |  |  |  | 9427000 |  |  | 65% | 138 | 138 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 25.83
0504-001-007 | Highway 32 Capacitor Bank Addition | Hays | 138 kV capacitor bank addition | 2024-01-08 | 2024-08-02 | 2024-10-10 |  | 1491000 |  |  | 100% | 138 | 138 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 25.83
0504-001-0008 | Seward Junction Capacitor Bank Addition | Williamson | 138 kV capacitor bank addition | 2024-01-08 | 2024-12-06 | 2024-12-19 |  | 1642000 |  |  | 100% | 138 | 138 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 25.83
501-001-0005 | Lago Vista T3 Addition | Travis | Construct new substation yard for T3 yard addition | 2024-03-01 |  |  |  | 14500000 |  |  | 50% | 138 | 138 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 25.83
1000-001-0014 | Buda to Turnersville (T380) | Hays | Overhaul and rebuild the existing T380 to bundled 795 ACSR. | 2024-05-31 | 2025-01-08 | 2025-01-09 |  | 5900000 |  |  | 99% | 138 | 138 | 4.3 | 795 MCM Drake, 2 cond per phase | Steel Monopoles | 100 | 4.3 | n/a | n/a | 25.101 ( c)(5)(B)
211000005 | Trading Post to Cedar Valley (T623) | Travis | Overhaul and rebuild the existing T623 to bundled 795 ACSR. | 2024-07-01 |  |  |  | 10900000 |  |  | 50% | 138 | 138 | 6.2 | 795 MCM Drake, 2 cond per phase | Steel Monopoles | 60 | 6.2 | n/a | n/a | 25.101 ( c)(5)(B)
211000006 | Lago Vista to Nameless (T333) | Travis | Overhaul and rebuild the existing T333 to bundled 795 ACSR. | 2024-08-01 |  |  |  | 11200000 |  |  | 95% | 138 | 138 | 6 | 795 MCM Drake, 2 cond per phase | Steel Monopoles | 100 | 6 | n/a | n/a | 25.101 ( c)(5)(B)
1000-001-0016 | Transmission Line Relocation - Leander to Seward Junction (T353) | Williamson | Relocate approximately 1500ft of T353 for new development. | 2025-01-20 |  |  |  | NA - Developer Requested & Funded |  |  | 5% | 138 | 138 | 3.4 | 795 ACSR | Steel Monopoles | 60 | 3.4 | 60 | 3.4 | 25.101 ( c)(5)(D)
1001-001-9800 | T466/T524 Foundation Repair | Hays | Replace pier foundations that are cracking | 2025-02-01 |  |  |  | 2750000 |  |  | 0% | 69 & 138 | 69 & 138 | 3.35 | 69V - 795 MCM Drake, 1 cond per phase 138kV - 795 MCM Drake, 2 cond per phase | Steel Monopoles | 60 | 3.35 | 60 | 3.35 | 25.101 ( c)(5)(B) | Updated cost to reflect construction cost difference after awarding project from estimated costs.