## LCRA TSC MCPR February 2025
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
1025502 | Cedar Canyon Substation Addition [Bakersfield-Big Hill TL Addition - 1024834] | Crockett County | Upgrade substation equipment to interconnect another TSP’s 345-kV circuit from Big Hill to Bakersfield | 2022-03-07 | 2024-11-15 | 2024-11-15 |  | 11005000 |  |  | 100 | 345 | n/a | n/a | n/a | A-Frame | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B)
1025479 | Bakersfield Substation Addition [Bakersfield-Big Hill TL Addition - 1024834] | Pecos County | Upgrade substation equipment to interconnect another TSP’s 345-kV circuit from Big Hill to Bakersfield | 2022-11-28 | 2024-11-19 | 2024-11-19 |  | 6909000 |  |  | 95 | 345 | n/a | n/a | n/a | A-Frame | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B)
1024727 | Antler-Bergheim TL Add (T493) [Antler-Bergheim Transmission Line Upgrade 1024576] | New Braunfels, Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2023-10-01 | 2024-12-12 |  |  | 22586000 |  |  | 95 | 138 | n/a | 7.17 | (2) 959.6 Suwannee/ACSS/TW/HS | Steel Monopole | 100 | 7.17 | n/a | n/a | 25.101 (C)(5)(B)
1024728 | Antler Flyover-Bergheim TL Add (T389) [Antler-Bergheim Transmission Line Upgrade 1024576] | New Braunfels, Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-11-28 | 2024-12-12 |  |  | 50011000 |  |  | 95 | 138 | n/a | 7.17 | (2) 1433.6 Merrimack/ACSS/TW/HS | Steel Monopole | 100 | 7.17 | n/a | n/a | 25.101 (C)(5)(B)
1024743 | River Oaks Flyover-Hwy 46 Flyover TL Add (389) [Highway 46-River Oaks Transmission Line Upgrade - 1024590] | Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2023-08-01 | 2024-05-29 |  |  | 58136000 |  |  | 100 | 345 | n/a | 8.64 | (2) 1433.6 Merrimack/ACSS/TW/HS | Steel Monopole | 100 | 8.64 | n/a | n/a | 25.101 (C)(5)(B)
1024745 | River Oaks-Hwy 46 TL Addition (T518) [Highway 46-River Oaks Transmission Line Upgrade - 1024590] | Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2023-08-01 | 2024-05-29 |  |  | 18988000 |  |  | 100 | 138 | n/a | 8.64 | (2) 959.6 Suwannee/ACSS/TW/HS | Steel Monopole | 100 | 8.64 | n/a | n/a | 25.101 (C)(5)(B)
1021446 | Crane Sub Add [Crane Circuit Breaker Addition - 1021215] | Crane, Crane | Provide transmission service to the Crane Substation. | 2025-01-06 | 2025-03-15 |  |  | 1185000 |  |  | 0 | n/a | 138 | 0.5 | (1) 1233.6 Yukon ACSS/TW | Steel Monopole | n/a | n/a | 100 | 0.5 | 25.101 (C)(5)(A)
1029191 | Starcke-Wirtz T654 TL Add Ph. 2 - 1029191 [Starcke - Wirtz TL Storm Hardening - 1024854] | Burnet | Phase 2 - Perform storm hardening on the Starcke – Wirtz (T654) from current STR#92 to Wirtz Substation. | 2022-07-11 | 2024-05-15 | 2024-05-13 |  | 6393000 |  |  | 100 | 138 | n/a | 6.65 | (1) 795 ACSR "Drake" | Steel Monopole | Varies | 6.65 | n/a | n/a | 25.101 (C)(5)(B) | Project work split into two phases - entire circuit was noticed and reported on April 2022 MCPR
1026437 | Eckert-Nebo TL Addition (T126) [Eckert Power Transformer Upgrade - 1025306] | Gillespie | Increase the reliability of substation equipment at the Eckert Substation. | 2025-04-04 | 2025-01-17 |  |  | 404000 |  |  | 0 | 69 | n/a | 0.7 | (1) 795 ACSR "Drake" | Steel Poles | 100 | 0.7 | n/a | n/a | 25.101 (C)(5)(B)
1026439 | Sandstone Mtn-Gillespie TL Addition (T130) [Eckert Power Transformer Upgrade - 1025306] | Gillespie, Llano | Increase the reliability of substation equipment at the Eckert Substation. | 2025-04-04 | 2025-01-17 |  |  | 1128000 |  |  | 0 | 69 | n/a | 36.33 | (1) 959 SUWANNEE ACSS | Steel H-Frames | 100 | 36.33 | n/a | n/a | 25.101 (C)(5)(B)
1025850 | Ferguson-Sherwood TL Addition (T187) [Starcke-Wirtz TL Storm Hardening - 1024854] | Burnet | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2024-05-15 | 2024-05-13 |  | 1981000 |  |  | 100 | 138 | n/a | 9.35 | (1) 795 ACSR "Drake" | Steel Poles and Lattice Towers | Varies | 9.35 | n/a | n/a | 25.101 (C)(5)(B)
1029190 | Ferg-GranMtn TL Addition (T376) Ph. 2 [Starcke - Wirtz TL Storm Hardening - 1024854] | Burnet | Phase 2 - Perform storm hardening on the Granite Mountain - Wirtz (T376) transmission line from STR#92 to Wirtz Substation. | 2022-07-01 | 2024-05-15 | 2024-05-13 |  | 1328000 |  |  | 100 | 138 | n/a | 5.75 | (1) 795 ACSR "Drake" | Steel Poles and Lattice Towers | Varies | 5.75 | n/a | n/a | 25.101 (C)(5)(B) | Project work split into two phases - entire circuit was noticed and reported on May 2022 MCPR
1026089 | Wirtz-Burnet TL Addition (T218) [Starcke-Wirtz TL Storm Hardening - 1024854 | Burnet | Storm hardening to allow safe and reliable operation during extreme weather events. | 2022-07-01 | 2024-05-15 | 2024-05-13 |  | 980000 |  |  | 100 | 138 | n/a | 16.08 | (1) 795 ACSR "Drake" | Steel Poles and Lattice Towers | Varies | 16.08 | n/a | n/a | 25.101 (C)(5)(B)
1024797 | Esperanza - Boerne TL Add (T657) [Boerne-Esperanza TL Upgrade -1024583 ] | Kendall | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-12-01 | 2024-08-01 | 2024-02-14 |  | 13679000 | 14995539.25 | 9.6 | 100 | 138 | n/a | 3.9 | (2) 959 ACSS/TS Suwannee | Steel Monopole | 35 / 70 / 85 / 100 / Undefined | 3.9 | n/a | n/a | 25.101 (C)(5)(B)
1024795 | Esperanza Bypass-Boerne Split Structure TL Add (T656) [Boerne-Esperanza TL Upgrade -1024583 ] | Kendall | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2022-12-01 | 2024-08-01 | 2024-02-14 |  | 12428000 | 14192266.43 | 14.2 | 100 | 345 | n/a | 1.5 | (2) 1433 ACSS/TW Merrimack | Steel Monopole | 85' / 100' | 1.5 | n/a | n/a | 25.101 (C)(5)(B)
1024732 | Bergheim-Fair Oaks TL Addition (T238) [Bergheim-Fair Oaks Ranch Transmission Line Upgrade -1024581] | Comal, Kendall | This project will increase the reliability of the transmission facilities by replacing the aging conductor. | 2024-02-01 | 2024-11-28 |  |  | 6297000 |  |  | 95 | 138 | n/a | 4.08 | (2) 959 ACSS/TS Suwannee | Steel Monopole | 100' | 4.08 | n/a | n/a | 25.101 (C)(5)(B)
1024733 | Bergheim-Fair Oaks Flyover TL Addition (T656) [Bergheim-Fair Oaks Ranch Transmission Line Upgrade -1024581] | Kendall | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2024-02-01 | 2024-11-28 |  |  | 25822000 |  |  | 95 | 345 | n/a | 4.08 | (2) 1433 ACSS/TW Merrimack | Steel Monopole | 100' | 4.08 | n/a | n/a | 25.101 (C)(5)(B)
1024799 | Boerne-Welfare TL Addition (T228) [Boerne Split-Welfare TL Upgrade - 1024582] | Kendall | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2025-01-13 | 2026-05-01 | 2025-12-15 |  | 11906000 |  |  | 10 | 138 | n/a | 9.51 | (2) 959 ACSS/TS Suwannee | Steel Monopole | 35 / 70 / 85 / 100 / Undefined | 9.51 | n/a | n/a | 25.101 (C)(5)(B)
1024801 | Boerne Split Structure-Welfare Flyover (T656) [Boerne Split-Welfare TL Upgrade - 1024582] | Kendall | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2025-01-13 | 2026-05-01 | 2025-12-15 |  | 69597000 |  |  | 10 | 345 | n/a | 7.25 | (2) 1433 ACSS/TW Merrimack | Steel Monopole | 85/100 | 7.25 | n/a | n/a | 25.101 (C)(5)(B)
1026324 | Bellville - Hwy. 36 TL Addition (T467) [Containment Structures Transmission Line Upgrade 1025812] | Washington, Austin | Install full dead-end containment structures | 2023-08-07 | 2023-11-06 | 2023-11-06 |  | 3587000 |  |  | 100 | 138 | n/a | 13.11 | (1) 959.6 ACSS/TW "SUWANNEE" | Steel Poles and Steel H-Frames | CL width undefined | 13.11 | n/a | n/a | 25.101 (C)(5)(B)
1027017 | Clear Springs Cir Bkr Add (T752) TL OH- 1027017 [Clear Springs Generator Circuit Breaker Addition - 1026518] | Seguin, Guadalupe | Upgrade the (S454) Clear Springs Substation to facilitate an interconnection project | 2022-07-19 | 2025-01-24 |  |  | 599000 |  |  | 47 | n/a | 138 | 0.1 | (1) 959.6 ACSS Suwannee | Steel Monopole | Substation property & POI 80' x 80' plot | Substation property | 80 x 80 plot | 80 x 80 plot | 25.101 (C)(5)(A)
1024742 | Bastrop W-Bluebonnet (T516) TL Addition [Bastrop West-Bluebonnet (T516) TL Relocation - 1024616] | Bastrop | Relocate T516 within existing ROW to accommodate TxDOT widening of State Hwy. 71 | 2024-03-01 | 2024-04-29 | 2024-05-13 |  | 2923000 | 2549499.55 | -12.8 | 100 | 138 | n/a | 6.1 | (1) Drake 795 ACSR | Steel Monopoles & Wood H-Frames | 100 | 6.1 | n/a | n/a | 25.101 (C)(5)(F)
1017679 | Peach-Headwaters TL Addition (T288) [T288 CTEC Transfer] [Mountain Home Substation Addition 1017394] | Gillespie | Remove existing 69kV structures and conductor with 138 kV structures and 795 ACSR Drake. Will also install OPGW. | 2023-01-16 | 2024-04-19 | 2024-04-19 |  | 32579000 | 38758388.62 | 19 | 100 | 69 | 138 | 21.72 | (1) 795 ACSR DRAKE | Steel Poles | Varies | 21.72 | n/a | n/a | 25.101 (C)(5)(B)
1027871 | Gillespie-Kerrville Stadium TL Addition (T207) [Mountain Home Substation Addition - 1017394] | Gillespie | Modification of two spans on T207 to accommodate the upgrade of T288 | 2023-01-01 | 2024-04-19 | 2024-04-19 |  | 150000 | 159554.38 | 6.4 | 100 | 138 | n/a | 22.8 | (1) 795 ACSR "Drake" (2) 3/8" EHS | Steel and Wood H-Frames | 75 - 100 | 22.8 | n/a | n/a | 25.101 (C)(5)(B)
1027381 | Twin Buttes - Angelo Solar TL Addition (T758) [Twin Buttes 345-kV Circuit Breaker Addition- 1027351] | Tom Green | Install transmission interconnection facilities for Twin Buttes Substation and Angelo Solar | 2023-01-30 | 2023-11-17 |  |  | 6162000 | 5864678.61 | -4.8 | 100 | n/a | 345 | 1 | (2) 959.6 ACSS "Suwanee"; (2)DNO-11243 | Steel Monopoles & H-Frames | n/a | n/a | 165 | 1 | 25.101 (C)(5)(A)
1028864 | BakerFld-CCanyon TL Addition [Bakersfield-Big Hill TL Addition - 1024834] | Pecos/Crockett | Re-terminate existing circuit at Cedar Canyon Substation and install new conductor and shield wire. | 2023-09-01 | 2024-11-15 | 2024-11-15 |  | 180000 |  |  | 100 | n/a | 345 | 0.06 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B) | STEC Owned ROW
1028859 | Bksfield-CCanyon TL Addition [Bakersfield-Big Hill TL Addition - 1024834] | Pecos/Crockett | String conductor and shield wire to STEC owned POI structures. | 2023-09-01 | 2024-11-15 | 2024-11-15 |  | 336000 |  |  | 100 | n/a | 345 | 0.15 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole | n/a | n/a | n/a | n/a | 25.101 (C)(5)(B) | STEC Owned ROW
1029595 | Birdhouse-Starling Solar (T757) [Birdhouse Substation Addition - 1027349] | Gonzales | Provide a point of interconnection for a new 123 MW solar system at the new 138-kV Birdhouse Substation by adding an initial three breaker ring bus. | 2023-04-19 | 2024-12-02 | 2025-11-17 |  | 208000 |  |  | 95 | n/a | 138 | 0.07 | (1) 959.6 ACSS Suwannee | Steel Pole | n/a | n/a | 100 | 0.07 | 25.101 (C)(5)(A)
1024717 | Lakeway - Marble Falls Ph. 1 (T497) TL Addition [Lakeway - Marble Falls TL Storm Hardening - 1024594] | Travis | Replace structures and conductor | 2023-07-01 | 2024-05-15 |  |  | 8431000 |  |  | 25 | 138 | n/a | 22.97 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole | 100 | 22.97 | n/a | n/a | 25.101 (C)(5)(B)
1024717 | Lakeway - Marble Falls Ph. 1A (T497) TL Addition [Lakeway - Marble Falls TL Storm Hardening - 1024594] | Travis | Replace structures and conductor | 2023-07-01 | 2024-06-30 |  |  | 8431000 |  |  | 100 | 138 | n/a | 22.97 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole | 100 | 22.97 | n/a | n/a | 25.101 (C)(5)(B)
1024718 | Paleface - Bee Creek (T458) TL Addition [Lakeway - Marble Falls TL Storm Hardening - 1024594] | Travis | Replace structures and conductor | 2023-07-01 | 2024-05-15 |  |  | 23776000 |  |  | 100 | 138 | n/a | 8.47 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole | 100 | 8.47 | n/a | n/a | 25.101 (C)(5)(B)
1024719 | Bee Creek - Lakeway (T525) TL Addition [Lakeway - Marble Falls TL Storm Hardening - 1024594] | Travis | Replace structures and conductor | 2023-07-01 | 2024-06-30 |  |  | 7788000 |  |  | 50 | 138 | n/a | 4.26 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole | 100 | 4.26 | n/a | n/a | 25.101 (C)(5)(B)
1025505 | Marshall Ford - Lakeway (T180) TL Add [Lakeway - Marble Falls TL Storm Hardening - 1024594] | Travis | Replace structures and conductor | 2023-07-01 | 2023-02-05 | 2023-02-05 |  | 9733000 | 3111650.88 | -68 | 100 | 138 | n/a | 5.03 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole | 100 | 5.03 | n/a | n/a | 25.101 (C)(5)(B)
1029888 | T161 TL Addition [Marshall Ford - McNeil TL Storm Hardening -1024596] | Austin/Travis | Replace one structure | 2023-07-15 | 2023-12-04 |  |  | 695000 | 757120.89 | 8.9 | 100 | 69 | n/a | 12.9 | (1) 795 ACSR/GA2 "DRAKE" | Wood H-Frames and Steel H-Frames | 100 | 13.3 | n/a | n/a | 25.101 (C)(5)(B)
1024734 | Spicewood-McNeil Storm Hardening TL Addition (T242) [Marshall Ford - McNeil TL Storm Hardening -1024596] | Austin/Travis | Replace structures conductor and OPGW | 2023-10-01 | 2024-05-15 |  |  | 3813000 |  |  | 100 | 138 | n/a | 8.7 | (1) 795 ACSR/GA2 "DRAKE" | Steel Poles and Steel H-Frames | 100 | 8.7 | n/a | n/a | 25.101 (C)(5)(B)
1024731 | Marshall Ford-Spicewood Storm Hardening TL Addition (T162) [Marshall Ford - McNeil TL Storm Hardening -1024596] | Austin/Travis | Replace structures conductor and OPGW | 2023-07-15 | 2023-12-31 | 2024-01-31 |  | 2791000 | 3452936.37 | 23.7 | 100 | 138 | n/a | 8.04 | (1) 795 ACSR/GA2 "DRAKE" | Steel Poles and Steel H-Frames | 100 | 8.04 | n/a | n/a | 25.101 (C)(5)(B)
1024726 | Marshall Ford-McNeil Storm Hardening TL Addition (T197) [Marshall Ford - McNeil TL Storm Hardening -1024596] | Austin/Travis | Replace structures conductor and OPGW | 2023-07-15 | 2024-05-15 |  |  | 29840000 |  |  | 100 | 138 | n/a | 15.5 | (1) 795 ACSR/GA2 "DRAKE" | Steel Poles and Steel H-Frames | 100 | 15.5 | n/a | n/a | 25.101 (C)(5)(B)
1026908 | Altair-Nada TL Addition (T545) [Altair-Garwood TL Overhaul - 1020884] | Colorado | Replace eight existing structures on T545 at intersection with T546 to maintain operating clearance. | 2023-08-01 | 2024-06-14 |  |  | 3894000 |  |  | 100 | 138 | n/a | 14.17 | (1) 795 ACSR/GA2 "DRAKE" | Steel Pole and Steel H-frame | 60' | 14.17 | n/a | n/a | 25.101 (C)(5)(B)
1020885 | Altair-Garwood OH TL Addition (T546) [Altair-Garwood TL Overhaul - 1020884] | Colorado | Perform overhaul of T546 (including all tapped lines) to improve reliability of structures and conductors. | 2023-08-01 | 2024-06-14 |  |  | 23824000 |  |  | 100 | 69 | n/a | 8.59 | (1) 795 ACSR/GA2 "DRAKE" | Steel Pole and Steel H-frame | 75 | 8.59 | n/a | n/a | 25.101 (C)(5)(B)
1027162 | FPP Lytton Springs (T255) TL Addition -[FPP Yard 2 - Lytton Springs Transmission Line Overhaul - 1024839] | Caldwell, Bastrop, and Fayette | Evaluate T255 structures and clearances using the existing conductor and shield wire while adding containment dead-end structures per L4100. Insulators and hardware on existing towers will need to be removed and replaced. 8 structure insulators were previously replaced and will only need hardware replaced. 30-32 structures will be removed and replaced with 60-64 new dead-end single circuit steel poles. | 2024-07-08 | 2025-01-15 |  |  | 97568000 |  |  | 10 | 345 | n/a | 61.32 | (2) 795 ACSR/GA2 DRAKE (2) 715.5 ACSR REDWING | Steel Pole and Lattice Tower | 100 | 61.32 | n/a | n/a | 25.101 (C)(5)(B)
1028960 | Cuero - Guadalupe TL Addition (T609) [Cuero Substation Upgrade - 1026635] | De Witt | LCRA TSC will improve the bus at Cuero substation by reconfiguring the existing bus from single bus single breaker to a breaker and a half configuration. This bus improvement will include the upgrade of bus work, switches, breakers, instrument transformers, surge arresters, protective schemes, the replacement of Cuero AT3, and facility structures as required. A new control enclosure is also necessary to meet high wind requirements. | 2023-07-03 | 2024-05-08 | 2024-05-08 |  | 1015000 |  |  | 100 | 138 | n/a | 2.75 | (1) 959.6 ACSS "SUWANNEE" | Steel Poles and Lattice Towers | 85 | 2.75 | n/a | n/a | 25.101 (C)(5)(B)
1028961 | Cuero - Yoakum TL Addition (T198) [Cuero Substation Upgrade - 1026635] | De Witt | LCRA TSC will improve the bus at Cuero substation by reconfiguring the existing bus from single bus single breaker to a breaker and a half configuration. This bus improvement will include the upgrade of bus work, switches, breakers, instrument transformers, surge arresters, protective schemes, the replacement of Cuero AT3, and facility structures as required. A new control enclosure is also necessary to meet high wind requirements. | 2023-07-03 | 2024-05-08 | 2024-05-08 |  | 919000 |  |  | 100 | 138 | n/a | 13.83 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole and Steel H-Frame | 100 | 13.84 | n/a | n/a | 25.101 (C)(5)(B)
1030105 | Cooks Point-Lyle Wolz (T680) Transmission Line Upgrade - 1030105 | Burleson | Conduct railway mitigation | 2023-06-05 | 2023-07-11 | 2023-07-11 |  | 2600000 |  |  | 100 | 138 | n/a | 18.4 | (2) 795 ACSR/GA2 "DRAKE" | Steel Poles | 80 | 18.4 | n/a | n/a | 25.101 (C)(5)(B)
1024782 | Guadalupe - Lost Creek TL Addition (T541) [Guadalupe - Lost Creek TL Upgrade - 1027911] | De Witt, Fayette | Increase transmission service reliability by replacing the current conductors | 2024-01-01 | 2024-05-15 |  |  | 5865000 | 4858801.44 | -17.2 | 100 | 138 | n/a | 6.08 | (1) 795 ACSR "DRAKE" | Steel Pole | 60 | 6.08 | n/a | n/a | 25.101 (C)(5)(B)
1024729 | Highway 46-Antler TL Add (T610) [Antler-Highway 46 Transmission Line Upgrade - 1024577] | Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2023-08-21 | 2024-06-29 |  |  | 9242000 |  |  | 100 | 138 | n/a | 10.4 | (1) 959.6 ACSS/TW-HS "SUWANNEE" | Steel Pole | 100 | 10.4 | n/a | n/a | 25.101 (C)(5)(B)
1024730 | Highway 46 Flyover-Antler Flyover TL Add (T389) [Antler-Highway 46 Transmission Line Upgrade - 1024577] | Comal | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2023-08-21 | 2024-06-29 |  |  | 66568000 |  |  | 100 | 345 | n/a | 34.17 | (2) 959.6 ACSS/TW-HS "SUWANNEE" | Steel Pole | 100 | 34.17 | n/a | n/a | 25.101 (C)(5)(B)
1024807 | Welfare - Kendall TL Addition (T584) - [Kendall-Welfare TL Upgrade -1024592] | Kendall | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2025-01-13 | 2026-05-01 | 2026-08-28 |  | 16051000 |  |  | 5 | 138 | n/a | 10.55 | (1) 959.6 ACSS/TW-HS "SUWANNEE" | Steel Pole | 100 | 10.55 | n/a | n/a | 25.101 (C)(5)(B)
1024809 | Welfare Flyover - Kendall TL Addition (T656)[Kendall-Welfare TL Upgrade -1024592] | Kendall | This project will Increase the reliability of the transmission facilities by replacing the aging conductor | 2025-01-13 | 2026-05-01 | 2026-08-28 |  | 90581000 |  |  | 5 | 345 | n/a | 27.22 | (2) 959.6 ACSS/TW-HS "SUWANNEE" | Steel Pole | 100 | 27.22 | n/a | n/a | 25.101 (C)(5)(B)
1027166 | Marshall Ford-Spicewood TL Addition (T162)[Marshall Ford-Spicewood TL Storm Hardening - 1026917] | Travis | Project will replace STR 1-6 coming out of MF substation along with conductor and OPGW | 2023-08-01 | 2024-01-31 |  |  | 2932400 | 1728138.16 | -41.1 | 100 | 138 | n/a | 8.09 | (1) 795 ACSR "DRAKE" | Steel H-Frame and Steel Poles | 100 | 8.09 | n/a | n/a | 25.101 (C)(5)(B)
1027207 | Flatonia-Muldoon TL Addition (T133)(T739) [Flood Mitigation FY23 System Upgrade - 1026636] | Fayette | Increase the reliability of transmission facilities by addressing erosion near transmission line structures. | 2024-09-30 | 2024-12-02 | 2024-12-06 |  | 520000 |  |  | 100 | 138 | n/a | 8.6 | (1) 959.6 ACSS/TW "SUWANNEE" | Wood/ Steel H-Frames, Steel Poles & Steel Lattice | 100 | 8.6 | n/a | n/a | 25.101 (C)(5)(B)
1029097 | T437 POI Tap TL Addition [Saxet Substation Addition - 1027352] | Nueces | Provide transmission service to a load-service substation | 2025-02-17 |  |  |  | 563000 |  |  | 0 | 138 | n/a | 17.34 | (2) 795 ACSR "DRAKE" | Wood Poles & Steel Poles | 60 | 17.34 | n/a | n/a | 25.101 (C)(5)(B)
1029096 | T522 POI Tap TL Addition [Saxet Substation Addition - 1027352] | Nueces | Provide transmission service to a load-service substation | 2024-05-16 | 2024-07-24 |  |  | 742000 |  |  | 0 | 138 | n/a | 10.17 | (2) 795 ACSR "DRAKE" | Wood Poles & Steel Poles | 60 | 10.17 | n/a | n/a | 25.101 (C)(5)(B)
1017683 | Gillespie-Goehmann Lane TL Addition (T287) [Gillespie County System Upgrade - 1029853] | Gillespie | Relocate the existing LCRA TSC-owned Gillespie to Live Oak 69-kV transmission circuit (T131) in order to connect with the existing CTEC-owned Live Oak to Goehmann transmission circuit (T287) to create a new Gillespie to Goehmann 69-kV transmission circuit. | 2023-08-01 | 2024-05-15 | 2024-05-15 |  | 1611000 | 1194025.97 | -25.9 | 100 | 69 | n/a | 7.73 | (1) 959.6 ACSS/TW "SUWANNEE" | Steel Pole | 40 | 7.73 | n/a | n/a | 25.101 (C)(5)(B)
1017681 | Fredericksburg-Peach TL Add (T379) [Gillespie County System Upgrade - 1029853] | Gillespie | Loop the Gillespie to Fredericksburg 138-kV transmission circuit (T379) into a new 138-kV yard at Live Oak substation. | 2023-08-01 | 2024-05-15 | 2024-05-15 |  | 1195000 | 1188228.59 | -0.6 | 100 | 138 | n/a | 0.62 | (1) 959.6 ACSS/TW "SUWANNEE" | Steel H-Frame and Poles | 100 | 0.62 | n/a | n/a | 25.101 (C)(5)(B)
1027870 | Peach-Gillespie TL Add (T679) [Gillespie County System Upgrade - 1029853] | Gillespie | Loop the Gillespie to Fredericksburg 138-kV transmission circuit (T379) into a new 138-kV yard at Live Oak substation. | 2023-08-01 | 2024-05-15 | 2024-05-15 |  | 1090000 | 1848348.55 | 69.6 | 100 | 138 | n/a | 3.1 | (1) 959.6 ACSS/TW "SUWANNEE" | Steel Pole | 100 | 3.1 | n/a | n/a | 25.101 (C)(5)(B)
1027614 | Chief Brady - Georgetown Transmission Line Addition (T355) [Chief Brady - Georgetown Transmission Line Upgrade - 1027397] | Williamson | Upgrade existing T355 to achieve a higher operational rating | 2024-08-26 | 2025-01-10 |  |  | 12660000 |  |  | 30 | 138 | n/a | 3 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole | 100 | 3 | n/a | n/a | 25.101 (C)(5)(B)
1027615 | Chief Brady-Round Rock (T378)TL Addition [Chief Brady - Round Rock TL Upgrade - 1027398] | Williamson | Upgrade existing T378 to achieve a higher operational rating | 2024-02-12 | 2024-06-30 | 2024-07-01 |  | 12219000 |  |  | 99 | 138 | n/a | 5.1 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole | 100 | 5.1 | n/a | n/a | 25.101 (C)(5)(B)
1030373 | Peach-Live Oak TL Addition (T743)[Gillespie County System Upgrade - 1029853] | Gillespie | Connect the CTEC owned Live Oak Substation with the new LCRA TSC Peach Substation | 2023-09-01 | 2024-04-19 | 2024-04-19 |  | 667000 | 349765.98 | -47.6 | 100 | n/a | 138 | 0.11 | (1) 795 ACSR/GA2 "DRAKE" | Steel Pole | n/a | n/a | 100 | 0.11 | 25.101 (C)(5)(A)
1029476 | Dale Power Transformer TL Addition (T125) [Dale Power Transformer Upgrade - 1026519] | Caldwell | Upgrade the PWT at the Dale Substation | 2023-11-06 | 2024-08-30 |  |  | 289000 |  |  | 100 | 69 | n/a | 7.29 | (1) 4/0 ACSR "PENGUIN" (1) 795 ACSR/GA2 "DRAKE" | Wood H-Frames & Steel Pole | 65 | 7.29 | n/a | n/a | 25.101 (C)(5)(B)
1027395 | North McCamey - Bearkat 345-kV Transmission Project (CCN) [North McCamey - Bearkat 345-kV TL Addition - 1027395] | Glascock, Reagan, Upton | This joint CCN project is a new double-circuit, 345-kV transmission line connecting LCRA TSC's existing North McCamey Switch Station to WETT's existing Bearkat Switching Station. | 2023-12-31 | 2026-06-01 |  |  | LCRA TSC T-Line Costs $146,500,000; LCRA TSC Substation Costs $11,800,000 |  |  | 0 | n/a | 345 | 33; tbd | 1926.9 kcmil ACSS/HS/TW Cumberland | Double-circuit steel lattice towers | n/a | n/a | 160; varies | 33; LCRA TSC half | 55120 | Commission approved Route NM19-OXY on 12/14/23. Joint CCN Application w/ WETT filed on 6/22/23. This docket was combined with PUC Docker No. 55121
1027561 | North McCamey - Sand Lake 345-kV Transmission Project (CCN) [North McCamey - Sand Lake TL Addition - 1027402] | Crane, Ward, Upton | This joint CCN project is a new double-circuit, 345-kV transmission line connecting LCRA TSC's existing North McCamey Switching Station to Oncor's existing Sand Lake Station. | 2023-12-31 | 2026-06-01 |  |  | LCRA T-Line Costs $159,264,500; LCRA TSC Substation Costs $11,800,000 |  |  | 0 | n/a | 345 | 44; tbd | 1926.9 kcmil ACSS/TW | Double-circuit steel lattice towers | n/a | n/a | 160; varies | 44; LCRA TSC half | 55121 | Commission approved Route 65 on 11/30/23; Joint CCN Application w/ Oncor filed on 6/22/23.
1024957 | Doss-Headwaters TL Addition (T508)[Doss-Headwaters TL Overhaul - 1024902] | Gillespie | Overhaul the 14.1 mile Doss-Headwaters T508 69kV transmission line. | 2023-10-01 | 2026-06-30 |  |  | 27006000 |  |  | 74 | 69 | n/a | 14.2 | (1) 795 ACSR/GA2 "DRAKE" | Steel Pole and H-frames | 80 | 14.2 | n/a | n/a | 25.101 (C)(5)(B)
1027031 | McCarty - Rattler TL Addition (T725) [McCarty Lane-Rattler TL Upgrade - 1026919] (T725) | Hays | Upgrading and increasing the capacity of the McCarty Lane to Rattler 138-kV transmission line | 2023-10-15 | 2024-01-24 | 2024-01-12 |  | 3245000 | 2283493.28 | -29.6 | 100 | 138 | n/a | 1.07 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole and H-frames | 80 | 1.07 | n/a | n/a | 25.101 (C)(5)(B)
1027033 | Rattler-Redwood TL Addition (T262) [Ratter-Redwood TL Upgrade - 1026293] | Hays | Upgrading and increasing the capacity of the Rattler to Redwood 138-kV transmission line. | 2023-10-15 | 2024-05-31 | 2024-05-15 |  | 4532000 |  |  | 100 | 138 | n/a | 1.27 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole and H-frames | 80 | 1.27 | n/a | n/a | 25.101 (C)(5)(B)
1029761 | Lakeway - Marble Falls Ph. 2 (T497) TL Addition [Lakeway - Marble Falls TL Storm Hardening - 1024594] | Burnet County Travis County | Replacing structures and conductor for reliability purposes from Paleface to Marble Falls | 2023-07-01 | 2025-05-15 |  |  | 2240000 |  |  | 50 | 138 | n/a | 22.97 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole | 100 / 75 | 22.97 | n/a | n/a | 25.101 (C)(5)(B)
1028237 | Soda Lake Generator CB TL Addition [Soda Lake Generator Circuit Breaker Addition - 1027750] | Upton | Adding one point of interconnection at Soda Lake Substation | 2023-11-01 | 2024-04-15 | 2024-04-22 |  | 610000 |  |  | 0 | 138 | n/a | 0.04 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole | n/a | n/a | 100 | 0.04 | 25.101 (C)(5)(A) | Generator conveyed ROW
1028341 | Nixon - Leesville TL Addition (T605)[Leesville Substation Addition - 1028249] | Gonzales | Install structures, conductor, and shield wire at new Leesville Substation | 2023-11-27 | 2024-05-09 | 2024-05-09 |  | 954000 |  |  | 100 | 138 | n/a | 11.51 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole | 65 | 11.51 | n/a | n/a | 25.101 (C)(5)(A)
1029055 | Leesville - Deer Creek TL Addition (T761)[Leesville Substation Addition - 1028249] | Gonzales | Install structures, conductor, and shield wire at new Leesville Substation. | 2023-11-27 | 2024-05-09 | 2024-05-09 |  | 713000 |  |  | 100 | 138 | n/a | 7.26 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole | 65 | 7.26 | n/a | n/a | 25.101 (C)(5)(A)
1029058 | Leesville - Rocinate Solar TL Addition (T762)[Leesville Substation Addition - 1028249] | Gonzales | Install POI Structure and string conductor and shield wire | 2023-11-27 | 2025-10-14 | 2025-10-21 |  | 391000 |  |  | 50 | 138 | n/a | 0.06 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole | 65 | 0.06 | n/a | n/a | 25.101 (C)(5)(A)
1027039 | Copperas Cove ONCOR - PEC TL Addition (T393) - [CppCve ONCOR-CppCVE PEC TL OH - 1026912] | Coryell/Lampasas | Perform an overhaul on the 2.4 mile portion of T393 Copperas Cove (Oncor) - Copperas Cove (PEC) 138-kV transmission line between Oncor-tie at structure 35/8 and Copperas Cove (PEC) Substation. | 2024-01-08 | 2024-05-14 | 2024-05-15 |  | 10449000 |  |  | 20 | 138 | n/a | 3.31 | (1) 959.6 ACSS "SUWANNEE" | Steel H frame | 100 | 3.31 | n/a | n/a | 25.101 (C)(5)(B)
1027014 | Sheriff’s Posse – Schumansville TL Addition (T307)[Sheriff’s Posse – Schumansville Transmission Line Storm Hardening - 1026930 | Comal, Guadalupe | Perform storm hardening work on 38 structures | 2024-01-02 | 2024-05-15 | 2024-05-15 |  | 9221000 |  |  | 100 | 138 | n/a | 5.65 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole | 80 | 5.65 | n/a | n/a | 25.101 (C)(5)(B)
1028187 | Elroy-Wolf Lane TL Addition (T582) [Wolf Lane Substation Upgrade - 1026526] | Bastrop | Upgrade Wolf Lane Substation to a 3000A, 138-kV single bus single breaker arrangement | 2024-10-01 | 2024-12-20 |  |  | 769000 |  |  | 100 | 138 | n/a | 3.78 | (1) 795 ACSR/GA2 "DRAKE" | Wood & Steel H-Frames, Steel Poles, Lattice | 100 | 3.78 | n/a | n/a | 25.101 (C)(5)(B)
1028186 | Wolf Lane-Wyldwood TL Addition (T141) [Wolf Lane Substation Upgrade - 1026526] | Bastrop | Upgrade Wolf Lane Substation to a 3000A, 138-kV single bus single breaker arrangement | 2024-10-01 | 2024-12-10 |  |  | 587000 |  |  | 100 | 138 | n/a | 5.85 | (1) 795 ACSR/GA2 "DRAKE" | Wood & Steel H-Frames, Steel Poles | 100 | 5.85 | n/a | n/a | 25.101 (C)(5)(B)
1028870 | RR-Spanish Oak (T642) TL Addition [Chief Brady - Round Rock TL Upgrade - 1027398] | Williamson | Upgrade transmission line to achieve a higher operational rating. | 2024-03-01 | 2024-04-30 | 2024-04-30 |  | 173000 |  |  | 99 | 138 | n/a | 7.84 | (1) 795 ACSR/GA2 "DRAKE" | Steel Pole | 100 | 7.84 | n/a | n/a | 25.101 (C)(5)(B)
1025194 | T614 Shoo-Fly Pilot Grove-Yoakum Gartner Rd. [Pilot Grove-Yoakum Gartne Rd TL Overhaul - 1024852] | De Witt | Replace T614 conductor with single-Suwannee. Replace structures with138 kV double-circuit Suwannee capable structures. Install OPGW. | 2024-09-09 | 2025-05-12 | 2025-05-12 |  | 12673000 |  |  | 93 | 138 | n/a | 9.27 | (1) 336.4 ACSR "LINNET" (1) 959 ACSS "SUWANNEE" | Wood Poles, Steel Poles | 55-100 | 7.81 | n/a | 1.46 | 25.101 (C)(5)(B)
1029586 | T510 TL Addition [John Dumas Substation Addition - 1029552] | Caldwell | Provide transmission point of interconnection to a new 184 MW natural gas resource via the new 345-kV John Dumas Substation on T511 between Clear Springs and Hornsby Substations. | 2024-07-15 | 2024-10-14 | 2024-10-14 |  | 3419000 |  |  | 100 | 345 | n/a | 75.46 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole & Steel Lattice | 120 | 75.46 | n/a | n/a | 25.101 (C)(5)(A)
1029588 | T511 TL Addition [John Dumas Substation Addition - 1029552] | Caldwell | Provide transmission point of interconnection to a new 184 MW natural gas resource via the new 345-kV John Dumas Substation on T511 between Clear Springs and Hornsby Substations. | 2024-07-15 | 2024-11-20 | 2024-11-20 |  | 2384000 |  |  | 100 | 345 | n/a | 24.85 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole & Steel Lattice | 120 | 24.85 | n/a | n/a | 25.101 (C)(5)(A)
1030287 | T775 TL Addition [John Dumas Substation Addition - 1029552] | Caldwell | Provide transmission point of interconnection to a new 184 MW natural gas resource via the new 345-kV John Dumas Substation on T511 between Clear Springs and Hornsby Substations. | 2024-07-15 | 2024-11-20 | 2024-11-20 |  | 358000 |  |  | 100 | 345 | n/a | 32.32 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole & Steel Lattice | 120 | 32.32 | n/a | n/a | 25.101 (C)(5)(B)
1030289 | T776 TL Addition [John Dumas Substation Addition - 1029552] | Caldwell | Provide transmission point of interconnection to a new 184 MW natural gas resource via the new 345-kV John Dumas Substation on T511 between Clear Springs and Hornsby Substations. | 2024-07-15 | 2024-11-20 | 2024-11-20 |  | 1015000 |  |  | 100 | n/a | 345 | 0.04 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole | n/a | n/a | 100 | 0.04 | 25.101 (C)(5)(B) | New ROW on existing LCRA TSC property
1030291 | T777 TL Addition [John Dumas Substation Addition - 1029552] | Caldwell | Provide transmission point of interconnection to a new 184 MW natural gas resource via the new 345-kV John Dumas Substation on T511 between Clear Springs and Hornsby Substations. | 2024-07-15 | 2024-11-20 | 2024-11-20 |  | 1817000 |  |  | 100 | n/a | 345 | 0.1 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole | n/a | n/a | 100 | 0.1 | 25.101 (C)(5)(B) | New ROW on existing LCRA TSC property
1030758 | Florence TL Addition (T413) [Florence Substation Addition 1029123 - Phase 1] | Williamson | Design and construct the high side of the Florence substation. Pedernales Electric Cooperative will design and own the Circuit Switcher and the PWT as well as the rest of the low side at Florence Substation. | 2024-05-15 | 2026-03-17 | 2026-03-18 |  | 736000 |  |  | 0 | 138 | n/a | 9.72 | (1) 959 ACSS "SUWANNEE" (1) 795 ACSR/GA2 "DRAKE" | Concrete and Steel monopoles | 60 | 9.68 | n/a | 0.04 | 25.101 (C)(5)(A) | New ROW on existing LCRA TSC property
1031378 | Florence TL Addition (781) [Florence Substation Addition 1029123 - Phase 1] | Williamson | Design and construct the high side of the Florence substation. Pedernales Electric Cooperative will design and own the Circuit Switcher and the PWT as well as the rest of the low side at Florence Substation. | 2024-05-15 | 2026-03-17 | 2026-03-18 |  | 966000 |  |  | 0 | 138 | n/a | 4.93 | (1) 959 ACSS "SUWANNEE" (1) 795 ACSR/GA2 "DRAKE" | Concrete and Steel monopoles | 60 | 4.88 | n/a | 0.05 | 25.101 (C)(5)(A) | New ROW on existing LCRA TSC property
1030798 | B&B Gravel Switch Addition (T546) [B&B Gravel Switch Substation Upgrade - 1030619] | Colorado | Increase transmission service reliability of the Garwood Pump Substation by incorporating a gang operated air break (GOAB) switch between B&B Gravel and Garwood Pump. | 2024-07-26 | 2024-06-14 | 2024-09-26 |  | 874000 |  |  | 100 | 69 | n/a | 8.79 | (1) 795 ACSR "DRAKE" | Steel Monopoles & Steel H-Frames | 60 | 8.79 | n/a | n/a | 25.101 (C)(5)(B)
1030768 | Gillieland Creek - Hutto TL Addition (T512) [Limmer Substation Addition] | Travis | This project will construct the new Limmer Substation. Limmer Substation will cut-in T510 Hutto to Zorn near Str 413 and will be the 345-kV POI for the new Oncor Hutto East Substation | 2025-01-06 | 2025-04-14 | 2025-05-15 |  | 5153000 |  |  | 5 | 345 | n/a | 14.17 | (2) 959.6 ACSS/TW "SUWANNEE" | Steel Lattice & Steel Pole | 120 | 14.17 | n/a | n/a | 25.101 (C)(5)(A)
1030693 | Goforth - Canyon TL Addition (T490)[Yarrington (PEC) Substation Addition -1029129] | Hays | Connect T490 Goforth (PEC) - Canyon to the new Yarrington substation. Install a 138-kV ring bus rated for at least 3000 amps. | 2024-04-02 |  |  |  | 853000 |  |  | 0 | 138 | n/a | 3.58 | (1) 959 ACSS "SUWANNEE" (1) 795 ACSR/GA2 "DRAKE" | Wood H-Frames & Steel Poles | 100 | 3.58 | n/a | n/a | 25.101 (C)(5)(A)
1031223 | Yarrington - Canyon TL Addition (T782)[Yarrington (PEC) Substation Addition -1029129] | Hays | Connect T490 Goforth (PEC) - Canyon to the new Yarrington substation. Install a 138-kV ring bus rated for at least 3000 amps. | 2024-04-02 |  |  |  | 710000 |  |  | 0 | 138 | n/a | 2.74 | (1) 959 ACSS "SUWANNEE" (1) 795 ACSR/GA2 "DRAKE" | Wood H-Frames & Steel Poles | 100 & 75 | 2.74 | n/a | n/a | 25.101 (C)(5)(A)
1027646 | Plum - Muldoon (T133) TL Addition [Plum - Flatonia TL Overhaul - 1027645] | Fayette | Perform an overhaul on the 19.6 mile T133/T739 Flatonia - Plum 138-kV transmission line. | 2024-08-19 | 2025-09-07 | 2025-03-31 |  | 4338000 |  |  | 60 | 138 | n/a | 11.07 | (1) 959.6 ACSS/TW "SUWANNEE" | Steel H-frame & Steel Pole | 100 | 11.07 | n/a | n/a | 25.101 (C)(5)(B)
1029733 | Muldoon - Flatonia (T739) TL Addition [Plum - Flatonia TL Overhaul - 1027645] | Fayette | Perform an overhaul on the 19.6 mile T133/T739 Flatonia - Plum 138-kV transmission line. | 2024-08-19 | 2025-09-07 | 2024-12-06 |  | 3975000 |  |  | 90 | 138 | n/a | 8.6 | (1) 959.6 ACSS/TW "SUWANNEE" | Steel H-frame & Steel Pole | 100 | 8.6 | n/a | n/a | 25.101 (C)(5)(B)
1029239 | Mag Mer - Luling TL Addition (T701) [Lockhart-Luling 69-kV TL Overhaul - 1027401] | Caldwell | Perform an overhaul on the 15.8 mile T157/T701 Lockhart - Luling 69-kV transmission line. | 2024-07-01 | 2025-06-20 | 2025-06-27 |  | 21038000 |  |  | 40 | 69 | n/a | 7.64 | (1) 959.6 ACSS/TW "SUWANNEE" | Steel H-frame & Steel Pole | 100 | 7.64 | n/a | n/a | 25.101 (C)(5)(B)
1028022 | Lockhart - Mag Mer TL Addition (T157) [Lockhart-Luling 69-kV TL Overhaul - 1027401] | Caldwell | Perform an overhaul on the 15.8 mile T157/T701 Lockhart - Luling 69-kV transmission line. | 2024-05-20 | 2024-12-03 | 2024-12-03 |  | 16770000 |  |  | 100 | 69 | n/a | 8.2 | (1) 959.6 ACSS/TW "SUWANNEE" | Steel H-frame & Steel Pole | 100 | 8.2 | n/a | n/a | 25.101 (C)(5)(B)
1029222 | Plum Substation Upgrade [shoo-fly outside of the substa. property - 1029125] | Fayette | Increase the reliability of equipment at Plum Substation | 2024-12-02 | 2025-05-15 |  |  | 7391010 | 4733898.06 | -36 | 10 | n/a | 138 | 0.09 | (1) 795 ACSR "DRAKE" | Wood Pole | n/a | n/a | 100 (temp.) | 0.09 (temp.) | 25.101 (C)(5)(A) | This is a temporary transmission line (shoo-fly) to be constructed adjacent to the Plum Substa.
1022921 | Mont-Pilot Grove TL Addition (T140) [Mont-Pilot Grove TL Overhaul - 1024847] | Lavaca | LCRA TSC will perform an overhaul of T593 Hallettsville – Mont to increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. | 2024-08-12 | 2025-01-27 |  |  | 14415000 |  |  | 80 | 138 | n/a | 7.85 | (1) 959.6 ACSS/TW-HS "SUWANNEE" | Steel Pole | 80-100 | 7.85 | n/a | n/a | 25.101 (C)(5)(B)
1027035 | Leon Switch-Putnam TL Addition (T727) [Leon Switch-Putnam TL OH-1026916] | Eastland | LCRA TSC will perform an overhaul on the 9.1-mile Leon Switch-Putnam (T727) 138-kV T-Line. This project will increase reliability of the structures and conductor by ensuring that the T-Line meets or exceeds current NESC & LCRA TSC design standards. | 2024-09-02 | 2024-12-26 |  |  | 16571000 |  |  | 5 | 138 | n/a | 8.95 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole | 80-100 | 8.95 | n/a | n/a | 25.101 (C)(5)(B)
1029516 | Piney Creek-Winchester TL Addition (T186) [Piney Creek - Winchester Fiber Upgrade - 1029343] | Fayette | Upgrade existing 48-count OPGW to 144-count OPGW on Piney Creek - Winchester (T186) line. Additionally, structure replacement associated with this OPGW upgrade is not within the scope of this project. | 2024-07-08 | 2024-10-31 | 2024-08-23 |  | 1813000 |  |  | 100 | 138 | n/a | 1.59 | (1) 1433 ACSS/TW "MERRIMACK" | Steel Poles & Concrete Poles | 85 | 1.59 | n/a | n/a | 25.101 (C)(5)(B)
1029130 | Sim Gideon - Swiftex TL Addition (T608) [Sim Gideon - Swiftex TL Upgrade - 1029104] | Bastrop | LCRA TSC will upgrade T608 Sim Gideon – Swiftex 138kV transmission line to achieve a higher operational rating. | 2024-07-10 | 2025-12-31 |  |  | 26742000 |  |  | 50 | 138 | n/a | 9.99 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole | 40/80/100 | 9.99 | 80/100/125 | n/a | 25.101 (C)(5)(B)
1030011 | Sim Gideon - Swiftex TL Addition (T172) [Sim Gideon - Swiftex TL Upgrade - 1029104] | Bastrop | LCRA TSC will upgrade T608 Sim Gideon – Swiftex 138kV transmission line to achieve a higher operational rating. | 2024-07-10 | 2024-12-06 | 2024-12-06 |  | 1109000 |  |  | 100 | 138 | n/a | 4.15 | (1) 959.6 ACSS "SUWANNEE" & (1) 795 ACSR/GA2 "DRAKE" | Steel Pole / Lattice | 80 | 4.15 | n/a | n/a | 25.101 (C)(5)(B)
1030013 | Sim Gideon - Swiftex TL Addition (T231) [Sim Gideon - Swiftex TL Upgrade - 1029104] | Bastrop, Travis | LCRA TSC will upgrade T608 Sim Gideon – Swiftex 138kV transmission line to achieve a higher operational rating. | 2024-07-10 | 2024-12-06 | 2024-12-06 |  | 895000 |  |  | 100 | 138 | n/a | 14.66 | (1) 959.6 ACSS "SUWANNEE" & (1) 795 ACSR/GA2 "DRAKE" | Steel Pole / Lattice | 80 | 14.66 | n/a | n/a | 25.101 (C)(5)(B)
1029648 | Elgin - Sim Gideon TL Addition (T260) [Elgin Switch Substation Upgrade - 1025307] | Bastrop, Williamson | Support the interconnection of solar generation at a new Oncor switching station by re-terminating existing transmission lines. | 2024-11-04 |  |  |  | 424000 |  |  | 5 | 138 | n/a | 2.79 | (1) 795 ACSR/GA2 "DRAKE" | Lattice / Wood H-Frames / Concrete Poles | 100 | 2.79 | n/a | n/a | 25.101 (C)(5)(B)
1029688 | Kimbro - Elgin Gideon TL Addition (T668) [Elgin Switch Substation Upgrade - 1025307] | Bastrop, Williamson, Travis | Support the interconnection of solar generation at a new Oncor switching station by re-terminating existing transmission lines. | 2025-01-17 |  |  |  | 99000 |  |  | 5 | 138 | n/a | 6.01 | (1) 1433.6 ACSS/TW "MERRIMACK" | Wood H-Frames | 100 | 6.01 | n/a | n/a | 25.101 (C)(5)(B)
1029264 | T749 Thompsonville TL Addition [Switching Structure FY23 SysUpg - 1026926] | Gonzales | Improve safety, reliability, and wildlife mitigation on transmission line switches at Thompsonville substation by replacing 3-way GOAB switches. | 2024-07-08 |  |  |  | 1169000 |  |  | 0 | 69 | n/a | 8.37 | (1) 959.6 ACSS "SUWANNEE" & (1) 795 ACSR/GA2 "DRAKE" | Steel Pole | 100 | 8.37 | n/a | n/a | 25.101 (C)(5)(B)
1030005 | Redwood - San Marcos TL Addition (T200) [Redwood-San Marcos T200 TL Upgrade - 1029878] | Hays | Upgrade T200 Redwood - San Marcos 138-kV transmission line to obtain a higher operational rating. | 2024-10-07 |  |  |  | 2483462 |  |  | 20 | 138 | n/a | 2.54 | (2) 959.6 ACSS "SUWANNEE" | Steel pole, Steel H-Frames | 100 | 2.54 | n/a | n/a | 25.101 (C)(5)(B)
1030555 | San Marcos - Kyle TL Addition (T322) [Redwood-San Marcos T200 TL Upgrade - 1029878] | Hays | Upgrade T200 Redwood - San Marcos 138-kV transmission line to obtain a higher operational rating. | 2024-10-07 |  |  |  | 7000 |  |  | 60 | 138 | n/a | 3.46 | (2) 795 ACSR/GA2 "DRAKE" | Steel pole | 100 | 3.46 | n/a | n/a | 25.101 (C)(5)(B)
1030136 | San Marcos - Canyon TL Addition (T273) [San Marcos - Strahan Transmission Line Upgrade - 1029609] | Hays | Upgrade T230 San Marcos - Strahan 138-kV transmission line to achieve a higher operational rating. | 2024-10-07 |  |  |  | 1135000 |  |  | 60 | 138 | 138 | 2.78 | (2) 959.6 ACSS "SUWANNEE" | Steel Poles | 100 | 2.78 | n/a | n/a | 25.101 (C)(5)(B)
1029730 | San Marcos - Strahan TL Addition (T230) [San Marcos - Strahan Transmission Line Upgrade - 1029609] | Hays | Upgrade T230 San Marcos - Strahan 138-kV transmission line to achieve a higher operational rating. | 2024-10-07 |  |  |  | 9051000 |  |  | 20 | 138 | 138 | 1.25 | (1) 1433.6 ACSS/TW "MERRIMACK" | Steel Poles | 100 | 1.25 | n/a | n/a | 25.101 (C)(5)(B)
1025504 | Marble Falls - Granite Mtn. TL Addition (T195) [Lakeway - Marble Falls TL Storm Hardening - 1024594] | Burnet | Increase the reliability of transmission facilities on the T497 Lakeway – Marble Falls 23-mile 138-kV and T458 Bee Creek – Paleface 8.5-mile 138-kV transmission line. | 2024-08-06 |  |  |  | 4118000 |  |  | 0 | 138 | n/a | 4.08 | (1) 795 ACSR/GA2 "DRAKE" | Lattice Tower & Steel Pole | 100 | 4.08 | n/a | n/a | 25.101 (C)(5)(B)
1025503 | Paleface - Starcke (T196) TL Addition[Lakeway - Marble Falls TL Storm Hardening - 1024594] | Burnet, Travis | Increase the reliability of transmission facilities on the T497 Lakeway – Marble Falls 23-mile 138-kV and T458 Bee Creek – Paleface 8.5-mile 138-kV transmission line. | 2024-10-04 |  |  |  | 34234000 |  |  | 0 | 138 | n/a | 12.57 | (1) 959.6 ACSS "SUWANNEE" | Steel Pole | 100 | 12.57 | n/a | n/a | 25.101 (C)(5)(B)
1022930 | Bellville S - Glidden (T113) TL Addition [Columbus Area Phase II - Transmission Line Relocation - 1022796] | Colorado | Relocate structures on T113 in the vicinity of TXDOT ROW in the Columbus area. | 2024-10-14 |  |  |  | 4419000 |  |  | 0 | 69 | n/a | 31.24 | (1) 795 ACSR/GA2 "DRAKE" | Steel Pole, Concrete Pole, Steel Lattice, Steel H-Frame, Concrete H-Frame | 100 | 31.24 | n/a | n/a | 25.101 (C)(5)(F) | Portion of line to be relocated is approx. 3,000 ft.
1031478 | Beback - Zorn TL Add (T201) SH [McCarty Lane East - Zorn Transmission Line Storm Hardening - 1028809] | Hays, Guadalupe | Perform storm hardening and replace conductor with bundled-Suwannee. Replacement structures should be 138-kV double-circuit bundled-Suwannee capable. Install dual (2) 72-count OPGW. | 2024-09-01 |  |  |  | 1445000 |  |  | 0 | 138 | n/a | 2.09 | (2) 959.6 ACSS "SUWANNEE" | Steel H-Frame, Steel Pole | 100 | 2.09 | n/a | n/a | 25.101 (C)(5)(B)
1028999 | McCarty Ln - Zorn TL Add (T202) SH [McCarty Lane East - Zorn Transmission Line Storm Hardening - 1028809] | Hays, Guadalupe | Perform storm hardening and replace conductor with bundled-Suwannee. Replacement structures should be 138-kV double-circuit bundled-Suwannee capable. Install dual (2) 72-count OPGW. | 2024-09-01 |  |  |  | 14709000 |  |  | 0 | 138 | n/a | 4.16 | (2) 959.6 ACSS "SUWANNEE" | Steel H-Frame, Steel Pole | 100 | 4.16 | n/a | n/a | 25.101 (C)(5)(B)
1031460 | McCarty Ln-BEBACK (T201) TL Add [McCarty Lane East - Zorn Transmission Line Storm Hardening - 1028809] | Hays | Perform storm hardening and replace conductor with bundled-Suwannee. Replacement structures should be 138-kV double-circuit bundled-Suwannee capable. Install dual (2) 72-count OPGW. | 2024-09-01 |  |  |  | 1577000 |  |  | 0 | 138 | n/a | 2.36 | (2) 959.6 ACSS "SUWANNEE" | Steel H-Frame, Steel Pole | 100 | 2.36 | n/a | n/a | 25.101 (C)(5)(B)
1025194 | Pilot Grove - Yoakum Gartner Rd TL Addition (T614) - [Pilot Grove - Yoakum Gartner Road TL Overhaul - 1024852] | Lavaca, De Witt | Perform an overhaul of T614 Pilot Grove – Yoakum Gartner Road structure #8/2 to increase reliability of the structures and conductor by ensuring that the transmission line meets or exceeds current NESC and LCRA TSC design standards. | 2025-01-13 |  |  |  | 12673000 |  |  | 20 | 138 | n/a | 7.83 | (1) 959.6 ACSS/TW-HS "SUWANNEE" | Steel Pole | 100 | 7.83 | n/a | n/a | 25.101 (C)(5)(B)
1028989 | Magnolia - Magnolia TL Addition Tap [Magnolia - Magnolia Tap Fiber Addition - 1028808] | Karnes | Increase the reliability and capability of the fiber network by adding 5.7 miles of Optical Grounding Wire (OPGW) at T630 between Magnolia AEP Substation and Magnolia Tap. | 2025-01-13 |  |  |  | 3135000 |  |  | 100 | 138 | n/a | 5.67 | (1) 795 ACSR "DRAKE" | Concrete Pole | 100 | 5.67 | n/a | n/a | 25.101 (C)(5)(B)
1018772 | Twelvemile-Big SampsnWnd TL Addition [Twelvemile Sub Addition - 1018747] | Crockett | Provide a transmission point of interconnection for a wind resource at a new 345-kV Twelvemile Substation between Noelke and Cedar Canyon substations. | 2024-10-09 |  |  |  | 796005 |  |  | 0 | n/a | 345 | 0.07 | (2) 959 ACSS/TW SUWANNEE | Steel Pole | 55 | 0.07 | n/a | n/a | 25.101 (C)(5)(B)
1030638 | Twelvemile-Cedar Canyon (T21485) TL Addition [Twelvemile Sub Addition - 1018747] | Crockett | Provide a transmission point of interconnection for a wind resource at a new 345-kV Twelvemile Substation between Noelke and Cedar Canyon substations. | 2024-09-16 |  |  |  | 327500 |  |  | 0 | 345 | n/a | 0.08 | (2) 959 ACSS/TW SUWANNEE | Steel Pole | 130 | 0.08 | n/a | n/a | 25.101 (C)(5)(B)
1030639 | Twelvemile-Cedar Canyon (T21511) TL Addition [Twelvemile Sub Addition - 1018747] | Crockett | Provide a transmission point of interconnection for a wind resource at a new 345-kV Twelvemile Substation between Noelke and Cedar Canyon substations. | 2024-09-16 |  |  |  | 320000 |  |  | 0 | 345 | n/a | 0.07 | (2) 959 ACSS/TW SUWANNEE | Steel Pole | 130 | 0.07 | n/a | n/a | 25.101 (C)(5)(B)
1030640 | Twelvemile-Noelke (T21522) TL Addition [Twelvemile Sub Addition - 1018747] | Crockett | Provide a transmission point of interconnection for a wind resource at a new 345-kV Twelvemile Substation between Noelke and Cedar Canyon substations. | 2024-09-16 |  |  |  | 327500 |  |  | 0 | n/a | 345 | 0.08 | (2) 959 ACSS/TW SUWANNEE | Steel Pole | 130 | 0.08 | n/a | n/a | 25.101 (C)(5)(B)
1030641 | Twelvemile-Noelke (T215223) TL Addition [Twelvemile Sub Addition - 1018747] | Crockett | Provide a transmission point of interconnection for a wind resource at a new 345-kV Twelvemile Substation between Noelke and Cedar Canyon substations. | 2024-09-16 |  |  |  | 334000 |  |  | 0 | n/a | 345 | 0.07 | (2) 959 ACSS/TW SUWANNEE | Steel Pole | 130 | 0.07 | n/a | n/a | 25.101 (C)(5)(B)
1030176 | Rosita Creek - Sunglow (T627) TL Addition Upgrade [Sunglow Substation Addition - 1029389] | Maverick | Cut-in T627 into the new the Sunglow Substation to be built by Recurrent Energy. | 2024-11-11 |  |  |  | 133600 |  |  | 20 | 138 | n/a | 0.2 | (1) 795 ACSR "DRAKE" | Steel Poles | 100 | 0.2 | n/a | n/a | 25.101 (C)(5)(B)
1031008 | Sun Glow - Fort Duncan BESS (T785) TL Addition [Sunglow Substation Addition - 1029389] | Maverick | Cut-in T785 into the new Sunglow Substation to be built by Recurrent Energy. | 2024-11-11 |  |  |  | 990000 |  |  | 20 | 138 | n/a | 0.12 | (1) 959.6 ACSS "SUWANNEE" | Steel Poles | 100 | 0.12 | n/a | n/a | 25.101 (C)(5)(B)
1031007 | Sun Glow - Escondido (T784) TL Addition [Sunglow Substation Addition - 1029389] | Maverick | Cut-in T784 into the new Sunglow Substation to be built by Recurrent Energy. | 2024-11-11 |  |  |  | 51000 |  |  | 20 | 138 | n/a | 5.94 | (1) 795 ACSR "DRAKE" | Steel Poles | 100 | 5.94 | n/a | n/a | 25.101 (C)(5)(B)
1031687 | T709 Concho Restoration TL Add [Concho County TL Restoration - 1031845] | Concho | T709 Storm Restoration (emergency project) | 2024-05-03 |  |  |  | 6260000 | 5069242.23 | -19 | 100 | 345 | n/a | 42.02 (entire length) | (2) 1590 ACSR FALCON (2) 1929 ACSS/TW CUMBERLAND | Steel Lattice, Steel Pole | 160 | 42.02 | n/a | n/a | 25.101 (C)(3) | Emergency repair of storm damaged transmission line
1031848 | T710 Concho County Restoration [Concho County TL Restoration - 1031845] | Concho | T710 Storm Restoration (emergency project) | 2024-05-03 |  |  |  | 5183000 | 6366017.61 | 22.8 | 100 | 345 | n/a | 42.02 (entire length) | (2) 1590 ACSR FALCON (2) 1929 ACSS/TW CUMBERLAND | Steel Lattice, Steel Pole | 160 | 42.02 | n/a | n/a | 25.101 (C)(3) | Emergency repair of storm damaged transmission line
1030786 | Hornsby Pwr Trnsfrmr Sub Add [Hornsby Power Transformer Add - 1030772] | Travis | Increase the transformation capacity at Hornsby Substation by adding a new power transformer with two new A-frame structures. | 2024-09-05 |  |  |  | 13261000 |  |  | 0 | 345 | n/a | 0.06 | (2) 959 ACSS/TW SUWANNEE | Steel Poles | 120 | 0.06 | n/a | n/a | 25.101 (C)(5)(B)
1031502 | T510 Zorn-Limmer TL Add [Limmer Substation Addition - 1028231] | Guadalupe, Caldwell, Hays, Travis, Williamson | This project will construct the new Limmer Substation. Limmer Substation will cut-in T510 Hutto to Zorn near Str 413 and will be the 345-kV POI for the new Oncor Hutto East Substation | 2025-01-06 |  |  |  | 4314000 |  |  | 5 | 345 | n/a | 71.26 | (2) 959 ACSS/TW SUWANNEE | Steel Pole and Lattice | 120 | 71.26 | n/a | n/a | 25.101 (C)(5)(A)
1030768 | Gilleland Creek-Hutto OPGW Add [Limmer Substation Addition - 1028231] | Travis, Williamson | This project will construct the new Limmer Substation. Limmer Substation will cut-in T510 Hutto to Zorn near Str 413 and will be the 345-kV POI for the new Oncor Hutto East Substation | 2025-01-06 |  |  |  | 5153000 |  |  | 5 | 345 | n/a | 10.8 | (2) 959 ACSS/TW SUWANNEE | Steel Pole and Lattice | 120' | 10.8 | n/a | n/a | 25.101 (C)(5)(B)
1031505 | T770 Limmer-Hutto TL Add [Limmer Substation Addition - 1028231] | Williamson | This project will construct the new Limmer Substation. Limmer Substation will cut-in T510 Hutto to Zorn near Str 413 and will be the 345-kV POI for the new Oncor Hutto East Substation | 2025-01-06 |  |  |  | 1902000 |  |  | 5 | 345 | n/a | 3.48 | (2) 959 ACSS/TW SUWANNEE | Steel Pole and Lattice | 120 | 3.37 | n/a | 0.11 | 25.101 (C)(5)(A)
1031506 | T21516 Limmer-Teal Add (Oncor) [Limmer Substation Addition - 1028231] | Williamson | This project will construct the new Limmer Substation. Limmer Substation will cut-in T510 Hutto to Zorn near Str 413 and will be the 345-kV POI for the new Oncor Hutto East Substation | 2025-01-06 |  |  |  | 142000 |  |  | 0 | n/a | 345 | 0.1 | (2) 959 ACSS/TW SUWANNEE | Steel Lattice | n/a | n/a | 100 | 0.1 | 25.101 (C)(5)(A)
1031507 | T21517 Limmer-Teal Add (Oncor) [Limmer Substation Addition - 1028231] | Williamson | This project will construct the new Limmer Substation. Limmer Substation will cut-in T510 Hutto to Zorn near Str 413 and will be the 345-kV POI for the new Oncor Hutto East Substation | 2025-01-06 |  |  |  | 198000 |  |  | 0 | n/a | 345 | 0.1 | (2) 959 ACSS/TW SUWANNEE | Steel Lattice | n/a | n/a | 100 | 0.1 | 25.101 (C)(5)(A)
1030757 | Elgin SW-Brushy Crk T768 TL Add [Elgin Switch Sub Upgrade 1025307] | Williamson | Oncor will construct a new 138-kV station known as Brushy Creek Switch which will be sited directly adjacent to Elgin Switch and will require the re-termination or relocation of T668 Elgin Switch - Kimbro and T260 Butler - Elgin Switch. | 2024-10-30 |  |  |  | 8000 |  |  | 5 | n/a | 138 | 0.07 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole | n/a | n/a | 100 | 0.07 | 25.101 (C)(5)(A)
1031346 | T510 John Dumas-Limmer TL Add [John Dumas Circuit Breaker Addition – 1031012] | Bastrop, Caldwell, Guadalupe, Travis, Williamson | LCRA TSC will install the transmission interconnection facilities including the install of new 345kV line terminal equipment at the John Dumas Substation. The install of new 345-kV equipment for the cut-in of T510, and (2) 345kV POI Structures. | 2025-02-01 |  |  |  | 1383000 |  |  | 1 | 345 | n/a | 57.43 | (2) 959.6 ACSS "SUWANNEE" | Steel Lattice & Steel Pole | 120 | 57.43 | n/a | n/a | 25.101 (C)(5)(A)
1031348 | T511ClrSprings-JohnDumas TLAdd [John Dumas Circuit Breaker Addition – 1031012] | Bastrop, Caldwell, Comal, Guadalupe, Travis | LCRA TSC will install the transmission interconnection facilities including the install of new 345kV line terminal equipment at the John Dumas Substation. The install of new 345-kV equipment for the cut-in of T510, and (2) 345kV POI Structures. | 2025-02-01 |  |  |  | 964000 |  |  | 1 | 345 | n/a | 24.83 | (2) 959.6 ACSS "SUWANNEE" | Steel Lattice & Steel Pole | 120 | 24.83 | n/a | n/a | 25.101 (C)(5)(A)
1031350 | T519 RbrtBrwnJr-Clr Frk TL Add [John Dumas Circuit Breaker Addition – 1031012] | Caldwell | LCRA TSC will install the transmission interconnection facilities including the install of new 345kV line terminal equipment at the John Dumas Substation. The install of new 345-kV equipment for the cut-in of T510, and (2) 345kV POI Structures. | 2025-02-01 |  |  |  | 1396000 |  |  | 1 | 138 | n/a | 8.75 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole, Steel 3-Pole & Steel H-Frame | 80 | 8.75 | n/a | n/a | 25.101 (C)(5)(A)
1031352 | T791 Zorn-John Dumas TL Add [John Dumas Circuit Breaker Addition – 1031012] | Caldwell | LCRA TSC will install the transmission interconnection facilities including the install of new 345kV line terminal equipment at the John Dumas Substation. The install of new 345-kV equipment for the cut-in of T510, and (2) 345kV POI Structures. | 2025-02-01 |  |  |  | 600000 |  |  | 1 | n/a | 345 | 14.48 | (2) 959.6 ACSS "SUWANNEE" | Steel Lattice & Steel Pole | 120 | 14.48 | n/a | n/a | 25.101 (C)(5)(A)
1031353 | T792JohnDumas-Generator TL Add [John Dumas Circuit Breaker Addition – 1031012] | Caldwell | LCRA TSC will install the transmission interconnection facilities including the install of new 345kV line terminal equipment at the John Dumas Substation. The install of new 345-kV equipment for the cut-in of T510, and (2) 345kV POI Structures. | 2025-02-01 |  |  |  | 603000 |  |  | 1 | n/a | 345 | 0.29 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole | n/a | n/a | 120 | 0.29 | 25.101 (C)(5)(A)
1031354 | T793JohnDumas-Generator TL Add [John Dumas Circuit Breaker Addition – 1031012] | Caldwell | LCRA TSC will install the transmission interconnection facilities including the install of new 345kV line terminal equipment at the John Dumas Substation. The install of new 345-kV equipment for the cut-in of T510, and (2) 345kV POI Structures. | 2025-02-01 |  |  |  | 613000 |  |  | 1 | n/a | 345 | 0.24 | (2) 959.6 ACSS "SUWANNEE" | Steel Pole | n/a | n/a | 120 | 0.24 | 25.101 (C)(5)(A)
1030004 | Lakeway-Lakeway Tap T180 TL Add [Lakeway - Marble Falls TL SH - 1024594] | Travis | Lakeway-Marble Falls Transmission Line Storm Hardening will upgrade the OPGW on T497 to 144-count fiber | 2025-02-01 |  |  |  | 520000 |  |  | 0 | 138 | n/a | 5.03 | (1) 959.6 ACSS/TW/MA3 HS "SUWANNEE" (1) 795 ACSR/GA2 "DRAKE" | Steel Lattice, Steel Pole & Steel H-Frame | 100 | 5.03 | n/a | n/a | 25.101 (C)(5)(B)
1032443 | Upton T783 TL Add [Upton Power Transformer Add - 1029737] | Upton | LCRA TSC will facilitate the install of one 47 MVA power transformer at Upton Substation (until decommissioning) by providing a POI to Oncor, extending the high side bay, and adding two high-side circuit breakers. | 2025-04-03 |  |  |  | 386000 |  |  | 0 | 138 | n/a | 14.7 | (1) 1233.6 ACSS "YUKON" | Steel/Concrete monopoles | 100 | 14.7 | n/a | n/a | 25.101 (C)(5)(A)
1030574 | Hill-Top La Cima Ph. 1 (T375) [La Cima Substation Addition – 1029607] | Hays | Pedernales Electric Cooperative will add a new substation to serve new customer load. The substation will be served from LCRA TSC owned 138-kV transmission line T375 Hilltop to Ranch Road 12. | 2025-10-06 |  |  |  | 622000 |  |  | 0 | 138 | n/a | 3.85 | (1) 1433.6 ACSS "MERRIMACK" | Steel Pole | 85 | 3.85 | n/a | n/a | 25.101 (C)(5)(A)
1030672 | La Cima - RR 12 Ph. 1 (T778) [La Cima Substation Addition – 1029607] | Hays | Pedernales Electric Cooperative will add a new substation to serve new customer load. The substation will be served from LCRA TSC owned 138-kV transmission line T375 Hilltop to Ranch Road 12. | 2025-10-06 |  |  |  | 622000 |  |  | 0 | 138 | n/a | 0.18 | (1) 1433.6 ACSS "MERRIMACK" | Steel Pole | 85 | 0.18 | n/a | n/a | 25.101 (C)(5)(A)
1032257 | T184 Lockhart-Luling TL Add [Lockhart-San Marcos TL Conversion - 1029608] | Caldwell | The five LCRA TSC-owned transmission lines from Lockhart to San Marcos will be converted to 138-kV (T220 Robert Brown Jr. to San Marcos, T472 Camp Gary to Lockhart, T519 Clear Fork to Robert Brown Jr., and T601 Clear Fork to Lockhart). | 2025-05-08 |  |  |  | 75000 |  |  | 0 | 138 | n/a | 16.78 | (1) 959.6 SUWANNEE ACSS/TW | Steel Pole | 100 | 16.78 | n/a | n/a | 25.101 (C)(5)(B)
1032259 | T578 Red Rock-Lockhart TL Add [Lockhart-San Marcos TL Conversion - 1029608] | Caldwell, Bastrop | The five LCRA TSC-owned transmission lines from Lockhart to San Marcos will be converted to 138-kV (T220 Robert Brown Jr. to San Marcos, T472 Camp Gary to Lockhart, T519 Clear Fork to Robert Brown Jr., and T601 Clear Fork to Lockhart). | 2025-05-08 |  |  |  | 300000 |  |  | 0 | 138 | n/a | 17.09 | (1) 959.6 SUWANNEE ACSS/TW | Steel Pole | 100 | 17.09 | n/a | n/a | 25.101 (C)(5)(B)
1032260 | T601 Clear Frk-Lockhart TL Add [Lockhart-San Marcos TL Conversion - 1029608] | Caldwell | The five LCRA TSC-owned transmission lines from Lockhart to San Marcos will be converted to 138-kV (T220 Robert Brown Jr. to San Marcos, T472 Camp Gary to Lockhart, T519 Clear Fork to Robert Brown Jr., and T601 Clear Fork to Lockhart). | 2025-05-08 |  |  |  | 300000 |  |  | 0 | 69 | 138 | 3.06 | (2) 959.6 SUWANNEE ACSS/TW | Steel Pole | 80 | 3.06 | n/a | n/a | 25.101 (C)(5)(B)
1030937 | Colorado-Nada T265 TL Add [Avian Protection FY25 - 1030775] | Colorado | Install PLP Spiral Vibration Dampers (diverters) at 15ft intervals on the shield wire spans for T265, 138-kV Colorado – Nada Transmission line between Colorado Substation and STEC tie. | 2025-05-01 |  |  |  | 785000 |  |  | 0 | 138 | n/a | 9.41 | (1) 795 ACSR/GA2 "DRAKE" | Steel Lattice | 100 | 9.41 | n/a | n/a | 25.101 (C)(5)(B)
1032770 | T437 STR108 Add [GAFY25-T437TowerLightUpgCorpus - 1032770] | Nueces | Upgrade the tower lights to the new Lumenserve standard including remote tower light monitoring and latest FAA lighting requirements on T437 structures 108 and 109 | 2025-05-01 |  |  |  | 287000 |  |  | 0 | 138 | n/a | 17.29 | (2) 795 ACSR "DRAKE" | Steel Monopole | 60 | 17.29 | n/a | n/a | 25.101 (C)(5)(B)
1031696 | T795 John Dumas-Euclid TL Add [Euclid Substation Addition - 1030210] | Caldwell | Construct a new 345-kV substation and cut-in T510 Hutto to Zorn near Structure #141. LCRA will install four (4) 345-kV power transformers with a minimum rating of 100 MVA. | 2025-05-16 |  |  |  | 1456000 |  |  | 0 | 345 | n/a | 74.57 | (2) 959.6 SUWANNEE ACSS/TW | Steel Pole and Lattice | 120 | 74.57 | 140 | 26.45 | 25.101 (C)(5)(A)
1032308 | T510 Euclid-Limmer TL Add [Euclid Substation Addition - 1030210] | Caldwell, Guadalupe | Construct a new 345-kV substation and cut-in T510 Hutto to Zorn near Structure #141. LCRA will install four (4) 345-kV power transformers with a minimum rating of 100 MVA. | 2025-05-16 |  |  |  | 3487000 |  |  | 0 | 345 | n/a | 74.57 | (2) 959.6 SUWANNEE ACSS/TW | Steel Pole and Lattice | 120 | 74.57 | 140 | 5.45 | 25.101 (C)(5)(A)
1031697 | T775 John Dumas-Hornsby TL Add [Euclid Substation Addition - 1030210] | Caldwell, Hays, Travis | Construct a new 345-kV substation and cut-in T510 Hutto to Zorn near Structure #141. LCRA will install four (4) 345-kV power transformers with a minimum rating of 100 MVA. | 2025-05-16 |  |  |  | 1193000 |  |  | 0 | 345 | n/a | 57.15 | (2) 959.6 SUWANNEE ACSS/TW | Steel Pole and Lattice | 120 | 57.15 | 140 | 51.45 | 25.101 (C)(5)(A)
1033024 | T486 STR 13_4 [GA FY25-T486 Tower Light Upg - 1033023] | Kerr | Upgrade the tower lights to the new Lumenserve standard which also includes remote tower light monitoring and latest FAA lighting requirements at the following 5 structures to T486 | 2025-04-20 |  |  |  | 472000 |  |  | 0 | 138 | n/a | 4.5 | (1) 795 ACSR "DRAKE" | Steel/Concrete monopoles | 80 | 4.5 | n/a | n/a | 25.101 (C)(5)(B)