## MonthlyReportForm
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
TPSU.20.000019 | Stillman BPUB 138kV Interconnection | Cameron County | Retermination of Waterport and Price Road 138kV lines at Stillman per BPUB's Request | 2021-01-01 |  |  |  | 2200000 |  |  | 90 | 138 | na | 0.08 | 1590 ACSS; Single Conductor | Steel Monopole (2) | na | na | na | na | 25.101 (c)(5)(A), 25.101 (c)(5)(B), 25.101 (c)(5)(E )
TPSU.21.000016 | Kingfisher to Palmito Second Circuit Additon | Cameron County | Install a second 345-kV circuit on the Sharyland's portion of the existing 345-kV transmission line that runs from the new Kingfisher station to Sharyland's Palmito station | 2023-02-28 | 2024-05-15 | 2024-05-15 |  | 62417829 | 65019858.73 | 4.169% | 100 | 345 | 345 | 47 | 954 ACSR; Bundled | Steel Monopole | 150 | 47 | na | na | 41606
TPSU.21.000017 | La Palma to Kingfisher 345-kV Transmission Line | Cameron County | Build half of the 345-kV transmission line between Sharyland's new 345-kV Kingsfisher switchyard and AEP's existing 345-kV La Palma station | 2025-06-18 |  |  | 16217000 |  |  |  | 7 | 0 | 345 | 2.5 | 2-954 ACSR/AW | Steel Monopole | na | na | 150 | 2.5 | 53727
TPSU.21.000018 | Kingfisher 345-kV Switchyard | Cameron County | Build a new Kingfisher 345-kV switchyard | 2025-05-26 |  |  | 43709000 |  |  |  | 3 | 0 | 345 | 0 | na | na | na | na | na | na | 53727
TPSU.23.000009 | Stillman SSVT Addition | Cameron County | Install three single phase 100kVA 138kV-120/240V SSVTs and one 3000A motor operated vertical break switch and associated equipment at Stillman Substation | 2024-09-18 |  |  | 1600000 |  |  |  | 0 | 138 | na | 0 | na | na | na | na | na | na | 25.101 (c)(5)(A) 25.101 (c)(5)(B)

## Cost Analysis - TPSU.15.006050 (hidden)
Project No.: | TPSU.15.006050
Project Name: | Bay Additions for Windmill Phase 1 Upgrade
PUC Docket No.: | 45622
2016-10-13
| Estimated Cost Included in Final Order | Estimated Cost at Construction Start | Final Cost
Substation
ROW & Land Acquisition | 0 | 0 | 0
Route Development / CCN Acquisition | 0 | 0 | 0
Engineering & Design - Utility | 0 | 0 | 0
Engineering & Design - Contract | 201162.33 | 201162.33 | 236633.43
Material & Equipment Procurement | 1485537.96 | 1485537.96 | 1022384.35
Construction of Facilities - Utility | 25612.72 | 25612.72 | 0
Construction of Facilities - Contract | 1023655.18 | 1023655.18 | 1113633.66
Other | 64031.81 | 64031.81 | 84879.76
TOTAL | 2800000 | 2800000 | 2457531.2
| 0 | 0 | 0
| 2800000 | 2800000 | 2457531.2
Cost Variance |  | 0% | -12.23%
Cost Analysis - Material costs were lower than projected which resulted in the -12% variance between the project estimate and the final project cost.