## MonthlyReportForm-AEPTX Central
Utility's Project Number | Project Name | Location (City/County) | Description | Estimated (or Actual) Start Date | Finish Date (Construction Complete) | Date Energized (If Applicable) | Initial Estimated Project Cost ($) | Final Estimated Project Cost ($) | Final Actual Project Cost ($) | % Variance | Percent Complete | Existing Voltage (kV) | Upgraded or New Voltage (kV) | Circuit Length (Miles) | Conductor Type & Size & Bundling | Structure Type(s) | Existing ROW Width (Feet) | Existing ROW Length (Miles) | New ROW Width (Feet) | New ROW Length (Miles) | Rule Section or PUC Control Number | Comments
TA-2021057 T10521465 (A21057008) | Abilene Northwest - Fort Phantom Plant 138-kV T-Line | Taylor,Jones | Replace eight (8) transmission line structures along the Abilene Northwest to Fort Phantom Plant 138-kV transmission line for HB-4150 Mitigation. | 2025-05-05 | 2025-05-15 |  |  | 570345.53 |  |  | 0 | 138 |  |  | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
TA-2021057 T10528704 (A21057022) | Fort Phantom – East Abilene 138-kV T-Line | Taylor | Replace six (6) transmission line structures along the Fort Phantom to East Abilene 138-kV transmission line for HB-4150 Mitigation. | 2025-05-18 | 2025-06-05 |  |  | 330240.22 |  |  | 0 | 138 |  |  | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed
TA-2021057 T10528703 (A21057021) | Fort Phantom - Paint Creek 138-kV T-line | Jones/Shackelford | Replace seventeen (17) transmission line structure along the Fort Phantom - Paint Creek 138-kV transmission line for HB-4150 Mitigation. | 2025-06-01 | 2025-12-31 |  |  | 1445247.3 |  |  | 0 | 138 |  |  | 795 KCM ACSS "Drake" | Steel Mono Pole |  |  |  |  | 16 TAC 25.101 (c)(5)(B) | Landowners Noticed