## Summary by Event
Resiliency Program Listing
RM # | Programs | Witness | 2026 | 2027 | 2028 | Total (2026-2028) | Dist % | Dist $ (2026-2028) | Dist $ (2026-2030) | Capital | O&M | # Assets in 3 yrs | Type | % Complete | Comments
| Extreme Wind |  | 981.2 | 1461.5 | 1570 | 4012.7 |  | 1998.135 | #REF! | 3864.61 | 148.09
RM-1 | Distribution Circuit Resiliency | Tumlinson | 165.2 | 171.4 | 176.8 | 513.4 | 100% | 513.4 | #REF! | 513.4 | 0 | 25000 | poles | on-going | $18K per fiberglass pole, based on # wood poles w/ fall in risk, ongoing due to VM risk changing
RM-2 | Strategic Undergrounding | Pryor | 116 | 266 | 478 | 860 | 100% | 860 | #REF! | 860 | 0 | 111.2143 | miles | 9.39% | $200M for 7 hospitals, $60M for 75 FW crossings ($20M/yr), $600M for high fall-in risk locations-ongoing due to VM risks, UG all 1st & 2nd sections
RM-3 | Restoration IGSD | Tumlinson | 34.9 | 35.9 | 37 | 107.8 | 100% | 107.8 | #REF! | 107.31 | 0.49 | 900 | devices | 53.73% | includes IT costs, ~$120K each, % complete based on # of 1675 OH circuits w/ at least 1 IGSD for cut & clear
RM-4 | Distribution Pole Replacement/Bracing | Tumlinson | 81.2 | 83.8 | 86.6 | 251.6 | 100% | 251.6 | #REF! | 251.6 | 0 | 30000 | poles | on-going | based on results of historical inspections, $18K fiberglass (3%), $10K wood (73%), $2K brace (23%)
RM-5 | Vegetation Management | Pryor | 54.5 | 45.2 | 46.4 | 146.1 | 100% | 146.1 | #REF! | 0 | 146.1 | 11700 | miles | on-going | incremental miles and spend only, does not include base VM which is 50% of 23,400 mi of OH, avg $/mi depends on voltage
RM-6 | Transmission System Hardening | Mercado | 285.35 | 649.5 | 533.15 | 1468 | 5% | 73.4 | #REF! | 1467.25 | 0.75 | 1715 | structures | 100%/19% | all energized transmission wood structures hardened by end of 2028. 100% Wood Completion, 19% legacy 345kV tangent double circuit transmission towers (242/1267)
RM-7 | 69kV Conversion Projects | Mercado | 166.75 | 173.1 | 29.45 | 369.3 | 10% | 36.93 | #REF! | 369.3 | 0 | 462 | structures | 93% | completion may extend to 2029, includes Downtown GIS sub. 93% Completion (14/15 Remaining 69kV Circuits)
RM-8 | S90 Tower Replacements | Mercado | 74.8 | 31.6 | 12 | 118.4 | 0% | 0 | #REF! | 118.4 | 0 | 37 | towers | 100% | all S90 towers replaced by end of 2028, ~$3M/tower
RM-9 | Coastal Resiliency Projects
| Location #1 | Mercado | 1.5 | 2.5 | 165.1 | 169.1 | 5% | 8.455 | #REF! | 168.35 | 0.75 | 1 | location | 100% | Requires ERCOT RPG review
| Location #2 | Mercado | 1 | 2.5 | 5.5 | 9 | 5% | 0.45 | #REF! | 9 | 0 | 1 | location | 3% | 3% Completion (9M/359M expected spend), Requires ERCOT RPG review
ERCOT Identified Resiliency Projects (placeholder pending ANL report)
| Programs | Witness | 2026 | 2027 | 2028 | Total (2026-2028) | Dist % | Dist $ (2026-2028) | Dist $ (2026-2030) | Capital | O&M
| Extreme Water |  | 31.6 | 31.7 | 28.3 | 91.6 |  | 76.36 | #REF! | 91.6 | 0
RM-10 | Substation Flood Control | Mercado | 14.6 | 14.6 | 14.6 | 43.8 | 70% | 30.66 | #REF! | 43.8 | 0 | 12 | substations | on-going | includes IT costs, assumes 4/year, based on Neara data + Harvey flooded locations, risk changes so on-going
RM-11 | Control Center Flood Control | Mercado | 3.5 | 3.5 | 0 | 7 | 70% | 4.9 | #REF! | 7 | 0 | 1 | locations | 100% | Backup control center floodwall
RM-12 | MUCAMS | Pryor | 3.5 | 3.6 | 3.7 | 10.8 | 100% | 10.8 | #REF! | 10.8 | 0 | 318 | sites | 64% | Various dedicated UG areas. % completed based on current location counts.
RM-13 | Mobile Substations | Mercado | 10 | 10 | 10 | 30 | 100% | 30 | #REF! | 30 | 0 | 6 | units | on-going | 2/year for 3 years, ongoing due to load, $5M each
| Extreme Temp (Freeze) |  | 14.03 | 21.03 | 21.03 | 56.09 |  | 41.84 | #REF! | 53.49 | 2.6
RM-14 | Anti-Galloping Technologies | Mercado | 5 | 5 | 5 | 15 | 5% | 0.75 | #REF! | 14 | 1 | 25 | circuit miles | on-going | based on galloping events so on-going; $180K/circuit mile + 75 sensors @ $15K each
RM-15 | Loadshed IGSD | Tumlinson | 1.53 | 1.53 | 1.53 | 4.59 | 100% | 4.59 | #REF! | 4.49 | 0.1 | 36 | devices | Annual Review | estimated 12 per year but depends on results of annual review, ~$120K each including IT costs
PP-1 | Microgrid Pilot Program | Tutunjian | 7.5 | 14.5 | 14.5 | 36.5 | 100% | 36.5 | #REF! | 35 | 1.5 | 3-5 | locations | N/A | estimated 3-5 locations at $7M/location (Per location: impact study $100K (94% cap/6% O&M), engineering and design $1M (95%/5%), transfer trip $120K (100%/0%), switches $3M (100%/0%), control system upgrades $2.5M (100%/0%))
| Extreme Temp (Heat) |  | 368.45 | 429.95 | 445.96 | 1244.36 |  | 1214.36 | #REF! | 1207.16 | 37.2
RM-16 | Distribution Capacity Enhancement/Substations | Mercado | 183.2 | 191.2 | 205.2 | 579.6 | 100% | 579.6 | #REF! | 579.6 | 0 | 20 | substations | on-going | DDP projects supporting resiliency, e.g. 12 kV islands, step up/down scenarios, ongoing due to load requests
RM-17 | MUG Reconductor | Pryor | 55 | 95 | 95 | 245 | 100% | 245 | #REF! | 245 | 0 | 21.72 | miles | on-going | Assumes majority under City of Houston streets, 4 miles of feeder main per mile of duct-bank
RM-18 | URD Cable Modernization | Pryor | 41.1 | 42.8 | 44.5 | 128.4 | 100% | 128.4 | #REF! | 128.4 | 0 | 34500 | spans | 100% | accelerate completion from 2030 to end of 2028, target all URD installed before 1985
RM-19 | Contamination Mitigation | Tumlinson | 50 | 50 | 50 | 150 | 80% | 120 | #REF! | 144 | 6 | 20 | circuits | 21% | includes distribution contamination circuits, EPRI sensors, and substation insulator replacement assuming 3-4 coastal substations per year to be completed. % Complete based on total number of southern zone circuits with fall in risk, 97 circuits
RM-20 | Substation Fire Barriers | Mercado | 3 | 3 | 3 | 9 | 100% | 9 | #REF! | 9 | 0 | 36 | firewalls | 38% | 21 substations, 36 firewalls
RM-21 | Digital Substation | Mercado | 9.3 | 11.1 | 11.4 | 31.8 | 100% | 31.8 | #REF! | 31.8 | 0 | 13 | substations | 5.682% | 4-5 per year
RM-22 | Wildfire Advanced Analytics | Easton | 0.3 | 0.3 | 0.3 | 0.9 | 100% | 0.9 | #REF! | 0 | 0.9 | N/A | N/A | on-going | Technosylva O&M
RM-23 | Wildfire Strategic Undergrounding | Pryor | 10 | 20 | 20 | 50 | 100% | 50 | #REF! | 50 | 0 | 7.1429 | miles | on-going | assumes $7M per mile, UG all 1st & 2nd sections in HFRA but risk may change so on-going
RM-24 | Wildfire Vegetation Management | Easton | 10 | 10 | 10 | 30 | 100% | 30 | #REF! | 0 | 30 | 3000 | miles | on-going | O&M only, $10K per mile
RM-25 | Wildfire IGSD | Easton | 6.55 | 6.55 | 6.56 | 19.66 | 100% | 19.66 | #REF! | 19.36 | 0.3 | 150 | devices | on-going | 50 per year, 130 ckts currently but HFRA may change so on-going
| Programs | Witness | 2026 | 2027 | 2028 | Total (2026-2028) | Dist % | Dist $ (2026-2028) | Dist $ (2026-2030) | Capital | O&M
| Physical Attack |  | 12.5 | 12.5 | 12.5 | 37.5 |  | 9.135 | #REF! | 37.4 | 0.1
RM-27 | Substation Security Upgrades | Mercado | 6.5 | 6.5 | 6.5 | 19.5 | 33% | 6.435 | #REF! | 19.4 | 0.1 | 30 | substations | on-going | 10 per year, refreshed every 5 yrs
RM-26 | Substation Physical Security Fencing | Mercado | 6 | 6 | 6 | 18 | 15% | 2.7 | #REF! | 18 | 0 | 21 | substations | 15% | 7 per year
| Technology & Cybersecurity |  | 67.22 | 15.46 | 10.32 | 93 |  | 46.5 | #REF! | 79.55 | 13.45
RM-28 | Spectrum Acquisition | Bahr | 42 | 0 | 0 | 42 | 50% | 21 | #REF! | 42 | 0 | N/A | N/A | 100% | Based on analysis and recommendation by West Monroe; assumes 1.6GHz lease/own
RM-29 | Data Center Modernization | Bahr | 6.62 | 3.76 | 3.52 | 13.9 | 50% | 6.95 | #REF! | 12.65 | 1.25 | N/A | N/A | 90% | CEHE Portion (42%); $5.5M M SCADA Link Redundancy, $2.5M - On-Premise Infrastructure, $1.7M - Data Protection Storage, $1.7M - SAN Fabric Redesign, $0.9M - Active-Active solution, $0.4M Disaster Recovery Toolset. O&M estimate 10%.
RM-30 | Network Security & Vulnerability Management | Ford | 4.9 | 2.3 | 2.3 | 9.5 | 50% | 4.75 | #REF! | 7.5 | 2 | N/A | N/A | on-going | Estimate includes related hardware/software purchases ($7.3M), additional FTEs ($2.1M) and training/certification requirements ($60K)
RM-31 | IT/OT Cybersecurity Monitoring | Ford | 7.7 | 6.4 | 3.5 | 17.6 | 50% | 8.8 | #REF! | 13.4 | 4.2 | N/A | N/A | on-going | Estimate includes related hardware/software purchases ($11.1M), additional FTEs ($6.0M) and training/certification requirements ($500K)
RM-32 | Cloud-based Customer Facing Website Hosting | Bahr | 0 |  |  | 0 | 50% | 0 | #REF! | 0 | 0 | N/A | N/A |  | Estimate includes related hardware/software purchases ($7.3M), additional FTEs ($2.1M) and training/certification requirements ($60K)
RM-33 | MyAccountOnline (Consolidated with Website Above) | Bahr | 0 |  |  | 0 | 50% | 0 | #REF! | 0 | 0 | N/A | N/A |  | Estimate includes related hardware/software purchases ($7.3M), additional FTEs ($2.1M) and training/certification requirements ($60K)
RM-32 | Cloud Security, Product Security & Risk Management | Ford | 6 | 3 | 1 | 10 | 50% | 5 | #REF! | 4 | 6 | N/A | N/A | on-going | Estimate includes related hardware/software purchases ($4.2M), additional FTEs ($5.3M) and training/certification requirements ($500K)
| Security Automations & Orchestration | Christensen | 0 | 0 | 0 | 0 |  | 0 | #REF! | 0 | 0
| Cybersecurity Operations Command Center Upgrade | Christensen | 0 | 0 | 0 | 0 |  | 0 | #REF! | 0 | 0
| Situational Awareness |  | 88.35 | 57.1 | 73.3 | 218.75 |  | 201.975 | #REF! | 209.51 | 9.24
RM-33 | Advanced Aerial Imagery/Digital Twin | Easton | 6.8 | 6.8 | 6.8 | 20.4 | 100% | 20.4 | #REF! | 18.36 | 2.04 | N/A | N/A | on-going | Annual LiDAR and aerial imagery capture, Neara
RM-34 | Weather Stations | Easton | 0.1 | 0.1 | 0.1 | 0.3 | 100% | 0.3 | #REF! | 0 | 0.3 | N/A | N/A | on-going | Capital spend in 2025, ongoing O&M
RM-35 | Wildfire Cameras | Easton | 0.3 | 0.3 | 0.3 | 0.9 | 100% | 0.9 | #REF! | 0 | 0.9 | N/A | N/A | on-going | Capital spend in 2025, ongoing O&M
RM-37 | Backhaul Microwave Communication | Bahr | 5.65 | 3.5 | 3.5 | 12.65 | 50% | 6.325 | #REF! | 12.65 | 0 | 165 | microwave radios | 25% | Estimated capital based on estimated equipment costs and estimated labor that will be completed yearly. The estimate is developed by number of links which includes a radio/antenna on each side of the link. Each radio link is approx. $75k. We plan to implement 75 links in 2026, 45 links in 2027, and 45 links in 2028.
RM-36 | Voice & Mobile Data Radio System | Bahr | 9.5 | 7.1 | 4.3 | 20.9 | 50% | 10.45 | #REF! | 20.9 | 0 | 27 | DMR Tier 3 Sites | 100% | Estimated capital based on RFP response for equipment costs and estimated other labor and work required to implement based on experience with similar implementations. Includes the antennas, console system, handhelds/ portables, vehicle radios, base station radios. This will also include the coverage analysis and optimization.
RM-38 | Emergency Operations Center | Brownell | 52 | 2 | 2 | 56 | 100% | 56 | #REF! | 50 | 6 | 1 | location | 100% | Majority of spend will be in 2025
RM-39 | Hardened Service Centers | Brownell | 14 | 37.3 | 56.3 | 107.6 | 100% | 107.6 |  | 107.6 | 0 | 4 | service centers | 78% | 4 locations; approxiately $26M/each
| Event Response |  | 0 | 0 | 0 | 0 |  | 0 | #REF! | 0 | 0
| Enhance Staging Sites | TBD | 0 | 0 | 0 | 0 | 100% | 0 | #REF! | 0 | 0 |  |  |  | * Money will be spent in 2025 for now*
| TOTAL PROGRAMS |  | 1563.35 | 2029.24 | 2161.41 | 5754 |  | 3588.305 | #REF! | 5543.32 | 210.68
|  |  | Contamination | +$11M/YEAR
|  |  | MUG Recond | +$5m/year
|  |  | strategic | + 6M, 6M, 8M
|  |  | capacity | +1M, 1M, 2M
|  |  | dist rebuild | +$11M,$12M,$12M
Note on D47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Agreed to remove 1/8